## Current Authority
PPIQ BACKLOG v2.24.0 — Industrial Integration authority 16Sep2026
Authority | Current value | As of | Meaning
Functional Design | v4.11.0 | 2026-09-16 | Owner-approved Industrial Integration Contract integrated into Chapters 1–6: stable field/layout identity, Time/Value-change/Trigger-counter policies, continuous acquisition sessions with finite accepted batches, logical Dump Store, source-data lifecycle/capacity truth. Existing closed work remains historical evidence.
Execution Backlog | v2.24.0 | 2026-09-16 | Meaningful authority revision: adds T-268..T-275 and amends affected OPC/design acceptance. No closed task is reopened; expanded industrial-integration scope is separately owned.
Integrated Chapter 3/4 visuals | v4.11.0 target contract; illustrated regeneration pending T-265/T-266 | 2026-09-16 | Functional contract is authoritative now; T-265/T-266 still own derived visual/prototype/illustrated synchronization and do not receive runtime credit.
Release 1 | M2 — approx. one month from owner planning checkpoint | Owner planning basis | No new absolute delivery date.
Release 2 | M3 — 45 days after M2 completion | Owner planning basis | 45 days after M2 completion; prior approved release allocation retained.
Rows and retirements | 187 active; T-105→T-104; T-111→T-110/T-155/T-159 | Adds T-268 through T-275 | Eight new bounded industrial-integration execution owners. No existing task retired or reopened by this design revision.
T-099 closure | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af | Final14Sep terminal transcript inspected15Sep | CLOSED GREEN/COMMITTED; exact transcript corroborated. DefinitionKind known-red remains; not release-wideGREEN.
T-262 evidence | CONTRACT GREEN COMMIT86e1b677; INTEGRATION UNVERIFIED | Evidence from12Sep; reviewed15Sep | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. Later 14-Sep coordination explicitly allocates live definition-store Gate 0 to T-261 Runner 2. Reconcile that integration gate separately; no producer rewrite.
Planning estimates | Existing estimates preserved; T-268..T-275 intentionally unestimated | 2026-09-16 | New scope is not zero hours. Source-level preflight is required before LOW/BASE/HIGH or P80 is accepted; historical OPC estimates are not silently reused for expanded v4.11.0 scope.
Current task table | Backlog!A1:BB188 | 187 task rows | Dependency validation reads the saved v2.24.0 task rows. New tasks are excluded from hour totals until explicitly estimated.
Derived views | Worker Tracks / Dependency Graph / Capability Map / Release Plan / dashboards | v2.24.0 | Formula ranges are extended through Backlog row 188. New task rows are appended to Worker Tracks and Dependency Graph.
Scope of validation | 51 scoped source reviews; all 34 M2-P2 + 17 other changed-estimate tasks | 2026-09-15 | Current implementation inspected from 14-Sep snapshot. 128 task scopes and all ten full session transcripts remain unreviewed/unrecovered. No live Git HEAD, product database or .NET test execution claimed. See Source Summary, Source Review, Source Evidence.
Chapter 2 notice | v4.11.0 Industrial Acquisition Contract integrated | 2026-09-16 | Preserves one J1–J15 journey and DF1–DF15 flow; OPC-UA-first OT boundary, optional native PLC adapters only by separate approved scope.
15Sep detailed review | Source Summary — current source, remaining effort and validation | 2026-09-15 | One workbook only. New Source Review and Source Evidence tabs supplement M2-P2 Review, Task Evidence 15Sep and the preserved session ledger.
Current mutation order | T-099 → T-100 → T-261 → T-245 | Latest owner update /15-Sep-2026 | Supersedes T-099→T-261→T-100; Worker 2 held pending final T-100 SHA.
T-100 stage | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | USER-REPORTED | Not independently rerun or source-verified; no T-100 commit recorded.
T-261 permission | HELD PENDING T-100 COMMIT | Worker 2 | No host mutation/final anchors/migration number. One bounded delta only after SHA.
Latest issued recovery artifact | Resume-ProjectionQuarantineCompletion_1.0.1.ps1 | Not executed/verified here | 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6
T-100 expected closure parent | 4e0f1219ddbac3163bafe7ce510b62520683a77c | EXPECTED, NOT OBSERVED | Verify against Runner-1 handoff/current HEAD. Do not overwrite an actual commit/parent ledger until commit occurs.
Evidence distinction | DB bootstrap/constraint is not live classification | USER-REPORTED | 110/110 SQL and 264 tables reported; harness stopped before live fixtures. Cleanup means certification DB must be rebuilt by recovery runner.
Controlled book | 12 document families / 14 physical files | Owner direction — 2026-09-14 | PPIQ_Definition.md registers the allowed files. The Backlog holds coverage, acceptance, validation and handoffs; no new status/JSON/README/atlas files.

## Backlog
Task Id | Milestone Id | Phase Id | Task Name | Module | Sub-module | Priority | Task Description | Task Validation | Hours | Status | AI Agent Owner | Depends On (IDs only) | Must Precede (IDs only) | Delivery Target | Release Criticality | AI Execution Class | AI Guarded Time P80 (h) | AI Sequence Wave | AI Start / Dependency Gate | File / Subsystem Lock | No-Rework Handoff Ruling | Product Track | Tech-Lead Ruling | Commit String | Commit Date | Primary Capability ID | Primary Capability Name | Secondary Capability IDs | Capability Contribution | Completeness Dimensions Targeted | Capability Requirement Class | Release Scope | Capability Closure Effect | Capability Evidence | Estimate Basis | Design Package | UI Companion Reference | Usable scope estimate (1/0) | Contract-ready predecessors (not completion) | Evidence State | Closure Evidence Basis | Parent Commit | Estimate Status | Usable planning hours | Usable planning P80 h | Source review coverage | Proposed remaining LOW h | Proposed remaining BASE h | Proposed remaining HIGH h | Remaining estimate confidence | Remaining estimate basis | Source locations | Source as-of / evidence boundary
T-086 | M2 | P1 | Freeze the legacy Fleet v2 controlled regression oracle | Testing | Emulated sources | Critical | Freeze and certify the existing Fleet v2 dataset only as a legacy discrete-manufacturing regression oracle with predeclared known answers/negative controls. It is not the canonical product vocabulary, not the generic M2 fixture authority and not the source of customer schema semantics. T-208 owns new generic controlled fixtures, including the continuous-process known-answer pack. | Fleet v2 is immutable and its declared phenomena/negative controls are reproducible. An architecture check proves no generic runtime/Layer-B/registry contract derives vocabulary or universal grain from Fleet. T-208 can run independently with neutral/continuous fixtures. | 8 | Done | Worker 1 | T-201 | T-087; T-088; T-131 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Integration/E2E/certification | 2.72 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | 77a8ea4f — T-086: freeze the legacy regression oracle and gate generic surfaces against its vocabulary | 2026-08-25 | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Validate | D5 | Core | R1 | Advances | 77a8ea4f — T-086: freeze the legacy regression oracle and gate generic surfaces against its vocabulary | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 2.72 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-087 | M2 | P1 | Physical three-schema migration | Database | Schema | Critical | The measured database carries twelve schemas with 162 tables in public, of which 108 use a ppiq_ name prefix, while the ruled schemas ppiq_plant and ppiq_meta exist and hold zero tables. Migrate to the three ruled schemas: ppiq_staging, ppiq_plant, ppiq_meta. The staging rename is already prepared, because the canvas reads its schema from the configuration key Prep:StagingSchema rather than a literal. | Rule 2 is provable in one query on a fresh database. All application tests pass. The canvas catalogue lists tables from the renamed schema with only a configuration change. AND THE BENCHMARK SURVIVES THE MOVE: the phenomenon and benchmark harness frozen in T-086 is re-run UNCHANGED after the schema migration and produces identical results. A migration that silently alters the reference dataset destroys every comparison made against it. | 12 | Done | Worker 1 | T-086; T-088 | T-089; T-099; T-102; T-112; T-114; T-128; T-196; T-233; T-251; T-252 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema/migration | 2.325 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | e7d82f078d7dfa4c1ca4ec6e88d0dbc7e1ecd6ba — subject not recovered | 2026-08-28 | L2.1 | Three-schema platform and placement law | L5.7 | Converge | D4; D5 | Core | R1 | Advances | e7d82f078d7dfa4c1ca4ec6e88d0dbc7e1ecd6ba — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2.325 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-088 | M2 | P1 | Canonical migration order and legacy script archival | Database | Schema | Very Important | Backend/database/scripts contains hotfix, repair, phase and drift-correction scripts accumulated over months, including cases where two scripts created the same table. Define one canonical ordered migration path, archive superseded scripts, and add a truth gate that no two scripts create the same table. | A fresh database builds from the canonical path with no manual step. The truth gate fails if a duplicate CREATE TABLE is introduced. | 12 | Done | Worker 1 | T-086 | T-087; T-089; T-112; T-128; T-251; T-252; T-256; T-260 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema/migration | 2.325 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | 6a62c9d6 — Establish canonical database migration authority | 2026-08-26 | L8.1 | Fresh install and upgrade authority | L5.7; L2.1 | Converge | D4; D5 | Core | R1 | Advances | 6a62c9d6 — Establish canonical database migration authority | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2.325 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-089 | M2 | P1 | definition_store, definition_versions and definition_dependencies | Database | Definition store | Critical | Create the tables specified in Chapter 3 4.5.11 with immutable versions and a dependency graph, plus a trigger that rejects a dependency cycle. | Integration tests: create, version, publish, and reject a cycle. Version rows must be immutable, proved by an update attempt that fails. | 12 | Done | Worker 1 | T-087; T-088 | T-090; T-092; T-095; T-099; T-106; T-114; T-128; T-183; T-243; T-244 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema/migration | 2.325 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | 0fd79e5e3516cdfd0ab5a73a02e16638fd02693a — subject not recovered |  | L2.5 | Unified definition store and immutable target/version governance | L5.6 | Build | D4; D5 | Core | R1 | Advances | 0fd79e5e3516cdfd0ab5a73a02e16638fd02693a — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2.325 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-090 | M2 | P1 | Move all five definition kinds onto the store | Backend | Definition store | Critical | Replace the M1 compatibility adapter behind IDefinitionService with the real implementation for all five purposes: S1 Transformation, S2 Pages and widgets and filters and master items, S3 Analysis, S4 Model, S5 Log rule. The old per-artifact tables become a compatibility projection and then are retired. v2.10.1 OUTCOME SEMANTICS BINDING. As part of canonical definition convergence, bind the already-frozen SM-06 OutcomeDefinition to the canonical immutable versioned definition authority; do not design a second outcome authority. The canonical binding preserves outcome_code, outcome_type, class_taxonomy_ref, ordinal_rank_map, grain_code, detection_position_code, detection_timestamp_field, direction, unit_code, censoring_policy and definition/version identity. Any legacy ml_outcome_definitions representation may remain only as a compatibility projection during convergence and must not remain an independent semantic authority. | The M1 integration test written against IDefinitionService must pass unchanged, since it references no table name. That is the proof that the visible contract did not move. Publish an SM-06 OutcomeDefinition and resolve it back by exact immutable version. Changing detection_position_code, detection_timestamp_field, grain, taxonomy, ordinal map, direction, unit or censoring policy creates a new definition version rather than silently mutating published meaning. If a compatibility outcome representation remains during convergence, prove it resolves to the same canonical definition/version and cannot diverge into a second authority. | 12 | Done | Worker 1 | T-089 | T-091; T-092; T-095; T-099; T-104; T-106; T-114; T-128; T-134; T-147; T-183; T-195; T-210; T-221; T-228; T-231; T-232; T-233; T-235; T-239; T-243; T-244 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Downstream consumers wait for the committed T-090 authority. Handover/progress notes do not substitute for closure; the pack must apply, build, test, replay and commit on the user machine. | Product Foundation & Release Truth | CENTRAL 30-Aug-2026: canonical definition convergence remains full scope. Deliver the standard executable PowerShell pack; no Task-ID-less changes. | a6399d9c — subject not recovered |  | L5.6 | Unified definition-store semantics | L2.5 | Converge | D3; D4; D5 | Core | R1 | Advances | a6399d9c — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-091 | M2 | P1 | Impact preview, export and import | Backend | Definition store | Very Important | Add dependency impact preview before a publish, and export and import of a definition with its dependencies, per Chapter 3 4.5.11. | Publish a change to a definition three others depend on and confirm the preview lists all three before the publish is confirmed. Export and reimport into an empty database and confirm equality. | 12 | Done | Worker 1 | T-090 | T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | c6d64289 — subject not recovered |  | L5.6 | Unified definition-store semantics | L2.5 | Build | D3; D5 | Core | R1 | Advances | c6d64289 — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-092 | M2 | P1 | Registry authority: dimensions and measures as rows | Backend | Registry | Critical | Replace compiled dimension/measure catalogues with canonical registry projections over published definition versions. Registry rows must support customer-defined dimensions/measures without rebuild, plus analysis-grain metadata, signal/aggregation semantics and reference-derived measure roles. It remains a projection/serving authority, not a competing mutable definition store. | Using the same binary, add a customer-shaped dimension and measure through definitions/registry data only and use them in an authored widget. No C#/React/product-SQL edit. Registry exposes declared grain and aggregation/reference metadata and rejects unresolved semantics. | 12 | Done | Worker 1 | T-089; T-090; T-210; T-231 | T-093; T-094; T-128; T-183; T-212; T-215; T-228; T-237; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | ab2962a4; 7cad36e4 — registry authority closure commits | 2026-09-02 | L3.9 | Master items, bookmarks and saved views | L5.1 | Build | D1; D3; D5 | Core | R1 | Advances | ab2962a4; 7cad36e4 — registry authority closure commits | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-093 | M2 | P1 | Plant-vocabulary sweep, part 1: build the term list and the architecture test | Backend | Registry | Very Important | Rule 1 needs an enforcement mechanism before the sweep, or the sweep is a one-off. Create a registry-held list of plant terms (the term list is itself DATA, never a compiled constant) and an architecture test that fails the build when any listed term appears in product code outside registry data, seed content or test fixtures. Seed the list from the dimension names already found compiled into DashboardWidgetQuerySafetyRegistry: ProductFamily, GradeOrRecipe, ShiftCode, DefectType, RiskClass. | Add a term to the list and confirm the build goes red on an existing violation, then goes green once that violation is fixed. Confirm removing a term from the list does not require a code change. | 6 | Done | Worker 1 | T-092; T-206 | T-094; T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 0.9 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | 4e2e0f654b93ceed2ecdfbce4d3c1768550b3079 — T-093 govern plant vocabulary as data-driven genericity debt | 2026-09-03 | L5.1 | Canonical entity catalogue |  | Build | D3; D5 | Core | R1 | Advances | 4e2e0f654b93ceed2ecdfbce4d3c1768550b3079 — T-093 govern plant vocabulary as data-driven genericity debt | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 0.9 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-094 | M2 | P1 | Plant-vocabulary sweep, part 2: remove hardcoded universal grain and industry vocabulary | Backend | Registry | Very Important | Clear generic-runtime/demo-vocabulary violations without replacing one industry noun with another. Complete the declared-dimension execution path on BOTH runtime wire surfaces: (A) persisted widget execution via DashboardWidgetFiltersDto/declared keyed dimensions and (B) workspace/global dashboard query execution via DashboardQueryDto and the overview/quality/risk/data-quality/materials routes. Remove fixed universal grain/industry vocabulary from DashboardReferenceDataDto and the frontend consumers by resolving published registry definitions, canonical members and governed Analysis Subject/relationship authority. The target contract is definition/registry member -> relationship/path resolution -> Analysis Subject -> typed refusal; the current direct single-reference resolver is an interim implementation until T-095/T-096 path authority lands. No presentation vocabulary becomes product authority. | Using the same binary, author a foreign/customer-shaped dimension and prove it filters both a persisted widget and the workspace/global route surface through the same published definition/member identity. Both surfaces must return the same typed refusal when the dimension is undeclared, inactive, unmapped, has no subject path, or becomes ambiguous. No compiled fallback to defectType/riskClass/shiftCode or a universal material grain. Frontend consumers use the keyed contract. Wave-C genericity arithmetic remains exact: every known fingerprint is retired or explicitly lawful; unknown=0. | 24 | Done | Worker 1 | T-092; T-093; T-209 | T-095; T-128; T-183; T-196; T-253; T-256; T-258 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 3.6 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Product Foundation & Release Truth | CENTRAL 04-Sep-2026: T-094 remains open. Scope is formally amended from one wire to both declared-dimension execution surfaces. No new task is created while T-094 is open; after closure any new surface requires a new Task ID. | 377aabdffb27d651d30537ce5228ee4afe268526; 6ab97ee2; e74ecd1c; 5a967f1b0ab45961c8b8a880bb4fdec53a783134 — final: T-094 close keyed declared-dimension cutover and genericity reconciliation | 2026-09-07 | L5.1 | Canonical entity catalogue | L5.3 | Build | D1; D3; D5 | Core | R1 | Advances | 377aabdffb27d651d30537ce5228ee4afe268526; 6ab97ee2; e74ecd1c; 5a967f1b0ab45961c8b8a880bb4fdec53a783134 — final: T-094 close keyed declared-dimension cutover and genericity reconciliation | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 24 | 3.6 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-201 | M2 | P1 | Freeze the successful M1 presentation baseline and transfer programme authority to M2 | Programme | Release baseline | Critical | Resolve the shared dirty tree, keep/revert the associative change on evidence, commit exact owned files, tag/freeze the successful presentation baseline, and formally stop presentation-only feature/page/data work. Remaining generic defects move to M2-P0 owners rather than being completed as M1 content. | Clean index and explicit foreign-file inventory; immutable release/tag or equivalent frozen artifact; presentation profile still launches; one ledger lists every unclosed M1 item as frozen, superseded, or consumed by a named M2 task. No customer-demo-only task remains on the September critical path. | 4 | Done | Worker 1 |  | T-086; T-202; T-203; T-204; T-205; T-206; T-207; T-208; T-213; T-241 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Release / governance | 1.5 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Git/worktree ownership + release/tag only. | After commit/tag, all workers consume the frozen baseline; nobody reopens M1 presentation scope without a proven regression. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | BASELINE HEAD 7da9d46ed29545f1c4f4686fa82c117c08b9fc86; TAG m1-presentation-baseline-2026-08-21 — no task commit; tag is closure artifact | 2026-08-24 | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Validate | D1; D5 | Core | R1 | Advances | BASELINE HEAD 7da9d46ed29545f1c4f4686fa82c117c08b9fc86; TAG m1-presentation-baseline-2026-08-21 — no task commit; tag is closure artifact | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 4 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-202 | M2 | P1 | Persisted page/widget definition replay gate | Quality | Release Truth | Critical | Enumerate every active customer-facing page/widget definition from the real database and execute its actual query contract against the release API/database. Validate declared terminal semantics, row/population evidence and compatibility. This gate tests the product as persisted, not merely source-code paths. | Every active persisted widget executes with 2xx plus Populated/Empty/Blocked/Refused as documented; unexpected 4xx/5xx is a failure. Deliberately corrupt one dimension/measure combination and prove the gate fails. Restore and prove green. Emit machine-readable report naming definition/page/widget. | 10 | Done | Worker 2 | T-201 | T-212; T-248 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | E2E / integration gate | 4 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend E2E + dashboard query test harness; no canonical schema edits. | T-150 later consumes this gate; it does not redesign it. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | ad37c324 — Add persisted definition replay gate for release truth | 2026-08-25 | L8.8 | C1–C4 performance certification and golden-journey release gate | L3.1; L3.4 | Validate | D2; D5 | Core | R1 | Advances | ad37c324 — Add persisted definition replay gate for release truth | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-203 | M2 | P1 | Customer-route network, console and widget-state invariant | Quality | Release Truth | Critical | For every customer-reachable route, navigate and settle against the real API; fail on unexpected HTTP >=400, failed required request, uncaught JS exception, unhandled console error, error toast, or widget Failed state. Record route/request/widget evidence. | Inject one failing API response and one uncaught render error and prove the route gate fails for the named cause. With faults removed, every customer route settles with zero unexpected network/console/widget failures. | 10 | Done | Worker 2 | T-201 | T-222; T-248 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Playwright / session | 4 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend E2E/session harness. | All later customer-facing feature tasks must add their route to this gate before close. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | cd1a450e — Add customer route invariant gate with durable evidence | 2026-08-25 | L8.8 | C1–C4 performance certification and golden-journey release gate | L6.7 | Validate | D2; D5 | Core | R1 | Advances | cd1a450e — Add customer route invariant gate with durable evidence | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-204 | M2 | P1 | Associative cross-filter state-machine certification | Frontend | Associative BI | Critical | Replace click-smoke acceptance with a state-machine proof: capture widgets A/B/C, click X in A, assert selection state, assert B/C re-query with X, assert returned populations and visible results change, clear X and assert restoration. Execute across interactive renderer families. | Bar, line, scatter, heatmap, table-row and interactive KPI families each prove selection propagation, dependent request mutation, population/result change, and restoration. A deliberate broken dependency-array/bridge falsification must fail the test. | 10 | Done | Worker 2 | T-201 | T-222; T-248 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend behavioural E2E | 4.25 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | AssociativeContext/filter bridge + E2E tests; no unrelated chart redesign. | This task supersedes using browser walking as the acceptance of cross-filtering. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | c6491e2d — closure-state HEAD; exact task commit subject not independently recovered | 2026-08-31 | L3.2 | Associative engine and selection strip |  | Validate | D2; D5 | Core | R1 | Advances | c6491e2d — closure-state HEAD; exact task commit subject not independently recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4.25 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-205 | M2 | P1 | Frontend global suite termination and machine-readable gate | Frontend | Test infrastructure | Very Important | Make the global frontend unit/component suite terminate deterministically, produce a machine-readable result, and fail the pipeline on non-termination, timeout, skipped mandatory tests or leaked handles. | Run the full suite twice from clean processes under the declared timeout; both terminate with identical pass/fail/skip counts and machine-readable output. Inject a leaked handle/non-terminating test and prove the gate goes red. | 8 | Done | Worker 2 | T-201 | T-150; T-248; T-250; T-255; T-257 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend test infrastructure | 3.2 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend test runner/config only. | T-205 remains closed. Deterministic suite-truth mutations are owned by T-250; do not amend or reopen T-205 for product/test corrections. | Product Foundation & Release Truth | CENTRAL 30-Aug-2026: T-205 CLOSED GREEN at b7fcc890. The gate correctly reports suite truth; bounded corrections are a separate explicit task. | b7fcc890 — Gate the frontend suite on deterministic termination and machine-readable evidence | 2026-08-30 | L8.2 | Test architecture with disposable isolated databases |  | Validate | D2; D5 | Core | R1 | Advances | b7fcc890 — Gate the frontend suite on deterministic termination and machine-readable evidence | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-206 | M2 | P1 | Scope-aware genericity architecture gate | Architecture | Genericity | Critical | Create a scope-aware architecture test that forbids customer/demo/industry vocabulary and compiled customer dimension/grain authorities inside generic runtime/engine/API contracts while allowing that vocabulary in explicitly classified fixtures, mappings and documentation. Include detection of compiled dimension arrays and implicit grain defaults. | Falsify the gate with a generic-runtime 'coil' fallback, a compiled customer dimension, and an industry-specific class; each fails. The same terms in approved fixture paths remain allowed. Gate consumes configured path/authority classes, not a naive whole-repo negative text scan. | 8 | Done | Worker 3 | T-201 | T-093; T-213 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Architecture/test | 2 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Architecture/genericity tests only; no W1 schema or W2 UI mutation. | Violations are routed to the owning task/file; Worker 3 does not fix foreign files. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L5.1 | Canonical entity catalogue |  | Validate | D1; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-208 | M2 | P1 | Generic controlled validation fixture authority and continuous-process known-answer pack | Quality | Test data | Critical | Create the dataset-neutral controlled fixture authority separate from product vocabulary. Keep Fleet v2 as legacy discrete regression oracle only; continuous-process fixture includes irregular analog samples, state intervals, counters, alarms, process windows, independent manual/business records, PLUS a declared transition/stabilisation event and conflicting multi-objective practice vectors with predeclared known answers. | Fixture manifests are machine-readable, immutable by version, inaccessible as planted truth to runtime, and include SampleMean vs TimeWeightedMean, StateDuration, Delta, interval overlap, transition/stabilisation regime truth, a pooled-vs-steady-state confounding case, a known Pareto frontier, negative controls and refusal cases. Product code contains no fixture vocabulary. | 10 | Done | Worker 3 | T-201 | T-209; T-211; T-216; T-217; T-218; T-234; T-238 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Test fixture / kernel | 2.5 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New generic fixture/test assets only. | T-211/T-217/T-219 consume this fixture; they never read planted expected answers at runtime. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | 969c767c — T-208: generic controlled validation fixture and continuous-process known answers |  | L8.2 | Test architecture with disposable isolated databases |  | Build | D1; D5 | Core | R1 | Advances | 969c767c — T-208: generic controlled validation fixture and continuous-process known answers | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 2.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-209 | M2 | P1 | Analysis Subject and Grain contract + schema-independent resolution kernel | Architecture / Analytics Engine | Generic subject/grain contract | Critical | Freeze the generic AnalysisSubject/GrainDefinition contract and a schema-independent resolver/kernel. It defines subject kinds, grain identity, time-window semantics, typed GR01 refusal and the rule that no analytical result requires a material identifier. No production migration, DI registration or canonical table edit in this task. | Known-answer tests resolve discrete, equipment-window and flow-interval subjects; missing grain refuses GR01; no industry noun/material-only assumption appears in the public contract. Runs without production DB access. | 6 | Done | Worker 3 | T-208 | T-094; T-210; T-214; T-231; T-234; T-253 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel/contract | 1.5 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New generic contract/kernel/tests only. | T-231 persists this contract; downstream consumers bind to contract, not table shape. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | f2bafdb4 — subject not recovered | 2026-08-25 | L5.3 | Analysis Subject, grain and signal aggregation authority |  | Build | D1; D3; D4; D5 | Core | R1 | Advances | f2bafdb4 — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-210 | M2 | P1 | Canonical signal and aggregation semantics authority | Backend | Semantic measurement authority | Critical | Extend parameter definitions and KPI bindings with signal_kind, aggregation_kind, interpolation, weight basis, maximum gap, quality policy, counter-reset and time basis. Remove any silent DEFAULT 'Average'. Store grammar as product-owned enums/registry; customer parameters select it. | Create Analog/State/Counter definitions and prove no aggregate can execute from data_type alone. Parameter or KPI binding may declare a valid method; absent semantics returns AG01. Invalid method for signal returns AG02. Fresh DB/replay green and no default Average in canonical schema. | 12 | Done | Worker 1 | T-090; T-209 | T-092; T-128; T-211; T-212; T-242 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema authority | 5.1 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Parameter definitions/KPI bindings/migrations/definition contract. | T-211 executes exactly this contract; no second aggregation registry. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | 92a655e1ddc4becedbaf89a3db96dc0d0f1eaf94 — subject not recovered | 2026-09-01 | L5.3 | Analysis Subject, grain and signal aggregation authority | L4.2 | Build | D1; D3; D5 | Core | R1 | Advances | 92a655e1ddc4becedbaf89a3db96dc0d0f1eaf94 — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 5.1 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-216 | M2 | P1 | Source Time Authority contract and timestamp-semantics kernel | Architecture / Analytics Engine | Temporal authority contract | Critical | Freeze the per-source time contract: timezone, timestamp basis/origin, DST policy, clock reference, observed skew, maximum tolerated skew, and source/server/ingest timestamp semantics. No production persistence in this task. | Known-answer contract tests distinguish source/server/ingest timestamps and prove skew beyond tolerance yields TemporalUncertain rather than conflict. Runs without production DB access. | 5 | Done | Worker 3 | T-208 | T-200; T-217; T-233 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel/contract | 1.25 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Temporal contract/tests only. | T-233 persists source-time authority; T-217 consumes contract without waiting for persistence. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | ea9103fd — Establish source time authority for plant timestamps | 2026-08-25 | L1.5 | Acquisition provenance and source lineage | L5.5 | Build | D1; D3; D5 | Core | R1 | Advances | ea9103fd — Establish source time authority for plant timestamps | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 5 | 1.25 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-231 | M2 | P1 | Persist Analysis Subject and Grain authority in canonical definition store | Backend / Database | Canonical subject/grain persistence | Critical | Persist the frozen T-209 AnalysisSubject/GrainDefinition contract through canonical definitions and analysis_subjects/grain-definition tables. This task owns migration, tenant-safe keys, version binding and canonical APIs only; it does not redesign the contract. | Fresh migration/replay green. Persist discrete, equipment-window and flow-interval grains; same binary resolves all via API. GR01 preserved. Tenant isolation and definition-version replay pass. | 6 | Done | Worker 1 | T-090; T-209 | T-092; T-128; T-139; T-232; T-235 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema authority | 2.55 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | analysis_subjects/grain definitions + API/migrations. | T-092/T-128/T-139/T-213 consume committed persistence; they do not invent subject identity. | Product Foundation & Release Truth | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work. | c930af079502aa1660ef2bd5c50756d3fc3cf8f3 — Persist-T231-canonical-analysis-subject-grain-authority |  | L5.3 | Analysis Subject, grain and signal aggregation authority |  | Build | D1; D3; D4; D5 | Core | R1 | Advances | c930af079502aa1660ef2bd5c50756d3fc3cf8f3 — Persist-T231-canonical-analysis-subject-grain-authority | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 2.55 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-250 | M2 | P1 | Frontend suite truth convergence: Journey routing and design-system corrections | Frontend | Release truth / design system | Very Important | Resolve only the six deterministic findings exposed by T-205 without reopening T-205: correct stale JourneyRail certification for Connections=J4 and Supervisor=J15; map the real /assistant/configuration route directly to J15 and guard redirect aliases; move constant MetricCard inline styles to CSS; retain HeatmapChart only as an exact-file semantic-matrix exception; convert SpecificationTable to StandardTable while preserving observed-state semantics. No broad frontend cleanup. | Narrow affected tests GREEN first: Connections=J4, Supervisor=J15, /assistant/configuration=J15, redirect-alias guard GREEN, MetricCard D2 violations=0, Heatmap exact-file exception only, SpecificationTable uses StandardTable and existing component tests stay GREEN. Then run the ordinary complete frontend suite once with failed=0 and skipped=0. Do not rerun T-205 Certify unless T-205 gate code changes. | 6 | Done | Worker 2 | T-205 | T-150; T-255; T-257; T-258 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend bounded correction | 2.5 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own only the bounded JourneyRail/Journey tests, MetricCard styling, exact Heatmap architecture exception and SpecificationTable convergence. No edits to T-205 runner/validator and no unrelated frontend cleanup. | T-205 remains closed. After T-250 GREEN, move directly to the next eligible existing Worker-2 task. No unnamed corrective work and no repeated expensive certification loop. | Product Foundation & Release Truth | CENTRAL 30-Aug-2026: no Task ID = no repository mutation. T-250 is the sole owner of these six findings; bounded correction only, narrow tests first, one final normal suite. | 6615481b — Converge frontend journey and design-system truth | 2026-08-30 | L8.2 | Test architecture with disposable isolated databases |  | Converge | D1; D2; D5 | Core | R1 | Advances | 6615481b — Converge frontend journey and design-system truth | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 2.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-251 | M2 | P1 | Physical database catalogue, naming authority and zero-unknown schema dictionary | Database | Schema governance | Critical | Create the generated physical database catalogue required by Master Design v4.10.1. Reconcile canonical migration/EF authority with fresh canonical certification database `ppiq_acceptance_empty` and long-lived `ppiq_app`. Every table/view and every column in ppiq_meta, ppiq_plant, ppiq_staging and permitted public infrastructure receives schema, logical family, lifecycle class, owner, purpose, creator, readers/writers, keys/FKs, design clause, backlog owner, retention/RLS policy and naming-conformance state. Generate the relation graph. Define/enforce the forward snake_case/no-customer-vocabulary naming standard without mass-renaming grandfathered objects. Read-only census first; deletion/rename is outside this task. | Fresh canonical certification DB `ppiq_acceptance_empty`: 100% tables/views/columns represented; zero unknown product objects; every table has logical family + lifecycle + owner + design clause; physical FK graph generated; public contains platform infrastructure only. Long-lived ppiq_app: every extra object classified, never auto-deleted. Generator reruns deterministically from executable schema authority. A new DDL object without catalogue classification makes the gate red. | 12 | Done | Worker 1 | T-087; T-088; T-260 | T-112; T-150; T-252; T-256; T-259 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema/migration | 1.8 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own generated DB catalogue tooling/documentation and read-only pg_catalog queries. No product table deletion, rename or unrelated DDL. | Publish semantic-named catalogue artifacts only; no task-number repository filename. Hand off the generated dictionary to T-115/T-123/T-150. | Product Foundation & Release Truth | CENTRAL 04-Sep-2026: table count is not a defect; unknown authority is. This task establishes zero-unknown physical schema governance before any cleanup. | 7ba31f96f3810bdac734bd1850275a601503d34d |  | L5.7 | Physical database governance and zero-unknown catalogue | L8.1 | Build | D4; D5 | Core | R1 | Advances | 7ba31f96f3810bdac734bd1850275a601503d34d | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Original catalogue closure explicitly frozen by CENTRAL. Retain Done; later catalogue/build changes do not retroactively erase this producer closure. Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-252 | M2 | P1 | Disposable database lifecycle and integration-test database isolation | Quality | Database isolation | Critical | Remove shared-live-database mutation from certification/test infrastructure. Integration suites and corrective packs create or clone a dedicated disposable database/template, record its name, execute against it, and drop it in an unconditional finally path on success/failure. Never flip or mutate live ppiq_app/ppiq_presentation as a test fixture. Add bounded cleanup for current orphan probe/backup/scratch databases after evidence-retention adjudication. v2.20.0 PROMOTION — this is now M2-P1 foundation scope, not late P5 hardening. Every DB-dependent certification path must either receive a dedicated disposable database/template from this authority or explicitly declare that it is a read-only external probe. Local developer runs may skip an external-probe-only test with a named reason when the probe is absent; Release-1 CI/certification provisions its own disposable target and permits zero DB-fixture skips. v2.20.1 DEPENDENCY CORRECTION — T-251 is an explicit prerequisite, not only a handover convention. T-251 classifies current/fresh physical database authority before T-252 changes certification/test database lifecycle. | Induced test failure, PowerShell/native-command failure and timeout each leave zero newly orphaned databases. Captured database names are gone after cleanup; ppiq_app, ppiq_acceptance_empty, ppiq_presentation and postgres are untouched. Two parallel suites use distinct DBs. A post-run orphan query is green. Current retained backups/probes are classified and removed only after retention proof. A release-profile certification provisions its own disposable DB and records zero database-fixture skips. A developer-local run with an intentionally absent external probe may skip only the named probe test and must emit the exact reason; it may not fail by mutating or assuming a shared live database. Emit the DB-fixture execution result using the canonical T-259 Release Evidence Envelope v1 fields. T-252 owns DB skip semantics and database_fixture_mode/name values; it does not invent a second envelope format. Producer contract is T-259 Release Evidence Envelope v1. T-252 may add DB-specific extension fields but may not rename/redefine common fields. For Release-1 DB-fixture certification specifically, `skipped_count` must be 0. A local approved external-probe skip is allowed only outside the Release-1 certification profile and still counts in total_count, not executed_count. | 8 | Done | Worker 1 | T-087; T-088; T-251; T-259 | T-106; T-112; T-150; T-256 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Integration/E2E/certification | 1.2 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own integration-test DB fixture/runner and disposable-DB lifecycle tooling only. Do not change product schema semantics. | Every pack that CREATE DATABASEs owns DROP in finally. Persistent DB roles are explicit and protected. | Product Foundation & Release Truth | CENTRAL v2.20.0 08-Sep-2026: promoted from P5 to P1. Certification DB isolation is foundational; Worker-1 sequence is T-251 → T-252 → T-256. |  |  | L8.2 | Test architecture with disposable isolated databases |  | Harden | D3; D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-256 | M2 | P1 | Runtime genericity and three-schema consumer convergence | Backend | Genericity / physical-consumer convergence | Critical | After T-251 classifies the physical catalogue and T-252 stabilises test DBs, converge runtime consumers onto the three-schema/generic product authority. Every runtime `public.*` product reference is either migrated to ppiq_meta/ppiq_plant/ppiq_staging/definition authority or explicitly catalogued as permitted platform compatibility with a bounded retirement owner. Material/heat/coil-specific endpoint/service families in the generic binary are retired, moved behind an explicit presentation/demo compatibility boundary, or replaced by Analysis Subject/relationship/registry-driven surfaces. Do not mass-rename blindly and do not break the retained presentation database. v2.20.1 OWNERSHIP BOUNDARY — T-256 is BACKEND/API/DB-RUNTIME convergence only. Do not edit Worker-2 frontend MaterialAnalytics pages, frontend route ownership, or productApiClient frontend types. Where backend convergence would otherwise break an existing frontend material surface, preserve a bounded typed compatibility contract long enough for T-258 to migrate/retire that frontend consumer; do not leave the generic build red. v2.20.2 RECORDED T-253 HANDOFF — `MappingDefinitionService.AllowedTargetEntities` is a measured hardcoded 12-name target vocabulary and is NOT T-253 scope. T-256 owns its backend convergence: consume the canonical projection-target capability and catalog authority established by T-253, remove the duplicate plant-vocabulary list as runtime authority, and preserve only any explicitly justified compatibility mapping. v2.20.3 DEPENDENCY RULING — T-253 remains a HARD dependency for T-256 because T-256 must replace MappingDefinitionService.AllowedTargetEntities with the exact canonical projection-target predicate created by T-253. Starting T-256 without that contract would either duplicate classification or broaden eligibility incorrectly. Phase IDs are product/outcome groupings, not chronological barriers; the dependency graph governs execution. | Runtime-project scan reports zero unapproved `public.` product reference; every permitted public object exists in the T-251 platform/compatibility catalogue with owner and retirement state. Genericity gate explicitly covers material endpoint/service and generic API composition paths and has unknown=0. A foreign customer-shaped backend/API/query journey runs on the same binary with no material/heat/coil backend product dependency. If a presentation-only compatibility route remains, it is disabled outside the explicit presentation profile and is not required by canonical product paths. Backend/API acceptance is green without editing Worker-2 frontend files. Enumerate every remaining frontend material-specific consumer discovered by the backend convergence and hand it to T-258 as machine-readable evidence. The current generic frontend build remains green through the compatibility handoff. Static/runtime proof shows MappingDefinitionService no longer owns an independent hardcoded AllowedTargetEntities plant vocabulary; valid target eligibility resolves from canonical catalog/registry authority and foreign-shaped targets require no source-code list edit. MappingDefinitionService target validation consumes the same T-253 projection-target predicate used by the authoring picker. Positive/negative eligibility decisions are identical across Canvas authoring and MappingDefinitionService; no second list or schema-only rule survives. | 12 | Done | Worker 1 | T-088; T-094; T-251; T-252; T-253 | T-116; T-150; T-247; T-258 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 3.2 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Backend runtime consumers, API composition, DB-facing services and backend architecture/genericity guards only. NO Frontend/PlantProcess.Web mutation. T-258 exclusively owns frontend material/genericity convergence. | Publish a bounded compatibility/consumer handoff manifest to T-258. Do not solve frontend Material pages/types/routes inside T-256; do not leave generic frontend red. | Product Foundation & Release Truth | New P1 convergence task; closed T-093/T-094 stay closed and act as regression authorities. | 36de9370 |  | L2.1 | Three-schema platform and placement law | L5.1; L5.7 | Converge | D1; D3; D4; D5 | Core | R1 | Advances | 36de9370 | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited accepted Done state retained. T-262's terminal summary identifies parent36de9370 as T-256. This corroborates a commit anchor, not a rerun of T-256 gates. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. |  | INHERITED ESTIMATE | 12 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-259 | M2 | P1 | Release evidence envelope v1 machine-readable contract | Release / governance | Evidence contract | Critical | Freeze the small representation-independent machine-readable Release Evidence Envelope contract before DB/frontend producers implement it. This task owns ONLY the shared schema/validator contract, not the T-227 production scorecard and not producer execution. Contract version `1.0` defines required common fields: contract_version, task_id, gate_id/suite_id, environment, profile, started_at, completed_at, total_count, executed_count, passed_count, failed_count, skipped_count, unapproved_skip_count, structured skip_reasons, commit_sha, artifact/evidence paths and final verdict. Optional producer extensions include database_fixture_mode/database_name and other namespaced evidence details. Count semantics are explicit: `total_count = executed_count + skipped_count`; `executed_count = passed_count + failed_count`; `0 <= unapproved_skip_count <= skipped_count`. A skipped case is discovered/total but NOT executed. GREEN is impossible when failed_count>0 or unapproved_skip_count>0. Producer-specific release policy may be stricter (for example T-252 Release-1 DB-fixture acceptance requires skipped_count=0). Use semantic repository filenames, never a task-number filename. | Validate one DB-fixture example shaped for T-252 and one frontend/E2E example shaped for T-257 against the same contract. Required invariants: total_count=executed_count+skipped_count; executed_count=passed_count+failed_count; unapproved_skip_count<=skipped_count. Negative controls reject: wrong contract version, inconsistent totals, a skipped case counted as executed, GREEN with failed_count>0, GREEN with unapproved_skip_count>0, unapproved_skip_count greater than skipped_count, and malformed skip-reason classification. Include an all-skipped fixture and prove executed_count=0 rather than total_count. The schema/validator is consumable from PowerShell/CI and application/test tooling without either producer redefining fields. No scorecard thresholds, DB lifecycle or frontend runner behavior is implemented here. | 2 | Done | Worker 1 | T-251 | T-150; T-227; T-252; T-257 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Architecture/test | 0.3 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Shared release-evidence schema/validator + focused contract tests only. No DB fixture implementation, frontend test runner, scorecard, feature code or release aggregation. | T-252/T-257 are producers. T-227 owns production acceptance scorecard/policy. T-150 aggregates. None may redefine the v1 envelope. | Product Foundation & Release Truth | v2.20.2 Option-A ruling from Worker-1 consistency review: split schema contract ahead of producers rather than pulling full T-227 P5 scorecard into P1. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 2 | 0.3 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-260 | M2 | P1 | Canonical acceptance database builder convergence | Database / release infrastructure | Fresh certification database build path | Critical | Correct the governed builder for `ppiq_acceptance_empty` so a fresh NO-SEED certification database is created by the complete canonical migration authority rather than a partial EF+scripts subset. The builder must consume `canonical-migration-order.json` (or the same single canonical ordering authority) and execute every required tier in declared order, including topology/storage convergence and declared views, while excluding demonstration/seed/test content. Trace the creator authority for `dump_store.src_caster_oracle_shape_cast_pieces`; if it enters through demo/seed/test content incorrectly present on the canonical fresh path, remove that path defect. If it is an explicitly required legacy compatibility migration, report it for T-256 rather than silently deleting product data. This task may rebuild the empty certification database as a governed certification operation; it must not mutate `ppiq_app` or `ppiq_presentation` and must not use them as fixtures. | One semantic PowerShell runner performs non-writing preflight, backs up owned builder/order files, builds a uniquely named disposable candidate from the canonical order, proves required topology convergence + declared views are present and demo/seed/test content is absent, then replaces/recreates `ppiq_acceptance_empty` only after the candidate is GREEN and the previous certification DB can be restored on failure. Prove the canonical-order consumer executed all declared required entries exactly once in order, with zero undeclared execution. Prove `ppiq_app` and `ppiq_presentation` are untouched. After rebuild, rerun the T-251 catalogue and record before/after counts; do not classify the old 106/81 queue. The `dump_store.src_caster_oracle_shape_cast_pieces` creator is identified exactly and ruled as canonical compatibility or excluded demo/seed/test path. Negative control: omit one terminal canonical tier in a disposable candidate and the build-path gate must go RED. | 6 | Done | Worker 1 | T-088 | T-251 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Database infrastructure corrective | 1.8 | M2-P1 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Fresh acceptance DB builder, canonical migration-order consumer/validation, focused builder tests and T-251 rerun orchestration only. No product runtime/API/frontend changes; no mutation of ppiq_app or ppiq_presentation; no broad migration rewrite. | T-260 corrects how the fresh certification DB is constructed; T-251 remains the physical catalogue owner and resumes only on the corrected DB. T-256 later owns genuine runtime/schema compatibility residue that remains after a correct fresh build. | Product Foundation & Release Truth | Created from T-251 runtime evidence on 09-Sep-2026. The catalogue machine is valid, but the designated fresh certification DB is built from an incomplete canonical path, so classifying its current queue would create false governance work. Narrow corrective task; closed T-088 is not reopened. |  |  | L8.1 | Fresh install and upgrade authority | L5.7; L8.2 | Converge | D3; D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-095 | M2 | P2 | Relationship members, cardinality, grain conversion and preferred paths | Backend | Relationship model | Critical | Extend the M1 slice to the full model in Chapter 3 4.5.10: members, cardinality, grain conversion between related entities, preferred path selection when more than one path exists, and published versions. v2.10.2 CONVERGENCE CORRECTION — T-095 does not merely 'extend' M1 physical tables. It converges the M1 relationship service/compatibility persistence onto the canonical Chapter 3 4.5.10 tables after definition_store exists, including source_definition_id/version, grain conversion, preferred paths, ambiguity/validation state and retirement semantics, while keeping the M1 external contract stable. | Declare two paths between the same pair of entities, mark one preferred, and confirm the resolver chooses it. Change the preference and confirm the resolution changes with no other edit. | 12 | Done | Worker 1 | T-057; T-089; T-090; T-094 | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-114; T-128; T-134; T-183; T-196; T-221 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e — subject not recovered | 2026-09-07 | L5.2 | Permanent relationship model |  | Build | D1; D3; D5 | Core | R1 | Advances | 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | SOURCE CORROBORATES CLOSED FOUNDATION | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Closed original scope; zero remaining here does not certify downstream Canvas integration. | Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — PublishAsync Backend/PlantProcess.Application/Relationships/RelationshipService.cs:218-260 — ValidateDeclaration | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-096 | M2 | P2 | Path resolver, part 1: resolver core and the first eight consumers | Backend | Relationship model | Critical | Chapter 2 3.15.4 names sixteen consumers of the relationship model. Build the resolver core, then route the first eight through it: canonical projection, page and widget queries, associative filtering, drill-down, drill-through, genealogy, statistics and correlation. | A regression test per consumer asserting it resolves through the published model, and refuses with a named reason when the relationship is unpublished. Eight tests, no exceptions. | 8 | Done | Worker 1 | T-095 | T-097; T-098; T-107; T-109; T-128; T-134; T-183; T-221 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.2 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | de243027073fc5e492d65e9f9845255342517510 — T-096 relationship resolver consumer convergence | 2026-09-08 | L5.2 | Permanent relationship model |  | Build | D3; D5 | Core | R1 | Advances | de243027073fc5e492d65e9f9845255342517510 — T-096 relationship resolver consumer convergence | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | SOURCE CORROBORATES CLOSED FOUNDATION | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Original resolver/convergence closure retained; no rebuilding cost. | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:34-113 — ResolveAsync Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-96 — ConsumerFamilies | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-097 | M2 | P2 | Path resolver, part 2: the remaining eight consumers and the regression suite | Backend | Relationship model | Critical | Route the remaining eight through the resolver: feature engineering, model training, prediction, practice learning, remediation search, value calculation, assistant retrieval and evidence. Some of these are built in Release 2; add the resolver seam now so they cannot be written against an ad-hoc join later. | Eight further regression tests. For consumers whose engine arrives in Release 2, the test asserts the seam exists and refuses when unpublished, which is what stops a later shortcut. | 6 | Done | Worker 1 | T-096 | T-098; T-107; T-109; T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 0.9 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | 95220d1804493f8e7b80347fe3ed4de24741f9ec — T-097 relationship consumer barrier across all sixteen families | 2026-09-08 | L5.2 | Permanent relationship model |  | Build | D3; D5 | Core | R1 | Advances | 95220d1804493f8e7b80347fe3ed4de24741f9ec — T-097 relationship consumer barrier across all sixteen families | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 0.9 | SOURCE CORROBORATES CLOSED GUARD | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | No remaining original implementation; avoid counting unwired later engines against this completed guard. | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:12-44 — barrier semantics Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-114 — consumer and forbidden-authority inventory | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-098 | M2 | P2 | Relationship Browser page and path evidence | Frontend | Relationship model | Very Important | Build the C6 Relationship Browser from Chapter 3 4.4 with the ten-field page contract, showing declared relationships, their members, their paths and the evidence for each path. v2.10.2 CONTINUITY CORRECTION — complete the existing T-060 /relationships page in place. Do not create a second C6 surface. Preserve the route, layout and M1 control contract while replacing/extending the hidden relationship authority and path evidence. | Open a relationship and confirm its members, cardinality and path are shown with evidence. Confirm an unpublished relationship is visibly distinct from a published one. Run the M1 C6 continuity snapshot before/after canonical cutover and prove no visible-contract regression. | 12 | Not Started | Worker 2 | T-095; T-096; T-097 | T-107; T-109; T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/UI feature | 2 | M2-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-060 M1 C6 surface + T-095 + T-096 + T-097. | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L5.2 | Permanent relationship model |  | Build | D1; D2; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — Use T-265 C6 relationship list/detail/member/cardinality/path-validation handoffs. Trace every applicable Chapter 3 control to a reachable UI variant and keep resolver behavior under its existing authority. | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2 | REUSABLE BACKEND PRESENT; CANONICAL UI NOT LOCATED | 6 | 9 | 14 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | UI 4/6/9 + contract/negative tests 1/2/3 + targeted closure 1/1/2. Reuse all relationship producer work. | Backend/PlantProcess.Api/Endpoints/Relationships/RelationshipEndpoints.cs:21-92 — MapRelationshipEndpoints Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:62-113 — path results | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-099 | M2 | P2 | Quarantine, part 1: the table, the reprocess API and the first eight PV classes | Backend | Quarantine | Critical | Chapter 3 4.5.14 specifies quarantine with fifteen typed PV codes. A repository search for projection_quarantine returns zero hits, so this does not exist. Build the table with its columns, the reprocess endpoint, and the first eight validation classes so a bad row is quarantined under a named code instead of corrupting the canonical layer or failing the whole batch. | Craft one malformed input per implemented class and assert each is quarantined under the correct code, while the good rows in the same batch still project. | 8 | Done | Worker 1 | T-087; T-089; T-090 | T-100; T-101; T-104; T-107; T-108; T-109; T-114; T-128; T-183; T-261 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.2 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. v2.22.1 — CLOSED GREEN / COMMITTED at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af (parent 86e1b677212195f191697ecdca7e9441b3dbde33). Preserve this closure unless a concrete later regression is demonstrated. Gate O has one exact inherited DefinitionKind RED and canonical replay limitations remain; this is not Release-wide GREEN. | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af |  | L2.3 | Canonical projection with validation, quarantine and reprocessing |  | Build | D3; D4; D5 | Core | R1 | Advances | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | CLOSED GREEN / COMMITTED — FINAL TRANSCRIPT CORROBORATED | Final executed terminal transcript corroborates the owner-reported closure: 49/49 live,5/5 catalogue,19/19 owned;6/6 disposable DBs dropped;0survivors. GateO900=899passed+1exact inheritedDefinitionKindRED. Exact staging and one semantic commit proven. No live rerun performed in this review; no release-wideGREEN. Pasted text(20260914-134548).txt ¦ lines430-450; final gatesQ/R; COMMITca02b40ea1b69050a45cb35a3e1d64f15b1f66af; PARENT86e1b677212195f191697ecdca7e9441b3dbde33; live49/49, catalogue5/5, owned19/19; not release-wideGREEN. | 86e1b677212195f191697ecdca7e9441b3dbde33 | INHERITED ESTIMATE | 8 | 1.2 | CLOSED SCOPE PRESERVED; SOURCE CORROBORATES | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | T-099 CLOSED GREEN at ca02b40e; its inherited DefinitionKind RED is not a reason to budget a rewrite. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:141-181 — MapMaterialUnitAsync Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — bounded reprocess surface Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:3-20 — narrow topology correction | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-100 | M2 | P2 | Quarantine, part 2: the remaining seven PV classes and per-class tests | Backend | Quarantine | Critical | Implement the remaining seven validation classes and give every class its own test fixture, so the class set is provably complete against Chapter 3 4.5.14 rather than approximately complete. | Distinct governed validation codes and fixture coverage must equal PV01..PV15 exactly. At least 15 classification fixtures; additional regression fixtures for an existing code are allowed. The completeness ratchet fails for an unproved enum member, not for duplicate display names or extra same-code tests. Live PostgreSQL proof executes every PV class; PV15 quarantine→cross-batch reference arrival→bounded reprocess passes; PV13 .60+.40=1.00 must not be quarantined. Exact live constraint, canonical migration order, disposable cleanup and exact single-commit closure required. | 6 | Done | Worker 1 | T-099 | T-101; T-107; T-109; T-128; T-183; T-261 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 0.9 | M2-P2 | RUNNER-1 CANDIDATE IS PRESENT; DO NOT RERUN RUNNER 1 or require a clean owned tree relative to HEAD. Resume from the exact handoff/postimages. Resume v1.0.1 is issued; success is not yet reported. Validate HEAD against the handoff and all owned postimage hashes before continuing. Expected parent supplied for closure is 4e0f1219ddbac3163bafe7ce510b62520683a77c; do not substitute the older T-099-only HEAD. If the exact gates fail, stop and report without manual resets, cleanup of unrelated work, or a fresh mutation pack. Worker 1/CENTRAL retains the execution lock through T-100 final commit; Worker 2 remains held. | Worker 1 is the recorded execution owner; CENTRAL-assisted delivery. Preserve the existing T-100 candidate and unrelated dirty work. Exclusive shared repository mutation lock until T-100 is committed. | Release Worker 2 only after T-100 final commit SHA and closure evidence. The successor consumes PROJECTION_* declaration, PV01..PV15 row-validation and JOB_EXEC_* runtime boundaries without duplication. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L2.3 | Canonical projection with validation, quarantine and reprocessing |  | Build | D3; D5 | Core | R1 | Advances |  | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. Expected Runner-2 parent (not an observed commit parent): 4e0f1219ddbac3163bafe7ce510b62520683a77c |  | RE-ESTIMATE REQUIRED |  |  | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | UNCONFIRMED | UNCONFIRMED | UNCONFIRMED | UNCONFIRMED — closure-only remaining effort; prior 6/10/16 h superseded | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | 14-Sep snapshot supplemented by latest 15-Sep user-reported runner progress; no current-HEAD or runner-byte verification
T-101 | M2 | P2 | Quarantine retry, reprocess and Mapping Health completion | Frontend | Quarantine | Very Important | Complete the C2 Mapping Health page against Chapter 3 4.4 C2: issues grouped by code, example rows, and Reprocess after the mapping is corrected. The M1 version delivered the shape; this delivers the full class set and the retry semantics. v2.22.0 — Quarantine inspection API/UI and schema-drift enforcement. Keep one drift event authority and reuse current schemas/compatibility safely. v2.22.1 — Own the M2 B4 Importing monitoring surface as well as C2 quarantine/Mapping Health: show each real batch status, failure code/reason, progress/counts, last committed cursor and its watermark range; drill into durable batch/run evidence. Use the existing canonical import/job contracts. T-106 owns terminal-status truth; T-108 owns durable cursor/replay; T-125 owns operational metrics/API observability. No second status or cursor authority and no advanced M3 recovery UI is introduced. | Quarantine rows under three different codes, correct one mapping, reprocess, and confirm only the affected rows clear. The M1 continuity snapshot of this page must still match. v2.22.0 — GET quarantine list/detail filtered by code, dataset and batch with staging lineage/correction hint; tenant denial; remove mapped source object/field -> typed execution refusal and persisted C2 event; corrected reprocess uses declared version and records outcome. v2.22.1 — Drive B4 against a successful batch, a failed batch and a capped/partial batch; displayed outcome, counts, error and last committed cursor equal the canonical response after reload. A failed batch is never green; a retry/correction links to the same durable evidence. Tenant denial and empty/loading/failure states are asserted. Consume frozen T-106/T-108/T-125 response contracts for parallel UI work; final live integration is certified by T-247/T-150, not by a mock-only result. | 12 | Not Started | Worker 2 | T-099; T-100 | T-107; T-109; T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/UI feature | 2 | M2-P2 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-061 final M1 API/page contract + T-099 + T-100 canonical quarantine impleme... | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L2.3 | Canonical projection with validation, quarantine and reprocessing | L1.6; L1.2; L1.7 | Build | D2; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-265 owns B4/C2/C3 visual depth. Implement its applicable batch outcome/error/committed cursor and catalogue-driven quarantine list/detail/refusal/reprocess states under the existing T-101 scope; all row actions and counts use canonical tenant-scoped payloads. Do not limit the renderer to eight PV codes. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | PARTIAL REUSE; CURRENT EXPANDED SCOPE OPEN | 12 | 18 | 28 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Read API/filter/detail 3/4/6 + B4/C2/C3 UI 4/6/10 + drift/retry integration 3/5/8 + tests/closure 2/3/4. | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — MapQuarantineEndpoints Backend/PlantProcess.Application/Integration/Services/Staging/StagingRecordService.cs:85-110 — durable staging identity | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-102 | M2 | P2 | Identity resolution across sources | Backend | Genealogy | Very Important | Harden material identity resolution using material_aliases so the same physical material arriving under two different source identifiers becomes one canonical unit. The schema already supports this: material_units carries a unique key on (site_id, material_code) plus a filtered unique on (source_system, source_record_id), which makes projection idempotent without forbidding rows that have no source identity. | Import the same material under two different source identifiers and confirm one canonical unit results with both aliases recorded. Re-run the import and confirm no duplicate appears. | 8 | Not Started | Worker 1 | T-087; T-095 | T-103; T-107; T-109; T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.2 | M2-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 canonical plant schema + T-095 relationship/material identity authority. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L2.4 | Genealogy resolution and attribution |  | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | EXISTING ALIAS FOUNDATION; IDENTITY-SAFETY GAP | 4 | 7 | 12 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Scope-safe lookup/merge 2/4/7 + ambiguity/idempotency tests 1/2/4 + closure 1/1/1. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:244-264 — MapMaterialAliasAsync Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:721-744 — ResolveMaterialIdAsync Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialAliasConfiguration.cs:27-36 — composite unique Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialUnitConfiguration.cs:43-47 — site/source uniqueness | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-103 | M2 | P2 | Genealogy bidirectional walk hardening and weight proof | Backend | Genealogy | Very Important | Confirm the genealogy layer walks both directions on the customer's own keys and that attribution weights are enforced to sum to exactly 1.0 per child by the database trigger on genealogy_edges.contribution_weight numeric(9,6). v2.22.0 — Retain genealogy semantics and add explicit cyclic/self-edge protection at service and database boundaries. | Walk a chain backward and forward and confirm the same edges are traversed. Attempt an insert whose weights sum to 0.99 inside a transaction and confirm the trigger rejects it, then roll back. v2.22.0 — Negative controls: self-edge, two-node and longer cycles refused; ordered weighted genealogy valid paths remain accepted; no silent deletion of lineage. | 6 | Not Started | Worker 1 | T-095; T-102 | T-107; T-109; T-128; T-183 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 0.9 | M2-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095 + T-102 canonical relationship/identity authority. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L2.4 | Genealogy resolution and attribution |  | Harden | D3; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | SUBSTANTIAL FOUNDATION; ACCEPTANCE-CONTRACT MISMATCH | 4 | 6 | 10 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Weight-contract correction 1/2/3 + direct-DB/traversal negatives 2/3/5 + closure 1/1/2. Existing cycle logic is not new work. | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:27-69 — CreateEdgeAsync Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:95-124 — WouldCreateCycleAsync Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:55-68 — deferred weight check | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-104 | M2 | P2 | Projection provenance, exact-version stamping and idempotent reprojection | Backend | Projection | Critical | Complete the DF5 contract: source-shaped staging projects into the canonical plant model through the customer-authored versioned mapping, and every projected row records the mapping version that produced it. v2.22.0 — Absorbs T-105: Make reprojection idempotent and add the regression suite: reprojecting the same batch must not duplicate rows, and rolling a mapping back to a previous version must produce the earlier result exactly. T-261 owns the executor. This task owns canonical row-level definition/version provenance and replay effects, using that executor; it does not implement a competing MappingDefinition runtime. | Project a batch, change the mapping version, project again, and confirm each row records the version that produced it. No row may carry a null mapping version. v2.22.0 — Reproject the same batch three times and confirm row counts are unchanged. Roll a mapping back and confirm the canonical output matches the earlier snapshot byte for byte. Assert exact resolved Transformation version/hash per run and row, tenant/dataset/batch source lineage, no duplicate accepted effect and byte-identical deterministic business output on rollback. Clock/run metadata is compared separately from business-result equivalence. | 14 | Not Started | Worker 1 | T-090; T-095; T-099; T-261 | T-107; T-108; T-109; T-128; T-183; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.2 | M2-P2 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-090 canonical versioned mapping definitions + T-095 relationship authority ... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L2.3 | Canonical projection with validation, quarantine and reprocessing | L2.5 | Build | D3; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | REPLAY FOUNDATION IS NOT VERSIONED REPROJECTION | 8 | 14 | 22 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Row-version/provenance integration 3/5/8 + replay/rollback semantics 3/6/10 + negative tests/closure 2/3/4. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:168-181 — existing-row skip Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-249 — ResolveDeclaredTargetAsync | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-106 | M2 | P2 | Canonical jobs: target/version, scheduling, dependencies, cancellation and outcome truth | Backend | Jobs | Critical | Build on the M1 target_definition_id work: add the full version policy (pinned or current published), the job dependency graph, and cycle validation. v2.10.2 BOUNDARY CORRECTION — the pinned/current-published PUBLIC semantics are already frozen by T-064. This task performs canonical physical convergence: job_definitions FK -> definition_store(id) ON DELETE RESTRICT, target-version policy CHECKs/target-surface trigger against the canonical store, target_parameters persistence, plus job_dependencies DAG/cycle validation. Do not redesign T-064's visible contract. v2.20.0 EXECUTION-PLANE EXPANSION — replace the central job-type switch as the authority for manual execution. Each executable job family registers an executor capability through DI/registry metadata: supported/unsupported state, target definition kind, version policy, input contract and run capability. A new executor family must be addable without editing a central switch. Unsupported families refuse at definition/save or capability discovery with a typed reason rather than surviving until RunNow. v2.20.0 LAYER-B PLACEMENT RULING — scheduling count, repetition, iteration windows and control flow belong to governed Job orchestration. Do not add new FOR/WHILE-style board execution semantics. Existing T-242 saved definitions remain readable through compatibility handling, but new orchestration authority is the Job plane. v2.22.0 — Deliver one canonical Job authority for target/version/capability, schedule grammar and occurrence identity, due scheduling, dependency resolution, cooperative cancellation and terminal-status truth. Implement Design v4.10.3 Ch4 5.3.2a / 5.3.6. The scheduler produces due requests; existing admission admits them. T-107 owns bounded pools; T-261 owns the actual Transformation executor. Keep these as separately testable sub-deliverables inside T-106 rather than additional task IDs. An executor supplied by tests proves orchestration before T-261 is commissioned, so T-106 must not depend on T-261 or T-107 closure. | Declare a three-job chain, run it, and confirm order. Introduce a cycle and confirm it is refused at save time with a named code. Enumerate every job family exposed by the product and prove each is either backed by a registered executor or explicitly unavailable by typed reason. Register a test executor through DI and prove it runs without editing the orchestrator switch. The current 'no manual executor'/'not implemented yet' runtime fall-through is no longer reachable for an advertised executable job. Newly authored execution schedules express repetition/window/control-flow in the Job contract rather than creating a new Canvas FOR/WHILE node. A compatibility fixture for an existing T-242 loop definition remains readable and produces an explicit compatibility interpretation rather than data loss. v2.22.0 — Prove canonical schedule parsing/normalisation and UI next-occurrence parity; UTC/timezone and DST gap/fold rules; one atomic admission per tenant/job/schedule-revision/occurrence under racing workers; restart/missed ticks; invalid or unsupported schedule typed refusal; paused state persists. Cancel API is tenant/role-scoped, idempotent, reaches executor and records exactly one final outcome. Cancellation request is not completion acknowledgement. Define all-success, mixed, all-failed, no-work, cancelled and interrupted outcomes; one failed import batch cannot be hidden in an Ok run in either manual or worker path. Current-cycle and earlier-success reuse follow explicit allow_stale_reuse and age ceiling, with timestamps, policy and watermark in job_run_dependencies. Trigger-fires, wrong-kind/surface and actual orchestration evidence use disposable DB fixtures. Keep existing historical closure evidence; certify newly widened obligations separately. | 12 | Done | Worker 3 | T-064; T-089; T-090; T-252 | T-107; T-122; T-125; T-245; T-261; T-263 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract |  | M2-P2 | Consume accepted producer contracts; remaining dependencies: T-064; T-089; T-090; T-252. No private scheduler/definition authority. Source-present is not closure proof. | Own T-106/T-107/T-109 only after W1 producer contracts; no schema authority rewrites. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | 8b3eb5c89352a2779d87f9205700f19e7c9b3e25; a5451dbaf6b55183fe65e2c626c49fdef85bd986 |  | L2.6 | Job definition, scheduling, execution monitor and history | L2.5; L2.7; L1.7 | Build | D3; D4; D5 | Core | R1 | Advances | 8b3eb5c89352a2779d87f9205700f19e7c9b3e25; a5451dbaf6b55183fe65e2c626c49fdef85bd986 | RE-ESTIMATE REQUIRED — prior Hours/P80 preserved in Estimate Review; not zero remaining effort. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | BASELINE COMMITS PROVEN; CURRENT WIDENED ACCEPTANCE OPEN | Original corrective run returned GREEN with22 corrective,26 foundation,84 target-regression and15 architecture tests in24 owned paths;CENTRAL freeze after review. Later v2.22 schedule/cancel/freshness/outcome-truth scope is not closed by a10Sep run. Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review. |  | RE-ESTIMATE REQUIRED |  |  | ORIGINAL CONTRACT CLOSED; EXPANDED RUNTIME OBLIGATIONS OPEN | 18 | 28 | 44 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Schedule/parser/due-work 8/12/18 + freshness/outcome policy 4/6/10 + cancellation consumer integration 2/4/6 + targeted service/DB tests and runner 4/6/10. Original completed contracts excluded. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobDefinitionService.cs:275-297 — schedule validation Backend/PlantProcess.Workers/Worker.cs:72-108 — fixed cadence loops Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:33-39 — no age/tolerance input Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:85-91 — Satisfied result Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-146 — terminal-state switch Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:262-276 — import result mapping | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-107 | M2 | P2 | Dual-predicate admission, bounded worker pools and the three ML execution lanes | Backend | Jobs | Critical | Replace the old single weighted-pool assumption with the frozen resource contract. Each lane has max_concurrency and resource_capacity; admission requires both running_count < max_concurrency and sum(compute_weight)+candidate <= resource_capacity. The logical ml class resolves to ml.training, ml.batch_scoring and ml.online_scoring. Online capacity is hard-reserved and unavailable to training or batch. Keep this platform-level scheduler generic; Worker 3 supplies the ML job classes and later integration tests, but this task must not wire any new AI runtime into the M1 presentation path. v2.10.2 MEASUREMENT RULING — this task implements the configurable dual-predicate admission mechanism and three-lane isolation. Test values may prove satisfiability, but no max_concurrency/resource_capacity/reserved fraction is a production-selected value here. Site values remain benchmark outputs owned by T-155/T-159. v2.20.0 BOUNDED-PARALLELISM EXPANSION — the same admission authority owns bounded parallel execution for eligible non-ML job families. The current serial import-loop behavior is replaced by queue/admission scheduling that respects both max_concurrency and resource_capacity. Do not implement unbounded Task.WhenAll/Parallel.ForEach. Per-family limits, cancellation, fair queueing and hard online reservation remain explicit. | Prove a declared job can be admitted under a satisfiable configuration and a too-heavy job is refused by name. Saturate training and batch and prove an online-scoring job still admits inside its reservation. Prove batch never enters the online lane and the same compute_weight is never used as a concurrency count. Existing import/projection/analysis/report behaviour remains green. The acceptance report labels resource values as TEST_CONFIGURATION unless they come from the named production/site benchmark manifest. No code default is presented as the final capacity decision. Run multiple slow import/analysis jobs and prove concurrency rises above one only up to the configured bound, then queues. Queueing must not increase memory without bound; cancellation frees capacity; a too-heavy job remains queued/refused by named policy. A negative-control implementation using unbounded fan-out must make the gate red. | 16 | Not Started | Worker 3 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-106 | T-122; T-125; T-141; T-187; T-192 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P2 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 canonical job contract + T-095..T-105 canonical data/relationship path;... | Own T-106/T-107/T-109 only after W1 producer contracts; no schema authority rewrites. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L8.4 | Execution lanes, admission and resource isolation | L2.6 | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 16 | 1.8 | TIMERS EXIST; GOVERNED JOB POOLS NOT ESTABLISHED | 12 | 20 | 32 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Pool/admission implementation 6/10/16 + lane/worker integration 3/5/8 + saturation/cancel/closure tests 3/5/8. | Backend/PlantProcess.Workers/Worker.cs:72-108 — ExecuteAsync cadence Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:76-107 — family capability vs capacity | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-108 | M2 | P2 | End-to-end delta correctness: source cursor, load protection, replay and projection watermark | Backend | Delta propagation | Critical | Today only import is incremental. Chapter 4 5.3.9 requires every downstream stage to be delta-scoped. Add the stage_watermarks table and make canonical projection delta-scoped against it. The arithmetic that justifies this: a naive full scan for one Pro-tier customer is 481 TB per day, while delta-scoped is 5 to 20 GB, a ratio of 24,000 to 1. v2.22.0 — Own acquisition-to-projection delta correctness: typed total-order cursor with source-stable tie-break for non-unique watermarks; one invariant provider-native ordering contract; durable cursor/staging/receipt atomicity; replay-safe accepted effects; per-dataset/profile budget resolution constrained by installation/source ceilings; apply pre-read budget/window/rate/concurrency/timeout checks on incremental as well as preview reads. Do not replace a stricter parent ceiling with a looser child override. Source native ordering and source-version identity govern legitimate updates. Retain existing stage-watermark and delta-projection duties; T-110 owns the advanced M3 parallel chunk engine. | Change one source row and confirm projection processes a bounded delta rather than a full scan, evidenced by rows-scanned telemetry. v2.22.0 — Use more equal-watermark records than three page limits, numeric/timestamp/composite cursors, declared key changes, source updates, no change, de-DE/en-US serialization, crash before and after commit and racing workers. Prove no missed rows/no duplicate accepted source revision, and checkpoint advanced only with durable effects. Over-budget incremental reads issue no source query. Replay of a partially failed import preserves legitimate later versions of the same business key. One changed source row produces bounded downstream work with recorded counts. |  | Not Started | Worker 1 | T-099; T-104 | T-109; T-110; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract |  | M2-P2 | Consume accepted producer contracts; remaining dependencies: T-099; T-104. No private scheduler/definition authority. Source-present is not closure proof. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L2.8 | Delta propagation law | L1.3; L1.1; L1.7 | Build | D3; D4; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — prior Hours/P80 preserved in Estimate Review; not zero remaining effort. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | IMPLEMENTED DELTA FOUNDATION WITH CONFIRMED CORRECTNESS GAPS | 22 | 34 | 52 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Tuple contract+reader adaptations 8/12/18 + budget enforcement 4/6/9 + durable staging/replay+projection token 5/8/13 + adverse-boundary tests/closure 5/8/12. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — read-path selection Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — row/cursor handling Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:236-280 — source identity and MaxCursor Backend/PlantProcess.Infrastructure/Connectors/PostgreSql/PostgreSqlConnector.cs:181-206 — scalar LIMIT query Backend/PlantProcess.Application/Integration/Protection/ThrottlingDataSourceReader.cs:36-70 — unequal protection Backend/PlantProcess.Infrastructure/Integration/Protection/OptionsSourceLoadBudgetProvider.cs:21-24 — global budget Backend/PlantProcess.Infrastructure/Persistence/Configurations/Integration/StagingRecordConfiguration.cs:31-42 — existing within-batch uniqueness Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:58-73 — current weak continuation assertions | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-109 | M2 | P2 | Delta-scoped feature refresh and analysis, with telemetry and ML hand-off | Backend | Delta propagation | Critical | Extend the stage-watermark mechanism into the canonical feature refresh and analysis path. The task owns delta discovery, dirty-feature identification and telemetry only; training must never read feature_store directly. Expose a bounded changed-population contract that Worker 3's Snapshot Materialiser consumes later. Do not add temporary M1/presentation schema dependencies. | Insert one bounded delta and prove only affected feature rows and analyses are recomputed. Record rows scanned, rows changed and Scan Amplification. Assert no training/encoding component is reachable from this task and the output contract contains no customer table name. | 6 | Not Started | Worker 3 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-108 | T-110; T-136; T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 0.9 | M2-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095..T-105; T-108 | Own T-106/T-107/T-109 only after W1 producer contracts; no schema authority rewrites. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L2.8 | Delta propagation law | L4.3 | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 0.9 | REUSABLE CALCULATION FOUNDATION; DELTA CONSUMER NOT PROVEN | 6 | 10 | 18 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Scope resolution/integration 3/5/9 + telemetry/handoff 1/2/4 + idempotent/late-data tests 2/3/5. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-217 — available source delta boundary Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:85-113 — governed automated path | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-207 | M2 | P2 | Connector capability truth: stop advertising unimplemented browse/read/subscription | Acquisition | Connector truth | Critical | Make connector capability metadata executable truth. Current OPC/historian configuration validation or deterministic sample generation must not advertise live browse/bounded-read/subscription unless the connector build executes and tests that operation. | Against the current implementation, unsupported browse/read/subscription report false/unavailable and attempts return typed OT01 rather than fabricated data. Add a contract test that makes any future advertised capability fail until an executable implementation passes. | 6 | Done | Worker 1 | T-201 | T-150; T-224; T-247; T-254; T-266 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend contract | 2.25 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Connector metadata/API contract and tests. | T-224..T-226 later may flip capabilities to true only by passing this contract. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L1.4 | Connector capability truth |  | Build | D1; D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 2.25 | SOURCE CORROBORATES CLOSED TRUTH CONTRACT | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Closed honesty contract retained; separate future live acquisition. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — HistorianConnectorCapabilities | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-212 | M2 | P2 | Integrate aggregation semantics into Layer-A widget/query execution | Backend/Frontend | Dashboard query semantics | Critical | Make dashboard/query aggregation resolve the canonical KPI/parameter semantics and certified kernel/database implementation. Remove raw-cap-before-aggregate and implicit average fallbacks in all customer-facing measures touched by this contract. | Persisted-definition replay on discrete and continuous fixtures proves exact known answers; no raw row limit is applied before aggregate; AG01/AG02 render typed Blocked/Refused rather than API 500. Query plan performs bounded server-side aggregation. | 10 | Not Started | Worker 2 | T-202; T-210; T-211; T-092; T-234; T-235; T-236 | T-150; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Cross-layer integration | 5.1429 | M2-P2 | T-202 + T-210/T-211 + T-092 + committed T-234/T-235/T-236. | Dashboard query service/executor + focused frontend state mapping. | Consumes W1 semantics and W3 kernel; no independent aggregation rules. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L3.4 | Widget catalogue and intelligence visualisation | L5.3; L4.2 | Build | D1; D2; D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 5.1429 | AUTHORITY EXISTS; PRODUCTION QUERY CONSUMPTION GAP | 6 | 9 | 14 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Query integration 3/5/8 + known-answer/refusal tests 2/3/4 + closure 1/1/2. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — ResolveAsync Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — not analytics mathematics | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-213 | M2 | P2 | Customer Data Intake and Capability Assessment authority | Onboarding | Customer data assessment | Critical | Create a versioned assessment workflow/report for an unknown customer: source inventory, entity/equipment map, time model, identity/join strategy, parameter catalogue, KPI candidates, references, aggregation gaps, data quality, historical coverage, reconciliation/ML eligibility, OT trial requirements and missing information. The intake MUST also capture same-calendar-window manual vs machine history availability, transition/changeover definitions and stabilisation rules, sequence/campaign boundaries, setup/preparation evidence, and customer objective sets/trade-off preferences. Accepted results become normal definitions/mappings; the assessment is not a second authority. | Run against one foreign/customer-shaped fixture and produce a complete report with explicit UNKNOWN/MISSING states, including regime-context readiness and multi-objective readiness. Same-window reconciliation evidence is separately reported. No product-code change is made for customer vocabulary. Re-run after one new source/field creates a new assessment version and diff. | 8 | Done | Worker 2 | T-201; T-206 | T-227; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend / product workflow | 3.2 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Onboarding assessment service/report; no customer-specific schema code. | Mappings/definitions become canonical through existing authorities; report does not become a shadow registry. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | 2748c7fba8a5c4763bc19112ce57e484cea5b9bb — subject not recovered | 2026-08-31 | L1.2 | Dataset registration and source selection | L1.1; L7.8 | Build | D1; D5 | Core | R1 | Advances | 2748c7fba8a5c4763bc19112ce57e484cea5b9bb — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 3.2 | SOURCE CORROBORATES CLOSED PRODUCER | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Original producer closure retained; no duplicate intake engine. | Backend/PlantProcess.Api/Endpoints/CustomerAssessmentEndpoints.cs:86-125 — assessment routes and tenant gate | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-224 | M2 | P2 | Production OPC UA edge runtime: endpoint security, certificates and session lifecycle | Acquisition | OPC UA edge | Critical | Implement real OPC UA client runtime inside the customer-side collector boundary: endpoint discovery/selection, security policy negotiation, application certificate/trust management, authenticated session lifecycle and read-only enforcement. Core never gains plant-network credentials/routes. v4.11.0 SCOPE DELTA — The session runtime consumes the governed Connection/Dataset/field/configuration identities from T-268 and must publish negotiated/effective source capability evidence without turning source settings into product guarantees. No native PLC driver is implied by OPC support. | Against a real SDK test server, establish trusted and rejected sessions, rotate trust, reconnect after server restart and prove no write/control verb/path exists. Capability metadata remains false until this task and downstream browse/subscription tasks pass. Additional acceptance: operation-level capability receipt names endpoint/source profile, security/trust result and negotiated limits; offline/takeover behavior must not create a second active capture owner. Source credentials remain collector-side only. | 12 | Not Started | Worker 3 | T-207 | T-153; T-225 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | External/site + backend | 7.2 | M2-P2 | Release 1 MUST — start after T-207 connector-truth authority. Site/customer OT certification may require customer access, but the executable production OPC UA runtime itself cannot be deferred past M2. | Customer-side edge agent/OPC adapter only. | T-225 consumes session adapter; site certification remains T-153/T-227-like acceptance, not hidden in code. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | CENTRAL 04-Sep-2026: remove the contradictory 'after 30-Sep demo' gate. M2 is genuine early production and its P2 outcome includes real read-only OPC UA runtime. |  |  | L1.8 | OPC-UA / historian / edge acquisition |  | Harden | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-266 supplies OPC profile/session/trust target and refusal designs, with Worker 1 technical review. This is a contract handoff, not a full-design completion prerequisite for backend implementation. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED — v4.11.0 scope delta |  |  | DESIGN v4.11.0 SCOPE DELTA — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED AFTER v4.11.0 | Original task closure remains open; new acceptance must be estimated from current source. | Design v4.11.0 + Industrial Integration review; current implementation source must be preflighted | 16-Sep-2026 design authority; no live source/runtime certification performed
T-225 | M2 | P2 | Production OPC UA edge runtime: browse, tag registration, subscription and monitored items | Acquisition | OPC UA edge | Critical | Implement namespace browse, tag selection/registration, subscriptions/monitored items, sampling/publishing interval and deadband configuration behind generic collector contracts. v4.11.0 SCOPE DELTA — Browse/tag registration emits stable field identities consumed by T-268; monitored-item sampling/publishing/filter settings remain protocol mechanics and must not be presented as PPIQ durable-record semantics. T-270 owns Time/Value-change/Trigger-counter business recording behavior. | Browse a test namespace, register N tags, subscribe, receive changed values and prove disconnect/reconnect resumes without fabricated deterministic samples. Read-only operations only. `supportsTagBrowse`/`supportsSubscription` become true only after these executed tests. Additional acceptance: Namespace URI + identifier identity survives namespace-index change; server-revised settings are recorded; source-side filter pushdown is accepted only when semantics match the authored recording policy; no ordinary multi-tag read is labelled a PLC-atomic snapshot. | 12 | Not Started | Worker 3 | T-224 | T-153; T-226 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | External/site + backend | 7.2 | M2-P2 | T-224. | Edge OPC adapter + tag registry integration. | T-226 consumes typed acquired values; no core API direct OPC connection. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L1.8 | OPC-UA / historian / edge acquisition |  | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-266 supplies browse tree, tag registration, bounded-read/subscription and keyboard/validation designs. Backend development follows frozen contracts in parallel; capability flags still require runtime proof. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED — v4.11.0 scope delta |  |  | DESIGN v4.11.0 SCOPE DELTA — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED AFTER v4.11.0 | Original task closure remains open; new acceptance must be estimated from current source. | Design v4.11.0 + Industrial Integration review; current implementation source must be preflighted | 16-Sep-2026 design authority; no live source/runtime certification performed
T-226 | M2 | P2 | Production OPC UA edge runtime: quality/timestamps, recovery and spool-to-canonical proof | Acquisition | OPC UA edge | Critical | Preserve OPC StatusCode/quality plus source/server timestamps, integrate reconnect/sequence-loss handling and existing store-and-forward spool, map acquired values into canonical observations under Source Time Authority. v4.11.0 SCOPE DELTA — OPC transport/recovery now hands durable observations through T-270/T-272/T-275: policy-state correctness, accepted-record identity, finite sealed batches during a continuous session, gap truth and replay-only behavior for a superseded collector. This task remains the OPC end-to-end proof owner, not a second storage/Job authority. | Good/bad/uncertain quality and source-vs-server timestamp cases land correctly; network interruption queues locally and resumes idempotently; duplicate replay does not duplicate canonical observations; customer-core direction remains one-way. Additional acceptance: continuous session remains active while finite batches become projection-ready; same record identity+same content is idempotent and different content conflicts; edge/core outage boundaries are distinguished; Bad/Uncertain quality and source/server/capture/ingest times survive; no fabricated payload for missing counter events. | 12 | Not Started | Worker 3 | T-225; T-233; T-270; T-272; T-275 | T-150; T-153 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | External/site + backend | 7.2 | M2-P2 | T-225 + T-216 Source Time Authority. | Edge spool/acquisition mapper + canonical ingest contract. | T-153 real-source connector certification consumes this implementation; do not call implementation itself site-certified. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L1.8 | OPC-UA / historian / edge acquisition |  | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-266 supplies quality/time/spool/reconnect/replay evidence presentation. The source-time and idempotency rules are unchanged; labelled design fixtures are not test-server proof. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED — v4.11.0 scope delta |  |  | DESIGN v4.11.0 SCOPE DELTA — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED AFTER v4.11.0 | Original task closure remains open; new acceptance must be estimated from current source. | Design v4.11.0 + Industrial Integration review; current implementation source must be preflighted | 16-Sep-2026 design authority; no live source/runtime certification performed
T-232 | M2 | P2 | Persist Performance Reference authority and projections | Backend / Database | Reference persistence | Critical | Persist the frozen T-214 Performance Reference contract, including declared standards/targets/envelopes, deterministic scope precedence, effective dating, directionality, provenance and projections from existing specifications/operating limits. No second reference authority. | Migration/replay green; Global/Site/Equipment reference precedence and effective-date replay pass; equal-authority ambiguity remains RF01; existing specification/limit projections resolve through one read authority. | 6 | Not Started | Worker 1 | T-090; T-231; T-214 | T-215 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema authority | 2.55 | M2-P2 | T-090 + T-231 + committed T-214 contract. | performance reference tables/projections/API. | T-215 consumes persistence; no local reference math. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L9.1 | Performance Reference |  | Build | D1; D3; D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 2.55 | TARGET AUTHORITY NOT LOCATED IN SUPPLIED SNAPSHOT | 5 | 8 | 13 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Persistence/resolution adapter 2/4/7 + projections/refusal tests 2/3/4 + closure 1/1/2. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — existing semantic infrastructure only | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-233 | M2 | P2 | Persist Source Time Authority and observation timestamp provenance | Backend / Database | Temporal authority persistence | Critical | Persist the frozen T-216 Source Time Authority contract per source/site and preserve source/server/ingest timestamp provenance on observations. Own migrations, tenant-safe keys and canonical read API; no settings UI and no alignment algorithm here. | Two sources with different declared timestamp origins and known skew persist/replay correctly; source/server/ingest timestamps survive ingestion; tenant isolation passes; the API exposes exactly the T-216 contract. | 5 | In Progress | Worker 1 | T-087; T-090; T-216 | T-221; T-226 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema authority | 2.125 | M2-P2 | T-087 + T-090 + committed T-216 contract. | source_time_authorities/observation timestamp provenance/API. | T-221/T-226 consume canonical persistence; T-217 kernel does not wait. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L1.5 | Acquisition provenance and source lineage | L5.5 | Build | D1; D3; D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 5 | 2.125 | TIME KERNEL EXISTS; PERSISTENCE/CONSUMER WORK REMAINS | 5 | 8 | 14 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Persistence/API adapter 2/3/6 + consumer binding 1/2/4 + ambiguity/timezone tests/closure 2/3/4. | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-97 — Resolve / ResolveAs Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:184-210 — current material time fields | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-235 | M2 | P2 | Persist transition/stabilisation authority and regime context | Backend / Database | Process regime persistence | Critical | Persist process_transition_definitions and process_transition_events plus effective-dated stabilisation policy, provenance and query API under the canonical definition/tenant authority. Do not model changeover as downtime by default; overlap is allowed and explicit. v2.22.0 — Wire existing TransitionAwarePoolingGuard into production statistics/correlation using persisted regime authority. This is M2 correctness, not a claim that every customer necessarily has transitions. | Fresh migration/replay green. A customer-authored transition definition and event round-trip with scope/from-to context/stabilisation rule; no shipped industry values. Querying an interval returns exact transition/stabilisation overlaps and evidence. v2.22.0 — Declared transitions/stabilisation are excluded or stratified per policy; undefined required regime context refuses rather than pooling; declared no-transition case supported with evidence; known-answer production-path test and provenance. | 8 | Not Started | Worker 1 | T-090; T-231; T-234 | T-164; T-212; T-237; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema authority | 3.4 | M2-P2 | T-090 + T-231 + committed T-234 contract. | process transition tables/API/migrations. | T-237/customer onboarding consume committed persistence; do not redesign contract. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L5.4 | Regime correctness |  | Build | D1; D3; D4; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | KERNELS COMPLETE; CURRENT PRODUCTION INTEGRATION OPEN | 6 | 11 | 18 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Persistence/regime adapter 2/4/7 + live-statistics integration 2/4/6 + adversarial tests/closure 2/3/5. | Backend/PlantProcess.Analytics.Core/Kernel/Regime/TransitionAwarePoolingGuard.cs:24-79 — Admit Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — time interpretation | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-241 | M2 | P2 | Canvas executable block contract, typed ports and graph validation | Frontend | No-code authoring | Important | Generalise the typed-port and graph semantics already proven in the M1 SharedAuthoringShell/VisualJoinCanvas slice into the production canvas contract. Reuse the existing shell and ports; do not create a second canvas. Define executable block kinds, typed input/output ports, required-port rules, graph validation and genericity constraints. No block or port may carry industry vocabulary. | Architecture test proves one shared canvas contract. Typed-port known answers pass; an unconnected required port returns a typed refusal; incompatible ports refuse before execution; no industry noun/default grain appears in the generic block contract. | 10 | Done | Worker 2 | T-032; T-201 | T-242; T-243; T-247; T-248; T-253; T-261 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Post-Sep product completion |  | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend shared authoring shell, canvas graph/ports only. | Reuse M1 SharedAuthoringShell and existing typed-port assets. No second canvas component. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | eb7fb2ab — subject not recovered |  | L3.6 | Board semantics, typed ports and property inspection |  | Build | D1; D2; D4; D5 | Core | R1 | Advances | eb7fb2ab — subject not recovered | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 |  | SOURCE CORROBORATES CLOSED GRAPH CONTRACT | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Closed graph contract; zero original remainder. | Frontend/PlantProcess.Web/src/authoring/graphSemantics.ts:22-40 — typed-port authority Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — capability separation | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-242 | M2 | P2 | Canvas production block library: relational, arithmetic, logic, window and governed aggregate | Frontend | No-code authoring | Important | Complete the executable block library behind the existing catalogue: source/filter/join, arithmetic, comparison, boolean logic, branch/window and governed aggregate blocks. Aggregate blocks resolve the canonical aggregation semantics authority and never default to Average. Include production arithmetic/comparison/Boolean blocks, IF/ELSE, ForEach, RepeatN and WhileBounded. WhileBounded requires max_iterations, runtime budget and cancellation; unbounded loops cannot publish. | Every executable block has deterministic known-answer and type-mismatch tests. Aggregate blocks consume the canonical aggregation contract and refuse AG01 when semantics are undeclared. Unsupported catalogue entries remain visibly unavailable rather than silently no-op. Known-answer graphs prove +,-,*,/, comparisons, AND/OR/NOT, IF/ELSE, ForEach, RepeatN and bounded While. A graph with no finite loop bound refuses validation. | 16 | Done | Worker 2 | T-241; T-210 | T-243; T-247; T-261 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Post-Sep product completion |  | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Canvas block registry and executable block nodes. | Do not duplicate analytics kernels; blocks call governed Layer-A/Layer-B contracts. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | CENTRAL 04-Sep-2026: remove 'After 30-Sep MUST lane'. A Release-1-MUST task cannot be scheduled after its own release date. | b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 — final: T-242 close governed aggregate and window block contracts | 2026-09-08 | L3.6 | Board semantics, typed ports and property inspection |  | Build | D2; D5 | Core | R1 | Advances | b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 — final: T-242 close governed aggregate and window block contracts | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 16 |  | CLOSED CONTRACT; DOWNSTREAM EXECUTION NOT IMPLIED | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Closed library/contract scope, not all future execution. Do not convert missing downstream execution into a new T-242 estimate. | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — one catalogue and separate capabilities Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — handoff boundary Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:49-77 — AG01 behavior | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-243 | M2 | P2 | Canvas persistence, immutable versioning and reopen/edit round-trip | Frontend | No-code authoring | Important | Persist the shared canvas graph through the unified definition_store/definition_versions authority. Save block positions, typed connections, parameters and purpose; reopen and edit a published/draft version under the existing lifecycle. No canvas-specific shadow store. v2.22.0 — Extend the existing saved-board lifecycle to transactional relationship publication. Publish via existing IRelationshipPublicationService; derive only customer-declared joins/grains/attribution, not every arbitrary join inferred as a business relation. No shadow store. Legacy VisualMapper must route through canonical lifecycle or be retired compatibility-safely. | Create/save/reopen/edit round-trip preserves semantic graph content; version history is immutable; rollback selects an existing version; no second definition lifecycle/table is introduced. The governed output target/Analysis Subject identity introduced by T-253 is part of the semantic round-trip and cannot collapse to a hardcoded material target. v2.22.0 — Publish a declared multi-member relationship and verify resolver consumption; republish supersedes not deletes; rollback/history remains explainable; simulated failure leaves neither a partially published definition nor a partially retired/emitted relationship set. Retain existing board/hash/Graph-SQL/reopen evidence; unproven new requirements do not erase previous implementation. | 12 | Done | Worker 2 | T-241; T-242; T-089; T-090; T-253 | T-245; T-246; T-247; T-248; T-261; T-262 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Post-Sep product completion | 4.8 | M2-P2 | Consume accepted producer contracts; remaining dependencies: T-241; T-242; T-089; T-090; T-253. No private scheduler/definition authority. Source-present is not closure proof. | Frontend canvas persistence + definition-store client contracts. | No canvas-specific persistence schema. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | 6f65bba1 |  | L2.5 | Unified definition store and immutable target/version governance | L3.5; L3.6; L2.2 | Build | D3; D4; D5 | Core | R1 | Advances | 6f65bba1 | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — Use T-265 C1/S1 selected-block, inspector, typed-port, validation/publish/reopen and SQL-mode handoffs. Shared C1/S1 shell is valid; prove semantic mode behavior rather than arbitrary visual differences. No change to canonical definition/relationship authorities. | 0 |  | BASELINE CLOSED; RELATIONSHIP-PUBLICATION EXTENSION UNPROVEN | Executed ancestry proves the original board/history/reopen closure. Later v2.22 transactional relationship publication remains a separate outstanding acceptance slice. Do not reimplement the saved-board baseline. Exact full SHA/date not recovered. Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors. |  | RE-ESTIMATE REQUIRED |  |  | ORIGINAL REOPEN CLOSED; ADDITIONAL PUBLICATION INTEGRATION OPEN | 5 | 9 | 15 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Declared relationship adapter 2/4/7 + atomic/rollback and compatibility tests 2/4/6 + closure 1/1/2. Reopen board work costs zero here. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — canonical graph/board content Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:265-333 — publish transaction Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — existing publication seam | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-244 | M2 | P2 | SQL-mode production convergence: compile, validate, bounded dry-run and definition persistence | Frontend | No-code authoring | Important | Converge the SQL mode already delivered in T-035/T-036 onto the canonical M2 definition store and production query budgets. Reuse SafeSqlValidator and the existing editor; do not rebuild them. Add compile/validate-before-run, bounded dry-run/result preview, row/scan/cost telemetry and canonical persisted definition/version identity. | The existing SQL safety suite remains green. An unvalidated or unbounded statement never executes. Dry-run returns bounded rows plus telemetry. Save/reopen uses the unified definition store. No duplicate SQL editor or validator is introduced. | 14 | Done | Worker 2 | T-035; T-036; T-089; T-090 | T-245; T-247; T-248; T-253 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Post-Sep product completion |  | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | SharedAuthoringShell SQL mode + canonical definition API. | Preserve SafeSqlValidator/editor behaviour and tests. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | 4d32c6b10b4605aeb6e0705ad03537d563125652 — T-244 close canonical Canvas lifecycle and selection model | 2026-09-04 | L3.5 | One authoring shell, five purposes, two modes | L3.7 | Converge | D2; D4; D5 | Core | R1 | Advances | 4d32c6b10b4605aeb6e0705ad03537d563125652 — T-244 close canonical Canvas lifecycle and selection model | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 14 |  | SOURCE CORROBORATES CLOSED SQL FOUNDATION | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Closed SQL validation/persistence scope only. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:173-205 — ForSql Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:297-333 — SQL publish path Frontend/PlantProcess.Web/src/api/canvasApi.ts:118-155 — SQL run/save API adapter | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-245 | M2 | P2 | Canvas-to-job compilation, binding, run monitor and per-block evidence | Frontend | No-code authoring | Important | Compile a validated canvas definition into the governed job/runtime contract, bind the declared target/version, launch it, monitor progress and correlate per-block diagnostics/evidence to the run id. Job target/version and dependency policy remain owned by the canonical job authority. Bind to the already accepted job runtime; do not wait for Release-2 advanced orchestration. | A validated canvas runs through the normal job API; each block is traceable to run diagnostics/evidence; a block failure is isolated and typed; target/version follows T-106; no private canvas scheduler is created. Capability discovery refuses compilation when the target job family has no registered executor; there is no late RunNow surprise. | 12 | Not Started | Worker 2 | T-243; T-244; T-106; T-261; T-262 | T-247; T-248 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Post-Sep product completion | 5.1 | M2-P2 | QUEUED after T-261 closure; current mutation sequence is T-099 → T-100 → T-261 → T-245. T-245 consumes the proven executor/runtime and per-block evidence, never recreates them. Retain all listed canonical prerequisite contracts. | Canvas compiler/job binding + run monitor only. | T-106 remains job policy authority. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L3.8 | Canvas → compile → governed job → run → per-block evidence | L2.6 | Build | D2; D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — Use T-265 run/schedule/cancellation UI handoffs; cancellation acknowledgement is not a terminal Cancelled result until the executor/runtime records it. Render exact resolved version, failure counts and evidence, not a browser-derived success. | 1 |  | QUEUED — T-261 NOT CLOSED; NO NEW IMPLEMENTATION OR LIVE RUN CLAIM | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 5.1 | BINDING WORK NOT COMMISSIONED; REUSE PRODUCER CONTRACTS | 6 | 10 | 16 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Binding/API/UI 3/5/8 + evidence/cancel views 1/2/4 + integration/negative tests 2/3/4. | Frontend/PlantProcess.Web/src/api/canvasApi.ts:111-155 — current save/preview/publish surface Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-124 — non-executable target families | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-247 | M2 | P2 | First-customer Day-1 Golden Journey and same-binary onboarding proof | Data Integration | Customer onboarding | Critical | Using the customer's own source shape/configuration, prove the same compiled product can create/test a DB Link, browse/preview, map/configure, prepare in Canvas, validate/dry-run, save/version, compile/bind to a Job, run/monitor/log, project canonical data and open a working BI result with zero customer-specific product code. | One end-to-end evidence pack proves zero C# diff, zero TypeScript diff and zero product-SQL diff; configuration/metadata only. The customer-shaped journey completes through product surfaces and replays deterministically. The evidence pack also proves the customer-facing connector availability text comes from executable capability truth, the authored output target is customer-shaped/governed, and no unapproved material-specific/public-schema runtime dependency is required. v2.23.0 — T-265/T-266 designs are accepted before the release walkthrough. Re-run the same-binary customer journey against real governed services after UI integration: source test/cursor/import, authored field map and relationship publish, exact version execution/cancel/failure, quarantine evidence and reprocess, selected/possible/excluded propagation, applicable table navigation/export and grounded Assistant. Screenshots must identify actual runtime versus prototype. Live acceptance cannot be satisfied by a Figma import, label-presence script or template count. | 12 | Not Started | Worker 2 | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235; T-262; T-125; T-265; T-266; T-274 | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Customer configuration / integration | 5.1 | M2-P2 | T-213 complete + T-092 green. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Configuration/mapping/registry definitions and customer-shaped demo profile; no product source files unless a generic defect is found. | If onboarding requires C#/TypeScript/product-SQL changes, stop and raise a generic product gap; do not patch around it. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate | L1.1; L1.2; L2.3; L3.8 | Build | D1; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 5.1 | RELEASE ACCEPTANCE NOT EXECUTABLE BEFORE PRODUCERS | 8 | 14 | 22 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Fixture/setup/data preparation 2/4/6 + actual connected acceptance and evidence 4/7/11 + triage/replay/closure 2/3/5; remediation implementation excluded. | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — concrete broken journey seam Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:32-73 — earlier tests are not full new journey proof | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-253 | M2 | P2 | Shared authoring governed output-target canonical-content contract | Frontend | No-code authoring | Critical | Correct the shared Canvas/SQL authoring output-target contract across both representations. The governed output identity is the CANONICAL ENTITY NAME from ICanonicalEntityCatalog (for example `QualityEvent`), never a physical relation name such as `canonical_material_units` and never an overloaded Analysis Subject key. Add a representation-independent root `outputTarget` to hashed Canvas canonical content for new Graph and SQL saves. For Graph, retain `graph.targetEntity` for T-242/backward compatibility but require it to equal the root outputTarget on new writes. For pre-T-253 Graph content lacking the root key, Read may derive outputTarget from the existing graph.targetEntity; for pre-T-253 SQL content lacking it, return null and do not fabricate a target. Re-saving an old definition after selecting/deriving the governed target creates a new immutable version because the canonical hash legitimately changes; previous versions remain untouched. Expose a minimal read-only enumeration from ICanonicalEntityCatalog through the existing AuthoringSupport endpoint group so the shell can populate a governed target picker without using MappingDefinitionService.AllowedTargetEntities. Server-side save validates the supplied outputTarget against the canonical catalog. Use StandardP2Select and conforming accessible caption/control semantics; SharedAuthoringShell currently has zero raw-control baseline. Do not change DB topology, mapping AllowedTargetEntities, Analysis Subject persistence, job runtime or unrelated charts. v2.20.3 TARGET-ELIGIBILITY RULING — enumeration of every mapped canonical entity is NOT a valid picker authority. Introduce one explicit model/type-sourced capability predicate for entities that are legal canonical projection/authoring targets: the marker interface `ICanonicalProjectionTarget` on the canonical entity type. This is the exact v2.20.3 implementation ruling; do not substitute an EF annotation or schema heuristic. ICanonicalEntityCatalog enumerates only mapped, uniquely named entities carrying that capability when serving the output-target picker, and exposes an `IsProjectionTarget`/equivalent validation path. Do not infer eligibility from schema alone: current legitimate targets include configuration/reference entities such as ParameterDefinition and DefectCatalog that are not in ppiq_plant, while ppiq_plant also contains analytical/result entities that must not become import/authoring targets automatically. The capability is the authority; physical schema/logical family is a consistency check, not the eligibility rule. | 1) Current-source preflight first verifies T-244 (`4d32c6b10b4605aeb6e0705ad03537d563125652`) is an ancestor of current HEAD; if not, STOP and return to CENTRAL. 2) New Graph save: selected canonical entity appears as root outputTarget and graph.targetEntity, values match, save/reopen preserves it. 3) New SQL save: selected canonical entity is hashed root outputTarget and save/reopen preserves it. 4) Existing pre-T-253 Graph with no root outputTarget reopens by compatibility derivation from graph.targetEntity; when re-saved it creates a new immutable version and leaves old content/hash untouched. 5) Existing pre-T-253 SQL with no target reopens with null target and cannot fabricate one; user must select a governed target before a target-required save. 6) Invalid/non-catalog output target is refused server-side with a typed reason. 7) Picker values come from ICanonicalEntityCatalog enumeration/read endpoint; no AllowedTargetEntities dependency. 8) Path-scoped architecture guard scans production shared-authoring/API-adapter source (comments stripped, tests and the guard itself excluded) and refuses both `MaterialUnit` and `canonical_material_units` literals; no new global UA-08 term is added. 9) `tsc -b`, focused frontend authoring tests, focused backend Canvas/lifecycle tests and the architecture guard are GREEN. 10) Negative controls: mismatched graph.targetEntity/root outputTarget, invalid target, and reintroduced material literal each make the correct gate red. Target-eligibility tests prove the picker/catalog does NOT enumerate every mapped CLR entity. Positive representatives include at least `QualityEvent`, `ParameterDefinition` and `DefectCatalog`; negative representatives include `ImportBatch`, `JobRunHistory`, `DashboardWidgetDefinition` and `SourceSystemDefinition`. A newly mapped entity without the explicit projection-target capability is unavailable/refused until intentionally classified. No standalone hardcoded string allowlist is introduced. The current 12-name MappingDefinitionService list remains untouched in T-253 and is later replaced by T-256 consuming this same predicate. | 12 | Done | Worker 2 | T-094; T-209; T-241; T-244 | T-150; T-243; T-247; T-256; T-262 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/backend integration | 4.8 | M2-P2 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Owned T-253 surfaces only: Frontend shared authoring shell + canvas API adapter + focused authoring tests; Backend CanvasDefinitionContent / Canvas lifecycle contracts+implementation/response path; ICanonicalEntityCatalog interface+implementation; the semantic `ICanonicalProjectionTarget` marker interface and the minimum existing canonical entity declarations needed to mark current legitimate targets; existing AuthoringSupport read endpoint group; focused backend/architecture tests. No DB topology/migrations, no MappingDefinitionService.AllowedTargetEntities edit, no Analysis Subject redesign, no Job runtime, no chart/page styling. | Canonical outputTarget namespace is canonical entity name, but picker eligibility is a separate explicit model-sourced capability. Root outputTarget is hashed representation-independent authority; graph.targetEntity is compatibility data and must agree on new writes. Do not expose all mapped entities and do not use schema as the sole eligibility predicate. T-243 consumes this contract; T-256 later removes the old MappingDefinitionService string allowlist by consuming the same capability. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | CENTRAL v2.20.3: canonical output identity = ICanonicalEntityCatalog CLR canonical name. Projection-target eligibility is separate and MUST use the `ICanonicalProjectionTarget` marker interface on mapped entity types; do not enumerate all mapped entities, do not use schema-only eligibility, and do not add a new string allowlist. New root outputTarget is hashed for Graph+SQL; legacy Graph derives from graph.targetEntity, legacy SQL missing target stays null; minimal catalog enumeration/read endpoint allowed; path-scoped comment-stripped guard only. T-243 remains Not Started. |  |  | L3.6 | Board semantics, typed ports and property inspection | L2.3 | Build | D1; D2; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 4.8 | SOURCE CORROBORATES CLOSED OUTPUT CONTRACT | 0 | 0 | 0 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Original target authority closed; no duplicate estimate. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — ForGraph outputTarget/board Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — strict compatibility | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-254 | M2 | P2 | Customer-facing connector capability truth convergence | Frontend | DB Link / capability truth | Critical | Eliminate independent frontend/website capability claims for connectors and source systems. Availability, browse/read/subscription/import certification, Planned/Unavailable/Certified state and descriptive capability text are rendered from the backend connector truth snapshot or a generated artifact derived from it. Remove static 'live source' counts/claims that are not backed by current executed certification evidence. v2.22.0 — Converge backend provider validation and customer-facing truth on one authority; no independent provider capability list. Unimplemented SAP/REST remain explicitly non-executable; OPC metadata must equal runtime facts. This is bounded newly reviewed scope, not blanket reopening of earlier closures. | Change a connector capability/certification state in a backend fixture and prove the DB Configuration UI and generated website proof change without editing frontend/website source. Unsupported/planned connectors remain dimmed and attempts retain the typed refusal from T-207. Static gate finds no second provider-capability availability registry and no unqualified '6 live source systems' claim. v2.22.0 — Profile create validation, /provider-types, UI, website and execution capability agree; architecture and behavioral test enumerate unsupported families; changing one authority is reflected by all consumers; preserve valid T-207/T-254 historical proof. | 6 | In Progress | Worker 2 | T-207 | T-150; T-153; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/backend integration | 2.55 | M2-P2 | Original UI/website convergence is frozen at f8a35725. Only the v2.22 backend-provider-authority delta is outstanding. Consume T-207 and existing contracts on disjoint paths; column M remains the completion-prerequisite list. This is not permission to redo the closed UI/website scope. | Frontend DB configuration capability rendering + generated website proof adapter/content only. No connector protocol implementation. | T-153 later changes certification state by executed real-source evidence; UI/website consume the same truth automatically. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | Narrow truth-regression task; T-207 remains closed. | f8a35725c9b0d7fb5a0515c0103a72807a704a97 |  | L1.4 | Connector capability truth |  | Converge | D1; D2; D3; D5 | Core | R1 | Advances | f8a35725c9b0d7fb5a0515c0103a72807a704a97 | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | BASELINE CLOSED GREEN / FROZEN; LATER BACKEND EXTENSION UNPROVEN | Original customer-facing connector convergence closed in 5 paths. Website typecheck not independently re-claimed in handover, not RED. v2.22 backend-provider-list extension has no new completion evidence; certify that delta only. Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension. |  | RE-ESTIMATE REQUIRED |  |  | ORIGINAL SURFACES CLOSED; BACKEND CONVERGENCE REMAINDER | 2 | 4 | 7 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Backend authority extraction/delegation 1/2/4 + consumer mismatch tests/closure 1/2/3. Original frontend/website work excluded. | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:17-39 — duplicate provider DTO source Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:81-102 — OPC flags Backend/PlantProcess.Application/Integration/Connectors/ConnectorProviderCatalog.cs:72-104 — second catalog OPC/SAP entries | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-261 | M2 | P2 | Governed Transformation/Projection job executor and per-block runtime evidence seam | Backend / Jobs | Governed projection runtime | Critical | Commission the real governed executor for the existing CanonicalRefresh job family so a resolved DefinitionKind.Transformation target/version is actually executed through the governed Transformation/projection machinery. Preserve T-106 as the single job capability/target/version authority. The runtime must execute the exact resolved immutable Transformation version, never route to generic pending_import, and expose deterministic per-block progress/evidence using stable authored board.nodes[].id correlated to the genuine JobRunHistoryId. Reuse existing run-history/evidence/provenance authorities; do not create a second scheduler, run-history store, capability registry or block-identity model. | Known-answer proof: a published Transformation resolves through T-106 and CanonicalRefresh executes that exact version through the real projection runtime; genuine JobRun exists only after admission; run evidence records exact definition/version; stable authored block IDs receive deterministic progress/evidence; measured row/result/runtime facts are tied to the real run and existing provenance; typed block failure is isolated; cancellation is honoured; unsupported job families still refuse JX01 pre-admission; pending_import is not used; no second execution/evidence authority exists. | 12 | In Progress | Worker 2 | T-106; T-241; T-242; T-243; T-099; T-262; T-100 | T-104; T-245 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/runtime execution | 5.1 | M2-P2 | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Worker 2 owns executor/runtime work, but holds no mutation permission until T-100 commits. Preserve the shared producer frontier; one bounded delta only after the final SHA. | After T-100 commits: one bounded delta, then T-261 Runner 1/2; after T-261 closes proceed to T-245. No second compiler, capability policy, run store or block-evidence authority. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L2.3 | Canonical projection with validation, quarantine and reprocessing | L3.8; L2.6 | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | SEMANTIC CONTRACT/PACKAGE IN PROGRESS; HOST MUTATION HELD PENDING T-100 COMMIT | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. |  | INHERITED ESTIMATE | 12 | 5.1 | CONTRACTS PRESENT; EXECUTOR NOT APPLIED IN PROVIDED SNAPSHOT LATEST: HELD PENDING T-100 COMMIT | 16 | 26 | 42 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Compiler/dispatch 3/5/8 + executor/write/evidence 6/10/17 + cancellation integration 2/3/5 + Graph/SQL/live Gate0/replay/cancel tests and closure 5/8/12. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — admission before real run Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-276 — discarded resolution/dispatch Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — uncommissioned executor Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-149 — terminal lifecycle | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-262 | M2 | P2 | Governed projection declaration and canonical field-binding contract | Product / Integration | Governed projection declaration and canonical field-binding contract | Critical | Reconcile the source-present T-262 work as an official task: one immutable outputTarget/field-binding declaration with shared Graph/SQL semantics and one server type-compatibility authority. T-261 consumes it; do not reimplement current source. | Required business fields bound once; system-owned fields not authorable; unknown/ambiguous sources refused; no inferred mapping by name/position/type; declaration changes hash; old versions reopen unchanged and refuse governed execution until explicitly upgraded; source tests plus needed integration closure. |  | Done | Worker 2 | T-253; T-243 | T-245; T-247; T-261 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Governed product integration |  | M2-P2 | Consume accepted producer contracts; remaining dependencies: T-253; T-243. No private scheduler/definition authority. Source-present is not closure proof. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Semantic product filenames only. CENTRAL assigns shared file locks before overlapping worker writes. | Reuse current canonical authorities; no shadow lifecycle/registry/scheduler. | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | 86e1b677212195f191697ecdca7e9441b3dbde33 |  | L2.2 | Transformation authoring and relationship publication | L2.3; L3.6 | Build | D2; D3; D4; D5 | Core | R1 | Advances | 86e1b677212195f191697ecdca7e9441b3dbde33 | UNESTIMATED — new/recognized task; owner calibration pending. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | COMMITTED CONTRACT GREEN; CURRENT INTEGRATION ACCEPTANCE UNVERIFIED | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | 36de9370 | UNESTIMATED |  |  | ORIGINAL CONTRACT CLOSED; NARROW CONSUMER VERIFICATION OPEN | 1 | 3 | 6 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Real-shell reproduction 1/1/2 + bounded callback correction if confirmed 0/1/2 + focused regression/closure 0/1/2. Consumer Gate0 cost counted in T-261. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:118-163 — immutable projection content Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — unknown/narrowing refusal Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:898-925 — doSaveSql callback inputs/dependencies | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-148 | M2 | P3 | Map the 108 page files onto the 40 target pages | Frontend | Namespace | Very Important | Chapter 3 4.3 specifies 40 route pages plus 6 shell components. The repository holds 108 page files in 42 groups with 48 lazy route components, and roughly 14 files are reachable by nobody. Produce the keep, merge and delete decision per file, then delete the unreachable ones under Rule 4, which requires the replacement to land with the deletion in the same change. | A test asserting every page file under src/pages is reachable from a declared route. The count of page files moves toward 40 and no orphan remains. v2.10.2 TARGET-INVENTORY GATE — do not merely prove every existing page file is reachable or that the count 'moves toward 40'. Assert the exact Chapter 3 inventory: all 40 target route pages are declared once at canonical routes, all 6 global shell components are present, no target route is missing, and no orphan page file remains. Any temporary legacy alias must have a named retirement owner. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. v2.22.1 — v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. v2.23.0 — Consume per-surface approved route/control/state handoffs from T-265/T-266; do not wait for entire backend tasks merely to draft UI. Bind chapter control IDs to actual reachable controls and screen variants. Shared shell/component geometry is required consistency, not a defect. A control-label match alone is not a workflow test. Complete all current M2 route content and record explicitly deferred M3 behavior under its named implementation owner. | 8 | Not Started | Worker 2 |  | T-248 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/UI feature | 1.3333 | M2-P3 | R1 route inventory and six shell contracts frozen. Contract-ready handoffs from T-196/T-197/T-198/T-199/T-200 are recorded separately in column AN. Do not wait for the entire M3 implementation or ship a simulated M3 page. | Own route inventory/redirect cleanup only; do not touch W3 intelligence surfaces. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | Enterprise BI & Customer Experience | M2 P3 — Enterprise BI & Customer Experience. Release 1 is genuine early production / first-week customer work. |  |  | L3.1 | Analysis page anatomy, layout and visual standard |  | Build | D2; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 | T-196; T-197; T-198; T-199; T-200; T-265; T-266 | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.3333 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-215 | M2 | P3 | Reference gap, attainment and envelope measures in registry/BI | Frontend/Backend | Reference analytics | Very Important | Expose governed derived measures: GapToReference, NormalizedDeviation, InEnvelope, DistanceToBoundary and Attainment where mathematically valid. Bind them as registry measures without creating a second reference authority. | Top reference cases higher-is-better, lower-is-better and inside-range produce known answers and correct labels/provenance. An inapplicable attainment formula refuses rather than displaying a misleading percentage. Measures are usable in Page Builder without code per customer reference. | 10 | Not Started | Worker 2 | T-092; T-214; T-232 | T-150; T-222 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/backend integration | 4 | M2-P3 | T-092 + T-214. | Registry projection + query measures + widget labels. | Consume reference ID/version and scoring semantics; no local UI formula. | Enterprise BI & Customer Experience | M2 P3 — Enterprise BI & Customer Experience. Release 1 is genuine early production / first-week customer work. |  |  | L9.1 | Performance Reference | L3.4 | Build | D2; D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-265 provides the active M2 reference/measure direction and bound-result UI; T-267 expands the deferred authoring depth. Do not introduce a second Performance Reference authority. | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-222 | M2 | P3 | D1/D4 reconciliation evidence surface and reference overlay | Frontend | Reconciliation UI | Very Important | Render reconciliation cases through existing Findings/Interactive Workspace paths with reference overlays, causal-confidence level and transition/stabilisation regime evidence from T-236. No oil-specific page. September surface consumes the governed kernel result seam; canonical reconciliation tables remain post-demo. | Customer-shaped historical fixture shows one case end-to-end; all values/evidence open; TemporalUncertain and MissingEvidence have distinct wording; no person/lie wording; cross-filtering remains functional and route/session gates stay green. | 10 | Not Started | Worker 2 | T-219; T-220; T-215; T-203; T-204 | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend integration | 4.25 | M2-P3 | T-219/T-220 result contract + T-215 + T-203/T-204. Do not create a demo-only store. | D1/D4 generic components only; no new oil route. | Use existing governed evidence/result contract. T-221 later changes persistence behind the contract without UI redesign. | Enterprise BI & Customer Experience | M2 P3 — Enterprise BI & Customer Experience. Release 1 is genuine early production / first-week customer work. |  |  | L10.3 | Operational evidence reconciliation |  | Build | D2; D5 | Advanced | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-265 provides the Release-1 reconciliation evidence/result/refusal surfaces. Use the canonical result envelope and citation references, not local display calculations. | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4.25 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-258 | M2 | P3 | Frontend material-surface genericity convergence and presentation compatibility | Frontend | HMI / genericity compatibility | Critical | Consume the T-256 backend compatibility/consumer handoff and remove material/heat/coil-specific frontend surfaces from the generic customer product path without breaking the retained presentation profile. Own frontend consumers including MaterialAnalytics pages/routes, material-specific DTO/type assumptions such as DashboardMaterialRow, navigation and UI labels that make a material plant universal. Replace them with Analysis Subject/registry-driven generic surfaces where they are valid product capability, or isolate them behind an explicit presentation compatibility profile when they exist only for the retained demonstration. Do not change backend/API semantics owned by T-256 and do not redesign Page Builder/Canvas. | Start from the machine-readable T-256 frontend-consumer handoff and close every row. Generic build/navigation has zero required Material/Heat/Coil-specific page, route, DTO or label dependency for a foreign customer-shaped configuration. The retained ppiq_presentation/presentation profile still renders any explicitly retained presentation-only material surface through the bounded compatibility path. Static genericity test covers frontend MaterialAnalytics routes/pages/types and reports unknown=0. No backend file is modified by T-258. T-247 same-binary journey consumes the generic result. | 8 | Not Started | Worker 2 | T-094; T-250; T-256 | T-150; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend bounded correction | 3.4 | M2-P3 | WAIT for T-256 CLOSED and its frontend-consumer handoff manifest. Then perform bounded frontend-only convergence; do not re-investigate backend genericity. | Frontend MaterialAnalytics/generic navigation/types/tests only. No Backend/API/DB mutation and no Canvas/Job implementation. | T-256 defines backend semantic/compatibility truth; T-258 consumes it. T-247 validates the same-binary customer journey and does not redesign either side. | Enterprise BI & Customer Experience | v2.20.1 ownership split: created to prevent Worker 1 T-256 from crossing into Worker-2 frontend ownership while still closing generic-binary material residue. |  |  | L5.1 | Canonical entity catalogue | L3.4 | Converge | D1; D2; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 3.4 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-137 | M2 | P4 | ModelServingRuntime and model-gateway adapter, isolated from the presentation dock | AI+ML | LLM runtime | Very Important | Replace the obsolete provider-specific POST assumption with a replaceable ModelServingRuntime plus model-gateway adapter. Support self-hosted/private/BYOM endpoints, minimum-scoped evidence payloads, provider/model release identity, timeout/cancellation and no-unapproved-fallback. IMPLEMENT NOW ONLY AS AN ISOLATED MODULE: do not register it into the current assistant DI or change the M1 dock/runtime. Canonical wiring happens in T-138. | Standalone contract tests run against a deterministic fake runtime and an HTTP translating stub. They prove minimum-scoped payload, timeout/cancel, governed provider/model identity, and refusal on unapproved fallback. A repository dependency test proves no production assistant registration or M1 route/file changed in this task. | 10 | Done | CLOSED |  | T-122; T-138; T-246 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L4.8 | Model registry, promotion, serving and fallback |  | Build | D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-168 | M2 | P4 | Versioned C#↔Python ML job protocol and isolated runtime harness | AI+ML | ML runtime | Critical | Build the schema-independent execution protocol between the .NET job runner and Python ML processes. A versioned job spec carries job/tenant/site identity, model family, semantic manifest handle when available, snapshot/artifact URI+hash, seed, code identity, resource/cancellation/checkpoint settings and output location. Python returns a versioned result manifest with terminal state, metrics, artifact hashes, warnings/refusal and checkpoint identity. This task is deliberately NOT registered into production DI, scheduler or presentation runtime. | Run deterministic fake trainers through success, honest refusal, crash, timeout, cancellation and checkpoint/resume. C# must preserve stdout/stderr and exit identity without parsing free-form text as truth. Re-running the same seeded fixture yields the same result-manifest content hashes. A dependency test proves no current M1 runtime registration changed. | 12 | Done | CLOSED |  | T-122; T-175; T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 16ea041a; 94ab4e40; 723b9434; 6aef283f; ef588f0c — multi-commit runtime/protocol/CI closure |  | L4.4 | Learned models MF-01 / MF-03 / MF-04 | L8.4 | Build | D3; D5 | Core | R1 | Advances | 16ea041a; 94ab4e40; 723b9434; 6aef283f; ef588f0c — multi-commit runtime/protocol/CI closure | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-169 | M2 | P4 | Typed columnar training-artifact library and B-03 harness | AI+ML | Data artifacts | Critical | Implement a typed columnar artifact abstraction used by sealed feature snapshots. Parquet/Arrow/equivalent remain implementation candidates behind the contract. Own schema/type mapping, column projection, content hash, byte/row counts, deterministic read order, corruption detection and a benchmark hook for B-03. No database table is the training read path and this task does not create final persistence. | Write and read the same representative fixture through each enabled candidate. Assert stable row/schema/content identity, projected-column reads, bounded memory and explicit refusal for unsupported/corrupt schemas. Produce B-03 benchmark output format without choosing a winner or guessing a production threshold. | 10 | Done | CLOSED |  | T-175; T-184; T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | a887c554 — T-169 Pack 1: typed columnar artifact contract, Parquet and Arrow IPC adapters, two hashes, B-03 hook | 2026-08-13 | L4.3 | Feature engineering and incremental feature refresh |  | Build | D3; D5 | Core | R1 | Advances | a887c554 — T-169 Pack 1: typed columnar artifact contract, Parquet and Arrow IPC adapters, two hashes, B-03 hook | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-170 | M2 | P4 | Chunked sequence-artifact library and bounded loader | AI+ML | Data artifacts | Critical | Implement the schema-independent sequence payload contract: immutable chunked typed numeric arrays, compression seam, chunk index, content hashes and bounded streaming/memory-mapped reads where supported. PostgreSQL array payloads are forbidden; final sequence_manifests persistence is T-185. Include the B-04 benchmark hook. | Generate a large synthetic multi-channel sequence fixture, read it without whole-payload materialisation, verify chunk order/content hash and detect a corrupted/missing chunk. Compare at least two chunk/compression settings and emit B-04 measurements without hardcoding the selected values. | 10 | Done | CLOSED |  | T-185; T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 5a216483 — T-170 Chunked sequence-artifact library and bounded loader | 2026-08-15 | L4.3 | Feature engineering and incremental feature refresh |  | Build | D3; D5 | Core | R1 | Advances | 5a216483 — T-170 Chunked sequence-artifact library and bounded loader | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-171 | M2 | P4 | Capability Profiler and eligibility/refusal kernel | Engine | Readiness | Critical | Implement a pure, industry-neutral Capability Profiler that converts declared semantic/data-product facts into measured capability states for statistics, similarity, novelty, supervised prediction, practice and remediation. Include collapsed-dimension handling, genealogy strength, outcome/label availability, population sufficiency and the canonical terminal/refusal taxonomy. No database access or presentation wiring. | Table-driven fixtures cover a rich plant, a sparse plant, no-genealogy, single-level context, missing labels and unsupported method cases. The same input produces the same capability profile; a collapsed single-level dimension is removed rather than treated as an error; method absence is NOT_APPLICABLE rather than a false zero-variance claim. | 10 | Done | CLOSED |  | T-131; T-186; T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 95cc019c — Capability Profiler Pack 2 |  | L4.1 | Readiness gate and statistical discipline chain |  | Build | D3; D5 | Core | R1 | Advances | 95cc019c — Capability Profiler Pack 2 | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-172 | M2 | P4 | MF-01 Process Encoder runtime behind a replaceable contract | AI+ML | MF-01 Encoder | Very Important | Implement ProcessEncoder as a replaceable runtime with a PyTorch candidate, channel_set_version, deterministic seed/environment manifest, train/encode/artifact contracts and serving-cost telemetry. The encoder is optional and no production promotion decision is made here. It consumes only sealed typed sequence/snapshot artifacts and never live feature_store. | Train/encode a deterministic fixture twice and compare artifact/embedding reproducibility within declared tolerance. Change channel_set_version and prove the prior encoder is incompatible. Measure metric-lift input hooks, p95 cost and artifact size for B-05; no task declares the encoder deployable merely because it trains. | 12 | Done | CLOSED |  | T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | d4321856 — T-172 MF-01 Process Encoder runtime behind a replaceable contract | 2026-08-15 | L4.4 | Learned models MF-01 / MF-03 / MF-04 |  | Build | D1; D3; D5 | Core | R1 | Advances | d4321856 — T-172 MF-01 Process Encoder runtime behind a replaceable contract | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-173 | M2 | P4 | MF-02 VectorSimilarityIndex with exact-Flat recall baseline | AI+ML | MF-02 Similarity | Critical | Implement the VectorSimilarityIndex product contract: build, seal, extend/new-generation, search and recall_probe. Exact Flat remains the permanent benchmark on a representative sample; ANN families such as HNSW/IVF/PQ/FAISS are candidates only. Index generations are immutable and identified by content/generation manifest. | Build Exact Flat and at least one approximate candidate on synthetic vectors. Measure recall@k, p95 search, build time and memory; deliberately degrade the ANN and prove a build below recall_floor is not eligible to serve. Repeating a sealed generation yields stable identity and search evidence handles. | 12 | Done | CLOSED |  | T-140; T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 00a14286 — T-173 MF-02 VectorSimilarityIndex with exact-Flat recall baseline | 2026-08-15 | L4.5 | Retrieval and similarity index MF-02 |  | Build | D3; D5 | Core | R1 | Advances | 00a14286 — T-173 MF-02 VectorSimilarityIndex with exact-Flat recall baseline | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-174 | M2 | P4 | MF-03 novelty-model runtime and honest refusal semantics | AI+ML | MF-03 Novelty | Very Important | Implement the novelty/anomaly family behind a replaceable contract with a simple baseline first and an isolation/density candidate only where eligible. Persistable outputs must separate score, threshold/calibration identity, population context and refusal state. No source-schema or industry vocabulary is allowed. | Known synthetic normal/outlier populations produce expected ranking; a too-small or degenerate population returns the correct refusal instead of a fabricated score. Run deterministic seed/environment checks and export artifact/metrics in the common T-168 result-manifest shape. | 10 | Done | CLOSED |  | T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | db033796 — T-174 MF-03 novelty runtime and honest refusal semantics | 2026-08-15 | L4.4 | Learned models MF-01 / MF-03 / MF-04 |  | Build | D1; D3; D5 | Core | R1 | Advances | db033796 — T-174 MF-03 novelty runtime and honest refusal semantics | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-175 | M2 | P4 | MF-04 supervised-outcome training runtime and mandatory simple baseline | AI+ML | MF-04 Supervised | Critical | Implement SupervisedOutcomeModel behind the common runtime: train a mandatory simple baseline first, then a LightGBM tabular candidate for supported binary/multiclass/ordinal/continuous outcomes. Enforce prediction_cutoff/feature availability before training and emit reproducible artifact, holdout and performance metadata. Do not wire registry activation in this task. v2.10.1 SAFE-NOW OUTCOME RULE. During SAFE-NOW work, outcome definitions, prediction points and detection cutoffs are fixture-declared typed contracts only. Do not bind this task to ppiq_app tables, current ml_outcome_definitions rows, presentation outcomes or any physical production schema. Production supervised training consumes the canonical published SM-06 OutcomeDefinition only after its Release 1 binding is certified. | Known-answer fixtures cover at least binary and multiclass/ordinal outcomes. Inject a post-cutoff feature and prove training is blocked. The candidate and baseline train on the same sealed snapshot and report comparable metrics plus environment/artifact hashes; no candidate is called champion here. Leakage tests derive cutoff/detection semantics from the typed fixture OutcomeDefinition contract rather than hardcoded product/plant constants. No SAFE-NOW model code contains a production outcome code, canonical grain literal or production detection anchor. The runtime executes completely against sealed in-memory/file fixtures. | 12 | Done | CLOSED | T-168; T-169 | T-187 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 2413c6e1 — T-175 MF-04 supervised training runtime and mandatory simple baseline | 2026-08-15 | L4.4 | Learned models MF-01 / MF-03 / MF-04 |  | Build | D3; D5 | Core | R1 | Advances | 2413c6e1 — T-175 MF-04 supervised training runtime and mandatory simple baseline | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-176 | M2 | P4 | Calibration, explanation stability and three-dimensional promotion kernel | AI+ML | Model governance | Critical | Implement the pure evaluation/promotion decision used by learned models. QUALITY covers discrimination/error, calibration, out-of-time, subgroup/regime stability, missingness robustness and explanation stability. SERVING covers p50/p95/p99, throughput, artifact size, RAM/VRAM and warm-up. TRAINING covers duration, peak memory and snapshot throughput. Include the encoder promotion inequality and TreeSHAP as an initial explanation candidate, not a product contract. | A better-discriminating but worse-calibrated challenger is rejected. A model with unstable explanations is rejected. A simpler baseline that falls within the declared lift threshold defeats a costly encoder. Every promotion decision is reproducible from a frozen metrics document and names the failed dimension. | 12 | Done | CLOSED |  | T-140; T-187; T-191 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 08b54b61; 0a61ccfb — Calibration/explanation stability/promotion kernel + real TreeSHAP Pack 2 | 2026-08-15 | L4.8 | Model registry, promotion, serving and fallback |  | Build | D3; D5 | Core | R1 | Advances | 08b54b61; 0a61ccfb — Calibration/explanation stability/promotion kernel + real TreeSHAP Pack 2 | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-177 | M2 | P4 | Production statistical-method kernel, including Numeric×Categorical | Engine | Statistics | Critical | Build the schema-independent statistical kernel that T-146 will later wire into production. Preserve the proven Numeric×Numeric, Binary×Numeric and Categorical×Categorical paths and implement Numeric×Categorical with assumption-aware one-way ANOVA and Kruskal-Wallis fallback. Produce aligned population/group counts, effect size, p-value, q/FDR and explicit exclusion taxonomy. v2.10.1 TRACEABILITY TIGHTENING. Before replacing, retiring or reimplementing any existing statistical path, inspect the current reachable statistical implementations and their behavioural tests/source trace and record the proven behaviour that must be preserved. Known-answer fixtures may be authored first because they are mathematics-only and database-independent; fixture construction does not authorise replacement of an existing path before that source/test trace is available. | Known-answer fixtures select the expected method and effect-size family. Assumption violation switches ANOVA to Kruskal-Wallis. Constant input, unsupported pairing and insufficient groups/sample are three distinct terminal reasons. The kernel has no DI registration, DB write or M1 presentation dependency. Existing proven Numeric×Numeric, Binary×Numeric and Categorical×Categorical behaviours are regression-compared against the new kernel after the current implementation/test trace is inspected. Known-answer fixtures independently certify the mathematics. T-177 may begin with fixture construction before source trace is available, but may not close, retire or replace an existing reachable statistical path until the source/test trace has been inspected and parity is evidenced. | 10 | Done | CLOSED |  | T-146; T-147 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 502f8ca3; 502e0da9; bb4c5686 — T-177 multi-commit statistical-kernel closure |  | L4.2 | Statistical engines MF-05 / MF-06 |  | Build | D3; D5 | Core | R1 | Advances | 502f8ca3; 502e0da9; bb4c5686 — T-177 multi-commit statistical-kernel closure | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-178 | M2 | P4 | Pure remediation eligibility and can_accept decision kernel | AI+ML | Remediation | Critical | Implement the nine-check remediation eligibility logic and the complete seven-condition can_accept authority as a pure, table-driven domain service. Return actionable, evidence_only, exploratory or suppressed plus named failed checks. No persistence, UI wiring or plant-control client in this task. | One deterministic case fails each check by name; combinations produce the correct final class. can_accept cannot be reconstructed from fewer fields. A safety-check failure always produces suppressed. Static/dependency tests prove the kernel has no customer-source write/control dependency. | 8 | Done | CLOSED |  | T-143 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | b8792516; b5dbf232 — remediation eligibility/can_accept kernel + corrective canonical precedence | 2026-08-16 | L4.7 | Prediction, drivers, explainability and remediation candidates |  | Build | D3; D5 | Core | R1 | Advances | b8792516; b5dbf232 — remediation eligibility/can_accept kernel + corrective canonical precedence | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-179 | M2 | P4 | Deterministic Assistant tool planner | AI+ML | LLM orchestration | Critical | Implement the deterministic planner between resolved intent/entity context and declared Layer A/Layer B tools. The LLM never chooses tools. The planner is tenant/permission aware, asks on ambiguity, prioritises structured tools for facts and emits an auditable plan object. Build in a new isolated namespace with no current dock wiring. | A fixed probe set covers paraphrases, ambiguous entities, permission differences and unsupported intents. Equivalent intents select the same tool set; ambiguity asks rather than guesses; a forbidden tool is never planned. No LLM call occurs during planning. | 10 | Done | CLOSED |  | T-138; T-223; T-228 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | d2bf1834 — T-179: deterministic Assistant tool planner | 2026-08-16 | L6.2 | Governed Assistant runtime |  | Build | D3; D5 | Core | R1 | Advances | d2bf1834 — T-179: deterministic Assistant tool planner | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-180 | M2 | P4 | Permission-first hybrid retrieval and evidence packer | AI+ML | LLM grounding | Critical | Implement hybrid lexical+semantic retrieval/fusion with permission filtering BEFORE ranking, deduplication, tool-result priority, evidence-handle retention and a hard token budget with reserved answer allowance. Truncation is recorded/disclosed. Re-ranking stays behind an optional benchmarked seam for B-08. Isolated module only; no current presentation corpus cutover. | A forbidden high-scoring chunk cannot displace an allowed chunk. Duplicate evidence is collapsed without losing handles. A token-overflow fixture records truncation and still preserves higher-priority structured evidence. Run with and without the reranker seam and emit B-07/B-08 measurements. | 12 | Done | CLOSED |  | T-138; T-223; T-228 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | 87428c512c6d6d1ca2bf70a6a8b04aadc7a4cc3b — T-180: permission-first hybrid retrieval and deterministic evidence packer | 2026-08-16 | L6.2 | Governed Assistant runtime | L4.5 | Build | D3; D5 | Core | R1 | Advances | 87428c512c6d6d1ca2bf70a6a8b04aadc7a4cc3b — T-180: permission-first hybrid retrieval and deterministic evidence packer | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-181 | M2 | P4 | Deterministic answer verifier and Q-01..Q-11 evaluation harness | AI+ML | LLM verification | Critical | Implement the post-LLM deterministic verifier plus a fixed Assistant quality harness. Verify numeric claims against supplied evidence handles, forbid claim-class upgrade, preserve engine refusal, distinguish transport failure from abstention and reject unsupported claims without another LLM call. Encode Q-01..Q-11 measurements including tool selection, groundedness, citation correctness, refusal and causal-overreach. | Probe answers deliberately contain an uncited number, upgraded causal wording, erased refusal, fabricated handle and transport failure; each is blocked or classified correctly. A valid cited answer passes. Q-01..Q-11 results are machine-readable and reproducible on the fixed probe set. | 12 | Done | CLOSED |  | T-138; T-223; T-228 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | eaa82b8b45fb1fdb4b406abfbe2809c5f6fc9cd5 — T-181: deterministic answer verifier and Q-01..Q-11 evaluation harness | 2026-08-16 | L6.2 | Governed Assistant runtime | L5.8 | Build | D3; D5 | Core | R1 | Advances | eaa82b8b45fb1fdb4b406abfbe2809c5f6fc9cd5 — T-181: deterministic answer verifier and Q-01..Q-11 evaluation harness | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-182 | M2 | P4 | Benchmark harness and result manifest for B-01..B-09 | Testing | AI/ML benchmarks | Very Important | Create the common benchmark runner/result schema for B-01 through B-09. Record hardware/runtime identity, commit, dataset/snapshot hash, parameters, warm-up, repetitions and p50/p95/p99/throughput/memory metrics as applicable. This task creates measurement machinery only; it must not guess production values. | Run at least one synthetic smoke benchmark for each B-ID and produce a complete machine-readable result manifest. The harness refuses to publish a 'selected' value without the benchmark inputs/results that justify it. Re-running the same fixture preserves experiment identity and traceability. | 10 | Done | CLOSED |  |  | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Closed | 0 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L8.5 | Sizing model and calibrated performance constants | L4.5; L4.8 | Validate | D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 0 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-211 | M2 | P4 | Aggregation semantics execution kernel with continuous known answers | Analytics Engine | Aggregation kernel | Critical | Implement schema-independent aggregation kernels for SampleMean, TimeWeightedMean, Integral, Delta, StateDuration, Count, Min, Max and Last with quality/gap/reset rules and typed refusal. Use controlled fixtures, including irregular sampling, states and counters. | Known answers match analytical construction; deliberately irregular data proves SampleMean and TimeWeightedMean differ where expected; state duration and counter reset cases pass; undeclared/invalid semantics refuse AG01/AG02. Zero industry vocabulary and no DB access. | 10 | Not Started | Worker 3 | T-208; T-210 | T-212; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel isolated | 2.5 | M2-P4 | T-208 fixture + T-210 frozen contract. No production DI/persistence until consumer hand-off. | New analytics kernel/tests only. | T-212 consumes this kernel unchanged; W3 does not edit dashboard query files. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. |  |  | L4.2 | Statistical engines MF-05 / MF-06 | L5.3 | Build | D1; D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 2.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-214 | M2 | P4 | Performance Reference contract, precedence and scoring-semantics kernel | Architecture / Analytics Engine | Reference contract | Critical | Freeze declared Performance Reference kinds, scope precedence, directionality/scoring semantics, effective dating, ambiguity refusal RF01 and deterministic resolution as a schema-independent contract/kernel. No production persistence in this task. | Known-answer contract tests cover HigherIsBetter, LowerIsBetter, InsideRange, ClosestToTarget, effective-date resolution and equal-authority ambiguity -> RF01. Runs without production DB access. | 6 | Not Started | Worker 3 | T-209 | T-215; T-223; T-232; T-238; T-239; T-264 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel/contract | 1.5 | M2-P4 | T-209 frozen generic subject contract. | Reference contract/resolver tests only. | T-232 persists reference authority; consumers do not redefine scoring semantics. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. |  |  | L9.1 | Performance Reference |  | Build | D1; D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-217 | M2 | P4 | Temporal evidence alignment kernel | Analytics Engine | Temporal alignment | Critical | Build an isolated kernel for source clock adjustment, interval overlap, tolerance windows, incomplete interval handling and TemporalUncertain refusal. It consumes Source Time Authority, not raw timezone assumptions. | Known-answer skew/overlap fixtures pass; DST/local-vs-UTC case is aligned only with declared authority; skew beyond tolerance returns TM01/TemporalUncertain rather than conflict. Deterministic repeatability and no DB access. | 10 | Done | Worker 3 | T-208; T-216 | T-219; T-236 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel isolated | 2.5 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New temporal kernel/tests only. | T-219 consumes alignment output; does not reimplement clock logic. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L5.5 | Provenance, evidence chain, claim guard and refusal integrity |  | Build | D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 2.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-218 | M2 | P4 | Fact Evidence Authority resolution kernel | Analytics Engine | Evidence authority | Critical | Define/implement fact-specific evidence authority resolution: for each semantic fact, resolve Primary/Supporting/Corroborating sources, quality floor and effective date. No global source ranking and no PLC-is-truth shortcut. | Known-answer cases distinguish valve command vs valve feedback, motor electrical state vs production-order fact, and manual declared reason. Same source may be primary for one fact and irrelevant for another. Ambiguous/missing primary authority returns typed evidence-unavailable state. | 8 | Done | Worker 3 | T-208 | T-219 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel isolated | 2 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New evidence-authority contracts/kernel/tests. | T-219 consumes authority result; no source priority duplicated elsewhere. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L5.5 | Provenance, evidence chain, claim guard and refusal integrity |  | Build | D1; D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-219 | M2 | P4 | Operational Evidence Reconciliation kernel and seven-state taxonomy | Analytics Engine | Reconciliation | Critical | Reconcile independently sourced assertions over the same aligned interval using temporal result, evidence quality and fact authority. Output Aligned, PartiallyAligned, MissingEvidence, TemporalUncertain, ConflictingEvidence, LikelyMisclassified or Unresolved with discrepancy evidence. For September, the kernel also emits the standard governed Finding/analysis-result projection with evidence handles so existing generic surfaces can consume it without a new persistence schema. | Historical manual/business/machine fixture for the same calendar window produces predeclared states; missing machine/business evidence refuses classification; temporal-uncertain case never becomes conflict. No operator/person identity or intent field exists. The standard governed result projection is deterministic and carries the reconciliation state, evidence handles and causal-confidence input required by T-222/T-223. | 12 | Done | Worker 3 | T-217; T-218; T-236 | T-220; T-221; T-222; T-223 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel isolated | 3.2 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New reconciliation kernel/tests only. | T-220 adds claim confidence; T-221 persists output after canonical/security hand-off. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L10.3 | Operational evidence reconciliation |  | Build | D3; D5 | Advanced | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-220 | M2 | P4 | Causal Confidence Ladder and root-cause hypothesis evaluator | Analytics Engine | Claim governance | Critical | Implement L0 Observed Fact, L1 Discrepancy, L2 Statistical Association, L3 Temporally Supported Hypothesis, L4 Mechanistically Supported Hypothesis, L5 Confirmed Cause. L5 requires governed external/human confirmation; language cannot upgrade level. | Known cases land at each level for the exact evidence reasons. Removing confirmation downgrades L5. A test fails any phrase/API mapping that calls L2-L4 'confirmed root cause'. Output carries what evidence is missing for the next level. | 8 | Done | Worker 3 | T-219 | T-221; T-222; T-223 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel isolated | 2 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Claim-confidence kernel/tests only. | T-221/T-223 consume stored level; UI/LLM never re-derive it. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L5.8 | Truth contracts and claim boundaries |  | Build | D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-221 | M2 | P4 | Canonical reconciliation persistence, evidence handles and bindable source | Backend | Reconciliation persistence | Critical | Persist reconciliation_cases/reconciliation_evidence under tenant/RLS authority, semantic manifest and evidence handles; register reconciliation as a bindable intelligence source so D1/D4/Assistant use the same evidence path. | Insert/replay a case with two evidence sources, time state and L0-L5 level; tenant isolation/RLS passes; evidence handles resolve; registry binding returns typed columns; history is immutable when a later case/version is computed. | 12 | Not Started | Worker 3 | T-112; T-114; T-090; T-095; T-096; T-219; T-220; T-233 |  | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/integration | 5.4 | M2-P4 | T-112 + T-114 + T-090 + T-095/T-096 + T-219 + T-220. If security hand-off is not green, remain on pure-kernel evidence and do not create insecure tables. | Reconciliation persistence/registry/evidence only. | Post-demo canonical convergence. T-222/T-223 must not wait for this table and must not invent a temporary persistence schema. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. |  |  | L10.3 | Operational evidence reconciliation | L5.5 | Build | D3; D4; D5 | Advanced | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 5.4 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-223 | M2 | P4 | Grounded Assistant tool for reconciliation and Performance Reference explanation | Assistant | Industrial investigation | Very Important | Add deterministic Assistant tool/result contracts that retrieve reconciliation, Performance Reference and transition/stabilisation evidence, state the strongest supported hypothesis and its causal-confidence level, and explain what evidence is missing. Consume CompareOperationalPeriods from T-237 when available, without making T-237 a blocker for the core reconciliation answer. v2.20.0 ASSISTANT CONVERGENCE — retire/replace any legacy tool that derives a material-specific KPI directly from public.canonical_material_units. KPI/measure tools resolve governed registry measures, Analysis Subject and evidence handles. Page context binds to canonical Page Definition identity when available, and snapshot/tool evidence carries the active governed filter context rather than an unconditional empty object. | Golden questions include 'why was equipment unavailable?', 'what conflicts with the recorded reason?', 'how far are we from the declared reference?'. Numeric claims resolve to evidence; missing evidence refuses; causal overreach and 'operator lied' language fail deterministic verification. Ask the same KPI/explanation question against two customer-shaped subjects with no product-code edit; both resolve through governed measure/subject authority. Static/runtime checks show no material-specific table in Assistant tool contracts. A nested/detail route resolves the correct Page Definition identity, and an active filter is present in the resulting evidence context. | 10 | Not Started | Worker 3 | T-179; T-180; T-181; T-214; T-219; T-220 | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Assistant integration | 4.25 | M2-P4 | T-179/T-180/T-181 CLOSED + T-214 + T-219/T-220. No canonical persistence dependency for September explanation. | Assistant tool/evidence pack/verifier only; current dock UI remains Worker-2 owned. | T-221 later swaps persistence behind the same evidence contract; Assistant tool does not redesign. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. |  |  | L6.2 | Governed Assistant runtime | L10.3; L9.1 | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4.25 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-234 | M2 | P4 | Operational Transition and Stabilisation contract/kernel | Analytics Core | Process regime semantics | Critical | Define the generic transition/stabilisation contract used by all industries: customer-declared transition kind/scope, from/to context, stabilisation basis (Time/SubjectCount/Condition/None), regime classification Stable/Transition/Stabilising/Mixed/Unknown and RG01 refusal. No industry vocabulary and no production DB migration. | Known-answer fixture contains a transition, a declared stabilisation window and stable operation. The kernel classifies all five regime states, boundary cases and RG01 deterministically. Removing or moving the declared stabilisation boundary changes only the expected governed classification, never hidden heuristics. | 8 | Done | Worker 3 | T-208; T-209 | T-212; T-235; T-236 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel/contract | 2 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New generic transition/stabilisation contract/tests only. | T-235 persists unchanged contract; T-236 consumes it without redefining semantics. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L5.4 | Regime correctness |  | Build | D1; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-236 | M2 | P4 | Transition-aware aggregation, statistics and reconciliation guard | Analytics Engine | Regime correctness | Critical | Implement the schema-independent regime segmentation/eligibility guard consumed by interval aggregation, statistics, practice and reconciliation. Given governed interval segments + T-234 transition context, steady-state analysis partitions/excludes Transition/Stabilising; Mixed without authored policy refuses RG01; every guarded result carries regime state and overlap evidence. Production widget integration is T-212; this kernel does not wait for canonical persistence. | Controlled fixture proves naive pooled analysis sees the planted ramp-up effect while governed steady-state analysis does not misattribute it. TimeWeightedMean clips at regime boundaries where required. Reconciliation sees transition context as evidence, never as automatic cause. | 10 | Done | Worker 3 | T-217; T-234 | T-212; T-219 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Kernel/integration | 2.6667 | M2-P4 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Analytics/reconciliation kernels only. | T-219 consumes the guard; consumers must not bypass RG01. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. | Not recovered from reviewed sessions |  | L5.4 | Regime correctness | L4.2; L10.3 | Build | D3; D5 | Core | R1 | Advances | Not recovered from reviewed sessions | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Recorded closed — inherited evidence | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 2.6667 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-237 | M2 | P4 | Operational Period Driver Decomposition exact API and evidence tool | Backend / BI | Exact period comparison | Very Important | Implement Layer-A CompareOperationalPeriods over two governed periods/scopes. Return exact A/B/delta metrics plus transition count/duration, stabilisation exposure, stable-run/sequence length, stopped and production-impact minutes, yield/scrap, energy and any further registry-backed exact measures with evidence handles. No causal claim and no assumption-based money. | Known-answer periods reproduce exact deltas from source rows. Every numeric field has evidence; missing metrics are explicit unavailable/refused. The same query works for discrete and continuous fixtures. The Assistant tool adapter consumes this result without recalculating values. | 10 | Not Started | Worker 2 | T-092; T-235 | T-164 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/API integration | 4.25 | M2-P4 | T-092 + T-235; can run in parallel with T-222 on separate files. | Layer-A period comparison API/evidence only. | T-138/T-164 may consume the stable contract; neither may duplicate calculations. | Industrial Intelligence — References, Reconciliation & Assistant | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work. |  |  | L10.2 | Period driver decomposition |  | Build | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 4.25 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-112 | M2 | P5 | Force RLS on every tenant-owned table with an architecture test | Database | Security | Critical | The measured database has one RLS policy against 193 tables, while migration scripts 510, 530, 540 and 560 contain dynamic CREATE POLICY loops, so the scripts exist but the coverage does not. Establish the true coverage, then force RLS on every tenant-owned table and add an architecture test that fails the build when a tenant table is added without a policy. v2.20.0 EVIDENCE CORRECTION — T-251's generated catalogue defines the tenant-owned table set; T-252 supplies the disposable certification database. Retire any vacuous tenant-isolation 'proof' that does not execute database behavior. | A query listing tenant-owned tables without a policy returns zero rows. Add a new tenant table in a branch and confirm the architecture test goes red before it is merged. Execute a two-tenant behavioral proof from the database layer alone: tenant A can read/write its allowed row, cannot read/write tenant B, and an unscoped session is refused according to policy. The existing Assert.True(true)-style proof is removed or excluded from release evidence. The test must fail under a deliberate RLS-policy removal negative control. | 12 | Not Started | Worker 1 | T-087; T-088; T-251; T-252 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema/migration | 2.325 | M2-P5 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087/T-088 canonical migration authority available; establish FORCE RLS guar... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Critical hand-off: after T-089..T-105 + T-112/T-114 are committed, W3 may open T-183/T-195/T-128 lane. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.2 | Tenant isolation |  | Harden | D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2.325 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-113 | M2 | P5 | Secret and configuration hygiene | Backend | Security | Very Important | Remove PlantProcess__Auth__Users__0__IsBootstrapAdmin=true from env/profiles/local.env and env/profiles/presentation.env, both at line 42. Move the hardcoded PPIQ_E2E_PASS and the CI signing key out of deploy/scripts/ci-e2e-stack.sh. Parameterise the fifteen hardcoded server-IP references. Add secret masking to the audit package generator, whose header currently reads 'Mask Secrets : False' while the package contains credentials. Also fix the duplicated ConnectionStrings__PlantProcessDb line in both env profiles. AUDIT HARDENING IN v2.9.2. Do not stop at deleting today's literals. Make environment separation structural: Production must reject demo/test/bootstrap users, development signing keys, presentation-only source/database defaults and hardcoded host fallbacks. Local, test and presentation conveniences remain available only through explicitly selected non-Production profiles; the same deployable artifact moves environments. v2.20.0 REVIEW ADDENDUM — remove the dead PPIQ_RUN_E2E runtime-env knob now that canonical Jenkins E2E is unconditionally blocking. Production administration must require MFA by default (or require an explicit, auditable production exception); Release-1 evidence must include one MFA-enabled admin path. v2.22.0 — Enforce release-profile secret/configuration and unsafe legacy route boundary. Secrets only through references; reject/migrate secret-bearing options, protect logs/backups; release profile disables bootstrap defaults, seeds/dev minting and hand-entered-outcome runtime exposure. | A secret scan across the repository returns no live credential. Generate an audit package and confirm secrets are masked. Confirm the E2E stack still runs with credentials supplied from the environment. Add a fail-closed Production configuration test that deliberately injects a bootstrap admin, a known demo/test credential marker, a development signing key and a presentation/local host fallback one at a time; each must stop startup or fail the configuration gate by name. A clean Production profile passes with all required values externally supplied. Confirm no executable production/runtime script supplies the retired server IP as a fallback. Confirm PPIQ_RUN_E2E is absent from runtime profile generation. A Production profile with privileged-admin MFA disabled fails the configuration gate unless an explicit governed exception fixture is supplied. Run one privileged-admin E2E path with MFA enabled. v2.22.0 — Harmless sentinel round trip on create/update/get/list and logs; test setup failures fail tests; no secrets in profile row/response/log; no demo seed on production path; release-profile negative probes for dev/legacy routes; secret-scan evidence without printing secrets. | 8 | Not Started | Worker 1 |  | T-122; T-200 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.2 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.5 | Secret and credential management |  | Harden | D3; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | SOURCE REVIEWED — IMPLEMENTATION GAPS / RELEASE RUNTIME UNVERIFIED | 12 | 20 | 32 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Credential boundary+tests 5/8/13; profile/route guards 4/7/11; redaction/deployment verification 3/5/8. | Backend/PlantProcess.Infrastructure/Connectors/ConnectorCredentialResolver.cs:16-51 — Resolve Backend/tests/PlantProcess.Api.IntegrationTests/Security/T08ConnectorSecretMaskingIntegrationTests.cs:19-46 — Connector_password_is_masked_on_readback Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — dev route refusal | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-114 | M2 | P5 | Tenant keys, tenant-aware uniqueness and canonical namespace on new APIs | Backend | Security | Very Important | Apply tenant keys and tenant-aware uniqueness to every table introduced in M1 and Release 1, and put every new endpoint on the canonical namespace from the outset so the migration does not have to catch up with new work. | Insert the same natural key for two tenants and confirm both persist. A test asserting every endpoint added after this date matches the canonical domain pattern. | 6 | Not Started | Worker 1 | T-087; T-089; T-090; T-095; T-099 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 0.9 | M2-P5 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-089/T-090 + T-095/T-099 canonical Release 1 tables available; establish t... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Critical hand-off: after T-089..T-105 + T-112/T-114 are committed, W3 may open T-183/T-195/T-128 lane. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.2 | Tenant isolation |  | Harden | D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 0.9 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-115 | M2 | P5 | Fresh-install Rule 2 acceptance test, ephemeral | Database | Schema | Very Important | MOVED FROM M1 IN v2.3, and the move is correct on two counts. First, it fails Gate A on its own terms: the customer never sees it, and no presentation-visible feature depends on it. Second, the shape I proposed was wrong. A third PERSISTENT database is a third environment somebody has to remember to maintain, and this project already has exactly two working databases that earn their keep - ppiq_app for development and ppiq_presentation for the prepared demonstration state. Note also that ppiq_dev is a PostgreSQL LOGIN, not a database, which is worth writing down because the name invites the confusion. The correct implementation is an EPHEMERAL fixture created inside the integration test: create a uniquely named clean database, apply exactly the migrations a customer installation applies, apply NO seed, run the one-query Rule 2 proof, assert zero, then drop the database. Nothing survives the test run. The proof is the artifact; the database is not. What it protects is real: a customer's IT reviewer who opens a fresh installation and finds another company's plant rows inside it has found a dead deal, and ninety-four post-EF SQL scripts are where that could hide. v2.22.1 — Own the bounded backend acceptance-hygiene follow-up reported in the 04-Sep audit: first inspect the current T-210 fixture and the named migration byte-order marks, then fix only reproduced issues. Reuse T-252 disposable-DB policy and T-259 evidence envelope; do not reopen their proven closures. The inherited DefinitionKind mismatch reported with T-099 is a separate test-authority convergence obligation, not a T-099 regression. | A fresh migration chain produces zero rows outside the declared prefill allowlist. The allowlist is data, at Backend/database/acceptance/rule2_prefill_allowlist.txt, so a table added later is plant data BY DEFAULT and the test goes red until somebody classifies it deliberately. The test fails if any future migration or seed introduces plant, customer or demonstration rows. The temporary database is dropped whether the assertion passes or fails. v2.22.1 — Verify actual current file bytes before calling the historical five-BOM finding still present; keep before/after hashes when a byte repair is required. A local intentionally absent external probe may skip only with the approved named reason; Release-1 certification provisions its own disposable database and a missing fixture is RED, never a passing skip. Reconcile the inherited DefinitionKind assertion with the current canonical kind authority and assert all required members rather than merely deleting or weakening the test. Keep T-099 closed; full-release GREEN remains forbidden while its independently tracked known-red or canonical replay limitations remain unresolved. | 4 | Not Started | Worker 1 |  | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | DB/schema/migration | 0.775 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L8.1 | Fresh install and upgrade authority | L8.2 | Validate | D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate v2.22.1 acceptance/ownership clarification; owner to review planning impact. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 4 | 0.775 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-119 | M2 | P5 | Eight-role catalogue convergence, one-to-one wire mapping and three enforcement layers | Backend | Users and roles | Critical | FormalPlantRole already contains the enterprise catalogue. Converge the shipped contract rather than rebuilding the model: one canonical external identity per formal role, fail-closed parsing of unknown values, generated/typed frontend role vocabulary, and enforcement at API, query/data and UI layers. Preserve the three-role minimum as the smallest legal customer configuration. Extend FormalRoleAccessMatrix rather than creating a second role list. Unknown roles must never silently downgrade to Viewer. | A matrix test asserts every formal role against every capability at API, query/data and UI layers. Every enum member has one stable wire identity; round-trip role→wire→role is lossless. Unknown role text is refused, not mapped to Viewer. The frontend compiles against a closed/generated role union rather than '¦ string'. Confirm a viewer cannot author SQL at any licence tier, and CEO/Executive distinctions remain explicit where the catalogue defines them. | 12 | Not Started | Worker 1 |  | T-121; T-197; T-198; T-200 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.1 | Users, roles, permissions, MFA and enterprise identity |  | Converge | D3; D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-120 | M2 | P5 | Users and Roles administration surface | Frontend | Users and roles | Very Important | Build the F1 Users and Roles page from Chapter 3 4.4 with the ten-field page contract. The code itself records that Users and Roles and System Health are missing from the UI. | Create, edit, disable and re-enable a user, and change a role assignment, entirely through the interface. Confirm the audit layer records each change. | 12 | Not Started | Worker 2 |  |  | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/UI feature | 2 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.1 | Users, roles, permissions, MFA and enterprise identity |  | Build | D2; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-265 covers only the existing M2 user/role safety slice; T-267 covers deferred administration depth. Render permissions/refusals from the current canonical role contract. | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-121 | M2 | P5 | Licence and entitlement enforcement | Backend | Licence | Critical | Chapter 6 6.3 requires the six commercial dimensions and the capacity envelope to bound a tier together. LicenseLimits already carries AllowsSqlEditor per tier, set by both LicenseService and VerifiedEd25519LicenseService and exposed by LicenseAdminEndpoints. Extend to full metering: retained volume, ingest rate, refresh floor, weighted compute slots and concurrent sessions. Exceeding a meter throttles rather than destroys, and every meter is visible to the customer. v2.10.2 PAGE-COVERAGE EXPANSION — this owner also delivers the required F3 Authoring Quota and Limits route /admin/quota. F2 shows licence/entitlement and total meters; F3 allocates authoring quotas by role/user with current consumption, Amber at >=80%, create disabled at 100%, and no lost draft. v2.20.0 TRUST-ROOT RULING — production licence issuance/signing authority is vendor-side. Customer databases contain verification/public-key material and licence artifacts, not a production private signing key capable of minting a valid licence. Any development-only local signing key is explicitly non-production and either truly encrypted at rest or stored under a truthful non-encrypted name; an `_encrypted` column may not contain raw PEM. v2.22.0 — Preserve vendor-only signing and existing F2/F3 quota ownership. Remove shadow ILicenseService registrations; dev signing storage/naming truthful and non-production. | Exceed a meter and confirm the import queues and the job waits for a slot rather than failing. Confirm the customer can see their own approach to each meter in the interface, since a limit the customer cannot see is a trap. In addition to licence-meter tests, open /admin/quota, change one role quota and one user override, approach 80% and 100%, and prove warning/disable semantics plus audit. Non-admin roles are denied by the final page contract. Issue a production-shaped licence outside the customer database, verify it on the customer installation, tamper and prove refusal. Prove the customer database alone cannot mint a valid production licence. Inspect signing-key persistence and prove no raw private PEM is stored in a field/schema claiming encryption. v2.22.0 — Exactly one effective registration; valid/tampered/expired licenses; no production signing secret; dev mint endpoint denied/unmapped in release profile; keep quota 80%/100%, role/user override and no lost draft acceptance. | 16 | Not Started | Worker 1 | T-119 | T-127 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain contract | 1.8 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 role catalogue/enforcement + licence authority. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.3 | Licence and feature entitlement | L7.4 | Build | D3; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — Use T-265 for existing M2 licence/quota states and T-267 for full administration depth. Entitlement, role and runtime capability are different inputs; no drawing enables a capability. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — METER/UI REMAINDER NEEDS DEEPER TRACE | 10 | 18 | 30 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | DI and entitlement reconciliation 2/3/5; meters/quota surfaces 5/10/17; acceptance/negative tests 3/5/8. | Backend/PlantProcess.Api/SignedLicensing/VerifiedEd25519LicenseService.cs:10-60 — feature/tier authority Backend/PlantProcess.Api/Program.cs:725-744 — licence DI Backend/PlantProcess.Application/DependencyInjection.cs:58-63 — legacy DI Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — development guard | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-123 | M2 | P5 | Install package, migration runner, upgrade and rollback | Infrastructure | Deployment | Critical | Build the fresh installation and upgrade paths from Chapter 6 6.1.4, including what an upgrade may never do, and a rollback path. Migration runs as a deployment step rather than as a manual action. Explicitly own in-place upgrade of a long-lived installation: canonical migration ledger/watermark continuity, upgrade from an older valid schema without rebuild, rollback boundary, and reconciliation of a development DB whose migration ledger is missing/stale. Do not conflate populated plant data with migration-ledger correctness. v2.20.0 DEPLOYMENT HARDENING — Release-1 production containers run with explicit non-root runtime users, and customer/public hostnames/IPs come from selected configuration profiles; executable install/smoke scripts have no legacy-server IP fallback. Do not wait for M3 isolated-ML container work to establish these minimum production properties. v2.22.0 — Keep deterministic install/upgrade/rollback. Production schema migration and demo/presentation seed authorities are separated; operational profile values are external to product source. | Install on a clean machine, upgrade from the previous version, then roll back. All three complete without manual database intervention. Run the fourteen post-deployment acceptance checks from 6.1.4.6. Clone an older populated installation, upgrade it in place through the canonical runner, prove schema_migrations/EF history records the executed path, preserve customer rows, and prove rollback/failed-upgrade recovery without substituting a fresh empty database. Inspect every Release-1 runtime image and prove its effective UID is non-root. Provision two different host/domain profiles without editing repository files and complete install/upgrade/smoke on both. A missing required production host value fails configuration rather than falling back to the historical server. v2.22.0 — Fresh production install has no demo/customer facts, no automatic presentation seed, external host/secret config, and restart/upgrade/rollback proof. Non-root process/container checks apply to the deployment profile actually shipped. | 14 | Not Started | Worker 1 |  | T-122; T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Infrastructure/deployment | 3.2 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L8.1 | Fresh install and upgrade authority | L8.3 | Converge | D4; D5 | Core | R1 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — DEPLOYMENT EXECUTION UNVERIFIED | 12 | 20 | 36 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Path/ledger convergence 4/7/12; populated-upgrade/rollback tests 5/8/15; clean-host profile/non-root proof 3/5/9. | deploy/scripts/ppiq.ps1:3-20 — command contract deploy/scripts/ppiq.ps1:44-63 — profile/path selection Backend/database/canonical-migration-order.json:1-20 — canonical ledger | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-124 | M2 | P5 | Backup with a tested restore acceptance procedure | Infrastructure | Backup | Critical | Chapter 6 6.1.11 requires not just backup but a tested restore acceptance procedure with a consistency rule. Implement schedule, retention, encryption and the restore rehearsal. | Perform a real restore into a clean environment and run the acceptance procedure against it. A backup that has never been restored does not count as a backup. | 12 | Not Started | Worker 1 |  | T-150; T-199 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Infrastructure/deployment | 3.2 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L8.7 | Backup, restore, PITR, DR and HA |  | Build | D4; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-125 | M2 | P5 | Minimum monitoring, health and alerting | Infrastructure | Monitoring | Very Important | Implement the minimum from Chapter 6 6.1.12 required to operate a soft test: per-component metrics, alert severity and escalation, and the operational dashboard. Full observability and SLOs are M3. v2.20.0 OPERABILITY FLOOR — establish one named health-check/operational status authority for API, database and job execution rather than proliferating ad-hoc health routes. Every executable job family emits a non-null run/correlation identity. Minimum Release-1 metrics include running/queued count, oldest queue age, wait time, runtime, failure/refusal count and configured worker-pool utilisation. Full SLO/OpenTelemetry-scale observability remains T-163. | Trigger each alert condition deliberately and confirm it fires with the correct severity and reaches the configured channel. Execute jobs through at least two families and prove every log/diagnostic row carries the same non-null run identity end-to-end. Induce queue saturation and show queued count/oldest age/wait time and pool utilisation change predictably. A component failure changes the canonical health state and alert; duplicate feature-specific /health routes are not required as separate authorities. v2.22.1 — The existing operational API/log projection exposes durable batch outcome, error/code, progress/counts and last committed cursor for B4, with run/batch correlation and tenant scoping. T-101 owns the consuming UI. No view computes a replacement status from message text. Final T-247/T-150 evidence joins UI observation to these source facts. | 14 | Not Started | Worker 1 | T-106; T-107 | T-150; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Infrastructure/deployment | 3.2 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L8.6 | Monitoring, observability, health and readiness | L1.7 | Build | D5 | Core | R1 | Advances |  | Inherited baseline estimate v2.22.1 acceptance/ownership clarification; owner to review planning impact. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-265 receives the frozen B4/B5 operational payload. Preserve T-101 UI versus T-125 API/metrics ownership already assigned in v2.22.1; prototype figures never replace persisted evidence. | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 14 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-126 | M2 | P5 | Support runbook and UAT dataset and configuration import | Documentation | Handover | Very Important | Write the runbook the customer's own operator will follow, and build the path to import the customer's UAT dataset and configuration. Include the operator, data engineer and administrator sections. | A person who has not worked on the project commissions a site and completes one import following only the runbook. Every step they had to ask about is a defect in the runbook. | 12 | Not Started | Worker 1 |  | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | AI documentation/static analysis | 0.9 | M2-P5 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L7.8 | Sales Administration and sales-to-engineering handover | L8.8 | Build | D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 0.9 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-150 | M2 | P5 | Release 1 final production gate: Day-1 workbench, BI, OPC, intelligence and hardening | Testing | CI/CD | Critical | Final Release-1 production gate. It does not rely on a hand-maintained dependency closure as the completeness definition. At execution time enumerate every Backlog row with Milestone Id=M2 and Release Criticality='Release 1 MUST'; require each to have current closure evidence and its owning acceptance green/replayable. Then execute Day-1 workbench, enterprise BI, production OPC, industrial intelligence, security/admin/install/recovery and clean frontend/CI truth gates. The Depends-On column remains sequencing hints, not the authoritative Release-1 completeness set. | Gate fails if ANY M2 Release-1-MUST task is not closed with evidence, even when it is absent from the direct dependency list. Prove the enumerated task count equals the workbook's current Release-1-MUST count. Execute real frontend/backend gates: enumeration-only --list commands cannot satisfy execution acceptance; no catchError/forced-success path may turn a failing required suite green. Day-1 Golden Journey, fresh-install/upgrade, RLS/roles/licence, OPC runtime, BI interaction, evidence/Assistant, backup/recovery and database zero-unknown catalogue checks must all be green before Release 1 is certified. The single machine-readable current-HEAD artifact records executed test counts and skipped counts; Release-1 required suites have zero unapproved skips. Any script named or consumed as a gate/validator executes its tests rather than merely enumerating them. If an audit package is attached to release evidence, it is generated in external-safe masked mode. | 12 | Not Started | Worker 1 | T-115; T-123; T-124; T-125; T-126; T-205; T-207; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-250; T-251; T-252; T-253; T-254; T-255; T-256; T-257; T-258; T-259 |  | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Integration/E2E/certification | 4.08 | M2-P5 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-192 + T-148 exact route/shell inventory + T-194 API-alias retirement + all ... | T-150 only after W2/W3 component freeze; route failures back to owning agent. | Final Release 1 gate. Fixes go back to the exclusive owning task/agent; T-150 owner does not edit other agents' feature files. | Release Hardening & Week-1 Production Acceptance | CENTRAL 04-Sep-2026: T-150 release completeness is generated from Release Criticality, not inferred from transitive Depends-On. A green T-150 with any Release-1-MUST row unproven is mechanically impossible. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Certify | D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 4.08 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-227 | M2 | P5 | Release 1 production acceptance scorecard and evidence policy | Documentation | Pilot governance | Very Important | Define the Release-1 production acceptance scorecard before final certification: Day-1 workbench completion, source truth, Canvas/Job usability, BI reliability, OPC read-only proof, evidence/Assistant correctness, minimum security, recovery and support criteria. Consume the frozen T-259 Release Evidence Envelope v1 contract. T-227 owns acceptance criteria, evidence ownership, measurement definitions, approved/not-applicable skip policy and release pass/fail policy; it does NOT own or redefine the common envelope schema. | The scorecard is versioned before final certification and every criterion has an evidence owner, measurement and pass/fail rule. Validate that T-252-shaped DB evidence and T-257-shaped frontend evidence conform directly to T-259 envelope v1 without field translation. The scorecard may impose stricter policy on producer fields, but it must not rename common fields, change contract_version or alter T-259 count invariants. | 6 | Not Started | Worker 1 | T-213; T-259 | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Documentation / governance | 2.25 | M2-P5 | Prepare before installation; can start after customer data assessment T-213. | Pilot documentation/evidence scorecard only. | Site/engineering teams later fill measured values; criteria are not rewritten after results are known without an audited amendment. | Release Hardening & Week-1 Production Acceptance | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Validate | D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 2.25 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-255 | M2 | P5 | Repository authority and audit-truth hygiene ratchet | Tooling | Repository governance / audit truth | Important | Establish a forward-clean source authority without mass-renaming historical implementation. Create a root allowlist; remove tracked transient pack payload/run-state files; normalise accidental blank-line-inflated source files; retain one current audit-generator authority and archive older generations; classify runtime/current vs test/tool/backup/generated scanner hits so executive severity is not self-referential. Add a forward filename gate that rejects new task-ID-named implementation/test/tool files while grandfathering the measured legacy set for opportunistic semantic rename. | Root allowlist returns zero unexpected tracked artifacts. No tracked *_state.json or stale pack payload remains. No ordinary source file exceeds 60% blank lines unless explicitly fixture/generated-allowlisted. Audit rerun does not count its own regex definitions, backup Jenkinsfiles or generated Playwright assets as current runtime CRIT. Negative control adding a new task-ID implementation filename makes the hygiene gate red. | 8 | Not Started | Worker 3 | T-205; T-250 | T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Architecture/test | 1.2 | M2-P5 | Run after T-106 or on a disjoint tooling-only lane; no runtime feature mutation. | Root/tooling/audit generator/architecture hygiene tests only. Do not rename or edit Worker-1/2 runtime feature files. | Legacy task-ID filenames are grandfathered, not mass-renamed. Future tasks consume the forward gate. | Release Hardening & Week-1 Production Acceptance | Created from merged v1/v2 Developer-persona review; source authority, not cosmetic cleanup. |  |  | NO-CAP — Execution Tooling | Execution tooling / implementation instrument — no product capability |  | Build | D1; D5 | No Capability | R1 | No maturity change |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-257 | M2 | P5 | Frontend execution-truth and release-profile skip-zero gate | Frontend | Test / release truth | Critical | Close the remaining frontend test-truth gap without reopening T-205/T-250. Any script named/used as a gate or validator executes the relevant tests; enumeration-only `--list` commands are named inventory tools and cannot satisfy acceptance. The Release-1 profile records executed/skipped counts and permits zero unapproved runtime-conditional skips. Generated Playwright report assets are not tracked as source/audit inputs. | Induce a failing frontend/visual/accessibility/E2E test and prove every configured release gate returns non-zero. Static gate finds no `--list` in scripts classified as gate/validate/acceptance. Release profile produces machine-readable executed and skipped counts with zero unapproved skips; deliberately missing seed/env causes a red prerequisite, not a green skipped spec. Generated report directories are ignored/excluded and do not contribute audit TODO/CRIT signals. Emit frontend/unit/E2E execution and skip counts using the canonical T-259 Release Evidence Envelope v1 fields. T-257 owns frontend skip policy and producer implementation only; it does not redefine the shared envelope. Producer contract is T-259 Release Evidence Envelope v1. T-257 may add frontend/E2E-specific extension fields but may not rename/redefine common fields. | 6 | Not Started | Worker 2 | T-205; T-250; T-259 | T-150; T-248 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend test infrastructure | 2.55 | M2-P5 | Run on frontend test/config/report files only after current authoring lane reaches a clean handoff; no product feature scope. | Frontend package/test configs/gate scripts/generated-report hygiene only. | T-150 consumes this machine-readable release truth; T-248 later extends enterprise visual parity, not test-runner semantics. | Release Hardening & Week-1 Production Acceptance | Created because the 08-Sep audit still has real --list enumeration signals outside the canonical blocking Jenkins stages. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate | L8.2 | Validate | D2; D3; D5 | Core | R1 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 2.55 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-110 | M3 | P1 | Bounded delta execution: chunks, resume, deterministic merge and scan budgets | Backend | Delta propagation | Critical | Implement Chapter 4 5.3.9.6a: bounded chunks with receipts, checkpoint and resume after interruption, and a deterministic merge so a resumed run produces the same result as an uninterrupted one. v2.22.0 — Absorb T-111 runtime scan-budget enforcement: bounded row/byte chunks, receipts, checkpoint/resume, deterministic merge, explicit scan mode, cumulative scan budget and abort/finding. T-155 owns calibrated constants/Scan Amplification bands; T-159 owns C1-C4 certification. M2 T-108/T-109 must still deliver safe bounded delta execution and replay; moving advanced chunk machinery does not waive Day-1 source limits or safe cancellation. | Kill a running job at 60 percent, restart it, and confirm the final result is byte-identical to an uninterrupted run over the same input. v2.22.0 — Record a baseline, then deliberately remove a delta scope and confirm the gate goes red. Restore and confirm green. Prove chunk parallelism 1 vs 8 business output parity; abort above cumulative scan budget; uncommitted chunk rolls back; resumes exactly from committed receipts; preserved input/version pins. | 24 | Not Started | Worker 1 | T-108; T-109 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | Backend/domain contract | 1.8 | M3-P1 | Consume accepted producer contracts; remaining dependencies: T-108; T-109. No private scheduler/definition authority. Source-present is not closure proof. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L2.8 | Delta propagation law | L8.4 | Build | D3; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — ADVANCED RUNTIME GAP | 16 | 28 | 44 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Chunk/receipt persistence 6/10/16; resume/merge/enforcement 6/11/17; interruption/parallelism tests 4/7/11. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — existing incremental reader use Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — batch/cursor persistence Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — existing admission/run boundary | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-122 | M3 | P1 | Container architecture and configuration profiles, including isolated ML runtimes | Infrastructure | Deployment | Critical | Implement the Chapter 6 container/profile architecture and include the frozen AI runtime split: ppiq-worker for ordinary batch work including ml.batch_scoring, ppiq-ml-train for ml.training, and ppiq-ml-online for hard-reserved online scoring only. Keep assistant serving behind ModelServingRuntime/model gateway. No training module may be imported by the online container. Preserve the same signed application artifact and profile-driven deployment. v2.20.0 CONTAINER BASELINE — all production runtime images, including isolated ML images, inherit/retain explicit non-root runtime users and profile-only secret/config injection. No training/online image bakes customer credentials or signing material. | Bring up each profile from a clean machine. Prove ppiq-ml-online admits online scoring only, has a warm-model readiness check, and fails a dependency test if a trainer module is imported. Prove training/batch saturation cannot consume the online reservation. All existing non-ML containers remain healthy. Inspect effective UID/GID for every production image and prove non-root. Scan built images for known runtime secret markers and fail on a match. | 12 | Not Started | Worker 1 | T-106; T-107; T-112; T-113; T-114; T-117; T-137; T-168; T-123 | T-141; T-185; T-192 | M3: 45 days after M2 completion | Release 2 MUST | Infrastructure/deployment | 3.2 | M3-P1 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 + T-107 + T-112 + T-113 + T-114 + T-117; T-137/T-168 runtime contracts ... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.3 | Deployment topologies |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-151 | M3 | P1 | Site defect burn-down | Backend | Site findings | Critical | Fix what soft testing finds, without changing the frozen visible contract unless a formal product decision is approved and recorded. | Each defect has a reproduction, a fix and a regression test. Any visible-contract change carries a written approval. | 12 | Not Started | Worker 1 |  |  | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-152 | M3 | P1 | Customer data edge cases | Database | Site findings | Critical | New source patterns, dirty data, unusual keys, timestamps, nulls, late arrivals and customer-specific mapping requirements, handled through the three doors. | Each case handled through import, registry or authoring. Any case requiring a code branch is escalated as a design gap. | 12 | Not Started | Worker 1 |  |  | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L2.3 | Canonical projection with validation, quarantine and reprocessing | L8.8 | Build | D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-153 | M3 | P1 | Connector certification against real sources | Backend | Connectors | Critical | Enable and certify the customer's actual connectors. A catalogue row is not a connector; an unbuilt one stays dimmed and badged as planned. | Each certified connector completes a read-only import against the real source with the load budget enforced. The customer-facing capability state changes to Certified only from the executed certification result; no frontend or website code edit is required. | 12 | Not Started | Worker 1 | T-224; T-225; T-226; T-254 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L1.1 | Read-only connection and source access | L1.4 | Validate | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-154 | M3 | P1 | Query plans, indexes and partition boundaries | Database | Performance | Very Important | Tune against real measurements from the customer's volumes, not against assumptions. | Before and after query plans recorded for the ten slowest queries, with the improvement measured. | 12 | Not Started | Worker 1 |  |  | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.5 | Sizing model and calibrated performance constants |  | Build | D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-155 | M3 | P1 | B-01/B-02 capacity tuning, scan amplification and model-serving memory | Infrastructure | Performance | Very Important | On site hardware, jointly execute resource measurements for lane max_concurrency/resource_capacity/compute_weight and the hard online reservation, plus scan-amplification and warm-model/assistant memory. This task supplies measured capacity values; it does not redesign the architecture. v2.22.0 — Absorb T-111 measured Scan Amplification baseline/calibrated bands. T-110 owns runtime enforcement. | Record hardware, commit and load profile. Saturate training/batch and prove online p95 remains inside the actionable budget. Publish measured lane values and before/after Scan Amplification with no starvation. v2.22.0 — Measure under declared profiles and record formula, numerator/denominator and scope; known missing delta predicate triggers breach, not a tuned threshold. | 12 | Not Started | Worker 3 |  |  | M3: 45 days after M2 completion | Release 2 MUST | Real-data AI/ML/site measurement | 4.32 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + site hardware | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.5 | Sizing model and calibrated performance constants | L8.4 | Build | D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | SOURCE FOUNDATION REVIEWED — SITE MEASUREMENTS UNVERIFIED | 8 | 14 | 24 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Workload/hook setup 3/5/8; measurement orchestration/analysis 3/5/9; governed result publication 2/4/7. | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:20-36 — benchmark metadata Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:32-75 — SelectedValueGuard | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-159 | M3 | P1 | C1 to C4 capacity certification | Infrastructure | Certification | Critical | Run the four Chapter 6 capacity profiles and site certification, consuming the measured benchmark outputs from B-01..B-09 where they affect sizing. Replace only CALIBRATION_REQUIRED/REFERENCE_ASSUMPTION constants with measured values and freeze Chapter 6 when all certification gates pass. v2.22.0 — Absorb T-111 capacity/regression certification; verify T-110 runtime scan guard using C1-C4 proofs. | Every worked sizing example recomputes from measured constants; C1-C4 profiles pass their promised envelope. The certification bundle records hardware, commit, dataset, benchmark outputs and sign-off. v2.22.0 — Known negative control exceeds scan band/aborts; restored predicate passes; results, workload, topology and sampled period pinned. | 12 | Not Started | Worker 3 |  | T-249 | M3: 45 days after M2 completion | Release 2 MUST | Real-data AI/ML/site measurement | 4.32 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + site hardware | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate | L8.5 | Certify | D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | FOUNDATION REVIEWED — CAPACITY CERTIFICATION NOT EXECUTED | 8 | 16 | 28 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Profile preparation 3/6/10; certification operation/analysis 3/6/11; reconciliation/sign-off evidence 2/4/7. | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:43-81 — evidence guard Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:65-90 — B-01..B-09 registry | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-160 | M3 | P1 | HA, DR and restore rehearsal | Infrastructure | Resilience | Critical | Production topology, RPO and RTO objectives, and a real disaster-recovery rehearsal. | A full recovery rehearsal completes within the stated RPO and RTO, witnessed and recorded. | 12 | Not Started | Worker 1 |  | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.7 | Backup, restore, PITR, DR and HA |  | Build | D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-163 | M3 | P1 | Monitoring, SLOs and support escalation | Infrastructure | Monitoring | Very Important | Operational dashboards, alerts, queue and latency and backup and certificate health, and the escalation path. | Each SLO has a measured baseline and an alert that fires before it is breached. | 12 | Not Started | Worker 1 |  | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P1 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Scale & OT Resilience | M3 P1 — Scale & OT Resilience. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.6 | Monitoring, observability, health and readiness |  | Build | D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-116 | M3 | P2 | API namespace migration, part 1: map the 92 prefixes onto the 27 domains and stand up dual-serve | Backend | Namespace | Very Important | Chapter 3 4.3 specifies 27 clean /api/{domain} domains. The repository registers 92 MapGroup prefixes and 544 verb-level routes, with 18 groups under /api/v5, 6 under /api/p15, plus /phase2, /phase4, /phase5, /api/phase8, /api/p09 and /admin/p03p04. Produce the mapping table, then serve both old and new paths during a transition window. v2.20.0 ORDERING — perform namespace renaming after T-256 has decided which material/legacy runtime surfaces remain legitimate compatibility surfaces. Do not preserve a semantically invalid endpoint merely to give it a cleaner URL. v2.22.0 — Maintain bounded-compatibility consumer register. Move live canon/public consumers to governed authorities before retiring compatibility objects; no delete-probes-first hotfix. | Every one of the 544 routes appears exactly once in the mapping table. Both the old and the new path return identical responses for a sample of twenty routes. v2.22.0 — Inventory each consumer/object, positive and negative parity tests, old history remains readable, retirement only after no active dependency remains; upgrade/fresh install agree. | 8 | Not Started | Worker 1 | T-256 |  | M3: 45 days after M2 completion | Release 2 MUST | Backend/domain contract | 1.2 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Converge | D3; D4; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — ROUTE-WIDE CENSUS NOT COMPLETE | 8 | 14 | 24 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Consumer/route inventory 3/5/8; safe dual routing and consumer convergence 3/5/9; parity/negative tests 2/4/7. | Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:16-66 — provenance dispatch and run resolution Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:69-90 — source/dataset existence lookup | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-117 | M3 | P2 | API namespace migration, part 2: migrate the clients and add the token gate | Backend | Namespace | Very Important | Move the ~177 frontend API client methods across 13 modules and the 72 methods on productCoreApiClient.runtime.ts onto the new paths. Then add a gate that fails the build when a registered route or a client base path contains a phase, version or task token. Schedule the removal of the dual-serve window as a named follow-up task rather than leaving it open indefinitely. v2.20.0 CLIENT-CONTRACT CONVERGENCE — retire the dynamic `productApi as legacyApi` dispatch slices while migrating paths. Migrated client modules use typed exported methods/contracts; do not retain `any` escape hatches as the permanent compatibility seam. | A test asserting no registered route matches /phase\d+¦\/v\d+\/¦p\d\d/. Open the browser network tab during the golden journey and confirm no request URL carries a phase or version token. Static gate: zero `productApi as legacyApi` in migrated API slices and no new `any`-typed escape for canonical clients. A deliberately removed client method fails TypeScript compilation rather than failing only at runtime. | 6 | Not Started | Worker 1 |  | T-122; T-194 | M3: 45 days after M2 completion | Release 2 MUST | Backend/domain contract | 0.9 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Converge | D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 0.9 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-127 | M3 | P2 | Canonical journey regression and the Continuity comparison | Testing | Continuity | Critical | Run J1 to J15 against a normal ppiq_app database with no presentation shortcut and no demonstration-only code path. Then run the Customer Contract Continuity comparison against the snapshots captured at the end of M1. | The journey passes on the canonical database. The continuity comparison shows no change to navigation, control placement, authoring flow, terminology or refusal semantics. Any difference is a defect in M2, not an improvement. | 12 | Not Started | Worker 2 | T-196; T-197; T-198; T-199; T-200; T-121 | T-194 | M3: 45 days after M2 completion | Release 2 MUST | Integration/E2E/certification | 4.08 | M3-P2 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: All Release 1 canonical-core/user-visible owners complete, including T-196/T-197/T-... | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Continuity green → W1 executes T-194; Release 1 release gate may close. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Build | D1; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 4.08 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-149 | M3 | P2 | Delete the legacy redirects and re-verify continuity | Frontend | Namespace | Very Important | Remove the roughly 20 legacy Navigate redirects and the live phase-token routes (/phase8/*, /phase9/*, /phase15/*) that App.tsx still declares among its 69 route paths, then re-run the Customer Contract Continuity comparison. | No route path matches /phase\d+/. The continuity comparison against the M1 snapshots still shows no change to any presented page. | 6 | Not Started | Worker 2 |  |  | M3: 45 days after M2 completion | Release 2 MUST | Frontend/UI feature | 1 | M3-P2 | M1 continuity frozen | Own route inventory/redirect cleanup only; do not touch W3 intelligence surfaces. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Converge | D2; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 1 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-161 | M3 | P2 | SSO and identity integration | Backend | Security | Very Important | Integrate the customer identity provider with the final role catalogue, account lifecycle and emergency access. | Account provisioning, de-provisioning and emergency access all tested against the customer directory. | 12 | Not Started | Worker 1 |  | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P2 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L7.1 | Users, roles, permissions, MFA and enterprise identity |  | Harden | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-162 | M3 | P2 | Site security hardening and sign-off | Infrastructure | Security | Critical | Network rules, secrets, certificate rotation, RLS and tenant proof, audit review. | A tenant-isolation proof from the database alone, plus a signed security review. | 12 | Not Started | Worker 1 |  | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P2 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L7.2 | Tenant isolation | L7.5 | Harden | D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-194 | M3 | P2 | Retire legacy API dual-serve aliases after canonical-client continuity proof | Backend | API namespace | Very Important | T-117 deliberately introduces a dual-serve transition while clients migrate. Close that transition explicitly after T-127 proves the canonical journey and continuity. Remove every legacy phase/version/task-token API alias, preserve only canonical /api/{domain} routes, and keep a machine-readable mapping artifact so support can interpret old logs without keeping old endpoints alive. | After T-127 is green, enumerate the route table and prove zero legacy alias remains. A representative old path returns the governed retired-route response or 404 according to the API policy, while the canonical path remains green. Re-run the route-token gate and a bounded canonical-journey regression. No frontend client calls an old alias. | 6 | Not Started | Worker 1 | T-117; T-127 |  | M3: 45 days after M2 completion | Release 2 MUST | Backend/domain contract | 0.9 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-117 + T-127 | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Converge | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 6 | 0.9 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-196 | M3 | P2 | C4 Plant Model Explorer canonical route and structural evidence surface | Frontend | Plant model | Very Important | Implement the missing Chapter 3 C4 /plant-model surface on the canonical plant authority. Show site/area/equipment hierarchy, search, unmapped-only state, selected-node details and the routes/operations that reference it. Unmapped equipment is explicit Amber evidence rather than silently dropped. The page is generic and uses imported plant vocabulary only. | Route /plant-model exists exactly once. Load a canonical reference plant and prove hierarchy/details match GET /api/plant/layout and /api/plant/equipment/{id}. Introduce one unmapped equipment reference and prove it is visible with its source object. Empty install renders the designed no-projection state. Keyboard tree traversal and RTL contract pass. | 8 | Not Started | Worker 2 | T-087; T-094; T-095 | T-127 | M3: 45 days after M2 completion | Release 2 MUST | Frontend/UI feature | 1.3333 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-094 + T-095 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L5.2 | Permanent relationship model |  | Build | D2; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.3333 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-197 | M3 | P2 | E6 Alert Routing and Escalation with delivery, retry and dead-letter evidence | Backend + Frontend | Alert routing | Very Important | Implement Chapter 3 E6 /alert-routing: routing rules over log/plant-data channels, severity, recipients, delivery channels, escalation delay, working hours/quiet periods, deduplication, grouping key, rate limit, suppression, test delivery, retry and dead-letter visibility. Entries are held during quiet periods, never silently lost. | Create and test a routing rule, force one delivery failure through its retry ceiling and prove it appears in dead letters with reason. Prove a rule with no recipient and an escalation with no escalation recipient are refused. Quiet-period traffic is held and later delivered. Role enforcement and audit evidence pass. | 10 | Not Started | Worker 2 | T-119; T-198 | T-127 | M3: 45 days after M2 completion | Release 2 MUST | Full-stack governed feature | 2.2857 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 + T-198 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L6.4 | Alert routing and escalation |  | Build | D2; D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 2.2857 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-198 | M3 | P2 | F5 Logging and Audit plus F6 Log Channel Configuration | Backend + Frontend | Logging administration | Critical | Implement the Chapter 3 canonical logging administration contract: /admin/logs with role-scoped System/Job/Data/Audit/Assistant/Plant Data families, filtering, live tail/replay, run correlation and export; plus /admin/log-channels for channel identity, severity mapping, routing/export target and reading roles. Built-in/audit channels are locked as specified; retention is read-only here and owned by F9. | Every permitted family is queryable and a forbidden family is absent for the role. Drop and resume the live stream and prove replay. Correlate one run across families. Audit has no edit/delete control. Create a custom channel, prove built-ins remain locked, and refuse an attempt to create/retarget the audit family. Canonical log tables and audit trail are used. | 12 | Not Started | Worker 2 | T-112; T-114; T-119 | T-127; T-197; T-199 | M3: 45 days after M2 completion | Release 2 MUST | Full-stack governed feature | 2.7429 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-112 + T-114 + T-119 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L6.6 | Plant data log, audit, log channels, retention and archival |  | Build | D2; D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2.7429 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-199 | M3 | P2 | F9 Log Retention and Archival with dry-run, legal hold and no-delete-on-archive-failure | Backend + Frontend | Log retention | Critical | Implement Chapter 3 F9 /admin/log-retention as the sole destructive log-history policy surface. Persist per-channel retention policy, archive-before-delete, destination, cleanup schedule/batch size, governed audit minimum and legal hold. Require pre-save dry-run impact. Cleanup history records cutoff, examined/archived/deleted rows, reclaimed storage, duration and failure reason. | Attempt audit retention below the governed minimum and refuse it. Save without preview and refuse it. Put a channel on legal hold and prove cleanup is blocked. Make the archive destination fail and prove zero rows are deleted. Complete one successful preview+cleanup and reconcile counts/history. Only Administrator can access the page. | 12 | Not Started | Worker 2 | T-124; T-198 | T-127 | M3: 45 days after M2 completion | Release 2 MUST | Full-stack governed feature | 2.7429 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-124 + T-198 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L6.6 | Plant data log, audit, log channels, retention and archival |  | Build | D2; D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2.7429 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-200 | M3 | P2 | F7 System Settings and F8 Translation/Language canonical administration | Backend + Frontend | System administration | Very Important | Implement Chapter 3 F7 /admin/settings and F8 /admin/translation. System settings own site identity, units/formats, plant time zone, documented retention defaults and per-tenant no-egress data boundary. Translation owns language packs, review/mirror-verification state, context-aware labels, import/export and fallback language. Presentation-era hardcoded translation tables become compatibility data only. | Change plant time zone through a confirmed action and prove the resulting setting is audited and used by a shift-aware display; toggle no-egress and prove affected capabilities report the new boundary. Add/edit a translation, mark review/mirror state, export and reimport a pack, and verify RTL rendering for Arabic. No machine-locale fallback silently changes formats. | 10 | Not Started | Worker 2 | T-113; T-119; T-216 | T-127 | M3: 45 days after M2 completion | Release 2 MUST | Full-stack governed feature | 2.2857 | M3-P2 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-113 + T-119 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Multi-user Enterprise Operations | M3 P2 — Multi-user Enterprise Operations. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L6.8 | Settings, time zone, units, localisation and translation |  | Build | D2; D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 2.2857 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-156 | M3 | P3 | Customer definitions built through the product | Frontend | Authoring | Very Important | Build and validate the customer's real pages, relationships, measures, analyses, models and log rules using the product's own authoring surfaces. | Every customer artifact exists as a definition in the store, created through the interface, with no manual database insert. | 12 | Not Started | Worker 2 |  |  | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P3 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own customer-facing UX/docs/website only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced BI, Authoring & Insight Boards | M3 P3 — Advanced BI, Authoring & Insight Boards. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L3.5 | One authoring shell, five purposes, two modes | L2.2 | Build | D2; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-166 | M3 | P3 | Five-product website production completion | Website | Public site | Important | CORRECTED IN v2.2. The redirect replacement, the portfolio page and the mega-menu are now M1 work, because the customer sees the company architecture in the room. What remains here is production completion of the five product pages: full content, proof sections, SEO and metadata, analytics, lead flows, localization, and the final honesty certification across every claim. AUDIT HARDENING IN v2.9.2. Production completion also certifies one coherent visual identity across all five product pages and shared public-site sections. Typography, UI primitives, graphical language, motion, responsive hierarchy and accessibility must come from the same design system used by the strongest PPIQ sections. Remove mojibake, visible HTML entities and locally invented low-quality box/flowchart styling; motion must reinforce meaning and degrade cleanly under reduced-motion preferences. | Each of the five products has a complete page under the Golden Rule product-page contract. Every claim passes the Chapter 6 6.2.10 honesty rule and the certification is recorded. Lead flow tested end to end on each page. Run a five-product visual-system audit at desktop, tablet and mobile. Zero mojibake/visible entities, text overflow, disconnected graphical connectors or page-local font/control systems. Automated visual/a11y checks are green, reduced-motion is honoured, and a reviewer comparison against the strongest PPIQ reference section records no page as visually less sophisticated. | 12 | Not Started | Worker 2 |  |  | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P3 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own customer-facing UX/docs/website only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced BI, Authoring & Insight Boards | M3 P3 — Advanced BI, Authoring & Insight Boards. Release 2 is heavy production / scale / deeper enterprise use. |  |  | BOUNDARY — SOU Website | SOU public website / portfolio boundary — not a PPIQ product capability |  | Build | D5 | Boundary | R2 | No maturity change |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-228 | M3 | P3 | Versioned InsightBoardPlan contract and deterministic validator | Assistant | Insight composition | Very Important | Define a versioned, reproducible InsightBoardPlan containing question, context snapshot, filters, evidence requirements, widget specs, planner version, definition versions and data-as-of. Deterministically validate registry, relationships, permissions, chart grammar and query safety. LLM cannot emit executable SQL/React authority. | Known valid plans validate; fabricated dimension, unsafe expression, unavailable relationship and permission violation refuse with typed reasons. Identical historical plan snapshot replays; asking later may produce a new version without mutating history. | 10 | Not Started | Worker 3 | T-090; T-092; T-134; T-179; T-180; T-181 | T-229; T-248 | M3: 45 days after M2 completion | Release 2 MUST | Kernel/contract | 3.2 | M3-P3 | After September customer RC; T-090/T-092 + T-134 + T-179..181. | New Assistant plan contract/tests only. | T-229 consumes validator; no direct UI generation. | Advanced BI, Authoring & Insight Boards | M3 P3 — Advanced BI, Authoring & Insight Boards. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L10.5 | Insight Board Composer |  | Build | D1; D5 | Advanced | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-229 | M3 | P3 | Governed Assistant plan-to-widget Investigation Board composition | Assistant/Frontend | Insight composition | Very Important | Execute validated InsightBoardPlan through existing Page Builder/widget/query contracts to create an ephemeral Investigation Board of KPIs/charts/tables/evidence without React/customer code generation. | Question -> validated plan -> real widget queries -> evidence-backed board. Every value resolves evidence, invalid chart grammar refuses, and ordinary authored pages remain unchanged. Board runs on both discrete and continuous fixtures. | 12 | Not Started | Worker 3 | T-228; T-134 | T-230 | M3: 45 days after M2 completion | Release 2 MUST | Cross-layer integration | 6.1714 | M3-P3 | T-228 + T-134 + stable Page Builder contract; coordinate UI consumption with Worker 2. | Assistant composition service; UI host changes require explicit W2 hand-off. | T-230 adds persistence; no separate rendering engine. | Advanced BI, Authoring & Insight Boards | M3 P3 — Advanced BI, Authoring & Insight Boards. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L10.5 | Insight Board Composer |  | Build | D2; D3; D5 | Advanced | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 6.1714 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-230 | M3 | P3 | Persisted Investigation Board version, replay and Save-as-Page handoff | Assistant | Insight governance | Important | Persist Investigation Board plan/result versions with question, context, filters, data-as-of, tool executions, definition versions, evidence handles and result snapshot. Add explicit Save-as-Page conversion into canonical definitions without mutating historical investigation evidence. | Historical board replays exactly as known at its data-as-of/version. Re-asking today creates a new version. Save-as-Page creates a normal Page Builder definition whose future refresh is independent while the original investigation remains immutable. | 12 | Not Started | Worker 3 | T-229; T-112; T-114 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | Persistence/integration | 5.1 | M3-P3 | T-229 + canonical definition/evidence persistence + T-112/T-114. | Investigation board persistence and conversion contract. | Page Builder owns resulting page definitions; Assistant owns historical investigation artifact only. | Advanced BI, Authoring & Insight Boards | M3 P3 — Advanced BI, Authoring & Insight Boards. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L10.5 | Insight Board Composer |  | Build | D2; D5 | Advanced | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 5.1 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-248 | M3 | P3 | Advanced enterprise BI and authoring parity closure against the 75-item outcome matrix | Frontend | Enterprise BI / Authoring | Very Important | Close the Release-2 remainder of the founder-approved F01-F15, S01-S30 and E01-E30 outcome matrix using native PPIQ semantics. Explicitly include Scoped Measure Context, Named Comparison State, pending lasso/range confirm-cancel, story/live-source return, complete current-state export matrix, advanced exploration, mini-overview navigation where applicable, and reusable versioned subflows as the PPIQ equivalent of script Include/Must_Include. v2.20.0 ENTERPRISE-BI PARITY EXPANSION — the 75-item matrix explicitly includes context-sensitive property inspection, named selections/bookmarks, pivot/crosstab or governed PPIQ-equivalent, conditional formatting, export/print fidelity, design-token/theme governance, accessibility/keyboard authoring, and removal of localStorage as a fallback for server-owned page/widget layout state. v2.20.0 AUTHORING-SEMANTICS CONVERGENCE — close the historical T-242/Layer-B placement contradiction without reopening T-242. For newly authored definitions, arithmetic/comparison/logic are expression configuration inside the block they configure, while FOR/WHILE-style control flow is Job orchestration. Existing persisted T-242 definitions remain reopenable through an explicit compatibility translation/representation; do not strand customer-authored history. v2.22.0 — Add G3 global search/command palette and G6 activity tray, preserving role/tenant scope, keyboard/focus, cross-page progress and reconnection. Use UI/Figma companion frames as visual implementation reference, not new behavior authority. | A 75-row acceptance matrix has no Unowned or Missing row. Every row is Implemented or PPIQ-Equivalent, has an automated/visual acceptance or an explicit non-applicability proof, and no proprietary Qlik syntax is required. Comparative acceptance against the defined PPIQ outcomes demonstrates no missing enterprise authoring row for inspector/style, bookmark/selection, pivot/crosstab, formatting, export and accessibility. Server-owned layouts survive a clean browser profile with localStorage cleared. Raw component colour literals are within an explicit design-token allowlist. A new definition authors arithmetic/logic through expression configuration and schedules repetition/control flow through the Job authority. A persisted legacy T-242 board definition reopens with semantic equivalence and an explicit compatibility marker; save-as-new converges to the current representation without losing history. v2.22.0 — Search scopes results/actions correctly; keyboard select/escape; tray shows run identity/state/progress with polling fallback and no fake percent; empty/failed/denied variants; existing 75-item authoring/BI acceptance retained. v2.23.0 — Use the accepted T-267 semantic/interaction matrix and per-scene handoffs for the existing 75-item parity contract. Do not reimplement or defer the M2 associative engine/selection behavior already accepted under T-204. A visual omission creates a design obligation, not a reopened product task without regression. | 30 | Not Started | Worker 2 | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257; T-267 | T-249; T-263 | M3: 45 days after M2 completion | Release 2 MUST | Bounded product convergence | 11.2 | M3-P3 | After M2 Release 1 and InsightBoard authoring base | Frontend BI / authoring only | Reuse the existing BI engine, Page Builder, Canvas, export and selection contracts; do not build a second dashboard engine. | Advanced BI, Authoring & Insight Boards | M3 P3 — advanced enterprise parity. M2 ships the Day-1 enterprise core; M3 closes the advanced authoring matrix. |  |  | L3.7 | Authoring professionalism | L3.1; L3.3; L3.4; L3.5; L3.6; L3.9; L6.7 | Build | D2; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — ALL 75 OUTCOMES NOT CERTIFIED | 24 | 40 | 64 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Remaining outcome mapping 4/6/10; advanced UI/runtime integration 14/24/38; parity/accessibility/recovery acceptance 6/10/16. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:1-55 — state and query orchestration Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — reopen application | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-263 | M3 | P3 | Governed reports, export and scheduled delivery | Product / Integration | Governed reports, export and scheduled delivery | Very Important | Deliver E5 report definitions, sections, period, recipients, scheduled generation and output/delivery history using definition_store, the shared Job scheduler and permission/evidence boundaries. | Create/reopen versioned report; generate by manual/scheduled run; empty-section refusal; tenant/role-scoped download; light report rendering; delivery retry/audit; same source evidence and filters survive export; no private report scheduler. |  | Not Started | Worker 2 | T-106; T-248 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | Governed product integration |  | M3-P3 | Consume accepted producer contracts; remaining dependencies: T-106; T-248. No private scheduler/definition authority. Source-present is not closure proof. | Semantic product filenames only. CENTRAL assigns shared file locks before overlapping worker writes. | Reuse current canonical authorities; no shadow lifecycle/registry/scheduler. | Advanced BI, Authoring & Insight Boards | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L6.5 | Reports, export and scheduled delivery | L2.6; L6.4 | Build | D2; D3; D4; D5 | Core | R2 | Advances |  | UNESTIMATED — new/recognized task; owner calibration pending. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-267 supplies E5 report-definition/generation/history/delivery interaction design. Generation remains a governed job; preserve period/filter/permission context and the existing source-evidence boundary. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | UNESTIMATED |  |  | SOURCE REVIEWED — SUBSTANTIAL REPORT FOUNDATION / LIFECYCLE GAP | 16 | 26 | 42 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Definition/editor/history 6/10/16; job/output/delivery integration 6/10/16; permission/empty/fidelity/retry tests 4/6/10. | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report routes Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:57-85 — existing report service/PDF path | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-128 | M3 | P4 | Feature store, outcome store and immutable snapshot metadata | AI+ML | Intelligence store | Critical | Implement canonical feature/outcome stores and immutable snapshot metadata using generic analysis_subject_id + grain_code identity, never a universal material_unit_id. Persist semantic-manifest lineage, feature-set/outcome definitions and dirty/incremental state. Training still consumes sealed typed snapshot artifacts, not live JSONB. | Persist features/outcomes for at least one discrete subject and one equipment/process-window subject using the same schema/runtime. No material-unit FK is mandatory for non-material subjects. Snapshot/hash/reproducibility and tenant/RLS gates pass. | 10 | Not Started | Worker 3 | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114; T-231; T-210 | T-129; T-130; T-131; T-135; T-146; T-147; T-184; T-186 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.5 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-087..T-105 + T-112 + T-114 security/tenant hand-off. Outcome semantics from... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.3 | Feature engineering and incremental feature refresh | L9.5 | Build | D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-129 | M3 | P4 | Compute runs, findings and common evidence persistence | AI+ML | Intelligence store | Critical | Unify compute run records, terminal refusal states, gate state/evidence, correlation/findings persistence and evidence handles on the common intelligence substrate. Every new governed run carries semantic_manifest_id once T-183 is present. A refusal is a persisted result state, never an exception-shaped blank screen. | For FINDING and each refusal class, resolve the row to run, manifest, gate evidence and source evidence. Break an evidence handle and prove the result is rejected. Break manifest coverage and prove G-55 refuses the new governed run. | 12 | Not Started | Worker 3 | T-128; T-183; T-112; T-114 | T-134; T-135; T-146; T-147; T-186; T-188 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-128 + T-183 + T-112 + T-114. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L5.5 | Provenance, evidence chain, claim guard and refusal integrity | L4.2; L4.4 | Build | D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-130 | M3 | P4 | Model registry, serving identity, activation and fallback | AI+ML | Model lifecycle | Critical | Implement ppiq_plant.model_registry per serving identity (tenant_id, model_code, outcome_code, grain_code) plus model_version. status and serving_role are independent; at most one active and one approved fallback exist per serving identity, and one version can never be both. There is no ModelBundle. Store artifact identity, semantic_manifest_id, acceptance floors, quality/serving/training metrics and drift observations. Promotion policy itself is implemented by T-176 and wired by T-187. | Create two serving identities with identical model_code but different outcome/grain and prove independent activation. Attempt duplicate active/fallback rows and primary=fallback and prove the database refuses them. Activate, retire and fall back atomically with every transition audited and manifest-resolvable. | 12 | Not Started | Worker 3 | T-128; T-183; T-112; T-114 | T-134; T-135; T-139; T-188; T-191; T-193; T-246 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-128 + T-183 + T-112 + T-114. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.8 | Model registry, promotion, serving and fallback |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-131 | M3 | P4 | Practice signature, windowing, context and cohorts | AI+ML | Practice learning | Critical | Implement the production practice-learning core: canonical signature construction, parameter windowing, declared context and comparison cohort. The engine consumes governed data-product contracts only and contains no source table/industry vocabulary. Persistence and the D10 surface remain T-133. | Against the certified M2 reference dataset, recover the planted good-practice band and refuse/avoid the null control. Run a genericity test showing the kernel receives only semantic codes/data-product fields, never source identifiers. | 12 | Not Started | Worker 3 | T-086; T-128; T-171 | T-132; T-133; T-136; T-142; T-240 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-086 + T-128 + T-171 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-132 | M3 | P4 | Support, confidence, back-off ladder and tolerance sensitivity | AI+ML | Practice learning | Critical | Add support/confidence ranking, sparse-cohort back-off, resampling stability and tolerance sensitivity to practice learning. A result that changes materially under reasonable tolerance changes is explicitly marked sensitive rather than promoted as stable. | A stable practice survives resampling and is ranked with support. A sparse cohort walks the declared back-off ladder. Widen tolerance and prove a flipping practice is marked sensitive with the tested settings persisted. | 12 | Not Started | Worker 3 | T-131 | T-133; T-136; T-142; T-240 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-131 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-133 | M3 | P4 | Practice persistence, drift and canonical D10 Practice Insights | AI+ML | Practice learning | Very Important | Persist practice_statistics/signatures with semantic_manifest_id and evidence, implement practice drift against the plant's own demonstrated best, and replace the M1 presentation adapter behind D10 with canonical sources without changing the frozen D10 visible contract. | Move operating data away from the learned band and prove drift is detected, persisted and surfaced with evidence. Run the M1 continuity snapshot for D10 and prove no route, control, wording or state-semantics regression. | 12 | Not Started | Worker 3 | T-131; T-132; T-183 | T-134; T-136; T-240 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-131 + T-132 + T-183 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 |  | Build | D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-134 | M3 | P4 | Bindable intelligence registry and evidence handles | AI+ML | Intelligence store | Critical | Make intelligence a first-class bindable source through registry_intelligence_sources. Fact-shaped measures may project through WidgetFact; native-grain rich sources retain declared columns. Predictions, findings, practice, readiness and model-state sources appear in the normal authoring shell with resolvable evidence. v2.10.2 PHASE CORRECTION — this task builds the generic bindable-intelligence registry/evidence mechanism and registers only canonical sources that actually exist at this point. Do not promise prediction bindings before T-139 creates canonical predictions; T-139/T-189 register those sources later through the same mechanism. | Bind one fact-shaped and one native-rich intelligence source through the standard authoring shell, filter/drill both and open evidence. Break an evidence handle and prove the widget refuses rather than rendering an uncited number. No ML-specific widget branch exists. | 12 | Not Started | Worker 3 | T-090; T-095; T-096; T-129; T-130; T-133; T-186; T-139 | T-138; T-228; T-229 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 definition authority + T-095/T-096 relationship resolver + available ca... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L5.5 | Provenance, evidence chain, claim guard and refusal integrity | L3.4 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-135 | M3 | P4 | Tenant-aware uniqueness across the intelligence tables | Database | Intelligence store | Very Important | Apply tenant ownership, tenant-first uniqueness and RLS to every new intelligence table in the frozen design, including model, prediction, practice, index-generation, capability/readiness and run/evidence tables. Semantic manifests use manifest_id PK plus UNIQUE(tenant_id, manifest_hash). v2.10.2 SECURITY-RATChET RULING — T-135 is not the first time RLS is applied. T-112/T-114 establish the mandatory pattern before Release 2 persistence. T-135 audits current intelligence tables and adds/extends the architecture ratchet so every future tenant-owned intelligence table fails CI if tenant_id, tenant-first uniqueness or FORCE RLS is missing. | Insert identical natural keys for two tenants and prove both persist. Prove cross-tenant reads fail from the database alone. The architecture test fails when any new tenant-owned intelligence table lacks forced RLS or tenant-first uniqueness. | 10 | Not Started | Worker 3 | T-112; T-114; T-128; T-129; T-130; T-183 | T-184; T-185; T-186; T-187 | M3: 45 days after M2 completion | Release 2 MUST | DB/schema/migration | 1.9375 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-112 + T-114 + current Release 2 persistence tables (including T-128/T-129/T-130/T... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L7.2 | Tenant isolation |  | Build | D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.9375 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-136 | M3 | P4 | Incremental practice recomputation | AI+ML | Practice learning | Important | Make practice recomputation incremental using Release 1 stage watermarks and changed-population contracts. Recompute only affected cohorts/signatures and preserve prior immutable evidence for unaffected historical results. | Add one day of data and prove recomputation scans a bounded delta, Scan Amplification stays inside the declared baseline, and unaffected practice rows/evidence hashes do not change. | 10 | Not Started | Worker 3 | T-131; T-132; T-133; T-109 |  | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.5 | M3-P4 | T-109 + T-131..T-133 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-138 | M3 | P4 | Canonical Assistant runtime cutover: planner, retrieval, evidence packing, serving and verifier | AI+ML | Chatbot | Critical | After M1 continuity is frozen and canonical intelligence is available, replace M1 retrieval/prepared-state internals behind the unchanged dock. Wire T-179 planner, T-180 retrieval/evidence packer, T-137 ModelServingRuntime and T-181 verifier. Structured Layer A/B tools take precedence. Expose stable CompareOperationalPeriods (T-237) and GetCompositePractices (T-240) when those producer contracts are complete; their absence must degrade honestly rather than block the core Assistant cutover. v2.20.0 PROVIDER-TRUTH RULING — provider names are capabilities, not aliases. Advertise Azure OpenAI, AWS Bedrock or any BYOM provider only when a concrete adapter/conformance path implements that provider's authentication, endpoint and response contract. OpenAI-compatible HTTP may serve only providers actually conforming to that contract. | Re-run the certified M1 question pack and continuity snapshot. Every numeric claim resolves to a supplied handle, permission filtering occurs before ranking, truncation is disclosed, an engine refusal stays a refusal, and a fabricated/unsupported claim is blocked before display. No prepared presentation corpus is required. Provider-conformance tests prove every advertised provider has a concrete adapter path. A provider label mapped only to the generic OpenAI-compatible client without declared conformance is unavailable rather than advertised. | 12 | Not Started | Worker 3 | T-179; T-180; T-181; T-137; T-134; T-188 |  | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-137 + T-179..T-181 + T-134 + T-188 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L6.2 | Governed Assistant runtime |  | Converge | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-139 | M3 | P4 | prediction_runs, predictions and prediction_current | AI+ML | Prediction | Critical | Persist prediction_runs, predictions and prediction_current per serving identity and generic analysis_subject_id + grain_code. A prediction may target a material unit, equipment state, campaign, batch or process window according to the published grain definition; no universal CoilId/material-unit assumption. | Same prediction contract stores and retrieves at least one discrete subject and one non-material equipment/process-window subject, preserving evidence, horizon, uncertainty and tenant isolation. | 12 | Not Started | Worker 3 | T-130; T-187; T-231 | T-134; T-140; T-141; T-142; T-189; T-193 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-130 + T-187 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-140 | M3 | P4 | Prediction drivers and comparables, persisted | AI+ML | Prediction | Critical | Persist prediction drivers, explanation metadata and comparable historical cases as evidence-grade rows. Drivers come from the governed explanation artifact and comparables from the served similarity generation; the UI never computes or narrates them from scratch. | Open a prediction and resolve every driver/comparable to persisted model/index/evidence identity. Delete/deny the rows and prove the consuming surface refuses rather than inventing an explanation. | 12 | Not Started | Worker 3 | T-139; T-173; T-176 | T-142; T-189 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-139 + T-173/T-176 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-141 | M3 | P4 | Actionable deadline and latency health | AI+ML | Prediction | Very Important | Implement actionable_deadline_utc, delivery_latency_seconds, scoring_mode and met_actionable_deadline. Tie online scoring to the hard-reserved ml.online_scoring lane. A late prediction is historical evidence, never actionable. | Saturate training and batch, submit online scoring and measure that the reserved lane still serves. Force a prediction past its actionable deadline and prove it is persisted as late and excluded from actionable presentation. | 12 | Not Started | Worker 3 | T-107; T-122; T-139; T-187 | T-189 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-107 + T-122 + T-139 + T-187 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates | L8.6 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-142 | M3 | P4 | Remediation candidate generation from the customer's own history | AI+ML | Remediation | Critical | Generate remediation candidates from the customer's own governed history by finding comparable early conditions with better later outcomes and the later-stage practices that differed. Persist support, effect range, limitations, evidence and the semantic/model/index identities used. No candidate is a control instruction. | On the certified M2 reference dataset, every emitted candidate meets the declared support threshold, has a bounded effect range and resolvable comparable evidence. Insufficient-support candidates do not emit. No source-system write API is reachable. | 8 | Not Started | Worker 3 | T-131; T-132; T-139; T-140 | T-143; T-189; T-190 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.2 | M3-P4 | T-131/T-132 + T-139/T-140 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-143 | M3 | P4 | Integrate the nine-check remediation gate, can_accept and suppression | AI+ML | Remediation | Critical | Wire the pure decision kernel from T-178 into prediction/remediation persistence and API contracts. Eligibility is per prediction. can_accept is the complete server authority and the client never re-derives it. Outcomes are actionable, evidence_only, exploratory or suppressed; suppressed rows are audited and never shown. | Run one persisted/API case per nine-check failure and per can_accept condition. Prove the same template can be suppressed for one prediction and actionable for another. Search every consuming API/UI payload and prove a suppressed candidate is absent. | 8 | Not Started | Worker 3 | T-178; T-142 | T-144; T-189; T-190 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.2 | M3-P4 | T-178 + T-142 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates |  | Validate | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-144 | M3 | P4 | Accept, Reject and Defer with action recording | AI+ML | Feedback loop | Critical | Implement Accept, Reject and Defer behind the server-authoritative can_accept boundary, with actor, timestamp and reason. Each decision creates the governed action/decision state only when allowed. PPIQ records human action and never issues a plant control command. | Exercise all three decisions with can_accept true and false. Allowed actions persist actor/reason/state; disallowed actions fail server-side even if a client is modified. A dependency/network test proves no customer-source write/control client is reachable. | 8 | Not Started | Worker 3 | T-143 | T-145; T-190 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.2 | M3-P4 | T-143 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L9.3 | Decision capture | L9.4 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 1.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-145 | M3 | P4 | Outcome capture, evaluation and escalation | AI+ML | Feedback loop | Critical | Capture observed outcomes, prediction/remediation evaluation and escalation records. Intervened instances are reported separately from ordinary prediction-accuracy metrics. Escalation is a record, never an automatic decision. v2.22.0 — Own canonical outcome, effectiveness and feedback quality/poisoning boundary. Retire the parallel hand-entered Phase-8 outcome authority with T-190; do not delete historical evidence unsafely. | Accept a candidate, let the outcome arrive and prove evaluation closes the loop with intervention state preserved. Confirm intervened instances are excluded from ordinary accuracy calculation and an escalation creates no action automatically. v2.22.0 — Canonical-only outcome (DC03), complete action record before eligible feedback, actor concentration DC07 evidence, eligible-only supervisor proposals, feedback IDs retained and no auto-retraining. M2 unsafe route denial belongs to T-113. | 8 | Not Started | Worker 3 | T-144 | T-190; T-193 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.2 | M3-P4 | T-144 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L9.5 | Canonical outcome capture | L9.6; L6.4; L9.8 | Build | D3; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | SOURCE REVIEWED — CANONICAL LOOP MISSING / LEGACY CONFLICT | 14 | 24 | 40 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Canonical persistence/evaluation 6/10/17; feedback/poisoning/escalation rules 5/8/13; migration/negative tests 3/6/10. | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — manual outcome DTO Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:66-90 — record calculation Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-48 — process-memory endpoints | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-146 | M3 | P4 | Converge the production statistical engine onto the certified method kernel | Engine | Consolidation | Very Important | Use the schema-independent statistical kernel from T-177 to converge the runtime onto one readiness-gated engine and retire the direct-SQL/superseded compute paths. Persist method, aligned population/group sizes, effect size, p-value, FDR/q-value, gate evidence and truthful exclusion reason. This is the production wiring/cutover task; do not perform it before M1 presentation continuity is frozen. v2.22.0 — Converge production statistical methods and discipline onto the accepted authorities; StatisticalDiscipline.cs contains currently consumed EffectRanking, BenjaminiHochberg, Stratification and Bootstrap functions and is not dead code. Converge only measured duplicate execution authorities after consumer and test obligations move; preserve these live discipline functions. No performance/style-only rewrite. | Only one production correlation engine is reachable. Known-answer fixtures cover Numeric×Numeric, Binary×Numeric, Categorical×Categorical and Numeric×Categorical. Numeric×Categorical selects ANOVA when assumptions hold and Kruskal-Wallis otherwise. Constant, unsupported and insufficient-sample cases retain distinct reasons. Re-run the M1 analysis continuity checks and prove no visible regression. v2.22.0 — One production discipline path; known-answer regression and required FDR/effect/stratification/refusal outputs survive. Reuse accepted kernel evidence; absence of callers alone is not justification to erase future integration work. | 10 | Not Started | Worker 3 | T-147; T-177; T-128; T-129 |  | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.5 | M3-P4 | T-147 COMPLETE + T-177 + T-128/T-129; M1 presentation continuity frozen. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.2 | Statistical engines MF-05 / MF-06 |  | Build | D3; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | SOURCE REVIEWED — PRIOR DEAD-FILE FINDING DISPROVEN | 8 | 14 | 24 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Pairing/result-contract cutover 3/5/9; producer/persistence convergence 3/5/8; known-answer/refusal regression 2/4/7. | Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:49-62 — readiness/old selector Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:91-115 — live discipline calls Backend/PlantProcess.Application/Analytics/Advanced/AdvancedCorrelationComputeService.cs:117-137 — live ranking/FDR/bootstrap Backend/PlantProcess.Analytics.Core/Kernel/KernelMethodSelector.cs:27-57 — kernel pairing | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-147 | M3 | P4 | Fix the outcome namespace, grain assignment and ordinal loader | Engine | Consolidation | Critical | Converge outcome namespace, grain ownership and ordinal/categorical loading on the canonical outcome store. Refresh must never silently reassign grain, and ordinal/categorical labels/classes are preserved as real outcomes rather than coerced to fake numeric targets. v2.10.1 SM-06 CONSUMPTION. Converge Engine-side outcome consumption on the canonical published SM-06 OutcomeDefinition and canonical outcome store. Consume — never redefine — outcome_type, class taxonomy, ordinal rank map, outcome-specific grain, detection_position_code, detection_timestamp_field, direction, unit and censoring policy. The two detection fields are the leakage anchors consumed by G-06. Refresh may not silently reassign grain, classes or outcome semantics, and categorical/ordinal outcomes remain real classes rather than fake numeric targets. | One namespace across registry, store and engines. Grain survives refresh. Load ordinal/multiclass outcomes and prove class labels/counts seen by T-177/T-146 exactly match the store without manual repair. For a published SM-06 definition, prove the Engine receives exactly the canonical grain, classes/ranks, direction/unit/censoring semantics and detection_position_code/detection_timestamp_field. Inject a feature that becomes available only after the declared detection anchor and prove G-06 blocks it fail-closed. Publish a new outcome-definition version and prove an older run/snapshot continues to resolve the old semantics rather than being silently reinterpreted. | 12 | Not Started | Worker 3 | T-090; T-128; T-129; T-177 | T-146 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 canonical SM-06 binding + T-128/T-129 + T-177; complete BEFORE T-146 fi... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L5.3 | Analysis Subject, grain and signal aggregation authority | L4.2 | Correct | D1; D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-157 | M3 | P4 | Practice, prediction and model calibration on real data | AI+ML | Calibration | Very Important | With a longer real-data window, execute governed retraining/calibration, OOT/subgroup/missingness/explanation-stability checks, drift review and the site portions of B-05/B-06. Tune only benchmark-open parameters; no gate threshold is weakened to make a model pass. | Each served model has a governed retraining/evaluation record, calibration evidence, drift decision and reproducible manifest. Any encoder/ANN choice is supported by the recorded benchmark against its simpler/exact baseline. | 12 | Not Started | Worker 3 |  |  | M3: 45 days after M2 completion | Release 2 MUST | Real-data AI/ML/site measurement | 4.32 | M3-P4 | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + customer data window | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.8 | Model registry, promotion, serving and fallback | L4.4; L4.7 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 4.32 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-158 | M3 | P4 | Remediation validation against real process constraints | AI+ML | Remediation | Very Important | Validate remediation actionability, support thresholds, controllability and process-stage timing against the customer's real constraints. The human approval/read-only boundary remains absolute. | Validate all nine checks against real constraints and replay at least one allowed and one refused case. No path permits automatic plant control and all refusal evidence is retained. | 12 | Not Started | Worker 3 |  |  | M3: 45 days after M2 completion | Release 2 MUST | Real-data AI/ML/site measurement | 4.32 | M3-P4 | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + customer data window | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 4.32 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-164 | M3 | P4 | The Value Engine | Backend | Value | Critical | Build value_impacts, cost_assumptions, the value realisation ledger and D7 Value Dashboard, honouring the two-downtime-quantity rule. Consume exact operational-period driver quantities from T-237 and transition/stabilisation evidence from T-235/T-236 so setup/changeover/ramp-up loss can be priced without inventing quantities. This is the only authority that converts assumption-based operational impact into bounded money. | A euro figure is only ever shown as a bounded range with its assumptions visible and its evidence resolvable. No number without evidence. | 12 | Not Started | Worker 1 | T-237; T-235 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P4 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L9.7 | Value engine |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-165 | M3 | P4 | Commercial capacity finalisation and the sales calculator | Backend | Commercial | Very Important | Validate the real user, page, job, DB-link and data bands against measured infrastructure, and build the Sales Administration and capacity calculator from Chapter 6 6.3.8. v2.22.0 — Explicitly deliver infrastructure-cost formula Ch6 6.3.5 and licence-price function 6.3.6 with their separate assumptions and units; avoid conflating entitlement with commercial price. | A quote produced by the calculator matches the measured server class for the same inputs. v2.22.0 — Known-answer cost and price inputs/outputs; unit/currency/time basis; invalid/missing assumptions refuse; customer figures not fabricated. | 12 | Not Started | Worker 1 |  |  | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P4 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L7.6 | Commercial capacity model and licence-price function | L7.7 | Build | D3; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — CALCULATOR NOT ESTABLISHED | 8 | 14 | 24 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Formula/input authority 3/5/8; sales calculator surface/integration 3/5/9; known-answer/refusal tests 2/4/7. | Website/PlantProcess.Website/src/components/proof/PricingLicenseMatrix.tsx:1-49 — plan display Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:17-26 — selected measured value identity | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-183 | M3 | P4 | Semantic Contract Manifest persistence, resolver and G-55 coverage | Backend | Semantic reproducibility | Critical | After Release 1-P1/P2 establish final definition/relationship authority, implement ppiq_meta.semantic_manifests as immutable tenant-owned reproducibility pins: manifest_id UUID PK, tenant_id, manifest_hash, referenced definition versions, relationship publication, registry/configuration hashes and UNIQUE(tenant_id, manifest_hash). Build ManifestResolver and semantic_manifest_id references on governed run/artifact/evidence tables. Legacy rows may be null; every new governed AI/ML execution must resolve a manifest. | Create identical content in two tenants and prove separate rows; identical content twice in one tenant reuses the same manifest. Attempt mutation and refuse it. Start a new governed AI/ML run without a resolvable manifest and prove G-55 refuses before output persistence. A changed answer can be traced to a manifest diff. | 12 | Not Started | Worker 3 | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114 | T-129; T-130; T-133; T-135; T-184; T-185; T-186; T-187; T-192 | M3: 45 days after M2 completion | Release 2 MUST | Backend/domain contract | 1.8 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-089..T-105 canonical definition/relationship authority + T-112 + T-114 secu... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L5.8 | Truth contracts and claim boundaries | L5.5 | Build | D1; D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-184 | M3 | P4 | Snapshot Materialiser: seal feature state into typed artifacts and enforce G-48 | AI+ML | Training data path | Critical | Wire T-169 into production as the Snapshot Materialiser. It is the sole component permitted to read feature_store for sealing; training/encoding consume only the immutable typed artifact. Persist hash/format/size/row-count/semantic_manifest_id and optional declared audit sample. No full duplicate JSONB training population. v2.10.2 BENCHMARK-STATE RULING — persist the artifact format actually used for each snapshot, but do not call one format the universal/site-selected winner merely because T-169/T-182 synthetic smoke runs. Selection remains measurement/site evidence; the materialiser must support explicit configured candidate identity. | Seal a snapshot, mutate live feature_store, then train/read through the artifact and reproduce the original input. Architecture gate G-48 fails if any trainer/encoder queries feature_store directly. Corrupt the artifact and prove hash verification refuses it before training. | 12 | Not Started | Worker 3 | T-128; T-169; T-183; T-112; T-114; T-135 | T-187; T-192 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-128 + T-169 + T-183 + T-112/T-114/T-135 security ratchet. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.3 | Feature engineering and incremental feature refresh |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-185 | M3 | P4 | sequence_manifests persistence and object-storage sequence path | AI+ML | Training data path | Critical | Wire T-170 into production: ppiq_plant.sequence_manifests stores subject/channel/time/count/hash/storage/chunk metadata while object storage holds immutable numeric payload chunks. Integrate retention/backup identity and bounded loader access. PostgreSQL stores no numeric sequence arrays. v2.10.2 BENCHMARK-STATE RULING — chunk/compression policy remains configured/recorded until representative/site B-04 evidence freezes it. Persist exact codec/chunk identity per manifest; do not hide the choice behind an unmeasured global default. | Persist and reload a large multi-chunk sequence with manifest/content verification and bounded memory. Search the canonical schema and prove no numeric sequence payload array column exists. Restore the artifact/DB pair and reproduce the sequence; a missing chunk produces a typed refusal. | 12 | Not Started | Worker 3 | T-170; T-183; T-122; T-112; T-114; T-135 | T-187; T-192 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-170 + T-183 + T-122 final object-storage/container path + T-112/T-114/T-135... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.3 | Feature engineering and incremental feature refresh |  | Build | D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-186 | M3 | P4 | Persist capability profiles, prediction points and the model-count governor | Engine | Readiness | Critical | Persist the T-171 capability profile per outcome/grain/manifest and implement governed prediction-point candidates plus the model-count governor. Only capabilities supported by measured data become eligible; collapsed dimensions and refusal reasons remain visible. Prediction points are activated under policy rather than multiplying models blindly. v2.22.0 — Persist and integrate CapabilityProfiler while preserving one readiness decision authority; coordinate T-146 consumers so a second production readiness result cannot disagree. | On one rich and one sparse reference population, persist different capability states with their measured basis. Generate prediction-point candidates and prove the governor caps/chooses them deterministically. An unsupported model family remains MODEL_NOT_READY/NOT_APPLICABLE rather than creating a placeholder model. v2.22.0 — Same population/definition/manifest yields same gate decision at all consumers; values/thresholds/refusal evidence visible; missing data fail-closed. | 12 | Not Started | Worker 3 | T-171; T-183; T-128; T-129; T-195; T-135 | T-134; T-187; T-188; T-192 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-171 + T-183 + T-128/T-129 + T-195 canonical readiness thresholds + T-135 se... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.1 | Readiness gate and statistical discipline chain | L4.8 | Build | D3; D4; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | SOURCE REVIEWED — KERNEL REUSABLE / PERSISTENCE AND WIRING GAP | 8 | 14 | 24 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Persistence/versioning 3/5/9; point/governor/consumer integration 3/5/8; deterministic/negative tests 2/4/7. | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:8-19 — pure kernel boundary Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:36-64 — profile calculation Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:69-96 — dimension assessment | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-187 | M3 | P4 | Production training/index integration: snapshots → ML lanes → registry activation | AI+ML | ML integration | Critical | Integrate T-168 runtime, T-172/T-174/T-175 learned families, T-173 index builder, T-176 promotion, T-183 manifests and T-184/T-185 artifacts with the Release 1 scheduler lanes. Training/index jobs consume sealed artifacts, checkpoint where declared, write governed result manifests and register candidates; only gate-approved versions activate. No daytime request enters training. v2.10.2 BENCHMARK-STATE RULING — integration may activate a candidate only against the declared frozen acceptance metrics for the environment. It must record candidate/runtime/index/artifact identities and may not convert synthetic benchmark smoke into a universal production selection. Site B-05/B-06 choices are frozen by T-157; final B-01..B-09 sizing/selection evidence is consumed by T-159. | Run a full candidate job from sealed snapshot through training/evaluation/registry. Prove direct feature_store access is absent, a failed gate cannot activate, a passed candidate activates atomically per serving identity, and online serving remains available while training/batch are saturated. MF-02 recall floor blocks an inadequate index. | 12 | Not Started | Worker 3 | T-168; T-169; T-170; T-171; T-172; T-173; T-174; T-175; T-176; T-183; T-184; T-185; T-186; T-107; T-109; T-112; T-114; T-135; T-195 | T-139; T-141; T-191; T-192; T-193; T-246 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-107 + T-109 + T-168..T-176 + T-183..T-186 + T-112/T-114/T-135 + T-195. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.4 | Learned models MF-01 / MF-03 / MF-04 | L4.5; L4.8 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-188 | M3 | P4 | Canonical D4 Findings and D8 ML Readiness/Models cutover | Frontend | Intelligence surfaces | Critical | Replace the M1 presentation adapters behind D4 Findings and D8 ML Readiness/Models with canonical run/finding/capability/model-registry sources. Preserve the frozen route, layout, labels, controls and refusal semantics; only the hidden data authority changes. Expose method/population/q-value/effect evidence and real readiness/model lifecycle state. | Run the M1 continuity snapshots for both pages and record no visible-contract regression. Kill a canonical source and prove the page shows the same bounded failure/refusal state rather than presentation fallback data. Every displayed model/finding resolves to manifest/run/evidence. | 10 | Not Started | Worker 3 | T-129; T-130; T-186; T-195 | T-138; T-192 | M3: 45 days after M2 completion | Release 2 MUST | Frontend/UI feature | 1.6667 | M3-P4 | T-129 + T-130 + T-186 + T-195 + M1 continuity snapshots. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L3.4 | Widget catalogue and intelligence visualisation | L4.1; L4.2 | Converge | D2; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.6667 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-189 | M3 | P4 | Canonical D5 Risk and D9 Early Warning cutover | Frontend | Prediction surfaces | Critical | Bind D5 Risk and D9 Early Warning to prediction_current/prediction evidence. D5 remains aggregate current risk; D9 remains the per-unit actionable queue with deadline, drivers, fallback state, comparables and can_accept/remediation status. Preserve the M1 visual contract and remove presentation-only backing data. | Continuity snapshots remain stable. Force a late prediction, fallback use, missing driver evidence and suppressed remediation; each renders the designed canonical state. No row appears actionable after its deadline and no client re-derives can_accept. | 12 | Not Started | Worker 3 | T-139; T-140; T-141; T-142; T-143 | T-192 | M3: 45 days after M2 completion | Release 2 MUST | Frontend/UI feature | 2 | M3-P4 | T-139..T-143 + M1 continuity snapshots | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.7 | Prediction, drivers, explainability and remediation candidates | L3.4 | Converge | D2; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-190 | M3 | P4 | Canonical D6 Suggestions and decision-action cutover | Frontend | Remediation surfaces | Critical | Bind D6 Suggestions to canonical remediation candidates/eligibility/decision records. Suppressed candidates never render. Accept/Reject/Defer controls obey server can_accept and preserve the human/read-only boundary. Preserve the M1 visual contract while deleting presentation-only decision data paths. v2.22.0 — Retire Phase8SuggestionOutcomeLoopEndpoints as an alternate decision/outcome authority during canonical cutover; preserve relevant historical records and route compatibility only where semantically lawful. | Run continuity snapshots. Attempt client-side manipulation to enable a forbidden decision and prove the server refuses it. Exercise actionable/evidence_only/exploratory/suppressed cases and confirm only allowed states appear with evidence and actor/reason history. v2.22.0 — No new hand-entered actual outcomes; canonical feedback loop with actor/time/provenance; disabled legacy routes cannot mutate production state. | 12 | Not Started | Worker 3 | T-142; T-143; T-144; T-145 | T-192 | M3: 45 days after M2 completion | Release 2 MUST | Frontend/UI feature | 2 | M3-P4 | T-142..T-145 + M1 continuity snapshots | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L9.2 | Suggestion generation from findings | L9.3; L9.4 | Converge | D2; D5 | Core | R2 | Advances |  | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | RE-ESTIMATE REQUIRED |  |  | BOUNDED SOURCE REVIEW — CANONICAL D6 CUTOVER UNVERIFIED | 8 | 14 | 24 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Canonical DTO/permission wiring 3/5/9; D6 state/history cutover 3/5/8; continuity/tampering tests 2/4/7. | Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-43 — legacy write path Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — caller outcome schema | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-191 | M3 | P4 | D11 Scenario Simulation: governed read-only modelled comparison | AI+ML | Scenario simulation | Very Important | Implement the already-designed D11 scenario path as decision support, not plant control: choose declared variables within valid ranges, hold the rest fixed, run against a named active model version/semantic manifest, compare with baseline and persist scenario_runs with uncertainty/disclaimer/evidence. It never writes to a customer system and never masquerades as an observed prediction. | Run a bounded scenario and resolve baseline/model/manifest/evidence. An out-of-range or non-controllable variable is refused. The result is labelled simulation, includes uncertainty, and no source-system write/control endpoint is reachable from the path. | 12 | Not Started | Worker 3 | T-130; T-176; T-187 | T-192 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.8 | M3-P4 | T-130 + T-176 + T-187 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L10.4 | Scenario simulation |  | Build | D3; D5 | Advanced | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 1.8 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-192 | M3 | P4 | Target-architecture gate pack G-48..G-55 | Testing | Architecture gates | Critical | Implement the eight target-architecture gates as executable tests: G-48 materialiser-only feature_store read; G-49 ML lane isolation; G-50 admission satisfiable; G-51 ANN recall floor; G-52 evidence-budget/truncation integrity; G-53 deterministic answer verification; G-54 governed-model-only learned multimodal output; G-55 semantic-manifest coverage. Keep them standalone and fail-closed; T-150 owns final pipeline wiring. | Falsify every gate once. Each deliberate violation fails for the named reason and passes only after the defect is removed. A missing test input/dependency is a failure, not a skip/pass. Produce one machine-readable gate report consumable by T-150. | 10 | Not Started | Worker 3 | T-183; T-184; T-185; T-186; T-187; T-188; T-189; T-190; T-191; T-107; T-122 |  | M3: 45 days after M2 completion | Release 2 MUST | Integration/E2E/certification | 1.7 | M3-P4 | T-183..T-191 + T-107/T-122 as applicable | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate | L4.3; L4.8; L5.8 | Validate | D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.7 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-193 | M3 | P4 | Drift Supervisor and governed model-action proposals | AI+ML | Model governance | Very Important | Implement the Drift Supervisor over served model/index/practice state. Detect declared distribution/performance/calibration/explanation drift, propose bounded actions, shadow-run where applicable and require human approval before applying. It may never lower readiness thresholds, refusal rules, evidence requirements, leakage gates, tenant isolation or semantic contracts, and it never performs continuous online weight updates. | Trigger each supported drift class on fixtures and prove a proposal is recorded with evidence. Attempt to propose a forbidden threshold/gate weakening and prove it is rejected structurally. Approve one allowed bounded action and confirm atomic application plus rollback pointer; reject one and confirm no state change. | 10 | Not Started | Worker 3 | T-130; T-187; T-139; T-145 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 1.5 | M3-P4 | T-130 + T-187 + T-139/T-145 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L6.3 | Supervisor and governed improvement proposals | L4.8 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-195 | M3 | P4 | Canonical readiness thresholds, governed change history and fail-closed readiness API | Backend | Readiness governance | Critical | Implement the Chapter 3 canonical readiness authority behind the M1-compatible facade: ppiq_meta.readiness_thresholds and readiness_threshold_changes, tenant/outcome-scoped thresholds, GET /api/readiness/evaluate, GET /api/readiness/matrix, GET /api/readiness/thresholds and governed PUT with required justification/audit. Evaluation failure is Blocked/readiness-could-not-be-measured, never Ready by default. | Create thresholds for two tenants/outcomes and prove isolation. Change one threshold through the governed API with justification and prove change history/audit. Attempt a non-human/unauthorised change and refuse it. Force the population measurement to fail and prove the result is Blocked with the fail-closed reason. M1 T-066 visible contract remains unchanged. | 10 | Not Started | Worker 3 | T-090; T-112; T-114 | T-186; T-187; T-188 | M3: 45 days after M2 completion | Release 2 MUST | Backend/domain contract | 1.5 | M3-P4 | T-090 + T-112 + T-114 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.1 | Readiness gate and statistical discipline chain |  | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 10 | 1.5 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-238 | M3 | P4 | Multi-objective Objective Set and Pareto practice kernel | AI+ML | Practice intelligence | Very Important | Implement schema-independent multi-objective practice semantics: Objective Set members, hard constraints, Pareto dominance/non-dominance, ParetoOnly/DeclaredUtility/LexicographicOrConstrained resolution and MO01/MO02 refusal. Normalisation consumes Performance Reference semantics; no default weights or sample min-max scaling. | Known-answer practice vectors produce the exact Pareto frontier. A conflicting set with no preference refuses a single winner. Declared utility/lexicographic policies produce deterministic rankings and preserve the full objective vector/support/uncertainty. | 12 | Not Started | Worker 3 | T-208; T-214 | T-239; T-240 | M3: 45 days after M2 completion | Release 2 MUST | Kernel/contract | 3.2 | M3-P4 | May start after T-214 contract; does not block September demo. | New objective/Pareto kernel/tests only. | T-239 persists objective authority; T-240 integrates practice family. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 | L10.1 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 3.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-239 | M3 | P4 | Persist Objective Set and preference authority | Backend / Database | Multi-objective persistence | Very Important | Persist objective_sets, objective_set_members and immutable objective_preference_versions under tenant/definition authority. Bind each member to registered outcomes/KPIs/measures and Performance Reference directionality/normalisation. No default weights. | Round-trip ParetoOnly and declared preference versions; equal data under a new preference creates a new version rather than rewriting history. Invalid/missing direction/reference refuses MO02. | 8 | Not Started | Worker 1 | T-090; T-214; T-238 | T-240 | M3: 45 days after M2 completion | Release 2 MUST | DB/schema authority | 3.4 | M3-P4 | After T-090 + frozen T-214/T-238 contracts. | objective-set tables/API/migrations. | T-240 consumes committed persistence. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 |  | Build | D1; D3; D4; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 8 | 3.4 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-240 | M3 | P4 | Composite practice results, trade-off explanation and Assistant tool integration | AI+ML / Assistant | Multi-objective practice integration | Very Important | Integrate T-238 with canonical practice learning: compute/persist composite_practice_results with objective vectors, support, uncertainty and dominance; expose GetCompositePractices to the deterministic Assistant tool layer. Reuse T-131/T-132/T-133 cohorts/stability/backoff; do not duplicate practice learning. | One customer-neutral fixture returns a supported Pareto frontier; unsupported/conflicting objectives refuse correctly; preference-resolved rank is reproducible by version. Assistant explains trade-offs and never calls a Pareto point universally best without declared preference. | 12 | Not Started | Worker 3 | T-131; T-132; T-133; T-238; T-239 | T-249; T-264 | M3: 45 days after M2 completion | Release 2 MUST | AI/ML production integration | 5.1 | M3-P4 | After practice core + objective persistence. | Practice intelligence/Assistant tool only. | T-138 may expose this tool after completion; no Assistant redesign. | Advanced ML, Optimisation & Value | M3 P4 — Advanced ML, Optimisation & Value. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L4.6 | Practice learning MF-07 | L6.2 | Build | D3; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 5.1 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-246 | M3 | P4 | Canvas governed model/intelligence block invocation | Frontend | No-code authoring | Important | Expose registered intelligence/model families as governed canvas blocks after the production model registry exists. Invocation resolves serving identity/model version and semantic manifest, calls the registered runtime, and returns governed result/evidence handles. No model framework or provider is exposed as the product contract. | Invocation resolves an active registered serving identity and semantic manifest; an unregistered/not-ready model refuses; result carries evidence handles/claim class; no direct Python/provider call exists in the frontend. | 11 | Not Started | Worker 2 | T-243; T-130; T-137; T-187 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | Post-Sep product completion | 4.7 | M3-P4 | Consume accepted producer contracts; remaining dependencies: T-243; T-130; T-137; T-187. No private scheduler/definition authority. Source-present is not closure proof. | Canvas model/intelligence block adapters only. | T-130/model registry and T-137 serving runtime remain authorities. | Advanced ML, Optimisation & Value | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L3.8 | Canvas → compile → governed job → run → per-block evidence | L4.2; L4.7 | Build | D2; D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 11 | 4.7 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-264 | M3 | P4 | Registry-driven internal benchmarking | Product / Integration | Registry-driven internal benchmarking | Very Important | Implement Core internal benchmarking Ch4 5.8.5 across registered dimensions and periods and against matching own-best practice. Reuse T-214/T-240 semantics; no assumed line/shift/customer taxonomy. | BM01 small-population refusal with both counts; BM02 no coloring without direction; explicit normalization/units and periods; context-comparable own-best practice; reproducible evidence/export and negative cross-tenant tests. |  | Not Started | Worker 3 | T-214; T-240 | T-249 | M3: 45 days after M2 completion | Release 2 MUST | Governed product integration |  | M3-P4 | Consume accepted producer contracts; remaining dependencies: T-214; T-240. No private scheduler/definition authority. Source-present is not closure proof. | Semantic product filenames only. CENTRAL assigns shared file locks before overlapping worker writes. | Reuse current canonical authorities; no shadow lifecycle/registry/scheduler. | Advanced ML, Optimisation & Value | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. |  |  | L10.1 | Internal benchmarking | L9.1; L4.6 | Build | D2; D3; D4; D5 | Core | R2 | Advances |  | UNESTIMATED — new/recognized task; owner calibration pending. | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook v2.23.0 — T-267 supplies D12 comparison/direction/sample-refusal/normalisation design. BM01/BM02 behavior and result evidence remain implementation acceptance, not illustrated proof. | 0 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | UNESTIMATED |  |  | SOURCE REVIEWED — LEGACY DEMO IS NOT TARGET IMPLEMENTATION | 10 | 18 | 30 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Registry/comparison service 4/7/12; result surface/evidence/export 3/6/10; BM01/BM02/tenant tests 3/5/8. | Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:17-35 — demo dashboard Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:50-85 — generated bands | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-167 | M3 | P5 | Documentation, training and production acceptance | Documentation | Handover | Critical | Runbook, operator and data-engineer and administrator guides, release notes, known limitations, rollback plan and the formal acceptance suite. | The acceptance suite passes and is signed. Known limitations are written down before the customer finds them. | 12 | Not Started | Worker 2 |  | T-249 | M3: 45 days after M2 completion | Release 2 MUST | External/site certification | 7.2 | M3-P5 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own customer-facing UX/docs/website only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Heavy-production Certification | M3 P5 — Heavy-production Certification. Release 2 is heavy production / scale / deeper enterprise use. |  |  | L7.8 | Sales Administration and sales-to-engineering handover | L8.8 | Build | D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 7.2 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-249 | M3 | P5 | Release 2 heavy-production final certification gate | Testing | Release certification | Critical | Final M3 gate for sustained heavy production: higher volumes, more users, OT endurance, enterprise operations, advanced BI/authoring, advanced intelligence/value, recovery and support. No release if a required M3 production capability is only a demo/proof seam. | One machine-readable M3 scorecard is GREEN across capacity, concurrency, customer-source endurance, security, backup/restore, monitoring, advanced BI/authoring, model lifecycle, value evidence and customer runbook. Zero unresolved Critical/Very Important release defects. | 12 | Not Started | Worker 1 | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110; T-267 |  | M3: 45 days after M2 completion | Release 2 MUST | Release certification | 6 | M3-P5 | After all M3 MUST gates | Cross-stack release evidence; exact staging only | Certification task only. Defects go back to the owning task/worker; do not patch features inside the gate. | Heavy-production Certification | M3 P5 final authority. Release 2 means heavy-production ready, not another demonstration. |  |  | L8.8 | C1–C4 performance certification and golden-journey release gate |  | Certify | D5 | Core | R2 | Advances |  | Inherited baseline estimate | v4.10.3 | Chapters 3/4 v4.10.3 — MD + illustrated Word; UI Coverage / UI Controls in this workbook | 1 |  | Not started — no completion claimed | Inherited v2.22.0 intended record; no new runtime certification in this repair. |  | INHERITED ESTIMATE | 12 | 6 | NOT SOURCE-REVIEWED IN THIS PASS |  |  |  | NOT ESTIMATED IN THIS PASS
T-265 | M2 | P3 | Release-1 UI design depth, workflow and illustrated-companion convergence | Frontend | Derived UI design and handoff | High | Revise the existing derived UI/Figma package, not the functional Design. Deliver build-ready, page-specific designs for every M2-exposed portion of the 40-page inventory, all applicable G1-G5 components, dialogs, S1/S2 and active S3/S5 editors, toolbox elements and inspectors; retain M3-only portions in T-267. Explicit M2 coverage includes A1/A2, B1-B6, C1/C2/C3/C5/C6, D1-D8 where active, E2/E3, F1-F4 minimum controls, and the actual release settings/logging surfaces. The approved page-by-page closure matrix, not this illustrative list, controls completeness. T-266 owns OPC content embedded in B1-B4/B6. For each obligation bind chapter/section -> semantic control/interaction ID -> reachable frame/state/node -> transition/data contract -> implementation owner -> acceptance evidence. Replace placeholder-only samples with labelled synthetic fixtures of realistic density and edge cases. Distinguish D1 view/selection from D2 authoring; B5 monitoring from F4 scheduling/dependency administration. Reuse the shell and components; C1 correctly hosts the S1 authoring mode and need not have an arbitrary different geometry. C1 must show selected Source/Join/Output inspectors, labelled typed ports, legal/illegal wiring, diagnostic-to-node focus, field binding, validate/preview, immutable publish/impact, reopen and SQL parity. C2/C3 must show catalogue-driven quarantine codes/counts, lineage, row detail and guarded reprocessing; target coverage includes the chapter's PV catalogue, never a hardcoded eight-code limit. B3 shows typed total-order cursors; B4/B5 show durable outcome/error/cursor and cancel-request acknowledgement versus canonical terminal state. D1 shows selected/possible/excluded values, pivot, clear-one/all and propagation, plus applicable table navigation/export; none of this M2 baseline moves to M3. Fix Home to J1-J15 or an explicitly mapped condensed rail; verify all 87 dialog source citations semantically, including rendered Word captions. Use page-specific applicability, permission/refusal, focus, keyboard, supported narrow-view and RTL states. Update Chapter 3/4 MD and illustrated Word from one maintained visual/interaction specification, with source prose preserved and the coverage register inside this workbook. Keep native Figma/tooling source in its implementation environment; store Figma file/node and acceptance references here, not in additional design-book files. No native-Figma, browser-runtime or enterprise-ready claim without the corresponding executed proof. | AC1: Every required M2 clause/control/transition is accounted for in a semantic traceability matrix; coverage resolves to a reachable frame/variant or a justified N/A. Literal label search is diagnostic only, not acceptance; no requirement to show permission-conditional controls in one default screenshot. AC2: Execute documented prototype walkthroughs with labelled fixtures for connect/test/discover/cursor/import, select/inspect/wire/map/publish/reopen, run/schedule/cancel/failure/quarantine/reprocess, and multi-widget selection/clear/export/evidence. Verify normal, refused and recovery transitions, preserved edits, focus and permission outcomes. AC3: Demonstrate D1/D2 and B5/F4 semantic differences while preserving reusable shell/components; C1/S1 shared structure is allowed. Show all required controls rather than inflating node count. AC4: J1-J15 mapping is exact; all 87 dialog references are verified against owning clauses in this workbook's coverage data and the Chapter 3/4 MD and illustrated Word (not merely matching an existing heading). All 40 pages, 6 shell components, 82 toolbox entries, 16 inspectors and 10 purpose/mode frames remain in the coverage ledger. AC5: Check keyboard traversal/focus return, meaningful disabled explanations, responsive panel behavior, RTL with SQL/identifiers kept LTR, and applicable loading/empty/error/read-only states using actual rendered designs. AC6: Re-open one native Figma import for each structural class and all changed scenes for diagnostics; confirm editable frames/text, fonts, component instances/variants and working prototype transitions. Save file/node references and inspection evidence. Pending Figma execution stays explicitly NOT EXECUTED, not pass. AC7: Export both illustrated Word chapters only after all included figures resolve, source prose is retained and the corrected images/captions pass a visual check. Task closure is design handoff only; D2/D5 product runtime completion remains with implementing tasks and T-247/T-150. |  | Not Started | Worker 2 |  | T-247; T-267 | Release 1 | Release 1 MUST | Design authoring |  | Contract-led parallel design | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | UI companion: non-OPC M2 scenes + Chapter 3/4 reading-edition assets. CENTRAL alone merges shared tokens/data/atlas; no product source lock. | UI design completion is not product implementation completion. Reuse the current authorities/components; use per-surface handoffs and no shared-file concurrent writes. | UI companion / design acceptance | Functional Design v4.10.3 unchanged. Design, rendered visual, prototype and live-runtime evidence are separate. |  |  | L3.1 | Analysis page anatomy, layout and visual standard | L1.1; L1.2; L1.3; L1.7; L2.2; L2.3; L2.6; L2.7; L3.2; L3.3; L3.5; L3.6; L3.7; L5.2; L6.1; L6.7 | Supports implementation; no runtime credit | D2 preparation only; D1-D5 product credit requires implementation evidence | Core | M2_REQUIRED | Design handoff only | PENDING — new design/prototype/native Figma evidence not yet executed | Fable's provisional estimate retained only in Estimate Review; not accepted as Hours or P80. | v4.11.0 | UI_Coverage_v2.23.0.json and UI_Workflow_Acceptance_v2.23.0.md; same companion version as revised visual edition, distinct from functional authority. | 0 | T-099; T-106; T-253; T-262; T-101; T-125 | NOT STARTED — DESIGN DELIVERY | No implementation or native-Figma closure claimed. |  | UNCONFIRMED DESIGN ESTIMATE |  |  | SOURCE + DELIVERED UI DATA REVIEWED — DESIGN DEPTH/PROTOTYPE NOT ACCEPTED | 28 | 44 | 68 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | Semantic/fixture mapping 6/10/15; connected M2 flows 16/24/37; native import/RTL/focus/Word synchronization 6/10/16. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — existing associative control semantics Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — existing reopen model PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE. | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-266 | M2 | P2 | Release-1 Industrial Integration / OPC UI workflows and capability-truth visual handoff | Frontend | Derived UI design and handoff | High | Functional Industrial Integration requirements are now integrated in Design v4.11.0. This task owns the derived visual/prototype/illustrated handoff inside canonical B1-B5/B6 surfaces: provider-aware connection states; stable field/layout editing; Time / Value change / Trigger-counter controls; requested/effective/qualified settings; continuous-session/batch/spool/gap states; capacity/retention refusal; and exact capability truth. It does not define a second functional contract and does not implement runtime. | AC1: Every v4.11.0 Industrial Integration UI obligation maps to an owning clause, semantic control/state and executable task T-268..T-275/T-224..T-226. AC2: Prototype connection/test -> select data -> fields/layout -> recording policy -> capacity/retention -> Job -> active/buffering/gap/replay -> completed batch -> canonical evidence using labelled synthetic data. AC3: Show rejected trust/session, unsupported operation, invalid layout, invalid interval/band/trigger, Bad/Uncertain quality, capacity-blocked, retention-blocked, source gap and replay states distinctly. AC4: Requested, effective and qualified settings are visually separate; no drawing certifies runtime capability. AC5: Keyboard/focus/virtualized field-grid/narrow-view/RTL checks and integrated Chapter 3/4 illustrated synchronization. AC6: Final live source/collector/storage proof remains with executable tasks and release gates. |  | Not Started | Worker 2 | T-207 | T-274; T-247 | Release 1 | Release 1 MUST | Design authoring |  | Contract-led parallel design | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | UI companion OPC scene subset only; Worker 1 reviews endpoint/security/time/spool contracts; CENTRAL merges shared UI data. | UI design completion is not product implementation completion. Reuse the current authorities/components; use per-surface handoffs and no shared-file concurrent writes. | UI companion / design acceptance | CENTRAL 16-Sep-2026: Functional Industrial Integration design is now v4.11.0 authority. T-266 remains open only for derived visual/prototype/illustrated handoff; no functional-design gap or runtime credit is claimed. |  |  | L1.8 | OPC-UA / historian / edge acquisition | L1.4; L1.1; L1.5; L6.8 | Supports implementation; no runtime credit | D2 preparation only; D1-D5 product credit requires implementation evidence | Core | M2_REQUIRED | Design handoff only | PENDING — new design/prototype/native Figma evidence not yet executed | Fable's provisional estimate retained only in Estimate Review; not accepted as Hours or P80. | v4.11.0 | Design v4.11.0; B1-B5/B6 visual/prototype synchronization | 0 | T-224; T-225; T-226; T-233 | NOT STARTED — DESIGN DELIVERY | No implementation or native-Figma closure claimed. |  | RE-ESTIMATE REQUIRED — v4.11.0 visual scope delta |  |  | DESIGN v4.11.0 SCOPE DELTA — SOURCE/PROTOTYPE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED AFTER v4.11.0 | Functional contract integrated; remaining derived UI/prototype effort must be re-estimated. | Design v4.11.0 Chapters 2–6; Industrial Integration Engineering Review 16-Sep-2026 | 16-Sep-2026 owner design decision; no live runtime/Figma execution claimed
T-267 | M3 | P3 | Release-2 interface depth and enterprise BI/authoring parity design | Frontend | Derived UI design and handoff | High | Complete the M3 remainder of the entire existing UI inventory, not just selected BI examples. Preserve all 40 page IDs, all 87 dialogs, 82 toolbox entries, 16 inspectors, 10 S1-S5 Block/SQL mode frames, expressions and G1-G6. Derive each remaining state/interaction from the owning chapter and the approved T-248 outcome matrix, including later Findings/Risk/Practice/Scenario/Benchmarking, Reports, Supervisor, alert/admin and licence/quota depth where deferred. Own advanced named selections/bookmarks, comparison states, drill/hierarchies, pivot/crosstab or governed equivalent, undo/redo, immutable version compare, multi-sheet layout, concurrency conflict recovery, advanced export fidelity, G3 command palette and G6 activity tray. Basic M2 selection/clear, table navigation, cancellation feedback and existing workflow correctness stay in T-265; do not defer them here. Use the common component library and model/report/benchmark/decision contracts; no unsupported window is made functional by a mockup. Finish distinct view/edit/inspect/pending/conflict/refusal recovery flows rather than producing duplicate placeholder frames. Deliver the revised visual specification inside Chapter 3/4 MD and both illustrated Word editions with stable traceable captions; retain native editable Figma evidence as file/node references inside this workbook. Do not add a standalone atlas or companion file to the design book. | AC1: Every uncompleted UI inventory obligation has a concrete M3 frame/state/interaction and one runtime owner; none disappears because an earlier template lacked it. Explicitly reconcile all 75 T-248 outcome rows with design/prototype evidence and then implementation acceptance; signed N/A only where the chapter allows it. AC2: Demonstrate advanced selection/save/restore, pending lasso confirm/cancel, drill/return, multi-sheet authoring, undo/redo, version diff, conflict resolution, and current-state export with applied filter/period/permission context. AC3: Include full deferred page workflows (Reports generation/delivery, Benchmarking sample/direction refusals, model activation/retirement, decisions/outcomes/effectiveness, Supervisor and administration) against their producer contracts. AC4: Apply semantic control coverage, applicable states, accessibility/focus/keyboard, responsive and RTL checks; shared components are encouraged, not forbidden. AC5: Native Figma editable import/prototype and no clipped/unreadable controls are observed; evidence references actual scenes and transitions. Updated Chapter 3/4 Markdown and illustrated Word preserve chapter prose and correct citations; coverage and verification remain in the latest Backlog. AC6: T-248 and T-249 verify product behavior independently. Design acceptance alone never raises product D2/D5 scores or marks an implementation task Done. |  | Not Started | Worker 2 | T-265 | T-248; T-249 | Release 2 | Release 2 MUST | Design authoring |  | Contract-led parallel design | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | UI companion M3 subset; shared token/atlas/Word merge owned by CENTRAL; no duplicate functional authority. | UI design completion is not product implementation completion. Reuse the current authorities/components; use per-surface handoffs and no shared-file concurrent writes. | UI companion / design acceptance | Functional Design v4.10.3 unchanged. Design, rendered visual, prototype and live-runtime evidence are separate. |  |  | L3.7 | Authoring professionalism | L3.1; L3.2; L3.3; L3.9; L6.5; L6.7; L7.4; L9.3; L9.5; L10.1; L10.4 | Supports implementation; no runtime credit | D2 preparation only; D1-D5 product credit requires implementation evidence | Core | M3_DEFERRED | Design handoff only | PENDING — new design/prototype/native Figma evidence not yet executed | Fable's provisional estimate retained only in Estimate Review; not accepted as Hours or P80. | v4.11.0 | Full remaining UI inventory + T-248 75-item matrix + UI_Workflow_Acceptance_v2.23.0.md | 0 | T-248; T-263; T-264; T-196; T-197; T-198; T-199; T-200 | NOT STARTED — DESIGN DELIVERY | No implementation or native-Figma closure claimed. |  | UNCONFIRMED DESIGN ESTIMATE |  |  | BOUNDED SOURCE + UI INVENTORY REVIEW — M3 DESIGN REMAINDER | 24 | 40 | 64 | UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed | M3 requirement/producer mapping 5/8/13; advanced connected flows 14/24/38; native/RTL/coverage/chapter checks 5/8/13. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — M2 behaviour to preserve Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report subset, not full E5 PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE. | 14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification
T-268 | M2 | P2 | Industrial acquisition configuration and stable field authority | Backend / Database | Source integration control plane | Critical | Extend the existing connection/dataset/field/definition authorities with provider-specific source selectors, stable field_id/source locator/technical key/display label separation, immutable raw layout/schema revisions, recording groups, Time / Value change / Trigger-counter policies, retention/capacity references and exact-version activation bindings. Runtime negotiated evidence remains separate from authored intent. No protocol client, scheduler, durable ingest or UI implementation in this task. | Save/reopen/version all three policies and raw/typed field definitions; label rename preserves field identity; address/type/layout edit creates reviewed revision; invalid type/band/trigger/layout combinations refuse server-side; old versions remain readable; tenant/role references are enforced; export/import preserves meaning without exporting secrets; same binary accepts two foreign source shapes. |  | Not Started | Worker 1 | T-207 | T-269; T-270; T-271; T-274; T-275 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L1.2 | Dataset registration and source selection | L1.1; L1.4; L1.5; L5.6 | Build | D1; D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-269 | M2 | P2 | Declarative DataBlock/message layout decoder and source-event identity | Backend / Edge | Industrial source decoding | Critical | Implement the bounded declarative raw-layout grammar for approved DataBlock/structured inputs: absolute/relative offset, bit/byte/word widths, signedness, byte/word order, strings, arrays and bounded structures; emit typed stable fields plus layout/source-event evidence. Typed OPC nodes bypass raw re-decoding. No arbitrary customer code and no native S7/Modbus transport unless separately approved. | Known-answer fixtures for at least two non-identical layouts; reject out-of-bounds/invalid bit/unsupported codec/overlap/resource-budget cases; preserve layout version and raw-source identity on replay; label rename does not alter decode; source-publication/sequence identity survives retry; unsupported transport profile refuses rather than guessing. |  | Not Started | Worker 1 | T-268 | T-270; T-274 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L1.2 | Dataset registration and source selection | L1.5; L5.5 | Build | D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-270 | M2 | P2 | Industrial recording policy and trigger/capture state-machine executor | Backend / Edge | Acquisition policy runtime | Critical | Execute PERIODIC, ON_CHANGE and TRIGGERED policies with durable deterministic state, exact field/layout/policy versions, baseline/edge/counter state, quality/time handling, achieved consistency class, explicit gaps and bounded record assembly. Reuse T-225 protocol operations, T-233 Source Time persistence and T-275 Job/session authority. No private scheduler, no second OPC runtime, no one-Job-per-sample design. | Constant periodic values create distinct admitted records; phase anchor does not drift; missed ticks are gap/history evidence, never retroactive clones; change-band baseline advances with durable acceptance; quality transitions are visible; startup/reconnect does not invent an edge; counter reset/wrap/jump semantics are declared; trigger members capture even when unchanged; source-consistency falsification rejects false atomicity; no latest-cache substitution for source-latched capture. |  | Not Started | Worker 1 | T-268; T-269; T-225; T-233; T-275 | T-226; T-274 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L1.8 | Industrial edge acquisition and recording | L1.5; L1.7; L2.6; L5.5 | Build | D1; D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-271 | M2 | P2 | Qualified relational and file acquisition convergence | Backend / Connectors | Database and file adapters | Critical | Converge SQL Server, Oracle, PostgreSQL, MySQL, Excel and CSV behind the shared Dataset/accepted-record contract while preserving provider-native typed ordering, cursor/revision/CDC or overlap policy, parser identity and source load budgets. Advertise only operations executed by that provider/version. Do not enable CDC from a successful login and do not create a second cursor authority. | Equal-watermark multi-page paging without loss; update/delete/revision policy; no-change rerun; source mutation consistency test; expired source position; each advertised database engine/version/path tested; workbook sheet/table/range and replaced-file behavior; quoted multiline CSV/encoding/delimiter/escape/header/null cases; exact parser identity; bounded source load and typed refusal for unsupported CDC/revision modes. |  | Not Started | Worker 1 | T-268; T-108 | T-274; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L1.3 | Incremental import into staging | L1.1; L1.4; L1.7 | Converge | D1; D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-272 | M2 | P2 | Dataset-oriented Dump Store accepted-record and consumer contract | Database / Backend | Staging and source-shaped data plane | Critical | Resolve logical-versus-physical staging semantics as one governed Dump Store in ppiq_staging. Persist immutable accepted-record identity, exact config/layout/policy/session/batch/source-revision envelope, typed values/quality/time/integrity and idempotency receipts; expose one typed tenant-scoped logical Dataset to preview, Canvas, safe SQL and exact-version projection. One authoritative payload placement only; exact original bytes are immutable artifacts when required, not a second mutable truth. | Core-commit/response-loss retry returns same receipt; same identity/different content refuses; precision and supported integer/type values survive; partition-safe identity proven; continuous session exposes only completed sealed batches; typed Dataset reader reopens identically across physical optimisation; original-byte artifact distinction proven; exact published transformation reads exact accepted batch/version; no duplicate JSON/typed raw authorities. |  | Not Started | Worker 1 | T-087; T-088; T-251; T-252; T-268 | T-273; T-274; T-226; T-247 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L1.3 | Incremental import into staging | L1.5; L2.3; L3.5; L5.7 | Build | D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-273 | M2 | P2 | Industrial source capacity, retention and replay lifecycle control | Infrastructure / Database | Acquisition capacity and source-data lifecycle | Critical | Bind per-dataset hot retention/archive/replay floors and source/collector/site/tenant aggregate capacity to activation. Account for source impact, accepted/event/value rates, payload size, queue/spool reserve, disconnected window, live+replay drain, core ingest/projection lag and backup/restore. Source-data lifecycle is distinct from T-199 log retention. Unknown rates remain unknown; no invented compression or throughput constants. | Combined-source admission rejection; capacity preview states basis/confidence; finite spool/outage horizon; replay drain exceeds continuing live input; disk-full/overload preserve explicit gap/fault evidence; unprojected/unreconciled input cannot be deleted; archive-before-delete verifies integrity and restore/replay; backup/restore preserves manifests/receipts; source change-log retention dependency enforced; high-rate profile cannot be certified from a configured interval alone. |  | Not Started | Worker 1 | T-272; T-124 | T-274; T-247; T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L8.5 | Sizing model and calibrated performance constants | L1.7; L8.6; L8.7; L8.8 | Validate | D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-274 | M2 | P2 | Executable unified Industrial Integration configuration UX | Frontend / API integration | B1-B5/B6 source workflow | Critical | Implement the v4.11.0 source configuration experience on the existing B1-B5/B6 surfaces for approved databases/files/OPC profiles: provider-aware connection, Select Data, Fields & Layout, Time/Value-change/Trigger-counter policy, requested/effective/qualified state, storage/retention/capacity preview, Job binding and active/buffering/gap/replay/completed-batch monitoring. Browser never becomes the acquisition runtime. | Real browser/API journey with keyboard/RTL and bulk field editing; save/reopen/version behavior; stable field picker identity; exact typed errors without leaking values/secrets; source preview obeys budget/permission; all three modes; capacity and retention refusal; capability truth from backend; close browser while collection continues; completed batch becomes available to T3/T4; denied raw-preview role cannot see sample values in error text. |  | Not Started | Worker 2 | T-254; T-266; T-268; T-269; T-270; T-271; T-272; T-273; T-275 | T-247; T-150 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Frontend/API integration |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L1.8 | Industrial edge acquisition and recording | L1.1; L1.2; L1.4; L1.7; L2.6 | Integrate | D1; D2; D3; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed
T-275 | M2 | P2 | Continuous acquisition Job runtime, fencing and finite microbatch lifecycle | Jobs / Workers | Continuous acquisition execution | Critical | Extend the existing Job authority with ContinuousAcquisition execution: long-lived activation/session plus finite sealed batches/windows, one fenced owner generation per source/group, approved disconnected-capture window, replay-only return of superseded owner, bounded live/replay lanes, pause/cancel safe boundary and session/batch progress/history. No private edge scheduler and no run row per sample. | One-owner negative control; central heartbeat loss inside offline allowance does not start duplicate capture; lawful takeover fences prior generation; superseded collector can replay old durable records but cannot capture new; browser/API restart does not stop edge capture; session stays Running while finite batches complete and unblock projection; live capture reserved during replay; disk/queue saturation is explicit; pause/cancel seals or fails in-flight batch truthfully and never advances uncommitted checkpoint. |  | Not Started | Worker 3 | T-106; T-107; T-268 | T-270; T-226; T-274 | M2: ~1 month from owner planning checkpoint; exact date not committed | Release 1 MUST | Backend/domain/runtime implementation |  | Industrial Integration v4.11.0 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | Day-1 Data Workbench — Industrial Integration | CENTRAL 16-Sep-2026: new bounded owner created from approved Industrial Integration design. No task-ID-named repository implementation files. |  |  | L2.6 | Job definition, scheduling, execution monitor and history | L1.7; L1.8; L8.4; L8.6 | Build | D1; D3; D4; D5 | Core | R1 | Advances | NOT EXECUTED — new v4.11.0 implementation scope | No hours fabricated. Source-level preflight required before LOW/BASE/HIGH/P80. | v4.11.0 | Chapters 3/4 v4.11.0 — integrated Industrial Integration contract; T-265/T-266 own derived visual synchronization. | 0 |  | NOT STARTED — v4.11.0 NEW SCOPE | Design authority only; no source/build/runtime closure claimed. |  | NOT ESTIMATED — SOURCE PREFLIGHT REQUIRED |  |  | DESIGN v4.11.0 NEW SCOPE — SOURCE PREFLIGHT REQUIRED |  |  |  | NOT ESTIMATED — not zero, not P80 | Estimate only after exact owned source/predecessor/runtime seam measurement. | PPIQ_Industrial_Integration_Engineering_Review_16Sep2026 + Design v4.11.0 owning clauses | 16-Sep-2026 owner-approved design; no live HEAD/DB/browser certification claimed

## Release Plan
Release Plan — v2.23.0 ¦ reviewed15Sep2026; partial non-withdrawn estimates only
Release | Planning target | Phase | Outcome | Active tasks | Done | Open | In progress | Usable scope h | Usable open scope h | Estimate unresolved rows | Exit condition
M2 | ~1 month from owner checkpoint | P1 | Product Foundation & Release Truth | 26 | 26 | 0 | 0 | 245 | 0 | 0 | T-150 Day-1 release gate
M2 | ~1 month from owner checkpoint | P2 | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | 42 | 14 | 28 | 3 | 199 | 99 | 22 | T-150 Day-1 release gate
M2 | ~1 month from owner checkpoint | P3 | Enterprise BI & Customer Experience | 5 | 0 | 5 | 0 | 36 | 36 | 1 | T-150 Day-1 release gate
M2 | ~1 month from owner checkpoint | P4 | Industrial Intelligence | 27 | 22 | 5 | 0 | 276 | 48 | 0 | T-150 Day-1 release gate
M2 | ~1 month from owner checkpoint | P5 | Release Hardening | 15 | 0 | 15 | 0 | 116 | 116 | 3 | T-150 Day-1 release gate
M3 | 45 days after M2 | P1 | Scale & OT Resilience | 10 | 0 | 10 | 0 | 84 | 84 | 3 | T-249 final release certification
M3 | 45 days after M2 | P2 | Multi-user Enterprise Operations | 12 | 0 | 12 | 0 | 106 | 106 | 1 | T-249 final release certification
M3 | 45 days after M2 | P3 | Advanced BI / Authoring | 8 | 0 | 8 | 0 | 58 | 58 | 3 | T-249 final release certification
M3 | 45 days after M2 | P4 | Advanced ML / Optimisation / Value | 40 | 0 | 40 | 0 | 377 | 377 | 6 | T-249 final release certification
M3 | 45 days after M2 | P5 | Heavy-production Certification | 2 | 0 | 2 | 0 | 24 | 24 | 0 | T-249 final release certification

## Worker Tracks
Worker Tracks — v2.23.0 ¦ Task-ID joins; design work is not runtime proof
Owner | Release | Phase | Task Id | Task Name | Status | Usable estimate h | Usable P80 h | Depends On | Start/Gate | Lock | Handoff | Evidence state | Contract-ready predecessors
CLOSED | M2 | P4 | T-137 | ModelServingRuntime and model-gateway adapter, isolated from the presentation dock | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-168 | Versioned C#↔Python ML job protocol and isolated runtime harness | Done | 12 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-169 | Typed columnar training-artifact library and B-03 harness | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-170 | Chunked sequence-artifact library and bounded loader | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-171 | Capability Profiler and eligibility/refusal kernel | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-172 | MF-01 Process Encoder runtime behind a replaceable contract | Done | 12 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-173 | MF-02 VectorSimilarityIndex with exact-Flat recall baseline | Done | 12 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-174 | MF-03 novelty-model runtime and honest refusal semantics | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-175 | MF-04 supervised-outcome training runtime and mandatory simple baseline | Done | 12 | 0 | T-168; T-169 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-176 | Calibration, explanation stability and three-dimensional promotion kernel | Done | 12 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-177 | Production statistical-method kernel, including Numeric×Categorical | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-178 | Pure remediation eligibility and can_accept decision kernel | Done | 8 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-179 | Deterministic Assistant tool planner | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-180 | Permission-first hybrid retrieval and evidence packer | Done | 12 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-181 | Deterministic answer verifier and Q-01..Q-11 evaluation harness | Done | 12 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
CLOSED | M2 | P4 | T-182 | Benchmark harness and result manifest for B-01..B-09 | Done | 10 | 0 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | No active lock. | None — preserve evidence. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-086 | Freeze the legacy Fleet v2 controlled regression oracle | Done | 8 | 2.72 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-087 | Physical three-schema migration | Done | 12 | 2.325 | T-086; T-088 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-088 | Canonical migration order and legacy script archival | Done | 12 | 2.325 | T-086 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-089 | definition_store, definition_versions and definition_dependencies | Done | 12 | 2.325 | T-087; T-088 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-090 | Move all five definition kinds onto the store | Done | 12 | 1.8 | T-089 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Downstream consumers wait for the committed T-090 authority. Handover/progress notes do not substitute for closure; the pack must apply, build, test, replay and commit on the user machine. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-091 | Impact preview, export and import | Done | 12 | 1.8 | T-090 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-092 | Registry authority: dimensions and measures as rows | Done | 12 | 1.8 | T-089; T-090; T-210; T-231 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-093 | Plant-vocabulary sweep, part 1: build the term list and the architecture test | Done | 6 | 0.9 | T-092; T-206 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-094 | Plant-vocabulary sweep, part 2: remove hardcoded universal grain and industry vocabulary | Done | 24 | 3.6 | T-092; T-093; T-209 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-201 | Freeze the successful M1 presentation baseline and transfer programme authority to M2 | Done | 4 | 1.5 |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Git/worktree ownership + release/tag only. | After commit/tag, all workers consume the frozen baseline; nobody reopens M1 presentation scope without a proven regression. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-210 | Canonical signal and aggregation semantics authority | Done | 12 | 5.1 | T-090; T-209 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Parameter definitions/KPI bindings/migrations/definition contract. | T-211 executes exactly this contract; no second aggregation registry. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-231 | Persist Analysis Subject and Grain authority in canonical definition store | Done | 6 | 2.55 | T-090; T-209 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | analysis_subjects/grain definitions + API/migrations. | T-092/T-128/T-139/T-213 consume committed persistence; they do not invent subject identity. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-251 | Physical database catalogue, naming authority and zero-unknown schema dictionary | Done | 12 | 1.8 | T-087; T-088; T-260 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own generated DB catalogue tooling/documentation and read-only pg_catalog queries. No product table deletion, rename or unrelated DDL. | Publish semantic-named catalogue artifacts only; no task-number repository filename. Hand off the generated dictionary to T-115/T-123/T-150. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-252 | Disposable database lifecycle and integration-test database isolation | Done | 8 | 1.2 | T-087; T-088; T-251; T-259 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own integration-test DB fixture/runner and disposable-DB lifecycle tooling only. Do not change product schema semantics. | Every pack that CREATE DATABASEs owns DROP in finally. Persistent DB roles are explicit and protected. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-256 | Runtime genericity and three-schema consumer convergence | Done | 12 | 3.2 | T-088; T-094; T-251; T-252; T-253 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Backend runtime consumers, API composition, DB-facing services and backend architecture/genericity guards only. NO Frontend/PlantProcess.Web mutation. T-258 exclusively owns frontend material/genericity convergence. | Publish a bounded compatibility/consumer handoff manifest to T-258. Do not solve frontend Material pages/types/routes inside T-256; do not leave generic frontend red. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-259 | Release evidence envelope v1 machine-readable contract | Done | 2 | 0.3 | T-251 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Shared release-evidence schema/validator + focused contract tests only. No DB fixture implementation, frontend test runner, scorecard, feature code or release aggregation. | T-252/T-257 are producers. T-227 owns production acceptance scorecard/policy. T-150 aggregates. None may redefine the v1 envelope. | Recorded closed — inherited evidence
Worker 1 | M2 | P1 | T-260 | Canonical acceptance database builder convergence | Done | 6 | 1.8 | T-088 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Fresh acceptance DB builder, canonical migration-order consumer/validation, focused builder tests and T-251 rerun orchestration only. No product runtime/API/frontend changes; no mutation of ppiq_app or ppiq_presentation; no broad migration rewrite. | T-260 corrects how the fresh certification DB is constructed; T-251 remains the physical catalogue owner and resumes only on the corrected DB. T-256 later owns genuine runtime/schema compatibility residue that remains after a correct fresh build. | Recorded closed — inherited evidence
Worker 1 | M2 | P2 | T-095 | Relationship members, cardinality, grain conversion and preferred paths | Done | 12 | 1.8 | T-057; T-089; T-090; T-094 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P2 | T-096 | Path resolver, part 1: resolver core and the first eight consumers | Done | 8 | 1.2 | T-095 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P2 | T-097 | Path resolver, part 2: the remaining eight consumers and the regression suite | Done | 6 | 0.9 | T-096 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Recorded closed — inherited evidence
Worker 1 | M2 | P2 | T-099 | Quarantine, part 1: the table, the reprocess API and the first eight PV classes | Done | 8 | 1.2 | T-087; T-089; T-090 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | CLOSED GREEN / COMMITTED — FINAL TRANSCRIPT CORROBORATED
Worker 1 | M2 | P2 | T-100 | Quarantine, part 2: the remaining seven PV classes and per-class tests | Done |  |  | T-099 | RUNNER-1 CANDIDATE IS PRESENT; DO NOT RERUN RUNNER 1 or require a clean owned tree relative to HEAD. Resume from the exact handoff/postimages. Resume v1.0.1 is issued; success is not yet reported. Validate HEAD against the handoff and all owned postimage hashes before continuing. Expected parent supplied for closure is 4e0f1219ddbac3163bafe7ce510b62520683a77c; do not substitute the older T-099-only HEAD. If the exact gates fail, stop and report without manual resets, cleanup of unrelated work, or a fresh mutation pack. Worker 1/CENTRAL retains the execution lock through T-100 final commit; Worker 2 remains held. | Worker 1 is the recorded execution owner; CENTRAL-assisted delivery. Preserve the existing T-100 candidate and unrelated dirty work. Exclusive shared repository mutation lock until T-100 is committed. | Release Worker 2 only after T-100 final commit SHA and closure evidence. The successor consumes PROJECTION_* declaration, PV01..PV15 row-validation and JOB_EXEC_* runtime boundaries without duplication. | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED
Worker 1 | M2 | P2 | T-102 | Identity resolution across sources | Not Started | 8 | 1.2 | T-087; T-095 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 canonical plant schema + T-095 relationship/material identity authority. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-103 | Genealogy bidirectional walk hardening and weight proof | Not Started |  |  | T-095; T-102 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095 + T-102 canonical relationship/identity authority. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-104 | Projection provenance, exact-version stamping and idempotent reprojection | Not Started |  |  | T-090; T-095; T-099; T-261 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-090 canonical versioned mapping definitions + T-095 relationship authority ... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-108 | End-to-end delta correctness: source cursor, load protection, replay and projection watermark | Not Started |  |  | T-099; T-104 | Consume accepted producer contracts; remaining dependencies: T-099; T-104. No private scheduler/definition authority. Source-present is not closure proof. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-207 | Connector capability truth: stop advertising unimplemented browse/read/subscription | Done | 6 | 2.25 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Connector metadata/API contract and tests. | T-224..T-226 later may flip capabilities to true only by passing this contract. | Recorded closed — inherited evidence
Worker 3 | M2 | P2 | T-224 | Production OPC UA edge runtime: endpoint security, certificates and session lifecycle | Not Started |  |  | T-207 | Release 1 MUST — start after T-207 connector-truth authority. Site/customer OT certification may require customer access, but the executable production OPC UA runtime itself cannot be deferred past M2. | Customer-side edge agent/OPC adapter only. | T-225 consumes session adapter; site certification remains T-153/T-227-like acceptance, not hidden in code. | Not started — no completion claimed
Worker 3 | M2 | P2 | T-225 | Production OPC UA edge runtime: browse, tag registration, subscription and monitored items | Not Started |  |  | T-224 | T-224. | Edge OPC adapter + tag registry integration. | T-226 consumes typed acquired values; no core API direct OPC connection. | Not started — no completion claimed
Worker 3 | M2 | P2 | T-226 | Production OPC UA edge runtime: quality/timestamps, recovery and spool-to-canonical proof | Not Started |  |  | T-225; T-233; T-270; T-272; T-275 | T-225 + T-216 Source Time Authority. | Edge spool/acquisition mapper + canonical ingest contract. | T-153 real-source connector certification consumes this implementation; do not call implementation itself site-certified. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-232 | Persist Performance Reference authority and projections | Not Started | 6 | 2.55 | T-090; T-231; T-214 | T-090 + T-231 + committed T-214 contract. | performance reference tables/projections/API. | T-215 consumes persistence; no local reference math. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-233 | Persist Source Time Authority and observation timestamp provenance | In Progress | 5 | 2.125 | T-087; T-090; T-216 | T-087 + T-090 + committed T-216 contract. | source_time_authorities/observation timestamp provenance/API. | T-221/T-226 consume canonical persistence; T-217 kernel does not wait. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-235 | Persist transition/stabilisation authority and regime context | Not Started |  |  | T-090; T-231; T-234 | T-090 + T-231 + committed T-234 contract. | process transition tables/API/migrations. | T-237/customer onboarding consume committed persistence; do not redesign contract. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-112 | Force RLS on every tenant-owned table with an architecture test | Not Started | 12 | 2.325 | T-087; T-088; T-251; T-252 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087/T-088 canonical migration authority available; establish FORCE RLS guar... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Critical hand-off: after T-089..T-105 + T-112/T-114 are committed, W3 may open T-183/T-195/T-128 lane. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-113 | Secret and configuration hygiene | Not Started |  |  |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-114 | Tenant keys, tenant-aware uniqueness and canonical namespace on new APIs | Not Started | 6 | 0.9 | T-087; T-089; T-090; T-095; T-099 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-089/T-090 + T-095/T-099 canonical Release 1 tables available; establish t... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Critical hand-off: after T-089..T-105 + T-112/T-114 are committed, W3 may open T-183/T-195/T-128 lane. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-115 | Fresh-install Rule 2 acceptance test, ephemeral | Not Started | 4 | 0.775 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-119 | Eight-role catalogue convergence, one-to-one wire mapping and three enforcement layers | Not Started | 12 | 1.8 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-121 | Licence and entitlement enforcement | Not Started |  |  | T-119 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 role catalogue/enforcement + licence authority. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-123 | Install package, migration runner, upgrade and rollback | Not Started |  |  |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-124 | Backup with a tested restore acceptance procedure | Not Started | 12 | 3.2 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-125 | Minimum monitoring, health and alerting | Not Started | 14 | 3.2 | T-106; T-107 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-126 | Support runbook and UAT dataset and configuration import | Not Started | 12 | 0.9 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-150 | Release 1 final production gate: Day-1 workbench, BI, OPC, intelligence and hardening | Not Started | 12 | 4.08 | T-115; T-123; T-124; T-125; T-126; T-205; T-207; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-250; T-251; T-252; T-253; T-254; T-255; T-256; T-257; T-258; T-259 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-192 + T-148 exact route/shell inventory + T-194 API-alias retirement + all ... | T-150 only after W2/W3 component freeze; route failures back to owning agent. | Final Release 1 gate. Fixes go back to the exclusive owning task/agent; T-150 owner does not edit other agents' feature files. | Not started — no completion claimed
Worker 1 | M2 | P5 | T-227 | Release 1 production acceptance scorecard and evidence policy | Not Started | 6 | 2.25 | T-213; T-259 | Prepare before installation; can start after customer data assessment T-213. | Pilot documentation/evidence scorecard only. | Site/engineering teams later fill measured values; criteria are not rewritten after results are known without an audited amendment. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-110 | Bounded delta execution: chunks, resume, deterministic merge and scan budgets | Not Started |  |  | T-108; T-109 | Consume accepted producer contracts; remaining dependencies: T-108; T-109. No private scheduler/definition authority. Source-present is not closure proof. | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-122 | Container architecture and configuration profiles, including isolated ML runtimes | Not Started | 12 | 3.2 | T-106; T-107; T-112; T-113; T-114; T-117; T-137; T-168; T-123 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 + T-107 + T-112 + T-113 + T-114 + T-117; T-137/T-168 runtime contracts ... | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-151 | Site defect burn-down | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-152 | Customer data edge cases | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-153 | Connector certification against real sources | Not Started | 12 | 7.2 | T-224; T-225; T-226; T-254 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-154 | Query plans, indexes and partition boundaries | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-160 | HA, DR and restore rehearsal | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P1 | T-163 | Monitoring, SLOs and support escalation | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P2 | T-116 | API namespace migration, part 1: map the 92 prefixes onto the 27 domains and stand up dual-serve | Not Started |  |  | T-256 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P2 | T-117 | API namespace migration, part 2: migrate the clients and add the token gate | Not Started | 6 | 0.9 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P2 | T-161 | SSO and identity integration | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P2 | T-162 | Site security hardening and sign-off | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P2 | T-194 | Retire legacy API dual-serve aliases after canonical-client continuity proof | Not Started | 6 | 0.9 | T-117; T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-117 + T-127 | Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P4 | T-164 | The Value Engine | Not Started | 12 | 7.2 | T-237; T-235 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P4 | T-165 | Commercial capacity finalisation and the sales calculator | Not Started |  |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own site/platform/backend/infra. No AI/ML calibration or customer UX docs. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 1 | M3 | P4 | T-239 | Persist Objective Set and preference authority | Not Started | 8 | 3.4 | T-090; T-214; T-238 | After T-090 + frozen T-214/T-238 contracts. | objective-set tables/API/migrations. | T-240 consumes committed persistence. | Not started — no completion claimed
Worker 1 | M3 | P5 | T-249 | Release 2 heavy-production final certification gate | Not Started | 12 | 6 | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110; T-267 | After all M3 MUST gates | Cross-stack release evidence; exact staging only | Certification task only. Defects go back to the owning task/worker; do not patch features inside the gate. | Not started — no completion claimed
Worker 2 | M2 | P1 | T-202 | Persisted page/widget definition replay gate | Done | 10 | 4 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend E2E + dashboard query test harness; no canonical schema edits. | T-150 later consumes this gate; it does not redesign it. | Recorded closed — inherited evidence
Worker 2 | M2 | P1 | T-203 | Customer-route network, console and widget-state invariant | Done | 10 | 4 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend E2E/session harness. | All later customer-facing feature tasks must add their route to this gate before close. | Recorded closed — inherited evidence
Worker 2 | M2 | P1 | T-204 | Associative cross-filter state-machine certification | Done | 10 | 4.25 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | AssociativeContext/filter bridge + E2E tests; no unrelated chart redesign. | This task supersedes using browser walking as the acceptance of cross-filtering. | Recorded closed — inherited evidence
Worker 2 | M2 | P1 | T-205 | Frontend global suite termination and machine-readable gate | Done | 8 | 3.2 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend test runner/config only. | T-205 remains closed. Deterministic suite-truth mutations are owned by T-250; do not amend or reopen T-205 for product/test corrections. | Recorded closed — inherited evidence
Worker 2 | M2 | P1 | T-250 | Frontend suite truth convergence: Journey routing and design-system corrections | Done | 6 | 2.5 | T-205 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Own only the bounded JourneyRail/Journey tests, MetricCard styling, exact Heatmap architecture exception and SpecificationTable convergence. No edits to T-205 runner/validator and no unrelated frontend cleanup. | T-205 remains closed. After T-250 GREEN, move directly to the next eligible existing Worker-2 task. No unnamed corrective work and no repeated expensive certification loop. | Recorded closed — inherited evidence
Worker 2 | M2 | P2 | T-098 | Relationship Browser page and path evidence | Not Started | 12 | 2 | T-095; T-096; T-097 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-060 M1 C6 surface + T-095 + T-096 + T-097. | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M2 | P2 | T-101 | Quarantine retry, reprocess and Mapping Health completion | Not Started |  |  | T-099; T-100 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-061 final M1 API/page contract + T-099 + T-100 canonical quarantine impleme... | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M2 | P2 | T-212 | Integrate aggregation semantics into Layer-A widget/query execution | Not Started | 10 | 5.1429 | T-202; T-210; T-211; T-092; T-234; T-235; T-236 | T-202 + T-210/T-211 + T-092 + committed T-234/T-235/T-236. | Dashboard query service/executor + focused frontend state mapping. | Consumes W1 semantics and W3 kernel; no independent aggregation rules. | Not started — no completion claimed
Worker 2 | M2 | P2 | T-213 | Customer Data Intake and Capability Assessment authority | Done | 8 | 3.2 | T-201; T-206 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Onboarding assessment service/report; no customer-specific schema code. | Mappings/definitions become canonical through existing authorities; report does not become a shadow registry. | Recorded closed — inherited evidence
Worker 2 | M2 | P2 | T-241 | Canvas executable block contract, typed ports and graph validation | Done | 10 |  | T-032; T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Frontend shared authoring shell, canvas graph/ports only. | Reuse M1 SharedAuthoringShell and existing typed-port assets. No second canvas component. | Recorded closed — inherited evidence
Worker 2 | M2 | P2 | T-242 | Canvas production block library: relational, arithmetic, logic, window and governed aggregate | Done | 16 |  | T-241; T-210 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Canvas block registry and executable block nodes. | Do not duplicate analytics kernels; blocks call governed Layer-A/Layer-B contracts. | Recorded closed — inherited evidence
Worker 2 | M2 | P2 | T-243 | Canvas persistence, immutable versioning and reopen/edit round-trip | Done |  |  | T-241; T-242; T-089; T-090; T-253 | Consume accepted producer contracts; remaining dependencies: T-241; T-242; T-089; T-090; T-253. No private scheduler/definition authority. Source-present is not closure proof. | Frontend canvas persistence + definition-store client contracts. | No canvas-specific persistence schema. | BASELINE CLOSED; RELATIONSHIP-PUBLICATION EXTENSION UNPROVEN
Worker 2 | M2 | P2 | T-244 | SQL-mode production convergence: compile, validate, bounded dry-run and definition persistence | Done | 14 |  | T-035; T-036; T-089; T-090 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | SharedAuthoringShell SQL mode + canonical definition API. | Preserve SafeSqlValidator/editor behaviour and tests. | Recorded closed — inherited evidence
Worker 2 | M2 | P2 | T-245 | Canvas-to-job compilation, binding, run monitor and per-block evidence | Not Started | 12 | 5.1 | T-243; T-244; T-106; T-261; T-262 | QUEUED after T-261 closure; current mutation sequence is T-099 → T-100 → T-261 → T-245. T-245 consumes the proven executor/runtime and per-block evidence, never recreates them. Retain all listed canonical prerequisite contracts. | Canvas compiler/job binding + run monitor only. | T-106 remains job policy authority. | QUEUED — T-261 NOT CLOSED; NO NEW IMPLEMENTATION OR LIVE RUN CLAIM
Worker 2 | M2 | P2 | T-247 | First-customer Day-1 Golden Journey and same-binary onboarding proof | Not Started | 12 | 5.1 | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235; T-262; T-125; T-265; T-266; T-274 | T-213 complete + T-092 green. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Configuration/mapping/registry definitions and customer-shaped demo profile; no product source files unless a generic defect is found. | If onboarding requires C#/TypeScript/product-SQL changes, stop and raise a generic product gap; do not patch around it. | Not started — no completion claimed
Worker 2 | M2 | P2 | T-253 | Shared authoring governed output-target canonical-content contract | Done | 12 | 4.8 | T-094; T-209; T-241; T-244 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Owned T-253 surfaces only: Frontend shared authoring shell + canvas API adapter + focused authoring tests; Backend CanvasDefinitionContent / Canvas lifecycle contracts+implementation/response path; ICanonicalEntityCatalog interface+implementation; the semantic `ICanonicalProjectionTarget` marker interface and the minimum existing canonical entity declarations needed to mark current legitimate targets; existing AuthoringSupport read endpoint group; focused backend/architecture tests. No DB topology/migrations, no MappingDefinitionService.AllowedTargetEntities edit, no Analysis Subject redesign, no Job runtime, no chart/page styling. | Canonical outputTarget namespace is canonical entity name, but picker eligibility is a separate explicit model-sourced capability. Root outputTarget is hashed representation-independent authority; graph.targetEntity is compatibility data and must agree on new writes. Do not expose all mapped entities and do not use schema as the sole eligibility predicate. T-243 consumes this contract; T-256 later removes the old MappingDefinitionService string allowlist by consuming the same capability. | Recorded closed — inherited evidence
Worker 2 | M2 | P2 | T-254 | Customer-facing connector capability truth convergence | In Progress |  |  | T-207 | Original UI/website convergence is frozen at f8a35725. Only the v2.22 backend-provider-authority delta is outstanding. Consume T-207 and existing contracts on disjoint paths; column M remains the completion-prerequisite list. This is not permission to redo the closed UI/website scope. | Frontend DB configuration capability rendering + generated website proof adapter/content only. No connector protocol implementation. | T-153 later changes certification state by executed real-source evidence; UI/website consume the same truth automatically. | BASELINE CLOSED GREEN / FROZEN; LATER BACKEND EXTENSION UNPROVEN
Worker 2 | M2 | P2 | T-261 | Governed Transformation/Projection job executor and per-block runtime evidence seam | In Progress | 12 | 5.1 | T-106; T-241; T-242; T-243; T-099; T-262; T-100 | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Worker 2 owns executor/runtime work, but holds no mutation permission until T-100 commits. Preserve the shared producer frontier; one bounded delta only after the final SHA. | After T-100 commits: one bounded delta, then T-261 Runner 1/2; after T-261 closes proceed to T-245. No second compiler, capability policy, run store or block-evidence authority. | SEMANTIC CONTRACT/PACKAGE IN PROGRESS; HOST MUTATION HELD PENDING T-100 COMMIT
Worker 2 | M2 | P2 | T-262 | Governed projection declaration and canonical field-binding contract | Done |  |  | T-253; T-243 | Consume accepted producer contracts; remaining dependencies: T-253; T-243. No private scheduler/definition authority. Source-present is not closure proof. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Semantic product filenames only. CENTRAL assigns shared file locks before overlapping worker writes. | Reuse current canonical authorities; no shadow lifecycle/registry/scheduler. | COMMITTED CONTRACT GREEN; CURRENT INTEGRATION ACCEPTANCE UNVERIFIED
Worker 2 | M2 | P2 | T-266 | Release-1 Industrial Integration / OPC UI workflows and capability-truth visual handoff | Not Started |  |  | T-207 | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | UI companion OPC scene subset only; Worker 1 reviews endpoint/security/time/spool contracts; CENTRAL merges shared UI data. | UI design completion is not product implementation completion. Reuse the current authorities/components; use per-surface handoffs and no shared-file concurrent writes. | NOT STARTED — DESIGN DELIVERY | T-224; T-225; T-226; T-233
Worker 2 | M2 | P3 | T-148 | Map the 108 page files onto the 40 target pages | Not Started | 8 | 1.3333 |  | R1 route inventory and six shell contracts frozen. Contract-ready handoffs from T-196/T-197/T-198/T-199/T-200 are recorded separately in column AN. Do not wait for the entire M3 implementation or ship a simulated M3 page. | Own route inventory/redirect cleanup only; do not touch W3 intelligence surfaces. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | Not started — no completion claimed | T-196; T-197; T-198; T-199; T-200; T-265; T-266
Worker 2 | M2 | P3 | T-215 | Reference gap, attainment and envelope measures in registry/BI | Not Started | 10 | 4 | T-092; T-214; T-232 | T-092 + T-214. | Registry projection + query measures + widget labels. | Consume reference ID/version and scoring semantics; no local UI formula. | Not started — no completion claimed
Worker 2 | M2 | P3 | T-222 | D1/D4 reconciliation evidence surface and reference overlay | Not Started | 10 | 4.25 | T-219; T-220; T-215; T-203; T-204 | T-219/T-220 result contract + T-215 + T-203/T-204. Do not create a demo-only store. | D1/D4 generic components only; no new oil route. | Use existing governed evidence/result contract. T-221 later changes persistence behind the contract without UI redesign. | Not started — no completion claimed
Worker 2 | M2 | P3 | T-258 | Frontend material-surface genericity convergence and presentation compatibility | Not Started | 8 | 3.4 | T-094; T-250; T-256 | WAIT for T-256 CLOSED and its frontend-consumer handoff manifest. Then perform bounded frontend-only convergence; do not re-investigate backend genericity. | Frontend MaterialAnalytics/generic navigation/types/tests only. No Backend/API/DB mutation and no Canvas/Job implementation. | T-256 defines backend semantic/compatibility truth; T-258 consumes it. T-247 validates the same-binary customer journey and does not redesign either side. | Not started — no completion claimed
Worker 2 | M2 | P3 | T-265 | Release-1 UI design depth, workflow and illustrated-companion convergence | Not Started |  |  |  | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | UI companion: non-OPC M2 scenes + Chapter 3/4 reading-edition assets. CENTRAL alone merges shared tokens/data/atlas; no product source lock. | UI design completion is not product implementation completion. Reuse the current authorities/components; use per-surface handoffs and no shared-file concurrent writes. | NOT STARTED — DESIGN DELIVERY | T-099; T-106; T-253; T-262; T-101; T-125
Worker 2 | M2 | P4 | T-237 | Operational Period Driver Decomposition exact API and evidence tool | Not Started | 10 | 4.25 | T-092; T-235 | T-092 + T-235; can run in parallel with T-222 on separate files. | Layer-A period comparison API/evidence only. | T-138/T-164 may consume the stable contract; neither may duplicate calculations. | Not started — no completion claimed
Worker 2 | M2 | P5 | T-120 | Users and Roles administration surface | Not Started | 12 | 2 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M2 | P5 | T-257 | Frontend execution-truth and release-profile skip-zero gate | Not Started | 6 | 2.55 | T-205; T-250; T-259 | Run on frontend test/config/report files only after current authoring lane reaches a clean handoff; no product feature scope. | Frontend package/test configs/gate scripts/generated-report hygiene only. | T-150 consumes this machine-readable release truth; T-248 later extends enterprise visual parity, not test-runner semantics. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-127 | Canonical journey regression and the Continuity comparison | Not Started | 12 | 4.08 | T-196; T-197; T-198; T-199; T-200; T-121 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: All Release 1 canonical-core/user-visible owners complete, including T-196/T-197/T-... | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Continuity green → W1 executes T-194; Release 1 release gate may close. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-149 | Delete the legacy redirects and re-verify continuity | Not Started | 6 | 1 |  | M1 continuity frozen | Own route inventory/redirect cleanup only; do not touch W3 intelligence surfaces. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-196 | C4 Plant Model Explorer canonical route and structural evidence surface | Not Started | 8 | 1.3333 | T-087; T-094; T-095 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-094 + T-095 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-197 | E6 Alert Routing and Escalation with delivery, retry and dead-letter evidence | Not Started | 10 | 2.2857 | T-119; T-198 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 + T-198 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-198 | F5 Logging and Audit plus F6 Log Channel Configuration | Not Started | 12 | 2.7429 | T-112; T-114; T-119 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-112 + T-114 + T-119 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-199 | F9 Log Retention and Archival with dry-run, legal hold and no-delete-on-archive-failure | Not Started | 12 | 2.7429 | T-124; T-198 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-124 + T-198 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P2 | T-200 | F7 System Settings and F8 Translation/Language canonical administration | Not Started | 10 | 2.2857 | T-113; T-119; T-216 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-113 + T-119 | Own named UI/admin task end-to-end only after producer APIs/security are committed. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P3 | T-156 | Customer definitions built through the product | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own customer-facing UX/docs/website only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P3 | T-166 | Five-product website production completion | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own customer-facing UX/docs/website only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 2 | M3 | P3 | T-248 | Advanced enterprise BI and authoring parity closure against the 75-item outcome matrix | Not Started |  |  | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257; T-267 | After M2 Release 1 and InsightBoard authoring base | Frontend BI / authoring only | Reuse the existing BI engine, Page Builder, Canvas, export and selection contracts; do not build a second dashboard engine. | Not started — no completion claimed
Worker 2 | M3 | P3 | T-263 | Governed reports, export and scheduled delivery | Not Started |  |  | T-106; T-248 | Consume accepted producer contracts; remaining dependencies: T-106; T-248. No private scheduler/definition authority. Source-present is not closure proof. | Semantic product filenames only. CENTRAL assigns shared file locks before overlapping worker writes. | Reuse current canonical authorities; no shadow lifecycle/registry/scheduler. | Not started — no completion claimed
Worker 2 | M3 | P3 | T-267 | Release-2 interface depth and enterprise BI/authoring parity design | Not Started |  |  | T-265 | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | UI companion M3 subset; shared token/atlas/Word merge owned by CENTRAL; no duplicate functional authority. | UI design completion is not product implementation completion. Reuse the current authorities/components; use per-surface handoffs and no shared-file concurrent writes. | NOT STARTED — DESIGN DELIVERY | T-248; T-263; T-264; T-196; T-197; T-198; T-199; T-200
Worker 2 | M3 | P4 | T-246 | Canvas governed model/intelligence block invocation | Not Started | 11 | 4.7 | T-243; T-130; T-137; T-187 | Consume accepted producer contracts; remaining dependencies: T-243; T-130; T-137; T-187. No private scheduler/definition authority. Source-present is not closure proof. | Canvas model/intelligence block adapters only. | T-130/model registry and T-137 serving runtime remain authorities. | Not started — no completion claimed
Worker 2 | M3 | P5 | T-167 | Documentation, training and production acceptance | Not Started | 12 | 7.2 |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence | Own customer-facing UX/docs/website only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M2 | P1 | T-206 | Scope-aware genericity architecture gate | Done | 8 | 2 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Architecture/genericity tests only; no W1 schema or W2 UI mutation. | Violations are routed to the owning task/file; Worker 3 does not fix foreign files. | Recorded closed — inherited evidence
Worker 3 | M2 | P1 | T-208 | Generic controlled validation fixture authority and continuous-process known-answer pack | Done | 10 | 2.5 | T-201 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New generic fixture/test assets only. | T-211/T-217/T-219 consume this fixture; they never read planted expected answers at runtime. | Recorded closed — inherited evidence
Worker 3 | M2 | P1 | T-209 | Analysis Subject and Grain contract + schema-independent resolution kernel | Done | 6 | 1.5 | T-208 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New generic contract/kernel/tests only. | T-231 persists this contract; downstream consumers bind to contract, not table shape. | Recorded closed — inherited evidence
Worker 3 | M2 | P1 | T-216 | Source Time Authority contract and timestamp-semantics kernel | Done | 5 | 1.25 | T-208 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Temporal contract/tests only. | T-233 persists source-time authority; T-217 consumes contract without waiting for persistence. | Recorded closed — inherited evidence
Worker 3 | M2 | P2 | T-106 | Canonical jobs: target/version, scheduling, dependencies, cancellation and outcome truth | Done |  |  | T-064; T-089; T-090; T-252 | Consume accepted producer contracts; remaining dependencies: T-064; T-089; T-090; T-252. No private scheduler/definition authority. Source-present is not closure proof. | Own T-106/T-107/T-109 only after W1 producer contracts; no schema authority rewrites. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | BASELINE COMMITS PROVEN; CURRENT WIDENED ACCEPTANCE OPEN
Worker 3 | M2 | P2 | T-107 | Dual-predicate admission, bounded worker pools and the three ML execution lanes | Not Started | 16 | 1.8 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-106 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 canonical job contract + T-095..T-105 canonical data/relationship path;... | Own T-106/T-107/T-109 only after W1 producer contracts; no schema authority rewrites. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M2 | P2 | T-109 | Delta-scoped feature refresh and analysis, with telemetry and ML hand-off | Not Started | 6 | 0.9 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-108 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095..T-105; T-108 | Own T-106/T-107/T-109 only after W1 producer contracts; no schema authority rewrites. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M2 | P4 | T-211 | Aggregation semantics execution kernel with continuous known answers | Not Started | 10 | 2.5 | T-208; T-210 | T-208 fixture + T-210 frozen contract. No production DI/persistence until consumer hand-off. | New analytics kernel/tests only. | T-212 consumes this kernel unchanged; W3 does not edit dashboard query files. | Not started — no completion claimed
Worker 3 | M2 | P4 | T-214 | Performance Reference contract, precedence and scoring-semantics kernel | Not Started | 6 | 1.5 | T-209 | T-209 frozen generic subject contract. | Reference contract/resolver tests only. | T-232 persists reference authority; consumers do not redefine scoring semantics. | Not started — no completion claimed
Worker 3 | M2 | P4 | T-217 | Temporal evidence alignment kernel | Done | 10 | 2.5 | T-208; T-216 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New temporal kernel/tests only. | T-219 consumes alignment output; does not reimplement clock logic. | Recorded closed — inherited evidence
Worker 3 | M2 | P4 | T-218 | Fact Evidence Authority resolution kernel | Done | 8 | 2 | T-208 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New evidence-authority contracts/kernel/tests. | T-219 consumes authority result; no source priority duplicated elsewhere. | Recorded closed — inherited evidence
Worker 3 | M2 | P4 | T-219 | Operational Evidence Reconciliation kernel and seven-state taxonomy | Done | 12 | 3.2 | T-217; T-218; T-236 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New reconciliation kernel/tests only. | T-220 adds claim confidence; T-221 persists output after canonical/security hand-off. | Recorded closed — inherited evidence
Worker 3 | M2 | P4 | T-220 | Causal Confidence Ladder and root-cause hypothesis evaluator | Done | 8 | 2 | T-219 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Claim-confidence kernel/tests only. | T-221/T-223 consume stored level; UI/LLM never re-derive it. | Recorded closed — inherited evidence
Worker 3 | M2 | P4 | T-221 | Canonical reconciliation persistence, evidence handles and bindable source | Not Started | 12 | 5.4 | T-112; T-114; T-090; T-095; T-096; T-219; T-220; T-233 | T-112 + T-114 + T-090 + T-095/T-096 + T-219 + T-220. If security hand-off is not green, remain on pure-kernel evidence and do not create insecure tables. | Reconciliation persistence/registry/evidence only. | Post-demo canonical convergence. T-222/T-223 must not wait for this table and must not invent a temporary persistence schema. | Not started — no completion claimed
Worker 3 | M2 | P4 | T-223 | Grounded Assistant tool for reconciliation and Performance Reference explanation | Not Started | 10 | 4.25 | T-179; T-180; T-181; T-214; T-219; T-220 | T-179/T-180/T-181 CLOSED + T-214 + T-219/T-220. No canonical persistence dependency for September explanation. | Assistant tool/evidence pack/verifier only; current dock UI remains Worker-2 owned. | T-221 later swaps persistence behind the same evidence contract; Assistant tool does not redesign. | Not started — no completion claimed
Worker 3 | M2 | P4 | T-234 | Operational Transition and Stabilisation contract/kernel | Done | 8 | 2 | T-208; T-209 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | New generic transition/stabilisation contract/tests only. | T-235 persists unchanged contract; T-236 consumes it without redefining semantics. | Recorded closed — inherited evidence
Worker 3 | M2 | P4 | T-236 | Transition-aware aggregation, statistics and reconciliation guard | Done | 10 | 2.6667 | T-217; T-234 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | Analytics/reconciliation kernels only. | T-219 consumes the guard; consumers must not bypass RG01. | Recorded closed — inherited evidence
Worker 3 | M2 | P5 | T-255 | Repository authority and audit-truth hygiene ratchet | Not Started | 8 | 1.2 | T-205; T-250 | Run after T-106 or on a disjoint tooling-only lane; no runtime feature mutation. | Root/tooling/audit generator/architecture hygiene tests only. Do not rename or edit Worker-1/2 runtime feature files. | Legacy task-ID filenames are grandfathered, not mass-renamed. Future tasks consume the forward gate. | Not started — no completion claimed
Worker 3 | M3 | P1 | T-155 | B-01/B-02 capacity tuning, scan amplification and model-serving memory | Not Started |  |  |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + site hardware | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P1 | T-159 | C1 to C4 capacity certification | Not Started |  |  |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + site hardware | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P3 | T-228 | Versioned InsightBoardPlan contract and deterministic validator | Not Started | 10 | 3.2 | T-090; T-092; T-134; T-179; T-180; T-181 | After September customer RC; T-090/T-092 + T-134 + T-179..181. | New Assistant plan contract/tests only. | T-229 consumes validator; no direct UI generation. | Not started — no completion claimed
Worker 3 | M3 | P3 | T-229 | Governed Assistant plan-to-widget Investigation Board composition | Not Started | 12 | 6.1714 | T-228; T-134 | T-228 + T-134 + stable Page Builder contract; coordinate UI consumption with Worker 2. | Assistant composition service; UI host changes require explicit W2 hand-off. | T-230 adds persistence; no separate rendering engine. | Not started — no completion claimed
Worker 3 | M3 | P3 | T-230 | Persisted Investigation Board version, replay and Save-as-Page handoff | Not Started | 12 | 5.1 | T-229; T-112; T-114 | T-229 + canonical definition/evidence persistence + T-112/T-114. | Investigation board persistence and conversion contract. | Page Builder owns resulting page definitions; Assistant owns historical investigation artifact only. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-128 | Feature store, outcome store and immutable snapshot metadata | Not Started | 10 | 1.5 | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114; T-231; T-210 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-087..T-105 + T-112 + T-114 security/tenant hand-off. Outcome semantics from... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-129 | Compute runs, findings and common evidence persistence | Not Started | 12 | 1.8 | T-128; T-183; T-112; T-114 | T-128 + T-183 + T-112 + T-114. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-130 | Model registry, serving identity, activation and fallback | Not Started | 12 | 1.8 | T-128; T-183; T-112; T-114 | T-128 + T-183 + T-112 + T-114. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-131 | Practice signature, windowing, context and cohorts | Not Started | 12 | 1.8 | T-086; T-128; T-171 | T-086 + T-128 + T-171 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-132 | Support, confidence, back-off ladder and tolerance sensitivity | Not Started | 12 | 1.8 | T-131 | T-131 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-133 | Practice persistence, drift and canonical D10 Practice Insights | Not Started | 12 | 1.8 | T-131; T-132; T-183 | T-131 + T-132 + T-183 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-134 | Bindable intelligence registry and evidence handles | Not Started | 12 | 1.8 | T-090; T-095; T-096; T-129; T-130; T-133; T-186; T-139 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 definition authority + T-095/T-096 relationship resolver + available ca... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-135 | Tenant-aware uniqueness across the intelligence tables | Not Started | 10 | 1.9375 | T-112; T-114; T-128; T-129; T-130; T-183 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-112 + T-114 + current Release 2 persistence tables (including T-128/T-129/T-130/T... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-136 | Incremental practice recomputation | Not Started | 10 | 1.5 | T-131; T-132; T-133; T-109 | T-109 + T-131..T-133 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-138 | Canonical Assistant runtime cutover: planner, retrieval, evidence packing, serving and verifier | Not Started | 12 | 1.8 | T-179; T-180; T-181; T-137; T-134; T-188 | T-137 + T-179..T-181 + T-134 + T-188 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-139 | prediction_runs, predictions and prediction_current | Not Started | 12 | 1.8 | T-130; T-187; T-231 | T-130 + T-187 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-140 | Prediction drivers and comparables, persisted | Not Started | 12 | 1.8 | T-139; T-173; T-176 | T-139 + T-173/T-176 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-141 | Actionable deadline and latency health | Not Started | 12 | 1.8 | T-107; T-122; T-139; T-187 | T-107 + T-122 + T-139 + T-187 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-142 | Remediation candidate generation from the customer's own history | Not Started | 8 | 1.2 | T-131; T-132; T-139; T-140 | T-131/T-132 + T-139/T-140 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-143 | Integrate the nine-check remediation gate, can_accept and suppression | Not Started | 8 | 1.2 | T-178; T-142 | T-178 + T-142 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-144 | Accept, Reject and Defer with action recording | Not Started | 8 | 1.2 | T-143 | T-143 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-145 | Outcome capture, evaluation and escalation | Not Started |  |  | T-144 | T-144 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-146 | Converge the production statistical engine onto the certified method kernel | Not Started |  |  | T-147; T-177; T-128; T-129 | T-147 COMPLETE + T-177 + T-128/T-129; M1 presentation continuity frozen. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-147 | Fix the outcome namespace, grain assignment and ordinal loader | Not Started | 12 | 1.8 | T-090; T-128; T-129; T-177 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 canonical SM-06 binding + T-128/T-129 + T-177; complete BEFORE T-146 fi... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-157 | Practice, prediction and model calibration on real data | Not Started | 12 | 4.32 |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + customer data window | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-158 | Remediation validation against real process constraints | Not Started | 12 | 4.32 |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + customer data window | Own AI/ML calibration/capacity evidence only. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-183 | Semantic Contract Manifest persistence, resolver and G-55 coverage | Not Started | 12 | 1.8 | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-089..T-105 canonical definition/relationship authority + T-112 + T-114 secu... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-184 | Snapshot Materialiser: seal feature state into typed artifacts and enforce G-48 | Not Started | 12 | 1.8 | T-128; T-169; T-183; T-112; T-114; T-135 | T-128 + T-169 + T-183 + T-112/T-114/T-135 security ratchet. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-185 | sequence_manifests persistence and object-storage sequence path | Not Started | 12 | 1.8 | T-170; T-183; T-122; T-112; T-114; T-135 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-170 + T-183 + T-122 final object-storage/container path + T-112/T-114/T-135... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-186 | Persist capability profiles, prediction points and the model-count governor | Not Started |  |  | T-171; T-183; T-128; T-129; T-195; T-135 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-171 + T-183 + T-128/T-129 + T-195 canonical readiness thresholds + T-135 se... | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-187 | Production training/index integration: snapshots → ML lanes → registry activation | Not Started | 12 | 1.8 | T-168; T-169; T-170; T-171; T-172; T-173; T-174; T-175; T-176; T-183; T-184; T-185; T-186; T-107; T-109; T-112; T-114; T-135; T-195 | T-107 + T-109 + T-168..T-176 + T-183..T-186 + T-112/T-114/T-135 + T-195. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-188 | Canonical D4 Findings and D8 ML Readiness/Models cutover | Not Started | 10 | 1.6667 | T-129; T-130; T-186; T-195 | T-129 + T-130 + T-186 + T-195 + M1 continuity snapshots. | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-189 | Canonical D5 Risk and D9 Early Warning cutover | Not Started | 12 | 2 | T-139; T-140; T-141; T-142; T-143 | T-139..T-143 + M1 continuity snapshots | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-190 | Canonical D6 Suggestions and decision-action cutover | Not Started |  |  | T-142; T-143; T-144; T-145 | T-142..T-145 + M1 continuity snapshots | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-191 | D11 Scenario Simulation: governed read-only modelled comparison | Not Started | 12 | 1.8 | T-130; T-176; T-187 | T-130 + T-176 + T-187 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-192 | Target-architecture gate pack G-48..G-55 | Not Started | 10 | 1.7 | T-183; T-184; T-185; T-186; T-187; T-188; T-189; T-190; T-191; T-107; T-122 | T-183..T-191 + T-107/T-122 as applicable | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-193 | Drift Supervisor and governed model-action proposals | Not Started | 10 | 1.5 | T-130; T-187; T-139; T-145 | T-130 + T-187 + T-139/T-145 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-195 | Canonical readiness thresholds, governed change history and fail-closed readiness API | Not Started | 10 | 1.5 | T-090; T-112; T-114 | T-090 + T-112 + T-114 | Own intelligence/ML/Assistant and named intelligence surfaces. W1/W2 forbidden after hand-off. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-238 | Multi-objective Objective Set and Pareto practice kernel | Not Started | 12 | 3.2 | T-208; T-214 | May start after T-214 contract; does not block September demo. | New objective/Pareto kernel/tests only. | T-239 persists objective authority; T-240 integrates practice family. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-240 | Composite practice results, trade-off explanation and Assistant tool integration | Not Started | 12 | 5.1 | T-131; T-132; T-133; T-238; T-239 | After practice core + objective persistence. | Practice intelligence/Assistant tool only. | T-138 may expose this tool after completion; no Assistant redesign. | Not started — no completion claimed
Worker 3 | M3 | P4 | T-264 | Registry-driven internal benchmarking | Not Started |  |  | T-214; T-240 | Consume accepted producer contracts; remaining dependencies: T-214; T-240. No private scheduler/definition authority. Source-present is not closure proof. | Semantic product filenames only. CENTRAL assigns shared file locks before overlapping worker writes. | Reuse current canonical authorities; no shadow lifecycle/registry/scheduler. | Not started — no completion claimed
Worker 1 | M2 | P2 | T-268 | Industrial acquisition configuration and stable field authority | Not Started |  |  | T-207 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 1 | M2 | P2 | T-269 | Declarative DataBlock/message layout decoder and source-event identity | Not Started |  |  | T-268 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 1 | M2 | P2 | T-270 | Industrial recording policy and trigger/capture state-machine executor | Not Started |  |  | T-268; T-269; T-225; T-233; T-275 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 1 | M2 | P2 | T-271 | Qualified relational and file acquisition convergence | Not Started |  |  | T-268; T-108 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 1 | M2 | P2 | T-272 | Dataset-oriented Dump Store accepted-record and consumer contract | Not Started |  |  | T-087; T-088; T-251; T-252; T-268 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 1 | M2 | P2 | T-273 | Industrial source capacity, retention and replay lifecycle control | Not Started |  |  | T-272; T-124 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 2 | M2 | P2 | T-274 | Executable unified Industrial Integration configuration UX | Not Started |  |  | T-254; T-266; T-268; T-269; T-270; T-271; T-272; T-273; T-275 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE
Worker 3 | M2 | P2 | T-275 | Continuous acquisition Job runtime, fencing and finite microbatch lifecycle | Not Started |  |  | T-106; T-107; T-268 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes. | Own only the named Industrial Integration subsystem slice; no private scheduler/definition/source-time/capability authority. | Preserve existing closed producers and contracts. Implement the delta; do not reopen earlier tasks merely because v4.11.0 adds a new consumer/acceptance slice. | NOT STARTED — v4.11.0 NEW SCOPE

## Requirement Traceability
Requirement Traceability — current Backlog v2.23.0
Requirement family | Design authority | M2 Release 1 | M3 Release 2 | Primary tasks | M2 acceptance | M3 acceptance | Customer use | Mirror state | Ruling
DB Link / external databases | Ch3 4.5 + Ch4 5.0.0 | Day-1 production | Scale/certification | T-207; T-247; T-254; T-095..105 | Connect→browse→preview→map→import→canonical with no product-code diff; capability/certification copy comes from one executable truth | Real-source endurance and complex relationship certification | Customer IT day 1 | MIRRORED | M2 first priority
Canvas / SQL / data preparation | Ch4 5.0.0 + 5.2 | Day-1 production core | Advanced authoring parity | T-241..246; T-253; T-248 | Typed Canvas/SQL, governed output target, validate/dry-run, save/version, Job bind; no hardcoded plant/material output identity | Scoped measure, named states, advanced story/export/subflow parity | Customer IT day 1 | MIRRORED | No unbounded loops
Jobs / scheduling / logs | Ch4 5.3 + Ch6 runtime | Day-1 run/schedule/monitor/log | High-volume lanes/capacity | T-106..111; T-125; T-245; T-227 | Registered executors, target/version, DAG, bounded admission/parallelism, run/monitor/log with mandatory run identity | Capacity, scan amplification, checkpoint/resume under heavy load | Customer IT day 1 | MIRRORED | Core in M2, scale in M3
Enterprise BI/HMI | Ch3 pages + Ch4 5.0.0/5.1 | Enterprise core | Advanced parity | T-148; T-202..205; T-212; T-215; T-222; T-250; T-257; T-258; T-248 | Associative/persisted enterprise core, frontend execution truth, and generic customer HMI with material-specific surfaces bounded to presentation compatibility; advanced BI parity in Release 2. | 75-item matrix fully closed incl advanced states/story/export | All users day 1 | MIRRORED | Qlik-class outcome, PPIQ semantics
Production OPC UA | Ch2 OT boundary + Ch6 edge | Read-only production path | Endurance/certification | T-207; T-224..226; T-153 | Real session/browse/subscription/quality/timestamps/spool-to-canonical | Real-source endurance and site certification | Operations week 1 | MIRRORED | No fake sample claim
Performance Reference | Ch3/Ch4 reference authority | Visible and usable | Deeper scale/authoring | T-214; T-232; T-215 | Customer standard/target/envelope visible with correct scoring direction | Advanced authoring and large-scale governance | Operations/Quality | MIRRORED | Reference can be 100% aim
Reconciliation / root cause | Ch3/Ch4 evidence authority | Historical + live evidence | Persisted/advanced | T-217..223; T-221 | Seven evidence states + causal confidence + grounded explanation | Canonical persistence at scale and richer workflows | Operations/Quality | MIRRORED | Never claim human intent/lie
Assistant / LLM | Ch4 Layer-B + Assistant contracts | Grounded investigation | InsightBoard composition | T-179..181; T-223; T-138; T-228..230 | Governed tools/evidence; no material-specific KPI authority; provider labels require concrete adapters/conformance | Auto-generated governed investigation boards | All analytical users | MIRRORED | LLM never invents plant numbers
Multi-objective best practice | Ch4 practice intelligence | Foundation available | Full Pareto/product integration | T-171..176; T-238..240 | Underlying kernels available; not Release-1 blocker | Objective sets, Pareto/non-dominance, trade-off explanation | Operations/CEO | MIRRORED | No hidden weights
Transition / stabilisation | Ch3/Ch4 regime context | Correctness gate | Scale/learning integration | T-234..236; T-235 | Findings state stable/transition/stabilising/mixed and refuse unsafe pooling | Extended real-data calibration | Operations/Quality | MIRRORED | Prevents confident wrong correlation
Financial value / ROI | Ch1 value promise + Ch4/Ch6 Value Engine | Existing potential-value evidence may be shown bounded | Customer-grade realised ROI | T-164; existing value engine + T-237 | No ungoverned monetary promise | Real assumptions, realised-value ledger, heavy-use value certification | CEO | MIRRORED | M3 owns customer-certified €/$ value
Users / roles / licence / security | Ch3/Ch6 administration/security | Minimum production-safe controls | Deep enterprise administration | T-112..121; T-161..162; T-198..200 | RLS behavioral proof, fail-closed eight-role mapping, vendor-held licence trust root, secret/config/MFA hygiene | SSO, advanced admin/logging/retention/site hardening | Admin/IT | MIRRORED | Important but not allowed to starve Day-1 workbench
Database schema authority / physical dictionary | Ch3 4.5.2/4.5.5b/4.5.20a | Zero-unknown fresh schema + upgrade reconciliation | Heavy-use schema evolution and compatibility-safe convergence | T-087; T-088; T-115; T-123; T-251; T-252; T-256; T-258 | Zero-unknown physical catalogue + disposable certification DBs + backend runtime three-schema/genericity convergence + frontend consumer handoff with no cross-owner mutation. | Schema evolution remains generated, reversible where possible and customer-operable at scale | Developer + Customer IT | MIRRORED | Table count is not a defect; unowned/undocumented authority is.
Repository / audit / release-truth source authority | Governance + Ch6 release truth | Forward-clean source authority and truthful executed gates | Sustained release governance | T-205; T-250; T-255; T-257; T-150; T-249 | Root allowlist; no transient run-state/pack payload; audit severity excludes self/backups/generated; gate scripts execute, release profile zero unapproved skips | Same rules remain green under Release-2 production certification | Developer / Customer IT | MIRRORED | No mass-renaming of grandfathered task-ID files; forward gate prevents new violations

## Dependency Graph
Task Id | Release | Phase | Owner | Status | Usable P80 h | Depends On | Must Precede | Gate | Contract-ready predecessors
T-086 | M2 | P1 | Worker 1 | Done | 2.72 | T-201 | T-087; T-088; T-131 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-087 | M2 | P1 | Worker 1 | Done | 2.325 | T-086; T-088 | T-089; T-099; T-102; T-112; T-114; T-128; T-196; T-233; T-251; T-252 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-088 | M2 | P1 | Worker 1 | Done | 2.325 | T-086 | T-087; T-089; T-112; T-128; T-251; T-252; T-256; T-260 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-089 | M2 | P1 | Worker 1 | Done | 2.325 | T-087; T-088 | T-090; T-092; T-095; T-099; T-106; T-114; T-128; T-183; T-243; T-244 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-090 | M2 | P1 | Worker 1 | Done | 1.8 | T-089 | T-091; T-092; T-095; T-099; T-104; T-106; T-114; T-128; T-134; T-147; T-183; T-195; T-210; T-221; T-228; T-231; T-232; T-233; T-235; T-239; T-243; T-244 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-091 | M2 | P1 | Worker 1 | Done | 1.8 | T-090 | T-128; T-183 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-092 | M2 | P1 | Worker 1 | Done | 1.8 | T-089; T-090; T-210; T-231 | T-093; T-094; T-128; T-183; T-212; T-215; T-228; T-237; T-247 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-093 | M2 | P1 | Worker 1 | Done | 0.9 | T-092; T-206 | T-094; T-128; T-183 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-094 | M2 | P1 | Worker 1 | Done | 3.6 | T-092; T-093; T-209 | T-095; T-128; T-183; T-196; T-253; T-256; T-258 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-201 | M2 | P1 | Worker 1 | Done | 1.5 |  | T-086; T-202; T-203; T-204; T-205; T-206; T-207; T-208; T-213; T-241 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-202 | M2 | P1 | Worker 2 | Done | 4 | T-201 | T-212; T-248 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-203 | M2 | P1 | Worker 2 | Done | 4 | T-201 | T-222; T-248 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-204 | M2 | P1 | Worker 2 | Done | 4.25 | T-201 | T-222; T-248 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-205 | M2 | P1 | Worker 2 | Done | 3.2 | T-201 | T-150; T-248; T-250; T-255; T-257 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-206 | M2 | P1 | Worker 3 | Done | 2 | T-201 | T-093; T-213 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-208 | M2 | P1 | Worker 3 | Done | 2.5 | T-201 | T-209; T-211; T-216; T-217; T-218; T-234; T-238 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-209 | M2 | P1 | Worker 3 | Done | 1.5 | T-208 | T-094; T-210; T-214; T-231; T-234; T-253 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-210 | M2 | P1 | Worker 1 | Done | 5.1 | T-090; T-209 | T-092; T-128; T-211; T-212; T-242 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-216 | M2 | P1 | Worker 3 | Done | 1.25 | T-208 | T-200; T-217; T-233 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-231 | M2 | P1 | Worker 1 | Done | 2.55 | T-090; T-209 | T-092; T-128; T-139; T-232; T-235 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-250 | M2 | P1 | Worker 2 | Done | 2.5 | T-205 | T-150; T-255; T-257; T-258 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-251 | M2 | P1 | Worker 1 | Done | 1.8 | T-087; T-088; T-260 | T-112; T-150; T-252; T-256; T-259 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-252 | M2 | P1 | Worker 1 | Done | 1.2 | T-087; T-088; T-251; T-259 | T-106; T-112; T-150; T-256 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-256 | M2 | P1 | Worker 1 | Done | 3.2 | T-088; T-094; T-251; T-252; T-253 | T-116; T-150; T-247; T-258 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-259 | M2 | P1 | Worker 1 | Done | 0.3 | T-251 | T-150; T-227; T-252; T-257 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-260 | M2 | P1 | Worker 1 | Done | 1.8 | T-088 | T-251 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-095 | M2 | P2 | Worker 1 | Done | 1.8 | T-057; T-089; T-090; T-094 | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-114; T-128; T-134; T-183; T-196; T-221 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-096 | M2 | P2 | Worker 1 | Done | 1.2 | T-095 | T-097; T-098; T-107; T-109; T-128; T-134; T-183; T-221 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-097 | M2 | P2 | Worker 1 | Done | 0.9 | T-096 | T-098; T-107; T-109; T-128; T-183 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-098 | M2 | P2 | Worker 2 | Not Started | 2 | T-095; T-096; T-097 | T-107; T-109; T-128; T-183 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-060 M1 C6 surface + T-095 + T-096 + T-097.
T-099 | M2 | P2 | Worker 1 | Done | 1.2 | T-087; T-089; T-090 | T-100; T-101; T-104; T-107; T-108; T-109; T-114; T-128; T-183; T-261 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-100 | M2 | P2 | Worker 1 | Done |  | T-099 | T-101; T-107; T-109; T-128; T-183; T-261 | RUNNER-1 CANDIDATE IS PRESENT; DO NOT RERUN RUNNER 1 or require a clean owned tree relative to HEAD. Resume from the exact handoff/postimages. Resume v1.0.1 is issued; success is not yet reported. Validate HEAD against the handoff and all owned postimage hashes before continuing. Expected parent supplied for closure is 4e0f1219ddbac3163bafe7ce510b62520683a77c; do not substitute the older T-099-only HEAD. If the exact gates fail, stop and report without manual resets, cleanup of unrelated work, or a fresh mutation pack. Worker 1/CENTRAL retains the execution lock through T-100 final commit; Worker 2 remains held.
T-101 | M2 | P2 | Worker 2 | Not Started |  | T-099; T-100 | T-107; T-109; T-128; T-183 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-061 final M1 API/page contract + T-099 + T-100 canonical quarantine impleme...
T-102 | M2 | P2 | Worker 1 | Not Started | 1.2 | T-087; T-095 | T-103; T-107; T-109; T-128; T-183 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 canonical plant schema + T-095 relationship/material identity authority.
T-103 | M2 | P2 | Worker 1 | Not Started |  | T-095; T-102 | T-107; T-109; T-128; T-183 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095 + T-102 canonical relationship/identity authority.
T-104 | M2 | P2 | Worker 1 | Not Started |  | T-090; T-095; T-099; T-261 | T-107; T-108; T-109; T-128; T-183; T-247 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-090 canonical versioned mapping definitions + T-095 relationship authority ...
T-106 | M2 | P2 | Worker 3 | Done |  | T-064; T-089; T-090; T-252 | T-107; T-122; T-125; T-245; T-261; T-263 | Consume accepted producer contracts; remaining dependencies: T-064; T-089; T-090; T-252. No private scheduler/definition authority. Source-present is not closure proof.
T-107 | M2 | P2 | Worker 3 | Not Started | 1.8 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-106 | T-122; T-125; T-141; T-187; T-192 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 canonical job contract + T-095..T-105 canonical data/relationship path;...
T-108 | M2 | P2 | Worker 1 | Not Started |  | T-099; T-104 | T-109; T-110; T-247 | Consume accepted producer contracts; remaining dependencies: T-099; T-104. No private scheduler/definition authority. Source-present is not closure proof.
T-109 | M2 | P2 | Worker 3 | Not Started | 0.9 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-108 | T-110; T-136; T-187 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095..T-105; T-108
T-207 | M2 | P2 | Worker 1 | Done | 2.25 | T-201 | T-150; T-224; T-247; T-254; T-266 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-212 | M2 | P2 | Worker 2 | Not Started | 5.1429 | T-202; T-210; T-211; T-092; T-234; T-235; T-236 | T-150; T-247 | T-202 + T-210/T-211 + T-092 + committed T-234/T-235/T-236.
T-213 | M2 | P2 | Worker 2 | Done | 3.2 | T-201; T-206 | T-227; T-247 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-224 | M2 | P2 | Worker 3 | Not Started |  | T-207 | T-153; T-225 | Release 1 MUST — start after T-207 connector-truth authority. Site/customer OT certification may require customer access, but the executable production OPC UA runtime itself cannot be deferred past M2.
T-225 | M2 | P2 | Worker 3 | Not Started |  | T-224 | T-153; T-226 | T-224.
T-226 | M2 | P2 | Worker 3 | Not Started |  | T-225; T-233; T-270; T-272; T-275 | T-150; T-153 | T-225 + T-216 Source Time Authority.
T-232 | M2 | P2 | Worker 1 | Not Started | 2.55 | T-090; T-231; T-214 | T-215 | T-090 + T-231 + committed T-214 contract.
T-233 | M2 | P2 | Worker 1 | In Progress | 2.125 | T-087; T-090; T-216 | T-221; T-226 | T-087 + T-090 + committed T-216 contract.
T-235 | M2 | P2 | Worker 1 | Not Started |  | T-090; T-231; T-234 | T-164; T-212; T-237; T-247 | T-090 + T-231 + committed T-234 contract.
T-241 | M2 | P2 | Worker 2 | Done |  | T-032; T-201 | T-242; T-243; T-247; T-248; T-253; T-261 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-242 | M2 | P2 | Worker 2 | Done |  | T-241; T-210 | T-243; T-247; T-261 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-243 | M2 | P2 | Worker 2 | Done |  | T-241; T-242; T-089; T-090; T-253 | T-245; T-246; T-247; T-248; T-261; T-262 | Consume accepted producer contracts; remaining dependencies: T-241; T-242; T-089; T-090; T-253. No private scheduler/definition authority. Source-present is not closure proof.
T-244 | M2 | P2 | Worker 2 | Done |  | T-035; T-036; T-089; T-090 | T-245; T-247; T-248; T-253 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-245 | M2 | P2 | Worker 2 | Not Started | 5.1 | T-243; T-244; T-106; T-261; T-262 | T-247; T-248 | QUEUED after T-261 closure; current mutation sequence is T-099 → T-100 → T-261 → T-245. T-245 consumes the proven executor/runtime and per-block evidence, never recreates them. Retain all listed canonical prerequisite contracts.
T-247 | M2 | P2 | Worker 2 | Not Started | 5.1 | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235; T-262; T-125; T-265; T-266; T-274 | T-150 | T-213 complete + T-092 green. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns.
T-253 | M2 | P2 | Worker 2 | Done | 4.8 | T-094; T-209; T-241; T-244 | T-150; T-243; T-247; T-256; T-262 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-254 | M2 | P2 | Worker 2 | In Progress |  | T-207 | T-150; T-153; T-247 | Original UI/website convergence is frozen at f8a35725. Only the v2.22 backend-provider-authority delta is outstanding. Consume T-207 and existing contracts on disjoint paths; column M remains the completion-prerequisite list. This is not permission to redo the closed UI/website scope.
T-261 | M2 | P2 | Worker 2 | In Progress | 5.1 | T-106; T-241; T-242; T-243; T-099; T-262; T-100 | T-104; T-245 | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance.
T-262 | M2 | P2 | Worker 2 | Done |  | T-253; T-243 | T-245; T-247; T-261 | Consume accepted producer contracts; remaining dependencies: T-253; T-243. No private scheduler/definition authority. Source-present is not closure proof. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns.
T-148 | M2 | P3 | Worker 2 | Not Started | 1.3333 |  | T-248 | R1 route inventory and six shell contracts frozen. Contract-ready handoffs from T-196/T-197/T-198/T-199/T-200 are recorded separately in column AN. Do not wait for the entire M3 implementation or ship a simulated M3 page. | T-196; T-197; T-198; T-199; T-200; T-265; T-266
T-215 | M2 | P3 | Worker 2 | Not Started | 4 | T-092; T-214; T-232 | T-150; T-222 | T-092 + T-214.
T-222 | M2 | P3 | Worker 2 | Not Started | 4.25 | T-219; T-220; T-215; T-203; T-204 | T-150 | T-219/T-220 result contract + T-215 + T-203/T-204. Do not create a demo-only store.
T-258 | M2 | P3 | Worker 2 | Not Started | 3.4 | T-094; T-250; T-256 | T-150; T-247 | WAIT for T-256 CLOSED and its frontend-consumer handoff manifest. Then perform bounded frontend-only convergence; do not re-investigate backend genericity.
T-137 | M2 | P4 | CLOSED | Done | 0 |  | T-122; T-138; T-246 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-168 | M2 | P4 | CLOSED | Done | 0 |  | T-122; T-175; T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-169 | M2 | P4 | CLOSED | Done | 0 |  | T-175; T-184; T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-170 | M2 | P4 | CLOSED | Done | 0 |  | T-185; T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-171 | M2 | P4 | CLOSED | Done | 0 |  | T-131; T-186; T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-172 | M2 | P4 | CLOSED | Done | 0 |  | T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-173 | M2 | P4 | CLOSED | Done | 0 |  | T-140; T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-174 | M2 | P4 | CLOSED | Done | 0 |  | T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-175 | M2 | P4 | CLOSED | Done | 0 | T-168; T-169 | T-187 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-176 | M2 | P4 | CLOSED | Done | 0 |  | T-140; T-187; T-191 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-177 | M2 | P4 | CLOSED | Done | 0 |  | T-146; T-147 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-178 | M2 | P4 | CLOSED | Done | 0 |  | T-143 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-179 | M2 | P4 | CLOSED | Done | 0 |  | T-138; T-223; T-228 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-180 | M2 | P4 | CLOSED | Done | 0 |  | T-138; T-223; T-228 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-181 | M2 | P4 | CLOSED | Done | 0 |  | T-138; T-223; T-228 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-182 | M2 | P4 | CLOSED | Done | 0 |  |  | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-211 | M2 | P4 | Worker 3 | Not Started | 2.5 | T-208; T-210 | T-212; T-247 | T-208 fixture + T-210 frozen contract. No production DI/persistence until consumer hand-off.
T-214 | M2 | P4 | Worker 3 | Not Started | 1.5 | T-209 | T-215; T-223; T-232; T-238; T-239; T-264 | T-209 frozen generic subject contract.
T-217 | M2 | P4 | Worker 3 | Done | 2.5 | T-208; T-216 | T-219; T-236 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-218 | M2 | P4 | Worker 3 | Done | 2 | T-208 | T-219 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-219 | M2 | P4 | Worker 3 | Done | 3.2 | T-217; T-218; T-236 | T-220; T-221; T-222; T-223 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-220 | M2 | P4 | Worker 3 | Done | 2 | T-219 | T-221; T-222; T-223 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-221 | M2 | P4 | Worker 3 | Not Started | 5.4 | T-112; T-114; T-090; T-095; T-096; T-219; T-220; T-233 |  | T-112 + T-114 + T-090 + T-095/T-096 + T-219 + T-220. If security hand-off is not green, remain on pure-kernel evidence and do not create insecure tables.
T-223 | M2 | P4 | Worker 3 | Not Started | 4.25 | T-179; T-180; T-181; T-214; T-219; T-220 | T-150 | T-179/T-180/T-181 CLOSED + T-214 + T-219/T-220. No canonical persistence dependency for September explanation.
T-234 | M2 | P4 | Worker 3 | Done | 2 | T-208; T-209 | T-212; T-235; T-236 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-236 | M2 | P4 | Worker 3 | Done | 2.6667 | T-217; T-234 | T-212; T-219 | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract.
T-237 | M2 | P4 | Worker 2 | Not Started | 4.25 | T-092; T-235 | T-164 | T-092 + T-235; can run in parallel with T-222 on separate files.
T-112 | M2 | P5 | Worker 1 | Not Started | 2.325 | T-087; T-088; T-251; T-252 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087/T-088 canonical migration authority available; establish FORCE RLS guar...
T-113 | M2 | P5 | Worker 1 | Not Started |  |  | T-122; T-200 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-114 | M2 | P5 | Worker 1 | Not Started | 0.9 | T-087; T-089; T-090; T-095; T-099 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-089/T-090 + T-095/T-099 canonical Release 1 tables available; establish t...
T-115 | M2 | P5 | Worker 1 | Not Started | 0.775 |  | T-150 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-119 | M2 | P5 | Worker 1 | Not Started | 1.8 |  | T-121; T-197; T-198; T-200 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-120 | M2 | P5 | Worker 2 | Not Started | 2 |  |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-121 | M2 | P5 | Worker 1 | Not Started |  | T-119 | T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 role catalogue/enforcement + licence authority.
T-123 | M2 | P5 | Worker 1 | Not Started |  |  | T-122; T-150 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-124 | M2 | P5 | Worker 1 | Not Started | 3.2 |  | T-150; T-199 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-125 | M2 | P5 | Worker 1 | Not Started | 3.2 | T-106; T-107 | T-150; T-247 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-126 | M2 | P5 | Worker 1 | Not Started | 0.9 |  | T-150 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-150 | M2 | P5 | Worker 1 | Not Started | 4.08 | T-115; T-123; T-124; T-125; T-126; T-205; T-207; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-250; T-251; T-252; T-253; T-254; T-255; T-256; T-257; T-258; T-259 |  | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-192 + T-148 exact route/shell inventory + T-194 API-alias retirement + all ...
T-227 | M2 | P5 | Worker 1 | Not Started | 2.25 | T-213; T-259 | T-150 | Prepare before installation; can start after customer data assessment T-213.
T-255 | M2 | P5 | Worker 3 | Not Started | 1.2 | T-205; T-250 | T-150 | Run after T-106 or on a disjoint tooling-only lane; no runtime feature mutation.
T-257 | M2 | P5 | Worker 2 | Not Started | 2.55 | T-205; T-250; T-259 | T-150; T-248 | Run on frontend test/config/report files only after current authoring lane reaches a clean handoff; no product feature scope.
T-110 | M3 | P1 | Worker 1 | Not Started |  | T-108; T-109 | T-249 | Consume accepted producer contracts; remaining dependencies: T-108; T-109. No private scheduler/definition authority. Source-present is not closure proof.
T-122 | M3 | P1 | Worker 1 | Not Started | 3.2 | T-106; T-107; T-112; T-113; T-114; T-117; T-137; T-168; T-123 | T-141; T-185; T-192 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 + T-107 + T-112 + T-113 + T-114 + T-117; T-137/T-168 runtime contracts ...
T-151 | M3 | P1 | Worker 1 | Not Started | 7.2 |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-152 | M3 | P1 | Worker 1 | Not Started | 7.2 |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-153 | M3 | P1 | Worker 1 | Not Started | 7.2 | T-224; T-225; T-226; T-254 | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-154 | M3 | P1 | Worker 1 | Not Started | 7.2 |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-155 | M3 | P1 | Worker 3 | Not Started |  |  |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + site hardware
T-159 | M3 | P1 | Worker 3 | Not Started |  |  | T-249 | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + site hardware
T-160 | M3 | P1 | Worker 1 | Not Started | 7.2 |  | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-163 | M3 | P1 | Worker 1 | Not Started | 7.2 |  | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-116 | M3 | P2 | Worker 1 | Not Started |  | T-256 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-117 | M3 | P2 | Worker 1 | Not Started | 0.9 |  | T-122; T-194 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order
T-127 | M3 | P2 | Worker 2 | Not Started | 4.08 | T-196; T-197; T-198; T-199; T-200; T-121 | T-194 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: All Release 1 canonical-core/user-visible owners complete, including T-196/T-197/T-...
T-149 | M3 | P2 | Worker 2 | Not Started | 1 |  |  | M1 continuity frozen
T-161 | M3 | P2 | Worker 1 | Not Started | 7.2 |  | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-162 | M3 | P2 | Worker 1 | Not Started | 7.2 |  | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-194 | M3 | P2 | Worker 1 | Not Started | 0.9 | T-117; T-127 |  | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-117 + T-127
T-196 | M3 | P2 | Worker 2 | Not Started | 1.3333 | T-087; T-094; T-095 | T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-094 + T-095
T-197 | M3 | P2 | Worker 2 | Not Started | 2.2857 | T-119; T-198 | T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 + T-198
T-198 | M3 | P2 | Worker 2 | Not Started | 2.7429 | T-112; T-114; T-119 | T-127; T-197; T-199 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-112 + T-114 + T-119
T-199 | M3 | P2 | Worker 2 | Not Started | 2.7429 | T-124; T-198 | T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-124 + T-198
T-200 | M3 | P2 | Worker 2 | Not Started | 2.2857 | T-113; T-119; T-216 | T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-113 + T-119
T-156 | M3 | P3 | Worker 2 | Not Started | 7.2 |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-166 | M3 | P3 | Worker 2 | Not Started | 7.2 |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-228 | M3 | P3 | Worker 3 | Not Started | 3.2 | T-090; T-092; T-134; T-179; T-180; T-181 | T-229; T-248 | After September customer RC; T-090/T-092 + T-134 + T-179..181.
T-229 | M3 | P3 | Worker 3 | Not Started | 6.1714 | T-228; T-134 | T-230 | T-228 + T-134 + stable Page Builder contract; coordinate UI consumption with Worker 2.
T-230 | M3 | P3 | Worker 3 | Not Started | 5.1 | T-229; T-112; T-114 | T-249 | T-229 + canonical definition/evidence persistence + T-112/T-114.
T-248 | M3 | P3 | Worker 2 | Not Started |  | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257; T-267 | T-249; T-263 | After M2 Release 1 and InsightBoard authoring base
T-263 | M3 | P3 | Worker 2 | Not Started |  | T-106; T-248 | T-249 | Consume accepted producer contracts; remaining dependencies: T-106; T-248. No private scheduler/definition authority. Source-present is not closure proof.
T-128 | M3 | P4 | Worker 3 | Not Started | 1.5 | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114; T-231; T-210 | T-129; T-130; T-131; T-135; T-146; T-147; T-184; T-186 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-087..T-105 + T-112 + T-114 security/tenant hand-off. Outcome semantics from...
T-129 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-128; T-183; T-112; T-114 | T-134; T-135; T-146; T-147; T-186; T-188 | T-128 + T-183 + T-112 + T-114.
T-130 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-128; T-183; T-112; T-114 | T-134; T-135; T-139; T-188; T-191; T-193; T-246 | T-128 + T-183 + T-112 + T-114.
T-131 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-086; T-128; T-171 | T-132; T-133; T-136; T-142; T-240 | T-086 + T-128 + T-171
T-132 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-131 | T-133; T-136; T-142; T-240 | T-131
T-133 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-131; T-132; T-183 | T-134; T-136; T-240 | T-131 + T-132 + T-183
T-134 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-090; T-095; T-096; T-129; T-130; T-133; T-186; T-139 | T-138; T-228; T-229 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 definition authority + T-095/T-096 relationship resolver + available ca...
T-135 | M3 | P4 | Worker 3 | Not Started | 1.9375 | T-112; T-114; T-128; T-129; T-130; T-183 | T-184; T-185; T-186; T-187 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-112 + T-114 + current Release 2 persistence tables (including T-128/T-129/T-130/T...
T-136 | M3 | P4 | Worker 3 | Not Started | 1.5 | T-131; T-132; T-133; T-109 |  | T-109 + T-131..T-133
T-138 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-179; T-180; T-181; T-137; T-134; T-188 |  | T-137 + T-179..T-181 + T-134 + T-188
T-139 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-130; T-187; T-231 | T-134; T-140; T-141; T-142; T-189; T-193 | T-130 + T-187
T-140 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-139; T-173; T-176 | T-142; T-189 | T-139 + T-173/T-176
T-141 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-107; T-122; T-139; T-187 | T-189 | T-107 + T-122 + T-139 + T-187
T-142 | M3 | P4 | Worker 3 | Not Started | 1.2 | T-131; T-132; T-139; T-140 | T-143; T-189; T-190 | T-131/T-132 + T-139/T-140
T-143 | M3 | P4 | Worker 3 | Not Started | 1.2 | T-178; T-142 | T-144; T-189; T-190 | T-178 + T-142
T-144 | M3 | P4 | Worker 3 | Not Started | 1.2 | T-143 | T-145; T-190 | T-143
T-145 | M3 | P4 | Worker 3 | Not Started |  | T-144 | T-190; T-193 | T-144
T-146 | M3 | P4 | Worker 3 | Not Started |  | T-147; T-177; T-128; T-129 |  | T-147 COMPLETE + T-177 + T-128/T-129; M1 presentation continuity frozen.
T-147 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-090; T-128; T-129; T-177 | T-146 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 canonical SM-06 binding + T-128/T-129 + T-177; complete BEFORE T-146 fi...
T-157 | M3 | P4 | Worker 3 | Not Started | 4.32 |  |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + customer data window
T-158 | M3 | P4 | Worker 3 | Not Started | 4.32 |  |  | WAIT for deployed Release 1 + real customer/site evidence. Release 2 accepted + customer data window
T-164 | M3 | P4 | Worker 1 | Not Started | 7.2 | T-237; T-235 | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-165 | M3 | P4 | Worker 1 | Not Started |  |  |  | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-183 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114 | T-129; T-130; T-133; T-135; T-184; T-185; T-186; T-187; T-192 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-089..T-105 canonical definition/relationship authority + T-112 + T-114 secu...
T-184 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-128; T-169; T-183; T-112; T-114; T-135 | T-187; T-192 | T-128 + T-169 + T-183 + T-112/T-114/T-135 security ratchet.
T-185 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-170; T-183; T-122; T-112; T-114; T-135 | T-187; T-192 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-170 + T-183 + T-122 final object-storage/container path + T-112/T-114/T-135...
T-186 | M3 | P4 | Worker 3 | Not Started |  | T-171; T-183; T-128; T-129; T-195; T-135 | T-134; T-187; T-188; T-192 | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-171 + T-183 + T-128/T-129 + T-195 canonical readiness thresholds + T-135 se...
T-187 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-168; T-169; T-170; T-171; T-172; T-173; T-174; T-175; T-176; T-183; T-184; T-185; T-186; T-107; T-109; T-112; T-114; T-135; T-195 | T-139; T-141; T-191; T-192; T-193; T-246 | T-107 + T-109 + T-168..T-176 + T-183..T-186 + T-112/T-114/T-135 + T-195.
T-188 | M3 | P4 | Worker 3 | Not Started | 1.6667 | T-129; T-130; T-186; T-195 | T-138; T-192 | T-129 + T-130 + T-186 + T-195 + M1 continuity snapshots.
T-189 | M3 | P4 | Worker 3 | Not Started | 2 | T-139; T-140; T-141; T-142; T-143 | T-192 | T-139..T-143 + M1 continuity snapshots
T-190 | M3 | P4 | Worker 3 | Not Started |  | T-142; T-143; T-144; T-145 | T-192 | T-142..T-145 + M1 continuity snapshots
T-191 | M3 | P4 | Worker 3 | Not Started | 1.8 | T-130; T-176; T-187 | T-192 | T-130 + T-176 + T-187
T-192 | M3 | P4 | Worker 3 | Not Started | 1.7 | T-183; T-184; T-185; T-186; T-187; T-188; T-189; T-190; T-191; T-107; T-122 |  | T-183..T-191 + T-107/T-122 as applicable
T-193 | M3 | P4 | Worker 3 | Not Started | 1.5 | T-130; T-187; T-139; T-145 | T-249 | T-130 + T-187 + T-139/T-145
T-195 | M3 | P4 | Worker 3 | Not Started | 1.5 | T-090; T-112; T-114 | T-186; T-187; T-188 | T-090 + T-112 + T-114
T-238 | M3 | P4 | Worker 3 | Not Started | 3.2 | T-208; T-214 | T-239; T-240 | May start after T-214 contract; does not block September demo.
T-239 | M3 | P4 | Worker 1 | Not Started | 3.4 | T-090; T-214; T-238 | T-240 | After T-090 + frozen T-214/T-238 contracts.
T-240 | M3 | P4 | Worker 3 | Not Started | 5.1 | T-131; T-132; T-133; T-238; T-239 | T-249; T-264 | After practice core + objective persistence.
T-246 | M3 | P4 | Worker 2 | Not Started | 4.7 | T-243; T-130; T-137; T-187 | T-249 | Consume accepted producer contracts; remaining dependencies: T-243; T-130; T-137; T-187. No private scheduler/definition authority. Source-present is not closure proof.
T-264 | M3 | P4 | Worker 3 | Not Started |  | T-214; T-240 | T-249 | Consume accepted producer contracts; remaining dependencies: T-214; T-240. No private scheduler/definition authority. Source-present is not closure proof.
T-167 | M3 | P5 | Worker 2 | Not Started | 7.2 |  | T-249 | WAIT for deployed Release 1 + real customer/site evidence. M3 sequence
T-249 | M3 | P5 | Worker 1 | Not Started | 6 | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110; T-267 |  | After all M3 MUST gates
T-265 | M2 | P3 | Worker 2 | Not Started |  |  | T-247; T-267 | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | T-099; T-106; T-253; T-262; T-101; T-125
T-266 | M2 | P2 | Worker 2 | Not Started |  | T-207 | T-274; T-247 | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | T-224; T-225; T-226; T-233
T-267 | M3 | P3 | Worker 2 | Not Started |  | T-265 | T-248; T-249 | Read v4.10.3 and frozen producer contracts. Contract-ready does not require producer completion; final design acceptance requires recorded walkthrough evidence. | T-248; T-263; T-264; T-196; T-197; T-198; T-199; T-200
T-268 | M2 | P2 | Worker 1 | Not Started |  | T-207 | T-269; T-270; T-271; T-274; T-275 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-269 | M2 | P2 | Worker 1 | Not Started |  | T-268 | T-270; T-274 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-270 | M2 | P2 | Worker 1 | Not Started |  | T-268; T-269; T-225; T-233; T-275 | T-226; T-274 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-271 | M2 | P2 | Worker 1 | Not Started |  | T-268; T-108 | T-274; T-247 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-272 | M2 | P2 | Worker 1 | Not Started |  | T-087; T-088; T-251; T-252; T-268 | T-273; T-274; T-226; T-247 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-273 | M2 | P2 | Worker 1 | Not Started |  | T-272; T-124 | T-274; T-247; T-150 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-274 | M2 | P2 | Worker 2 | Not Started |  | T-254; T-266; T-268; T-269; T-270; T-271; T-272; T-273; T-275 | T-247; T-150 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.
T-275 | M2 | P2 | Worker 3 | Not Started |  | T-106; T-107; T-268 | T-270; T-226; T-274 | Consume accepted v4.11.0 contracts and listed producer contracts. Source-present is not closure proof; execute named acceptance and preserve unrelated lanes.

## Prior Baseline Archive
Historical / Superseded Task Evidence — not current execution authority
Task Id | Task Name | Historical status | Hours | Evidence / Commit | Archive ruling | Column1 | Column2
T-001 | Build the six-beat Design Traceability Matrix | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-002 | Audit every presented route and control against the Chapter 3 page inventory | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-003 | Lock the presentation profile as a data profile, not a branch | Done | 4 |  | Historical baseline evidence only; not current execution authority.
T-004 | Create the M1 acceptance checklist and evidence folder | Done | 4 |  | Historical baseline evidence only; not current execution authority.
T-005 | Rebuild ppiq_presentation into scratch and diff against live | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-006 | Convert every diff finding into a seed or migration script | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-007 | Presentation Phenomena and Widget Coverage Matrix, part 1: inventory and the 36-chart blueprint | Done | 10 |  | Historical baseline evidence only; not current execution authority.
T-008 | Presentation Phenomena and Widget Coverage Matrix, part 2: map, classify, close | Done | 10 |  | Historical baseline evidence only; not current execution authority.
T-009 | Downtime two-quantity contract: final schema and domain slice | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-010 | Run the canonical semantic path end to end through the M1 compatibility boundaries | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-011 | Establish and fix the architecture test pool reliability | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-012 | Canonicalise the JourneyRail to J1 to J15 | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-013 | Three-way source reconciliation: KEEP, EXTEND or ADD | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-014 | Capture the current source-shaped donor schemas in a committed generator | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-015 | Presentation Fleet v2 target specification | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-016 | Extend the generator: defect catalogue and chemistry elements | Done | 10 |  | Historical baseline evidence only; not current execution authority.
T-017 | Extend the generator: grade specification, and shift as BEHAVIOUR | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-018 | Extend the generator: downtime two quantities and buffer posture | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-019 | Shift and crew operating-practice regimes | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-020 | Post-maintenance recovery and campaign-ageing regimes | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-021 | Equipment personality and temporal regime changes | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-022 | Merge the best existing material into one Fleet v2 truth | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-023 | Scale Fleet v2 to the target plant size | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-024 | Emit and populate the presentation canonical operational entities | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-025 | Compute and populate the presentation analysis entities with the real engines | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-026 | Phenomenon test harness: manifest schema and runner | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-027 | Populate the manifest and prove every phenomenon | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-028 | Verify the confounded correlation and the insufficient-support refusal | Done | 2 |  | Historical baseline evidence only; not current execution authority.
T-029 | Five-layer realism audit of the emulated plant | Done | 4 |  | Historical baseline evidence only; not current execution authority.
T-030 | Emit and populate the presentation staging representation, source-shaped | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-031 | Certify cross-layer consistency and retire the obsolete donor state | Done | 10 |  | Historical baseline evidence only; not current execution authority.
T-032 | Shared Authoring Shell, part 1: the shell contract and the four regions | Done | 12 |  | Historical baseline evidence only; not current execution authority.
T-033 | Shared Authoring Shell, part 2: relational block grammar on the board | Done | 12 |  | Historical baseline evidence only; not current execution authority.
T-034 | Registry-driven schema, table and attribute tree | Done | 10 |  | Historical baseline evidence only; not current execution authority.
T-035 | Compiled-SQL pane and debug log with rows and cost | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-036 | SQL mode: safe editor, run test, returned columns and the reconstructability rule | Done | 12 |  | Historical baseline evidence only; not current execution authority.
T-037 | Certify returned-column role mapping inside the S2 shell | Done | 3 |  | Historical baseline evidence only; not current execution authority.
T-038 | Add Widget and Edit Widget open the shared shell in S2 mode | Done | 12 |  | Historical baseline evidence only; not current execution authority.
T-039 | Final definition service interface with a compatibility adapter | Done | 12 |  | Historical baseline evidence only; not current execution authority.
T-040 | Authoring states, keyboard path, RTL and error wording | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-041 | D2 Page Builder, part 1: create a page and reach the shared shell | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-042 | D2 Page Builder, part 2: arrange, save layout and publish | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-043 | Bring the workspace to the final D1 anatomy | Done | 12 |  | Historical baseline evidence only; not current execution authority.
T-044 | Certify the three operational dashboards and fix their bindings | Done | 8 | f966719f functional/data closure + 55157a98 EF/runtime migration parity | Historical baseline evidence only; not current execution authority.
T-045 | Certify the analysis and model dashboards and choose the six shown | Done | 6 | T-045-R1 closed: c56008c0 / dd9a6b04 / 39ce59ef / 283aae2c | Historical baseline evidence only; not current execution authority.
T-046 | Register the final chart grammar and implement the presentation subset | Done | 8 | 56ade951 R1 generic heatmap/combo; prior grammar fc146483 | Historical baseline evidence only; not current execution authority.
T-047 | Give the seven pages distinct visual grammars from the registered grammar | Done | 10 | 4b431463 semantic/data certification + 3cdd3a23 frontend conformance | Historical baseline evidence only; not current execution authority.
T-048 | Associative model, part 1: the alternative state and registry-driven fields | Done | 4 | b687cba4 associative selection states | Historical baseline evidence only; not current execution authority.
T-049 | Certify layout drag, resize, save, reload and responsive behaviour | Done | 4 | 16-Aug-2026 R1–R4: auth/license + canonical persistence green; current work is final test isolation/oracle convergence, not backend persistence. | F-070 — Each viewport must snapshot/restore its original layout in finally, mutate relative to its starting state, use PATCH canonical as authoritative changed state, poll DOM to converge after save/reload, and then restore baseline. No more diagnostic-only packs.
T-050 | Drill to population, provenance and evidence | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-051 | Widget failure isolation and the seven states | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-052 | Remove the hardcoded parameter default from the API client | Done | 4 |  | Historical baseline evidence only; not current execution authority.
T-053 | Reduce the demonstration navigation and add the inventory ratchet | Frozen | 4 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-054 | J4 Connections: read-only proof and load budget made visible | Frozen | 4 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-055 | J5 and J6 Dataset registry browse and watermark suggestion | Frozen | 6 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-056 | J6 Import progress visibility | Frozen | 4 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-057 | J7 Relationship model vertical slice, part 1: publish one relationship | Done | 10 |  | F-052 — T-057 must deliver the final external relationship service/API and M1-compatible persistence only. Do not claim final physical schema. T-095 owns canonical ppiq_meta.plant_relationships/_members/_paths convergence after T-089/T-090. T-058/T-059/T-060 consume the service, never table names.
T-058 | J7 Relationship model vertical slice, part 2: one resolver consumer | Done | 10 |  | F-052 — T-057 must deliver the final external relationship service/API and M1-compatible persistence only. Do not claim final physical schema. T-095 owns canonical ppiq_meta.plant_relationships/_members/_paths convergence after T-089/T-090. T-058/T-059/T-060 consume the service, never table names.
T-059 | Associative model, part 2: cross-source state through the published relationship | Frozen | 4 |  | Frozen as M1. Cross-widget selection correctness is re-owned by T-204 Customer-session associative state-machine certification. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-060 | C6 Relationship Browser, minimal read-only slice | Frozen | 4 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was In Progress. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-061 | C2 Mapping Health, part 1: the typed issue contract and the reprocess API | Frozen | 6 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-062 | C2 Mapping Health, part 2: the final visible page | Frozen | 4 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-063 | C5 Genealogy: converge the legacy workbench onto the final two-state surface | Frozen | 10 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-064 | Add job_definitions.target_definition_id and the JB error codes | Done | 8 |  | F-053 — Keep T-064 mandatory for M1/J12/T7, but implement stable semantic fields through IDefinitionService/compatibility storage with no fake FK. Cover target_definition_id, target_definition_version, target_version_policy, target_parameters, executed-version history and JB01-JB04. T-106 performs canonical FK/check/trigger convergence after T-089/T-090 and adds the dependency DAG. F-061 — T-064 owns the M1 functional/public contract and compatibility semantics. T-106 owns canonical physical convergence after definition_store exists plus job_dependencies/DAG/cycle validation; it must not redesign the visible target/version contract.
T-065 | J12 Analysis authoring: converge onto D3 Analysis Toolbox in S3 mode | Frozen | 12 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was In Progress. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-066 | One visible readiness authority on Home and Analysis | Frozen | 6 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was In Progress. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-067 | Findings evidence panel, registry-driven throughout | Frozen | 8 |  | Do not plan downstream work on T-067 as Done until explicit commit/runtime evidence exists. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-068 | Retire the hardcoded outcome and grain arrays | Done | 6 |  | F-056 — T-068 must consume a stable analysis-options/outcome-registry service contract, not a physical table or temporary route. Release 1 swaps storage behind the contract. Complete T-068 before T-065 so the S3 authoring page is built registry-first instead of being rewritten immediately. F-059 — Remove hardcoded/default coil semantics. Preserve customer-declared multi-grain unit types and outcome-specific grain_code. Rename T-094 scope from 'rename canonical grain' to 'remove hardcoded canonical grain default and bind to registry/material-unit authority'. F-062 — Dependency order is T-068 -> T-065. T-065 consumes registry-driven outcome/grain options from first implementation.
T-069 | Website, part 1: the five-product information architecture | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-070 | Website, part 2: polish the presentation routes | Done | 6 |  | Historical baseline evidence only; not current execution authority.
T-071 | Build the G1 persistent assistant dock | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-072 | Page and widget context envelope | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-073 | Add the page and widget chunk family to the retrieval corpus | Done | 8 |  | Historical baseline evidence only; not current execution authority.
T-074 | Registry-typed quantity guard on assistant answers | Done | 4 |  | Historical baseline evidence only; not current execution authority.
T-075 | Citation chips, evidence strip and suggested questions | Done | 4 |  | Historical baseline evidence only; not current execution authority.
T-076 | Certified question pack and offline fallback | Frozen | 4 |  | Do not continue as M1 content. Preserve generic correctness findings only; execute them through named M2-P0/product-truth owners. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-077 | One Playwright journey covering all six beats | Frozen | 6 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-078 | Execute visual regression and accessibility on the presented routes | Frozen | 4 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-079 | Failure injection suite | Frozen | 3 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-080 | Capture the Customer Contract Continuity snapshots | Frozen | 4 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-081 | Write the screen-by-screen demonstration script | Frozen | 6 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-082 | Presentation environment preparation and clean-start verification | Frozen | 4 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-083 | Three rehearsals, hostile hands and the fallback package | Frozen | 6 |  | Frozen as M1. Reusable release acceptance is absorbed by T-202/T-203/T-204/T-205; no more presentation-only gate work. ¦ M1 programme scope frozen after the successful 21-Aug-2026 customer presentation. Prior live status was Not Started. Do not schedule this presentation-era task. Any reusable generic requirement must be owned by an M2 task.
T-084 | Emit the frozen Fleet v2 into native customer-source fixtures | Superseded | 10 |  | Removed from the current release roadmap. Generic fixture authority T-208 supersedes Fleet-v2-specific rebuild work.
T-085 | Clean-room rebuild of the Fleet v2 emulator sources from source control | Superseded | 10 |  | Removed from the current release roadmap. Generic fixture authority T-208 supersedes Fleet-v2-specific rebuild work.
T-118 | J1 to J3 commissioning built for real | SUPERSEDED / removed from active v2.20.0 | 12 |  | 08-Sep-2026 final review ruling: commissioning umbrella duplicated T-120 Users/Roles, T-121 licence, T-123 install/upgrade, T-126 runbook/UAT and T-150 final certification. No task depended on T-118, so active scope is retired without deleting historical evidence.

## Governance
Execution Governance — v2.23.0
Rule | Current authority | Rationale
Functional authority | Six full Design Chapters v4.10.3 | Current approved technical contracts
Visual authority | Integrated Chapter 3/4 visual sections and illustrated Word | Derived visual arrangements; no standalone seventh functional authority or companion file.
Execution authority | Backlog sheet v2.23.0 | Single active task truth; generated sheets derive from it
M2 | Real Day-1 bounded customer production | Correctness, source limits, cancellation, replay and isolation do not move to M3
M3 | Advanced model invocation and heavy chunk/scan mechanisms | Owner-approved T-246/T-110 placement; final target retained
Merges | T-105→T-104; T-111→T-110/T-155/T-159 | Acceptance retained, reverse references regenerated
New rows | T-262 projection declaration; T-263 reports; T-264 benchmarking | Official under owner's update instruction
Status | Done evidence preserved; source-present/newly extended work not auto-closed | No fabricated commits or runtime proof
Estimates | New rows unestimated; widened inherited estimates flagged | Known-hour totals are not delivery forecasts
Tests | Targeted suites, isolated DBs, negative controls; never silent green skips | Evidence lives with the acceptance it proves
Filename law | No task ID in implementation filenames | Task IDs allowed in backlog/commit/evidence descriptions
Compatibility | No delete-first retirement | Migrate consumers and preserve historical meaning
Source safety | Single effective load budget, stricter configured ceilings cannot be bypassed | Policy applies to incremental and one-shot reads
Dependencies | Depends On is canonical; Must Precede derived | Separate contract-ready handoffs from runtime closure
Version policy | Only meaningful authority changes increment backlog release | Small status/evidence corrections update in place
Historical sheets | v220 / verified/commit ledgers are historical evidence | They do not override active Backlog statuses
Physical database authority | Zero unknown product tables/columns on fresh certification DB | Every object has schema, family, lifecycle, owner, design clause and generated dictionary entry.
Disposable database lifecycle | CREATE DATABASE implies owner + finally DROP unless explicitly declared persistent | Prevents probe/scratch/backup debris and cross-worker shared-DB contamination.
Database naming | Forward snake_case + no customer vocabulary + no redundant ppiq_ prefix in governed schemas | Existing names are grandfathered; no mass rename without owned compatibility proof.
Authority precedence | Current Master Design / frozen Layer-B semantic rulings > current Backlog execution wording > historical task prose. | When two current documents conflict semantically, Central must rule and amend future scope; workers are not blamed for following the then-current backlog.
Closed-task regression handling | Do not broadly reopen closed tasks. A newly discovered concrete regression receives a narrow new Task ID unless the original closure evidence itself is proven false. | Prevents scope erosion and preserves auditability.
Release evidence envelope | Superseded wording: T-259 owns envelope v1; T-252/T-257 produce; T-227 owns scorecard/policy; T-150 aggregates. See rule below. | Prevents duplicated skip-count formats and keeps final release gate from redefining evidence semantics late.
Cross-worker genericity handoff | Backend runtime convergence and frontend material-surface convergence have separate owners: T-256 Worker 1, T-258 Worker 2. | Worker 1 must not repair Worker-2 frontend files; compatibility must remain green across the handoff.
Canvas output-target namespace | Canonical entity name from ICanonicalEntityCatalog; never physical relation name and never an overloaded Analysis Subject key. | Graph and SQL share one governed output identity while Analysis Subject remains a separate semantic authority.
Canvas output-target hashing | New Graph/SQL saves carry root `outputTarget` in hashed canonical content. Legacy Graph may derive from graph.targetEntity; legacy SQL missing target returns null, never fabricated. | Hash change on re-save legitimately creates a new immutable version; prior version remains untouched.
Release evidence envelope v1 | T-259 owns the small shared machine-readable envelope contract. T-252/T-257 produce it; T-227 owns scorecard/policy; T-150 aggregates. | Removes the impossible dependency where producers needed a P5 schema that did not yet exist.
Release evidence count semantics | total_count = executed_count + skipped_count; executed_count = passed_count + failed_count; skipped work is never counted as executed. | Prevents an all-skipped suite from appearing fully exercised.
Canonical projection-target eligibility | Canonical entity identity and projection-target eligibility are separate facts. Eligibility is an explicit model/type-sourced capability, not 'all mapped entities' and not schema-only. | Prevents ImportBatch/JobRunHistory/etc. from becoming Canvas/mapping targets while preserving valid reference targets outside ppiq_plant.
Schema role in target eligibility | ppiq_plant/ppiq_meta topology is a consistency/governance signal, not the sole target predicate. | ParameterDefinition/DefectCatalog are valid current targets outside ppiq_plant; ppiq_plant also contains analytical outputs.
T-256 synchronization | T-253 is a hard dependency of T-256. If Worker 1 reaches the gate first, CENTRAL assigns a disjoint lane rather than allowing duplicate target-classification work. | Correctness and single authority take precedence over keeping P1 locally wait-free.
Fresh certification DB authority | A database called ppiq_acceptance_empty is not authoritative merely by name; it must be constructed by the complete canonical migration-order authority. | Prevents catalogue/adjudication against a partial fresh build.
T-251/T-260 split | T-251 owns read-only physical truth; T-260 owns correction of the fresh certification DB builder discovered by T-251. | Avoids violating T-251's read-only lock while preventing false classification work.
Adjudication order | Do not classify the old 106/81 fresh-DB queue. Correct/rebuild first, rerun census second, adjudicate only the remaining true queue. | Avoids spending governance effort on objects stranded by an incomplete build path.
Book file boundary | Exactly 14 files in PPIQ_Definition.md | Insert new information in its existing document/worksheet home; no new top-level file for a review, acceptance, manifest, handoff or UI atlas.

## Method & Notes
Method and Notes — v2.23.0 ¦15Sep2026 evidence reconciliation
Topic | Current rule
Supersedes | Supersedes defective delivered v2.22.0; source is v2.21.0 plus task-keyed approved edit data. Historical notes remain archives.
Source package | 14-Sep repository export; design v4.10.3; current row amendments approved by owner.
T-106 boundary | Orchestration tested with registered fake executor; does not wait for T-261/T-107 closure. T-107 deepens admission, T-261 commissions Transformation execution.
T-243 / T-262 boundary | T-243 owns saved-board lifecycle and relationship publication; T-262 owns declared field-binding contract; no private shadow store.
T-104 / T-261 boundary | T-261 executes exact immutable definition; T-104 proves persisted row provenance/version stamping and absorbed T-105 replay/rollback semantics.
T-108 / T-110 boundary | M2: total-order ingestion, source limits, replay, stage delta. M3: advanced chunk receipts/parallel checkpoint/merge/scan mechanism.
Scope versus feature truth | Moving advanced implementation to M3 cannot advertise it executable in M2. Required active-path safeguards still pass release-profile proof.
UI design scope | Full target product visual inventory includes M3 surfaces. Presence of a Figma frame is not implementation evidence.
External baseline dependencies | T-032, T-035, T-036, T-057, T-064 remain historical baseline prerequisites; their original acceptance records are not regenerated here.
Content preservation | All original task columns retained. Every changed cell recorded with before/after; retired task definitions retained.
No invented date | M2 approx. one month from owner's planning checkpoint; M3 45 days later. Historical dates in logs are not new promises.
Audit package safety | The 08-Sep UltimateAudit package was generated with Mask Secrets=False and is internal engineering evidence only; external evidence must be regenerated masked.
Evidence hierarchy | Current runtime/source path + executed tests > current source trace > commit/closure > handover > backlog/design prose. Backup/archive copies never override the live path.
Evidence-envelope ownership | T-259 owns Release Evidence Envelope v1; T-252/T-257 are producers, T-227 scorecard/policy and T-150 aggregation. Supersedes old T-227 schema-ownership wording.
T-256/T-258 ownership split | T-256 is backend/API/DB-runtime only. Frontend MaterialAnalytics/routes/types are Worker-2 T-258. T-256 must preserve a bounded compatibility handoff so it does not leave the generic frontend red.
Fresh certification DB | The named fresh canonical certification database for T-251 is `ppiq_acceptance_empty`; do not invent ad-hoc fresh database names before T-252 lifecycle authority.
T-253 measured ruling | T-243 baseline closure6f65bba1 is proven by an executed10Sep ancestry report. Its later transactional relationship-publication extension remains unverified. Do not relabel the original work as merely source-present.
T-253 target identity | Persist canonical entity name. New hashed root `outputTarget` is representation-independent; graph.targetEntity remains compatibility data and must match on new graph writes.
T-253 legacy compatibility | Legacy Graph lacking root outputTarget may derive it from graph.targetEntity; legacy SQL lacking it returns null. Re-save under the new content schema creates a new immutable version.
T-253 picker | Enumerate ICanonicalEntityCatalog through a minimal existing-authoring-support read endpoint. Do not use MappingDefinitionService.AllowedTargetEntities and do not add MaterialUnit as global UA-08 vocabulary.
T-259 ruling | Option A accepted: 2h P1 Release Evidence Envelope v1 contract after T-251 and before T-252/T-257. T-227 stays P5 scorecard/policy owner.
Dirty-tree checkpoint | Unrelated Documentation/audit dirt does not mean T-243 source exists. T-253 may proceed only with clean owned product paths, strict path staging and T-244 ancestor proof; task-number preflight filename must be renamed semantically before commit.
T-148 dependency types | v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148.
T-227 ownership check | v2.20.2 already removed the accidental schema ownership from T-227. Its 6h remains because that was the original scorecard/policy task size; no funded hours were transferred out. Stale T-252/T-257 references to T-227 fields are corrected to T-259.
Projection-target predicate | Do not enumerate every mapped entity and do not use schema-only eligibility. T-253 creates one explicit model/type-sourced projection-target capability; catalog identity stays CLR canonical name.
T-251 relationship | T-251 logical-family catalogue later cross-checks the projection-target capability but does not define runtime target eligibility; T-253 can proceed independently.
T-256 dependency | T-253 is intentionally hard in T-256 Depends On. If T-253 is late, Worker 1 stops after T-252 and CENTRAL selects a disjoint lane.
T-260 trigger | T-251 runner is valid/deterministic, but its fresh reference DB exposed an incomplete builder path (EF+scripts without required topology/views).
T-260 execution | Build a disposable candidate using the canonical order first; only replace/recreate ppiq_acceptance_empty after candidate GREEN. Never mutate ppiq_app/ppiq_presentation.
T-251 resume | After T-260, rerun catalogue from scratch. The old 106 unclassified / 81 public-offender counts are diagnostic history, not classification input.
Platform allowlist | `public.__EFMigrationsHistory` is platform migration bookkeeping and may be allowlisted in T-251 after the corrected rebuild; dead assumed-pattern rules should be removed rather than preserved.
Capability standard | Product capability mapping follows PPIQ_Product_Analysis_and_Evaluation_Standard_v1.1 (10 layers, 78 capability points).
Primary mapping law | Every product task has one Primary Capability ID. Secondary IDs are used only where task acceptance genuinely advances another capability.
Task closure law | Closing mapped tasks does not make a capability 5/5. D1–D5 product evidence remains the completeness authority.
Non-capability work | Pure execution instruments may use NO-CAP — Execution Tooling; product-boundary work is labelled explicitly rather than forced into a PPIQ capability.
Summary-sheet authority | Current execution views use Backlog v2.23.0. Historical v220/Prior/Retired/previous-revision sheets preserve past states, not current truth.
Keyed write law | Task ID, never row offset, joins baseline/change-data to Backlog. Must Precede is the exact inverse of current active Depends On.
Acceptance order vs contract | M records completion prerequisites; AN records contract-only handoffs. No M3 implementation completion is hidden as an M2 contract dependency.
T-099 evidence | Final executed terminal transcript corroborates the owner-reported closure: 49/49 live,5/5 catalogue,19/19 owned;6/6 disposable DBs dropped;0survivors. GateO900=899passed+1exact inheritedDefinitionKindRED. Exact staging and one semantic commit proven. No live rerun performed in this review; no release-wideGREEN. Pasted text(20260914-134548).txt ¦ lines430-450; final gatesQ/R; COMMITca02b40ea1b69050a45cb35a3e1d64f15b1f66af; PARENT86e1b677212195f191697ecdca7e9441b3dbde33; live49/49, catalogue5/5, owned19/19; not release-wideGREEN.
T-262 state | T-262 producer contract GREEN committed86e1b677; live integration explicitly unexecuted. Current expanded acceptance remains open pending disposition; no claim that the producer lacks a SHA.
B4 monitoring owner | T-101 (Worker 2) owns UI; T-125 (Worker 1) owns operational API/metrics. T-106 owns status truth. T-247 certifies the joined path.
Backend test hygiene | T-115 owns reproduce-then-fix follow-up for T-210 fixture, historical BOM issues and inherited DefinitionKind assertion. Release DB-fixture skips remain zero.
Re-estimation | J/R hold supplied scope estimates, not measured actual time.8 entries have no accepted numeric estimate;19 additional changed-scope rows are stale. AS/AT exclude all27 from live planning sums. No remaining-hours forecast is certified.
Repair validation | After save, independently parse Backlog cells from OOXML, recompute the graph, compare derived cached/formula values, test self-edges/cycles/releases/retirements and estimate flags.
Capability links | Secondary Capability Links is generated from Backlog column AC. Regenerate membership on mapping edits; status/release cells remain keyed formulas. Validator compares every pair against Backlog.
Historical closure versus current scope | Progress is not execution readiness. Current In Progress may combine a closed baseline with an unstarted extension. Preserve both facts in Task Evidence15Sep; do not infer an active worker or release certification from the status color.

## Commit Ledger
Task ID | Phase | Worker | Commit SHA(s) / Tag | Commit Subject / Label | Commit / Closure Date | Date Basis | Evidence Confidence | Notes
T-086 | P1 | Worker 1 | 77a8ea4f | T-086: freeze the legacy regression oracle and gate generic surfaces against its vocabulary | 2026-08-25 | Terminal / closure session day | Short SHA + subject verified | Committed after exact 3-file staging; freeze gate GREEN.
T-087 | P1 | Worker 1 | e7d82f078d7dfa4c1ca4ec6e88d0dbc7e1ecd6ba |  | 2026-08-28 | Closure-session day; exact Git timestamp not recovered | SHA verified | Final three-schema closure HEAD/commit authority recovered from late-Aug closure session.
T-088 | P1 | Worker 1 | 6a62c9d6 | Establish canonical database migration authority | 2026-08-26 | Closure session day; exact Git timestamp not recovered | Short SHA + subject verified | Historical canonical migration-order / legacy archival authority.
T-089 | P1 | Worker 1 | 0fd79e5e3516cdfd0ab5a73a02e16638fd02693a |  |  | Exact day not recovered | SHA verified | Canonical Definition Store authority.
T-090 | P1 | Worker 1 | a6399d9c |  |  | Exact day not recovered | Short SHA verified | Definition-kind convergence authority.
T-091 | P1 | Worker 1 | c6d64289 |  |  | Exact day not recovered | Short SHA verified | Impact preview/export/import closure authority.
T-092 | P1 | Worker 1 | ab2962a4; 7cad36e4 |  | 2026-09-02 | Session/git-log day | Multi-commit SHAs verified | Registry authority used two commits; latest closure authority is 7cad36e4.
T-093 | P1 | Worker 1 | 4e2e0f654b93ceed2ecdfbce4d3c1768550b3079 | T-093 govern plant vocabulary as data-driven genericity debt | 2026-09-03 | Closure session day | Full SHA + subject verified | CLOSED GREEN.
T-094 | P1 | Worker 1 | 377aabdffb27d651d30537ce5228ee4afe268526; 6ab97ee2; e74ecd1c; 5a967f1b0ab45961c8b8a880bb4fdec53a783134 | Wave A part 1; Wave A part 2a; 2b/stage 1; T-094 close keyed declared-dimension cutover and genericity reconciliation | 2026-09-07 | Final closure transcript day | Final full SHA + subject verified; stage SHAs verified | Final closure is 5a967f1b... Earlier part-commits retained for forensic lookup.
T-095 | P2 | Worker 1 | 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e |  | 2026-09-07 | Confirmed baseline in 07-Sep T096 preflight; exact Git timestamp not recovered | Full SHA verified | T-095 closure is ancestral baseline for T-096/T-242 work.
T-096 | P2 | Worker 1 | de243027073fc5e492d65e9f9845255342517510 | T-096 relationship resolver consumer convergence | 2026-09-08 | Closure transcript day (logs 08Sep2026_100134) | Full SHA + subject verified | CLOSED GREEN.
T-097 | P2 | Worker 1 | 95220d1804493f8e7b80347fe3ed4de24741f9ec | T-097 relationship consumer barrier across all sixteen families | 2026-09-08 | Commit/closure session day | Full SHA + subject verified | Committed after T-096; all sixteen families guarded.
T-168 | P4 | CLOSED | 16ea041a; 94ab4e40; 723b9434; 6aef283f; ef588f0c | Python runtime; C# protocol; real C#→Python→C#; closure evidence; W3-016 CI dependency correction |  | Closed before 15-Aug handover | Multi-commit SHAs verified | Full Backend regression after dependency correction green/no skips.
T-169 | P4 | CLOSED | a887c554 | T-169 Pack 1: typed columnar artifact contract, Parquet and Arrow IPC adapters, two hashes, B-03 hook | 2026-08-13 | Terminal/session day | Short SHA + subject verified | 81 Python tests green.
T-170 | P4 | CLOSED | 5a216483 | T-170 Chunked sequence-artifact library and bounded loader | 2026-08-15 | Eight-tasks-closed-today session day | Short SHA + subject verified | 402 Python tests.
T-171 | P4 | CLOSED | 95cc019c | Capability Profiler Pack 2 |  | Closed before 15-Aug handover | Short SHA verified; subject label from handover | 24 targeted tests.
T-172 | P4 | CLOSED | d4321856 | T-172 MF-01 Process Encoder runtime behind a replaceable contract | 2026-08-15 | Eight-tasks-closed-today session day | Short SHA + subject verified | 448 Python tests.
T-173 | P4 | CLOSED | 00a14286 | T-173 MF-02 VectorSimilarityIndex with exact-Flat recall baseline | 2026-08-15 | Eight-tasks-closed-today session day | Short SHA + subject verified | 297 tests.
T-174 | P4 | CLOSED | db033796 | T-174 MF-03 novelty runtime and honest refusal semantics | 2026-08-15 | Eight-tasks-closed-today session day | Short SHA + subject verified | 340 green.
T-175 | P4 | CLOSED | 2413c6e1 | T-175 MF-04 supervised training runtime and mandatory simple baseline | 2026-08-15 | Exact terminal/session day | Short SHA + subject verified | 141 Python tests / zero skipped.
T-176 | P4 | CLOSED | 08b54b61; 0a61ccfb | T-176 Calibration, explanation stability and three-dimensional promotion kernel ¦ T-176 Pack 2: real TreeSHAP candidate behind an explanation-provider boundary | 2026-08-15 | Session day | Two short SHAs + subjects verified | Final 230 tests / zero skipped.
T-177 | P4 | CLOSED | 502f8ca3; 502e0da9; bb4c5686 | T-177 multi-commit statistical-kernel closure |  | Closed before 15-Aug handover | Three short SHAs verified | 52 targeted tests; individual Git subjects not all recovered.
T-178 | P4 | CLOSED | b8792516; b5dbf232 | T-178 Pure remediation eligibility and can_accept decision kernel ¦ T-178 corrective: canonical remediation precedence totalisation | 2026-08-16 | Corrective verified in 16-Aug git log/session | Two short SHAs + subjects verified | Base + corrective; 503 tests after corrective.
T-179 | P4 | CLOSED | d2bf1834 | T-179: deterministic Assistant tool planner | 2026-08-16 | Git-log/session day | Short SHA + subject verified | Deterministic planner.
T-180 | P4 | CLOSED | 87428c512c6d6d1ca2bf70a6a8b04aadc7a4cc3b | T-180: permission-first hybrid retrieval and deterministic evidence packer | 2026-08-16 | Terminal/session day | Full SHA + subject verified | 43 probes.
T-181 | P4 | CLOSED | 0b8a1c74 | INVALID — explicitly corrected; commit does not exist | 2026-08-16 | Correction session day | REJECTED / DO NOT USE | Authoritative T-181 = eaa82b8b45fb1fdb4b406abfbe2809c5f6fc9cd5.
T-181 | P4 | CLOSED | eaa82b8b45fb1fdb4b406abfbe2809c5f6fc9cd5 | T-181: deterministic answer verifier and Q-01..Q-11 evaluation harness | 2026-08-16 | Exact terminal/session day | Full SHA + subject verified | IMPORTANT: authoritative hash is eaa82b8b; earlier reported 0b8a1c74 was explicitly corrected as nonexistent.
T-201 | P1 | Worker 1 | BASELINE HEAD 7da9d46ed29545f1c4f4686fa82c117c08b9fc86; TAG m1-presentation-baseline-2026-08-21 | No task commit — immutable baseline tag is the closure artifact | 2026-08-24 | Executed freeze transcript day | Tag + baseline HEAD verified | T-201 changed no W1 files and required no task commit. Health smoke PASS; tag is the freeze artifact.
T-202 | P1 | Worker 2 | ad37c324 | Add persisted definition replay gate for release truth | 2026-08-25 | Terminal / session day | Short SHA + subject verified | Direct session evidence says the six T-202 files landed in ad37c324. This supersedes the earlier incorrect association to 5920bf27.
T-203 | P1 | Worker 2 | cd1a450e | Add customer route invariant gate with durable evidence | 2026-08-25 | Terminal/session day | Short SHA + subject verified | 7 files / durable route evidence.
T-204 | P1 | Worker 2 | c6491e2d |  | 2026-08-31 | Post-close HEAD day; exact task-commit mapping not independently proven | Closure HEAD only | Use as closure-state anchor, not as an independently verified task commit subject.
T-205 | P1 | Worker 2 | b7fcc890 | Gate the frontend suite on deterministic termination and machine-readable evidence | 2026-08-30 | Backlog + closure session day | Short SHA + subject + date verified | CLOSED GREEN; do not reopen absent gate-contract regression.
T-208 | P1 | Worker 3 | 969c767c | T-208: generic controlled validation fixture and continuous-process known answers |  | Exact day not recovered | Short SHA + subject verified | Commit also carried already-staged T-206/T-207 files per session record.
T-209 | P1 | Worker 3 | f2bafdb4 |  | 2026-08-25 | Task closure session day | Short SHA verified | Analysis Subject + Grain contract/kernel.
T-210 | P1 | Worker 1 | 92a655e1ddc4becedbaf89a3db96dc0d0f1eaf94 |  | 2026-09-01 | Executed closure transcript day | Full SHA verified; Git subject not recovered | T-210 CLOSED GREEN; 7 owned paths, 15/15 acceptance, fresh 102-script replay, 0 introduced regression failures.
T-213 | P2 | Worker 2 | 2748c7fba8a5c4763bc19112ce57e484cea5b9bb |  | 2026-08-31 | Closure transcript day | Full SHA verified | 18-file exact owned commit; CLOSED GREEN.
T-216 | P1 | Worker 3 | ea9103fd | Establish source time authority for plant timestamps | 2026-08-25 | Terminal / closure session day | Short SHA + subject verified | T-216 CLOSED; 30/30 T-216, 14/14 T-208, 19/19 genericity.
T-231 | P1 | Worker 1 | c930af079502aa1660ef2bd5c50756d3fc3cf8f3 | Persist-T231-canonical-analysis-subject-grain-authority |  | Exact day not recovered | Full SHA + subject verified | Canonical Analysis Subject/Grain persistence authority.
T-241 | P2 | Worker 2 | eb7fb2ab |  |  | Exact day not recovered | Short SHA verified | Canvas executable block contract prerequisite.
T-242 | P2 | Worker 2 | b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 | T-242 Stage 1: extend Canvas executable vocabulary; exhaustive serialisation ¦ T-242 Stage 2: deterministic block algebra and the boolean port type ¦ T-242 close governed aggregate and window block contracts | 2026-09-08 | Final closure state as of 08-Sep; stage 2 explicitly seen 07-Sep | Final full SHA + staged subjects verified | Final closure = aa57a503...
T-244 | P2 | Worker 2 | 4d32c6b10b4605aeb6e0705ad03537d563125652 | T-244 close canonical Canvas lifecycle and selection model | 2026-09-04 | Closure authority known by 04-Sep; exact Git timestamp not recovered | Full SHA + subject verified | CLOSED; parent of T-094 Wave A part 1.
T-250 | P1 | Worker 2 | 6615481b | Converge frontend journey and design-system truth | 2026-08-30 | Terminal/session day | Short SHA + subject verified | CLOSED.
T-099 | P2 | Worker 1 | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af | CLOSED GREEN / COMMITTED (owner-reported task closure) | 2026-09-14 — report received; exact Git timestamp not supplied | Owner message / final runner summary | Owner-reported measured closure; not independently executed in this repair | Parent 86e1b677212195f191697ecdca7e9441b3dbde33. Owner-provided final runner report in this conversation, received 14-Sep-2026; not independently rerun or verified against a live Git checkout here. Live acceptance 49/49; catalogue 5/5; owned contract 19/19; cleanup 6/6, survivors 0. Gate O: 900 = 899 passed + 1 exact inherited DefinitionKind RED; 900 unique testId and executionId. Exact staging/byte boundary passed; cleanup before one semantic commit. Task closure GREEN, not release-wide GREEN; canonical replay limitations remain separately tracked.
T-106 | P2 | Worker 3 | 8b3eb5c89352a2779d87f9205700f19e7c9b3e25; a5451dbaf6b55183fe65e2c626c49fdef85bd986 | Canonical jobs: target/version, scheduling, dependencies, cancellation and outcome truth |  | Exact Git timestamp not recovered; dated source is observation evidence. | Source-bound terminal/central/ancestry evidence; not a live repository rerun. | Original corrective run returned GREEN with22 corrective,26 foundation,84 target-regression and15 architecture tests in24 owned paths;CENTRAL freeze after review. Later v2.22 schedule/cancel/freshness/outcome-truth scope is not closed by a10Sep run. Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review.
T-243 | P2 | Worker 2 | 6f65bba1 | Canvas persistence, immutable versioning and reopen/edit round-trip |  | Exact Git timestamp not recovered; source document date is evidence date, not commit time. | Executed transcript/closure excerpt; no live Git verification in this review. | Executed ancestry proves the original board/history/reopen closure. Later v2.22 transactional relationship publication remains a separate outstanding acceptance slice. Do not reimplement the saved-board baseline. Exact full SHA/date not recovered. Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
T-254 | P2 | Worker 2 | f8a35725c9b0d7fb5a0515c0103a72807a704a97 | Customer-facing connector capability truth convergence |  | Exact Git timestamp not recovered; source document date is evidence date, not commit time. | Executed transcript/closure excerpt; no live Git verification in this review. | Original customer-facing connector convergence closed in 5 paths. Website typecheck not independently re-claimed in handover, not RED. v2.22 backend-provider-list extension has no new completion evidence; certify that delta only. Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
T-262 | P2 | Worker 2 | 86e1b677212195f191697ecdca7e9441b3dbde33 | Governed projection declaration and canonical field-binding contract |  | Exact Git timestamp not recovered; source document date is evidence date, not commit time. | Executed transcript/closure excerpt; no live Git verification in this review. | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
T-251 | P1 | Worker 1 | 7ba31f96f3810bdac734bd1850275a601503d34d | Physical database catalogue, naming authority and zero-unknown schema dictionary |  | Exact Git timestamp not recovered; dated source is observation evidence. | Source-bound terminal/central/ancestry evidence; not a live repository rerun. | Original catalogue closure explicitly frozen by CENTRAL. Retain Done; later catalogue/build changes do not retroactively erase this producer closure. Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes.
T-256 | P1 | Worker 1 | 36de9370 | Runtime genericity and three-schema consumer convergence |  | Exact Git timestamp not recovered; dated source is observation evidence. | Source-bound terminal/central/ancestry evidence; not a live repository rerun. | Inherited accepted Done state retained. T-262's terminal summary identifies parent36de9370 as T-256. This corroborates a commit anchor, not a rerun of T-256 gates. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.

## Backlog Change Log
Historical revisions through v2.21.0 — see Revision Changes v222 for current applied changes
Action | Task | Release/Phase | Owner | Hours Δ | Ruling | Why | Downstream
ADD | T-253 | M2/P2 | Worker 2 | +6 | Shared authoring generic output-target authority | Closed genericity tasks did not own the new hardcoded Canvas/SQL target regression. | Precedes T-243/T-245/T-247/T-150
ADD | T-254 | M2/P2 | Worker 2 | +6 | Connector/customer capability truth convergence | Frontend/website contain a second capability truth after T-207 closure. | Precedes T-247/T-150/T-153
ADD | T-255 | M2/P5 | Worker 3 | +8 | Repository authority + audit-truth hygiene ratchet | Root/transient/audit self-reference/blank-line findings have no safe current owner. | Precedes T-150/T-249
ADD | T-256 | M2/P1 | Worker 1 | +12 | Runtime genericity + three-schema consumer convergence | T-251 is read-only catalogue scope and cannot itself mutate 64 public/runtime/material residues. | After T-251/T-252; precedes T-247/T-150/T-116
ADD | T-257 | M2/P5 | Worker 2 | +6 | Frontend execution-truth and skip-zero gate | Real --list enumeration and release-profile skip truth are outside closed T-205/T-250. | Precedes T-150/T-248
RETIRE | T-118 | M2/P5 | Worker 1 | -12 | Remove duplicate commissioning umbrella from active authority | Install/licence/users/runbook are already uniquely owned by T-123/T-121/T-120/T-126; T-150 is final gate; no dependency references T-118. | Archived, not deleted from history
PROMOTE | T-252 | M2 P5 → P1 | Worker 1 | 0 | Disposable DB lifecycle becomes foundation | Current certification fixtures can touch/assume shared databases; downstream evidence cannot be trusted until isolated. | Worker-1 P1: T-251 → T-252 → T-256
STATUS | T-245 | M2/P2 | Worker 2 | 0 | In Progress → Not Started / QUEUED | T-243 is open and T-245 also consumes T-106 job target/executor authority. | Start only after T-243 + T-106
AMEND | T-106 | M2/P2 | Worker 3 | +4 | Add executor capability registry to target/version/DAG | Current RunNow central switch exposes unsupported late failures. | Unblocks T-245
AMEND | T-107 | M2/P2 | Worker 3 | +4 | Add bounded parallel worker pools | Current import queue is serial and no runtime concurrency primitive is present. | Feeds T-125 / Release-1 job plane
AMEND | T-112 | M2/P5 | Worker 1 | 0 | Real two-tenant RLS proof | Vacuous Assert.True(true) cannot count as evidence. | Depends T-251/T-252
AMEND | T-113 | M2/P5 | Worker 1 | 0 | MFA/config/dead-knob hardening | PPIQ_RUN_E2E is dead; prod MFA minimum must be explicit. | T-150 security gate
AMEND | T-119 | M2/P5 | Worker 1 | 0 | Converge existing formal role catalogue | Model exists; mapping/surface silently collapses/refuses poorly. | T-120/T-121
AMEND | T-121 | M2/P5 | Worker 1 | +4 | Vendor-held licence trust root | Customer DB must verify, not mint, production licences; encryption naming must be truthful. | T-150 / CEO persona
AMEND | T-123 | M2/P5 | Worker 1 | +2 | Non-root Release-1 runtime + profile-only host config | Current Docker/runtime defaults are not yet enterprise-hard. | T-150
AMEND | T-125 | M2/P5 | Worker 1 | +2 | Canonical health + mandatory job correlation + queue metrics | Customer IT needs operational evidence before M3 full SLO work. | T-150/T-163
AMEND | T-223 | M2/P4 | Worker 3 | 0 | Generic Assistant tool/context convergence | Material-specific run_kpi/page/filter context are in existing Assistant tool scope. | T-138
AMEND | T-116/T-117/T-138/T-153/T-248 | M3 | Mixed | +6 (T-248) | Absorb route/client/provider/connector/BI parity findings into existing Release-2 owners | Avoid duplicate tasks where a natural owner already exists. | T-249
CORRECT | T-252 | M2/P1 | Worker 1 | 0 | Add T-251 to dependency cell | Handover and workbook must carry the same mechanical sequence. | T-251 → T-252 → T-256
CLARIFY | T-251 | M2/P1 | Worker 1 | 0 | Name fresh certification DB `ppiq_acceptance_empty` | Prevents ad-hoc fresh DB naming before T-252 lifecycle authority. | T-252 protected database list remains consistent
SPLIT | T-256/T-258 | M2/P1 + P3 | W1/W2 | +8 | Backend/frontend genericity ownership split | T-256 cannot touch Worker-2 MaterialAnalytics/pages/types; T-258 owns frontend convergence. | T-256 → T-258 → T-247/T-150
RULING | T-227 | M2/P5 | Worker 1 | 0 | Canonical evidence-envelope schema owner | Avoids duplicate skip-count artifact formats between T-252 and T-257; T-150 only aggregates. | T-252/T-257 producers → T-150 consumer
AMEND | T-253 | M2/P2 | Worker 2 | +6 | Measured canonical-content expansion | Two namespaces exist; SQL target is not hashed and cannot round-trip. Scope now includes catalog enumeration, hashed root outputTarget, compatibility read and focused cross-layer tests. | T-243
STATUS | T-243 | M2/P2 | Worker 2 | 0 | In Progress → Not Started | Measured main HEAD is T-242 and zero T-243 product-source work exists. | Starts fresh after T-253
ADD | T-259 | M2/P1 | Worker 1 | +2 | Release Evidence Envelope v1 contract | Producers T-252/T-257 cannot consume a schema owned only by later P5 T-227. | T-259 → T-252/T-257/T-227/T-150
AMEND | T-227 | M2/P5 | Worker 1 | 0 | Scorecard/policy only; consume T-259 schema | Keeps P5 acceptance content separate from P1 machine-readable contract. | T-150
P80 | New/open review tasks | M2 | Mixed | 0 | Populate missing AI Guarded Time P80 | Prevents new tasks from counting as zero in capacity views. | Release Plan / worker capacity views
HANDOFF | T-253 → T-256 | M2/P2 → P1 | W2 → W1 | 0 | AllowedTargetEntities hardcode assigned to T-256 | Worker 2 measured the 12-name list but correctly refused to absorb it into T-253. | T-256 consumes T-253 catalog authority; no duplicate enumeration.
CORRECT | T-259 | M2/P1 | Worker 1 | 0 | Split total from executed counts | Skipped cases were incorrectly counted as executed. | Envelope v1 invariants corrected
CONFIRM | T-227 | M2/P5 | Worker 1 | 0 | Scorecard/policy only | v2.20.2 already removed schema ownership; stale producer references were the remaining issue. | T-259 schema → T-227 policy
AMEND | T-253 | M2/P2 | Worker 2 | 0 | Add model-sourced projection-target eligibility predicate | All mapped canonical entities are not all legal mapping/authoring targets; schema-only also misclassifies valid/invalid entities. | T-256 consumes same predicate
RULING | T-256 | M2/P1 | Worker 1 | 0 | Keep T-253 as hard dependency | Removing it would permit duplicate or broadened target classification. | If blocked, return to CENTRAL for disjoint lane
ADD | T-260 | M2/P1 | Worker 1 | +6 | Canonical acceptance database builder convergence | T-251 proved the named fresh DB is built from an incomplete canonical path; classifying it now would be false work. | T-260 → resume T-251 → T-259
PAUSE | T-251 | M2/P1 | Worker 1 | 0 | Pause adjudication until T-260 | Catalogue machine is good; fresh reference state is not yet authoritative. | Do not classify current 106/81 queue
ADD | T-261 | M2/P2 | Worker 2 | +12 | Governed Transformation/Projection executor | Measured T-245 preflight proved binding exists but CanonicalRefresh honestly has no governed Transformation executor. | T-261 → T-245 → T-247 → T-150
TRACE | ALL | All | CENTRAL | 0 | Product Capability Traceability Standard v1.1 | Every backlog task now declares a Primary Capability point; secondary capability IDs capture real cross-capability contribution without double-counting. | Backlog → capability → D-dimension → evidence reporting
ADD | T-268 | M2/P2 | Worker 1 | UNESTIMATED | Industrial acquisition configuration and stable field authority | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-269; T-270; T-271; T-274; T-275
ADD | T-269 | M2/P2 | Worker 1 | UNESTIMATED | Declarative DataBlock/message layout decoder and source-event identity | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-270; T-274
ADD | T-270 | M2/P2 | Worker 1 | UNESTIMATED | Industrial recording policy and trigger/capture state-machine executor | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-226; T-274
ADD | T-271 | M2/P2 | Worker 1 | UNESTIMATED | Qualified relational and file acquisition convergence | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-274; T-247
ADD | T-272 | M2/P2 | Worker 1 | UNESTIMATED | Dataset-oriented Dump Store accepted-record and consumer contract | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-273; T-274; T-226; T-247
ADD | T-273 | M2/P2 | Worker 1 | UNESTIMATED | Industrial source capacity, retention and replay lifecycle control | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-274; T-247; T-150
ADD | T-274 | M2/P2 | Worker 2 | UNESTIMATED | Executable unified Industrial Integration configuration UX | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-247; T-150
ADD | T-275 | M2/P2 | Worker 3 | UNESTIMATED | Continuous acquisition Job runtime, fencing and finite microbatch lifecycle | New implementation owner required by Design v4.11.0 Industrial Integration Contract. | T-270; T-226; T-274
AMEND | T-224/T-225/T-226 | M2/P2 | Worker 3 | RE-ESTIMATE | OPC acceptance consumes v4.11.0 field/policy/job/dump contracts | Preserve original OPC transport ownership; add exact integration acceptance without reopening closed producers. | T-226 now consumes T-270/T-272/T-275
AMEND | T-266 | M2/P2 | Worker 2 | RE-ESTIMATE | Functional design gap integrated; task becomes derived visual/prototype handoff | Avoid duplicate design authority; keep runtime acceptance with implementation tasks. | Precedes T-274/T-247
CLASS | L1.8 | M2/R1 | CENTRAL | 0 | Advanced → Core | Current design makes read-only production industrial acquisition a Release-1 gate; evaluation/backlog classification converged. | T-224/T-225/T-226/T-270/T-274

## Verified Task Ledger
HISTORICAL SNAPSHOT — NOT CURRENT AUTHORITY ¦ Task ID | Release | Phase | Worker | Task Name | Nominal h | Backlog Status | Verified Status | Closed h | Remaining h | Active Scope h | Commit String | Commit Date | Depends On | Must Precede | Release Criticality | Tech-Lead Ruling
T-086 | M2 | P1 | Worker 1 | Freeze the legacy Fleet v2 controlled regression oracle | 8 | Done | Done | 8 | 0 | 0 | 77a8ea4f — T-086: freeze the legacy regression oracle and gate generic surfaces against its vocabulary | 2026-08-25 | T-201 | T-087; T-088; T-131 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-087 | M2 | P1 | Worker 1 | Physical three-schema migration | 12 | Done | Done | 12 | 0 | 0 | e7d82f078d7dfa4c1ca4ec6e88d0dbc7e1ecd6ba — subject not recovered | 2026-08-28 | T-086; T-088 | T-061; T-089; T-099; T-102; T-112; T-114; T-128; T-196; T-233 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-088 | M2 | P1 | Worker 1 | Canonical migration order and legacy script archival | 12 | Done | Done | 12 | 0 | 0 | 6a62c9d6 — Establish canonical database migration authority | 2026-08-26 | T-086 | T-087; T-089; T-112; T-128 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-089 | M2 | P1 | Worker 1 | definition_store, definition_versions and definition_dependencies | 12 | Done | Done | 12 | 0 | 0 | 0fd79e5e3516cdfd0ab5a73a02e16638fd02693a — subject not recovered |  | T-087; T-088 | T-061; T-090; T-092; T-095; T-099; T-106; T-114; T-128; T-183; T-243; T-244 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-090 | M2 | P1 | Worker 1 | Move all five definition kinds onto the store | 12 | Done | Done | 12 | 0 | 0 | a6399d9c — subject not recovered |  | T-089 | T-061; T-091; T-092; T-095; T-099; T-104; T-106; T-114; T-128; T-134; T-147; T-183; T-195; T-210; T-221; T-228; T-231; T-232; T-233; T-235; T-239; T-243; T-244 | Release 1 MUST | CENTRAL 30-Aug-2026: canonical definition convergence remains full scope. Deliver the standard executable PowerShell pack; no Task-ID-less changes.
T-091 | M2 | P1 | Worker 1 | Impact preview, export and import | 12 | Done | Done | 12 | 0 | 0 | c6d64289 — subject not recovered |  | T-090 | T-128; T-183 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-092 | M2 | P1 | Worker 1 | Registry authority: dimensions and measures as rows | 12 | Done | Done | 12 | 0 | 0 | ab2962a4; 7cad36e4 — registry authority closure commits | 2026-09-02 | T-089; T-090; T-210; T-231 | T-093; T-094; T-128; T-183; T-212; T-215; T-228; T-237; T-247 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-093 | M2 | P1 | Worker 1 | Plant-vocabulary sweep, part 1: build the term list and the architecture test | 6 | Done | Done | 6 | 0 | 0 | 4e2e0f654b93ceed2ecdfbce4d3c1768550b3079 — T-093 govern plant vocabulary as data-driven genericity debt | 2026-09-03 | T-092; T-206 | T-094; T-128; T-183 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-094 | M2 | P1 | Worker 1 | Plant-vocabulary sweep, part 2: remove hardcoded universal grain and industry vocabulary | 24 | Done | Done | 24 | 0 | 0 | 377aabdffb27d651d30537ce5228ee4afe268526; 6ab97ee2; e74ecd1c; 5a967f1b0ab45961c8b8a880bb4fdec53a783134 — final: T-094 close keyed declared-dimension cutover and genericity reconciliation | 2026-09-07 | T-092; T-093; T-209 | T-095; T-128; T-183; T-196 | Release 1 MUST | CENTRAL 04-Sep-2026: T-094 remains open. Scope is formally amended from one wire to both declared-dimension execution surfaces. No new task is created while T-094 is open; after closure any new surface requires a new Task ID.
T-201 | M2 | P1 | Worker 1 | Freeze the successful M1 presentation baseline and transfer programme authority to M2 | 4 | Done | Done | 4 | 0 | 0 | BASELINE HEAD 7da9d46ed29545f1c4f4686fa82c117c08b9fc86; TAG m1-presentation-baseline-2026-08-21 — no task commit; tag is closure artifact | 2026-08-24 |  | T-086; T-202; T-203; T-204; T-205; T-206; T-207; T-208; T-213; T-241 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-202 | M2 | P1 | Worker 2 | Persisted page/widget definition replay gate | 10 | Done | Done | 10 | 0 | 0 | ad37c324 — Add persisted definition replay gate for release truth | 2026-08-25 | T-201 | T-150; T-212 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-203 | M2 | P1 | Worker 2 | Customer-route network, console and widget-state invariant | 10 | Done | Done | 10 | 0 | 0 | cd1a450e — Add customer route invariant gate with durable evidence | 2026-08-25 | T-201 | T-150; T-222 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-204 | M2 | P1 | Worker 2 | Associative cross-filter state-machine certification | 10 | Done | Done | 10 | 0 | 0 | c6491e2d — closure-state HEAD; exact task commit subject not independently recovered | 2026-08-31 | T-201 | T-150; T-222 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-205 | M2 | P1 | Worker 2 | Frontend global suite termination and machine-readable gate | 8 | Done | Done | 8 | 0 | 0 | b7fcc890 — Gate the frontend suite on deterministic termination and machine-readable evidence | 2026-08-30 | T-201 | T-150; T-250 | Release 1 MUST | CENTRAL 30-Aug-2026: T-205 CLOSED GREEN at b7fcc890. The gate correctly reports suite truth; bounded corrections are a separate explicit task.
T-206 | M2 | P1 | Worker 3 | Scope-aware genericity architecture gate | 8 | Done | Done | 8 | 0 | 0 | Not recovered from reviewed sessions |  | T-201 | T-093; T-150; T-213 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-208 | M2 | P1 | Worker 3 | Generic controlled validation fixture authority and continuous-process known-answer pack | 10 | Done | Done | 10 | 0 | 0 | 969c767c — T-208: generic controlled validation fixture and continuous-process known answers |  | T-201 | T-150; T-209; T-211; T-216; T-217; T-218; T-234; T-238 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-209 | M2 | P1 | Worker 3 | Analysis Subject and Grain contract + schema-independent resolution kernel | 6 | Done | Done | 6 | 0 | 0 | f2bafdb4 — subject not recovered | 2026-08-25 | T-208 | T-094; T-210; T-214; T-231; T-234 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-210 | M2 | P1 | Worker 1 | Canonical signal and aggregation semantics authority | 12 | Done | Done | 12 | 0 | 0 | 92a655e1ddc4becedbaf89a3db96dc0d0f1eaf94 — subject not recovered | 2026-09-01 | T-090; T-209 | T-092; T-128; T-211; T-212; T-242 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-216 | M2 | P1 | Worker 3 | Source Time Authority contract and timestamp-semantics kernel | 5 | Done | Done | 5 | 0 | 0 | ea9103fd — Establish source time authority for plant timestamps | 2026-08-25 | T-208 | T-200; T-217; T-233 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-231 | M2 | P1 | Worker 1 | Persist Analysis Subject and Grain authority in canonical definition store | 6 | Done | Done | 6 | 0 | 0 | c930af079502aa1660ef2bd5c50756d3fc3cf8f3 — Persist-T231-canonical-analysis-subject-grain-authority |  | T-090; T-209 | T-092; T-128; T-139; T-232; T-235 | Release 1 MUST | M2 P1 — Product Foundation & Release Truth. Release 1 is genuine early production / first-week customer work.
T-095 | M2 | P2 | Worker 1 | Relationship members, cardinality, grain conversion and preferred paths | 12 | Done | Done | 12 | 0 | 0 | 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e — subject not recovered | 2026-09-07 | T-057; T-089; T-090; T-094 | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-114; T-128; T-134; T-183; T-196; T-221 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-096 | M2 | P2 | Worker 1 | Path resolver, part 1: resolver core and the first eight consumers | 8 | Done | Done | 8 | 0 | 0 | de243027073fc5e492d65e9f9845255342517510 — T-096 relationship resolver consumer convergence | 2026-09-08 | T-095 | T-097; T-098; T-107; T-109; T-128; T-134; T-183; T-221 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-097 | M2 | P2 | Worker 1 | Path resolver, part 2: the remaining eight consumers and the regression suite | 6 | Done | Done | 6 | 0 | 0 | 95220d1804493f8e7b80347fe3ed4de24741f9ec — T-097 relationship consumer barrier across all sixteen families | 2026-09-08 | T-096 | T-098; T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-098 | M2 | P2 | Worker 2 | Relationship Browser page and path evidence | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-095; T-096; T-097 | T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-099 | M2 | P2 | Worker 1 | Quarantine, part 1: the table, the reprocess API and the first eight PV classes | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-087; T-089; T-090 | T-061; T-100; T-101; T-104; T-107; T-109; T-114; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-100 | M2 | P2 | Worker 1 | Quarantine, part 2: the remaining seven PV classes and per-class tests | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-099 | T-101; T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-101 | M2 | P2 | Worker 2 | Quarantine retry, reprocess and Mapping Health completion | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-099; T-100 | T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-102 | M2 | P2 | Worker 1 | Identity resolution across sources | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-087; T-095 | T-103; T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-103 | M2 | P2 | Worker 1 | Genealogy bidirectional walk hardening and weight proof | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-095; T-102 | T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-104 | M2 | P2 | Worker 1 | Projection through the versioned mapping, with version stamping | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-090; T-095; T-099 | T-105; T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-105 | M2 | P2 | Worker 1 | Idempotent reprojection and mapping-version regression | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-104 | T-107; T-109; T-128; T-183 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-106 | M2 | P2 | Worker 3 | Job target/version policy, executor capability registry and dependency DAG | 16 | Not Started | Not Started | 0 | 16 | 0 |  |  | T-064; T-089; T-090 | T-107; T-122; T-245; T-125 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-107 | M2 | P2 | Worker 3 | Dual-predicate admission, bounded worker pools and the three ML execution lanes | 16 | Not Started | Not Started | 0 | 16 | 0 |  |  | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-105; T-106 | T-122; T-141; T-187; T-192; T-125 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-108 | M2 | P2 | Worker 1 | stage_watermarks and delta-scoped projection | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  |  | T-109 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-109 | M2 | P2 | Worker 3 | Delta-scoped feature refresh and analysis, with telemetry and ML hand-off | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-105; T-108 | T-136; T-187 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-110 | M2 | P2 | Worker 1 | Chunk manifests, checkpoint, resume and deterministic merge | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  |  |  | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-111 | M2 | P2 | Worker 1 | Scan budget and the Scan Amplification metric | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  |  |  | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-207 | M2 | P2 | Worker 1 | Connector capability truth: stop advertising unimplemented browse/read/subscription | 6 | Done | Done | 6 | 0 | 0 | Not recovered from reviewed sessions |  | T-201 | T-150; T-224 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-212 | M2 | P2 | Worker 2 | Integrate aggregation semantics into Layer-A widget/query execution | 10 | Not Started | Not Started | 0 | 10 | 0 |  |  | T-202; T-210; T-211; T-092; T-234; T-235; T-236 |  | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-213 | M2 | P2 | Worker 2 | Customer Data Intake and Capability Assessment authority | 8 | Done | Done | 8 | 0 | 0 | 2748c7fba8a5c4763bc19112ce57e484cea5b9bb — subject not recovered | 2026-08-31 | T-201; T-206 | T-227; T-247 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-224 | M2 | P2 | Worker 1 | Production OPC UA edge runtime: endpoint security, certificates and session lifecycle | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-207 | T-153; T-225 | Release 1 MUST | CENTRAL 04-Sep-2026: remove the contradictory 'after 30-Sep demo' gate. M2 is genuine early production and its P2 outcome includes real read-only OPC UA runtime.
T-225 | M2 | P2 | Worker 1 | Production OPC UA edge runtime: browse, tag registration, subscription and monitored items | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-224 | T-153; T-226 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-226 | M2 | P2 | Worker 1 | Production OPC UA edge runtime: quality/timestamps, recovery and spool-to-canonical proof | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-225; T-233 | T-153 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-232 | M2 | P2 | Worker 1 | Persist Performance Reference authority and projections | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-090; T-231; T-214 | T-215 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-233 | M2 | P2 | Worker 1 | Persist Source Time Authority and observation timestamp provenance | 5 | Not Started | Not Started | 0 | 5 | 0 |  |  | T-087; T-090; T-216 | T-221; T-226 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-235 | M2 | P2 | Worker 1 | Persist transition/stabilisation authority and regime context | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-090; T-231; T-234 | T-164; T-212; T-237 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-241 | M2 | P2 | Worker 2 | Canvas executable block contract, typed ports and graph validation | 10 | Done | Done | 10 | 0 | 0 | eb7fb2ab — subject not recovered |  | T-032; T-201 | T-242; T-243 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-242 | M2 | P2 | Worker 2 | Canvas production block library: relational, arithmetic, logic, window and governed aggregate | 16 | Done | Done | 16 | 0 | 0 | b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 — final: T-242 close governed aggregate and window block contracts | 2026-09-08 | T-241; T-210 | T-243 | Release 1 MUST | CENTRAL 04-Sep-2026: remove 'After 30-Sep MUST lane'. A Release-1-MUST task cannot be scheduled after its own release date.
T-243 | M2 | P2 | Worker 2 | Canvas persistence, immutable versioning and reopen/edit round-trip | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-241; T-242; T-089; T-090; T-253 | T-245; T-246 | Release 1 MUST | CENTRAL v2.20.2 measured-source correction: current main has zero T-243 product-source work. Status is Not Started; begin fresh only after T-253 closes.
T-244 | M2 | P2 | Worker 2 | SQL-mode production convergence: compile, validate, bounded dry-run and definition persistence | 14 | Done | Done | 14 | 0 | 0 | 4d32c6b10b4605aeb6e0705ad03537d563125652 — T-244 close canonical Canvas lifecycle and selection model | 2026-09-04 | T-035; T-036; T-089; T-090 | T-245 | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-245 | M2 | P2 | Worker 2 | Canvas-to-job compilation, binding, run monitor and per-block evidence | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-243; T-244; T-106 |  | Release 1 MUST | CENTRAL 04-Sep-2026: remove 'After 30-Sep MUST lane'. A Release-1-MUST task cannot be scheduled after its own release date.
T-246 | M2 | P2 | Worker 2 | Canvas governed model/intelligence block invocation | 11 | Not Started | Not Started | 0 | 11 | 0 |  |  | T-243; T-130; T-137 |  | Release 1 MUST | CENTRAL 04-Sep-2026: remove 'After 30-Sep MUST lane'. A Release-1-MUST task cannot be scheduled after its own release date.
T-247 | M2 | P2 | Worker 2 | First-customer Day-1 Golden Journey and same-binary onboarding proof | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258 |  | Release 1 MUST | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work.
T-253 | M2 | P2 | Worker 2 | Shared authoring governed output-target canonical-content contract | 12 | In Progress | In Progress | 0 | 12 | 12 |  |  | T-094; T-209; T-241; T-244 | T-243; T-245; T-247; T-150 | Release 1 MUST | CENTRAL v2.20.3: canonical output identity = ICanonicalEntityCatalog CLR canonical name. Projection-target eligibility is separate and MUST use the `ICanonicalProjectionTarget` marker interface on mapped entity types; do not enumerate all mapped entities, do not use schema-only eligibility, and do not add a new string allowlist. New root outputTarget is hashed for Graph+SQL; legacy Graph derives from graph.targetEntity, legacy SQL missing target stays null; minimal catalog enumeration/read endpoint allowed; path-scoped comment-stripped guard only. T-243 remains Not Started.
T-254 | M2 | P2 | Worker 2 | Customer-facing connector capability truth convergence | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-207 | T-247; T-150; T-153 | Release 1 MUST | Narrow truth-regression task; T-207 remains closed.
T-258 | M2 | P3 | Worker 2 | Frontend material-surface genericity convergence and presentation compatibility | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-094; T-250; T-256 | T-247; T-150 | Release 1 MUST | v2.20.1 ownership split: created to prevent Worker 1 T-256 from crossing into Worker-2 frontend ownership while still closing generic-binary material residue.
T-148 | M2 | P3 | Worker 2 | Map the 108 page files onto the 40 target pages | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-196; T-197; T-198; T-199; T-200 | T-150 | Release 1 MUST | M2 P3 — Enterprise BI & Customer Experience. Release 1 is genuine early production / first-week customer work.
T-215 | M2 | P3 | Worker 2 | Reference gap, attainment and envelope measures in registry/BI | 10 | Not Started | Not Started | 0 | 10 | 0 |  |  | T-092; T-214; T-232 | T-222 | Release 1 MUST | M2 P3 — Enterprise BI & Customer Experience. Release 1 is genuine early production / first-week customer work.
T-222 | M2 | P3 | Worker 2 | D1/D4 reconciliation evidence surface and reference overlay | 10 | Not Started | Not Started | 0 | 10 | 0 |  |  | T-219; T-220; T-215; T-203; T-204 |  | Release 1 MUST | M2 P3 — Enterprise BI & Customer Experience. Release 1 is genuine early production / first-week customer work.
T-137 | M2 | P4 | CLOSED | ModelServingRuntime and model-gateway adapter, isolated from the presentation dock | 10 | Done | Done | 10 | 0 | 0 | Not recovered from reviewed sessions |  |  | T-122; T-138; T-246 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-168 | M2 | P4 | CLOSED | Versioned C#↔Python ML job protocol and isolated runtime harness | 12 | Done | Done | 12 | 0 | 0 | 16ea041a; 94ab4e40; 723b9434; 6aef283f; ef588f0c — multi-commit runtime/protocol/CI closure |  |  | T-122; T-175; T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-169 | M2 | P4 | CLOSED | Typed columnar training-artifact library and B-03 harness | 10 | Done | Done | 10 | 0 | 0 | a887c554 — T-169 Pack 1: typed columnar artifact contract, Parquet and Arrow IPC adapters, two hashes, B-03 hook | 2026-08-13 |  | T-175; T-184; T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-170 | M2 | P4 | CLOSED | Chunked sequence-artifact library and bounded loader | 10 | Done | Done | 10 | 0 | 0 | 5a216483 — T-170 Chunked sequence-artifact library and bounded loader | 2026-08-15 |  | T-185; T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-171 | M2 | P4 | CLOSED | Capability Profiler and eligibility/refusal kernel | 10 | Done | Done | 10 | 0 | 0 | 95cc019c — Capability Profiler Pack 2 |  |  | T-131; T-186; T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-172 | M2 | P4 | CLOSED | MF-01 Process Encoder runtime behind a replaceable contract | 12 | Done | Done | 12 | 0 | 0 | d4321856 — T-172 MF-01 Process Encoder runtime behind a replaceable contract | 2026-08-15 |  | T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-173 | M2 | P4 | CLOSED | MF-02 VectorSimilarityIndex with exact-Flat recall baseline | 12 | Done | Done | 12 | 0 | 0 | 00a14286 — T-173 MF-02 VectorSimilarityIndex with exact-Flat recall baseline | 2026-08-15 |  | T-140; T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-174 | M2 | P4 | CLOSED | MF-03 novelty-model runtime and honest refusal semantics | 10 | Done | Done | 10 | 0 | 0 | db033796 — T-174 MF-03 novelty runtime and honest refusal semantics | 2026-08-15 |  | T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-175 | M2 | P4 | CLOSED | MF-04 supervised-outcome training runtime and mandatory simple baseline | 12 | Done | Done | 12 | 0 | 0 | 2413c6e1 — T-175 MF-04 supervised training runtime and mandatory simple baseline | 2026-08-15 | T-168; T-169 | T-187 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-176 | M2 | P4 | CLOSED | Calibration, explanation stability and three-dimensional promotion kernel | 12 | Done | Done | 12 | 0 | 0 | 08b54b61; 0a61ccfb — Calibration/explanation stability/promotion kernel + real TreeSHAP Pack 2 | 2026-08-15 |  | T-140; T-187; T-191 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-177 | M2 | P4 | CLOSED | Production statistical-method kernel, including Numeric×Categorical | 10 | Done | Done | 10 | 0 | 0 | 502f8ca3; 502e0da9; bb4c5686 — T-177 multi-commit statistical-kernel closure |  |  | T-146; T-147 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-178 | M2 | P4 | CLOSED | Pure remediation eligibility and can_accept decision kernel | 8 | Done | Done | 8 | 0 | 0 | b8792516; b5dbf232 — remediation eligibility/can_accept kernel + corrective canonical precedence | 2026-08-16 |  | T-143 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-179 | M2 | P4 | CLOSED | Deterministic Assistant tool planner | 10 | Done | Done | 10 | 0 | 0 | d2bf1834 — T-179: deterministic Assistant tool planner | 2026-08-16 |  | T-138; T-223; T-228 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-180 | M2 | P4 | CLOSED | Permission-first hybrid retrieval and evidence packer | 12 | Done | Done | 12 | 0 | 0 | 87428c512c6d6d1ca2bf70a6a8b04aadc7a4cc3b — T-180: permission-first hybrid retrieval and deterministic evidence packer | 2026-08-16 |  | T-138; T-223; T-228 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-181 | M2 | P4 | CLOSED | Deterministic answer verifier and Q-01..Q-11 evaluation harness | 12 | Done | Done | 12 | 0 | 0 | eaa82b8b45fb1fdb4b406abfbe2809c5f6fc9cd5 — T-181: deterministic answer verifier and Q-01..Q-11 evaluation harness | 2026-08-16 |  | T-138; T-223; T-228 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-182 | M2 | P4 | CLOSED | Benchmark harness and result manifest for B-01..B-09 | 10 | Done | Done | 10 | 0 | 0 | Not recovered from reviewed sessions |  |  |  | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-211 | M2 | P4 | Worker 3 | Aggregation semantics execution kernel with continuous known answers | 10 | Not Started | Not Started | 0 | 10 | 0 |  |  | T-208; T-210 | T-212 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-214 | M2 | P4 | Worker 3 | Performance Reference contract, precedence and scoring-semantics kernel | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-209 | T-215; T-223; T-232; T-238; T-239 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-217 | M2 | P4 | Worker 3 | Temporal evidence alignment kernel | 10 | Done | Done | 10 | 0 | 0 | Not recovered from reviewed sessions |  | T-208; T-216 | T-219; T-236 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-218 | M2 | P4 | Worker 3 | Fact Evidence Authority resolution kernel | 8 | Done | Done | 8 | 0 | 0 | Not recovered from reviewed sessions |  | T-208 | T-219 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-219 | M2 | P4 | Worker 3 | Operational Evidence Reconciliation kernel and seven-state taxonomy | 12 | Done | Done | 12 | 0 | 0 | Not recovered from reviewed sessions |  | T-217; T-218; T-236 | T-220; T-221; T-222; T-223 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-220 | M2 | P4 | Worker 3 | Causal Confidence Ladder and root-cause hypothesis evaluator | 8 | Done | Done | 8 | 0 | 0 | Not recovered from reviewed sessions |  | T-219 | T-221; T-222; T-223 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-221 | M2 | P4 | Worker 3 | Canonical reconciliation persistence, evidence handles and bindable source | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-112; T-114; T-090; T-095; T-096; T-219; T-220; T-233 |  | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-223 | M2 | P4 | Worker 3 | Grounded Assistant tool for reconciliation and Performance Reference explanation | 10 | Not Started | Not Started | 0 | 10 | 0 |  |  | T-179; T-180; T-181; T-214; T-219; T-220 |  | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-234 | M2 | P4 | Worker 3 | Operational Transition and Stabilisation contract/kernel | 8 | Done | Done | 8 | 0 | 0 | Not recovered from reviewed sessions |  | T-208; T-209 | T-212; T-235; T-236 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-236 | M2 | P4 | Worker 3 | Transition-aware aggregation, statistics and reconciliation guard | 10 | Done | Done | 10 | 0 | 0 | Not recovered from reviewed sessions |  | T-217; T-234 | T-212; T-219 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-237 | M2 | P4 | Worker 2 | Operational Period Driver Decomposition exact API and evidence tool | 10 | Not Started | Not Started | 0 | 10 | 0 |  |  | T-092; T-235 | T-164 | Release 1 MUST | M2 P4 — Industrial Intelligence — Reference, Reconciliation & Assistant. Release 1 is genuine early production / first-week customer work.
T-112 | M2 | P5 | Worker 1 | Force RLS on every tenant-owned table with an architecture test | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-087; T-088; T-251; T-252 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-113 | M2 | P5 | Worker 1 | Secret and configuration hygiene | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  |  | T-122; T-200 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-114 | M2 | P5 | Worker 1 | Tenant keys, tenant-aware uniqueness and canonical namespace on new APIs | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-087; T-089; T-090; T-095; T-099 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-115 | M2 | P5 | Worker 1 | Fresh-install Rule 2 acceptance test, ephemeral | 4 | Not Started | Not Started | 0 | 4 | 0 |  |  |  |  | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-119 | M2 | P5 | Worker 1 | Eight-role catalogue convergence, one-to-one wire mapping and three enforcement layers | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  |  | T-121; T-197; T-198; T-200 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-120 | M2 | P5 | Worker 2 | Users and Roles administration surface | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  |  |  | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-121 | M2 | P5 | Worker 1 | Licence and entitlement enforcement | 16 | Not Started | Not Started | 0 | 16 | 0 |  |  | T-119 | T-127 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-123 | M2 | P5 | Worker 1 | Install package, migration runner, upgrade and rollback | 14 | Not Started | Not Started | 0 | 14 | 0 |  |  |  |  | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-124 | M2 | P5 | Worker 1 | Backup with a tested restore acceptance procedure | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  |  | T-199 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-125 | M2 | P5 | Worker 1 | Minimum monitoring, health and alerting | 14 | Not Started | Not Started | 0 | 14 | 0 |  |  | T-106; T-107 |  | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-126 | M2 | P5 | Worker 1 | Support runbook and UAT dataset and configuration import | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  |  |  | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-150 | M2 | P5 | Worker 1 | Release 1 final production gate: Day-1 workbench, BI, OPC, intelligence and hardening | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-115; T-123; T-124; T-125; T-126; T-205; T-207; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-250; T-251; T-252; T-253; T-254; T-255; T-256; T-257; T-258; T-259 |  | Release 1 MUST | CENTRAL 04-Sep-2026: T-150 release completeness is generated from Release Criticality, not inferred from transitive Depends-On. A green T-150 with any Release-1-MUST row unproven is mechanically impossible.
T-227 | M2 | P5 | Worker 1 | Release 1 production acceptance scorecard and evidence policy | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-213; T-259 | T-150 | Release 1 MUST | M2 P5 — Release Hardening & Week-1 Production Acceptance. Release 1 is genuine early production / first-week customer work.
T-250 | M2 | P1 | Worker 2 | Frontend suite truth convergence: Journey routing and design-system corrections | 6 | Done | Done | 6 | 0 | 0 | 6615481b — Converge frontend journey and design-system truth | 2026-08-30 | T-205 | T-150 | Release 1 MUST | CENTRAL 30-Aug-2026: no Task ID = no repository mutation. T-250 is the sole owner of these six findings; bounded correction only, narrow tests first, one final normal suite.
T-251 | M2 | P1 | Worker 1 | Physical database catalogue, naming authority and zero-unknown schema dictionary | 12 | In Progress | In Progress | 0 | 12 | 12 |  |  | T-087; T-088 | T-115; T-123; T-150 | Release 1 MUST | CENTRAL 04-Sep-2026: table count is not a defect; unknown authority is. This task establishes zero-unknown physical schema governance before any cleanup.
T-259 | M2 | P1 | Worker 1 | Release evidence envelope v1 machine-readable contract | 2 | Not Started | Not Started | 0 | 2 | 0 |  |  | T-251 | T-252; T-257; T-227; T-150 | Release 1 MUST | v2.20.2 Option-A ruling from Worker-1 consistency review: split schema contract ahead of producers rather than pulling full T-227 P5 scorecard into P1.
T-252 | M2 | P1 | Worker 1 | Disposable database lifecycle and integration-test database isolation | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-087; T-088; T-251; T-259 | T-150; T-256 | Release 1 MUST | CENTRAL v2.20.0 08-Sep-2026: promoted from P5 to P1. Certification DB isolation is foundational; Worker-1 sequence is T-251 → T-252 → T-256.
T-256 | M2 | P1 | Worker 1 | Runtime genericity and three-schema consumer convergence | 12 | Not Started | Not Started | 0 | 12 | 0 |  |  | T-088; T-094; T-251; T-252; T-253 | T-247; T-150; T-116; T-258 | Release 1 MUST | New P1 convergence task; closed T-093/T-094 stay closed and act as regression authorities.
T-255 | M2 | P5 | Worker 3 | Repository authority and audit-truth hygiene ratchet | 8 | Not Started | Not Started | 0 | 8 | 0 |  |  | T-205; T-250 | T-150; T-249 | Release 1 MUST | Created from merged v1/v2 Developer-persona review; source authority, not cosmetic cleanup.
T-257 | M2 | P5 | Worker 2 | Frontend execution-truth and release-profile skip-zero gate | 6 | Not Started | Not Started | 0 | 6 | 0 |  |  | T-205; T-250; T-259 | T-150; T-248 | Release 1 MUST | Created because the 08-Sep audit still has real --list enumeration signals outside the canonical blocking Jenkins stages.

## Phase Worker v220
HISTORICAL SNAPSHOT — NOT CURRENT AUTHORITY ¦ M2 v2.20.4 — Dynamic Phase × Worker Scoreboard
Phase | Worker | Scope h | Closed h | Remaining h | Active h | Progress % | Open tasks
P1 | Worker 1 | 172 | 172 | 0 | 0 | 100% | 0
P1 | Worker 2 | 44 | 44 | 0 | 0 | 100% | 0
P1 | Worker 3 | 29 | 29 | 0 | 0 | 100% | 0
P2 | Worker 1 | 137 | 32 | 105 | 8 | 23.36% | 12
P2 | Worker 2 | 148 | 60 | 88 | 24 | 40.54% | 9
P2 | Worker 3 | 38 | 0 | 38 | 16 | 0% | 3
P3 | Worker 1 | 0 | 0 | 0 | 0 | 0% | 0
P3 | Worker 2 | 36 | 0 | 36 | 0 | 0% | 4
P3 | Worker 3 | 0 | 0 | 0 | 0 | 0% | 0
P4 | Worker 1 | 0 | 0 | 0 | 0 | 0% | 0
P4 | Worker 2 | 10 | 0 | 10 | 0 | 0% | 1
P4 | Worker 3 | 94 | 56 | 38 | 0 | 59.57% | 4
P5 | Worker 1 | 128 | 0 | 128 | 0 | 0% | 12
P5 | Worker 2 | 18 | 0 | 18 | 0 | 0% | 2
P5 | Worker 3 | 8 | 0 | 8 | 0 | 0% | 1
Phase | Scope h | Closed h | Remaining h | Active h | Progress % | Open tasks | Central interpretation
P1 | 245 | 245 | 0 | 0 | 100% | 0 | T-251 → T-259 → T-252 → T-256. Physical catalogue, evidence-envelope contract, disposable certification DBs, then backend runtime genericity.
P2 | 323 | 92 | 231 | 48 | 28.48% | 24 | T-253 expanded to canonical-content contract; T-243 measured Not Started; T-245 waits for T-243 + T-106.
P3 | 36 | 0 | 36 | 0 | 0% | 4 | Release-1 enterprise BI core unchanged. Full comparative BI parity remains Release 2 / T-248.
P4 | 276 | 228 | 48 | 0 | 82.61% | 5 | No duplicate task added; T-223 absorbs Assistant genericity/context convergence.
P5 | 154 | 0 | 154 | 0 | 0% | 15 | T-118 retired; T-255/T-257 added. Security/licence/deploy/monitoring scopes sharpened.
Worker | Scope h | Closed h | Remaining h | Active h | Progress % | Open tasks
Worker 1 | 437 | 204 | 233 | 8 | 46.68% | 24
Worker 2 | 256 | 104 | 152 | 24 | 40.62% | 16
Worker 3 | 169 | 85 | 84 | 16 | 50.3% | 8

## Dashboard v220
HISTORICAL SNAPSHOT — NOT CURRENT AUTHORITY ¦ PlantProcess IQ — M2 v2.20.4 Governance Dashboard ¦ 09-Sep-2026
v2.20.4 adds T-260: correct the incomplete fresh acceptance DB builder before T-251 classification continues.
M2 Scope h |  |  | Closed h |  |  | Remaining h |  |  | Formal Progress
1034 |  |  | 565 |  |  | 469 |  |  | 54.64%
Centrally governed next sequence
Lane | Now | State | Hours | Then | Waits for | Why | Central ruling
Worker 1 | T-260 | In Progress | 6 | Resume T-251 → T-259 → T-252 | T-088 authority | Fix fresh acceptance DB build path first; do not classify old 106/81 queue. | T-251 machine is valid and remains installed.
Worker 2 | T-253 | In Progress | 12 | T-243 → T-254 | T-244 ancestry | Continue implementation, not more architecture review. | Single standard runner.
Worker 3 | T-106 | Start now | 16 | T-255 if T-107 blocked | — | Canonical job authority remains T-245 prerequisite. | No Canvas-private scheduler.
Worker 1 | T-256 | Gated | 12 | After T-252 + T-253 | T-252; T-253 | Backend convergence only after both foundations. | If blocked, CENTRAL assigns disjoint work.
Phase | Closed h | Remaining h | Active h | Progress % |  | Worker | Closed h | Remaining h | Active h | Progress %
P1 | 245 | 0 | 0 | 100% |  | Worker 1 | 204 | 233 | 8 | 46.68%
P2 | 92 | 231 | 48 | 28.48% |  | Worker 2 | 104 | 152 | 24 | 40.62%
P3 | 0 | 36 | 0 | 0% |  | Worker 3 | 85 | 84 | 16 | 50.3%
P4 | 228 | 48 | 0 | 82.61%
P5 | 0 | 154 | 0 | 0%
Metric | v2.20.1 | v2.20.2 | Change | Interpretation
M2 scope h | 1043 | 1051 | 8 | T-253 measured expansion + T-259 evidence contract; no valid closure changed.
M2 closed h | 513 | 513 | 0 | Valid closures stay frozen.
M2 remaining h | 530 | 538 | 8 | Previously hidden canonical-content/evidence-contract work is now explicit.
M2 formal progress | 49.19% | 48.81% | -0.3744% | Denominator correction only.
Active task truth | T-243 In Progress | T-253 In Progress / T-243 Not Started | Measured-source correction | Current main has no T-243 product source changes.
Remaining h | Worker 1 | Worker 2 | Worker 3 | Phase Total | Open tasks
P1 | 0 | 0 | 0 | 0 | 0
P2 | 105 | 88 | 38 | 231 | 24
P3 | 0 | 36 | 0 | 36 | 4
P4 | 0 | 10 | 38 | 48 | 5
P5 | 128 | 18 | 8 | 154 | 15
TOTAL | 233 | 152 | 84 | 469 | 48

## Capability Map v1.1
Capability Map v1.2 ↔ Backlog v2.24.0
Task mapping and closure counts only. A closed task is not D1–D5 product certification.
ID | Layer | Capability | Class | Primary tasks | Done primary | Open primary | M2 primary | M3 primary | Primary task IDs | Secondary tasks | Done secondary | Secondary task IDs | Meaning
L1.1 | L1 | Read-only connection and source access | Core | 1 | 0 | 1 | 0 | 1 | T-153 | 5 | 1 | T-108; T-213; T-247; T-265; T-266; T-268; T-271; T-274 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.2 | L1 | Dataset registration and source selection | Core | 3 | 1 | 2 | 3 | 0 | T-213; T-268; T-269 | 3 | 0 | T-101; T-247; T-265; T-274 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.3 | L1 | Incremental import into staging | Core | 2 | 0 | 2 | 2 | 0 | T-271; T-272 | 2 | 0 | T-108; T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.4 | L1 | Connector capability truth | Core | 2 | 1 | 1 | 2 | 0 | T-207; T-254 | 2 | 0 | T-153; T-266; T-268; T-271; T-274 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.5 | L1 | Acquisition provenance and source lineage | Core | 2 | 1 | 1 | 2 | 0 | T-216; T-233 | 1 | 0 | T-266; T-268; T-269; T-270; T-272 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.6 | L1 | Source schema drift and mapping-health signalling | Core | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | T-101 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.7 | L1 | Import monitoring, recovery and dead-letter visibility | Core | 0 | 0 | 0 | 0 | 0 |  | 5 | 1 | T-101; T-106; T-108; T-125; T-265; T-270; T-271; T-273; T-274; T-275 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L1.8 | L1 | Industrial edge acquisition and recording | Core | 6 | 0 | 6 | 6 | 0 | T-224; T-225; T-226; T-266; T-270; T-274 | 0 | 0 | T-275 | v4.11.0: Release-1 Core. Covers approved industrial source runtime plus stable field/layout, governed recording policy, durable bounded delivery and exact capability truth. Native PLC transport remains separately scoped.
L2.1 | L2 | Three-schema platform and placement law | Core | 2 | 2 | 0 | 2 | 0 | T-087; T-256 | 1 | 1 | T-088 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.2 | L2 | Transformation authoring and relationship publication | Core | 1 | 1 | 0 | 1 | 0 | T-262 | 3 | 1 | T-243; T-156; T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.3 | L2 | Canonical projection with validation, quarantine and reprocessing | Core | 6 | 2 | 4 | 5 | 1 | T-099; T-100; T-101; T-104; T-261; T-152 | 4 | 2 | T-247; T-253; T-262; T-265; T-272 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.4 | L2 | Genealogy resolution and attribution | Core | 2 | 0 | 2 | 2 | 0 | T-102; T-103 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.5 | L2 | Unified definition store and immutable target/version governance | Core | 2 | 2 | 0 | 2 | 0 | T-089; T-243 | 4 | 3 | T-090; T-091; T-104; T-106 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.6 | L2 | Job definition, scheduling, execution monitor and history | Core | 2 | 1 | 1 | 2 | 0 | T-106; T-275 | 5 | 0 | T-107; T-245; T-261; T-263; T-265; T-270; T-274 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.7 | L2 | Job dependency DAG | Core | 0 | 0 | 0 | 0 | 0 |  | 2 | 1 | T-106; T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L2.8 | L2 | Delta propagation law | Core | 3 | 0 | 3 | 2 | 1 | T-108; T-109; T-110 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.1 | L3 | Analysis page anatomy, layout and visual standard | Core | 2 | 0 | 2 | 2 | 0 | T-148; T-265 | 3 | 1 | T-202; T-248; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.2 | L3 | Associative engine and selection strip | Core | 1 | 1 | 0 | 1 | 0 | T-204 | 2 | 0 | T-265; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.3 | L3 | Dynamic filter authoring | Core | 0 | 0 | 0 | 0 | 0 |  | 3 | 0 | T-248; T-265; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.4 | L3 | Widget catalogue and intelligence visualisation | Core | 2 | 0 | 2 | 1 | 1 | T-212; T-188 | 6 | 1 | T-202; T-215; T-258; T-248; T-134; T-189 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.5 | L3 | One authoring shell, five purposes, two modes | Core | 2 | 1 | 1 | 1 | 1 | T-244; T-156 | 3 | 1 | T-243; T-248; T-265; T-272 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.6 | L3 | Board semantics, typed ports and property inspection | Core | 3 | 3 | 0 | 3 | 0 | T-241; T-242; T-253 | 4 | 2 | T-243; T-262; T-248; T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.7 | L3 | Authoring professionalism | Core | 2 | 0 | 2 | 0 | 2 | T-248; T-267 | 2 | 1 | T-244; T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.8 | L3 | Canvas -> compile -> governed job -> run -> per-block evidence | Core | 2 | 0 | 2 | 1 | 1 | T-245; T-246 | 2 | 0 | T-247; T-261 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L3.9 | L3 | Master items, bookmarks and saved views | Core | 1 | 1 | 0 | 1 | 0 | T-092 | 2 | 0 | T-248; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.1 | L4 | Readiness gate and statistical discipline chain | Core | 3 | 1 | 2 | 1 | 2 | T-171; T-186; T-195 | 1 | 0 | T-188 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.2 | L4 | Statistical engines MF-05 / MF-06 | Core | 3 | 1 | 2 | 2 | 1 | T-177; T-211; T-146 | 7 | 2 | T-210; T-212; T-236; T-129; T-147; T-188; T-246 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.3 | L4 | Feature engineering and incremental feature refresh | Core | 5 | 2 | 3 | 2 | 3 | T-169; T-170; T-128; T-184; T-185 | 2 | 0 | T-109; T-192 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.4 | L4 | Learned models MF-01 / MF-03 / MF-04 | Core | 5 | 4 | 1 | 4 | 1 | T-168; T-172; T-174; T-175; T-187 | 2 | 0 | T-129; T-157 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.5 | L4 | Retrieval and similarity index MF-02 | Core | 1 | 1 | 0 | 1 | 0 | T-173 | 3 | 2 | T-180; T-182; T-187 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.6 | L4 | Practice learning MF-07 | Core | 7 | 0 | 7 | 0 | 7 | T-131; T-132; T-133; T-136; T-238; T-239; T-240 | 1 | 0 | T-264 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.7 | L4 | Prediction, drivers, explainability and remediation candidates | Core | 8 | 1 | 7 | 1 | 7 | T-178; T-139; T-140; T-141; T-142; T-143; T-158; T-189 | 2 | 0 | T-157; T-246 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L4.8 | L4 | Model registry, promotion, serving and fallback | Core | 4 | 2 | 2 | 2 | 2 | T-137; T-176; T-130; T-157 | 5 | 1 | T-182; T-186; T-187; T-192; T-193 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.1 | L5 | Canonical entity catalogue | Core | 4 | 3 | 1 | 4 | 0 | T-093; T-094; T-206; T-258 | 2 | 2 | T-092; T-256 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.2 | L5 | Permanent relationship model | Core | 5 | 3 | 2 | 4 | 1 | T-095; T-096; T-097; T-098; T-196 | 1 | 0 | T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.3 | L5 | Analysis Subject, grain and signal aggregation authority | Core | 4 | 3 | 1 | 3 | 1 | T-209; T-210; T-231; T-147 | 3 | 1 | T-094; T-212; T-211 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.4 | L5 | Regime correctness | Core | 3 | 2 | 1 | 3 | 0 | T-235; T-234; T-236 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.5 | L5 | Provenance, evidence chain, claim guard and refusal integrity | Core | 4 | 2 | 2 | 2 | 2 | T-217; T-218; T-129; T-134 | 4 | 1 | T-216; T-233; T-221; T-183; T-269; T-270 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.6 | L5 | Unified definition-store semantics | Core | 2 | 2 | 0 | 2 | 0 | T-090; T-091 | 1 | 1 | T-089; T-268 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.7 | L5 | Physical database governance and zero-unknown catalogue | Core | 1 | 1 | 0 | 1 | 0 | T-251 | 4 | 4 | T-087; T-088; T-256; T-260; T-272 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L5.8 | L5 | Truth contracts and claim boundaries | Core | 2 | 1 | 1 | 1 | 1 | T-220; T-183 | 2 | 1 | T-181; T-192 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.1 | L6 | Persistent Assistant dock and context envelope | Core | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | T-265 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.2 | L6 | Governed Assistant runtime | Core | 5 | 3 | 2 | 4 | 1 | T-179; T-180; T-181; T-223; T-138 | 1 | 0 | T-240 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.3 | L6 | Supervisor and governed improvement proposals | Core | 1 | 0 | 1 | 0 | 1 | T-193 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.4 | L6 | Alert routing and escalation | Core | 1 | 0 | 1 | 0 | 1 | T-197 | 2 | 0 | T-263; T-145 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.5 | L6 | Reports, export and scheduled delivery | Core | 1 | 0 | 1 | 0 | 1 | T-263 | 1 | 0 | T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.6 | L6 | Plant data log, audit, log channels, retention and archival | Core | 2 | 0 | 2 | 0 | 2 | T-198; T-199 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.7 | L6 | Global shell components G1-G6 | Core | 0 | 0 | 0 | 0 | 0 |  | 4 | 1 | T-203; T-248; T-265; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L6.8 | L6 | Settings, time zone, units, localisation and translation | Core | 1 | 0 | 1 | 0 | 1 | T-200 | 1 | 0 | T-266 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.1 | L7 | Users, roles, permissions, MFA and enterprise identity | Core | 3 | 0 | 3 | 2 | 1 | T-119; T-120; T-161 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.2 | L7 | Tenant isolation | Core | 4 | 0 | 4 | 2 | 2 | T-112; T-114; T-162; T-135 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.3 | L7 | Licence and feature entitlement | Core | 1 | 0 | 1 | 1 | 0 | T-121 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.4 | L7 | Authoring quota and capacity guardrail | Core | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | T-121; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.5 | L7 | Secret and credential management | Core | 1 | 0 | 1 | 1 | 0 | T-113 | 1 | 0 | T-162 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.6 | L7 | Commercial capacity model and licence-price function | Core | 1 | 0 | 1 | 0 | 1 | T-165 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.7 | L7 | Infrastructure cost formula | Core | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | T-165 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L7.8 | L7 | Sales Administration and sales-to-engineering handover | Core | 2 | 0 | 2 | 1 | 1 | T-126; T-167 | 1 | 1 | T-213 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.1 | L8 | Fresh install and upgrade authority | Core | 4 | 2 | 2 | 4 | 0 | T-088; T-260; T-115; T-123 | 1 | 1 | T-251 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.2 | L8 | Test architecture with disposable isolated databases | Core | 4 | 4 | 0 | 4 | 0 | T-205; T-208; T-250; T-252 | 3 | 1 | T-260; T-115; T-257 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.3 | L8 | Deployment topologies | Core | 1 | 0 | 1 | 0 | 1 | T-122 | 1 | 0 | T-123 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.4 | L8 | Execution lanes, admission and resource isolation | Core | 1 | 0 | 1 | 1 | 0 | T-107 | 3 | 1 | T-168; T-110; T-155; T-275 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.5 | L8 | Sizing model and calibrated performance constants | Core | 4 | 1 | 3 | 2 | 2 | T-182; T-154; T-155; T-273 | 1 | 0 | T-159 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.6 | L8 | Monitoring, observability, health and readiness | Core | 2 | 0 | 2 | 1 | 1 | T-125; T-163 | 1 | 0 | T-141; T-273; T-275 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.7 | L8 | Backup, restore, PITR, DR and HA | Core | 2 | 0 | 2 | 1 | 1 | T-124; T-160 | 0 | 0 | T-273 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L8.8 | L8 | C1-C4 performance certification and golden-journey release gate | Core | 18 | 5 | 13 | 9 | 9 | T-086; T-201; T-202; T-203; T-259; T-247; T-150; T-227; T-257; T-151; T-159; T-116; T-117; T-127; T-149; T-194; T-192; T-249 | 3 | 0 | T-126; T-152; T-167; T-273 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.1 | L9 | Performance Reference | Core | 3 | 0 | 3 | 3 | 0 | T-232; T-215; T-214 | 2 | 0 | T-223; T-264 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.2 | L9 | Suggestion generation from findings | Core | 1 | 0 | 1 | 0 | 1 | T-190 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.3 | L9 | Decision capture | Core | 1 | 0 | 1 | 0 | 1 | T-144 | 2 | 0 | T-190; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.4 | L9 | Action tracking | Core | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | T-144; T-190 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.5 | L9 | Canonical outcome capture | Core | 1 | 0 | 1 | 0 | 1 | T-145 | 2 | 0 | T-128; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.6 | L9 | Effectiveness evaluation | Core | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | T-145 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.7 | L9 | Value engine | Core | 1 | 0 | 1 | 0 | 1 | T-164 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L9.8 | L9 | Feedback quality and poisoning prevention | Core | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | T-145 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L10.1 | L10 | Internal benchmarking | Core | 1 | 0 | 1 | 0 | 1 | T-264 | 2 | 0 | T-238; T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L10.2 | L10 | Period driver decomposition | Core | 1 | 0 | 1 | 1 | 0 | T-237 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L10.3 | L10 | Operational evidence reconciliation | Advanced | 3 | 1 | 2 | 3 | 0 | T-222; T-219; T-221 | 2 | 1 | T-223; T-236 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L10.4 | L10 | Scenario simulation | Advanced | 1 | 0 | 1 | 0 | 1 | T-191 | 1 | 0 | T-267 | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
L10.5 | L10 | Insight Board Composer | Advanced | 3 | 0 | 3 | 0 | 3 | T-228; T-229; T-230 | 0 | 0 |  | Existing primary mapping preserved; secondary ownership amended only where acceptance names the capability.
Secondary links are a normalized generated view of Backlog column AC. Regenerate this view when capability assignments change; status/release values recalculate from task-ID lookups.

## Retired Tasks v222
Retired ID | Disposition | Merged responsibilities | Prior task name | Prior description | Prior acceptance | Prior hours | Prior status
T-105 | Retired / merged | T-104 | Idempotent reprojection and mapping-version regression | Make reprojection idempotent and add the regression suite: reprojecting the same batch must not duplicate rows, and rolling a mapping back to a previous version must produce the earlier result exactly. | Reproject the same batch three times and confirm row counts are unchanged. Roll a mapping back and confirm the canonical output matches the earlier snapshot byte for byte. | 6 | Not Started
T-111 | Retired / merged | T-110 (runtime); T-155 (calibration); T-159 (certification) | Scan budget and the Scan Amplification metric | Add scan admission and the Scan Amplification Ratio from Chapter 6 6.1.12.2a, with a baseline and a regression gate that fails the build when amplification rises beyond the baseline. | Record a baseline, then deliberately remove a delta scope and confirm the gate goes red. Restore and confirm green. | 12 | Not Started

## Revision Changes v222
Task / view | Field / operation | Previous | New | Reason
T-104 | Task Description | Complete the DF5 contract: source-shaped staging projects into the canonical plant model through the customer-authored versioned mapping, and every projected row records the mapping version that produced it. | Complete the DF5 contract: source-shaped staging projects into the canonical plant model through the customer-authored versioned mapping, and every projected row records the mapping version that produced it. v2.22.0 — Absorbs T-105: Make reprojection idempotent and add the regression suite: reprojecting the same batch must not duplicate rows, and rolling a mapping back to a previous version must produce the earlier result exactly. T-261 owns the executor. This task owns canonical row-level definition/version provenance and replay effects, using that executor; it does not implement a competing MappingDefinition runtime. | Merge with acceptance conservation
T-104 | Task Validation | Project a batch, change the mapping version, project again, and confirm each row records the version that produced it. No row may carry a null mapping version. | Project a batch, change the mapping version, project again, and confirm each row records the version that produced it. No row may carry a null mapping version. v2.22.0 — Reproject the same batch three times and confirm row counts are unchanged. Roll a mapping back and confirm the canonical output matches the earlier snapshot byte for byte. Assert exact resolved Transformation version/hash per run and row, tenant/dataset/batch source lineage, no duplicate accepted effect and byte-identical deterministic business output on rollback. Clock/run metadata is compared separately from business-result equivalence. | Merge T105 validation
T-104 | Task Name | Projection through the versioned mapping, with version stamping | Projection provenance, exact-version stamping and idempotent reprojection | Merge T105
T-104 | Hours | 8 | 14 | Preserve summed baseline estimates; not a re-estimate
T-106 | Task Description | Build on the M1 target_definition_id work: add the full version policy (pinned or current published), the job dependency graph, and cycle validation. v2.10.2 BOUNDARY CORRECTION — the pinned/current-published PUBLIC semantics are already frozen by T-064. This task performs canonical physical convergence: job_definitions FK -> definition_store(id) ON DELETE RESTRICT, target-version policy CHECKs/target-surface trigger against the canonical store, target_parameters persistence, plus job_dependencies DAG/cycle validation. Do not redesign T-064's visible contract. v2.20.0 EXECUTION-PLANE EXPANSION — replace the central job-type switch as the authority for manual execution. Each executable job family registers an executor capability through DI/registry metadata: supported/unsupported state, target definition kind, version policy, input contract and run capability. A new executor family must be addable without editing a central switch. Unsupported families refuse at definition/save or capability discovery with a typed reason rather than surviving until RunNow. v2.20.0 LAYER-B PLACEMENT RULING — scheduling count, repetition, iteration windows and control flow belong to governed Job orchestration. Do not add new FOR/WHILE-style board execution semantics. Existing T-242 saved definitions remain readable through compatibility handling, but new orchestration authority is the Job plane. | Build on the M1 target_definition_id work: add the full version policy (pinned or current published), the job dependency graph, and cycle validation. v2.10.2 BOUNDARY CORRECTION — the pinned/current-published PUBLIC semantics are already frozen by T-064. This task performs canonical physical convergence: job_definitions FK -> definition_store(id) ON DELETE RESTRICT, target-version policy CHECKs/target-surface trigger against the canonical store, target_parameters persistence, plus job_dependencies DAG/cycle validation. Do not redesign T-064's visible contract. v2.20.0 EXECUTION-PLANE EXPANSION — replace the central job-type switch as the authority for manual execution. Each executable job family registers an executor capability through DI/registry metadata: supported/unsupported state, target definition kind, version policy, input contract and run capability. A new executor family must be addable without editing a central switch. Unsupported families refuse at definition/save or capability discovery with a typed reason rather than surviving until RunNow. v2.20.0 LAYER-B PLACEMENT RULING — scheduling count, repetition, iteration windows and control flow belong to governed Job orchestration. Do not add new FOR/WHILE-style board execution semantics. Existing T-242 saved definitions remain readable through compatibility handling, but new orchestration authority is the Job plane. v2.22.0 — Deliver one canonical Job authority for target/version/capability, schedule grammar and occurrence identity, due scheduling, dependency resolution, cooperative cancellation and terminal-status truth. Implement Design v4.10.3 Ch4 5.3.2a / 5.3.6. The scheduler produces due requests; existing admission admits them. T-107 owns bounded pools; T-261 owns the actual Transformation executor. Keep these as separately testable sub-deliverables inside T-106 rather than additional task IDs. An executor supplied by tests proves orchestration before T-261 is commissioned, so T-106 must not depend on T-261 or T-107 closure. | Approved scope expansion, avoid dependency cycle
T-106 | Task Validation | Declare a three-job chain, run it, and confirm order. Introduce a cycle and confirm it is refused at save time with a named code. Enumerate every job family exposed by the product and prove each is either backed by a registered executor or explicitly unavailable by typed reason. Register a test executor through DI and prove it runs without editing the orchestrator switch. The current 'no manual executor'/'not implemented yet' runtime fall-through is no longer reachable for an advertised executable job. Newly authored execution schedules express repetition/window/control-flow in the Job contract rather than creating a new Canvas FOR/WHILE node. A compatibility fixture for an existing T-242 loop definition remains readable and produces an explicit compatibility interpretation rather than data loss. | Declare a three-job chain, run it, and confirm order. Introduce a cycle and confirm it is refused at save time with a named code. Enumerate every job family exposed by the product and prove each is either backed by a registered executor or explicitly unavailable by typed reason. Register a test executor through DI and prove it runs without editing the orchestrator switch. The current 'no manual executor'/'not implemented yet' runtime fall-through is no longer reachable for an advertised executable job. Newly authored execution schedules express repetition/window/control-flow in the Job contract rather than creating a new Canvas FOR/WHILE node. A compatibility fixture for an existing T-242 loop definition remains readable and produces an explicit compatibility interpretation rather than data loss. v2.22.0 — Prove canonical schedule parsing/normalisation and UI next-occurrence parity; UTC/timezone and DST gap/fold rules; one atomic admission per tenant/job/schedule-revision/occurrence under racing workers; restart/missed ticks; invalid or unsupported schedule typed refusal; paused state persists. Cancel API is tenant/role-scoped, idempotent, reaches executor and records exactly one final outcome. Cancellation request is not completion acknowledgement. Define all-success, mixed, all-failed, no-work, cancelled and interrupted outcomes; one failed import batch cannot be hidden in an Ok run in either manual or worker path. Current-cycle and earlier-success reuse follow explicit allow_stale_reuse and age ceiling, with timestamps, policy and watermark in job_run_dependencies. Trigger-fires, wrong-kind/surface and actual orchestration evidence use disposable DB fixtures. Keep existing historical closure evidence; certify newly widened obligations separately. | Scheduler, outcome and freshness acceptance
T-106 | Task Name | Job target/version policy, executor capability registry and dependency DAG | Canonical jobs: target/version, scheduling, dependencies, cancellation and outcome truth | Approved scope expansion
T-106 | Status | Not Started | In Progress | Source exists; expanded closure remains unproven
T-106 | Secondary Capability IDs | L2.5; L2.7 | L2.5; L2.7; L1.7 | Traceability coverage
T-106 | Depends On (IDs only) | T-064; T-089; T-090 | T-064; T-089; T-090; T-252 | Dependency aligned to owning producer
T-108 | Task Description | Today only import is incremental. Chapter 4 5.3.9 requires every downstream stage to be delta-scoped. Add the stage_watermarks table and make canonical projection delta-scoped against it. The arithmetic that justifies this: a naive full scan for one Pro-tier customer is 481 TB per day, while delta-scoped is 5 to 20 GB, a ratio of 24,000 to 1. | Today only import is incremental. Chapter 4 5.3.9 requires every downstream stage to be delta-scoped. Add the stage_watermarks table and make canonical projection delta-scoped against it. The arithmetic that justifies this: a naive full scan for one Pro-tier customer is 481 TB per day, while delta-scoped is 5 to 20 GB, a ratio of 24,000 to 1. v2.22.0 — Own acquisition-to-projection delta correctness: typed total-order cursor with source-stable tie-break for non-unique watermarks; one invariant provider-native ordering contract; durable cursor/staging/receipt atomicity; replay-safe accepted effects; per-dataset/profile budget resolution constrained by installation/source ceilings; apply pre-read budget/window/rate/concurrency/timeout checks on incremental as well as preview reads. Do not replace a stricter parent ceiling with a looser child override. Source native ordering and source-version identity govern legitimate updates. Retain existing stage-watermark and delta-projection duties; T-110 owns the advanced M3 parallel chunk engine. | Absorb acquisition defects into existing delta owner
T-108 | Task Validation | Change one source row and confirm projection processes a bounded delta rather than a full scan, evidenced by rows-scanned telemetry. | Change one source row and confirm projection processes a bounded delta rather than a full scan, evidenced by rows-scanned telemetry. v2.22.0 — Use more equal-watermark records than three page limits, numeric/timestamp/composite cursors, declared key changes, source updates, no change, de-DE/en-US serialization, crash before and after commit and racing workers. Prove no missed rows/no duplicate accepted source revision, and checkpoint advanced only with durable effects. Over-budget incremental reads issue no source query. Replay of a partially failed import preserves legitimate later versions of the same business key. One changed source row produces bounded downstream work with recorded counts. | Total-order, replay and source-load acceptance
T-108 | Task Name | stage_watermarks and delta-scoped projection | End-to-end delta correctness: source cursor, load protection, replay and projection watermark | Approved delta scope expansion
T-108 | Secondary Capability IDs | L1.3 | L1.3; L1.1; L1.7 | Traceability coverage
T-108 | Depends On (IDs only) |  | T-099; T-104 | Dependency aligned to owning producer
T-110 | Task Description | Implement Chapter 4 5.3.9.6a: bounded chunks with receipts, checkpoint and resume after interruption, and a deterministic merge so a resumed run produces the same result as an uninterrupted one. | Implement Chapter 4 5.3.9.6a: bounded chunks with receipts, checkpoint and resume after interruption, and a deterministic merge so a resumed run produces the same result as an uninterrupted one. v2.22.0 — Absorb T-111 runtime scan-budget enforcement: bounded row/byte chunks, receipts, checkpoint/resume, deterministic merge, explicit scan mode, cumulative scan budget and abort/finding. T-155 owns calibrated constants/Scan Amplification bands; T-159 owns C1-C4 certification. M2 T-108/T-109 must still deliver safe bounded delta execution and replay; moving advanced chunk machinery does not waive Day-1 source limits or safe cancellation. | Merge T111 runtime into scale execution
T-110 | Task Validation | Kill a running job at 60 percent, restart it, and confirm the final result is byte-identical to an uninterrupted run over the same input. | Kill a running job at 60 percent, restart it, and confirm the final result is byte-identical to an uninterrupted run over the same input. v2.22.0 — Record a baseline, then deliberately remove a delta scope and confirm the gate goes red. Restore and confirm green. Prove chunk parallelism 1 vs 8 business output parity; abort above cumulative scan budget; uncommitted chunk rolls back; resumes exactly from committed receipts; preserved input/version pins. | Conserve T111 negative control
T-110 | Task Name | Chunk manifests, checkpoint, resume and deterministic merge | Bounded delta execution: chunks, resume, deterministic merge and scan budgets | Merge and move
T-110 | Hours | 12 | 24 | Conservative combined baseline estimate; calibration allocations need re-estimation
T-110 | Depends On (IDs only) |  | T-108; T-109 | Dependency aligned to owning producer
T-110 | Milestone Id | M2 | M3 | Owner-approved release placement
T-110 | Phase Id | P2 | P1 | Owner-approved release placement
T-110 | Release Criticality | Release 1 MUST | Release 2 MUST | Owner-approved release placement
T-110 | Release Scope | R1 | R2 | Owner-approved release placement
T-246 | Milestone Id | M2 | M3 | Owner-approved release placement
T-246 | Phase Id | P2 | P4 | Owner-approved release placement
T-246 | Release Criticality | Release 1 MUST | Release 2 MUST | Owner-approved release placement
T-246 | Release Scope | R1 | R2 | Owner-approved release placement
T-246 | Depends On (IDs only) | T-243; T-130; T-137 | T-243; T-130; T-137; T-187 | Dependency aligned to owning producer
T-248 | Depends On (IDs only) | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-246; T-257 | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257 | Authoring grammar closure is not dependent on commissioned model family
T-101 | Task Description | Complete the C2 Mapping Health page against Chapter 3 4.4 C2: issues grouped by code, example rows, and Reprocess after the mapping is corrected. The M1 version delivered the shape; this delivers the full class set and the retry semantics. | Complete the C2 Mapping Health page against Chapter 3 4.4 C2: issues grouped by code, example rows, and Reprocess after the mapping is corrected. The M1 version delivered the shape; this delivers the full class set and the retry semantics. v2.22.0 — Quarantine inspection API/UI and schema-drift enforcement. Keep one drift event authority and reuse current schemas/compatibility safely. | Approved audit correction
T-101 | Task Validation | Quarantine rows under three different codes, correct one mapping, reprocess, and confirm only the affected rows clear. The M1 continuity snapshot of this page must still match. | Quarantine rows under three different codes, correct one mapping, reprocess, and confirm only the affected rows clear. The M1 continuity snapshot of this page must still match. v2.22.0 — GET quarantine list/detail filtered by code, dataset and batch with staging lineage/correction hint; tenant denial; remove mapped source object/field -> typed execution refusal and persisted C2 event; corrected reprocess uses declared version and records outcome. | Named acceptance conservation/extension
T-103 | Task Description | Confirm the genealogy layer walks both directions on the customer's own keys and that attribution weights are enforced to sum to exactly 1.0 per child by the database trigger on genealogy_edges.contribution_weight numeric(9,6). | Confirm the genealogy layer walks both directions on the customer's own keys and that attribution weights are enforced to sum to exactly 1.0 per child by the database trigger on genealogy_edges.contribution_weight numeric(9,6). v2.22.0 — Retain genealogy semantics and add explicit cyclic/self-edge protection at service and database boundaries. | Approved audit correction
T-103 | Task Validation | Walk a chain backward and forward and confirm the same edges are traversed. Attempt an insert whose weights sum to 0.99 inside a transaction and confirm the trigger rejects it, then roll back. | Walk a chain backward and forward and confirm the same edges are traversed. Attempt an insert whose weights sum to 0.99 inside a transaction and confirm the trigger rejects it, then roll back. v2.22.0 — Negative controls: self-edge, two-node and longer cycles refused; ordered weighted genealogy valid paths remain accepted; no silent deletion of lineage. | Named acceptance conservation/extension
T-243 | Task Description | Persist the shared canvas graph through the unified definition_store/definition_versions authority. Save block positions, typed connections, parameters and purpose; reopen and edit a published/draft version under the existing lifecycle. No canvas-specific shadow store. | Persist the shared canvas graph through the unified definition_store/definition_versions authority. Save block positions, typed connections, parameters and purpose; reopen and edit a published/draft version under the existing lifecycle. No canvas-specific shadow store. v2.22.0 — Extend the existing saved-board lifecycle to transactional relationship publication. Publish via existing IRelationshipPublicationService; derive only customer-declared joins/grains/attribution, not every arbitrary join inferred as a business relation. No shadow store. Legacy VisualMapper must route through canonical lifecycle or be retired compatibility-safely. | Approved audit correction
T-243 | Task Validation | Create/save/reopen/edit round-trip preserves semantic graph content; version history is immutable; rollback selects an existing version; no second definition lifecycle/table is introduced. The governed output target/Analysis Subject identity introduced by T-253 is part of the semantic round-trip and cannot collapse to a hardcoded material target. | Create/save/reopen/edit round-trip preserves semantic graph content; version history is immutable; rollback selects an existing version; no second definition lifecycle/table is introduced. The governed output target/Analysis Subject identity introduced by T-253 is part of the semantic round-trip and cannot collapse to a hardcoded material target. v2.22.0 — Publish a declared multi-member relationship and verify resolver consumption; republish supersedes not deletes; rollback/history remains explainable; simulated failure leaves neither a partially published definition nor a partially retired/emitted relationship set. Retain existing board/hash/Graph-SQL/reopen evidence; unproven new requirements do not erase previous implementation. | Named acceptance conservation/extension
T-254 | Task Description | Eliminate independent frontend/website capability claims for connectors and source systems. Availability, browse/read/subscription/import certification, Planned/Unavailable/Certified state and descriptive capability text are rendered from the backend connector truth snapshot or a generated artifact derived from it. Remove static 'live source' counts/claims that are not backed by current executed certification evidence. | Eliminate independent frontend/website capability claims for connectors and source systems. Availability, browse/read/subscription/import certification, Planned/Unavailable/Certified state and descriptive capability text are rendered from the backend connector truth snapshot or a generated artifact derived from it. Remove static 'live source' counts/claims that are not backed by current executed certification evidence. v2.22.0 — Converge backend provider validation and customer-facing truth on one authority; no independent provider capability list. Unimplemented SAP/REST remain explicitly non-executable; OPC metadata must equal runtime facts. This is bounded newly reviewed scope, not blanket reopening of earlier closures. | Approved audit correction
T-254 | Task Validation | Change a connector capability/certification state in a backend fixture and prove the DB Configuration UI and generated website proof change without editing frontend/website source. Unsupported/planned connectors remain dimmed and attempts retain the typed refusal from T-207. Static gate finds no second provider-capability availability registry and no unqualified '6 live source systems' claim. | Change a connector capability/certification state in a backend fixture and prove the DB Configuration UI and generated website proof change without editing frontend/website source. Unsupported/planned connectors remain dimmed and attempts retain the typed refusal from T-207. Static gate finds no second provider-capability availability registry and no unqualified '6 live source systems' claim. v2.22.0 — Profile create validation, /provider-types, UI, website and execution capability agree; architecture and behavioral test enumerate unsupported families; changing one authority is reflected by all consumers; preserve valid T-207/T-254 historical proof. | Named acceptance conservation/extension
T-113 | Task Description | Remove PlantProcess__Auth__Users__0__IsBootstrapAdmin=true from env/profiles/local.env and env/profiles/presentation.env, both at line 42. Move the hardcoded PPIQ_E2E_PASS and the CI signing key out of deploy/scripts/ci-e2e-stack.sh. Parameterise the fifteen hardcoded server-IP references. Add secret masking to the audit package generator, whose header currently reads 'Mask Secrets : False' while the package contains credentials. Also fix the duplicated ConnectionStrings__PlantProcessDb line in both env profiles. AUDIT HARDENING IN v2.9.2. Do not stop at deleting today's literals. Make environment separation structural: Production must reject demo/test/bootstrap users, development signing keys, presentation-only source/database defaults and hardcoded host fallbacks. Local, test and presentation conveniences remain available only through explicitly selected non-Production profiles; the same deployable artifact moves environments. v2.20.0 REVIEW ADDENDUM — remove the dead PPIQ_RUN_E2E runtime-env knob now that canonical Jenkins E2E is unconditionally blocking. Production administration must require MFA by default (or require an explicit, auditable production exception); Release-1 evidence must include one MFA-enabled admin path. | Remove PlantProcess__Auth__Users__0__IsBootstrapAdmin=true from env/profiles/local.env and env/profiles/presentation.env, both at line 42. Move the hardcoded PPIQ_E2E_PASS and the CI signing key out of deploy/scripts/ci-e2e-stack.sh. Parameterise the fifteen hardcoded server-IP references. Add secret masking to the audit package generator, whose header currently reads 'Mask Secrets : False' while the package contains credentials. Also fix the duplicated ConnectionStrings__PlantProcessDb line in both env profiles. AUDIT HARDENING IN v2.9.2. Do not stop at deleting today's literals. Make environment separation structural: Production must reject demo/test/bootstrap users, development signing keys, presentation-only source/database defaults and hardcoded host fallbacks. Local, test and presentation conveniences remain available only through explicitly selected non-Production profiles; the same deployable artifact moves environments. v2.20.0 REVIEW ADDENDUM — remove the dead PPIQ_RUN_E2E runtime-env knob now that canonical Jenkins E2E is unconditionally blocking. Production administration must require MFA by default (or require an explicit, auditable production exception); Release-1 evidence must include one MFA-enabled admin path. v2.22.0 — Enforce release-profile secret/configuration and unsafe legacy route boundary. Secrets only through references; reject/migrate secret-bearing options, protect logs/backups; release profile disables bootstrap defaults, seeds/dev minting and hand-entered-outcome runtime exposure. | Approved audit correction
T-113 | Task Validation | A secret scan across the repository returns no live credential. Generate an audit package and confirm secrets are masked. Confirm the E2E stack still runs with credentials supplied from the environment. Add a fail-closed Production configuration test that deliberately injects a bootstrap admin, a known demo/test credential marker, a development signing key and a presentation/local host fallback one at a time; each must stop startup or fail the configuration gate by name. A clean Production profile passes with all required values externally supplied. Confirm no executable production/runtime script supplies the retired server IP as a fallback. Confirm PPIQ_RUN_E2E is absent from runtime profile generation. A Production profile with privileged-admin MFA disabled fails the configuration gate unless an explicit governed exception fixture is supplied. Run one privileged-admin E2E path with MFA enabled. | A secret scan across the repository returns no live credential. Generate an audit package and confirm secrets are masked. Confirm the E2E stack still runs with credentials supplied from the environment. Add a fail-closed Production configuration test that deliberately injects a bootstrap admin, a known demo/test credential marker, a development signing key and a presentation/local host fallback one at a time; each must stop startup or fail the configuration gate by name. A clean Production profile passes with all required values externally supplied. Confirm no executable production/runtime script supplies the retired server IP as a fallback. Confirm PPIQ_RUN_E2E is absent from runtime profile generation. A Production profile with privileged-admin MFA disabled fails the configuration gate unless an explicit governed exception fixture is supplied. Run one privileged-admin E2E path with MFA enabled. v2.22.0 — Harmless sentinel round trip on create/update/get/list and logs; test setup failures fail tests; no secrets in profile row/response/log; no demo seed on production path; release-profile negative probes for dev/legacy routes; secret-scan evidence without printing secrets. | Named acceptance conservation/extension
T-121 | Task Description | Chapter 6 6.3 requires the six commercial dimensions and the capacity envelope to bound a tier together. LicenseLimits already carries AllowsSqlEditor per tier, set by both LicenseService and VerifiedEd25519LicenseService and exposed by LicenseAdminEndpoints. Extend to full metering: retained volume, ingest rate, refresh floor, weighted compute slots and concurrent sessions. Exceeding a meter throttles rather than destroys, and every meter is visible to the customer. v2.10.2 PAGE-COVERAGE EXPANSION — this owner also delivers the required F3 Authoring Quota and Limits route /admin/quota. F2 shows licence/entitlement and total meters; F3 allocates authoring quotas by role/user with current consumption, Amber at >=80%, create disabled at 100%, and no lost draft. v2.20.0 TRUST-ROOT RULING — production licence issuance/signing authority is vendor-side. Customer databases contain verification/public-key material and licence artifacts, not a production private signing key capable of minting a valid licence. Any development-only local signing key is explicitly non-production and either truly encrypted at rest or stored under a truthful non-encrypted name; an `_encrypted` column may not contain raw PEM. | Chapter 6 6.3 requires the six commercial dimensions and the capacity envelope to bound a tier together. LicenseLimits already carries AllowsSqlEditor per tier, set by both LicenseService and VerifiedEd25519LicenseService and exposed by LicenseAdminEndpoints. Extend to full metering: retained volume, ingest rate, refresh floor, weighted compute slots and concurrent sessions. Exceeding a meter throttles rather than destroys, and every meter is visible to the customer. v2.10.2 PAGE-COVERAGE EXPANSION — this owner also delivers the required F3 Authoring Quota and Limits route /admin/quota. F2 shows licence/entitlement and total meters; F3 allocates authoring quotas by role/user with current consumption, Amber at >=80%, create disabled at 100%, and no lost draft. v2.20.0 TRUST-ROOT RULING — production licence issuance/signing authority is vendor-side. Customer databases contain verification/public-key material and licence artifacts, not a production private signing key capable of minting a valid licence. Any development-only local signing key is explicitly non-production and either truly encrypted at rest or stored under a truthful non-encrypted name; an `_encrypted` column may not contain raw PEM. v2.22.0 — Preserve vendor-only signing and existing F2/F3 quota ownership. Remove shadow ILicenseService registrations; dev signing storage/naming truthful and non-production. | Approved audit correction
T-121 | Task Validation | Exceed a meter and confirm the import queues and the job waits for a slot rather than failing. Confirm the customer can see their own approach to each meter in the interface, since a limit the customer cannot see is a trap. In addition to licence-meter tests, open /admin/quota, change one role quota and one user override, approach 80% and 100%, and prove warning/disable semantics plus audit. Non-admin roles are denied by the final page contract. Issue a production-shaped licence outside the customer database, verify it on the customer installation, tamper and prove refusal. Prove the customer database alone cannot mint a valid production licence. Inspect signing-key persistence and prove no raw private PEM is stored in a field/schema claiming encryption. | Exceed a meter and confirm the import queues and the job waits for a slot rather than failing. Confirm the customer can see their own approach to each meter in the interface, since a limit the customer cannot see is a trap. In addition to licence-meter tests, open /admin/quota, change one role quota and one user override, approach 80% and 100%, and prove warning/disable semantics plus audit. Non-admin roles are denied by the final page contract. Issue a production-shaped licence outside the customer database, verify it on the customer installation, tamper and prove refusal. Prove the customer database alone cannot mint a valid production licence. Inspect signing-key persistence and prove no raw private PEM is stored in a field/schema claiming encryption. v2.22.0 — Exactly one effective registration; valid/tampered/expired licenses; no production signing secret; dev mint endpoint denied/unmapped in release profile; keep quota 80%/100%, role/user override and no lost draft acceptance. | Named acceptance conservation/extension
T-123 | Task Description | Build the fresh installation and upgrade paths from Chapter 6 6.1.4, including what an upgrade may never do, and a rollback path. Migration runs as a deployment step rather than as a manual action. Explicitly own in-place upgrade of a long-lived installation: canonical migration ledger/watermark continuity, upgrade from an older valid schema without rebuild, rollback boundary, and reconciliation of a development DB whose migration ledger is missing/stale. Do not conflate populated plant data with migration-ledger correctness. v2.20.0 DEPLOYMENT HARDENING — Release-1 production containers run with explicit non-root runtime users, and customer/public hostnames/IPs come from selected configuration profiles; executable install/smoke scripts have no legacy-server IP fallback. Do not wait for M3 isolated-ML container work to establish these minimum production properties. | Build the fresh installation and upgrade paths from Chapter 6 6.1.4, including what an upgrade may never do, and a rollback path. Migration runs as a deployment step rather than as a manual action. Explicitly own in-place upgrade of a long-lived installation: canonical migration ledger/watermark continuity, upgrade from an older valid schema without rebuild, rollback boundary, and reconciliation of a development DB whose migration ledger is missing/stale. Do not conflate populated plant data with migration-ledger correctness. v2.20.0 DEPLOYMENT HARDENING — Release-1 production containers run with explicit non-root runtime users, and customer/public hostnames/IPs come from selected configuration profiles; executable install/smoke scripts have no legacy-server IP fallback. Do not wait for M3 isolated-ML container work to establish these minimum production properties. v2.22.0 — Keep deterministic install/upgrade/rollback. Production schema migration and demo/presentation seed authorities are separated; operational profile values are external to product source. | Approved audit correction
T-123 | Task Validation | Install on a clean machine, upgrade from the previous version, then roll back. All three complete without manual database intervention. Run the fourteen post-deployment acceptance checks from 6.1.4.6. Clone an older populated installation, upgrade it in place through the canonical runner, prove schema_migrations/EF history records the executed path, preserve customer rows, and prove rollback/failed-upgrade recovery without substituting a fresh empty database. Inspect every Release-1 runtime image and prove its effective UID is non-root. Provision two different host/domain profiles without editing repository files and complete install/upgrade/smoke on both. A missing required production host value fails configuration rather than falling back to the historical server. | Install on a clean machine, upgrade from the previous version, then roll back. All three complete without manual database intervention. Run the fourteen post-deployment acceptance checks from 6.1.4.6. Clone an older populated installation, upgrade it in place through the canonical runner, prove schema_migrations/EF history records the executed path, preserve customer rows, and prove rollback/failed-upgrade recovery without substituting a fresh empty database. Inspect every Release-1 runtime image and prove its effective UID is non-root. Provision two different host/domain profiles without editing repository files and complete install/upgrade/smoke on both. A missing required production host value fails configuration rather than falling back to the historical server. v2.22.0 — Fresh production install has no demo/customer facts, no automatic presentation seed, external host/secret config, and restart/upgrade/rollback proof. Non-root process/container checks apply to the deployment profile actually shipped. | Named acceptance conservation/extension
T-235 | Task Description | Persist process_transition_definitions and process_transition_events plus effective-dated stabilisation policy, provenance and query API under the canonical definition/tenant authority. Do not model changeover as downtime by default; overlap is allowed and explicit. | Persist process_transition_definitions and process_transition_events plus effective-dated stabilisation policy, provenance and query API under the canonical definition/tenant authority. Do not model changeover as downtime by default; overlap is allowed and explicit. v2.22.0 — Wire existing TransitionAwarePoolingGuard into production statistics/correlation using persisted regime authority. This is M2 correctness, not a claim that every customer necessarily has transitions. | Approved audit correction
T-235 | Task Validation | Fresh migration/replay green. A customer-authored transition definition and event round-trip with scope/from-to context/stabilisation rule; no shipped industry values. Querying an interval returns exact transition/stabilisation overlaps and evidence. | Fresh migration/replay green. A customer-authored transition definition and event round-trip with scope/from-to context/stabilisation rule; no shipped industry values. Querying an interval returns exact transition/stabilisation overlaps and evidence. v2.22.0 — Declared transitions/stabilisation are excluded or stratified per policy; undefined required regime context refuses rather than pooling; declared no-transition case supported with evidence; known-answer production-path test and provenance. | Named acceptance conservation/extension
T-145 | Task Description | Capture observed outcomes, prediction/remediation evaluation and escalation records. Intervened instances are reported separately from ordinary prediction-accuracy metrics. Escalation is a record, never an automatic decision. | Capture observed outcomes, prediction/remediation evaluation and escalation records. Intervened instances are reported separately from ordinary prediction-accuracy metrics. Escalation is a record, never an automatic decision. v2.22.0 — Own canonical outcome, effectiveness and feedback quality/poisoning boundary. Retire the parallel hand-entered Phase-8 outcome authority with T-190; do not delete historical evidence unsafely. | Approved audit correction
T-145 | Task Validation | Accept a candidate, let the outcome arrive and prove evaluation closes the loop with intervention state preserved. Confirm intervened instances are excluded from ordinary accuracy calculation and an escalation creates no action automatically. | Accept a candidate, let the outcome arrive and prove evaluation closes the loop with intervention state preserved. Confirm intervened instances are excluded from ordinary accuracy calculation and an escalation creates no action automatically. v2.22.0 — Canonical-only outcome (DC03), complete action record before eligible feedback, actor concentration DC07 evidence, eligible-only supervisor proposals, feedback IDs retained and no auto-retraining. M2 unsafe route denial belongs to T-113. | Named acceptance conservation/extension
T-146 | Task Description | Use the schema-independent statistical kernel from T-177 to converge the runtime onto one readiness-gated engine and retire the direct-SQL/superseded compute paths. Persist method, aligned population/group sizes, effect size, p-value, FDR/q-value, gate evidence and truthful exclusion reason. This is the production wiring/cutover task; do not perform it before M1 presentation continuity is frozen. | Use the schema-independent statistical kernel from T-177 to converge the runtime onto one readiness-gated engine and retire the direct-SQL/superseded compute paths. Persist method, aligned population/group sizes, effect size, p-value, FDR/q-value, gate evidence and truthful exclusion reason. This is the production wiring/cutover task; do not perform it before M1 presentation continuity is frozen. v2.22.0 — Converge production statistical methods and discipline onto the accepted authorities; absorb/retire duplicate StatisticalDiscipline code only after all consumer and test obligations move. No performance/style-only rewrite. | Approved audit correction
T-146 | Task Validation | Only one production correlation engine is reachable. Known-answer fixtures cover Numeric×Numeric, Binary×Numeric, Categorical×Categorical and Numeric×Categorical. Numeric×Categorical selects ANOVA when assumptions hold and Kruskal-Wallis otherwise. Constant, unsupported and insufficient-sample cases retain distinct reasons. Re-run the M1 analysis continuity checks and prove no visible regression. | Only one production correlation engine is reachable. Known-answer fixtures cover Numeric×Numeric, Binary×Numeric, Categorical×Categorical and Numeric×Categorical. Numeric×Categorical selects ANOVA when assumptions hold and Kruskal-Wallis otherwise. Constant, unsupported and insufficient-sample cases retain distinct reasons. Re-run the M1 analysis continuity checks and prove no visible regression. v2.22.0 — One production discipline path; known-answer regression and required FDR/effect/stratification/refusal outputs survive. Reuse accepted kernel evidence; absence of callers alone is not justification to erase future integration work. | Named acceptance conservation/extension
T-186 | Task Description | Persist the T-171 capability profile per outcome/grain/manifest and implement governed prediction-point candidates plus the model-count governor. Only capabilities supported by measured data become eligible; collapsed dimensions and refusal reasons remain visible. Prediction points are activated under policy rather than multiplying models blindly. | Persist the T-171 capability profile per outcome/grain/manifest and implement governed prediction-point candidates plus the model-count governor. Only capabilities supported by measured data become eligible; collapsed dimensions and refusal reasons remain visible. Prediction points are activated under policy rather than multiplying models blindly. v2.22.0 — Persist and integrate CapabilityProfiler while preserving one readiness decision authority; coordinate T-146 consumers so a second production readiness result cannot disagree. | Approved audit correction
T-186 | Task Validation | On one rich and one sparse reference population, persist different capability states with their measured basis. Generate prediction-point candidates and prove the governor caps/chooses them deterministically. An unsupported model family remains MODEL_NOT_READY/NOT_APPLICABLE rather than creating a placeholder model. | On one rich and one sparse reference population, persist different capability states with their measured basis. Generate prediction-point candidates and prove the governor caps/chooses them deterministically. An unsupported model family remains MODEL_NOT_READY/NOT_APPLICABLE rather than creating a placeholder model. v2.22.0 — Same population/definition/manifest yields same gate decision at all consumers; values/thresholds/refusal evidence visible; missing data fail-closed. | Named acceptance conservation/extension
T-165 | Task Description | Validate the real user, page, job, DB-link and data bands against measured infrastructure, and build the Sales Administration and capacity calculator from Chapter 6 6.3.8. | Validate the real user, page, job, DB-link and data bands against measured infrastructure, and build the Sales Administration and capacity calculator from Chapter 6 6.3.8. v2.22.0 — Explicitly deliver infrastructure-cost formula Ch6 6.3.5 and licence-price function 6.3.6 with their separate assumptions and units; avoid conflating entitlement with commercial price. | Approved audit correction
T-165 | Task Validation | A quote produced by the calculator matches the measured server class for the same inputs. | A quote produced by the calculator matches the measured server class for the same inputs. v2.22.0 — Known-answer cost and price inputs/outputs; unit/currency/time basis; invalid/missing assumptions refuse; customer figures not fabricated. | Named acceptance conservation/extension
T-248 | Task Description | Close the Release-2 remainder of the founder-approved F01-F15, S01-S30 and E01-E30 outcome matrix using native PPIQ semantics. Explicitly include Scoped Measure Context, Named Comparison State, pending lasso/range confirm-cancel, story/live-source return, complete current-state export matrix, advanced exploration, mini-overview navigation where applicable, and reusable versioned subflows as the PPIQ equivalent of script Include/Must_Include. v2.20.0 ENTERPRISE-BI PARITY EXPANSION — the 75-item matrix explicitly includes context-sensitive property inspection, named selections/bookmarks, pivot/crosstab or governed PPIQ-equivalent, conditional formatting, export/print fidelity, design-token/theme governance, accessibility/keyboard authoring, and removal of localStorage as a fallback for server-owned page/widget layout state. v2.20.0 AUTHORING-SEMANTICS CONVERGENCE — close the historical T-242/Layer-B placement contradiction without reopening T-242. For newly authored definitions, arithmetic/comparison/logic are expression configuration inside the block they configure, while FOR/WHILE-style control flow is Job orchestration. Existing persisted T-242 definitions remain reopenable through an explicit compatibility translation/representation; do not strand customer-authored history. | Close the Release-2 remainder of the founder-approved F01-F15, S01-S30 and E01-E30 outcome matrix using native PPIQ semantics. Explicitly include Scoped Measure Context, Named Comparison State, pending lasso/range confirm-cancel, story/live-source return, complete current-state export matrix, advanced exploration, mini-overview navigation where applicable, and reusable versioned subflows as the PPIQ equivalent of script Include/Must_Include. v2.20.0 ENTERPRISE-BI PARITY EXPANSION — the 75-item matrix explicitly includes context-sensitive property inspection, named selections/bookmarks, pivot/crosstab or governed PPIQ-equivalent, conditional formatting, export/print fidelity, design-token/theme governance, accessibility/keyboard authoring, and removal of localStorage as a fallback for server-owned page/widget layout state. v2.20.0 AUTHORING-SEMANTICS CONVERGENCE — close the historical T-242/Layer-B placement contradiction without reopening T-242. For newly authored definitions, arithmetic/comparison/logic are expression configuration inside the block they configure, while FOR/WHILE-style control flow is Job orchestration. Existing persisted T-242 definitions remain reopenable through an explicit compatibility translation/representation; do not strand customer-authored history. v2.22.0 — Add G3 global search/command palette and G6 activity tray, preserving role/tenant scope, keyboard/focus, cross-page progress and reconnection. Use UI/Figma companion frames as visual implementation reference, not new behavior authority. | Approved audit correction
T-248 | Task Validation | A 75-row acceptance matrix has no Unowned or Missing row. Every row is Implemented or PPIQ-Equivalent, has an automated/visual acceptance or an explicit non-applicability proof, and no proprietary Qlik syntax is required. Comparative acceptance against the defined PPIQ outcomes demonstrates no missing enterprise authoring row for inspector/style, bookmark/selection, pivot/crosstab, formatting, export and accessibility. Server-owned layouts survive a clean browser profile with localStorage cleared. Raw component colour literals are within an explicit design-token allowlist. A new definition authors arithmetic/logic through expression configuration and schedules repetition/control flow through the Job authority. A persisted legacy T-242 board definition reopens with semantic equivalence and an explicit compatibility marker; save-as-new converges to the current representation without losing history. | A 75-row acceptance matrix has no Unowned or Missing row. Every row is Implemented or PPIQ-Equivalent, has an automated/visual acceptance or an explicit non-applicability proof, and no proprietary Qlik syntax is required. Comparative acceptance against the defined PPIQ outcomes demonstrates no missing enterprise authoring row for inspector/style, bookmark/selection, pivot/crosstab, formatting, export and accessibility. Server-owned layouts survive a clean browser profile with localStorage cleared. Raw component colour literals are within an explicit design-token allowlist. A new definition authors arithmetic/logic through expression configuration and schedules repetition/control flow through the Job authority. A persisted legacy T-242 board definition reopens with semantic equivalence and an explicit compatibility marker; save-as-new converges to the current representation without losing history. v2.22.0 — Search scopes results/actions correctly; keyboard select/escape; tray shows run identity/state/progress with polling fallback and no fake percent; empty/failed/denied variants; existing 75-item authoring/BI acceptance retained. | Named acceptance conservation/extension
T-116 | Task Description | Chapter 3 4.3 specifies 27 clean /api/{domain} domains. The repository registers 92 MapGroup prefixes and 544 verb-level routes, with 18 groups under /api/v5, 6 under /api/p15, plus /phase2, /phase4, /phase5, /api/phase8, /api/p09 and /admin/p03p04. Produce the mapping table, then serve both old and new paths during a transition window. v2.20.0 ORDERING — perform namespace renaming after T-256 has decided which material/legacy runtime surfaces remain legitimate compatibility surfaces. Do not preserve a semantically invalid endpoint merely to give it a cleaner URL. | Chapter 3 4.3 specifies 27 clean /api/{domain} domains. The repository registers 92 MapGroup prefixes and 544 verb-level routes, with 18 groups under /api/v5, 6 under /api/p15, plus /phase2, /phase4, /phase5, /api/phase8, /api/p09 and /admin/p03p04. Produce the mapping table, then serve both old and new paths during a transition window. v2.20.0 ORDERING — perform namespace renaming after T-256 has decided which material/legacy runtime surfaces remain legitimate compatibility surfaces. Do not preserve a semantically invalid endpoint merely to give it a cleaner URL. v2.22.0 — Maintain bounded-compatibility consumer register. Move live canon/public consumers to governed authorities before retiring compatibility objects; no delete-probes-first hotfix. | Approved audit correction
T-116 | Task Validation | Every one of the 544 routes appears exactly once in the mapping table. Both the old and the new path return identical responses for a sample of twenty routes. | Every one of the 544 routes appears exactly once in the mapping table. Both the old and the new path return identical responses for a sample of twenty routes. v2.22.0 — Inventory each consumer/object, positive and negative parity tests, old history remains readable, retirement only after no active dependency remains; upgrade/fresh install agree. | Named acceptance conservation/extension
T-190 | Task Description | Bind D6 Suggestions to canonical remediation candidates/eligibility/decision records. Suppressed candidates never render. Accept/Reject/Defer controls obey server can_accept and preserve the human/read-only boundary. Preserve the M1 visual contract while deleting presentation-only decision data paths. | Bind D6 Suggestions to canonical remediation candidates/eligibility/decision records. Suppressed candidates never render. Accept/Reject/Defer controls obey server can_accept and preserve the human/read-only boundary. Preserve the M1 visual contract while deleting presentation-only decision data paths. v2.22.0 — Retire Phase8SuggestionOutcomeLoopEndpoints as an alternate decision/outcome authority during canonical cutover; preserve relevant historical records and route compatibility only where semantically lawful. | Approved audit correction
T-190 | Task Validation | Run continuity snapshots. Attempt client-side manipulation to enable a forbidden decision and prove the server refuses it. Exercise actionable/evidence_only/exploratory/suppressed cases and confirm only allowed states appear with evidence and actor/reason history. | Run continuity snapshots. Attempt client-side manipulation to enable a forbidden decision and prove the server refuses it. Exercise actionable/evidence_only/exploratory/suppressed cases and confirm only allowed states appear with evidence and actor/reason history. v2.22.0 — No new hand-entered actual outcomes; canonical feedback loop with actor/time/provenance; disabled legacy routes cannot mutate production state. | Named acceptance conservation/extension
T-155 | Task Description | On site hardware, jointly execute resource measurements for lane max_concurrency/resource_capacity/compute_weight and the hard online reservation, plus scan-amplification and warm-model/assistant memory. This task supplies measured capacity values; it does not redesign the architecture. | On site hardware, jointly execute resource measurements for lane max_concurrency/resource_capacity/compute_weight and the hard online reservation, plus scan-amplification and warm-model/assistant memory. This task supplies measured capacity values; it does not redesign the architecture. v2.22.0 — Absorb T-111 measured Scan Amplification baseline/calibrated bands. T-110 owns runtime enforcement. | Approved audit correction
T-155 | Task Validation | Record hardware, commit and load profile. Saturate training/batch and prove online p95 remains inside the actionable budget. Publish measured lane values and before/after Scan Amplification with no starvation. | Record hardware, commit and load profile. Saturate training/batch and prove online p95 remains inside the actionable budget. Publish measured lane values and before/after Scan Amplification with no starvation. v2.22.0 — Measure under declared profiles and record formula, numerator/denominator and scope; known missing delta predicate triggers breach, not a tuned threshold. | Named acceptance conservation/extension
T-159 | Task Description | Run the four Chapter 6 capacity profiles and site certification, consuming the measured benchmark outputs from B-01..B-09 where they affect sizing. Replace only CALIBRATION_REQUIRED/REFERENCE_ASSUMPTION constants with measured values and freeze Chapter 6 when all certification gates pass. | Run the four Chapter 6 capacity profiles and site certification, consuming the measured benchmark outputs from B-01..B-09 where they affect sizing. Replace only CALIBRATION_REQUIRED/REFERENCE_ASSUMPTION constants with measured values and freeze Chapter 6 when all certification gates pass. v2.22.0 — Absorb T-111 capacity/regression certification; verify T-110 runtime scan guard using C1-C4 proofs. | Approved audit correction
T-159 | Task Validation | Every worked sizing example recomputes from measured constants; C1-C4 profiles pass their promised envelope. The certification bundle records hardware, commit, dataset, benchmark outputs and sign-off. | Every worked sizing example recomputes from measured constants; C1-C4 profiles pass their promised envelope. The certification bundle records hardware, commit, dataset, benchmark outputs and sign-off. v2.22.0 — Known negative control exceeds scan band/aborts; restored predicate passes; results, workload, topology and sampled period pinned. | Named acceptance conservation/extension
T-101 | Secondary Capability IDs | L1.6 | L1.6; L1.2 | Traceability coverage
T-121 | Secondary Capability IDs |  | L7.4 | Traceability coverage
T-145 | Secondary Capability IDs | L9.6; L6.4 | L9.6; L6.4; L9.8 | Traceability coverage
T-248 | Secondary Capability IDs | L3.1; L3.3; L3.4; L3.5; L3.6; L3.9 | L3.1; L3.3; L3.4; L3.5; L3.6; L3.9; L6.7 | Traceability coverage
T-243 | Secondary Capability IDs | L3.5; L3.6 | L3.5; L3.6; L2.2 | Traceability coverage
T-254 | Secondary Capability IDs |  | L1.4 | Traceability coverage
T-243 | Status | Not Started | In Progress | Source present; newly expanded publication acceptance unproven
T-245 | Status | In Progress | Not Started | Queued until producer closures, preserve existing binding work evidence
T-261 | Depends On (IDs only) | T-106; T-241; T-242; T-243 | T-106; T-241; T-242; T-243; T-099; T-262 | Dependency aligned to owning producer
T-104 | Depends On (IDs only) | T-090; T-095; T-099 | T-090; T-095; T-099; T-261 | Dependency aligned to owning producer
T-104 | Must Precede (IDs only) | T-105; T-107; T-109; T-128; T-183 | T-107; T-109; T-128; T-183 | Replace retired dependencies
T-107 | Depends On (IDs only) | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-105; T-106 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-106 | Replace retired dependencies
T-109 | Depends On (IDs only) | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-105; T-108 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-108 | Replace retired dependencies
T-128 | Depends On (IDs only) | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-105; T-112; T-114; T-231; T-210 | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114; T-231; T-210 | Replace retired dependencies
T-183 | Depends On (IDs only) | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-105; T-112; T-114 | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114 | Replace retired dependencies
T-262 | ADD |  | Governed projection declaration and canonical field-binding contract | Owner-authorised task; hours not fabricated
T-263 | ADD |  | Governed reports, export and scheduled delivery | Owner-authorised task; hours not fabricated
T-264 | ADD |  | Registry-driven internal benchmarking | Owner-authorised task; hours not fabricated
T-249 | Depends On (IDs only) | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248 | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110 | Dependency aligned to owning producer
T-247 | Depends On (IDs only) | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258 | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235 | Dependency aligned to owning producer
T-086 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-087 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-088 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-089 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-090 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-091 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-092 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-093 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-094 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-201 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-202 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-203 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-204 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-205 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-206 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-208 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-209 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-210 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-216 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-231 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-095 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-096 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-097 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-098 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-099 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-100 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-101 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-102 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-103 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-104 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-106 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-106 | AI Start / Dependency Gate | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-064 functional contract + T-089 + T-090 canonical definition authority. | Consume accepted producer contracts; remaining dependencies: T-064; T-089; T-090; T-252. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-106 | Tech-Lead Ruling | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-107 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-108 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-108 | AI Start / Dependency Gate | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Consume accepted producer contracts; remaining dependencies: T-099; T-104. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-108 | Tech-Lead Ruling | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-109 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-110 | Delivery Target | 2026-09-30 Release 1 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-110 | AI Sequence Wave | M2-P2 | M3-P1 | Release/phase synchronization
T-110 | Product Track | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | Scale & OT Resilience | Release/phase synchronization
T-110 | AI Start / Dependency Gate | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Consume accepted producer contracts; remaining dependencies: T-108; T-109. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-110 | Tech-Lead Ruling | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-207 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-212 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-213 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-224 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-225 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-226 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-232 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-233 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-235 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-241 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-242 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-243 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-243 | AI Start / Dependency Gate | NOT STARTED — measured 08-Sep current main HEAD is T-242 closure with zero T-243 product-source changes. Start fresh only after T-253 is CLOSED GREEN/committed; consume its canonical outputTarget contract rather than re-investigating target identity. | Consume accepted producer contracts; remaining dependencies: T-241; T-242; T-089; T-090; T-253. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-243 | Tech-Lead Ruling | CENTRAL v2.20.2 measured-source correction: current main has zero T-243 product-source work. Status is Not Started; begin fresh only after T-253 closes. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-244 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-245 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-245 | AI Start / Dependency Gate | QUEUED — start only after T-243, T-106 and T-261 are CLOSED GREEN; T-244 is already closed. T-245 consumes the governed Transformation executor and canonical job target/version authority; it must not invent a private Canvas scheduler. | Consume accepted producer contracts; remaining dependencies: T-243; T-244; T-106; T-261. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-245 | Tech-Lead Ruling | CENTRAL 04-Sep-2026: remove 'After 30-Sep MUST lane'. A Release-1-MUST task cannot be scheduled after its own release date. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-246 | Delivery Target | 2026-09-30 Release 1 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-246 | AI Sequence Wave | M2-P2 | M3-P4 | Release/phase synchronization
T-246 | Product Track | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | Advanced ML, Optimisation & Value | Release/phase synchronization
T-246 | AI Start / Dependency Gate | Release 1 MUST — execute after T-243 and governed model/intelligence contracts. Not a prerequisite of T-247 unless T-247 acceptance is amended to invoke a model block. | Consume accepted producer contracts; remaining dependencies: T-243; T-130; T-137; T-187. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-246 | Tech-Lead Ruling | CENTRAL 04-Sep-2026: remove 'After 30-Sep MUST lane'. A Release-1-MUST task cannot be scheduled after its own release date. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-247 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-253 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-254 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-258 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-148 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-215 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-222 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-137 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-137 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-168 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-168 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-169 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-169 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-170 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-170 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-171 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-171 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-172 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-172 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-173 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-173 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-174 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-174 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-175 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-175 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-176 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-176 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-177 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-177 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-178 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-178 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-179 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-179 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-180 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-180 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-181 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-181 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-182 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-182 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-211 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-211 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-214 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-214 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-217 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-217 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-218 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-218 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-219 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-219 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-220 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-220 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-221 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-221 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-223 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-223 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-234 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-234 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-236 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-236 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-237 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-237 | Product Track | Industrial Intelligence — Reference, Reconciliation & Assistant | Industrial Intelligence — References, Reconciliation & Assistant | Release/phase synchronization
T-112 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-113 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-114 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-115 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-119 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-120 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-121 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-123 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-124 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-125 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-126 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-150 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-227 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-122 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-151 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-152 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-153 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-154 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-155 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-159 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-160 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-163 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-116 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-117 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-127 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-149 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-161 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-162 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-194 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-196 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-197 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-198 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-199 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-200 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-156 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-166 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-228 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-229 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-230 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-248 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-128 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-129 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-130 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-131 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-132 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-133 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-134 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-135 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-136 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-138 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-139 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-140 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-141 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-142 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-143 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-144 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-145 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-146 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-147 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-157 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-158 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-164 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-165 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-183 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-184 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-185 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-186 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-187 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-188 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-189 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-190 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-191 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-192 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-193 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-195 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-238 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-239 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-240 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-167 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-249 | Delivery Target | 2026-10-30 Release 2 | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-250 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-251 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-260 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-259 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-252 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-256 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-255 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-257 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-261 | Delivery Target | 2026-09-30 Release 1 | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-261 | AI Start / Dependency Gate | Start only after T-106, T-241, T-242 and T-243 are CLOSED GREEN. Close T-261 as a separate semantic commit before resuming T-245. | Consume accepted producer contracts; remaining dependencies: T-106; T-241; T-242; T-243; T-099; T-262. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-261 | Tech-Lead Ruling | CENTRAL 11-Sep-2026: new Release-1 prerequisite created from measured T-245 preflight. Binding already exists; this task commissions honest governed Transformation execution. | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-262 | Delivery Target |  | M2: ~1 month from owner planning checkpoint; exact date not committed | Latest owner planning supersedes old calendar targets
T-262 | Product Track |  | Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC | Release/phase synchronization
T-262 | AI Start / Dependency Gate | Use producer contracts; close only after listed dependencies and targeted evidence. | Consume accepted producer contracts; remaining dependencies: T-253; T-243. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-262 | Tech-Lead Ruling |  | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-263 | Delivery Target |  | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-263 | Product Track |  | Advanced BI, Authoring & Insight Boards | Release/phase synchronization
T-263 | AI Start / Dependency Gate | Use producer contracts; close only after listed dependencies and targeted evidence. | Consume accepted producer contracts; remaining dependencies: T-106; T-248. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-263 | Tech-Lead Ruling |  | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-264 | Delivery Target |  | M3: 45 days after M2 completion | Latest owner planning supersedes old calendar targets
T-264 | Product Track |  | Advanced ML, Optimisation & Value | Release/phase synchronization
T-264 | AI Start / Dependency Gate | Use producer contracts; close only after listed dependencies and targeted evidence. | Consume accepted producer contracts; remaining dependencies: T-214; T-240. No private scheduler/definition authority. Source-present is not closure proof. | Replace stale contradictory gate
T-264 | Tech-Lead Ruling |  | v2.22.0 owner-approved scope and release disposition; original evidence remains in change log/archive. | Current ruling replaces superseded active notes
T-087 | Must Precede (IDs only) | T-061; T-089; T-099; T-102; T-112; T-114; T-128; T-196; T-233 | T-089; T-099; T-102; T-233; T-112; T-114; T-196; T-128; T-251; T-252 | Derived reverse dependency, not second authority
T-088 | Must Precede (IDs only) | T-087; T-089; T-112; T-128 | T-087; T-089; T-112; T-128; T-251; T-260; T-252; T-256 | Derived reverse dependency, not second authority
T-089 | Must Precede (IDs only) | T-061; T-090; T-092; T-095; T-099; T-106; T-114; T-128; T-183; T-243; T-244 | T-090; T-092; T-095; T-099; T-106; T-243; T-244; T-114; T-128; T-183 | Derived reverse dependency, not second authority
T-090 | Must Precede (IDs only) | T-061; T-091; T-092; T-095; T-099; T-104; T-106; T-114; T-128; T-134; T-147; T-183; T-195; T-210; T-221; T-228; T-231; T-232; T-233; T-235; T-239; T-243; T-244 | T-091; T-092; T-210; T-231; T-095; T-099; T-104; T-106; T-232; T-233; T-235; T-243; T-244; T-221; T-114; T-228; T-128; T-134; T-147; T-183; T-195; T-239 | Derived reverse dependency, not second authority
T-092 | Must Precede (IDs only) | T-093; T-094; T-128; T-183; T-212; T-215; T-228; T-237; T-247 | T-093; T-094; T-212; T-247; T-215; T-237; T-228; T-128; T-183 | Derived reverse dependency, not second authority
T-094 | Must Precede (IDs only) | T-095; T-128; T-183; T-196 | T-095; T-253; T-258; T-196; T-128; T-183; T-256 | Derived reverse dependency, not second authority
T-201 | Must Precede (IDs only) | T-086; T-202; T-203; T-204; T-205; T-206; T-207; T-208; T-213; T-241 | T-086; T-202; T-203; T-204; T-205; T-206; T-208; T-207; T-213; T-241 | Derived reverse dependency, not second authority
T-202 | Must Precede (IDs only) | T-150; T-212 | T-212; T-248 | Derived reverse dependency, not second authority
T-203 | Must Precede (IDs only) | T-150; T-222 | T-222; T-248 | Derived reverse dependency, not second authority
T-204 | Must Precede (IDs only) | T-150; T-222 | T-222; T-248 | Derived reverse dependency, not second authority
T-205 | Must Precede (IDs only) | T-150; T-250 | T-150; T-248; T-250; T-255; T-257 | Derived reverse dependency, not second authority
T-206 | Must Precede (IDs only) | T-093; T-150; T-213 | T-093; T-213 | Derived reverse dependency, not second authority
T-208 | Must Precede (IDs only) | T-150; T-209; T-211; T-216; T-217; T-218; T-234; T-238 | T-209; T-216; T-211; T-217; T-218; T-234; T-238 | Derived reverse dependency, not second authority
T-209 | Must Precede (IDs only) | T-094; T-210; T-214; T-231; T-234 | T-094; T-210; T-231; T-253; T-214; T-234 | Derived reverse dependency, not second authority
T-210 | Must Precede (IDs only) | T-092; T-128; T-211; T-212; T-242 | T-092; T-212; T-242; T-211; T-128 | Derived reverse dependency, not second authority
T-216 | Must Precede (IDs only) | T-200; T-217; T-233 | T-233; T-217; T-200 | Derived reverse dependency, not second authority
T-231 | Must Precede (IDs only) | T-092; T-128; T-139; T-232; T-235 | T-092; T-232; T-235; T-128; T-139 | Derived reverse dependency, not second authority
T-095 | Must Precede (IDs only) | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-114; T-128; T-134; T-183; T-196; T-221 | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-221; T-114; T-196; T-128; T-134; T-183 | Derived reverse dependency, not second authority
T-096 | Must Precede (IDs only) | T-097; T-098; T-107; T-109; T-128; T-134; T-183; T-221 | T-097; T-098; T-107; T-109; T-221; T-128; T-134; T-183 | Derived reverse dependency, not second authority
T-099 | Must Precede (IDs only) | T-061; T-100; T-101; T-104; T-107; T-109; T-114; T-128; T-183 | T-100; T-101; T-104; T-107; T-108; T-109; T-114; T-128; T-183; T-261 | Derived reverse dependency, not second authority
T-104 | Must Precede (IDs only) | T-107; T-109; T-128; T-183 | T-107; T-108; T-109; T-247; T-128; T-183 | Derived reverse dependency, not second authority
T-106 | Must Precede (IDs only) | T-107; T-122; T-245; T-125; T-261 | T-107; T-245; T-125; T-122; T-261; T-263 | Derived reverse dependency, not second authority
T-107 | Must Precede (IDs only) | T-122; T-141; T-187; T-192; T-125 | T-125; T-122; T-141; T-187; T-192 | Derived reverse dependency, not second authority
T-108 | Must Precede (IDs only) | T-109 | T-109; T-110; T-247 | Derived reverse dependency, not second authority
T-109 | Must Precede (IDs only) | T-136; T-187 | T-110; T-136; T-187 | Derived reverse dependency, not second authority
T-110 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-207 | Must Precede (IDs only) | T-150; T-224 | T-224; T-247; T-254; T-150 | Derived reverse dependency, not second authority
T-212 | Must Precede (IDs only) |  | T-247; T-150 | Derived reverse dependency, not second authority
T-213 | Must Precede (IDs only) | T-227; T-247 | T-247; T-227 | Derived reverse dependency, not second authority
T-224 | Must Precede (IDs only) | T-153; T-225 | T-225; T-153 | Derived reverse dependency, not second authority
T-225 | Must Precede (IDs only) | T-153; T-226 | T-226; T-153 | Derived reverse dependency, not second authority
T-226 | Must Precede (IDs only) | T-153 | T-150; T-153 | Derived reverse dependency, not second authority
T-233 | Must Precede (IDs only) | T-221; T-226 | T-226; T-221 | Derived reverse dependency, not second authority
T-235 | Must Precede (IDs only) | T-164; T-212; T-237 | T-212; T-247; T-237; T-164 | Derived reverse dependency, not second authority
T-241 | Must Precede (IDs only) | T-242; T-243; T-261 | T-242; T-243; T-247; T-253; T-248; T-261 | Derived reverse dependency, not second authority
T-242 | Must Precede (IDs only) | T-243; T-261 | T-243; T-247; T-261 | Derived reverse dependency, not second authority
T-243 | Must Precede (IDs only) | T-245; T-246; T-261 | T-245; T-246; T-247; T-248; T-261; T-262 | Derived reverse dependency, not second authority
T-244 | Must Precede (IDs only) | T-245 | T-245; T-247; T-253; T-248 | Derived reverse dependency, not second authority
T-245 | Must Precede (IDs only) |  | T-247; T-248 | Derived reverse dependency, not second authority
T-246 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-247 | Must Precede (IDs only) |  | T-150 | Derived reverse dependency, not second authority
T-253 | Must Precede (IDs only) | T-243; T-245; T-247; T-150 | T-243; T-247; T-150; T-256; T-262 | Derived reverse dependency, not second authority
T-148 | Must Precede (IDs only) | T-150 | T-248 | Derived reverse dependency, not second authority
T-215 | Must Precede (IDs only) | T-222 | T-222; T-150 | Derived reverse dependency, not second authority
T-222 | Must Precede (IDs only) |  | T-150 | Derived reverse dependency, not second authority
T-137 | Must Precede (IDs only) | T-122; T-138; T-246 | T-246; T-122; T-138 | Derived reverse dependency, not second authority
T-168 | Must Precede (IDs only) | T-122; T-175; T-187 | T-175; T-122; T-187 | Derived reverse dependency, not second authority
T-179 | Must Precede (IDs only) | T-138; T-223; T-228 | T-223; T-228; T-138 | Derived reverse dependency, not second authority
T-180 | Must Precede (IDs only) | T-138; T-223; T-228 | T-223; T-228; T-138 | Derived reverse dependency, not second authority
T-181 | Must Precede (IDs only) | T-138; T-223; T-228 | T-223; T-228; T-138 | Derived reverse dependency, not second authority
T-211 | Must Precede (IDs only) | T-212 | T-212; T-247 | Derived reverse dependency, not second authority
T-214 | Must Precede (IDs only) | T-215; T-223; T-232; T-238; T-239 | T-232; T-215; T-223; T-238; T-239; T-264 | Derived reverse dependency, not second authority
T-219 | Must Precede (IDs only) | T-220; T-221; T-222; T-223 | T-222; T-220; T-221; T-223 | Derived reverse dependency, not second authority
T-220 | Must Precede (IDs only) | T-221; T-222; T-223 | T-222; T-221; T-223 | Derived reverse dependency, not second authority
T-223 | Must Precede (IDs only) |  | T-150 | Derived reverse dependency, not second authority
T-112 | Must Precede (IDs only) | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | T-221; T-122; T-198; T-230; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195 | Derived reverse dependency, not second authority
T-114 | Must Precede (IDs only) | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | T-221; T-122; T-198; T-230; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195 | Derived reverse dependency, not second authority
T-115 | Must Precede (IDs only) |  | T-150 | Derived reverse dependency, not second authority
T-123 | Must Precede (IDs only) |  | T-150; T-122 | Derived reverse dependency, not second authority
T-124 | Must Precede (IDs only) | T-199 | T-150; T-199 | Derived reverse dependency, not second authority
T-125 | Must Precede (IDs only) |  | T-150 | Derived reverse dependency, not second authority
T-126 | Must Precede (IDs only) |  | T-150 | Derived reverse dependency, not second authority
T-153 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-159 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-160 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-163 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-161 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-162 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-194 | Must Precede (IDs only) | T-150 |  | Derived reverse dependency, not second authority
T-196 | Must Precede (IDs only) | T-127; T-148 | T-148; T-127 | Derived reverse dependency, not second authority
T-197 | Must Precede (IDs only) | T-127; T-148 | T-148; T-127 | Derived reverse dependency, not second authority
T-198 | Must Precede (IDs only) | T-127; T-148; T-197; T-199 | T-148; T-127; T-197; T-199 | Derived reverse dependency, not second authority
T-199 | Must Precede (IDs only) | T-127; T-148 | T-148; T-127 | Derived reverse dependency, not second authority
T-200 | Must Precede (IDs only) | T-127; T-148 | T-148; T-127 | Derived reverse dependency, not second authority
T-228 | Must Precede (IDs only) | T-229 | T-229; T-248 | Derived reverse dependency, not second authority
T-230 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-248 | Must Precede (IDs only) | T-249 | T-249; T-263 | Derived reverse dependency, not second authority
T-130 | Must Precede (IDs only) | T-134; T-135; T-139; T-188; T-191; T-193; T-246 | T-246; T-134; T-135; T-139; T-188; T-191; T-193 | Derived reverse dependency, not second authority
T-134 | Must Precede (IDs only) | T-138; T-228; T-229 | T-228; T-229; T-138 | Derived reverse dependency, not second authority
T-164 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-187 | Must Precede (IDs only) | T-139; T-141; T-191; T-192; T-193 | T-246; T-139; T-141; T-191; T-192; T-193 | Derived reverse dependency, not second authority
T-192 | Must Precede (IDs only) | T-150 |  | Derived reverse dependency, not second authority
T-193 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-195 | Must Precede (IDs only) | T-066; T-186; T-187; T-188 | T-186; T-187; T-188 | Derived reverse dependency, not second authority
T-240 | Must Precede (IDs only) |  | T-249; T-264 | Derived reverse dependency, not second authority
T-167 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-250 | Must Precede (IDs only) | T-150 | T-258; T-150; T-255; T-257 | Derived reverse dependency, not second authority
T-251 | Must Precede (IDs only) | T-115; T-123; T-150 | T-112; T-150; T-259; T-252; T-256 | Derived reverse dependency, not second authority
T-260 | Must Precede (IDs only) | T-251; T-259 | T-251 | Derived reverse dependency, not second authority
T-259 | Must Precede (IDs only) | T-252; T-257; T-227; T-150 | T-150; T-227; T-252; T-257 | Derived reverse dependency, not second authority
T-252 | Must Precede (IDs only) | T-150; T-256 | T-106; T-112; T-150; T-256 | Derived reverse dependency, not second authority
T-256 | Must Precede (IDs only) | T-247; T-150; T-116; T-258 | T-247; T-258; T-150; T-116 | Derived reverse dependency, not second authority
T-255 | Must Precede (IDs only) | T-150; T-249 | T-150 | Derived reverse dependency, not second authority
T-261 | Must Precede (IDs only) | T-245 | T-104; T-245 | Derived reverse dependency, not second authority
T-262 | Must Precede (IDs only) |  | T-261 | Derived reverse dependency, not second authority
T-263 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-264 | Must Precede (IDs only) |  | T-249 | Derived reverse dependency, not second authority
T-148 | Completion vs contract dependency | T-196; T-197; T-198; T-199; T-200 | T-196; T-197; T-198; T-199; T-200 (contract-ready only) | v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148.

## Phase Worker v222
Phase × Worker — v2.23.0 ¦ reviewed15Sep2026; not an actual/remaining-hours ledger
Release | Phase | Worker | Active tasks | Done tasks | Open tasks | Usable scope h | Done scope h | Open scope h | Estimate unresolved
M2 | P1 | Worker 1 | 17 | 17 | 0 | 172 | 172 | 0 | 0
M2 | P1 | Worker 2 | 5 | 5 | 0 | 44 | 44 | 0 | 0
M2 | P1 | Worker 3 | 4 | 4 | 0 | 29 | 29 | 0 | 0
M2 | P2 | Worker 1 | 19 | 6 | 13 | 59 | 40 | 19 | 11
M2 | P2 | Worker 2 | 16 | 7 | 9 | 118 | 60 | 58 | 6
M2 | P2 | Worker 3 | 7 | 1 | 6 | 22 | 0 | 22 | 5
M2 | P3 | Worker 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M2 | P3 | Worker 2 | 5 | 0 | 5 | 36 | 0 | 36 | 1
M2 | P3 | Worker 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M2 | P4 | Worker 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M2 | P4 | Worker 2 | 1 | 0 | 1 | 10 | 0 | 10 | 0
M2 | P4 | Worker 3 | 10 | 6 | 4 | 94 | 56 | 38 | 0
M2 | P5 | Worker 1 | 12 | 0 | 12 | 90 | 0 | 90 | 3
M2 | P5 | Worker 2 | 2 | 0 | 2 | 18 | 0 | 18 | 0
M2 | P5 | Worker 3 | 1 | 0 | 1 | 8 | 0 | 8 | 0
M3 | P1 | Worker 1 | 8 | 0 | 8 | 84 | 0 | 84 | 1
M3 | P1 | Worker 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M3 | P1 | Worker 3 | 2 | 0 | 2 | 0 | 0 | 0 | 2
M3 | P2 | Worker 1 | 5 | 0 | 5 | 36 | 0 | 36 | 1
M3 | P2 | Worker 2 | 7 | 0 | 7 | 70 | 0 | 70 | 0
M3 | P2 | Worker 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M3 | P3 | Worker 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M3 | P3 | Worker 2 | 5 | 0 | 5 | 24 | 0 | 24 | 3
M3 | P3 | Worker 3 | 3 | 0 | 3 | 34 | 0 | 34 | 0
M3 | P4 | Worker 1 | 3 | 0 | 3 | 20 | 0 | 20 | 1
M3 | P4 | Worker 2 | 1 | 0 | 1 | 11 | 0 | 11 | 0
M3 | P4 | Worker 3 | 36 | 0 | 36 | 346 | 0 | 346 | 5
M3 | P5 | Worker 1 | 1 | 0 | 1 | 12 | 0 | 12 | 0
M3 | P5 | Worker 2 | 1 | 0 | 1 | 12 | 0 | 12 | 0
M3 | P5 | Worker 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Prior Notes v222
Original sheet | Row | Cell contents — preserved as historical evidence
Current Authority | 1 | ["PPIQ Backlog v2.21.0 — Product Capability Traceability + Governed Projection Executor", null, null, null]
Current Authority | 2 | [null, null, null, null]
Current Authority | 3 | ["Authority", "Current value", "Date", "Meaning"]
Current Authority | 4 | ["Master Design", "v4.10.1", "2026-09-04", "Six design chapters only"]
Current Authority | 5 | ["Execution Backlog", "v2.21.0", 46276, "This workbook is the v2.21.0 execution authority. Capability traceability and T-261 are current; legacy summary sheets retaining v220 labels are preserved as prior generated views and are not the source of task/capability truth."]
Current Authority | 6 | ["Release 1", "M2 — 30 Sep 2026", null, "Early production / customer first-week ready"]
Current Authority | 7 | ["Release 2", "M3 — 30 Oct 2026", null, "Heavy production / more users / more data"]
Current Authority | 8 | ["Phase vocabulary", "P1 · P2 · P3 · P4 · P5", null, "No alternative milestone/phase codes are current authority"]
Current Authority | 9 | ["Mirror law", "100% traceability required", null, "Every design requirement maps to backlog acceptance; every task maps to design"]
Current Authority | 10 | ["Historical work", "Archive only", null, "Prior M1/Fleet-specific work is evidence, not current execution scope"]
Current Authority | 11 | ["Latest revision", "T-261 added as the governed Transformation/Projection executor prerequisite for T-245. Product Capability Traceability Standard v1.1 mapped every backlog task to a stable capability point.", 46276, "v2.21.0 is a semantic version change because T-261 is a genuine new task. Capability mapping itself changes traceability/reporting only and does not redefine existing task scope."]
Governance | 1 | ["Execution Governance & Vocabulary", null, null]
Governance | 2 | [null, null, null]
Governance | 3 | ["Rule", "Current authority", "Why"]
Governance | 4 | ["Release vocabulary", "Only M2 and M3", "No alternative roadmap names are current authority"]
Governance | 5 | ["Phase vocabulary", "Only P1/P2/P3/P4/P5", "Immediately shows before/after and product purpose"]
Governance | 6 | ["M2 meaning", "Release 1 — real early production", "Not demo, not pilot-only, not presentation branch"]
Governance | 7 | ["M3 meaning", "Release 2 — heavy production", "More users, more data, sustained runtime and deeper capability"]
Governance | 8 | ["One task / one owner", "Mandatory", "No cross-worker implementation ownership"]
Governance | 9 | ["Dependencies", "IDs only", "Machine-readable semicolon-separated Task IDs"]
Governance | 10 | ["Release truth", "Browser walk is final confirmation", "Basic defects must fail automated gates before browser walk"]
Governance | 11 | ["Genericity", "Same binary; customer changes configuration, not product", "Customer-specific product code fails onboarding"]
Governance | 12 | ["Canvas expression / control-flow placement", "Layer-B is final semantic authority: arithmetic/comparison/logic are expression configuration; FOR/WHILE are Job orchestration. T-242 closed artifacts are compatibility inputs only; no new board-level expansion.", "Preserves valid T-242 closure while preventing the backlog/design contradiction from propagating into S3/S4 and Release 2."]
Governance | 13 | ["OPC", "Read-only/outbound edge", "No control/writeback path"]
Governance | 14 | ["Assistant", "Evidence-first", "No invented numbers or unsupported root-cause certainty"]
Governance | 15 | ["Value", "Bounded and evidenced", "Potential value ≠ realised value"]
Governance | 16 | ["Repository mutation ownership", "No Task ID = no repository mutation", "Every code/test/config change or corrective finding maps to an existing task or a newly created task; closed tasks stay closed."]
Governance | 17 | ["Test execution economy", "Narrow affected tests first; expensive full certification only at the owning gate or when that gate changes", "Prevents repeated hour-scale reruns while preserving final release truth."]
Governance | 18 | ["Release gate completeness", "T-150 enumerates every M2 row with Release Criticality = Release 1 MUST", "Direct Depends-On is sequencing metadata, never a substitute for complete release acceptance."]
Governance | 19 | ["Physical database authority", "Zero unknown product tables/columns on fresh certification DB", "Every object has schema, family, lifecycle, owner, design clause and generated dictionary entry."]
Governance | 20 | ["Disposable database lifecycle", "CREATE DATABASE implies owner + finally DROP unless explicitly declared persistent", "Prevents probe/scratch/backup debris and cross-worker shared-DB contamination."]
Governance | 21 | ["Database naming", "Forward snake_case + no customer vocabulary + no redundant ppiq_ prefix in governed schemas", "Existing names are grandfathered; no mass rename without owned compatibility proof."]
Governance | 22 | ["Authority precedence", "Current Master Design / frozen Layer-B semantic rulings > current Backlog execution wording > historical task prose.", "When two current documents conflict semantically, Central must rule and amend future scope; workers are not blamed for following the then-current backlog."]
Governance | 23 | ["Closed-task regression handling", "Do not broadly reopen closed tasks. A newly discovered concrete regression receives a narrow new Task ID unless the original closure evidence itself is proven false.", "Prevents scope erosion and preserves auditability."]
Governance | 24 | ["Release evidence envelope", "T-227 owns one canonical machine-readable schema; T-252/T-257 emit producer-specific evidence into it; T-150 aggregates it.", "Prevents duplicated skip-count formats and keeps final release gate from redefining evidence semantics late."]
Governance | 25 | ["Cross-worker genericity handoff", "Backend runtime convergence and frontend material-surface convergence have separate owners: T-256 Worker 1, T-258 Worker 2.", "Worker 1 must not repair Worker-2 frontend files; compatibility must remain green across the handoff."]
Governance | 26 | ["Canvas output-target namespace", "Canonical entity name from ICanonicalEntityCatalog; never physical relation name and never an overloaded Analysis Subject key.", "Graph and SQL share one governed output identity while Analysis Subject remains a separate semantic authority."]
Governance | 27 | ["Canvas output-target hashing", "New Graph/SQL saves carry root `outputTarget` in hashed canonical content. Legacy Graph may derive from graph.targetEntity; legacy SQL missing target returns null, never fabricated.", "Hash change on re-save legitimately creates a new immutable version; prior version remains untouched."]
Governance | 28 | ["Release evidence envelope v1", "T-259 owns the small shared machine-readable envelope contract. T-252/T-257 produce it; T-227 owns scorecard/policy; T-150 aggregates.", "Removes the impossible dependency where producers needed a P5 schema that did not yet exist."]
Governance | 29 | ["Release evidence count semantics", "total_count = executed_count + skipped_count; executed_count = passed_count + failed_count; skipped work is never counted as executed.", "Prevents an all-skipped suite from appearing fully exercised."]
Governance | 30 | ["Canonical projection-target eligibility", "Canonical entity identity and projection-target eligibility are separate facts. Eligibility is an explicit model/type-sourced capability, not 'all mapped entities' and not schema-only.", "Prevents ImportBatch/JobRunHistory/etc. from becoming Canvas/mapping targets while preserving valid reference targets outside ppiq_plant."]
Governance | 31 | ["Schema role in target eligibility", "ppiq_plant/ppiq_meta topology is a consistency/governance signal, not the sole target predicate.", "ParameterDefinition/DefectCatalog are valid current targets outside ppiq_plant; ppiq_plant also contains analytical outputs."]
Governance | 32 | ["T-256 synchronization", "T-253 is a hard dependency of T-256. If Worker 1 reaches the gate first, CENTRAL assigns a disjoint lane rather than allowing duplicate target-classification work.", "Correctness and single authority take precedence over keeping P1 locally wait-free."]
Governance | 33 | ["Fresh certification DB authority", "A database called ppiq_acceptance_empty is not authoritative merely by name; it must be constructed by the complete canonical migration-order authority.", "Prevents catalogue/adjudication against a partial fresh build."]
Governance | 34 | ["T-251/T-260 split", "T-251 owns read-only physical truth; T-260 owns correction of the fresh certification DB builder discovered by T-251.", "Avoids violating T-251's read-only lock while preventing false classification work."]
Governance | 35 | ["Adjudication order", "Do not classify the old 106/81 fresh-DB queue. Correct/rebuild first, rerun census second, adjudicate only the remaining true queue.", "Avoids spending governance effort on objects stranded by an incomplete build path."]
Method & Notes | 1 | ["Method, evidence hierarchy, and v2.20.4 reconciliation", null]
Method & Notes | 2 | [null, null]
Method & Notes | 3 | ["Topic", "Rule / interpretation"]
Method & Notes | 4 | ["Execution authority", "PPIQ Backlog v2.20.2 dated 08-Sep-2026. It supersedes v2.20.1 after Worker-2 current-tree measurement and Worker-1 evidence-envelope dependency review."]
Method & Notes | 5 | ["Hours denominator", "Nominal Hours remain the progress denominator. The review added real uncovered scope and retired one duplicate task, so M2 scope changes from 993h to 1035h."]
Method & Notes | 6 | ["Strict completion", "In Progress receives zero closed-hour credit. Only Verified/Backlog Status = Done earns the task's full nominal hours."]
Method & Notes | 7 | ["Regression law", "Valid closed tasks stay closed. Concrete regressions discovered after closure receive narrow new Task IDs unless closure evidence itself is invalidated."]
Method & Notes | 8 | ["T-245 ruling", "T-245 is Not Started / QUEUED. It starts only after T-243 and T-106 are CLOSED GREEN; T-244 is already closed."]
Method & Notes | 9 | ["T-252 ruling", "T-252 is M2-P1 and explicitly depends on T-251 in the dependency cell. Worker-1 P1 sequence is mechanically T-251 → T-252 → T-256."]
Method & Notes | 10 | ["T-118 ruling", "T-118 is retired from active scope as a duplicate commissioning umbrella. Historical evidence is preserved in Prior Baseline Archive."]
Method & Notes | 11 | ["Canvas semantic ruling", "Layer-B governs placement: arithmetic/comparison/logic are expression configuration and FOR/WHILE are Job orchestration. T-242 remains closed; existing persisted artifacts are compatibility inputs and future authoring converges without data loss."]
Method & Notes | 12 | ["CI correction", "Worker-1 review correction accepted: the live canonical Jenkinsfile has blocking E2E. Historical gated copies exist only in backups. Remaining test-truth work concerns enumeration-only --list scripts, skips and release-profile evidence."]
Method & Notes | 13 | ["Commit date", "A Commit Date may be exact Git date or closure-session date depending on evidence. Missing subject/date is left unrecovered rather than guessed."]
Method & Notes | 14 | ["Audit package safety", "The 08-Sep UltimateAudit package was generated with Mask Secrets=False and is internal engineering evidence only; external evidence must be regenerated masked."]
Method & Notes | 15 | ["Evidence hierarchy", "Current runtime/source path + executed tests > current source trace > commit/closure > handover > backlog/design prose. Backup/archive copies never override the live path."]
Method & Notes | 16 | ["Evidence-envelope ownership", "T-227 owns the canonical Release-1 machine-readable evidence-envelope schema. T-252 and T-257 are producers for DB-fixture and frontend/E2E results respectively. T-150 only aggregates/validates the shared envelope."]
Method & Notes | 17 | ["T-256/T-258 ownership split", "T-256 is backend/API/DB-runtime only. Frontend MaterialAnalytics/routes/types are Worker-2 T-258. T-256 must preserve a bounded compatibility handoff so it does not leave the generic frontend red."]
Method & Notes | 18 | ["Fresh certification DB", "The named fresh canonical certification database for T-251 is `ppiq_acceptance_empty`; do not invent ad-hoc fresh database names before T-252 lifecycle authority."]
Method & Notes | 19 | ["T-253 measured ruling", "Current main HEAD is T-242 (`aa57a503`) with zero T-243 product-source changes. T-253 is current; T-243 is Not Started and begins fresh after T-253."]
Method & Notes | 20 | ["T-253 target identity", "Persist canonical entity name. New hashed root `outputTarget` is representation-independent; graph.targetEntity remains compatibility data and must match on new graph writes."]
Method & Notes | 21 | ["T-253 legacy compatibility", "Legacy Graph lacking root outputTarget may derive it from graph.targetEntity; legacy SQL lacking it returns null. Re-save under the new content schema creates a new immutable version."]
Method & Notes | 22 | ["T-253 picker", "Enumerate ICanonicalEntityCatalog through a minimal existing-authoring-support read endpoint. Do not use MappingDefinitionService.AllowedTargetEntities and do not add MaterialUnit as global UA-08 vocabulary."]
Method & Notes | 23 | ["T-259 ruling", "Option A accepted: 2h P1 Release Evidence Envelope v1 contract after T-251 and before T-252/T-257. T-227 stays P5 scorecard/policy owner."]
Method & Notes | 24 | ["Dirty-tree checkpoint", "Unrelated Documentation/audit dirt does not mean T-243 source exists. T-253 may proceed only with clean owned product paths, strict path staging and T-244 ancestor proof; task-number preflight filename must be renamed semantically before commit."]
Method & Notes | 25 | ["T-259 count correction", "Skipped tests are not executed. Envelope v1 requires total_count=executed_count+skipped_count and executed_count=passed_count+failed_count."]
Method & Notes | 26 | ["T-227 ownership check", "v2.20.2 already removed the accidental schema ownership from T-227. Its 6h remains because that was the original scorecard/policy task size; no funded hours were transferred out. Stale T-252/T-257 references to T-227 fields are corrected to T-259."]
Method & Notes | 27 | ["Projection-target predicate", "Do not enumerate every mapped entity and do not use schema-only eligibility. T-253 creates one explicit model/type-sourced projection-target capability; catalog identity stays CLR canonical name."]
Method & Notes | 28 | ["T-251 relationship", "T-251 logical-family catalogue later cross-checks the projection-target capability but does not define runtime target eligibility; T-253 can proceed independently."]
Method & Notes | 29 | ["T-256 dependency", "T-253 is intentionally hard in T-256 Depends On. If T-253 is late, Worker 1 stops after T-252 and CENTRAL selects a disjoint lane."]
Method & Notes | 30 | ["T-260 trigger", "T-251 runner is valid/deterministic, but its fresh reference DB exposed an incomplete builder path (EF+scripts without required topology/views)."]
Method & Notes | 31 | ["T-260 execution", "Build a disposable candidate using the canonical order first; only replace/recreate ppiq_acceptance_empty after candidate GREEN. Never mutate ppiq_app/ppiq_presentation."]
Method & Notes | 32 | ["T-251 resume", "After T-260, rerun catalogue from scratch. The old 106 unclassified / 81 public-offender counts are diagnostic history, not classification input."]
Method & Notes | 33 | ["Platform allowlist", "`public.__EFMigrationsHistory` is platform migration bookkeeping and may be allowlisted in T-251 after the corrected rebuild; dead assumed-pattern rules should be removed rather than preserved."]
Method & Notes | 34 | ["Capability standard", "Product capability mapping follows PPIQ_Product_Analysis_and_Evaluation_Standard_v1.1 (10 layers, 78 capability points)."]
Method & Notes | 35 | ["Primary mapping law", "Every product task has one Primary Capability ID. Secondary IDs are used only where task acceptance genuinely advances another capability."]
Method & Notes | 36 | ["Task closure law", "Closing mapped tasks does not make a capability 5/5. D1–D5 product evidence remains the completeness authority."]
Method & Notes | 37 | ["Non-capability work", "Pure execution instruments may use NO-CAP — Execution Tooling; product-boundary work is labelled explicitly rather than forced into a PPIQ capability."]
Method & Notes | 38 | ["Summary-sheet authority", "Backlog + Current Authority + Capability Map v1.1 are current for v2.21.0. Existing v220 dashboard/phase summary sheets are preserved snapshots and must not override task rows or capability mapping."]
Requirement Traceability | 1 | ["Design ↔ Backlog Mirror — Product Requirement Traceability", null, null, null, null, null, null, null, null, null]
Requirement Traceability | 2 | [null, null, null, null, null, null, null, null, null, null]
Requirement Traceability | 3 | ["Requirement family", "Design authority", "M2 Release 1", "M3 Release 2", "Primary tasks", "M2 acceptance", "M3 acceptance", "Customer use", "Mirror state", "Ruling"]
Requirement Traceability | 4 | ["DB Link / external databases", "Ch3 4.5 + Ch4 5.0.0", "Day-1 production", "Scale/certification", "T-207; T-247; T-254; T-095..105", "Connect→browse→preview→map→import→canonical with no product-code diff; capability/certification copy comes from one executable truth", "Real-source endurance and complex relationship certification", "Customer IT day 1", "MIRRORED", "M2 first priority"]
Requirement Traceability | 5 | ["Canvas / SQL / data preparation", "Ch4 5.0.0 + 5.2", "Day-1 production core", "Advanced authoring parity", "T-241..246; T-253; T-248", "Typed Canvas/SQL, governed output target, validate/dry-run, save/version, Job bind; no hardcoded plant/material output identity", "Scoped measure, named states, advanced story/export/subflow parity", "Customer IT day 1", "MIRRORED", "No unbounded loops"]
Requirement Traceability | 6 | ["Jobs / scheduling / logs", "Ch4 5.3 + Ch6 runtime", "Day-1 run/schedule/monitor/log", "High-volume lanes/capacity", "T-106..111; T-125; T-245; T-227", "Registered executors, target/version, DAG, bounded admission/parallelism, run/monitor/log with mandatory run identity", "Capacity, scan amplification, checkpoint/resume under heavy load", "Customer IT day 1", "MIRRORED", "Core in M2, scale in M3"]
Requirement Traceability | 7 | ["Enterprise BI/HMI", "Ch3 pages + Ch4 5.0.0/5.1", "Enterprise core", "Advanced parity", "T-148; T-202..205; T-212; T-215; T-222; T-250; T-257; T-258; T-248", "Associative/persisted enterprise core, frontend execution truth, and generic customer HMI with material-specific surfaces bounded to presentation compatibility; advanced BI parity in Release 2.", "75-item matrix fully closed incl advanced states/story/export", "All users day 1", "MIRRORED", "Qlik-class outcome, PPIQ semantics"]
Requirement Traceability | 8 | ["Production OPC UA", "Ch2 OT boundary + Ch6 edge", "Read-only production path", "Endurance/certification", "T-207; T-224..226; T-153", "Real session/browse/subscription/quality/timestamps/spool-to-canonical", "Real-source endurance and site certification", "Operations week 1", "MIRRORED", "No fake sample claim"]
Requirement Traceability | 9 | ["Performance Reference", "Ch3/Ch4 reference authority", "Visible and usable", "Deeper scale/authoring", "T-214; T-232; T-215", "Customer standard/target/envelope visible with correct scoring direction", "Advanced authoring and large-scale governance", "Operations/Quality", "MIRRORED", "Reference can be 100% aim"]
Requirement Traceability | 10 | ["Reconciliation / root cause", "Ch3/Ch4 evidence authority", "Historical + live evidence", "Persisted/advanced", "T-217..223; T-221", "Seven evidence states + causal confidence + grounded explanation", "Canonical persistence at scale and richer workflows", "Operations/Quality", "MIRRORED", "Never claim human intent/lie"]
Requirement Traceability | 11 | ["Assistant / LLM", "Ch4 Layer-B + Assistant contracts", "Grounded investigation", "InsightBoard composition", "T-179..181; T-223; T-138; T-228..230", "Governed tools/evidence; no material-specific KPI authority; provider labels require concrete adapters/conformance", "Auto-generated governed investigation boards", "All analytical users", "MIRRORED", "LLM never invents plant numbers"]
Requirement Traceability | 12 | ["Multi-objective best practice", "Ch4 practice intelligence", "Foundation available", "Full Pareto/product integration", "T-171..176; T-238..240", "Underlying kernels available; not Release-1 blocker", "Objective sets, Pareto/non-dominance, trade-off explanation", "Operations/CEO", "MIRRORED", "No hidden weights"]
Requirement Traceability | 13 | ["Transition / stabilisation", "Ch3/Ch4 regime context", "Correctness gate", "Scale/learning integration", "T-234..236; T-235", "Findings state stable/transition/stabilising/mixed and refuse unsafe pooling", "Extended real-data calibration", "Operations/Quality", "MIRRORED", "Prevents confident wrong correlation"]
Requirement Traceability | 14 | ["Financial value / ROI", "Ch1 value promise + Ch4/Ch6 Value Engine", "Existing potential-value evidence may be shown bounded", "Customer-grade realised ROI", "T-164; existing value engine + T-237", "No ungoverned monetary promise", "Real assumptions, realised-value ledger, heavy-use value certification", "CEO", "MIRRORED", "M3 owns customer-certified €/$ value"]
Requirement Traceability | 15 | ["Users / roles / licence / security", "Ch3/Ch6 administration/security", "Minimum production-safe controls", "Deep enterprise administration", "T-112..121; T-161..162; T-198..200", "RLS behavioral proof, fail-closed eight-role mapping, vendor-held licence trust root, secret/config/MFA hygiene", "SSO, advanced admin/logging/retention/site hardening", "Admin/IT", "MIRRORED", "Important but not allowed to starve Day-1 workbench"]
Requirement Traceability | 16 | ["Database schema authority / physical dictionary", "Ch3 4.5.2/4.5.5b/4.5.20a", "Zero-unknown fresh schema + upgrade reconciliation", "Heavy-use schema evolution and compatibility-safe convergence", "T-087; T-088; T-115; T-123; T-251; T-252; T-256; T-258", "Zero-unknown physical catalogue + disposable certification DBs + backend runtime three-schema/genericity convergence + frontend consumer handoff with no cross-owner mutation.", "Schema evolution remains generated, reversible where possible and customer-operable at scale", "Developer + Customer IT", "MIRRORED", "Table count is not a defect; unowned/undocumented authority is."]
Requirement Traceability | 17 | ["Repository / audit / release-truth source authority", "Governance + Ch6 release truth", "Forward-clean source authority and truthful executed gates", "Sustained release governance", "T-205; T-250; T-255; T-257; T-150; T-249", "Root allowlist; no transient run-state/pack payload; audit severity excludes self/backups/generated; gate scripts execute, release profile zero unapproved skips", "Same rules remain green under Release-2 production certification", "Developer / Customer IT", "MIRRORED", "No mass-renaming of grandfathered task-ID files; forward gate prevents new violations"]

## Dashboard v222
PLANTPROCESS IQ ¦ BACKLOG v2.23.0
15Sep2026 evidence/cell review • historical closure separated from widened scope • source-history review incomplete
Metric | M2 | M3 | Total | Interpretation | Status | M2 | M3
Active tasks | 115 | 72 | 187 | 176 repaired baseline tasks + 3 UI design tasks | Done | 62 | 0
Done | 62 | 0 | 62 | T-099 final terminal transcript corroborated | In Progress | 3 | 0
In progress | 3 | 0 | 3 | Partial current scopes; see baseline/extension evidence | Not Started | 50 | 72
Not started | 50 | 72 | 122 | No inferred implementation completion
Usable scope estimates | 872 | 649 | 1521 | Partial estimate sum; stale and missing figures excluded
Usable open estimates | 299 | 649 | 948 | Scope estimates, not measured hours remaining
Estimates unresolved | 26 | 13 | 39 | 27:8 missing/withdrawn +19 stale-scope figures
CRITICAL HANDOFF — T-262
Depends: T-253; T-243 → Must precede: T-261; T-245; T-247
T-099: task CLOSED GREEN; Gate O keeps 1 exact inherited DefinitionKind RED. Follow-up is T-115, not reopening T-099.
v2.23.0 • reviewed15Sep2026. Cell checks do not replace ten-session evidence; see Review15Sep.
B4 monitoring: T-101 UI + T-125 operational API. Fixture/BOM/known-red follow-up: T-115.

## Contract Handoffs
Consumer | Producer | Consumer release | Producer release | Type | Required evidence | Status
T-148 | T-196 | M2 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-148 | T-197 | M2 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-148 | T-198 | M2 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-148 | T-199 | M2 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-148 | T-200 | M2 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-148 | T-265 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-148 | T-266 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-265 | T-099 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-265 | T-106 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-265 | T-253 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-265 | T-262 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-265 | T-101 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-265 | T-125 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-266 | T-224 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-266 | T-225 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-266 | T-226 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-266 | T-233 | M2 | M2 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-248 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-263 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-264 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-196 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-197 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-198 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-199 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-267 | T-200 | M3 | M3 | CONTRACT_READY — not completion | Frozen route/field/state/permission/response semantics from chapter and producer; identity + revision/evidence reference required. | Record per-surface contract evidence; do not wait for full producer closure
T-261 | T-100 | M2 | M2 | COMPLETION + MUTATION LOCK — NOT CONTRACT-ONLY | Final T-100 commit SHA; exact closure/cleanup evidence; then one bounded delta over shared producer/runtime/migration surfaces. PROJECTION_* / PV01..PV15 / JOB_EXEC_* boundaries preserved. | HELD — Runner 1 GREEN and DB build reported; live certification/commit not yet supplied.

## Estimate Review
Task Id | Prior hours | Prior AI P80 h | Disposition | Owner | Recorded hours (may be stale) | Current estimate state
T-106 | 16 | 1.8 | WITHDRAWN — widened scope requires owner re-estimation | Worker 3 | 12 | RE-ESTIMATE REQUIRED
T-108 | 8 | 1.2 | WITHDRAWN — widened scope requires owner re-estimation | Worker 1 |  | RE-ESTIMATE REQUIRED
T-262 |  |  | UNESTIMATED — owner calibration required | Worker 2 |  | UNESTIMATED
T-263 |  |  | UNESTIMATED — owner calibration required | Worker 2 |  | UNESTIMATED
T-264 |  |  | UNESTIMATED — owner calibration required | Worker 3 |  | UNESTIMATED
T-265 | 40 | 40 | FABLE PROPOSAL ONLY — unconfirmed, not accepted P80; withheld from live sums | Worker 2 |  | UNCONFIRMED DESIGN ESTIMATE
T-266 | 16 | 16 | FABLE PROPOSAL ONLY — unconfirmed, not accepted P80; withheld from live sums | Worker 2 |  | RE-ESTIMATE REQUIRED — v4.11.0 visual scope delta
T-267 | 32 | 32 | FABLE PROPOSAL ONLY — unconfirmed, not accepted P80; withheld from live sums | Worker 2 |  | UNCONFIRMED DESIGN ESTIMATE
T-101 | 12 | 2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 2 | 12 | RE-ESTIMATE REQUIRED
T-103 | 6 | 0.9 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 6 | RE-ESTIMATE REQUIRED
T-104 | 14 | 1.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 14 | RE-ESTIMATE REQUIRED
T-235 | 8 | 3.4 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 8 | RE-ESTIMATE REQUIRED
T-243 | 12 | 4.8 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 2 | 12 | RE-ESTIMATE REQUIRED
T-254 | 6 | 2.55 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 2 | 6 | RE-ESTIMATE REQUIRED
T-113 | 8 | 1.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 8 | RE-ESTIMATE REQUIRED
T-121 | 16 | 1.8 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 16 | RE-ESTIMATE REQUIRED
T-123 | 14 | 3.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 14 | RE-ESTIMATE REQUIRED
T-110 | 24 | 1.8 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 24 | RE-ESTIMATE REQUIRED
T-155 | 12 | 4.32 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 3 | 12 | RE-ESTIMATE REQUIRED
T-159 | 12 | 4.32 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 3 | 12 | RE-ESTIMATE REQUIRED
T-116 | 8 | 1.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 8 | RE-ESTIMATE REQUIRED
T-248 | 30 | 11.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 2 | 30 | RE-ESTIMATE REQUIRED
T-145 | 8 | 1.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 3 | 8 | RE-ESTIMATE REQUIRED
T-146 | 10 | 1.5 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 3 | 10 | RE-ESTIMATE REQUIRED
T-165 | 12 | 7.2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 1 | 12 | RE-ESTIMATE REQUIRED
T-186 | 12 | 1.8 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 3 | 12 | RE-ESTIMATE REQUIRED
T-190 | 12 | 2 | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Worker 3 | 12 | RE-ESTIMATE REQUIRED
SOURCE-BASED REMAINING WORK — nominal engineer-hours, unconfirmed; not original task Hours or AI P80
Task ID | Review level | Low h | Base h | High h | Basis / exclusions | Remaining work | Source refs
T-095 | SOURCE CORROBORATES CLOSED FOUNDATION | 0 | 0 | 0 | Closed original scope; zero remaining here does not certify downstream Canvas integration. T-243 consumes existing publication authority. | No new implementation within the accepted original task scope is established here. Canvas publication wiring is owned by the later T-243 addition, not reopening this foundation. | Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — PublishAsync Backend/PlantProcess.Application/Relationships/RelationshipService.cs:218-260 — ValidateDeclaration
T-096 | SOURCE CORROBORATES CLOSED FOUNDATION | 0 | 0 | 0 | Original resolver/convergence closure retained; no rebuilding cost. | No new work is assigned to this closed convergence slice. Live downstream execution remains a separate consumer acceptance and is not proven by this source read. | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:34-113 — ResolveAsync Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-96 — ConsumerFamilies
T-097 | SOURCE CORROBORATES CLOSED GUARD | 0 | 0 | 0 | No remaining original implementation; avoid counting unwired later engines against this completed guard. | Keep the original barrier task closed. New consumers must pass it; their runtime wiring belongs to their own integration tasks. | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:12-44 — barrier semantics Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-114 — consumer and forbidden-authority inventory
T-098 | REUSABLE BACKEND PRESENT; CANONICAL UI NOT LOCATED | 6 | 9 | 14 | UI 4/6/9 + contract/negative tests 1/2/3 + targeted closure 1/1/2. Reuse all relationship producer work. Do not duplicate T-095..T-097 or charge their work here. | Build C6 list/detail/path/validation views against existing services, including ambiguity, preferred-path and refusal evidence; add frontend/API-contract tests and one runtime acceptance. | Backend/PlantProcess.Api/Endpoints/Relationships/RelationshipEndpoints.cs:21-92 — MapRelationshipEndpoints Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:62-113 — path results
T-099 | CLOSED SCOPE PRESERVED; SOURCE CORROBORATES | 0 | 0 | 0 | T-099 CLOSED GREEN at ca02b40e; its inherited DefinitionKind RED is not a reason to budget a rewrite. | Zero remaining inside T-099's closed first-eight-PV scope. PV09–PV15, full replay/update semantics, monitoring and exact weight semantics remain with T-100/T-101/T-104/T-103. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:141-181 — MapMaterialUnitAsync Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — bounded reprocess surface Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:3-20 — narrow topology correction
T-100 | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | UNCONFIRMED | UNCONFIRMED | UNCONFIRMED | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs.
T-101 | PARTIAL REUSE; CURRENT EXPANDED SCOPE OPEN | 12 | 18 | 28 | Read API/filter/detail 3/4/6 + B4/C2/C3 UI 4/6/10 + drift/retry integration 3/5/8 + tests/closure 2/3/4. T-106 owns run-outcome semantics; T-125 owns operational data/health; do not bill those twice. | Add bounded list/detail by code/dataset/batch and source lineage, extend the existing reprocess path, persist/display mapped-column drift, and B4 batch/error/durable-cursor monitoring. Validate API, UI and failure recovery. | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — MapQuarantineEndpoints Backend/PlantProcess.Application/Integration/Services/Staging/StagingRecordService.cs:85-110 — durable staging identity
T-102 | EXISTING ALIAS FOUNDATION; IDENTITY-SAFETY GAP | 4 | 7 | 12 | Scope-safe lookup/merge 2/4/7 + ambiguity/idempotency tests 1/2/4 + closure 1/1/1. Do not recreate alias tables or the full row projector. | Reuse alias persistence; resolve by governed tenant/site/source/key scope, refuse ambiguity, reconcile two source identifiers into one material and prove idempotent re-import with same alias text across sources/sites. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:244-264 — MapMaterialAliasAsync Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:721-744 — ResolveMaterialIdAsync Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialAliasConfiguration.cs:27-36 — composite unique Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialUnitConfiguration.cs:43-47 — site/source uniqueness
T-103 | SUBSTANTIAL FOUNDATION; ACCEPTANCE-CONTRACT MISMATCH | 4 | 6 | 10 | Weight-contract correction 1/2/3 + direct-DB/traversal negatives 2/3/5 + closure 1/1/2. Existing cycle logic is not new work. Weight semantics/negative acceptance stay T-103; 841 topology repair remains accepted. | Retain cycle/self-edge implementation; prove DB direct-write cycle controls and both traversal directions, then reconcile exact declared weight semantics with the 0.015 inherited tolerance and add the explicit 0.99 negative case. | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:27-69 — CreateEdgeAsync Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:95-124 — WouldCreateCycleAsync Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:55-68 — deferred weight check
T-104 | REPLAY FOUNDATION IS NOT VERSIONED REPROJECTION | 8 | 14 | 22 | Row-version/provenance integration 3/5/8 + replay/rollback semantics 3/6/10 + negative tests/closure 2/3/4. T-261 owns first resolved-target runtime call and executor; T-104 owns row effects and rollback proof after it. | On top of the T-261 executor, prove canonical row/run version provenance, idempotent accepted effects and rollback-to-version business equivalence. Reuse first-eight-PV/quarantine infrastructure; do not implement a second executor. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:168-181 — existing-row skip Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-249 — ResolveDeclaredTargetAsync
T-106 | ORIGINAL CONTRACT CLOSED; EXPANDED RUNTIME OBLIGATIONS OPEN | 18 | 28 | 44 | Schedule/parser/due-work 8/12/18 + freshness/outcome policy 4/6/10 + cancellation consumer integration 2/4/6 + targeted service/DB tests and runner 4/6/10. Original completed contracts excluded. T-261 owns executor implementation, first RecordResolvedTarget and common cancellation seam. T-106 owns schedule/DAG/outcome semantics; no double estimate of executor. | Implement the v4.10.3 schedule contract/parser/due dispatch, explicit freshness policy, truthful aggregate outcomes and cancellation coordination. Reuse the original target/DAG work; T-261 commissions the shared executor/cancellation seam and this task consumes it, not a competing runtime. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobDefinitionService.cs:275-297 — schedule validation Backend/PlantProcess.Workers/Worker.cs:72-108 — fixed cadence loops Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:33-39 — no age/tolerance input Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:85-91 — Satisfied result Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-146 — terminal-state switch Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:262-276 — import result mapping
T-107 | TIMERS EXIST; GOVERNED JOB POOLS NOT ESTABLISHED | 12 | 20 | 32 | Pool/admission implementation 6/10/16 + lane/worker integration 3/5/8 + saturation/cancel/closure tests 3/5/8. T-155/T-159 calibrate heavy-production constants later; no retraining or new scheduler here. | Add actual bounded job queues/pool slots and dual-predicate resource admission, isolation of three ML lanes, backpressure and exact cancellation/release behavior; test saturation and interactive reservation without inventing production capacity constants. | Backend/PlantProcess.Workers/Worker.cs:72-108 — ExecuteAsync cadence Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:76-107 — family capability vs capacity
T-108 | IMPLEMENTED DELTA FOUNDATION WITH CONFIRMED CORRECTNESS GAPS | 22 | 34 | 52 | Tuple contract+reader adaptations 8/12/18 + budget enforcement 4/6/9 + durable staging/replay+projection token 5/8/13 + adverse-boundary tests/closure 5/8/12. T-106 owns Job aggregate status; T-101 B4 UI; T-109 consumes this watermark; no duplicate billing for those consumers. | Implement total-order cursor/tie-key semantics for every supported incremental reader, typed invariant comparisons, per-source effective budget on incremental calls, durable checkpoint/replay identity and projection watermark handoff. Do not recreate source/staging infrastructure already present. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — read-path selection Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — row/cursor handling Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:236-280 — source identity and MaxCursor Backend/PlantProcess.Infrastructure/Connectors/PostgreSql/PostgreSqlConnector.cs:181-206 — scalar LIMIT query Backend/PlantProcess.Application/Integration/Protection/ThrottlingDataSourceReader.cs:36-70 — unequal protection Backend/PlantProcess.Infrastructure/Integration/Protection/OptionsSourceLoadBudgetProvider.cs:21-24 — global budget Backend/PlantProcess.Infrastructure/Persistence/Configurations/Integration/StagingRecordConfiguration.cs:31-42 — existing within-batch uniqueness Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:58-73 — current weak continuation assertions
T-109 | REUSABLE CALCULATION FOUNDATION; DELTA CONSUMER NOT PROVEN | 6 | 10 | 18 | Scope resolution/integration 3/5/9 + telemetry/handoff 1/2/4 + idempotent/late-data tests 2/3/5. T-108 owns source/projection checkpoint; M3 materializers own full training artifacts. | Consume T-108's committed batch/delta token, materialize changed subjects through governed relations, refresh bounded feature/analysis scope and telemetry, and emit the ML handoff. Prove late data and interrupted retries without a second cursor store. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-217 — available source delta boundary Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:85-113 — governed automated path
T-207 | SOURCE CORROBORATES CLOSED TRUTH CONTRACT | 0 | 0 | 0 | Closed honesty contract retained; separate future live acquisition. | No original T-207 reimplementation. New backend provider-list convergence belongs to expanded T-254; live OPC operations belong to T-224..T-226. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — HistorianConnectorCapabilities
T-212 | AUTHORITY EXISTS; PRODUCTION QUERY CONSUMPTION GAP | 6 | 9 | 14 | Query integration 3/5/8 + known-answer/refusal tests 2/3/4 + closure 1/1/2. T-211 computes math; T-210 governs semantics; T-212 wires actual queries. | Wire the existing semantics authority into Layer-A widget/query execution and consume the T-211 arithmetic contract. Preserve declared weighting/sampling/null rules, typed refusals and result evidence; do not implement a new aggregation authority. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — ResolveAsync Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — not analytics mathematics
T-213 | SOURCE CORROBORATES CLOSED PRODUCER | 0 | 0 | 0 | Original producer closure retained; no duplicate intake engine. | No new work within the accepted T-213 authority scope. Customer intake use within the real UI journey remains the consumer's acceptance, not reopening this producer. | Backend/PlantProcess.Api/Endpoints/CustomerAssessmentEndpoints.cs:86-125 — assessment routes and tenant gate
T-224 | CONFIGURATION FOUNDATION ONLY; LIVE SESSION UNCOMMISSIONED | 10 | 16 | 26 | Session/client/trust implementation 5/8/13 + collector lifecycle 2/4/7 + negative/security/closure tests 3/4/6. Vendor access delays excluded. T-225 browse/subscription; T-226 end-to-end data/recovery; T-266 design. No M3 deferral. | Implement real read-only OPC endpoint/session/certificate lifecycle on the customer-side collector, with governed trust references, security-policy rejection, reconnect and safe telemetry. Reuse configuration/capability contracts, not their success text as handshake proof. | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration test Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — live capability declarations
T-225 | LIVE ACQUISITION OPERATIONS NOT COMMISSIONED | 10 | 16 | 26 | Browse/registration 3/5/8 + monitored-item/read lifecycle 4/6/10 + limits/refusal/closure tests 3/5/8. Do not recreate session security or count T-266 graphics as real read proof. | Build namespace browse, stable node identities, tag registration, bounded read/subscriptions and monitored-item lifecycle using the T-224 session and source-load policy; test partial browse, disconnect and invalid intervals. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:76-95 — browse/read/subscription capability state Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:53-70 — metadata-only legacy claim
T-226 | SPOOL/TIME FOUNDATIONS; LIVE END-TO-END PROOF MISSING | 10 | 16 | 28 | Quality/time/canonical adapter 3/5/9 + spool/ack/recovery 4/6/11 + interruption/replay acceptance 3/5/8. No new time-authority kernel; no reuse of demo telemetry as customer-source proof. | Integrate source/server/ingest time and quality handling, spool/ack/reconnect/gap recovery and idempotent canonical replay using T-233/T-224/T-225; run controlled interruption and real-source evidence. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — upstream live-operation boundary Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — existing time kernel
T-232 | TARGET AUTHORITY NOT LOCATED IN SUPPLIED SNAPSHOT | 5 | 8 | 13 | Persistence/resolution adapter 2/4/7 + projections/refusal tests 2/3/4 + closure 1/1/2. T-214 owns reference decision kernel; T-215 consumes BI projections; a negative symbol search alone is not live absence proof. | Implement effective-dated reference persistence, precedence/provenance and governed projections consuming T-214; test overlapping definitions, missing direction/unit and deterministic read-back. Do not reimplement the T-214 decision kernel. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — existing semantic infrastructure only
T-233 | TIME KERNEL EXISTS; PERSISTENCE/CONSUMER WORK REMAINS | 5 | 8 | 14 | Persistence/API adapter 2/3/6 + consumer binding 1/2/4 + ambiguity/timezone tests/closure 2/3/4. Do not charge T-216 kernel work again; OPC T-226 consumes the approved time contract. | Persist declared time authority and observation provenance, bind acquisition/projector consumers to the existing kernel, and prove zone/offset/uncertainty conflict handling without machine-locale fallback. | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-97 — Resolve / ResolveAs Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:184-210 — current material time fields
T-235 | KERNELS COMPLETE; CURRENT PRODUCTION INTEGRATION OPEN | 6 | 11 | 18 | Persistence/regime adapter 2/4/7 + live-statistics integration 2/4/6 + adversarial tests/closure 2/3/5. Do not redo T-234/T-236; later broad engine convergence stays T-146. | Persist transition/stabilisation declarations and wire current M2 statistical/correlation pooling to the existing guard. Include source-time uncertainty and explicit undeclared-regime handling; prove the live path refuses mixed/uncertain populations. | Backend/PlantProcess.Analytics.Core/Kernel/Regime/TransitionAwarePoolingGuard.cs:24-79 — Admit Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — time interpretation
T-241 | SOURCE CORROBORATES CLOSED GRAPH CONTRACT | 0 | 0 | 0 | Closed graph contract; zero original remainder. | Retain original typed-port/graph-validation closure. Any actual execution or visual-depth remainder belongs to T-245/T-261/T-265, not recreation of the T-241 graph model. | Frontend/PlantProcess.Web/src/authoring/graphSemantics.ts:22-40 — typed-port authority Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — capability separation
T-242 | CLOSED CONTRACT; DOWNSTREAM EXECUTION NOT IMPLIED | 0 | 0 | 0 | Closed library/contract scope, not all future execution. Do not convert missing downstream execution into a new T-242 estimate. | Original algebra/catalogue/validation closure remains closed. Persistence/compilation/runtime integration is the relevant downstream work and must retain honest unavailable states until accepted. | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — one catalogue and separate capabilities Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — handoff boundary Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:49-77 — AG01 behavior
T-243 | ORIGINAL REOPEN CLOSED; ADDITIONAL PUBLICATION INTEGRATION OPEN | 5 | 9 | 15 | Declared relationship adapter 2/4/7 + atomic/rollback and compatibility tests 2/4/6 + closure 1/1/2. Reopen board work costs zero here. Do not implement a second relationship store. T-262 save-mapping concern is tracked once there, not charged again. | Only the added relationship-emission/atomicity/legacy-path convergence remains: derive declared relationships, publish through the existing service in the correct unit of work, and prove rollback/read-back. Preserve the saved-board implementation and its closure. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — canonical graph/board content Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:265-333 — publish transaction Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — existing publication seam
T-244 | SOURCE CORROBORATES CLOSED SQL FOUNDATION | 0 | 0 | 0 | Closed SQL validation/persistence scope only. | Keep the original T-244 closure. The later projection-binding callback concern belongs to the T-262 consumer boundary, and runtime transformation execution belongs to T-261. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:173-205 — ForSql Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:297-333 — SQL publish path Frontend/PlantProcess.Web/src/api/canvasApi.ts:118-155 — SQL run/save API adapter
T-245 | BINDING WORK NOT COMMISSIONED; REUSE PRODUCER CONTRACTS | 6 | 10 | 16 | Binding/API/UI 3/5/8 + evidence/cancel views 1/2/4 + integration/negative tests 2/3/4. T-261 owns executor and block-evidence storage, T-106 schedule/outcome policy; do not count those implementations again. | Implement the thin Canvas-to-job binding/launch/monitor/error/cancel surface over T-261's real executor, carry exact version and stable block IDs, and test unavailable-family refusal before launch. | Frontend/PlantProcess.Web/src/api/canvasApi.ts:111-155 — current save/preview/publish surface Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-124 — non-executable target families
T-247 | RELEASE ACCEPTANCE NOT EXECUTABLE BEFORE PRODUCERS | 8 | 14 | 22 | Fixture/setup/data preparation 2/4/6 + actual connected acceptance and evidence 4/7/11 + triage/replay/closure 2/3/5; remediation implementation excluded. No source-code or drawing count can close runtime acceptance; no duplicate budget for T-106/T-108/T-261 fixes. | After producer closures, execute one customer-shaped real-source-to-canonical-to-BI/Assistant journey with immutable-version/retry/cancel/refusal/isolation evidence and zero customer-specific product diff. Budget acceptance coordination only; bugs remain with their owning tasks. | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — concrete broken journey seam Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:32-73 — earlier tests are not full new journey proof
T-253 | SOURCE CORROBORATES CLOSED OUTPUT CONTRACT | 0 | 0 | 0 | Original target authority closed; no duplicate estimate. | No new original output-target work. Preserve original 7a6f91f9 closure; downstream publication and executor consume that authority. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — ForGraph outputTarget/board Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — strict compatibility
T-254 | ORIGINAL SURFACES CLOSED; BACKEND CONVERGENCE REMAINDER | 2 | 4 | 7 | Backend authority extraction/delegation 1/2/4 + consumer mismatch tests/closure 1/2/3. Original frontend/website work excluded. No rewrite of T-207, no source availability invented from a certification flag. | Complete only the widened backend validation/catalogue convergence and regression tests ensuring profile validation, API truth, UI and website consume one result. Retain frontend/website original closure and absence-of-fallback evidence. | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:17-39 — duplicate provider DTO source Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:81-102 — OPC flags Backend/PlantProcess.Application/Integration/Connectors/ConnectorProviderCatalog.cs:72-104 — second catalog OPC/SAP entries
T-261 | CONTRACTS PRESENT; EXECUTOR NOT APPLIED IN PROVIDED SNAPSHOT | 16 | 26 | 42 | Compiler/dispatch 3/5/8 + executor/write/evidence 6/10/17 + cancellation integration 2/3/5 + Graph/SQL/live Gate0/replay/cancel tests and closure 5/8/12. Do not implement a new schedule or PV taxonomy. Common cancellation seam billed once here; T-106 handles policy/endpoint coordination. | Extract/reuse the compiler; implement resolver+executor, carry the pre-admission target into the real run, canonical row effects/idempotency/provenance and stable block evidence, common cancellation/status wiring; run Graph/SQL and failure/cancel proof on disposable DB. Include T-262 live Gate 0 once. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — admission before real run Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-276 — discarded resolution/dispatch Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — uncommissioned executor Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-149 — terminal lifecycle
T-262 | ORIGINAL CONTRACT CLOSED; NARROW CONSUMER VERIFICATION OPEN | 1 | 3 | 6 | Real-shell reproduction 1/1/2 + bounded callback correction if confirmed 0/1/2 + focused regression/closure 0/1/2. Consumer Gate0 cost counted in T-261. T-261 owns disposable Gate0 and commissioned projection execution. The executable-book dependency remains until owner confirms acceptance boundary; do not silently mark Done. | Do not rebuild the declaration. Reproduce the mapping-only SQL-save transition against the real shell, fix only any demonstrated stale callback, and run targeted field-map tests. Live definition-store Gate 0 is already assigned to T-261 Runner2, so it is not estimated again here. Final status remains current-scope open until this correction/acceptance is resolved. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:118-163 — immutable projection content Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — unknown/narrowing refusal Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:898-925 — doSaveSql callback inputs/dependencies
T-113 | SOURCE REVIEWED — IMPLEMENTATION GAPS / RELEASE RUNTIME UNVERIFIED | 12 | 20 | 32 | Credential boundary+tests 5/8/13; profile/route guards 4/7/11; redaction/deployment verification 3/5/8. T-121 owns DI/quota logic; T-123 install/upgrade; this estimate covers their security gate, not reimplementation. | Close accepted-input, persistence and response secret boundaries with sentinel tests; replace vacuous setup returns; validate the actual release-profile bootstrap/MFA/seed/legacy-route boundary and log/audit redaction. Preserve explicit development-only behaviour. | Backend/PlantProcess.Infrastructure/Connectors/ConnectorCredentialResolver.cs:16-51 — Resolve Backend/tests/PlantProcess.Api.IntegrationTests/Security/T08ConnectorSecretMaskingIntegrationTests.cs:19-46 — Connector_password_is_masked_on_readback Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — dev route refusal
T-121 | BOUNDED SOURCE REVIEW — METER/UI REMAINDER NEEDS DEEPER TRACE | 10 | 18 | 30 | DI and entitlement reconciliation 2/3/5; meters/quota surfaces 5/10/17; acceptance/negative tests 3/5/8. T-113 release profile gate; T-165 pricing/cost model, not licence enforcement. | Reconcile to one effective licence authority, implement or complete the declared F2/F3 role/user meters and thresholds, and execute tamper/expiry/meter/no-lost-draft acceptance. Do not build a new signing authority or reclassify the development route as a production mint. | Backend/PlantProcess.Api/SignedLicensing/VerifiedEd25519LicenseService.cs:10-60 — feature/tier authority Backend/PlantProcess.Api/Program.cs:725-744 — licence DI Backend/PlantProcess.Application/DependencyInjection.cs:58-63 — legacy DI Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — development guard
T-123 | BOUNDED SOURCE REVIEW — DEPLOYMENT EXECUTION UNVERIFIED | 12 | 20 | 36 | Path/ledger convergence 4/7/12; populated-upgrade/rollback tests 5/8/15; clean-host profile/non-root proof 3/5/9. T-113 security policy is consumed, not re-estimated here. | Converge the shipped install/upgrade path onto the canonical ledger, preserve populated data, prove failed-upgrade/rollback recovery and non-root runtime for the selected deployment. Audit actual production selection rather than deleting development tooling blindly. | deploy/scripts/ppiq.ps1:3-20 — command contract deploy/scripts/ppiq.ps1:44-63 — profile/path selection Backend/database/canonical-migration-order.json:1-20 — canonical ledger
T-110 | BOUNDED SOURCE REVIEW — ADVANCED RUNTIME GAP | 16 | 28 | 44 | Chunk/receipt persistence 6/10/16; resume/merge/enforcement 6/11/17; interruption/parallelism tests 4/7/11. T-108/109 M2 delta; T-155 measured thresholds; T-159 site certification. No waits/soak included. | Implement persistent row/byte-bounded chunks, pinned inputs, receipt-atomic progress, interruption resume, deterministic merge and cumulative scan-budget abort. Reuse the M2 source-cursor/replay work rather than implementing it twice. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — existing incremental reader use Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — batch/cursor persistence Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — existing admission/run boundary
T-155 | SOURCE FOUNDATION REVIEWED — SITE MEASUREMENTS UNVERIFIED | 8 | 14 | 24 | Workload/hook setup 3/5/8; measurement orchestration/analysis 3/5/9; governed result publication 2/4/7. T-110 enforcement implementation and T-159 certification reruns are distinct. | Integrate site workloads with those harnesses, collect training/batch/online latency and amplification evidence, and publish measured limits. Do not invent measured capacity from fixture outputs or replace the existing evidence contract. | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:20-36 — benchmark metadata Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:32-75 — SelectedValueGuard
T-159 | FOUNDATION REVIEWED — CAPACITY CERTIFICATION NOT EXECUTED | 8 | 16 | 28 | Profile preparation 3/6/10; certification operation/analysis 3/6/11; reconciliation/sign-off evidence 2/4/7. No reimplementation of T-110 or calibration billed again from T-155. | Prepare reproducible C1-C4 workloads, consume T-155 calibration, exercise the T-110 negative controls, reconcile measured sizing examples and capture sign-off without accepting fixture data as production measurements. | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:43-81 — evidence guard Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:65-90 — B-01..B-09 registry
T-116 | BOUNDED SOURCE REVIEW — ROUTE-WIDE CENSUS NOT COMPLETE | 8 | 14 | 24 | Consumer/route inventory 3/5/8; safe dual routing and consumer convergence 3/5/9; parity/negative tests 2/4/7. Do not remove compatibility objects before all live consumers and upgrade paths converge. | Resolve every active old/new route and compatibility consumer, dual-serve only lawful semantic equivalents, test response/permission parity and keep historical handles readable before retiring consumers/objects. | Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:16-66 — provenance dispatch and run resolution Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:69-90 — source/dataset existence lookup
T-248 | BOUNDED SOURCE REVIEW — ALL 75 OUTCOMES NOT CERTIFIED | 24 | 40 | 64 | Remaining outcome mapping 4/6/10; advanced UI/runtime integration 14/24/38; parity/accessibility/recovery acceptance 6/10/16. T-267 designs; T-248 implementation; T-249 release acceptance. Existing T-204 selection closure retained. | Complete the unfulfilled advanced outcome rows, native-grain drill, named/comparison states, concurrency recovery and server-owned persistence; wire G3/G6 consistently. Freeze the precise remaining matrix before code and reuse existing selection/history/validator behaviour. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:1-55 — state and query orchestration Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — reopen application
T-263 | SOURCE REVIEWED — SUBSTANTIAL REPORT FOUNDATION / LIFECYCLE GAP | 16 | 26 | 42 | Definition/editor/history 6/10/16; job/output/delivery integration 6/10/16; permission/empty/fidelity/retry tests 4/6/10. T-106 scheduler and generic delivery components not recreated; fixtures alone cannot prove scheduled delivery. | Add governed report definition/version/sections/period, shared-job generation, output history, tenant-scoped download and delivery retries/audit; reuse existing PDF/evidence materialisation. Use the same scheduler, never a private report scheduler. | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report routes Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:57-85 — existing report service/PDF path
T-145 | SOURCE REVIEWED — CANONICAL LOOP MISSING / LEGACY CONFLICT | 14 | 24 | 40 | Canonical persistence/evaluation 6/10/17; feedback/poisoning/escalation rules 5/8/13; migration/negative tests 3/6/10. T-190 D6 cutover; T-113 M2 denial; no double price of the same endpoint removal. | Implement canonical-only outcomes, durable evaluation/effectiveness records, intervention-aware metrics, feedback eligibility/concentration evidence and controlled Supervisor input. Retire the contradictory writer safely after replacement and preserve legitimate history. | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — manual outcome DTO Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:66-90 — record calculation Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-48 — process-memory endpoints
T-146 | SOURCE REVIEWED — PRIOR DEAD-FILE FINDING DISPROVEN | 8 | 14 | 24 | Pairing/result-contract cutover 3/5/9; producer/persistence convergence 3/5/8; known-answer/refusal regression 2/4/7. T-186 persistent capability authority; this task consumes it and does not implement a second profile store. | Wire the certified pairing/refusal kernel into real producers, align persistence/readiness/evidence and consolidate genuinely duplicate paths after consumer migration. Preserve the live discipline functions; do not delete StatisticalDiscipline.cs based on its filename or a zero-hit search for a nonexistent class. | Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:49-62 — readiness/old selector Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:91-115 — live discipline calls Backend/PlantProcess.Application/Analytics/Advanced/AdvancedCorrelationComputeService.cs:117-137 — live ranking/FDR/bootstrap Backend/PlantProcess.Analytics.Core/Kernel/KernelMethodSelector.cs:27-57 — kernel pairing
T-165 | BOUNDED SOURCE REVIEW — CALCULATOR NOT ESTABLISHED | 8 | 14 | 24 | Formula/input authority 3/5/8; sales calculator surface/integration 3/5/9; known-answer/refusal tests 2/4/7. T-121 entitlement differs from commercial pricing; T-155 supplies measurement constants. | Implement explicit units/currency/time assumptions, the separate infrastructure-cost and licence-price formulae, governed input validation and known-answer quote checks against measured capacity. | Website/PlantProcess.Website/src/components/proof/PricingLicenseMatrix.tsx:1-49 — plan display Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:17-26 — selected measured value identity
T-186 | SOURCE REVIEWED — KERNEL REUSABLE / PERSISTENCE AND WIRING GAP | 8 | 14 | 24 | Persistence/versioning 3/5/9; point/governor/consumer integration 3/5/8; deterministic/negative tests 2/4/7. T-171 kernel closed; do not reopen. T-146 consumes the commissioned authority. | Persist versioned outcome/grain/manifest-scoped profiles, connect governed prediction-point candidates/model-count limits and use one readiness authority for producers. Prove deterministic rich/sparse decisions and missing-data refusals. | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:8-19 — pure kernel boundary Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:36-64 — profile calculation Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:69-96 — dimension assessment
T-190 | BOUNDED SOURCE REVIEW — CANONICAL D6 CUTOVER UNVERIFIED | 8 | 14 | 24 | Canonical DTO/permission wiring 3/5/9; D6 state/history cutover 3/5/8; continuity/tampering tests 2/4/7. T-145 owns outcome/effectiveness persistence; this task consumes it. M2 route denial owned by T-113. | Bind the actual D6 controls to canonical eligibility and decision records, enforce can_accept on the server, preserve actor/reason history and cut over legacy routes with continuity/negative tests. | Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-43 — legacy write path Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — caller outcome schema
T-264 | SOURCE REVIEWED — LEGACY DEMO IS NOT TARGET IMPLEMENTATION | 10 | 18 | 30 | Registry/comparison service 4/7/12; result surface/evidence/export 3/6/10; BM01/BM02/tenant tests 3/5/8. T-214/T-240 semantics reused; no industry taxonomy or a second practice engine. | Implement registered population/period comparisons with real counts, BM01/BM02, direction-aware normalisation and context-comparable own-best practice; preserve evidence/export and tenant isolation. | Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:17-35 — demo dashboard Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:50-85 — generated bands
T-265 | SOURCE + DELIVERED UI DATA REVIEWED — DESIGN DEPTH/PROTOTYPE NOT ACCEPTED | 28 | 44 | 68 | Semantic/fixture mapping 6/10/15; connected M2 flows 16/24/37; native import/RTL/focus/Word synchronization 6/10/16. T-266 OPC design; T-267 M3 design; runtime implementation remains its own task. | Complete the M2 semantic control/transition matrix, selected source/join/output inspector states, refused/recovery paths and labelled realistic fixtures; execute the specified native import/prototype checks and update only Chapters 3/4 MD+Word and workbook coverage. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — existing associative control semantics Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — existing reopen model PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE.
T-266 | DESIGN TASK STILL OPEN; MOCKUP DOES NOT PROVE RUNTIME | 6 | 10 | 16 | Flow/state specification 2/4/6 + detailed visual/prototype integration 2/3/5 + semantic acceptance/handoff 2/3/5. No backend implementation counted. T-224..T-226 implement/live-certify; T-233 time authority; native design execution availability is a separate uncertainty. | Design the named OPC profile/browse/read/subscription/quality/time/spool/replay flow and its unavailable states against T-224..T-226 contracts, integrate into Chapter3/4 and embedded Word images, and execute one observed design import/prototype check without claiming live OPC. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — actual unavailable contract Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration interface
T-267 | BOUNDED SOURCE + UI INVENTORY REVIEW — M3 DESIGN REMAINDER | 24 | 40 | 64 | M3 requirement/producer mapping 5/8/13; advanced connected flows 14/24/38; native/RTL/coverage/chapter checks 5/8/13. No basic selection/clear deferred from M2; no duplicate generic frame batch treated as acceptance. | Design the complete M3 remainder against the existing 75-outcome matrix, producer contracts and accepted M2 flows, including advanced states, conflict/recovery, exports and G3/G6. Verify the native scenes and synchronize the two illustrated chapters. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — M2 behaviour to preserve Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report subset, not full E5 PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE.

## Repair Changes v2221
Task Id | Column | Field | Rejected v2.22.0 | Corrected v2.22.1 | Reason
T-086 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-086 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-086 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-087 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-087 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-087 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-088 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-088 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-088 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-089 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-089 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-089 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-090 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-090 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-090 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-091 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-091 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-091 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-092 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-092 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-092 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-093 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-093 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-093 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-094 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-094 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-094 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-201 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-201 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-201 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-202 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-202 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-202 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-203 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-203 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-203 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-204 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-204 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-204 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-205 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-205 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-205 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-206 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-206 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-206 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-208 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-208 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-208 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-209 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-209 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-209 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-210 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-210 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-210 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-216 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-216 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-216 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-231 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-231 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-231 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-250 | M | Depends On (IDs only) | T-057; T-089; T-090; T-094 | T-205 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-250 | N | Must Precede (IDs only) | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-114; T-128; T-134; T-183; T-196; T-221 | T-150; T-255; T-257; T-258 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-250 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-250 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-250 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-251 | M | Depends On (IDs only) | T-095 | T-087; T-088; T-260 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-251 | N | Must Precede (IDs only) | T-097; T-098; T-107; T-109; T-128; T-134; T-183; T-221 | T-112; T-150; T-252; T-256; T-259 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-251 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-251 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-251 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-252 | M | Depends On (IDs only) | T-096 | T-087; T-088; T-251; T-259 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-252 | N | Must Precede (IDs only) | T-098; T-107; T-109; T-128; T-183 | T-106; T-112; T-150; T-256 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-252 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-252 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-252 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-256 | M | Depends On (IDs only) | T-095; T-096; T-097 | T-088; T-094; T-251; T-252; T-253 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-256 | N | Must Precede (IDs only) | T-107; T-109; T-128; T-183 | T-116; T-150; T-247; T-258 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-256 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-256 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-256 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-259 | M | Depends On (IDs only) | T-087; T-089; T-090 | T-251 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-259 | N | Must Precede (IDs only) | T-100; T-101; T-104; T-107; T-108; T-109; T-114; T-128; T-183; T-261 | T-150; T-227; T-252; T-257 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-259 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-259 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-259 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-260 | M | Depends On (IDs only) | T-099 | T-088 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-260 | N | Must Precede (IDs only) | T-101; T-107; T-109; T-128; T-183 | T-251 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-260 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-260 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-260 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-095 | M | Depends On (IDs only) | T-099; T-100 | T-057; T-089; T-090; T-094 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-095 | N | Must Precede (IDs only) | T-107; T-109; T-128; T-183 | T-096; T-098; T-102; T-103; T-104; T-107; T-109; T-114; T-128; T-134; T-183; T-196; T-221 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-095 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-095 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-095 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-096 | M | Depends On (IDs only) | T-087; T-095 | T-095 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-096 | N | Must Precede (IDs only) | T-103; T-107; T-109; T-128; T-183 | T-097; T-098; T-107; T-109; T-128; T-134; T-183; T-221 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-096 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-096 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-096 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-097 | M | Depends On (IDs only) | T-095; T-102 | T-096 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-097 | N | Must Precede (IDs only) | T-107; T-109; T-128; T-183 | T-098; T-107; T-109; T-128; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-097 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-097 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-097 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-098 | M | Depends On (IDs only) | T-090; T-095; T-099; T-261 | T-095; T-096; T-097 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-098 | N | Must Precede (IDs only) | T-107; T-108; T-109; T-128; T-183; T-247 | T-107; T-109; T-128; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-098 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-098 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-098 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-099 | K | Status | In Progress | Done | Owner reports final CLOSED GREEN / COMMITTED closure.
T-099 | M | Depends On (IDs only) | T-064; T-089; T-090; T-252 | T-087; T-089; T-090 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-099 | N | Must Precede (IDs only) | T-107; T-122; T-125; T-245; T-261; T-263 | T-100; T-101; T-104; T-107; T-108; T-109; T-114; T-128; T-183; T-261 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-099 | X | Tech-Lead Ruling | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. | M2 P2 — Day-1 Data Workbench — DB Link, Canvas, Jobs & OPC. Release 1 is genuine early production / first-week customer work. v2.22.1 — CLOSED GREEN / COMMITTED at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af (parent 86e1b677212195f191697ecdca7e9441b3dbde33). Preserve this closure unless a concrete later regression is demonstrated. Gate O has one exact inherited DefinitionKind RED and canonical replay limitations remain; this is not Release-wide GREEN. | Supersede stale build-state wording without rewriting original acceptance or replaying the task.
T-099 | Y | Commit String |  | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af | Exact SHA supplied by owner.
T-099 | AI | Capability Evidence |  | Owner-provided final runner report in this conversation, received 14-Sep-2026; not independently rerun or verified against a live Git checkout here. Live acceptance 49/49; catalogue 5/5; owned contract 19/19; cleanup 6/6, survivors 0. Gate O: 900 = 899 passed + 1 exact inherited DefinitionKind RED; 900 unique testId and executionId. Exact staging/byte boundary passed; cleanup before one semantic commit. Task closure GREEN, not release-wide GREEN; canonical replay limitations remain separately tracked. | Preserve positive closure and known-red caveat separately.
T-099 | AO | Evidence State |  | CLOSED GREEN / COMMITTED — owner-reported | Owner final runner verdict; no automatic reopening.
T-099 | AP | Closure Evidence Basis |  | Owner-provided final runner report in this conversation, received 14-Sep-2026; not independently rerun or verified against a live Git checkout here. Live acceptance 49/49; catalogue 5/5; owned contract 19/19; cleanup 6/6, survivors 0. Gate O: 900 = 899 passed + 1 exact inherited DefinitionKind RED; 900 unique testId and executionId. Exact staging/byte boundary passed; cleanup before one semantic commit. Task closure GREEN, not release-wide GREEN; canonical replay limitations remain separately tracked. | Evidence provenance explicitly reported, not newly executed.
T-099 | AQ | Parent Commit |  | 86e1b677212195f191697ecdca7e9441b3dbde33 | Exact parent SHA supplied by owner.
T-099 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-100 | M | Depends On (IDs only) | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-106 | T-099 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-100 | N | Must Precede (IDs only) | T-122; T-125; T-141; T-187; T-192 | T-101; T-107; T-109; T-128; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-100 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-100 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-100 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-101 | H | Task Description | Complete the C2 Mapping Health page against Chapter 3 4.4 C2: issues grouped by code, example rows, and Reprocess after the mapping is corrected. The M1 version delivered the shape; this delivers the full class set and the retry semantics. v2.22.0 — Quarantine inspection API/UI and schema-drift enforcement. Keep one drift event authority and reuse current schemas/compatibility safely. | Complete the C2 Mapping Health page against Chapter 3 4.4 C2: issues grouped by code, example rows, and Reprocess after the mapping is corrected. The M1 version delivered the shape; this delivers the full class set and the retry semantics. v2.22.0 — Quarantine inspection API/UI and schema-drift enforcement. Keep one drift event authority and reuse current schemas/compatibility safely. v2.22.1 — Own the M2 B4 Importing monitoring surface as well as C2 quarantine/Mapping Health: show each real batch status, failure code/reason, progress/counts, last committed cursor and its watermark range; drill into durable batch/run evidence. Use the existing canonical import/job contracts. T-106 owns terminal-status truth; T-108 owns durable cursor/replay; T-125 owns operational metrics/API observability. No second status or cursor authority and no advanced M3 recovery UI is introduced. | Close explicitly reported B4 monitoring ownership gap in the existing Worker-2 UI task.
T-101 | I | Task Validation | Quarantine rows under three different codes, correct one mapping, reprocess, and confirm only the affected rows clear. The M1 continuity snapshot of this page must still match. v2.22.0 — GET quarantine list/detail filtered by code, dataset and batch with staging lineage/correction hint; tenant denial; remove mapped source object/field -> typed execution refusal and persisted C2 event; corrected reprocess uses declared version and records outcome. | Quarantine rows under three different codes, correct one mapping, reprocess, and confirm only the affected rows clear. The M1 continuity snapshot of this page must still match. v2.22.0 — GET quarantine list/detail filtered by code, dataset and batch with staging lineage/correction hint; tenant denial; remove mapped source object/field -> typed execution refusal and persisted C2 event; corrected reprocess uses declared version and records outcome. v2.22.1 — Drive B4 against a successful batch, a failed batch and a capped/partial batch; displayed outcome, counts, error and last committed cursor equal the canonical response after reload. A failed batch is never green; a retry/correction links to the same durable evidence. Tenant denial and empty/loading/failure states are asserted. Consume frozen T-106/T-108/T-125 response contracts for parallel UI work; final live integration is certified by T-247/T-150, not by a mock-only result. | Substantive M2 monitoring acceptance; integration proof does not create a completion cycle.
T-101 | M | Depends On (IDs only) | T-099; T-104 | T-099; T-100 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-101 | N | Must Precede (IDs only) | T-109; T-110; T-247 | T-107; T-109; T-128; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-101 | AC | Secondary Capability IDs | L1.6; L1.2 | L1.6; L1.2; L1.7 | Map the actual additional acceptance obligation.
T-101 | AJ | Estimate Basis | Inherited estimate; scope changed — re-estimation required | Inherited estimate; scope changed — re-estimation required v2.22.1 acceptance/ownership clarification; owner to review planning impact. | Add explicit evidence / estimation provenance in repair revision.
T-101 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-101 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-101 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-102 | M | Depends On (IDs only) | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-108 | T-087; T-095 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-102 | N | Must Precede (IDs only) | T-110; T-136; T-187 | T-103; T-107; T-109; T-128; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-102 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-102 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-102 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-103 | M | Depends On (IDs only) | T-108; T-109 | T-095; T-102 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-103 | N | Must Precede (IDs only) | T-249 | T-107; T-109; T-128; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-103 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-103 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-103 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-104 | M | Depends On (IDs only) | T-201 | T-090; T-095; T-099; T-261 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-104 | N | Must Precede (IDs only) | T-150; T-224; T-247; T-254 | T-107; T-108; T-109; T-128; T-183; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-104 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-104 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-104 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-106 | J | Hours | 16 |  | Old estimate no longer represents enlarged scope; preserve prior value in Estimate Review.
T-106 | M | Depends On (IDs only) | T-202; T-210; T-211; T-092; T-234; T-235; T-236 | T-064; T-089; T-090; T-252 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-106 | N | Must Precede (IDs only) | T-150; T-247 | T-107; T-122; T-125; T-245; T-261; T-263 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-106 | R | AI Guarded Time P80 (h) | 1.8 |  | Derived planning time is also invalid until re-estimated.
T-106 | AJ | Estimate Basis | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — prior Hours/P80 preserved in Estimate Review; not zero remaining effort. | Prevent inflated confidence in inherited estimate.
T-106 | AM | Has estimate | 1 | 0 | Add explicit evidence / estimation provenance in repair revision.
T-106 | AO | Evidence State |  | In progress — closure not recorded | Add explicit evidence / estimation provenance in repair revision.
T-106 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-106 | AR | Estimate Status |  | RE-ESTIMATE REQUIRED | Add explicit evidence / estimation provenance in repair revision.
T-107 | M | Depends On (IDs only) | T-201; T-206 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-106 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-107 | N | Must Precede (IDs only) | T-227; T-247 | T-122; T-125; T-141; T-187; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-107 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-107 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-107 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-108 | J | Hours | 8 |  | Old estimate no longer represents enlarged scope; preserve prior value in Estimate Review.
T-108 | M | Depends On (IDs only) | T-207 | T-099; T-104 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-108 | N | Must Precede (IDs only) | T-153; T-225 | T-109; T-110; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-108 | R | AI Guarded Time P80 (h) | 1.2 |  | Derived planning time is also invalid until re-estimated.
T-108 | AJ | Estimate Basis | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — prior Hours/P80 preserved in Estimate Review; not zero remaining effort. | Prevent inflated confidence in inherited estimate.
T-108 | AM | Has estimate | 1 | 0 | Add explicit evidence / estimation provenance in repair revision.
T-108 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-108 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-108 | AR | Estimate Status |  | RE-ESTIMATE REQUIRED | Add explicit evidence / estimation provenance in repair revision.
T-109 | M | Depends On (IDs only) | T-224 | T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-108 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-109 | N | Must Precede (IDs only) | T-153; T-226 | T-110; T-136; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-109 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-109 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-109 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-207 | M | Depends On (IDs only) | T-225; T-233 | T-201 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-207 | N | Must Precede (IDs only) | T-150; T-153 | T-150; T-224; T-247; T-254 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-207 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-207 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-207 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-212 | M | Depends On (IDs only) | T-090; T-231; T-214 | T-202; T-210; T-211; T-092; T-234; T-235; T-236 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-212 | N | Must Precede (IDs only) | T-215 | T-150; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-212 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-212 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-212 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-213 | M | Depends On (IDs only) | T-087; T-090; T-216 | T-201; T-206 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-213 | N | Must Precede (IDs only) | T-221; T-226 | T-227; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-213 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-213 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-213 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-224 | M | Depends On (IDs only) | T-090; T-231; T-234 | T-207 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-224 | N | Must Precede (IDs only) | T-164; T-212; T-237; T-247 | T-153; T-225 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-224 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-224 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-224 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-225 | M | Depends On (IDs only) | T-032; T-201 | T-224 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-225 | N | Must Precede (IDs only) | T-242; T-243; T-247; T-248; T-253; T-261 | T-153; T-226 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-225 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-225 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-225 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-226 | M | Depends On (IDs only) | T-241; T-210 | T-225; T-233 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-226 | N | Must Precede (IDs only) | T-243; T-247; T-261 | T-150; T-153 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-226 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-226 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-226 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-232 | M | Depends On (IDs only) | T-241; T-242; T-089; T-090; T-253 | T-090; T-231; T-214 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-232 | N | Must Precede (IDs only) | T-245; T-246; T-247; T-248; T-261; T-262 | T-215 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-232 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-232 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-232 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-233 | M | Depends On (IDs only) | T-035; T-036; T-089; T-090 | T-087; T-090; T-216 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-233 | N | Must Precede (IDs only) | T-245; T-247; T-248; T-253 | T-221; T-226 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-233 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-233 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-233 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-235 | M | Depends On (IDs only) | T-243; T-244; T-106; T-261 | T-090; T-231; T-234 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-235 | N | Must Precede (IDs only) | T-247; T-248 | T-164; T-212; T-237; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-235 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-235 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-235 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-241 | M | Depends On (IDs only) | T-243; T-130; T-137; T-187 | T-032; T-201 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-241 | N | Must Precede (IDs only) | T-249 | T-242; T-243; T-247; T-248; T-253; T-261 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-241 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-241 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-241 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-242 | M | Depends On (IDs only) | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235 | T-241; T-210 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-242 | N | Must Precede (IDs only) | T-150 | T-243; T-247; T-261 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-242 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-242 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-242 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-243 | M | Depends On (IDs only) | T-094; T-209; T-241; T-244 | T-241; T-242; T-089; T-090; T-253 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-243 | N | Must Precede (IDs only) | T-150; T-243; T-247; T-256; T-262 | T-245; T-246; T-247; T-248; T-261; T-262 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-243 | AO | Evidence State |  | In progress — closure not recorded | Add explicit evidence / estimation provenance in repair revision.
T-243 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-243 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-244 | M | Depends On (IDs only) | T-207 | T-035; T-036; T-089; T-090 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-244 | N | Must Precede (IDs only) | T-150; T-153; T-247 | T-245; T-247; T-248; T-253 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-244 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-244 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-244 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-245 | M | Depends On (IDs only) | T-094; T-250; T-256 | T-243; T-244; T-106; T-261; T-262 | Restore explicit T-262 handoff stated in the approved proposal; also mirror in Must Precede.
T-245 | N | Must Precede (IDs only) | T-150; T-247 | T-247; T-248 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-245 | T | AI Start / Dependency Gate | Consume accepted producer contracts; remaining dependencies: T-243; T-244; T-106; T-261. No private scheduler/definition authority. Source-present is not closure proof. | Consume accepted producer contracts; remaining dependencies: T-243; T-244; T-106; T-261. No private scheduler/definition authority. Source-present is not closure proof. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Align consumer start gate with repaired task-keyed columns.
T-245 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-245 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-245 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-247 | I | Task Validation | A test asserting every page file under src/pages is reachable from a declared route. The count of page files moves toward 40 and no orphan remains. v2.10.2 TARGET-INVENTORY GATE — do not merely prove every existing page file is reachable or that the count 'moves toward 40'. Assert the exact Chapter 3 inventory: all 40 target route pages are declared once at canonical routes, all 6 global shell components are present, no target route is missing, and no orphan page file remains. Any temporary legacy alias must have a named retirement owner. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | One end-to-end evidence pack proves zero C# diff, zero TypeScript diff and zero product-SQL diff; configuration/metadata only. The customer-shaped journey completes through product surfaces and replays deterministically. The evidence pack also proves the customer-facing connector availability text comes from executable capability truth, the authored output target is customer-shaped/governed, and no unapproved material-specific/public-schema runtime dependency is required. | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-247 | M | Depends On (IDs only) |  | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235; T-262; T-125 | B4 end-to-end acceptance waits for operational observability; T-101 may implement against the contract first.
T-247 | N | Must Precede (IDs only) | T-248 | T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-247 | T | AI Start / Dependency Gate | R1 route inventory and six shell contracts frozen. Contract-ready handoffs from T-196/T-197/T-198/T-199/T-200 are recorded separately in column AN. Do not wait for the entire M3 implementation or ship a simulated M3 page. | T-213 complete + T-092 green. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Align consumer start gate with repaired task-keyed columns.
T-247 | V | No-Rework Handoff Ruling | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | If onboarding requires C#/TypeScript/product-SQL changes, stop and raise a generic product gap; do not patch around it. | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-247 | AN | Contract-ready predecessors (not completion) | T-196; T-197; T-198; T-199; T-200 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-247 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-247 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-247 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-253 | M | Depends On (IDs only) | T-092; T-214; T-232 | T-094; T-209; T-241; T-244 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-253 | N | Must Precede (IDs only) | T-150; T-222 | T-150; T-243; T-247; T-256; T-262 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-253 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-253 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-253 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-254 | M | Depends On (IDs only) | T-219; T-220; T-215; T-203; T-204 | T-207 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-254 | N | Must Precede (IDs only) | T-150 | T-150; T-153; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-254 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-254 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-254 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-261 | M | Depends On (IDs only) |  | T-106; T-241; T-242; T-243; T-099; T-262 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-261 | N | Must Precede (IDs only) | T-122; T-138; T-246 | T-104; T-245 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-261 | T | AI Start / Dependency Gate | Consume accepted producer contracts; remaining dependencies: T-106; T-241; T-242; T-243; T-099; T-262. No private scheduler/definition authority. Source-present is not closure proof. | Consume accepted producer contracts; remaining dependencies: T-106; T-241; T-242; T-243; T-099; T-262. No private scheduler/definition authority. Source-present is not closure proof. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Align consumer start gate with repaired task-keyed columns.
T-261 | AO | Evidence State |  | In progress — closure not recorded | Add explicit evidence / estimation provenance in repair revision.
T-261 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-261 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-262 | M | Depends On (IDs only) |  | T-253; T-243 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-262 | N | Must Precede (IDs only) | T-122; T-175; T-187 | T-245; T-247; T-261 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-262 | T | AI Start / Dependency Gate | Consume accepted producer contracts; remaining dependencies: T-253; T-243. No private scheduler/definition authority. Source-present is not closure proof. | Consume accepted producer contracts; remaining dependencies: T-253; T-243. No private scheduler/definition authority. Source-present is not closure proof. v2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns. | Align consumer start gate with repaired task-keyed columns.
T-262 | AI | Capability Evidence | Estimate pending owner calibration; no completion or runtime proof inferred from this row. | Source present / unclosed. Exact accepted closure commit and runtime acceptance are not supplied; existing implementation must not be recreated merely because closure is unverified. | Do not conflate estimate note with closure evidence.
T-262 | AJ | Estimate Basis | UNESTIMATED — new row; no hours inferred from source presence | UNESTIMATED — new/recognized task; owner calibration pending. | Blank is unknown effort, not zero.
T-262 | AO | Evidence State |  | SOURCE PRESENT / UNCLOSED — closure unverified | Distinguish existing source from accepted closure.
T-262 | AP | Closure Evidence Basis |  | 14-Sep source export and current review establish source presence. No accepted closure SHA/run supplied; not counted Done. | Clarify source-present state.
T-262 | AR | Estimate Status |  | UNESTIMATED | Add explicit evidence / estimation provenance in repair revision.
T-148 | I | Task Validation | A test asserting every page file under src/pages is reachable from a declared route. The count of page files moves toward 40 and no orphan remains. v2.10.2 TARGET-INVENTORY GATE — do not merely prove every existing page file is reachable or that the count 'moves toward 40'. Assert the exact Chapter 3 inventory: all 40 target route pages are declared once at canonical routes, all 6 global shell components are present, no target route is missing, and no orphan page file remains. Any temporary legacy alias must have a named retirement owner. | A test asserting every page file under src/pages is reachable from a declared route. The count of page files moves toward 40 and no orphan remains. v2.10.2 TARGET-INVENTORY GATE — do not merely prove every existing page file is reachable or that the count 'moves toward 40'. Assert the exact Chapter 3 inventory: all 40 target route pages are declared once at canonical routes, all 6 global shell components are present, no target route is missing, and no orphan page file remains. Any temporary legacy alias must have a named retirement owner. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. v2.22.1 — v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | Restore the contract-only ruling to T-148; reject its misplaced copy on T-247.
T-148 | N | Must Precede (IDs only) | T-175; T-184; T-187 | T-248 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-148 | T | AI Start / Dependency Gate | M1 continuity frozen + all target-route implementation owners available, incl... | R1 route inventory and six shell contracts frozen. Contract-ready handoffs from T-196/T-197/T-198/T-199/T-200 are recorded separately in column AN. Do not wait for the entire M3 implementation or ship a simulated M3 page. | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-148 | V | No-Rework Handoff Ruling | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. | Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-148 | AN | Contract-ready predecessors (not completion) |  | T-196; T-197; T-198; T-199; T-200 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-148 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-148 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-148 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-215 | M | Depends On (IDs only) |  | T-092; T-214; T-232 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-215 | N | Must Precede (IDs only) | T-185; T-187 | T-150; T-222 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-215 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-215 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-215 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-222 | M | Depends On (IDs only) |  | T-219; T-220; T-215; T-203; T-204 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-222 | N | Must Precede (IDs only) | T-131; T-186; T-187 | T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-222 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-222 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-222 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-258 | M | Depends On (IDs only) |  | T-094; T-250; T-256 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-258 | N | Must Precede (IDs only) | T-187 | T-150; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-258 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-258 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-258 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-137 | N | Must Precede (IDs only) | T-140; T-187 | T-122; T-138; T-246 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-137 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-137 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-137 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-168 | N | Must Precede (IDs only) | T-187 | T-122; T-175; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-168 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-168 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-168 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-169 | M | Depends On (IDs only) | T-168; T-169 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-169 | N | Must Precede (IDs only) | T-187 | T-175; T-184; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-169 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-169 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-169 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-170 | N | Must Precede (IDs only) | T-140; T-187; T-191 | T-185; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-170 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-170 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-170 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-171 | N | Must Precede (IDs only) | T-146; T-147 | T-131; T-186; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-171 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-171 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-171 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-172 | N | Must Precede (IDs only) | T-143 | T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-172 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-172 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-172 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-173 | N | Must Precede (IDs only) | T-138; T-223; T-228 | T-140; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-173 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-173 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-173 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-174 | N | Must Precede (IDs only) | T-138; T-223; T-228 | T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-174 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-174 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-174 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-175 | M | Depends On (IDs only) |  | T-168; T-169 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-175 | N | Must Precede (IDs only) | T-138; T-223; T-228 | T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-175 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-175 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-175 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-176 | N | Must Precede (IDs only) |  | T-140; T-187; T-191 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-176 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-176 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-176 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-177 | M | Depends On (IDs only) | T-208; T-210 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-177 | N | Must Precede (IDs only) | T-212; T-247 | T-146; T-147 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-177 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-177 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-177 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-178 | M | Depends On (IDs only) | T-209 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-178 | N | Must Precede (IDs only) | T-215; T-223; T-232; T-238; T-239; T-264 | T-143 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-178 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-178 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-178 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-179 | M | Depends On (IDs only) | T-208; T-216 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-179 | N | Must Precede (IDs only) | T-219; T-236 | T-138; T-223; T-228 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-179 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-179 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-179 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-180 | M | Depends On (IDs only) | T-208 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-180 | N | Must Precede (IDs only) | T-219 | T-138; T-223; T-228 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-180 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-180 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-180 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-181 | M | Depends On (IDs only) | T-217; T-218; T-236 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-181 | N | Must Precede (IDs only) | T-220; T-221; T-222; T-223 | T-138; T-223; T-228 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-181 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-181 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-181 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-182 | M | Depends On (IDs only) | T-219 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-182 | N | Must Precede (IDs only) | T-221; T-222; T-223 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-182 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-182 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-182 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-211 | M | Depends On (IDs only) | T-112; T-114; T-090; T-095; T-096; T-219; T-220; T-233 | T-208; T-210 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-211 | N | Must Precede (IDs only) |  | T-212; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-211 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-211 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-211 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-214 | M | Depends On (IDs only) | T-179; T-180; T-181; T-214; T-219; T-220 | T-209 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-214 | N | Must Precede (IDs only) | T-150 | T-215; T-223; T-232; T-238; T-239; T-264 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-214 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-214 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-214 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-217 | M | Depends On (IDs only) | T-208; T-209 | T-208; T-216 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-217 | N | Must Precede (IDs only) | T-212; T-235; T-236 | T-219; T-236 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-217 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-217 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-217 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-218 | M | Depends On (IDs only) | T-217; T-234 | T-208 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-218 | N | Must Precede (IDs only) | T-212; T-219 | T-219 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-218 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-218 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-218 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-219 | M | Depends On (IDs only) | T-092; T-235 | T-217; T-218; T-236 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-219 | N | Must Precede (IDs only) | T-164 | T-220; T-221; T-222; T-223 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-219 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-219 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-219 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-220 | M | Depends On (IDs only) | T-087; T-088; T-251; T-252 | T-219 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-220 | N | Must Precede (IDs only) | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | T-221; T-222; T-223 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-220 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-220 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-220 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-221 | M | Depends On (IDs only) |  | T-112; T-114; T-090; T-095; T-096; T-219; T-220; T-233 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-221 | N | Must Precede (IDs only) | T-122; T-200 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-221 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-221 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-221 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-223 | M | Depends On (IDs only) | T-087; T-089; T-090; T-095; T-099 | T-179; T-180; T-181; T-214; T-219; T-220 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-223 | N | Must Precede (IDs only) | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-223 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-223 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-223 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-234 | M | Depends On (IDs only) |  | T-208; T-209 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-234 | N | Must Precede (IDs only) | T-150 | T-212; T-235; T-236 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-234 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-234 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-234 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-236 | M | Depends On (IDs only) |  | T-217; T-234 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-236 | N | Must Precede (IDs only) | T-121; T-197; T-198; T-200 | T-212; T-219 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-236 | AO | Evidence State |  | Recorded closed — inherited evidence | Add explicit evidence / estimation provenance in repair revision.
T-236 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-236 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-237 | M | Depends On (IDs only) |  | T-092; T-235 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-237 | N | Must Precede (IDs only) |  | T-164 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-237 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-237 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-237 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-112 | M | Depends On (IDs only) | T-119 | T-087; T-088; T-251; T-252 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-112 | N | Must Precede (IDs only) | T-127 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-112 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-112 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-112 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-113 | N | Must Precede (IDs only) | T-122; T-150 | T-122; T-200 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-113 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-113 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-113 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-114 | M | Depends On (IDs only) |  | T-087; T-089; T-090; T-095; T-099 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-114 | N | Must Precede (IDs only) | T-150; T-199 | T-122; T-128; T-129; T-130; T-135; T-183; T-184; T-185; T-187; T-195; T-198; T-221; T-230 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-114 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-114 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-114 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-115 | H | Task Description | MOVED FROM M1 IN v2.3, and the move is correct on two counts. First, it fails Gate A on its own terms: the customer never sees it, and no presentation-visible feature depends on it. Second, the shape I proposed was wrong. A third PERSISTENT database is a third environment somebody has to remember to maintain, and this project already has exactly two working databases that earn their keep - ppiq_app for development and ppiq_presentation for the prepared demonstration state. Note also that ppiq_dev is a PostgreSQL LOGIN, not a database, which is worth writing down because the name invites the confusion. The correct implementation is an EPHEMERAL fixture created inside the integration test: create a uniquely named clean database, apply exactly the migrations a customer installation applies, apply NO seed, run the one-query Rule 2 proof, assert zero, then drop the database. Nothing survives the test run. The proof is the artifact; the database is not. What it protects is real: a customer's IT reviewer who opens a fresh installation and finds another company's plant rows inside it has found a dead deal, and ninety-four post-EF SQL scripts are where that could hide. | MOVED FROM M1 IN v2.3, and the move is correct on two counts. First, it fails Gate A on its own terms: the customer never sees it, and no presentation-visible feature depends on it. Second, the shape I proposed was wrong. A third PERSISTENT database is a third environment somebody has to remember to maintain, and this project already has exactly two working databases that earn their keep - ppiq_app for development and ppiq_presentation for the prepared demonstration state. Note also that ppiq_dev is a PostgreSQL LOGIN, not a database, which is worth writing down because the name invites the confusion. The correct implementation is an EPHEMERAL fixture created inside the integration test: create a uniquely named clean database, apply exactly the migrations a customer installation applies, apply NO seed, run the one-query Rule 2 proof, assert zero, then drop the database. Nothing survives the test run. The proof is the artifact; the database is not. What it protects is real: a customer's IT reviewer who opens a fresh installation and finds another company's plant rows inside it has found a dead deal, and ninety-four post-EF SQL scripts are where that could hide. v2.22.1 — Own the bounded backend acceptance-hygiene follow-up reported in the 04-Sep audit: first inspect the current T-210 fixture and the named migration byte-order marks, then fix only reproduced issues. Reuse T-252 disposable-DB policy and T-259 evidence envelope; do not reopen their proven closures. The inherited DefinitionKind mismatch reported with T-099 is a separate test-authority convergence obligation, not a T-099 regression. | Assign historical fixture/BOM and inherited known-red follow-up to an existing Worker-1 acceptance task.
T-115 | I | Task Validation | A fresh migration chain produces zero rows outside the declared prefill allowlist. The allowlist is data, at Backend/database/acceptance/rule2_prefill_allowlist.txt, so a table added later is plant data BY DEFAULT and the test goes red until somebody classifies it deliberately. The test fails if any future migration or seed introduces plant, customer or demonstration rows. The temporary database is dropped whether the assertion passes or fails. | A fresh migration chain produces zero rows outside the declared prefill allowlist. The allowlist is data, at Backend/database/acceptance/rule2_prefill_allowlist.txt, so a table added later is plant data BY DEFAULT and the test goes red until somebody classifies it deliberately. The test fails if any future migration or seed introduces plant, customer or demonstration rows. The temporary database is dropped whether the assertion passes or fails. v2.22.1 — Verify actual current file bytes before calling the historical five-BOM finding still present; keep before/after hashes when a byte repair is required. A local intentionally absent external probe may skip only with the approved named reason; Release-1 certification provisions its own disposable database and a missing fixture is RED, never a passing skip. Reconcile the inherited DefinitionKind assertion with the current canonical kind authority and assert all required members rather than merely deleting or weakening the test. Keep T-099 closed; full-release GREEN remains forbidden while its independently tracked known-red or canonical replay limitations remain unresolved. | Make findings conditional on current proof and preserve release skip-zero policy.
T-115 | M | Depends On (IDs only) | T-106; T-107 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-115 | AJ | Estimate Basis | Inherited baseline estimate | Inherited baseline estimate v2.22.1 acceptance/ownership clarification; owner to review planning impact. | Add explicit evidence / estimation provenance in repair revision.
T-115 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-115 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-115 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-119 | N | Must Precede (IDs only) | T-150 | T-121; T-197; T-198; T-200 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-119 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-119 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-119 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-120 | M | Depends On (IDs only) | T-115; T-123; T-124; T-125; T-126; T-205; T-207; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-250; T-251; T-252; T-253; T-254; T-255; T-256; T-257; T-258; T-259 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-120 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-120 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-120 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-121 | M | Depends On (IDs only) | T-213; T-259 | T-119 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-121 | N | Must Precede (IDs only) | T-150 | T-127 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-121 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-121 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-121 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-123 | M | Depends On (IDs only) | T-106; T-107; T-112; T-113; T-114; T-117; T-137; T-168; T-123 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-123 | N | Must Precede (IDs only) | T-141; T-185; T-192 | T-122; T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-123 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-123 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-123 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-124 | N | Must Precede (IDs only) |  | T-150; T-199 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-124 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-124 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-124 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-125 | I | Task Validation | Trigger each alert condition deliberately and confirm it fires with the correct severity and reaches the configured channel. Execute jobs through at least two families and prove every log/diagnostic row carries the same non-null run identity end-to-end. Induce queue saturation and show queued count/oldest age/wait time and pool utilisation change predictably. A component failure changes the canonical health state and alert; duplicate feature-specific /health routes are not required as separate authorities. | Trigger each alert condition deliberately and confirm it fires with the correct severity and reaches the configured channel. Execute jobs through at least two families and prove every log/diagnostic row carries the same non-null run identity end-to-end. Induce queue saturation and show queued count/oldest age/wait time and pool utilisation change predictably. A component failure changes the canonical health state and alert; duplicate feature-specific /health routes are not required as separate authorities. v2.22.1 — The existing operational API/log projection exposes durable batch outcome, error/code, progress/counts and last committed cursor for B4, with run/batch correlation and tenant scoping. T-101 owns the consuming UI. No view computes a replacement status from message text. Final T-247/T-150 evidence joins UI observation to these source facts. | Explicit backend observability handoff for B4, without duplicating T-106 outcome authority.
T-125 | M | Depends On (IDs only) |  | T-106; T-107 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-125 | N | Must Precede (IDs only) |  | T-150; T-247 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-125 | AC | Secondary Capability IDs |  | L1.7 | Map the actual additional acceptance obligation.
T-125 | AJ | Estimate Basis | Inherited baseline estimate | Inherited baseline estimate v2.22.1 acceptance/ownership clarification; owner to review planning impact. | Add explicit evidence / estimation provenance in repair revision.
T-125 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-125 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-125 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-126 | M | Depends On (IDs only) | T-224; T-225; T-226; T-254 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-126 | N | Must Precede (IDs only) | T-249 | T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-126 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-126 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-126 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-150 | M | Depends On (IDs only) |  | T-115; T-123; T-124; T-125; T-126; T-205; T-207; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-250; T-251; T-252; T-253; T-254; T-255; T-256; T-257; T-258; T-259 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-150 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-150 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-150 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-227 | M | Depends On (IDs only) |  | T-213; T-259 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-227 | N | Must Precede (IDs only) |  | T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-227 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-227 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-227 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-255 | M | Depends On (IDs only) |  | T-205; T-250 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-255 | N | Must Precede (IDs only) | T-249 | T-150 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-255 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-255 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-255 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-257 | M | Depends On (IDs only) |  | T-205; T-250; T-259 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-257 | N | Must Precede (IDs only) | T-249 | T-150; T-248 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-257 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-257 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-257 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-110 | M | Depends On (IDs only) |  | T-108; T-109 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-110 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-110 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-110 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-122 | M | Depends On (IDs only) | T-256 | T-106; T-107; T-112; T-113; T-114; T-117; T-137; T-168; T-123 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-122 | N | Must Precede (IDs only) |  | T-141; T-185; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-122 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-122 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-122 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-151 | N | Must Precede (IDs only) | T-122; T-194 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-151 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-151 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-151 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-152 | M | Depends On (IDs only) | T-196; T-197; T-198; T-199; T-200; T-121 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-152 | N | Must Precede (IDs only) | T-194 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-152 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-152 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-152 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-153 | M | Depends On (IDs only) |  | T-224; T-225; T-226; T-254 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-153 | N | Must Precede (IDs only) |  | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-153 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-153 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-153 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-154 | N | Must Precede (IDs only) | T-249 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-154 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-154 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-154 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-155 | N | Must Precede (IDs only) | T-249 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-155 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-155 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-155 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-159 | M | Depends On (IDs only) | T-117; T-127 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-159 | N | Must Precede (IDs only) |  | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-159 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-159 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-159 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-160 | M | Depends On (IDs only) | T-087; T-094; T-095 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-160 | N | Must Precede (IDs only) | T-127 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-160 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-160 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-160 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-163 | M | Depends On (IDs only) | T-119; T-198 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-163 | N | Must Precede (IDs only) | T-127 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-163 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-163 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-163 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-116 | M | Depends On (IDs only) | T-112; T-114; T-119 | T-256 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-116 | N | Must Precede (IDs only) | T-127; T-197; T-199 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-116 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-116 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-116 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-117 | M | Depends On (IDs only) | T-124; T-198 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-117 | N | Must Precede (IDs only) | T-127 | T-122; T-194 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-117 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-117 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-117 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-127 | M | Depends On (IDs only) | T-113; T-119; T-216 | T-196; T-197; T-198; T-199; T-200; T-121 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-127 | N | Must Precede (IDs only) | T-127 | T-194 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-127 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-127 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-127 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-149 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-149 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-149 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-161 | N | Must Precede (IDs only) |  | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-161 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-161 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-161 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-162 | M | Depends On (IDs only) | T-090; T-092; T-134; T-179; T-180; T-181 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-162 | N | Must Precede (IDs only) | T-229; T-248 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-162 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-162 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-162 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-194 | M | Depends On (IDs only) | T-228; T-134 | T-117; T-127 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-194 | N | Must Precede (IDs only) | T-230 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-194 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-194 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-194 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-196 | M | Depends On (IDs only) | T-229; T-112; T-114 | T-087; T-094; T-095 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-196 | N | Must Precede (IDs only) | T-249 | T-127 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-196 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-196 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-196 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-197 | M | Depends On (IDs only) | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257 | T-119; T-198 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-197 | N | Must Precede (IDs only) | T-249; T-263 | T-127 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-197 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-197 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-197 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-198 | M | Depends On (IDs only) | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114; T-231; T-210 | T-112; T-114; T-119 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-198 | N | Must Precede (IDs only) | T-129; T-130; T-131; T-135; T-146; T-147; T-184; T-186 | T-127; T-197; T-199 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-198 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-198 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-198 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-199 | M | Depends On (IDs only) | T-128; T-183; T-112; T-114 | T-124; T-198 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-199 | N | Must Precede (IDs only) | T-134; T-135; T-146; T-147; T-186; T-188 | T-127 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-199 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-199 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-199 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-200 | M | Depends On (IDs only) | T-128; T-183; T-112; T-114 | T-113; T-119; T-216 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-200 | N | Must Precede (IDs only) | T-134; T-135; T-139; T-188; T-191; T-193; T-246 | T-127 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-200 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-200 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-200 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-156 | M | Depends On (IDs only) | T-086; T-128; T-171 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-156 | N | Must Precede (IDs only) | T-132; T-133; T-136; T-142; T-240 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-156 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-156 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-156 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-166 | M | Depends On (IDs only) | T-131 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-166 | N | Must Precede (IDs only) | T-133; T-136; T-142; T-240 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-166 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-166 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-166 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-228 | M | Depends On (IDs only) | T-131; T-132; T-183 | T-090; T-092; T-134; T-179; T-180; T-181 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-228 | N | Must Precede (IDs only) | T-134; T-136; T-240 | T-229; T-248 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-228 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-228 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-228 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-229 | M | Depends On (IDs only) | T-090; T-095; T-096; T-129; T-130; T-133; T-186; T-139 | T-228; T-134 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-229 | N | Must Precede (IDs only) | T-138; T-228; T-229 | T-230 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-229 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-229 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-229 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-230 | M | Depends On (IDs only) | T-112; T-114; T-128; T-129; T-130; T-183 | T-229; T-112; T-114 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-230 | N | Must Precede (IDs only) | T-184; T-185; T-186; T-187 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-230 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-230 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-230 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-248 | M | Depends On (IDs only) | T-131; T-132; T-133; T-109 | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-248 | N | Must Precede (IDs only) |  | T-249; T-263 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-248 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-248 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-248 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-263 | M | Depends On (IDs only) | T-179; T-180; T-181; T-137; T-134; T-188 | T-106; T-248 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-263 | N | Must Precede (IDs only) |  | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-263 | AJ | Estimate Basis | UNESTIMATED — new row; no hours inferred from source presence | UNESTIMATED — new/recognized task; owner calibration pending. | Blank is unknown effort, not zero.
T-263 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-263 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-263 | AR | Estimate Status |  | UNESTIMATED | Add explicit evidence / estimation provenance in repair revision.
T-128 | M | Depends On (IDs only) | T-130; T-187; T-231 | T-087; T-088; T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114; T-231; T-210 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-128 | N | Must Precede (IDs only) | T-134; T-140; T-141; T-142; T-189; T-193 | T-129; T-130; T-131; T-135; T-146; T-147; T-184; T-186 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-128 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-128 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-128 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-129 | M | Depends On (IDs only) | T-139; T-173; T-176 | T-128; T-183; T-112; T-114 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-129 | N | Must Precede (IDs only) | T-142; T-189 | T-134; T-135; T-146; T-147; T-186; T-188 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-129 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-129 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-129 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-130 | M | Depends On (IDs only) | T-107; T-122; T-139; T-187 | T-128; T-183; T-112; T-114 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-130 | N | Must Precede (IDs only) | T-189 | T-134; T-135; T-139; T-188; T-191; T-193; T-246 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-130 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-130 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-130 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-131 | M | Depends On (IDs only) | T-131; T-132; T-139; T-140 | T-086; T-128; T-171 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-131 | N | Must Precede (IDs only) | T-143; T-189; T-190 | T-132; T-133; T-136; T-142; T-240 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-131 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-131 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-131 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-132 | M | Depends On (IDs only) | T-178; T-142 | T-131 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-132 | N | Must Precede (IDs only) | T-144; T-189; T-190 | T-133; T-136; T-142; T-240 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-132 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-132 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-132 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-133 | M | Depends On (IDs only) | T-143 | T-131; T-132; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-133 | N | Must Precede (IDs only) | T-145; T-190 | T-134; T-136; T-240 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-133 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-133 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-133 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-134 | M | Depends On (IDs only) | T-144 | T-090; T-095; T-096; T-129; T-130; T-133; T-186; T-139 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-134 | N | Must Precede (IDs only) | T-190; T-193 | T-138; T-228; T-229 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-134 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-134 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-134 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-135 | M | Depends On (IDs only) | T-147; T-177; T-128; T-129 | T-112; T-114; T-128; T-129; T-130; T-183 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-135 | N | Must Precede (IDs only) |  | T-184; T-185; T-186; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-135 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-135 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-135 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-136 | M | Depends On (IDs only) | T-090; T-128; T-129; T-177 | T-131; T-132; T-133; T-109 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-136 | N | Must Precede (IDs only) | T-146 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-136 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-136 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-136 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-138 | M | Depends On (IDs only) |  | T-179; T-180; T-181; T-137; T-134; T-188 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-138 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-138 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-138 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-139 | M | Depends On (IDs only) |  | T-130; T-187; T-231 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-139 | N | Must Precede (IDs only) |  | T-134; T-140; T-141; T-142; T-189; T-193 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-139 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-139 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-139 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-140 | M | Depends On (IDs only) | T-237; T-235 | T-139; T-173; T-176 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-140 | N | Must Precede (IDs only) | T-249 | T-142; T-189 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-140 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-140 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-140 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-141 | M | Depends On (IDs only) |  | T-107; T-122; T-139; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-141 | N | Must Precede (IDs only) |  | T-189 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-141 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-141 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-141 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-142 | M | Depends On (IDs only) | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114 | T-131; T-132; T-139; T-140 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-142 | N | Must Precede (IDs only) | T-129; T-130; T-133; T-135; T-184; T-185; T-186; T-187; T-192 | T-143; T-189; T-190 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-142 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-142 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-142 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-143 | M | Depends On (IDs only) | T-128; T-169; T-183; T-112; T-114; T-135 | T-178; T-142 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-143 | N | Must Precede (IDs only) | T-187; T-192 | T-144; T-189; T-190 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-143 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-143 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-143 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-144 | M | Depends On (IDs only) | T-170; T-183; T-122; T-112; T-114; T-135 | T-143 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-144 | N | Must Precede (IDs only) | T-187; T-192 | T-145; T-190 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-144 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-144 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-144 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-145 | M | Depends On (IDs only) | T-171; T-183; T-128; T-129; T-195; T-135 | T-144 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-145 | N | Must Precede (IDs only) | T-134; T-187; T-188; T-192 | T-190; T-193 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-145 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-145 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-145 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-146 | M | Depends On (IDs only) | T-168; T-169; T-170; T-171; T-172; T-173; T-174; T-175; T-176; T-183; T-184; T-185; T-186; T-107; T-109; T-112; T-114; T-135; T-195 | T-147; T-177; T-128; T-129 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-146 | N | Must Precede (IDs only) | T-139; T-141; T-191; T-192; T-193; T-246 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-146 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-146 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-146 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-147 | M | Depends On (IDs only) | T-129; T-130; T-186; T-195 | T-090; T-128; T-129; T-177 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-147 | N | Must Precede (IDs only) | T-138; T-192 | T-146 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-147 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-147 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-147 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-157 | M | Depends On (IDs only) | T-139; T-140; T-141; T-142; T-143 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-157 | N | Must Precede (IDs only) | T-192 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-157 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-157 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-157 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-158 | M | Depends On (IDs only) | T-142; T-143; T-144; T-145 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-158 | N | Must Precede (IDs only) | T-192 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-158 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-158 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-158 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-164 | M | Depends On (IDs only) | T-130; T-176; T-187 | T-237; T-235 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-164 | N | Must Precede (IDs only) | T-192 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-164 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-164 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-164 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-165 | M | Depends On (IDs only) | T-183; T-184; T-185; T-186; T-187; T-188; T-189; T-190; T-191; T-107; T-122 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-165 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-165 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-165 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-183 | M | Depends On (IDs only) | T-130; T-187; T-139; T-145 | T-089; T-090; T-091; T-092; T-093; T-094; T-095; T-096; T-097; T-098; T-099; T-100; T-101; T-102; T-103; T-104; T-112; T-114 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-183 | N | Must Precede (IDs only) | T-249 | T-129; T-130; T-133; T-135; T-184; T-185; T-186; T-187; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-183 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-183 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-183 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-184 | M | Depends On (IDs only) | T-090; T-112; T-114 | T-128; T-169; T-183; T-112; T-114; T-135 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-184 | N | Must Precede (IDs only) | T-186; T-187; T-188 | T-187; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-184 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-184 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-184 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-185 | M | Depends On (IDs only) | T-208; T-214 | T-170; T-183; T-122; T-112; T-114; T-135 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-185 | N | Must Precede (IDs only) | T-239; T-240 | T-187; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-185 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-185 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-185 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-186 | M | Depends On (IDs only) | T-090; T-214; T-238 | T-171; T-183; T-128; T-129; T-195; T-135 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-186 | N | Must Precede (IDs only) | T-240 | T-134; T-187; T-188; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-186 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-186 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-186 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-187 | M | Depends On (IDs only) | T-131; T-132; T-133; T-238; T-239 | T-168; T-169; T-170; T-171; T-172; T-173; T-174; T-175; T-176; T-183; T-184; T-185; T-186; T-107; T-109; T-112; T-114; T-135; T-195 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-187 | N | Must Precede (IDs only) | T-249; T-264 | T-139; T-141; T-191; T-192; T-193; T-246 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-187 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-187 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-187 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-188 | M | Depends On (IDs only) |  | T-129; T-130; T-186; T-195 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-188 | N | Must Precede (IDs only) | T-249 | T-138; T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-188 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-188 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-188 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-189 | M | Depends On (IDs only) | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110 | T-139; T-140; T-141; T-142; T-143 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-189 | N | Must Precede (IDs only) |  | T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-189 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-189 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-189 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-190 | M | Depends On (IDs only) | T-205 | T-142; T-143; T-144; T-145 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-190 | N | Must Precede (IDs only) | T-150; T-255; T-257; T-258 | T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-190 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-190 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-190 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-191 | M | Depends On (IDs only) | T-087; T-088; T-260 | T-130; T-176; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-191 | N | Must Precede (IDs only) | T-112; T-150; T-252; T-256; T-259 | T-192 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-191 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-191 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-191 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-192 | M | Depends On (IDs only) | T-088 | T-183; T-184; T-185; T-186; T-187; T-188; T-189; T-190; T-191; T-107; T-122 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-192 | N | Must Precede (IDs only) | T-251 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-192 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-192 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-192 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-193 | M | Depends On (IDs only) | T-251 | T-130; T-187; T-139; T-145 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-193 | N | Must Precede (IDs only) | T-150; T-227; T-252; T-257 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-193 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-193 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-193 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-195 | M | Depends On (IDs only) | T-087; T-088; T-251; T-259 | T-090; T-112; T-114 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-195 | N | Must Precede (IDs only) | T-106; T-112; T-150; T-256 | T-186; T-187; T-188 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-195 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-195 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-195 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-238 | M | Depends On (IDs only) | T-088; T-094; T-251; T-252; T-253 | T-208; T-214 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-238 | N | Must Precede (IDs only) | T-116; T-150; T-247; T-258 | T-239; T-240 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-238 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-238 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-238 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-239 | M | Depends On (IDs only) | T-205; T-250 | T-090; T-214; T-238 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-239 | N | Must Precede (IDs only) | T-150 | T-240 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-239 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-239 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-239 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-240 | M | Depends On (IDs only) | T-205; T-250; T-259 | T-131; T-132; T-133; T-238; T-239 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-240 | N | Must Precede (IDs only) | T-150; T-248 | T-249; T-264 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-240 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-240 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-240 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-246 | M | Depends On (IDs only) | T-106; T-241; T-242; T-243; T-099; T-262 | T-243; T-130; T-137; T-187 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-246 | N | Must Precede (IDs only) | T-104; T-245 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-246 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-246 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-246 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-264 | M | Depends On (IDs only) | T-253; T-243 | T-214; T-240 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-264 | N | Must Precede (IDs only) | T-261 | T-249 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-264 | AJ | Estimate Basis | UNESTIMATED — new row; no hours inferred from source presence | UNESTIMATED — new/recognized task; owner calibration pending. | Blank is unknown effort, not zero.
T-264 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-264 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-264 | AR | Estimate Status |  | UNESTIMATED | Add explicit evidence / estimation provenance in repair revision.
T-167 | M | Depends On (IDs only) | T-106; T-248 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-167 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-167 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-167 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.
T-249 | M | Depends On (IDs only) | T-214; T-240 | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110 | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-249 | N | Must Precede (IDs only) | T-249 |  | Repair positional corruption using task-keyed baseline and approved edit dataset.
T-249 | AO | Evidence State |  | Not started — no completion claimed | Add explicit evidence / estimation provenance in repair revision.
T-249 | AP | Closure Evidence Basis |  | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Add explicit evidence / estimation provenance in repair revision.
T-249 | AR | Estimate Status |  | INHERITED ESTIMATE | Add explicit evidence / estimation provenance in repair revision.

## External Prerequisites
ID | Type | Used by active tasks | Evidence boundary
T-032 | Historical baseline prerequisite | T-241 | Retained from v2.21.0; not recreated or recertified in this repair.
T-035 | Historical baseline prerequisite | T-244 | Retained from v2.21.0; not recreated or recertified in this repair.
T-036 | Historical baseline prerequisite | T-244 | Retained from v2.21.0; not recreated or recertified in this repair.
T-057 | Historical baseline prerequisite | T-095 | Retained from v2.21.0; not recreated or recertified in this repair.
T-064 | Historical baseline prerequisite | T-106 | Retained from v2.21.0; not recreated or recertified in this repair.

## Secondary Capability Links
Task Id | Capability ID | Current status | Current release
T-087 | L5.7 | Done | M2
T-088 | L5.7 | Done | M2
T-088 | L2.1 | Done | M2
T-089 | L5.6 | Done | M2
T-090 | L2.5 | Done | M2
T-091 | L2.5 | Done | M2
T-092 | L5.1 | Done | M2
T-094 | L5.3 | Done | M2
T-202 | L3.1 | Done | M2
T-202 | L3.4 | Done | M2
T-203 | L6.7 | Done | M2
T-210 | L4.2 | Done | M2
T-216 | L5.5 | Done | M2
T-251 | L8.1 | Done | M2
T-256 | L5.1 | Done | M2
T-256 | L5.7 | Done | M2
T-260 | L5.7 | Done | M2
T-260 | L8.2 | Done | M2
T-101 | L1.6 | Not Started | M2
T-101 | L1.2 | Not Started | M2
T-101 | L1.7 | Not Started | M2
T-104 | L2.5 | Not Started | M2
T-106 | L2.5 | Done | M2
T-106 | L2.7 | Done | M2
T-106 | L1.7 | Done | M2
T-107 | L2.6 | Not Started | M2
T-108 | L1.3 | Not Started | M2
T-108 | L1.1 | Not Started | M2
T-108 | L1.7 | Not Started | M2
T-109 | L4.3 | Not Started | M2
T-212 | L5.3 | Not Started | M2
T-212 | L4.2 | Not Started | M2
T-213 | L1.1 | Done | M2
T-213 | L7.8 | Done | M2
T-233 | L5.5 | In Progress | M2
T-243 | L3.5 | Done | M2
T-243 | L3.6 | Done | M2
T-243 | L2.2 | Done | M2
T-244 | L3.7 | Done | M2
T-245 | L2.6 | Not Started | M2
T-247 | L1.1 | Not Started | M2
T-247 | L1.2 | Not Started | M2
T-247 | L2.3 | Not Started | M2
T-247 | L3.8 | Not Started | M2
T-253 | L2.3 | Done | M2
T-261 | L3.8 | In Progress | M2
T-261 | L2.6 | In Progress | M2
T-262 | L2.3 | Done | M2
T-262 | L3.6 | Done | M2
T-215 | L3.4 | Not Started | M2
T-258 | L3.4 | Not Started | M2
T-168 | L8.4 | Done | M2
T-180 | L4.5 | Done | M2
T-181 | L5.8 | Done | M2
T-182 | L4.5 | Done | M2
T-182 | L4.8 | Done | M2
T-211 | L5.3 | Not Started | M2
T-221 | L5.5 | Not Started | M2
T-223 | L10.3 | Not Started | M2
T-223 | L9.1 | Not Started | M2
T-236 | L4.2 | Done | M2
T-236 | L10.3 | Done | M2
T-115 | L8.2 | Not Started | M2
T-121 | L7.4 | Not Started | M2
T-123 | L8.3 | Not Started | M2
T-125 | L1.7 | Not Started | M2
T-126 | L8.8 | Not Started | M2
T-257 | L8.2 | Not Started | M2
T-110 | L8.4 | Not Started | M3
T-152 | L8.8 | Not Started | M3
T-153 | L1.4 | Not Started | M3
T-155 | L8.4 | Not Started | M3
T-159 | L8.5 | Not Started | M3
T-162 | L7.5 | Not Started | M3
T-156 | L2.2 | Not Started | M3
T-248 | L3.1 | Not Started | M3
T-248 | L3.3 | Not Started | M3
T-248 | L3.4 | Not Started | M3
T-248 | L3.5 | Not Started | M3
T-248 | L3.6 | Not Started | M3
T-248 | L3.9 | Not Started | M3
T-248 | L6.7 | Not Started | M3
T-263 | L2.6 | Not Started | M3
T-263 | L6.4 | Not Started | M3
T-128 | L9.5 | Not Started | M3
T-129 | L4.2 | Not Started | M3
T-129 | L4.4 | Not Started | M3
T-134 | L3.4 | Not Started | M3
T-141 | L8.6 | Not Started | M3
T-144 | L9.4 | Not Started | M3
T-145 | L9.6 | Not Started | M3
T-145 | L6.4 | Not Started | M3
T-145 | L9.8 | Not Started | M3
T-147 | L4.2 | Not Started | M3
T-157 | L4.4 | Not Started | M3
T-157 | L4.7 | Not Started | M3
T-165 | L7.7 | Not Started | M3
T-183 | L5.5 | Not Started | M3
T-186 | L4.8 | Not Started | M3
T-187 | L4.5 | Not Started | M3
T-187 | L4.8 | Not Started | M3
T-188 | L4.1 | Not Started | M3
T-188 | L4.2 | Not Started | M3
T-189 | L3.4 | Not Started | M3
T-190 | L9.3 | Not Started | M3
T-190 | L9.4 | Not Started | M3
T-192 | L4.3 | Not Started | M3
T-192 | L4.8 | Not Started | M3
T-192 | L5.8 | Not Started | M3
T-193 | L4.8 | Not Started | M3
T-238 | L10.1 | Not Started | M3
T-240 | L6.2 | Not Started | M3
T-246 | L4.2 | Not Started | M3
T-246 | L4.7 | Not Started | M3
T-264 | L9.1 | Not Started | M3
T-264 | L4.6 | Not Started | M3
T-167 | L8.8 | Not Started | M3
T-265 | L1.1 | Not Started | M2
T-265 | L1.2 | Not Started | M2
T-265 | L1.3 | Not Started | M2
T-265 | L1.7 | Not Started | M2
T-265 | L2.2 | Not Started | M2
T-265 | L2.3 | Not Started | M2
T-265 | L2.6 | Not Started | M2
T-265 | L2.7 | Not Started | M2
T-265 | L3.2 | Not Started | M2
T-265 | L3.3 | Not Started | M2
T-265 | L3.5 | Not Started | M2
T-265 | L3.6 | Not Started | M2
T-265 | L3.7 | Not Started | M2
T-265 | L5.2 | Not Started | M2
T-265 | L6.1 | Not Started | M2
T-265 | L6.7 | Not Started | M2
T-266 | L1.4 | Not Started | M2
T-266 | L1.1 | Not Started | M2
T-266 | L1.5 | Not Started | M2
T-266 | L6.8 | Not Started | M2
T-267 | L3.1 | Not Started | M3
T-267 | L3.2 | Not Started | M3
T-267 | L3.3 | Not Started | M3
T-267 | L3.9 | Not Started | M3
T-267 | L6.5 | Not Started | M3
T-267 | L6.7 | Not Started | M3
T-267 | L7.4 | Not Started | M3
T-267 | L9.3 | Not Started | M3
T-267 | L9.5 | Not Started | M3
T-267 | L10.1 | Not Started | M3
T-267 | L10.4 | Not Started | M3
T-268 | L1.1 | Not Started | M2
T-268 | L1.4 | Not Started | M2
T-268 | L1.5 | Not Started | M2
T-268 | L5.6 | Not Started | M2
T-269 | L1.5 | Not Started | M2
T-269 | L5.5 | Not Started | M2
T-270 | L1.5 | Not Started | M2
T-270 | L1.7 | Not Started | M2
T-270 | L2.6 | Not Started | M2
T-270 | L5.5 | Not Started | M2
T-271 | L1.1 | Not Started | M2
T-271 | L1.4 | Not Started | M2
T-271 | L1.7 | Not Started | M2
T-272 | L1.5 | Not Started | M2
T-272 | L2.3 | Not Started | M2
T-272 | L3.5 | Not Started | M2
T-272 | L5.7 | Not Started | M2
T-273 | L1.7 | Not Started | M2
T-273 | L8.6 | Not Started | M2
T-273 | L8.7 | Not Started | M2
T-273 | L8.8 | Not Started | M2
T-274 | L1.1 | Not Started | M2
T-274 | L1.2 | Not Started | M2
T-274 | L1.4 | Not Started | M2
T-274 | L1.7 | Not Started | M2
T-274 | L2.6 | Not Started | M2
T-275 | L1.7 | Not Started | M2
T-275 | L1.8 | Not Started | M2
T-275 | L8.4 | Not Started | M2
T-275 | L8.6 | Not Started | M2

## UI Coverage v223
Artifact ID | Kind | Name | Release portion | Design owner | Runtime owner(s) | Chapter / source | Existing scene IDs | Design state | Required correction / outcome | Citation status
A1 | Page | Login | M2 | T-265 | T-113; T-119; T-120 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | A1--populated; A1--loading; A1--blocked; A1--refused; A1--failed | DESIGN DEPTH PENDING | Authenticated/locked/challenge/session recovery; secrets never shown. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
A2 | Page | Home | M2 | T-265 | T-148; T-247 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A2 | A2--populated; A2--loading; A2--empty; A2--filtered-empty; A2--blocked; A2--refused; A2--failed; A2--read-only | DESIGN DEPTH PENDING | Canonical J1-J15 identity, or a labelled condensed mapping; no second journey. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
B1 | Page | Connections | M2 | T-265 | T-113; T-254; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | B1--populated; B1--loading; B1--empty; B1--filtered-empty; B1--blocked; B1--refused; B1--failed; B1--read-only | DESIGN DEPTH PENDING | Provider-aware fields/test/budget/secret reference; OPC variant T-266. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
B2 | Page | Dataset Registry | M2 | T-265 | T-148; T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | B2--populated; B2--loading; B2--empty; B2--filtered-empty; B2--blocked; B2--refused; B2--failed; B2--read-only | DESIGN DEPTH PENDING | Discovery tree/selection/register/preview; confirm suggestions; OPC variant T-266. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
B3 | Page | Prepare Import | M2 | T-265 | T-108; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | B3--populated; B3--loading; B3--empty; B3--filtered-empty; B3--blocked; B3--refused; B3--failed; B3--read-only | DESIGN DEPTH PENDING | Typed watermark and deterministic tie-break; no-watermark warning/cadence; OPC T-266. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
B4 | Page | Importing | M2 | T-265 | T-101; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | B4--populated; B4--loading; B4--empty; B4--filtered-empty; B4--blocked; B4--refused; B4--failed; B4--read-only | DESIGN DEPTH PENDING | Durable batch state/error/counts/last committed cursor; retry and spool variant. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
B5 | Page | Jobs Monitor | M2 | T-265 | T-106; T-125; T-245 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | B5--populated; B5--loading; B5--empty; B5--filtered-empty; B5--blocked; B5--refused; B5--failed; B5--read-only | DESIGN DEPTH PENDING | Monitor and history, cancellation acknowledgement, canonical outcomes. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
B6 | Page | Connector Truth | M2 | T-265 | T-254; T-224; T-225; T-226 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B6 | B6--populated; B6--loading; B6--empty; B6--filtered-empty; B6--blocked; B6--refused; B6--failed; B6--read-only | DESIGN DEPTH PENDING | Availability is role/entitlement/runtime-specific; OPC design T-266. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
C1 | Page | Transformation Studio | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | C1--populated; C1--loading; C1--empty; C1--filtered-empty; C1--blocked; C1--refused; C1--failed; C1--read-only | DESIGN DEPTH PENDING | S1 hosting is intentional; selected-block/property/wiring/run flow is required. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
C2 | Page | Mapping Health | M2 | T-265 | T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | C2--populated; C2--loading; C2--empty; C2--filtered-empty; C2--blocked; C2--refused; C2--failed; C2--read-only | DESIGN DEPTH PENDING | Catalogue-driven PV groups, lineage, drift and reprocess; not exactly eight fixed groups. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
C3 | Page | Data Quality | M2 | T-265 | T-100; T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C3 | C3--populated; C3--loading; C3--empty; C3--filtered-empty; C3--blocked; C3--refused; C3--failed; C3--read-only | DESIGN DEPTH PENDING | Quality diagnostics and quarantine states with safe row-detail actions. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
C4 | Page | Plant Model Explorer | M3 | T-267 | T-196 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C4 | C4--populated; C4--loading; C4--empty; C4--filtered-empty; C4--blocked; C4--refused; C4--failed; C4--read-only | DESIGN DEPTH PENDING | Full Plant Model Explorer; canonical route contract available to T-148. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
C5 | Page | Genealogy Explorer | M2 | T-265 | T-102; T-103; T-258 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | C5--populated; C5--loading; C5--empty; C5--filtered-empty; C5--blocked; C5--refused; C5--failed; C5--read-only | DESIGN DEPTH PENDING | Genealogy path, aliases, weights, cycles/refusal and evidence. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
C6 | Page | Relationship Browser | M2 | T-265 | T-098 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | C6--populated; C6--loading; C6--empty; C6--filtered-empty; C6--blocked; C6--refused; C6--failed; C6--read-only | DESIGN DEPTH PENDING | Published relationship members, cardinality, paths and validation controls. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D1 | Page | Interactive Workspace | M2 + M3 | T-265; T-267 | T-148; T-258; T-247; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | D1--populated; D1--loading; D1--empty; D1--filtered-empty; D1--blocked; D1--refused; D1--failed; D1--read-only | DESIGN DEPTH PENDING | M2 selection strip, excluded pivot, propagation/table UX; advanced comparison/bookmarks M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D2 | Page | Page Builder | M2 + M3 | T-265; T-267 | T-148; T-212; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | D2--populated; D2--loading; D2--empty; D2--filtered-empty; D2--blocked; D2--refused; D2--failed; D2--read-only | DESIGN DEPTH PENDING | Creation/editing/layout/role binding; distinguish from D1 view mode. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D3 | Page | Analysis Toolbox | M2 + M3 | T-265; T-267 | T-211; T-212; T-237; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | D3--populated; D3--loading; D3--empty; D3--filtered-empty; D3--blocked; D3--refused; D3--failed; D3--read-only | DESIGN DEPTH PENDING | Active method/subject/grain/readiness controls; unsupported methods refuse honestly. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D4 | Page | Findings | M2 + M3 | T-265; T-267 | T-212; T-247; T-188 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | D4--populated; D4--loading; D4--empty; D4--filtered-empty; D4--blocked; D4--refused; D4--failed; D4--read-only | DESIGN DEPTH PENDING | Existing findings minimum and evidence M2; full findings cutover M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D5 | Page | Risk Dashboard | M2 + M3 | T-265; T-267 | T-247; T-189 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D5 | D5--populated; D5--loading; D5--empty; D5--filtered-empty; D5--blocked; D5--refused; D5--failed; D5--read-only | DESIGN DEPTH PENDING | Existing risk foundation only in M2; operational prediction depth remains M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D6 | Page | Suggestions | M2 + M3 | T-265; T-267 | T-247; T-113; T-190 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D6 | D6--populated; D6--loading; D6--empty; D6--filtered-empty; D6--blocked; D6--refused; D6--failed; D6--read-only | DESIGN DEPTH PENDING | Existing evidence-linked suggestions M2; full decisions cutover M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D7 | Page | Value Dashboard | M2 + M3 | T-265; T-267 | T-247; T-164 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D7 | D7--populated; D7--loading; D7--empty; D7--filtered-empty; D7--blocked; D7--refused; D7--failed; D7--read-only | DESIGN DEPTH PENDING | Bounded potential value only M2; realised-value evidence M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D8 | Page | ML Readiness and Models | M2 + M3 | T-265; T-267 | T-247; T-211; T-186; T-187; T-188 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | D8--populated; D8--loading; D8--empty; D8--filtered-empty; D8--blocked; D8--refused; D8--failed; D8--read-only | DESIGN DEPTH PENDING | Live readiness/refusal minimum M2; model production lifecycle M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D9 | Page | Early Warning | M3 | T-267 | T-189; T-141 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | D9--populated; D9--loading; D9--empty; D9--filtered-empty; D9--blocked; D9--refused; D9--failed; D9--read-only | DESIGN DEPTH PENDING | Operational warning, deadline and remediation state under canonical contracts. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D10 | Page | Practice Insights | M3 | T-267 | T-136; T-240 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | D10--populated; D10--loading; D10--empty; D10--filtered-empty; D10--blocked; D10--refused; D10--failed; D10--read-only | DESIGN DEPTH PENDING | Practice selection/benchmark/limitations under declared context. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D11 | Page | Scenario Simulation | M3 | T-267 | T-191 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | D11--populated; D11--loading; D11--empty; D11--filtered-empty; D11--blocked; D11--refused; D11--failed; D11--read-only | DESIGN DEPTH PENDING | Scenario assumptions, comparison and evidence; no invented monetary result. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
D12 | Page | Benchmarking | M3 | T-267 | T-264 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | D12--populated; D12--loading; D12--empty; D12--filtered-empty; D12--blocked; D12--refused; D12--failed; D12--read-only | DESIGN DEPTH PENDING | Sample/direction refusals BM01/BM02 and declared normalisation. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
E2 | Page | Assistant Configuration | M2 + M3 | T-265; T-267 | T-113; T-247; T-138 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E2 | E2--populated; E2--loading; E2--empty; E2--filtered-empty; E2--blocked; E2--refused; E2--failed; E2--read-only | DESIGN DEPTH PENDING | Safe existing Assistant config M2; canonical advanced runtime config M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
E3 | Page | Plant Data Log | M2 + M3 | T-265; T-267 | T-125; T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | E3--populated; E3--loading; E3--empty; E3--filtered-empty; E3--blocked; E3--refused; E3--failed; E3--read-only | DESIGN DEPTH PENDING | Minimum attributable logs M2; deeper audit/channel workflows M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
E4 | Page | Supervisor | M3 | T-267 | T-193 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E4 | E4--populated; E4--loading; E4--empty; E4--filtered-empty; E4--blocked; E4--refused; E4--failed; E4--read-only | DESIGN DEPTH PENDING | Supervisor proposals/shadow/review; no silent self-modification. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
E5 | Page | Reports | M3 | T-267 | T-263 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E5 | E5--populated; E5--loading; E5--empty; E5--filtered-empty; E5--blocked; E5--refused; E5--failed; E5--read-only | DESIGN DEPTH PENDING | Report define/generate/history/download/delivery with job evidence. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
E6 | Page | Alert Routing and Escalation | M3 | T-267 | T-197 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | E6--populated; E6--loading; E6--empty; E6--filtered-empty; E6--blocked; E6--refused; E6--failed; E6--read-only | DESIGN DEPTH PENDING | Routing/escalation/dedupe/retry/dead-letter contract. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F1 | Page | Users and Roles | M2 + M3 | T-265; T-267 | T-119; T-120; T-161 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F1 | F1--populated; F1--loading; F1--empty; F1--filtered-empty; F1--blocked; F1--refused; F1--failed; F1--read-only | DESIGN DEPTH PENDING | Existing M2 role/user security scope; advanced enterprise identity M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F2 | Page | Licence and Entitlement | M2 + M3 | T-265; T-267 | T-121; T-165 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F2 | F2--populated; F2--loading; F2--empty; F2--filtered-empty; F2--blocked; F2--refused; F2--failed; F2--read-only | DESIGN DEPTH PENDING | Verification-only activation and clear entitlements; deeper commercial UI M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F3 | Page | Authoring Quota and Limits | M2 + M3 | T-265; T-267 | T-121; T-165 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F3 | F3--populated; F3--loading; F3--empty; F3--filtered-empty; F3--blocked; F3--refused; F3--failed; F3--read-only | DESIGN DEPTH PENDING | T-121 quota/limits scope retained; only explicitly deferred depth follows M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F4 | Page | Jobs Administration | M2 + M3 | T-265; T-267 | T-106; T-107; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | F4--populated; F4--loading; F4--empty; F4--filtered-empty; F4--blocked; F4--refused; F4--failed; F4--read-only | DESIGN DEPTH PENDING | M2 schedule/DAG/admission/cancel/history controls; heavy administration depth M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F5 | Page | Logging and Audit | M3 | T-267 | T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | F5--populated; F5--loading; F5--empty; F5--filtered-empty; F5--blocked; F5--refused; F5--failed; F5--read-only | DESIGN DEPTH PENDING | Full logging/audit page; minimum M2 log evidence remains E3/B5. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F6 | Page | Log Channel Configuration | M3 | T-267 | T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F6 | F6--populated; F6--loading; F6--empty; F6--filtered-empty; F6--blocked; F6--refused; F6--failed; F6--read-only | DESIGN DEPTH PENDING | Full channel configuration; no parallel log authority. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F7 | Page | System Settings | M2 + M3 | T-265; T-267 | T-233; T-200 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F7 | F7--populated; F7--loading; F7--empty; F7--filtered-empty; F7--blocked; F7--refused; F7--failed; F7--read-only | DESIGN DEPTH PENDING | Plant time semantics M2 at existing commissioning surface; full admin page M3. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F8 | Page | Translation and Language | M3 | T-267 | T-200 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F8 | F8--populated; F8--loading; F8--empty; F8--filtered-empty; F8--blocked; F8--refused; F8--failed; F8--read-only | DESIGN DEPTH PENDING | Translation/language management; M2 rendered RTL/focus states still T-265. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
F9 | Page | Log Retention and Archival | M3 | T-267 | T-199 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | F9--populated; F9--loading; F9--empty; F9--filtered-empty; F9--blocked; F9--refused; F9--failed; F9--read-only | DESIGN DEPTH PENDING | Retention/archive/legal-hold preview and destructive confirmation. | SOURCE SECTION RETAINED; SEMANTIC REVIEW REQUIRED
G1 | Global component | Assistant dock | M2 | T-265 | T-148; T-247 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G1 | G1 | DESIGN DEPTH PENDING | Applicable source controls/states; no automatic eight-state template. Preserve existing closed implementations. | SEMANTIC REVIEW REQUIRED
G2 | Global component | Application header and navigation | M2 | T-265 | T-148; T-247 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G2 | G2 | DESIGN DEPTH PENDING | Applicable source controls/states; no automatic eight-state template. Preserve existing closed implementations. | SEMANTIC REVIEW REQUIRED
G3 | Global component | Global search and command palette | M3 | T-267 | T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G3 | G3 | DESIGN DEPTH PENDING | Applicable source controls/states; no automatic eight-state template. Preserve existing closed implementations. | SEMANTIC REVIEW REQUIRED
G4 | Global component | Notification and toast host | M2 | T-265 | T-148; T-247 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G4 | G4 | DESIGN DEPTH PENDING | Applicable source controls/states; no automatic eight-state template. Preserve existing closed implementations. | SEMANTIC REVIEW REQUIRED
G5 | Global component | Refusal and error boundary | M2 | T-265 | T-148; T-247 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G5 | G5 | DESIGN DEPTH PENDING | Applicable source controls/states; no automatic eight-state template. Preserve existing closed implementations. | SEMANTIC REVIEW REQUIRED
G6 | Global component | Activity and progress tray | M3 | T-267 | T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G6 | G6 | DESIGN DEPTH PENDING | Applicable source controls/states; no automatic eight-state template. Preserve existing closed implementations. | SEMANTIC REVIEW REQUIRED
DLG-A1-mfa | Dialog | Verify administrator access | M2 | T-265 | T-113; T-119; T-120 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | DLG-A1-mfa--default; DLG-A1-mfa--invalid | DESIGN DEPTH PENDING | Verification code ¦ No authenticated page until required verification succeeds. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-A1-session | Dialog | Session expired | M2 | T-265 | T-113; T-119; T-120 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | DLG-A1-session--default; DLG-A1-session--invalid | DESIGN DEPTH PENDING | ¦ Explain expiry; never silently discard a dirty authored draft. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B1-create | Dialog | Connection profile | M2 | T-265 | T-113; T-254; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | DLG-B1-create--default; DLG-B1-create--invalid | DESIGN DEPTH PENDING | Name; Provider; Host; Port; Database; Schema; Credential reference; Read-only posture; Allowed window; Row cap; Timeout; Rate cap ¦ Do not display a stored secret; only a credential reference is returned. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B1-test | Dialog | Test source connection | M2 | T-265 | T-113; T-254; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | DLG-B1-test--default; DLG-B1-test--invalid | DESIGN DEPTH PENDING | Connection identity; Provider identity; Read-only evidence; Measured source budget ¦ Read-only proof and source-budget check, not just reachability. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B1-deactivate | Dialog | Deactivate connection | M2 | T-265 | T-113; T-254; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | DLG-B1-deactivate--default; DLG-B1-deactivate--invalid | DESIGN DEPTH PENDING | Affected datasets; Affected jobs; Reason ¦ Show dependency impact; no deletion of source history. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B1-credential | Dialog | Replace credential reference | M2 | T-265 | T-113; T-254; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | DLG-B1-credential--default; DLG-B1-credential--invalid | DESIGN DEPTH PENDING | Current reference (masked label); New protected reference; Reason ¦ No plaintext secret persisted in options or returned by read-back. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B2-register | Dialog | Register dataset | M2 | T-265 | T-148; T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | DLG-B2-register--default; DLG-B2-register--invalid | DESIGN DEPTH PENDING | Connection; Schema; Source object; Included columns; Taxonomy source ¦ Author confirms source metadata; suggestions are not declarations. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B2-preview | Dialog | Source preview | M2 | T-265 | T-148; T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | DLG-B2-preview--default; DLG-B2-preview--invalid | DESIGN DEPTH PENDING | Source identity; Column names and types; Bounded sample; Rows and elapsed time ¦ Read under the effective source budget. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B3-key | Dialog | Business-key members | M2 | T-265 | T-108; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | DLG-B3-key--default; DLG-B3-key--invalid | DESIGN DEPTH PENDING | Ordered source fields; Member order; Uniqueness evidence ¦ All selected key members belong to imported columns. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B3-cursor | Dialog | Incremental cursor | M2 | T-265 | T-108; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | DLG-B3-cursor--default; DLG-B3-cursor--invalid | DESIGN DEPTH PENDING | Watermark field; Watermark type; Stable tie-break members; Initial position; Source upper bound ¦ v4.10.3 total-order contract; no guessed type or tie-break. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B3-fullscan | Dialog | No watermark: daily floor | M2 | T-265 | T-108; T-148 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | DLG-B3-fullscan--default; DLG-B3-fullscan--invalid | DESIGN DEPTH PENDING | Source object; Forced daily minimum; Expected scan budget ¦ Not eligible for fast cadence without a safe incremental contract. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B4-rerun | Dialog | Re-run import batch | M2 | T-265 | T-101; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | DLG-B4-rerun--default; DLG-B4-rerun--invalid | DESIGN DEPTH PENDING | Batch identity; Persisted cursor range; Failure reason; Replay policy ¦ Replay produces idempotent accepted effects, not duplicate staging. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B4-backfill | Dialog | Historical backfill | M2 | T-265 | T-101; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | DLG-B4-backfill--default; DLG-B4-backfill--invalid | DESIGN DEPTH PENDING | Dataset; From / to; Row and byte cap; Checkpoint; Source window ¦ Bounded, pausable/resumable; does not starve cadence work. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B4-detail | Drawer | Import batch detail | M2 | T-265 | T-101; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | DLG-B4-detail--default; DLG-B4-detail--invalid | DESIGN DEPTH PENDING | Status; Watermark from / to; Rows read / staged; Failed rows; Source lineage; Run log ¦ Failed rows cannot be hidden inside a green aggregate run. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B5-cancel | Dialog | Cancel running job | M2 | T-265 | T-106; T-125; T-245 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | DLG-B5-cancel--default; DLG-B5-cancel--invalid | DESIGN DEPTH PENDING | Job identity; Run identity; Committed work; Reason ¦ A cancellation request is not an acknowledged terminal state. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B5-pause | Dialog | Pause scheduled job | M2 | T-265 | T-106; T-125; T-245 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | DLG-B5-pause--default; DLG-B5-pause--invalid | DESIGN DEPTH PENDING | Schedule; Next occurrence; Reason ¦ Pauses future admission; separately cancel any current run. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B5-run | Dialog | Run job now | M2 | T-265 | T-106; T-125; T-245 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | DLG-B5-run--default; DLG-B5-run--invalid | DESIGN DEPTH PENDING | Definition version; Dependency verdict; Budget verdict; Parameters ¦ Target pinned at admission; unsupported families refuse before execution. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B5-history | Drawer | Run evidence | M2 | T-265 | T-106; T-125; T-245 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | DLG-B5-history--default; DLG-B5-history--invalid | DESIGN DEPTH PENDING | Run identity; Resolved version; Counts; Duration; Upstream evidence; Failure / refusal ¦ Historical identities remain immutable and tenant-scoped. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-B6-export | Dialog | Export capability truth | M2 | T-265 | T-254; T-224; T-225; T-226 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B6 | DLG-B6-export--default; DLG-B6-export--invalid | DESIGN DEPTH PENDING | Provider set; State filter; Evidence date ¦ Read-only representation of server capability truth. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-publish | Dialog | Publish Transformation | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-publish--default; DLG-C1-publish--invalid | DESIGN DEPTH PENDING | Definition name; Version / hash; Output target; Relationship emission; Downstream impact ¦ Definition and relationship publication must not partially commit. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-impact | Dialog | Downstream impact | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-impact--default; DLG-C1-impact--invalid | DESIGN DEPTH PENDING | Definitions; Pages; Analyses; Models; Relationships; Required action ¦ No implicit deletion or widening of existing contracts. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-fork | Dialog | Edit published definition | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-fork--default; DLG-C1-fork--invalid | DESIGN DEPTH PENDING | Published version; Next draft; Reason ¦ Never mutate the existing immutable version. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-rollback | Dialog | Select prior version | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-rollback--default; DLG-C1-rollback--invalid | DESIGN DEPTH PENDING | Version history; Current pointer; Downstream impact; Reason ¦ Preserve later historical versions and explain the pointer change. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-import | Dialog | Import definition | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-import--default; DLG-C1-import--invalid | DESIGN DEPTH PENDING | Artifact; Source schema bindings; Target catalog; Validation diagnostics ¦ No authored file bypasses the canonical lifecycle. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-mode | Dialog | Switch authoring representation | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-mode--default; DLG-C1-mode--invalid | DESIGN DEPTH PENDING | Current representation; Reconstructability; Preserved SQL; Diagram consequence ¦ Do not claim a SQL diagram is reconstructable when it is not. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-dirty | Dialog | Unsaved definition changes | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-dirty--default; DLG-C1-dirty--invalid | DESIGN DEPTH PENDING | Changed fields; Last persisted version ¦ Actions: save, discard with confirmation, stay. Never silently lose edits. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-conflict | Dialog | Concurrent edit conflict | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-conflict--default; DLG-C1-conflict--invalid | DESIGN DEPTH PENDING | Base version; Server version; Local changes; Rebase / save-as ¦ No last-write-wins overwrite of a published version. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-sqlerror | Dialog | SQL validation details | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-sqlerror--default; DLG-C1-sqlerror--invalid | DESIGN DEPTH PENDING | Message; Offending fragment; Token / line / column; Suggested correction ¦ Message + echoed fragment + in-place token highlight. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-expression | Dialog | Expression editor | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-expression--default; DLG-C1-expression--invalid | DESIGN DEPTH PENDING | Typed fields; Operators; Expression; Declared result type; Validation; Test sample ¦ Single row context; no free control-flow board. Accept is one undo step. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C1-mapping | Dialog | Canonical field mapping | M2 + M3 | T-265; T-267 | T-243; T-262; T-245; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | DLG-C1-mapping--default; DLG-C1-mapping--invalid | DESIGN DEPTH PENDING | Target entity; Required business fields; Source output binding; Type verdict; System provenance (read-only) ¦ No inference by ordinal/name resemblance; unknown source type refuses. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C2-drift | Dialog | Schema drift event | M2 | T-265 | T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | DLG-C2-drift--default; DLG-C2-drift--invalid | DESIGN DEPTH PENDING | Dataset; Changed field; Old / new type; Affected mappings; State ¦ Acknowledgement is not automatic repair or reactivation. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C2-reprocess | Dialog | Reprocess corrected rows | M2 | T-265 | T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | DLG-C2-reprocess--default; DLG-C2-reprocess--invalid | DESIGN DEPTH PENDING | Batch; Quarantine code; Corrected definition version; Estimated scope ¦ Preserve original rejection and exact selected correction version. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C3-quarantine | Drawer | Quarantine row detail | M2 | T-265 | T-100; T-101 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C3 | DLG-C3-quarantine--default; DLG-C3-quarantine--invalid | DESIGN DEPTH PENDING | Validation code; Offending field; Staging row; Source provenance; Correction hint ¦ Actual failure evidence, not invented successful output. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C4-entity | Dialog | Canonical entity detail | M3 | T-267 | T-196 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C4 | DLG-C4-entity--default; DLG-C4-entity--invalid | DESIGN DEPTH PENDING | Entity type; Registered dimensions; Relationships; Evidence ¦ Generic registry vocabulary; no customer-specific hardcoding. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C5-genealogy | Drawer | Genealogy contribution | M2 | T-265 | T-102; T-103; T-258 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | DLG-C5-genealogy--default; DLG-C5-genealogy--invalid | DESIGN DEPTH PENDING | Parent / child identities; Ordered key; Weight; Grain; Source definition ¦ Weights and direction are evidence-bearing, never decorative lines. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C6-validate | Dialog | Validate relationship | M2 | T-265 | T-098 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | DLG-C6-validate--default; DLG-C6-validate--invalid | DESIGN DEPTH PENDING | Relationship version; Ordered members; Cardinality; Grain conversion; Attribution; Evidence ¦ Server measures validation state; user cannot assert proven=true. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-C6-path | Dialog | Preferred relationship path | M2 | T-265 | T-098 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | DLG-C6-path--default; DLG-C6-path--invalid | DESIGN DEPTH PENDING | Source / destination; Candidate paths; Ambiguity; Declared preference ¦ No guessed path when more than one lawful route exists. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D1-selection | Dialog | Selection state | M2 + M3 | T-265; T-267 | T-148; T-258; T-247; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | DLG-D1-selection--default; DLG-D1-selection--invalid | DESIGN DEPTH PENDING | Selected; Possible; Excluded; Clear one / all ¦ Excluded values remain clickable to pivot; color is not the sole signal. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D1-bookmark | Dialog | Save current view | M2 + M3 | T-265; T-267 | T-148; T-258; T-247; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | DLG-D1-bookmark--default; DLG-D1-bookmark--invalid | DESIGN DEPTH PENDING | Name; Selection state; Layout version; Visibility ¦ Persist through governed definitions; no layout authority in localStorage. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D1-export | Dialog | Export current state | M2 + M3 | T-265; T-267 | T-148; T-258; T-247; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | DLG-D1-export--default; DLG-D1-export--invalid | DESIGN DEPTH PENDING | Format; Current filters; Period; Evidence inclusion; Scope ¦ Export the displayed state and label incomplete/unavailable evidence. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D2-page | Dialog | Page definition | M2 + M3 | T-265; T-267 | T-148; T-212; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | DLG-D2-page--default; DLG-D2-page--invalid | DESIGN DEPTH PENDING | Title; Description; Visibility; Layout; Default selection ¦ Reuse page lifecycle, not a separate dashboard engine. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D2-widget | Dialog | Widget binding | M2 + M3 | T-265; T-267 | T-148; T-212; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | DLG-D2-widget--default; DLG-D2-widget--invalid | DESIGN DEPTH PENDING | Source class; Source identity; Grain; Dimensions; Measures; Chart; Evidence handles ¦ Keep native-grain rich sources intact; refuse invalid joins/roles. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D2-filter | Dialog | Filter definition | M2 + M3 | T-265; T-267 | T-148; T-212; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | DLG-D2-filter--default; DLG-D2-filter--invalid | DESIGN DEPTH PENDING | Name; Scope; Registered field; Filter kind; Default; Version ¦ Page/global/widget scopes stay distinct; stale bindings are visible. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D2-delete | Dialog | Remove widget | M2 + M3 | T-265; T-267 | T-148; T-212; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | DLG-D2-delete--default; DLG-D2-delete--invalid | DESIGN DEPTH PENDING | Widget identity; Page version; Unsaved changes ¦ Removal changes the draft only; saved history retained. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D3-readiness | Dialog | Analysis readiness | M2 + M3 | T-265; T-267 | T-211; T-212; T-237; T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | DLG-D3-readiness--default; DLG-D3-readiness--invalid | DESIGN DEPTH PENDING | Population; Grain; Method; Measured values; Thresholds; Refusal reasons ¦ A refusal cannot be bypassed by enabling a UI checkbox. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D4-evidence | Drawer | Finding evidence | M2 + M3 | T-265; T-267 | T-212; T-247; T-188 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | DLG-D4-evidence--default; DLG-D4-evidence--invalid | DESIGN DEPTH PENDING | Claim class; Method; Population; Effect / uncertainty; q-value; Source handles ¦ A statistical association is not upgraded to a causal claim. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D5-risk | Dialog | Risk record | M2 + M3 | T-265; T-267 | T-247; T-189 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D5 | DLG-D5-risk--default; DLG-D5-risk--invalid | DESIGN DEPTH PENDING | Subject identity; Risk band; Drivers; Model / engine version; Evidence ¦ No certainty claim; source and model states remain explicit. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D6-decision | Dialog | Suggestion decision | M2 + M3 | T-265; T-267 | T-247; T-113; T-190 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D6 | DLG-D6-decision--default; DLG-D6-decision--invalid | DESIGN DEPTH PENDING | Suggestion; Evidence; Reason code; Decision; Actor ¦ Server can_accept/permission authority gates action; no plant control write. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D6-defer | Dialog | Defer suggestion | M2 + M3 | T-265; T-267 | T-247; T-113; T-190 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D6 | DLG-D6-defer--default; DLG-D6-defer--invalid | DESIGN DEPTH PENDING | Reason code; Review time; Evidence ¦ Record actor/time; do not fabricate an action or outcome. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D7-assumptions | Dialog | Cost assumptions | M2 + M3 | T-265; T-267 | T-247; T-164 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D7 | DLG-D7-assumptions--default; DLG-D7-assumptions--invalid | DESIGN DEPTH PENDING | Measure; Unit / currency; Effective period; Assumption value; Source; Reason ¦ No monetary claim without declared basis and audit. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D7-value | Dialog | Value derivation | M2 + M3 | T-265; T-267 | T-247; T-164 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D7 | DLG-D7-value--default; DLG-D7-value--invalid | DESIGN DEPTH PENDING | Potential / realised class; Assumptions; Counterfactual; Uncertainty; Evidence ¦ Do not combine unsupported realised value with a modeled potential figure. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D8-activate | Dialog | Activate model version | M2 + M3 | T-265; T-267 | T-247; T-211; T-186; T-187; T-188 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | DLG-D8-activate--default; DLG-D8-activate--invalid | DESIGN DEPTH PENDING | Candidate; Serving identity; Gate results; Snapshot / manifest; Warm-up; Fallback ¦ Only approved gates and held-out evidence permit activation. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D8-retire | Dialog | Retire model version | M2 + M3 | T-265; T-267 | T-247; T-211; T-186; T-187; T-188 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | DLG-D8-retire--default; DLG-D8-retire--invalid | DESIGN DEPTH PENDING | Version; Dependent consumers; Fallback; Reason ¦ Never erase provenance of historical predictions. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D9-remediation | Dialog | Remediation eligibility | M3 | T-267 | T-189; T-141 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | DLG-D9-remediation--default; DLG-D9-remediation--invalid | DESIGN DEPTH PENDING | Prediction; Deadline; Candidate; Nine check results; Expected effect; Evidence ¦ No accept action after deadline or any failed mandatory gate. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D10-practice | Dialog | Practice evidence | M3 | T-267 | T-136; T-240 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | DLG-D10-practice--default; DLG-D10-practice--invalid | DESIGN DEPTH PENDING | Comparable context; Support; Outcome; Confidence; Sensitivity; Benchmark status ¦ Observed practice is not automatically a proven benchmark. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D11-save | Dialog | Save scenario | M3 | T-267 | T-191 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | DLG-D11-save--default; DLG-D11-save--invalid | DESIGN DEPTH PENDING | Name; Baseline; Variable changes; Fixed assumptions; Model version; Uncertainty ¦ Simulation label permanent; no plant write path. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D11-compare | Dialog | Compare scenarios | M3 | T-267 | T-191 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | DLG-D11-compare--default; DLG-D11-compare--invalid | DESIGN DEPTH PENDING | Saved versions; Common baseline; Variables; Result intervals ¦ All models/bases/assumptions explicit; incomparable cases refuse. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-D12-comparison | Dialog | Benchmark population evidence | M3 | T-267 | T-264 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | DLG-D12-comparison--default; DLG-D12-comparison--invalid | DESIGN DEPTH PENDING | Both populations; Measure direction; Normalization; Support; Reference ¦ BM01 support and BM02 direction-of-goodness guards are visible. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E2-reset | Dialog | Reset Assistant configuration | M2 + M3 | T-265; T-267 | T-113; T-247; T-138 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E2 | DLG-E2-reset--default; DLG-E2-reset--invalid | DESIGN DEPTH PENDING | Current policies; Default policies; Impact; Reason ¦ Cannot weaken grounding or evidence rules. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E2-reindex | Dialog | Reindex knowledge | M2 + M3 | T-265; T-267 | T-113; T-247; T-138 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E2 | DLG-E2-reindex--default; DLG-E2-reindex--invalid | DESIGN DEPTH PENDING | Allowed source families; Current index; Expected bounded work ¦ Tenant and permission scope preserved. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E3-rule | Dialog | Plant data log rule | M2 + M3 | T-265; T-267 | T-125; T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | DLG-E3-rule--default; DLG-E3-rule--invalid | DESIGN DEPTH PENDING | Rule name; Parameter; Comparator; Limit; Severity ¦ Comparator whitelist enforced both server and persistence. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E3-ack | Dialog | Acknowledge log entry | M2 + M3 | T-265; T-267 | T-125; T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | DLG-E3-ack--default; DLG-E3-ack--invalid | DESIGN DEPTH PENDING | Entry; Rule; Source subject; Actor; Note ¦ No acknowledgment rewrites the observed measurement. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E4-proposal | Dialog | Review Supervisor proposal | M3 | T-267 | T-193 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E4 | DLG-E4-proposal--default; DLG-E4-proposal--invalid | DESIGN DEPTH PENDING | Target; Before / after; Reason; Evidence; Shadow comparison ¦ Forbidden authority targets remain unwriteable by construction. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E4-reject | Dialog | Reject Supervisor proposal | M3 | T-267 | T-193 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E4 | DLG-E4-reject--default; DLG-E4-reject--invalid | DESIGN DEPTH PENDING | Proposal; Reason ¦ Preserve proposal and evidence history. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E5-definition | Dialog | Report definition | M3 | T-267 | T-263 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E5 | DLG-E5-definition--default; DLG-E5-definition--invalid | DESIGN DEPTH PENDING | Title; Sections; Period; Recipients; Schedule; Delivery target ¦ One report definition and platform Job scheduler. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E5-output | Drawer | Generated report output | M3 | T-267 | T-263 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E5 | DLG-E5-output--default; DLG-E5-output--invalid | DESIGN DEPTH PENDING | Period; Filter state; Generation run; Sections; Evidence; Delivery status ¦ All-empty sections refuse generation; report uses light surface. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E6-routing | Dialog | Alert routing rule | M3 | T-267 | T-197 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | DLG-E6-routing--default; DLG-E6-routing--invalid | DESIGN DEPTH PENDING | Channel / severity; Recipients; Delivery channels; Quiet hours; Dedupe; Rate; Escalation ¦ Recipient and escalation validity checked before save. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-E6-delivery | Dialog | Delivery attempt | M3 | T-267 | T-197 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | DLG-E6-delivery--default; DLG-E6-delivery--invalid | DESIGN DEPTH PENDING | Recipient; Channel; Attempts; Reason; Next retry ¦ Retry without duplicate external delivery where receipt exists. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F1-user | Dialog | Create user | M2 + M3 | T-265; T-267 | T-119; T-120; T-161 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F1 | DLG-F1-user--default; DLG-F1-user--invalid | DESIGN DEPTH PENDING | Name; Email; Role ¦ Authorised admin; permission matrix derives from approved role contract. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F1-role | Dialog | Role / user permission override | M2 + M3 | T-265; T-267 | T-119; T-120; T-161 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F1 | DLG-F1-role--default; DLG-F1-role--invalid | DESIGN DEPTH PENDING | Principal; Role inheritance; Surface × action; Overrides; Reason ¦ Show inherited versus overridden grants; fail-closed at API too. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F1-disable | Dialog | Disable user | M2 + M3 | T-265; T-267 | T-119; T-120; T-161 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F1 | DLG-F1-disable--default; DLG-F1-disable--invalid | DESIGN DEPTH PENDING | User; Active sessions; Reason ¦ Audit; revoke active access according to session policy. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F2-license | Dialog | Activate signed licence | M2 + M3 | T-265; T-267 | T-121; T-165 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F2 | DLG-F2-license--default; DLG-F2-license--invalid | DESIGN DEPTH PENDING | Signed artifact; Tenant; Instance; Tier; Validity; Verification result ¦ Customer verifies vendor-signed artifact; no production self-signing. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F3-quota | Dialog | Role or user quota | M2 + M3 | T-265; T-267 | T-121; T-165 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F3 | DLG-F3-quota--default; DLG-F3-quota--invalid | DESIGN DEPTH PENDING | Principal / role; Object type; Inherited limit; Override; Current use ¦ 80% warning, 100% creation guard; never discard existing draft. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F4-job | Dialog | Job definition | M2 + M3 | T-265; T-267 | T-106; T-107; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | DLG-F4-job--default; DLG-F4-job--invalid | DESIGN DEPTH PENDING | Name; Family; Target identity; Version policy; Parameters; Schedule; Pool / weight ¦ One scheduler authority; unsupported family refused as unavailable. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F4-schedule | Dialog | Schedule editor | M2 + M3 | T-265; T-267 | T-106; T-107; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | DLG-F4-schedule--default; DLG-F4-schedule--invalid | DESIGN DEPTH PENDING | Kind; Canonical expression; Time zone; Next occurrences; Jitter; Missed-tick policy ¦ v4.10.3 machine grammar; UI words never executable source text. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F4-dependency | Dialog | Dependency policy | M2 + M3 | T-265; T-267 | T-106; T-107; T-125 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | DLG-F4-dependency--default; DLG-F4-dependency--invalid | DESIGN DEPTH PENDING | Upstream job; Required / optional; Pinned version; Allow prior-success reuse; Age ceiling; Cycle impact ¦ Default reuse=false; no beyond-limit acceptance; negative cases named. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F5-filter | Dialog | Log search / export | M3 | T-267 | T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | DLG-F5-filter--default; DLG-F5-filter--invalid | DESIGN DEPTH PENDING | Family; Severity; Actor; Run id; From / to; Export format ¦ Permission and tenant scope retained in export. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F6-channel | Dialog | Log channel | M3 | T-267 | T-198 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F6 | DLG-F6-channel--default; DLG-F6-channel--invalid | DESIGN DEPTH PENDING | Name; Family; Severity policy; Retention policy; Enabled ¦ Cannot redirect customer entries into protected audit authority. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F7-timezone | Dialog | Change plant time zone | M2 + M3 | T-265; T-267 | T-233; T-200 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F7 | DLG-F7-timezone--default; DLG-F7-timezone--invalid | DESIGN DEPTH PENDING | Current zone; New zone; Shift-analysis impact; Next schedule previews ¦ Does not rewrite historical source timestamps; audit setting revision. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F7-egress | Dialog | Change data egress policy | M2 + M3 | T-265; T-267 | T-233; T-200 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F7 | DLG-F7-egress--default; DLG-F7-egress--invalid | DESIGN DEPTH PENDING | Current policy; New policy; Affected tools; Reason ¦ No-egress state reaches every external model/tool boundary. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F8-language | Dialog | Import language pack | M3 | T-267 | T-200 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F8 | DLG-F8-language--default; DLG-F8-language--invalid | DESIGN DEPTH PENDING | Language; Pack version; Changed labels; Fallback; Review state ¦ Keep technical identifiers unchanged; translation does not redefine semantics. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F9-retention | Dialog | Retention impact preview | M3 | T-267 | T-199 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | DLG-F9-retention--default; DLG-F9-retention--invalid | DESIGN DEPTH PENDING | Channel; Cutoff; Rows / storage; Archive destination; Legal hold; Preview receipt ¦ No destructive save without preview; failed archive -> zero deletions. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F9-hold | Dialog | Place or remove legal hold | M3 | T-267 | T-199 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | DLG-F9-hold--default; DLG-F9-hold--invalid | DESIGN DEPTH PENDING | Channel; Current hold; Actor; Reason ¦ Authorised audited action; held data cannot be purged. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-F9-cleanup | Dialog | Run retention cleanup | M3 | T-267 | T-199 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | DLG-F9-cleanup--default; DLG-F9-cleanup--invalid | DESIGN DEPTH PENDING | Channels; Exact cutoff; Archive status; Expected count; Preview identity ¦ Abort deletion on archive failure; persist actual terminal summary. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-G1-citations | Drawer | Assistant citations | M2 | T-265 | T-148; T-247 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G1 | DLG-G1-citations--default; DLG-G1-citations--invalid | DESIGN DEPTH PENDING | Answer claim; Evidence handles; Source identity; Permission scope ¦ Context is not evidence; unresolved evidence cannot be upgraded. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-G3-commands | Dialog | Global command palette | M3 | T-267 | T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G3 | DLG-G3-commands--default; DLG-G3-commands--invalid | DESIGN DEPTH PENDING | Search; Permitted pages; Definitions; Fields; Findings; Commands ¦ Only permitted search results/actions; keyboard focus returns to trigger. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
DLG-G6-activity | Drawer | Activity tray | M3 | T-267 | T-248 | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G6 | DLG-G6-activity--default; DLG-G6-activity--invalid | DESIGN DEPTH PENDING | Running jobs; Stage / counts; Last heartbeat; Outcome; Evidence ¦ No fabricated percent; poll fallback explicitly visible. ¦ Use meaningful controls, filled/invalid/pending/refused/recovery states only where applicable; prototype focus-return. | CHECK DATA / WORD CAPTION / IMAGE AGAINST PARENT CLAUSE
TB-001 | Toolbox entry | Source table | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 1 - Source and output | TB-001 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-002 | Toolbox entry | Output to canonical entity | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 1 - Source and output | TB-002 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-003 | Toolbox entry | Output to named dataset | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 1 - Source and output | TB-003 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-004 | Toolbox entry | Join | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-004 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-005 | Toolbox entry | Filter | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-005 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-006 | Toolbox entry | Select columns | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-006 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-007 | Toolbox entry | Rename / alias | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-007 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-008 | Toolbox entry | Group by | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-008 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-009 | Toolbox entry | Sort | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-009 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-010 | Toolbox entry | Union | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-010 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-011 | Toolbox entry | Distinct | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-011 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-012 | Toolbox entry | Limit | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-012 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-013 | Toolbox entry | Pivot / unpivot | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-013 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-014 | Toolbox entry | Derived column | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-014 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-015 | Toolbox entry | Cast | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-015 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-016 | Toolbox entry | Lookup | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §Group 2 - Relational | TB-016 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-017 | Toolbox entry | Summary statistics | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-017 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-018 | Toolbox entry | Distribution | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-018 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-019 | Toolbox entry | Category counts | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-019 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-020 | Toolbox entry | Time series | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-020 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-021 | Toolbox entry | Cross-tabulation | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-021 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-022 | Toolbox entry | Outlier detection (IQR / z-score) | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-022 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-023 | Toolbox entry | Missingness profile | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.2 Group A - Descriptive | TB-023 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-024 | Toolbox entry | Pearson correlation | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-024 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-025 | Toolbox entry | Spearman rank correlation | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-025 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-026 | Toolbox entry | Correlation matrix | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-026 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-027 | Toolbox entry | Chi-square independence | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-027 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-028 | Toolbox entry | ANOVA / Kruskal-Wallis | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-028 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-029 | Toolbox entry | Odds ratio / relative risk | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-029 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-030 | Toolbox entry | Point-biserial | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-030 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-031 | Toolbox entry | Lagged correlation | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-031 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-032 | Toolbox entry | Genealogy-attributed correlation | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.3 Group B - Association and correlation | TB-032 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-033 | Mandatory discipline output / inspection | False-discovery control | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.4 Group C - Discipline (always applied, never optional) | TB-033 | DESIGN DEPTH PENDING | Always-applied discipline; inspect outputs only. Do not turn it into an optional drag/drop bypass. | SEMANTIC REVIEW REQUIRED
TB-034 | Mandatory discipline output / inspection | Effect-size ranking | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.4 Group C - Discipline (always applied, never optional) | TB-034 | DESIGN DEPTH PENDING | Always-applied discipline; inspect outputs only. Do not turn it into an optional drag/drop bypass. | SEMANTIC REVIEW REQUIRED
TB-035 | Mandatory discipline output / inspection | Stratification | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.4 Group C - Discipline (always applied, never optional) | TB-035 | DESIGN DEPTH PENDING | Always-applied discipline; inspect outputs only. Do not turn it into an optional drag/drop bypass. | SEMANTIC REVIEW REQUIRED
TB-036 | Mandatory discipline output / inspection | Bootstrap stability | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.4 Group C - Discipline (always applied, never optional) | TB-036 | DESIGN DEPTH PENDING | Always-applied discipline; inspect outputs only. Do not turn it into an optional drag/drop bypass. | SEMANTIC REVIEW REQUIRED
TB-037 | Mandatory discipline output / inspection | Confounder check | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.4 Group C - Discipline (always applied, never optional) | TB-037 | DESIGN DEPTH PENDING | Always-applied discipline; inspect outputs only. Do not turn it into an optional drag/drop bypass. | SEMANTIC REVIEW REQUIRED
TB-038 | Toolbox entry | Control chart | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-038 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-039 | Toolbox entry | Capability | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-039 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-040 | Toolbox entry | Pareto of causes | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-040 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-041 | Toolbox entry | Yield decomposition | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-041 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-042 | Toolbox entry | Downtime impact split | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-042 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-043 | Toolbox entry | Transition analysis | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-043 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-044 | Toolbox entry | Window comparison | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.5.5 Group D - Process and quality specific | TB-044 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-045 | Toolbox entry | Feature assembly | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-045 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-046 | Toolbox entry | Genealogy roll-up | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-046 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-047 | Toolbox entry | Lag feature | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-047 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-048 | Toolbox entry | Rolling window feature | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-048 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-049 | Toolbox entry | Binning | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-049 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-050 | Toolbox entry | Encoding | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-050 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-051 | Toolbox entry | Missing-value policy | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-051 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-052 | Toolbox entry | Scaling | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.2 Group E - Feature engineering blocks | TB-052 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-053 | Toolbox entry | Train/validation split | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-053 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-054 | Toolbox entry | Classification model | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-054 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-055 | Toolbox entry | Regression model | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-055 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-056 | Toolbox entry | Anomaly detection | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-056 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-057 | Toolbox entry | Clustering | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-057 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-058 | Toolbox entry | Feature importance | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-058 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-059 | Toolbox entry | Partial dependence | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-059 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-060 | Toolbox entry | Model evaluation | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-060 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-061 | Toolbox entry | Calibration | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-061 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-062 | Toolbox entry | Scoring | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.3 Group F - Model blocks | TB-062 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-063 | Toolbox entry | Early-stage risk score | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4 Group G - Prediction and recommendation | TB-063 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-064 | Toolbox entry | Downstream remediation search | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4 Group G - Prediction and recommendation | TB-064 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-065 | Toolbox entry | Practice comparison | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4 Group G - Prediction and recommendation | TB-065 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-066 | Toolbox entry | Suggestion generation | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4 Group G - Prediction and recommendation | TB-066 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-067 | Toolbox entry | Value attachment | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4 Group G - Prediction and recommendation | TB-067 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-068 | Toolbox entry | Practice reconstruction | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4a Practice authoring blocks - Group G2 (guideline 1.3.b) | TB-068 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-069 | Toolbox entry | Practice-outcome linkage | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4a Practice authoring blocks - Group G2 (guideline 1.3.b) | TB-069 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-070 | Toolbox entry | Best-practice benchmark | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4a Practice authoring blocks - Group G2 (guideline 1.3.b) | TB-070 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-071 | Toolbox entry | Failure-practice linkage | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4a Practice authoring blocks - Group G2 (guideline 1.3.b) | TB-071 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-072 | Toolbox entry | Drift detection | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.6.4a Practice authoring blocks - Group G2 (guideline 1.3.b) | TB-072 | DESIGN DEPTH PENDING | Map the exact input/output/configuration/validation to a selected-node inspector, with typed ports and refusal/recovery as applicable. | SEMANTIC REVIEW REQUIRED
TB-073 | Engine classification reference | Correlation | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-073 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-074 | Engine classification reference | Statistics | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-074 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-075 | Engine classification reference | Deep analysis | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-075 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-076 | Engine classification reference | Anomaly | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-076 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-077 | Engine classification reference | Similarity / fingerprint | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-077 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-078 | Engine classification reference | Supervised prediction | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-078 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-079 | Engine classification reference | Practice learning | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-079 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-080 | Engine classification reference | Remediation search | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-080 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-081 | Engine classification reference | Scenario | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-081 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
TB-082 | Engine classification reference | Value | M3 | T-267 | T-246; T-248; T-187 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §36.4 Naming discipline, ruled | TB-082 | DESIGN DEPTH PENDING | Reference classification row; reconcile with the actual registry. Not automatically another independent draggable block. | SEMANTIC REVIEW REQUIRED
INS-01 | Property inspector | Source | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-01 | DESIGN DEPTH PENDING | Schema, table (typed pickers), row estimate, column checklist with types, sample toggle ¦ Validation: Table must be registered; at least one column ¦ Preview: First 20 rows | SEMANTIC REVIEW REQUIRED
INS-02 | Property inspector | Join | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-02 | DESIGN DEPTH PENDING | Type (inner/left/right/full), **ordered key-pair rows** with add and reorder, grain on both sides, cardinality (declared, then observed after preview), **attribution rule when grain converts**, weight expression ¦ Validation: `TR08` incomplete or unordered members; `TR09` conversion without attribution; `TR10` weights cannot sum to one; observed cardinality contradicting declared is a warning ¦ Preview: Row counts in, out and expansion factor; **a fan-out warning when output exceeds either input** | SEMANTIC REVIEW REQUIRED
INS-03 | Property inspector | Filter | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-03 | DESIGN DEPTH PENDING | Expression (opens 5.2.16), null handling, case sensitivity ¦ Validation: Return type must be boolean ¦ Preview: Rows in, rows out, percentage removed; a warning above 95 percent removal | SEMANTIC REVIEW REQUIRED
INS-04 | Property inspector | Select columns | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-04 | DESIGN DEPTH PENDING | Column checklist, rename pairs, output order ¦ Validation: At least one column; no duplicate output name ¦ Preview: Output schema | SEMANTIC REVIEW REQUIRED
INS-05 | Property inspector | Group by | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-05 | DESIGN DEPTH PENDING | Group keys (multi), aggregate rows: function, column, alias ¦ Validation: An aggregate over a grouped key; a non-aggregated column not in the keys ¦ Preview: Group count and the largest group size | SEMANTIC REVIEW REQUIRED
INS-06 | Property inspector | Derived column | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-06 | DESIGN DEPTH PENDING | Name, expression (opens 5.2.16), declared type, unit ¦ Validation: Name collision; type mismatch; unit mismatch inside arithmetic ¦ Preview: The column beside its inputs | SEMANTIC REVIEW REQUIRED
INS-07 | Property inspector | Sort / Limit | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-07 | DESIGN DEPTH PENDING | Column, direction, n ¦ Validation: n within the absolute cap ¦ Preview: - | SEMANTIC REVIEW REQUIRED
INS-08 | Property inspector | Union | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-08 | DESIGN DEPTH PENDING | Second input, column alignment map ¦ Validation: Arity and type compatibility per aligned pair ¦ Preview: Combined count | SEMANTIC REVIEW REQUIRED
INS-09 | Property inspector | Output to canonical | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-09 | DESIGN DEPTH PENDING | Target entity (typed picker), field map rows, `const:` literals, provenance columns (read-only, shown) ¦ Validation: Required target field unmapped; type mismatch; the fifteen `PV` classes previewed ¦ Preview: **The projected error profile from the pre-flight sample**, grouped by code | SEMANTIC REVIEW REQUIRED
INS-10 | Property inspector | Statistical method | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-10 | DESIGN DEPTH PENDING | Method, outcome, factor set, window, stratification dimensions, method-auto toggle ¦ Validation: `ST01` to `ST06`; sample-size precondition checked before run ¦ Preview: Population size, and the readiness verdict inline | SEMANTIC REVIEW REQUIRED
INS-11 | Property inspector | Model | M3 | T-267 | T-246; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-11 | DESIGN DEPTH PENDING | Algorithm, feature set version, split strategy, missing-value policy, scaling, hyperparameters, acceptance floor ¦ Validation: `ML01` to `ML07`; a random split on time-ordered data warns ¦ Preview: Train and validation row counts, and the overlap count which must be zero | SEMANTIC REVIEW REQUIRED
INS-12 | Property inspector | Scoring | M3 | T-267 | T-246; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-12 | DESIGN DEPTH PENDING | Model version, scope rule, batch size, latency budget, trigger kind ¦ Validation: `PD01` schema mismatch with counts; `PD02` no active model ¦ Preview: Units in scope, and an estimated duration range | SEMANTIC REVIEW REQUIRED
INS-13 | Property inspector | Prediction | M3 | T-267 | T-246; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-13 | DESIGN DEPTH PENDING | Outcome, horizon stage, risk banding thresholds, confidence display ¦ Validation: Horizon stage must exist on the route; banding must be monotonic ¦ Preview: Distribution of scores on a sample | SEMANTIC REVIEW REQUIRED
INS-14 | Property inspector | Remediation | M3 | T-267 | T-246; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-14 | DESIGN DEPTH PENDING | Comparable-condition rule, candidate practice set, **minimum support**, expected-effect measure, limitations text ¦ Validation: Minimum support below the floor is refused; a proposed stage after the horizon is refused ¦ Preview: Candidate count, and how many pass support | SEMANTIC REVIEW REQUIRED
INS-15 | Property inspector | Alert condition | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-15 | DESIGN DEPTH PENDING | Parameter, comparator, limit or limit source (specification or operating limit), severity, message template with tokens ¦ Validation: Comparator outside the set; a template token that does not resolve ¦ Preview: The message rendered with sample values | SEMANTIC REVIEW REQUIRED
INS-16 | Property inspector | Action | M2 + M3 | T-265; T-267 | T-243; T-245; T-211; T-212; T-248 | PPIQ_Chapter4_Specific_Technical_Function_Description_v4.10.3.md §5.2.17 Per-block property inspectors | INS-16 | DESIGN DEPTH PENDING | Action kind (log, notify, route), channel, recipients, dedup window ¦ Validation: `AR01` no recipient ¦ Preview: Rendered notification | SEMANTIC REVIEW REQUIRED
S1-Block | Authoring / expression frame | Transformation — Block mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S1-Block | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S1-SQL | Authoring / expression frame | Transformation — SQL mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S1-SQL | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S2-Block | Authoring / expression frame | Widget / query — Block mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S2-Block | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S2-SQL | Authoring / expression frame | Widget / query — SQL mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S2-SQL | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S3-Block | Authoring / expression frame | Analysis — Block mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S3-Block | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S3-SQL | Authoring / expression frame | Analysis — SQL mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S3-SQL | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S4-Block | Authoring / expression frame | Model / features — Block mode | M3 | T-267 | T-246; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S4-Block | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S4-SQL | Authoring / expression frame | Model / features — SQL mode | M3 | T-267 | T-246; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S4-SQL | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S5-Block | Authoring / expression frame | Rule / alert — Block mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S5-Block | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
S5-SQL | Authoring / expression frame | Rule / alert — SQL mode | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | S5-SQL | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
EXPR-01 | Authoring / expression frame | Expression editor — typed row context | M2 + M3 | T-265; T-267 | T-243; T-244; T-245; T-248 | Chapter 4 v4.10.3 §5.2 / §5.5 / §5.6 (exact owning clause to be confirmed per frame) | EXPR-01 | DESIGN DEPTH PENDING | Per-purpose schema/toolbox/permission and representability; SQL diagnostic positions and read-only bounded preview; stable definitions; no SQL/RTL corruption. | EXACT SUBSECTION REQUIRED
EXPR-ITEM-01 | Expression vocabulary entry | + | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-02 | Expression vocabulary entry | − | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-03 | Expression vocabulary entry | × | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-04 | Expression vocabulary entry | ÷ | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-05 | Expression vocabulary entry | = | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-06 | Expression vocabulary entry | <> | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-07 | Expression vocabulary entry | > | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-08 | Expression vocabulary entry | >= | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-09 | Expression vocabulary entry | < | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-10 | Expression vocabulary entry | <= | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-11 | Expression vocabulary entry | AND | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-12 | Expression vocabulary entry | OR | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-13 | Expression vocabulary entry | NOT | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-14 | Expression vocabulary entry | IF / ELSE | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-15 | Expression vocabulary entry | IS NULL | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-16 | Expression vocabulary entry | LIKE | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-17 | Expression vocabulary entry | IN | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-18 | Expression vocabulary entry | BETWEEN | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-19 | Expression vocabulary entry | COALESCE | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-20 | Expression vocabulary entry | ROUND | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-21 | Expression vocabulary entry | ABS | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
EXPR-ITEM-22 | Expression vocabulary entry | Date arithmetic | M2 + M3 | T-265; T-267 | T-243; T-244; T-248 | Chapter 4 v4.10.3 §5.2.16 (verify applicable grammar for each purpose) | EXPR-01 | DESIGN DEPTH PENDING | Typed expression configuration inside the containing block; operator/function legality and named refusal; not a second arithmetic board. | SEMANTIC REVIEW REQUIRED
OPC-UX-01 | Missing OPC workflow design | Profile and trusted/rejected session | M2 | T-266 | T-224; T-113 | Chapter 2/6 OPC boundary; Chapter 3 B1; existing T-224..T-226 contracts | MISSING — to author | MISSING DESIGN — T-266 OWNS | endpoint, policy, certificate reference, authentication, source identity, connection test | EXACT CLAUSE REQUIRED BEFORE ACCEPTANCE
OPC-UX-02 | Missing OPC workflow design | Browse, tag select and registration | M2 | T-266 | T-225 | Chapter 2/6 OPC boundary; Chapter 3 B2; existing T-224..T-226 contracts | MISSING — to author | MISSING DESIGN — T-266 OWNS | namespace/node tree, type, tag identity, selection, bounded discovery, register | EXACT CLAUSE REQUIRED BEFORE ACCEPTANCE
OPC-UX-03 | Missing OPC workflow design | Bounded read and subscription | M2 | T-266 | T-225 | Chapter 2/6 OPC boundary; Chapter 3 B3; existing T-224..T-226 contracts | MISSING — to author | MISSING DESIGN — T-266 OWNS | sampling/publishing/deadband, budget/invalid settings, monitored items | EXACT CLAUSE REQUIRED BEFORE ACCEPTANCE
OPC-UX-04 | Missing OPC workflow design | Quality and source-time inspection | M2 | T-266 | T-226; T-233 | Chapter 2/6 OPC boundary; Chapter 3 B4; existing T-224..T-226 contracts | MISSING — to author | MISSING DESIGN — T-266 OWNS | StatusCode and Good/Bad/Uncertain; source/server/ingested timestamps; gaps | EXACT CLAUSE REQUIRED BEFORE ACCEPTANCE
OPC-UX-05 | Missing OPC workflow design | Disconnect, spool and replay | M2 | T-266 | T-226 | Chapter 2/6 OPC boundary; Chapter 3 B4; existing T-224..T-226 contracts | MISSING — to author | MISSING DESIGN — T-266 OWNS | buffer depth, outage, replay cursor/acknowledgement, duplicates and sequence loss | EXACT CLAUSE REQUIRED BEFORE ACCEPTANCE
OPC-UX-06 | Missing OPC workflow design | Capability/permission/refusal | M2 | T-266 | T-254; T-224; T-225; T-226 | Chapter 2/6 OPC boundary; Chapter 3 B6; existing T-224..T-226 contracts | MISSING — to author | MISSING DESIGN — T-266 OWNS | separate current unavailable versus target commissioned; no flip of runtime flags | EXACT CLAUSE REQUIRED BEFORE ACCEPTANCE

## UI Controls v223
Control review ID | Parent | Chapter control text | Type | Position / reachability | Enabled / condition | Source | Release portion | Design owner | Trace state | Acceptance requirement
A1/CTRL-01 | A1 | Username | `StandardInput` | card, first | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A1/CTRL-02 | A1 | Password | `StandardInput type=password` | card, second | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A1/CTRL-03 | A1 | Sign in | primary button | card footer, full width | both fields non-empty | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A1/CTRL-04 | A1 | Second factor code | `StandardInput` | replaces form after step 1 | challenge issued | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A1/CTRL-05 | A1 | Language | select | block-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A2/CTRL-01 | A2 | Journey rail node | link chip | rail | node's page permitted | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A2/CTRL-02 | A2 | Stat tile | `StandardStatGrid` cell | grid | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A2/CTRL-03 | A2 | Readiness dimension bar | progress bar | inline-start column | gate evaluated | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A2/CTRL-04 | A2 | Finding row | link | inline-end column | findings exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
A2/CTRL-05 | A2 | Refresh | secondary | header inline-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §A2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-01 | B1 | Refresh | secondary, `RefreshCw` | layout header, inline-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-02 | B1 | New Connection Profile | primary, `Plus` | panel 1 header, inline-end | LIST mode | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-03 | B1 | Back | secondary | panel 1 header, inline-start | FORM mode | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-04 | B1 | Name / Code / Host / Port / Database / Schema / Username | `StandardInput` | form grid, two columns | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-05 | B1 | Password | `StandardInput type=password` | form grid | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-06 | B1 | Provider type | `StandardSelect` | form grid | provider types loaded | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-07 | B1 | Source system tag | `StandardSelect` | form grid | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-08 | B1 | File path | `StandardInput` | form grid | provider is file-based | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-09 | B1 | Max rows / Timeout / Requests per minute / Approved window | `StandardInput`, time pickers | budget group | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-10 | B1 | Test connection | secondary | form footer | host, database and credentials non-empty | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-11 | B1 | Save | primary | form footer, inline-end | client validation passes | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B1/CTRL-12 | B1 | Row Edit / Test / Activate / Deactivate | icon buttons | table row, inline-end | per row state | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B1 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B2/CTRL-01 | B2 | Connection selector | `StandardSelect` | inline-start, block-start | profiles exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B2/CTRL-02 | B2 | Tree node expander | disclosure | tree | node has children | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B2/CTRL-03 | B2 | Register | primary | tree row, inline-end | a table is selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B2/CTRL-04 | B2 | Unregister | secondary | registered row | row selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B2/CTRL-05 | B2 | Filter tables | `StandardInput` search | above tree | tree loaded | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B3/CTRL-01 | B3 | Dataset row | list item | inline-start | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B3/CTRL-02 | B3 | Column include | checkbox per column, plus select-all | Columns group | dataset selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B3/CTRL-03 | B3 | Business key | multi-select of columns | Business key group | dataset selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B3/CTRL-04 | B3 | Watermark column | `StandardSelect` of orderable columns only | Watermark group | dataset selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B3/CTRL-05 | B3 | Save preparation | primary | footer, inline-end | at least one column included | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B3 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B4/CTRL-01 | B4 | Run due imports | primary | batch card header | at least one dataset is due | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B4/CTRL-02 | B4 | Batch row expander | disclosure | batch table | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B4/CTRL-03 | B4 | Re-run batch | secondary | expanded row | batch is terminal | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B4/CTRL-04 | B4 | Mapping selector | `StandardSelect` | schedule card | mappings exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B4/CTRL-05 | B4 | Interval minutes | `StandardInput` numeric, default 15 | schedule card | mapping selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B4/CTRL-06 | B4 | Save schedule | primary | schedule card footer | interval valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B4 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B5/CTRL-01 | B5 | Family / Status / Time filter | `StandardSelect` | filter bar | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B5/CTRL-02 | B5 | Run now | primary small | row, inline-end | job runnable and not running | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B5/CTRL-03 | B5 | Pause / Resume | secondary small | row, inline-end | per state | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B5/CTRL-04 | B5 | Cancel | destructive small | row, inline-end | job running | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B5/CTRL-05 | B5 | Status pill | `StatusPill` | Status column | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
B6/CTRL-PROSE | B6 | Filter by state; export the matrix. No mutating control exists on this page by design. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §B6 | M2 | T-265 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
C1/CTRL-01 | C1 | Mode toggle Block / SQL | segmented control | block-start, inline-start | SQL requires tier and role | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-02 | C1 | Zoom in / out / **Zoom fit** / **Arrange** | icon buttons | canvas toolbar | board has nodes | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-03 | C1 | Validity indicator | badge | beside Run | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-04 | C1 | Preview (dry-run) | secondary | toolbar inline-end | graph valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-05 | C1 | Compiled SQL | secondary | toolbar inline-end | graph valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-06 | C1 | Publish version | primary | toolbar inline-end | graph valid and previewed | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-07 | C1 | Export / Import definition | icon buttons | toolbar overflow | always / always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-08 | C1 | Node status badge | badge on node | each node | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-09 | C1 | Node inspector fields | typed controls fed from live schema | inline-end when a node is selected | node selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C1/CTRL-10 | C1 | Debug log severity filter | segmented | log header | log has entries | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-01 | C2 | Time range | `StandardSelect` | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-02 | C2 | Re-validate | secondary | header inline-end | a definition is selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-03 | C2 | Open in Studio | link per row | mapping row | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-04 | C2 | Acknowledge drift | secondary | drift row | drift unacknowledged | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-05 | C2 | Quarantine group expander | disclosure per error code, with count and examples | quarantine section | quarantined rows exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-06 | C2 | **Reprocess quarantined** | primary, **confirmed** | quarantine section header | unresolved quarantined rows exist for the selected definition version | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-07 | C2 | Dismiss row | destructive small, confirmed, **reason required** | quarantine example row | row selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C2/CTRL-08 | C2 | Export quarantine | secondary | quarantine section header | rows present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C2 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C3/CTRL-PROSE | C3 | Class / Source / Severity filters; Run scan (primary); Export (secondary); Open the affected dataset (link). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C3 | M2 | T-265 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
C4/CTRL-PROSE | C4 | Tree expanders; search; Show unmapped only (toggle); Open in Genealogy (link where a unit is selected). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C4 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
C5/CTRL-01 | C5 | Search unit | `StandardInput` | header inline-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C5/CTRL-02 | C5 | Direction toggle back / forward / both | segmented | graph header | graph loaded | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C5/CTRL-03 | C5 | Depth | stepper | graph header | graph loaded | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C5/CTRL-04 | C5 | Edge weight badge | badge | each edge | weight present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C5/CTRL-05 | C5 | Drill to source rows | link per node | node detail | provenance present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C5/CTRL-06 | C5 | Open in Workspace | secondary | header inline-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C5 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-01 | C6 | Entity search | `StandardInput` | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-02 | C6 | State filter: all / validated / unproven / ambiguous / superseded | `StandardSelect` | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-03 | C6 | Graph node | selectable | centre | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-04 | C6 | Preferred-path badge | badge | on the edge | a preferred path exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-05 | C6 | Ambiguity badge | badge | on the edge | two equally valid paths | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-06 | C6 | Member list | read-only ordered rows | detail panel | relationship selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-07 | C6 | Grain, cardinality, attribution rule | read-only fields | detail panel | relationship selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-08 | C6 | Validate against data | secondary | detail panel | validationState is unproven | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-09 | C6 | Set preferred path | secondary, confirmed | detail panel | ambiguityState is ambiguous | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-10 | C6 | Open source definition | link | detail panel | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-11 | C6 | Path finder: from / to | two selects plus Find | header | two entities chosen | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
C6/CTRL-12 | C6 | Retire relationship | destructive, confirmed | detail panel | Administrator, and no active dependent | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §C6 | M2 | T-265 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-01 | D1 | Sheet selector | `StandardSelect` | header | more than one sheet | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-02 | D1 | Filter bar field | dropdown per field | filter bar | field is filterable | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-03 | D1 | Clear all | secondary | selections bar, inline-end | a selection exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-04 | D1 | Selection chip | removable chip | selections bar | per selection | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-05 | D1 | Card hover tools: maximise, collapse, export, clone, remove, edit | icon buttons | card header, inline-end | per permission | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-06 | D1 | Chart-type switcher | select on card | card header | server registry accepts the type for this binding | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-07 | D1 | Save layout / Reset layout | primary / secondary | header inline-end | layout dirty | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D1/CTRL-08 | D1 | Edit mode toggle | segmented | header | edit permission | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D1 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-01 | D2 | Create page | primary | inline-start header | quota not exhausted | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-02 | D2 | Add widget | primary | preview header | page selected, quota available | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-03 | D2 | Kind picker: chart, table, KPI, calculated label, calendar filter, filter | tile picker | modal step 1 | Add widget pressed | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-04 | D2 | Widget name | `StandardInput` | modal step 2 | kind chosen | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-05 | D2 | Binding mode: Catalogue / Query | segmented | shell, block-start | always; Query needs Pro and role | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-06 | D2 | Chart type / Dimension / Measure | `StandardSelect` | shell, catalogue mode | catalogue mode | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-07 | D2 | Query editor | monospace editor, IBM Plex Mono | shell, query mode | query mode | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-08 | D2 | Run test | secondary | shell footer | query non-empty | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-09 | D2 | Result columns to axes | mapping rows | shell, after Run test | test returned columns | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-10 | D2 | Saved filter | filter rows | shell | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-11 | D2 | Preview | secondary | shell footer | binding valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D2/CTRL-12 | D2 | Save | primary | shell footer, inline-end | binding valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D2 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-01 | D3 | New definition | primary | inline-start header | quota available | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-02 | D3 | Outcome / Grain / Window blocks | selects fed from `definition-options` | centre | options loaded | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-03 | D3 | Method | `StandardSelect` from the method registry | centre | outcome and grain chosen | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-04 | D3 | Population filters | filter rows | centre | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-05 | D3 | Parity line | badge | payload panel | payload built | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-06 | D3 | Check readiness | secondary | readiness panel | outcome, grain, window chosen | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-07 | D3 | Run governed analysis | primary | footer inline-end | definition valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D3/CTRL-08 | D3 | Save definition | primary | footer | definition valid | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D4/CTRL-01 | D4 | Outcome / Window / Method / Significance filters | `StandardSelect` | filter bar | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D4/CTRL-02 | D4 | Sortable column headers | `SortableDataTable` | table head | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D4/CTRL-03 | D4 | Evidence drawer | drawer | inline-end on row click | row selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D4/CTRL-04 | D4 | Drill to population | link | drawer | population recorded | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D4/CTRL-05 | D4 | Export | secondary | header inline-end | rows present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D4/CTRL-06 | D4 | Add to page | secondary | drawer footer | authoring permission | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D5/CTRL-PROSE | D5 | Horizon select; risk-class filter; Recalculate (secondary); Open in Genealogy (link); Export. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D5 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
D6/CTRL-PROSE | D6 | Generate suggestions (primary); Accept / Reject / Defer (per card, Accept primary, Reject Hot Red); Comment (`StandardTextArea`); Open the evidence (link per reference). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D6 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
D7/CTRL-PROSE | D7 | Period select; Edit cost assumptions (secondary, Administrator only); Drill to rows (link per input); Compare scenario (secondary); Export monthly report (primary). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D7 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
D8/CTRL-01 | D8 | Outcome and grain select | `StandardSelect` | header | registered values exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-02 | D8 | Readiness cell | selectable, measured value against threshold | matrix | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-03 | D8 | Ensure jobs | secondary | header inline-end | Data Engineer | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-04 | D8 | Train | primary | model row | a snapshot exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-05 | D8 | **Activate** | primary, confirmed | model row | acceptance floor met and schema-compatible | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-06 | D8 | Retire model | destructive, confirmed | model row | not the only serving version | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-07 | D8 | **Serving-role column** | badge: **Active**, **Fallback** or **None** | model table | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-08 | D8 | **Approve as fallback** | secondary, **confirmed, justification required** | model row | all six fallback conditions currently pass | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-09 | D8 | **Remove fallback approval** | destructive, confirmed | model row | `serving_role = 'serving_fallback'` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-10 | D8 | **Fallback readiness panel** | per condition: approved, lifecycle status, schema compatibility, drift and validity, outcome and grain match, acceptance floor - each pass or fail with its measured basis | inline-end when a model is selected | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-11 | D8 | **Current fallback summary** | the approved fallback version per outcome and grain, its justification, who approved it and when, its validity window | header block | a fallback is approved | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-12 | D8 | **Latency and deadline health** | miss rate, median and p95 delivery latency, current scoring mode, per outcome and route | block-end | predictions exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D8/CTRL-13 | D8 | Label preview refresh | secondary | inline-end | outcome selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D8 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-01 | D9 | Horizon | `StandardSelect` | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-02 | D9 | Outcome / risk class / stage filters | `StandardSelect` | header | registered values exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-03 | D9 | **Scoring-mode badge** | badge with text: Event, Micro-batch or Scheduled | header inline-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-04 | D9 | **Degraded-mode notice** | persistent banner naming the fallback version and reason | block-start | `fallbackInUse` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-05 | D9 | Queue row | selectable row | table | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-06 | D9 | **Time-remaining column** | countdown to `actionableDeadlineUtc` | table | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-07 | D9 | **Past-actionable-stage chip** | chip reading "past actionable stage - historical evidence" | table row and drawer | `isPastActionableStage` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-08 | D9 | Driver bar | horizontal bar per driver, with current value against normal range | drawer | unit selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-09 | D9 | **Actionable remediation card** | card: practice, proposed stage, support, expected-effect interval, limitations, uplift basis | drawer, Decision group | **`canAccept` is true** | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-10 | D9 | **Evidence-only entry** | list row reading "observed historical difference - not actionable here", with the failed check named | drawer, Investigation group | `eligibilityState = evidence_only` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-11 | D9 | **Exploratory entry** | list row behind an explicit disclosure, with the uncertainty and the failed check stated, **no accept affordance** | drawer, Investigation group | `eligibilityState = exploratory` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-12 | D9 | **Show gate evaluation** | secondary, opens the nine-check result | drawer | any candidate selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-13 | D9 | **Acknowledge** | secondary | drawer footer | open and unacknowledged, engineer or operator | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-14 | D9 | **Assign** | secondary, opens assignee and due-stage picker | drawer footer | acknowledged, engineer role | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-15 | D9 | **Accept** | primary, confirmed | drawer footer, Decision group | **`canAccept` is true. Nothing else is tested** | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-16 | D9 | **Reject** | destructive, confirmed, **reason required** | drawer footer, Decision group | **`canAccept` is true** | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-17 | D9 | **Defer** | secondary, with a return-stage picker | drawer footer, Decision group | **`canAccept` is true** | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-18 | D9 | **Inspect** | secondary, opens the candidate detail | drawer, Investigation group | any non-actionable candidate | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-19 | D9 | **Compare** | secondary, opens the comparable cohort | drawer, Investigation group | any non-actionable candidate | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-20 | D9 | **Escalate for investigation** | secondary, reason required | drawer, Investigation group | `evidence_only` or `exploratory` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-21 | D9 | **Record action** | primary, opens planned versus actual action, timestamp and process stage | drawer footer | decision is accept | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-22 | D9 | **View evaluation** | link to the prediction evaluation and remediation effectiveness | drawer footer | evaluation exists or is pending | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-23 | D9 | Open in Genealogy | link | drawer | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D9/CTRL-24 | D9 | Open the model in D8 | link | drawer | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-01 | D10 | Outcome select | `StandardSelect` | header | registered outcomes exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-02 | D10 | Context select | `StandardSelect` from registry | header | contexts exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-03 | D10 | **Match-type filter: All, Exact only, Relaxed only** | segmented | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-04 | D10 | **Sensitivity filter: All, Stable only, Exclude fragile** | `StandardSelect` | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-05 | D10 | **Match-type badge** | badge reading **Exact** or **Relaxed (L`<n>`)** | every benchmark card and row | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-06 | D10 | **Sensitivity badge** | badge reading **Stable**, **Fragile** or **Unstable** | every benchmark card and row | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-07 | D10 | **Support pair** | text `exact <n> / relaxed <m>` | benchmark card | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-08 | D10 | **Relaxed-dimensions disclosure** | expander listing each relaxed dimension, its original and widened tolerance and the rule applied | benchmark card | `similarityLevel > 0` | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-09 | D10 | **Sensitivity detail** | expander showing the band tested and what changed at each end | benchmark card | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-10 | D10 | Practice row expander | disclosure showing the parameter combination and sequence | comparison table | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-11 | D10 | Evidence link | link to the periods behind the statistic | benchmark card and row | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-12 | D10 | Drift period select | date-range | drift panel | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D10/CTRL-13 | D10 | Export | secondary | header inline-end | rows present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D10 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-01 | D11 | New scenario | primary | inline-start header | quota available | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-02 | D11 | Baseline selector | `StandardSelect` (period, context or a saved state) | variable panel | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-03 | D11 | Variable row: include toggle, value or range | toggle plus numeric or slider | variable panel | variable registered and model-supported | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-04 | D11 | Fixed assumptions | read-only list | variable panel | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-05 | D11 | Model version | `StandardSelect` | variable panel | an active model exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-06 | D11 | Run simulation | primary | footer inline-end | at least one variable included and all values in range | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-07 | D11 | Save scenario | secondary | footer | a result exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-08 | D11 | Compare | secondary | comparison strip | two or more saved scenarios | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D11/CTRL-09 | D11 | Export | secondary | header inline-end | a result exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D11 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-01 | D12 | Compare by | `StandardSelect` from registry: line, equipment, route, product family, shift or crew where registered, period | header | registered dimensions exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-02 | D12 | Measure | `StandardSelect` from registry | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-03 | D12 | Period and comparison period | date-range pair | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-04 | D12 | Matrix cell | selectable | matrix | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-05 | D12 | Normalise by | `StandardSelect` (per tonne, per hour, per unit) | header | measure supports it | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-06 | D12 | Significance badge | badge with text | significance panel | both populations above minimum | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-07 | D12 | Compare to own best practice | secondary | block-end | practice benchmarks exist for the context | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
D12/CTRL-08 | D12 | Export | secondary | header inline-end | a result exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §D12 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E2/CTRL-PROSE | E2 | Grounding policy select (`strict-citations-required`); Evidence policy select (`citations-and-provenance-required`); Max citations stepper; Tools matrix (tool against role and tier); Knowledge sources checklist; Glossary term and synonym rows; Guardrail phrase rows; Serving mode select (self-hosted, private endpoint, customer model) with the no-egress indicator; Save (primary); Reset (secondary, confirmed); Reindex (secondary). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E2 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
E3/CTRL-01 | E3 | Run evaluation | primary | header inline-end | not already running | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-02 | E3 | Rule name | `StandardInput`, placeholder "<rule name>" | rule form | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-03 | E3 | Parameter code | `StandardInput`, placeholder "<parameter_code>" | rule form | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-04 | E3 | Comparator | `StandardSelect`, exactly `>` `>=` `<` `<=` `=` | rule form | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-05 | E3 | Limit | `StandardInput` numeric, placeholder "<limit value>" | rule form | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-06 | E3 | Severity | `StandardSelect` Info / Warning / Critical | rule form | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-07 | E3 | Add rule | primary | rule form footer | validation passes | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-08 | E3 | Deactivate rule | secondary | rules row | rule active | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E3/CTRL-09 | E3 | Acknowledge | secondary | log row | entry unacknowledged | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E3 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E4/CTRL-PROSE | E4 | Run review now (primary, disabled with a spinner while busy); per proposal: Dry-run (secondary), Approve (primary, confirmed), Reject (Hot Red); Open provenance (link). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E4 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
E5/CTRL-PROSE | E5 | New definition (primary); Sections picker; Period select; Recipients rows; Schedule (cron-like select, plain language); Generate now (primary); Download (link per output); Delivery target rows (email, webhook). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E5 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
E6/CTRL-01 | E6 | New routing rule | primary | inline-start header | Administrator | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-02 | E6 | Source channel and severity | two selects | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-03 | E6 | Recipients: roles and users | multi-select | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-04 | E6 | Delivery channel: in-app, email, webhook | multi-select with per-channel target field | editor | channel enabled in settings | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-05 | E6 | Escalate after | duration stepper plus escalation recipients | editor | acknowledgement is required | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-06 | E6 | Working hours and quiet periods | time ranges plus days | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-07 | E6 | Deduplication window | duration | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-08 | E6 | Grouping key | `StandardSelect` from registry | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-09 | E6 | Rate limit | count per period | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-10 | E6 | Suppression rule | condition rows | suppression panel | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-11 | E6 | Test delivery | secondary | editor footer | recipients and channel set | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-12 | E6 | Save rule | primary | editor footer | validation passes | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-13 | E6 | Retry delivery | secondary | delivery row | delivery failed and retries remain | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
E6/CTRL-14 | E6 | Dead-letter list | table | delivery panel | dead letters exist | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §E6 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F1/CTRL-PROSE | F1 | New user (primary); Role select; permission cells (inherited rendered Muted Steel, overridden rendered Electric Cyan); Reset overrides (secondary); Deactivate (Hot Red, confirmed); Force password reset (secondary); Require second factor (toggle). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F1 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
F2/CTRL-PROSE | F2 | Paste token (`StandardTextArea`); Apply (primary); Verify (secondary); capability list (read-only, next-tier additions shown Muted Steel); five meter bars each linking to the administration page that would relieve it. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F2 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
F3/CTRL-PROSE | F3 | Cell limit editor; Add override (secondary); Remove override; Save (primary); Reset role default (secondary, confirmed). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F3 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
F4/CTRL-01 | F4 | New definition | primary | header | **Administrator only** | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-02 | F4 | View toggle Table / Graph | segmented | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-03 | F4 | **Target definition** | `StandardSelect` of published definitions **filtered to the surface the job class requires** | Schedule tab | job class requires a target | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-04 | F4 | **Version policy** | segmented: **Current published** or **Pinned** | Schedule tab | a target is chosen | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-05 | F4 | **Pinned version** | `StandardSelect` of published version numbers | Schedule tab | policy is Pinned | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-06 | F4 | **Open the target definition** | link | Schedule tab | a target is chosen | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-07 | F4 | Schedule editor | schedule control in plain language | Schedule tab | definition selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-08 | F4 | Pool select (import, projection, analysis, ml, report, retention) | `StandardSelect`, **separate confirmed action** | Schedule tab | definition selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-09 | F4 | Compute weight stepper | stepper, **confirmed** | Schedule tab | definition selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-10 | F4 | **Add dependency** | primary small | Dependencies tab | definition selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-11 | F4 | **Depends-on job** | `StandardSelect` of job definitions | dependency row | adding or editing | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-12 | F4 | **Dependency kind** | `StandardSelect`: data, schedule, resource | dependency row | adding or editing | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-13 | F4 | **Required / Optional** | toggle; required is the default | dependency row | adding or editing | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-14 | F4 | **Version pin** | `StandardSelect`: current published, or a specific version number | dependency row | dependency kind is data | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-15 | F4 | **Staleness tolerance** | duration stepper in minutes | dependency row | dependency kind is data | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-16 | F4 | Remove dependency | destructive small, confirmed | dependency row | dependency exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-17 | F4 | **Validate graph** | secondary | Dependencies tab footer | a dependency changed | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-18 | F4 | **Impact preview** | secondary | header inline-end | definition selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-19 | F4 | Enable / Disable | secondary | row or editor | per state | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-20 | F4 | Delete | destructive, confirmed | row | no dependent definition | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-21 | F4 | DAG node | selectable, coloured by last outcome | Graph view | Graph view | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-22 | F4 | DAG edge | solid required, dashed optional | Graph view | Graph view | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F4/CTRL-23 | F4 | Highlight critical path | toggle | Graph view header | Graph view | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F4 | M2 + M3 | T-265; T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-01 | F5 | Family tabs | `StandardTabs` | header | per readable family | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-02 | F5 | **Live tail** | toggle with pause | header inline-end | a family tab is active | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-03 | F5 | Time range / Severity / Actor / Job family / Channel | filters | filter bar | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-04 | F5 | Free-text search | `StandardInput` | filter bar | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-05 | F5 | **Correlate by run** | link on any row carrying a run identifier | entry row | `run_id` present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-06 | F5 | Correlation panel | cross-family entry list for that run, time-ordered | inline-end | a run selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-07 | F5 | Open the run in B5 | link | correlation panel | run exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-08 | F5 | Pin filter | secondary | filter bar | a filter is set | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-09 | F5 | Export | secondary | header inline-end | rows present | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-10 | F5 | Row expander | disclosure | entry row | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F5/CTRL-11 | F5 | **Retention policy (read-only)** | text plus link to F9 | header | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F5 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F6/CTRL-PROSE | F6 | New channel (primary); Name; Family (fixed for built-ins); Severity mapping rows; Routing and export target select (none, file, syslog, webhook) with its address field; Reading roles multi-select; Save (primary); Disable (secondary). **Retention is not editable here.** F6 owns channel identity, severity mapping, routing and reading roles. **F9 exclusively owns retention, archival, cleanup, dry-run impact and legal hold**, because those are the only destructive controls and one destructive policy must have one surface. F6 renders the current retention as read-only text with **Manage retention in F9** as a link. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F6 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
F7/CTRL-PROSE | F7 | Site name and code; units selects; **plant time zone select - confirmed**; date and number format selects with a live example; retention per stage; per-tenant no-egress toggle; Save (primary). | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F7 | M2 + M3 | T-265; T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
F8/CTRL-PROSE | F8 | Language add; per-cell text editor; Mark reviewed (secondary); Mark verified in mirror (secondary); Export pack (secondary); Import pack (secondary, confirmed); Fallback language select. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F8 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
F9/CTRL-01 | F9 | Retention preset: 1, 2, 3, 6, 12 months, Custom | `StandardSelect` | editor | row selected | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-02 | F9 | Custom days | `StandardInput` numeric | editor | preset is Custom | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-03 | F9 | Archive before deletion | toggle | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-04 | F9 | Archive destination | `StandardSelect` plus target field | editor | archive on | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-05 | F9 | Cleanup schedule | schedule editor in plain language | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-06 | F9 | Maximum rows per cleanup batch | `StandardInput` numeric | editor | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-07 | F9 | **Dry-run preview** | secondary | editor footer | policy changed | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-08 | F9 | Save policy | primary, **confirmed** | editor footer | preview run and validation passed | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-09 | F9 | Run cleanup now | destructive, **confirmed** | editor footer | no legal hold | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-10 | F9 | View cleanup history | link | block-end | always | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-11 | F9 | Place legal hold | secondary, confirmed | editor | no hold | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
F9/CTRL-12 | F9 | Remove legal hold | destructive, confirmed | editor | hold exists | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §F9 | M3 | T-267 | PENDING SEMANTIC TRACE | Frame/state/node + action/outcome proof required
G1/CTRL-PROSE | G1 | Composer (`StandardTextArea`, auto-growing, Enter sends, Shift-Enter newline); Send (Electric Blue); citation chips (Electric Cyan) beneath each answer; evidence strip sliding from block-end with **Open in page**; expand-width, full-screen, new conversation, copy answer, close; three registry-derived suggested questions on an empty conversation. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G1 | M2 | T-265 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
G2/CTRL-PROSE | G2 | Navigation group expanders; navigation items (hidden, not disabled, where the role lacks permission); tier badge (Muted Steel Light, Amber Pro, Electric Blue Pro Plus, Cyan Green Enterprise) linking to F2; user menu with profile, units, time zone, language, sign out; breadcrumb segments as links. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G2 | M2 | T-265 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
G3/CTRL-PROSE | G3 | Search input; result groups (Pages, Fields, Measures, Definitions, Findings, Predictions, Log entries, Commands); arrow navigation; Enter to open; Escape to close. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G3 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
G4/CTRL-PROSE | G4 | Toast with message, optional action, dismiss; auto-dismiss for success; persistent for warning until dismissed. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G4 | M2 | T-265 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
G5/CTRL-PROSE | G5 | Title; the sentence stating **what was refused, why, and what would satisfy it**; the stable error code; the offending fragment echoed where one exists; a Retry where retrying can succeed; a link to the surface that would resolve it; and a copy-diagnostics action carrying the code and the trace identifier. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G5 | M2 | T-265 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.
G6/CTRL-PROSE | G6 | Run rows with name, stage, rows processed, progress or indeterminate spinner, elapsed time; Cancel where permitted; Open in Jobs Monitor; dismiss a completed row. | Source prose | See source | See source | PPIQ_Chapter3_General_Technical_Function_Description_v4.10.3.md §G6 | M3 | T-267 | PENDING DECOMPOSITION | Split prose obligations into controls; do not count zero controls.

## Changes v223
Task ID | Field | Before | After | Reason
T-265 | NEW TASK |  | Release-1 UI design depth, workflow and illustrated-companion convergence | Adopt Fable's proposed ID with bounded release scope, semantic/interaction acceptance and preserved runtime ownership.
T-266 | NEW TASK |  | Release-1 OPC-UA UI workflows and capability-truth design | Adopt Fable's proposed ID with bounded release scope, semantic/interaction acceptance and preserved runtime ownership.
T-267 | NEW TASK |  | Release-2 interface depth and enterprise BI/authoring parity design | Adopt Fable's proposed ID with bounded release scope, semantic/interaction acceptance and preserved runtime ownership.
T-247 | Depends On (IDs only) | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235; T-262; T-125 | T-092; T-207; T-212; T-213; T-241; T-242; T-243; T-244; T-245; T-253; T-254; T-256; T-258; T-104; T-108; T-211; T-235; T-262; T-125; T-265; T-266 | Require accepted UI delivery at integration acceptance
T-248 | Depends On (IDs only) | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257 | T-148; T-202; T-203; T-204; T-205; T-228; T-241; T-243; T-244; T-245; T-257; T-267 | Require accepted UI delivery at integration acceptance
T-249 | Depends On (IDs only) | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110 | T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-248; T-263; T-264; T-246; T-110; T-267 | Require accepted UI delivery at integration acceptance
T-148 | Contract-ready predecessors (not completion) | T-196; T-197; T-198; T-199; T-200 | T-196; T-197; T-198; T-199; T-200; T-265; T-266 | Explicit UI handoff, not runtime completion
T-247 | Task Validation | One end-to-end evidence pack proves zero C# diff, zero TypeScript diff and zero product-SQL diff; configuration/metadata only. The customer-shaped journey completes through product surfaces and replays deterministically. The evidence pack also proves the customer-facing connector availability text comes from executable capability truth, the authored output target is customer-shaped/governed, and no unapproved material-specific/public-schema runtime dependency is required. | One end-to-end evidence pack proves zero C# diff, zero TypeScript diff and zero product-SQL diff; configuration/metadata only. The customer-shaped journey completes through product surfaces and replays deterministically. The evidence pack also proves the customer-facing connector availability text comes from executable capability truth, the authored output target is customer-shaped/governed, and no unapproved material-specific/public-schema runtime dependency is required. v2.23.0 — T-265/T-266 designs are accepted before the release walkthrough. Re-run the same-binary customer journey against real governed services after UI integration: source test/cursor/import, authored field map and relationship publish, exact version execution/cancel/failure, quarantine evidence and reprocess, selected/possible/excluded propagation, applicable table navigation/export and grounded Assistant. Screenshots must identify actual runtime versus prototype. Live acceptance cannot be satisfied by a Figma import, label-presence script or template count. | Close visual-to-runtime acceptance seam, preserving the existing producer prerequisites.
T-248 | Task Validation | A 75-row acceptance matrix has no Unowned or Missing row. Every row is Implemented or PPIQ-Equivalent, has an automated/visual acceptance or an explicit non-applicability proof, and no proprietary Qlik syntax is required. Comparative acceptance against the defined PPIQ outcomes demonstrates no missing enterprise authoring row for inspector/style, bookmark/selection, pivot/crosstab, formatting, export and accessibility. Server-owned layouts survive a clean browser profile with localStorage cleared. Raw component colour literals are within an explicit design-token allowlist. A new definition authors arithmetic/logic through expression configuration and schedules repetition/control flow through the Job authority. A persisted legacy T-242 board definition reopens with semantic equivalence and an explicit compatibility marker; save-as-new converges to the current representation without losing history. v2.22.0 — Search scopes results/actions correctly; keyboard select/escape; tray shows run identity/state/progress with polling fallback and no fake percent; empty/failed/denied variants; existing 75-item authoring/BI acceptance retained. | A 75-row acceptance matrix has no Unowned or Missing row. Every row is Implemented or PPIQ-Equivalent, has an automated/visual acceptance or an explicit non-applicability proof, and no proprietary Qlik syntax is required. Comparative acceptance against the defined PPIQ outcomes demonstrates no missing enterprise authoring row for inspector/style, bookmark/selection, pivot/crosstab, formatting, export and accessibility. Server-owned layouts survive a clean browser profile with localStorage cleared. Raw component colour literals are within an explicit design-token allowlist. A new definition authors arithmetic/logic through expression configuration and schedules repetition/control flow through the Job authority. A persisted legacy T-242 board definition reopens with semantic equivalence and an explicit compatibility marker; save-as-new converges to the current representation without losing history. v2.22.0 — Search scopes results/actions correctly; keyboard select/escape; tray shows run identity/state/progress with polling fallback and no fake percent; empty/failed/denied variants; existing 75-item authoring/BI acceptance retained. v2.23.0 — Use the accepted T-267 semantic/interaction matrix and per-scene handoffs for the existing 75-item parity contract. Do not reimplement or defer the M2 associative engine/selection behavior already accepted under T-204. A visual omission creates a design obligation, not a reopened product task without regression. | Keep M2 baseline separate from M3 parity.
T-148 | Task Validation | A test asserting every page file under src/pages is reachable from a declared route. The count of page files moves toward 40 and no orphan remains. v2.10.2 TARGET-INVENTORY GATE — do not merely prove every existing page file is reachable or that the count 'moves toward 40'. Assert the exact Chapter 3 inventory: all 40 target route pages are declared once at canonical routes, all 6 global shell components are present, no target route is missing, and no orphan page file remains. Any temporary legacy alias must have a named retirement owner. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. v2.22.1 — v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. | A test asserting every page file under src/pages is reachable from a declared route. The count of page files moves toward 40 and no orphan remains. v2.10.2 TARGET-INVENTORY GATE — do not merely prove every existing page file is reachable or that the count 'moves toward 40'. Assert the exact Chapter 3 inventory: all 40 target route pages are declared once at canonical routes, all 6 global shell components are present, no target route is missing, and no orphan page file remains. Any temporary legacy alias must have a named retirement owner. v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. v2.22.1 — v2.22.0 dependency-kind clarification: T-196/T-197/T-198/T-199/T-200 are CONTRACT_READY predecessors for canonical route identity, permissions and unavailable-state interfaces, not full-M3-completion prerequisites for M2. Every one of the 40 target route identities remains in the inventory. M2 active surfaces must work; a deferred M3 surface must not promise executable functionality. Its implementation and runtime acceptance remain owned by the original M3 task. No M3 functionality is marked complete by T-148. v2.23.0 — Consume per-surface approved route/control/state handoffs from T-265/T-266; do not wait for entire backend tasks merely to draft UI. Bind chapter control IDs to actual reachable controls and screen variants. Shared shell/component geometry is required consistency, not a defect. A control-label match alone is not a workflow test. Complete all current M2 route content and record explicitly deferred M3 behavior under its named implementation owner. | Replace mechanical geometry/text-only notions of UI completeness.
T-101 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-265 owns B4/C2/C3 visual depth. Implement its applicable batch outcome/error/committed cursor and catalogue-driven quarantine list/detail/refusal/reprocess states under the existing T-101 scope; all row actions and counts use canonical tenant-scoped payloads. Do not limit the renderer to eight PV codes. | Explicit design-to-implementation handoff within existing functional scope.
T-125 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-265 receives the frozen B4/B5 operational payload. Preserve T-101 UI versus T-125 API/metrics ownership already assigned in v2.22.1; prototype figures never replace persisted evidence. | Explicit design-to-implementation handoff within existing functional scope.
T-243 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — Use T-265 C1/S1 selected-block, inspector, typed-port, validation/publish/reopen and SQL-mode handoffs. Shared C1/S1 shell is valid; prove semantic mode behavior rather than arbitrary visual differences. No change to canonical definition/relationship authorities. | Explicit design-to-implementation handoff within existing functional scope.
T-245 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — Use T-265 run/schedule/cancellation UI handoffs; cancellation acknowledgement is not a terminal Cancelled result until the executor/runtime records it. Render exact resolved version, failure counts and evidence, not a browser-derived success. | Explicit design-to-implementation handoff within existing functional scope.
T-098 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — Use T-265 C6 relationship list/detail/member/cardinality/path-validation handoffs. Trace every applicable Chapter 3 control to a reachable UI variant and keep resolver behavior under its existing authority. | Explicit design-to-implementation handoff within existing functional scope.
T-224 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-266 supplies OPC profile/session/trust target and refusal designs, with Worker 1 technical review. This is a contract handoff, not a full-design completion prerequisite for backend implementation. | Explicit design-to-implementation handoff within existing functional scope.
T-225 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-266 supplies browse tree, tag registration, bounded-read/subscription and keyboard/validation designs. Backend development follows frozen contracts in parallel; capability flags still require runtime proof. | Explicit design-to-implementation handoff within existing functional scope.
T-226 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-266 supplies quality/time/spool/reconnect/replay evidence presentation. The source-time and idempotency rules are unchanged; labelled design fixtures are not test-server proof. | Explicit design-to-implementation handoff within existing functional scope.
T-263 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-267 supplies E5 report-definition/generation/history/delivery interaction design. Generation remains a governed job; preserve period/filter/permission context and the existing source-evidence boundary. | Explicit design-to-implementation handoff within existing functional scope.
T-264 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-267 supplies D12 comparison/direction/sample-refusal/normalisation design. BM01/BM02 behavior and result evidence remain implementation acceptance, not illustrated proof. | Explicit design-to-implementation handoff within existing functional scope.
T-120 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-265 covers only the existing M2 user/role safety slice; T-267 covers deferred administration depth. Render permissions/refusals from the current canonical role contract. | Explicit design-to-implementation handoff within existing functional scope.
T-121 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — Use T-265 for existing M2 licence/quota states and T-267 for full administration depth. Entitlement, role and runtime capability are different inputs; no drawing enables a capability. | Explicit design-to-implementation handoff within existing functional scope.
T-215 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-265 provides the active M2 reference/measure direction and bound-result UI; T-267 expands the deferred authoring depth. Do not introduce a second Performance Reference authority. | Explicit design-to-implementation handoff within existing functional scope.
T-222 | UI Companion Reference | PPIQ_UI_Figma_Design_Spec_v4.10.3.md | PPIQ_UI_Figma_Design_Spec_v4.10.3.md v2.23.0 — T-265 provides the Release-1 reconciliation evidence/result/refusal surfaces. Use the canonical result envelope and citation references, not local display calculations. | Explicit design-to-implementation handoff within existing functional scope.
T-207 | Must Precede (IDs only) | T-150; T-224; T-247; T-254 | T-150; T-224; T-247; T-254; T-266 | Derived reciprocal completion dependencies, keyed by Task ID.
T-265 | Must Precede (IDs only) |  | T-247; T-267 | Derived reciprocal completion dependencies, keyed by Task ID.
T-266 | Must Precede (IDs only) |  | T-247 | Derived reciprocal completion dependencies, keyed by Task ID.
T-267 | Must Precede (IDs only) |  | T-248; T-249 | Derived reciprocal completion dependencies, keyed by Task ID.

## UI Delivery v223
PLANTPROCESS IQ ¦ UI CONVERGENCE • v2.23.0
Functional Design v4.10.3 unchanged. Design tasks close visual handoffs; product behavior still requires runtime acceptance.
Metric | M2 | M3 | Total | Meaning
Active tasks | 115 | 72 | 187 | 176 repaired + 3 design tasks
Done | 62 | 0 | 62 | T-099 closure preserved
In progress | 3 | 0 | 3 | No unearned status change
Not started | 50 | 72 | 122 | Design tasks not completed
Unknown estimates | 26 | 13 | 39 | Old/proposed estimates excluded
Task | Release | Design owner | Technical review | Status | Handoff boundary
T-265 | M2 | Worker 2 | Producer owners / CENTRAL | Not Started | Day-1 depth + full citation/Word/atlas correction
T-266 | M2 | Worker 2 | Worker 1: OPC contracts | Not Started | Missing OPC states inside canonical B1–B4/B6
T-267 | M3 | Worker 2 | Producer owners / CENTRAL | Not Started | All M3 UI remainder + advanced parity
Acceptance: semantic coverage + rendered/prototype walkthrough + implementation ownership; not frame counts or literal label matches.
START: UI Coverage v223 → UI Controls v223 → Backlog T-265..T-267. All 270 coverage records are pending depth work; this workbook contains no claim of a completed redesign.
T-099: ca02b40ea1b69050a45cb35a3e1d64f15b1f66af ¦ Task CLOSED GREEN; inherited DefinitionKind RED remains tracked separately.
[6 empty] | Status | M2 | M3
[6 empty] | Done | 62 | 0
[6 empty] | In Progress | 3 | 0
[6 empty] | Not Started | 50 | 72

## Book Register
Record | Owner / file | Purpose / result | Evidence / boundary
CONTROL | 14 files / 12 document families | Definition + six chapters + two illustrated editions + two DB design docs + identity + evaluation + latest Backlog | No extra subfolder or standalone deliverable in the book.
VERSIONS | Design v4.11.0 / Backlog v2.24.0 | Material Industrial Integration design change: functional contract + eight bounded execution tasks. | Owner-approved 16-Sep-2026. Existing runtime/closure evidence remains separately classified.
SOURCE | PPIQ_Backlog_v2.23.0_14Sep2026.xlsx | Actual Library backing file, 464046 bytes | SHA256 d1e7998d1f6ef382c69925ff8668f334a7a6da883bd3c74fdc52b194f9c9e7e6
DEFINITION | PPIQ_Definition.md | Book register + routing rules + preserved original owner brief | Existing owner definition incorporated verbatim; current chapters govern conflicts.
VISUALS | Chapter 3 MD v4.11.0 + illustrated Word regeneration under T-265/T-266 | Functional Industrial Integration clauses are in Markdown authority; derived images/prototype remain implementation/design-delivery work. | No native-Figma or browser runtime proof implied.
EDITORS | Chapter 4 MD v4.11.0 + illustrated Word regeneration under T-265/T-266/T-267 | Adds continuous acquisition Job/state-machine contract while preserving existing authoring/job authorities. | No second scheduler or edge runtime authority.
METHOD | Product Analysis and Evaluation Standard v1.2 | L1.8 converged to Release-1 Core and expanded to field/layout/recording/durability acceptance. | No implementation score increase without D5 evidence.
HANDOFFS | Contract Handoffs | T-265 already has T-262 and T-101 producers in the actual v2.23.0 source. | Verified rows 12 and 13; no new dependency or duplicate handoff added.
PENDING | T-265 capability-link simplification | Reviewer proposes reducing secondary links to actual D2 ownership and retaining broader traceability in UI Coverage. | Proposal recorded, not silently applied in a document-consolidation pass.
BASELINE | T-099 | CLOSED GREEN / COMMITTED remains unchanged. | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af; owner-reported, not release-wide GREEN.
ESTIMATES | T-106/T-108/T-262..T-267 | Eight absent/withdrawn/unconfirmed estimates preserved. | No estimated hours invented by repackaging.
ARCHIVE | Historical sheets already in the workbook | Earlier version references in historical evidence remain historical. | Current Authority, Governance and Backlog are current; old captions do not restore old authority.
SECURITY | Identity and Topology file | Existing file copied unchanged; complete book is confidential. | Do not publish or distribute unrestricted. No credential values added to workbook/chapter text.
DATABASE | Data Dictionary gains target-logical Industrial Integration sheet; Naming Standard v1.2 | Current physical catalogue is not relabelled as implemented target DDL. | New physical objects require canonical migration + catalogue convergence when implemented.
EXCLUDED | Standalone atlas / SVG folder / JSON / README / diff / handoff files | Not part of the controlled book. Useful content is integrated; executable tooling belongs in the repository. | No original user or Library file is deleted by creating this consolidated copy.
Task reference edit | Field | Prior output home | Current output home
T-265 | H | Regenerate the derived specification, atlas, editable scene import and illustrated Word chapters from the same revised UI data with source text preserved. | Update Chapter 3/4 MD and illustrated Word from one maintained visual/interaction specification, with source prose preserved and the coverage register inside this workbook. Keep native Figma/tooling source in its implementation environment; store Figma file/node and acceptance references here, not in additional design-book files.
T-265 | I | in data, Markdown, atlas and Word | in this workbook's coverage data and the Chapter 3/4 MD and illustrated Word
T-266 | I | include OPC scenes in the same atlas/Word citation checks | include OPC scenes in the same integrated Chapter 3/4 MD and Word citation checks
T-267 | H | Deliver the revised visual specification, native editable Figma evidence, atlas and both illustrated reading editions with stable traceable captions. | Deliver the revised visual specification inside Chapter 3/4 MD and both illustrated Word editions with stable traceable captions; retain native editable Figma evidence as file/node references inside this workbook. Do not add a standalone atlas or companion file to the design book.
T-267 | I | Regenerated Markdown/HTML/Word preserves chapter prose and correct citations. | Updated Chapter 3/4 Markdown and illustrated Word preserve chapter prose and correct citations; coverage and verification remain in the latest Backlog.
All active tasks | Design package reference | v4.10.3 / prior UI references | v4.11.0 Chapters 1–6; illustrated synchronization remains T-265/T-266/T-267; Backlog v2.24.0 is execution authority.

## Book Validation
14Sep book-consolidation check (historical) | Count | Result | Basis | Current task totals (formula) | M2 | M3 | Total
Active task IDs | 179 | PASS | 179 unchanged, unique Task IDs from actual Backlog. | Active | 107 | 72 | 179
M2 tasks | 107 | PASS | Preserved source classification. | Done | 62 | 0 | 62
M3 tasks | 72 | PASS | Preserved source classification. | Unconfirmed estimates | 18 | 13 | 31
Done | 58 | PASS | Including T-099, commit and parent unchanged.
In Progress | 4 | PASS | Preserved.
Not Started | 117 | PASS | Preserved.
Self-dependencies / self-precede | 0 | PASS | Both dependency columns checked by Task ID.
M2 completion depends on M3 | 0 | PASS | Completion edges only; contract-ready edges are not completion.
Reciprocal Must Precede | 179 | PASS | All reverse links equal forward dependency relations.
Acyclic nodes | 179 | PASS | Topological resolution covers all active tasks.
Declared external predecessors | 5 | PASS | T-032; T-035; T-036; T-057; T-064. Not silently removed.
T-265 T-262/T-101 handoffs | 2 | PASS | Already present in Contract Handoffs; retained.
Word images embedded | 607 | PASS | 497 + 110; original DOCX bytes retained.
Named dialog catalogue | 87 | PASS | Full derived descriptions integrated in Chapter 3 MD.
Toolbox catalogue | 82 | PASS | Full records integrated in Chapter 4 MD.
Detailed inspectors | 16 | PASS | Full records integrated in Chapter 4 MD.
Runtime / database certification |  | NOT RUN | File consolidation does not execute product gates.

## Task Evidence 15Sep
Task ID | Release / Phase | Current status | Evidence-review verdict | Recovered original delivery | Current scope conclusion | Recorded hours | Estimate state | Open completion predecessors | Source / location | Cell flags | Next evidence / action
T-086 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 77a8ea4f — T-086: freeze the legacy regression oracle and gate generic surfaces against its vocabulary ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row2. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-087 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: e7d82f078d7dfa4c1ca4ec6e88d0dbc7e1ecd6ba — subject not recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row3. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-088 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 6a62c9d6 — Establish canonical database migration authority ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row4. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-089 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 0fd79e5e3516cdfd0ab5a73a02e16638fd02693a — subject not recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row5. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-090 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: a6399d9c — subject not recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row6. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-091 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: c6d64289 — subject not recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row7. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-092 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: ab2962a4; 7cad36e4 — registry authority closure commits ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row8. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-093 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 4e2e0f654b93ceed2ecdfbce4d3c1768550b3079 — T-093 govern plant vocabulary as data-driven genericity debt ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row9. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-094 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 377aabdffb27d651d30537ce5228ee4afe268526; 6ab97ee2; e74ecd1c; 5a967f1b0ab45961c8b8a880bb4fdec53a783134 — final: T-094 close keyed declared-dimension cutover and genericity reconciliation ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 24 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row10. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-201 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: BASELINE HEAD 7da9d46ed29545f1c4f4686fa82c117c08b9fc86; TAG m1-presentation-baseline-2026-08-21 — no task commit; tag is closure artifact ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 4 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row11. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-202 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: ad37c324 — Add persisted definition replay gate for release truth ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row12. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-203 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: cd1a450e — Add customer route invariant gate with durable evidence ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row13. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-204 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: c6491e2d — closure-state HEAD; exact task commit subject not independently recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row14. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-205 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: b7fcc890 — Gate the frontend suite on deterministic termination and machine-readable evidence ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row15. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-206 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row16. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-208 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 969c767c — T-208: generic controlled validation fixture and continuous-process known answers ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row17. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-209 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: f2bafdb4 — subject not recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row18. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-210 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 92a655e1ddc4becedbaf89a3db96dc0d0f1eaf94 — subject not recovered ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row19. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-216 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: ea9103fd — Establish source time authority for plant timestamps ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 5 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row20. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-231 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: c930af079502aa1660ef2bd5c50756d3fc3cf8f3 — Persist-T231-canonical-analysis-subject-grain-authority ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row21. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-250 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 6615481b — Converge frontend journey and design-system truth ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row22. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-251 | M2-P1 | Done | CENTRAL CLOSURE SOURCE RECOVERED | 7ba31f96f3810bdac734bd1850275a601503d34d | Inherited Done now has the explicitly recovered CENTRAL closure anchor. | 12 | INHERITED ESTIMATE |  | Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | No reopening from older RED receipts or later catalogue changes.
T-252 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row24. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-256 | M2-P1 | Done | SHORT ANCESTRY CORROBORATION | 36de9370 (short parent named by T-262) | Accepted Done retained. Recovered parent association is not a rerun of T-256 tests. | 12 | INHERITED ESTIMATE |  | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Preserve status; exact full SHA/closure output remains missing in this bounded retrieval.
T-259 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 2 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row26. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-260 | M2-P1 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row27. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-095 | M2-P2 | Done | SOURCE CORROBORATES CLOSED FOUNDATION | INHERITED WORKBOOK COMMIT: 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e — subject not recovered ¦ not independently re-verified from complete sessions in this review | RelationshipService already validates ordered composite members, join/cardinality vocabulary and grain attribution, publishes through the store and returns read-back. The existing relationship infrastructure is real and must not be recreated. REMAINS: No new implementation within the accepted original task scope is established here. Canvas publication wiring is owned by the later T-243 addition, not reopening this foundation. | 12 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — PublishAsync Backend/PlantProcess.Application/Relationships/RelationshipService.cs:218-260 — ValidateDeclaration | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | T-243 consumes existing publication authority. Runtime/complete-session proof still not executed/recovered here.
T-096 | M2-P2 | Done | SOURCE CORROBORATES CLOSED FOUNDATION | INHERITED WORKBOOK COMMIT: de243027073fc5e492d65e9f9845255342517510 — T-096 relationship resolver consumer convergence ¦ not independently re-verified from complete sessions in this review | RelationshipResolver reads the published model, finds deterministic shortest/preferred paths, refuses ambiguous or missing paths and prevents automated use of unvalidated relationships. Existing join-planner consumers should be retained. REMAINS: No new work is assigned to this closed convergence slice. Live downstream execution remains a separate consumer acceptance and is not proven by this source read. | 8 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:34-113 — ResolveAsync Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-96 — ConsumerFamilies | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-097 | M2-P2 | Done | SOURCE CORROBORATES CLOSED GUARD | INHERITED WORKBOOK COMMIT: 95220d1804493f8e7b80347fe3ed4de24741f9ec — T-097 relationship consumer barrier across all sixteen families ¦ not independently re-verified from complete sessions in this review | The permanent consumer barrier names sixteen families and forbids private path authority while allowing intrinsic owning-key navigation. It explicitly covers future engine directories too: a barrier is not proof that all engines are commissioned. REMAINS: Keep the original barrier task closed. New consumers must pass it; their runtime wiring belongs to their own integration tasks. | 6 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:12-44 — barrier semantics Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-114 — consumer and forbidden-authority inventory | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-098 | M2-P2 | Not Started | REUSABLE BACKEND PRESENT; CANONICAL UI NOT LOCATED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The relationship API already exposes list, entities, detail and validation, and the resolver/publication services exist. The reviewed frontend route/page sources contain no canonical Relationship Browser implementation. This is a UI/consumer task, not new relationship storage. REMAINS: Build C6 list/detail/path/validation views against existing services, including ambiguity, preferred-path and refusal evidence; add frontend/API-contract tests and one runtime acceptance. | 12 | Proposed remaining 6/9/14 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Api/Endpoints/Relationships/RelationshipEndpoints.cs:21-92 — MapRelationshipEndpoints Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:62-113 — path results | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Do not duplicate T-095..T-097 or charge their work here. Runtime/complete-session proof still not executed/recovered here.
T-099 | M2-P2 | Done | CLOSED SCOPE PRESERVED; SOURCE CORROBORATES | CLOSED GREEN / COMMITTED ca02b40e | MappingRowProjector contains PV01–PV08 row classification, existing-row replay behavior, shared mapping context and quarantine reprocess integration. Later owner-supplied closure and recovered transcript report the exact semantic commit and live targeted tests. REMAINS: Zero remaining inside T-099's closed first-eight-PV scope. PV09–PV15, full replay/update semantics, monitoring and exact weight semantics remain with T-100/T-101/T-104/T-103. | 8 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:141-181 — MapMaterialUnitAsync Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — bounded reprocess surface Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:3-20 — narrow topology correction | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-100 | M2-P2 | Done | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | 6 [STALE] | Prior 6/10/16 h superseded; closure-only effort UNCONFIRMED. Reported implementation and unit gates are not charged again. |  | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | Previous Not Started and PV01..PV08-only current-state wording superseded by reported Runner-1 implementation. No Done/commit inference. | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED.
T-101 | M2-P2 | Not Started | PARTIAL REUSE; CURRENT EXPANDED SCOPE OPEN | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | POST /api/quarantine/reprocess and row-level reprocess service exist; the endpoint explicitly leaves list/detail/Mapping Health to T-101. Existing C2/import views are reusable scaffolding, not the complete PV/drift/retry monitoring flow. REMAINS: Add bounded list/detail by code/dataset/batch and source lineage, extend the existing reprocess path, persist/display mapped-column drift, and B4 batch/error/durable-cursor monitoring. Validate API, UI and failure recovery. | 12 [STALE] | Proposed remaining 12/18/28 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — MapQuarantineEndpoints Backend/PlantProcess.Application/Integration/Services/Staging/StagingRecordService.cs:85-110 — durable staging identity | CURRENT ESTIMATE NOT USABLE; TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | T-106 owns run-outcome semantics; T-125 owns operational data/health; do not bill those twice. Runtime/complete-session proof still not executed/recovered here.
T-102 | M2-P2 | Not Started | EXISTING ALIAS FOUNDATION; IDENTITY-SAFETY GAP | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | material_aliases storage and uniqueness exist. MappingRowProjector creates aliases and resolves a supplied alias, but resolves by AliasCode alone and selects the first material; material-code lookup similarly omits SiteId despite per-site uniqueness. Automatic collision-safe cross-source identity is not complete. REMAINS: Reuse alias persistence; resolve by governed tenant/site/source/key scope, refuse ambiguity, reconcile two source identifiers into one material and prove idempotent re-import with same alias text across sources/sites. | 8 | Proposed remaining 4/7/12 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:244-264 — MapMaterialAliasAsync Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:721-744 — ResolveMaterialIdAsync Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialAliasConfiguration.cs:27-36 — composite unique Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialUnitConfiguration.cs:43-47 — site/source uniqueness | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Source-proven ambiguity mechanism: storage permits shared AliasCode across materials/sources; reader selects first by alias alone. No live wrong-material incident asserted. Do not recreate alias tables or the full row projector. Runtime/complete-session proof still not executed/recovered here.
T-103 | M2-P2 | Not Started | SUBSTANTIAL FOUNDATION; ACCEPTANCE-CONTRACT MISMATCH | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | GenealogyService already rejects self-edges, duplicate edges and cycles by traversal. Migration 841 repairs the deferred weight trigger's schema binding while deliberately preserving its old tolerance. The effective predicate uses abs(sum-1)>0.015, so 0.99 passes that predicate although this task requires rejection. REMAINS: Retain cycle/self-edge implementation; prove DB direct-write cycle controls and both traversal directions, then reconcile exact declared weight semantics with the 0.015 inherited tolerance and add the explicit 0.99 negative case. | 6 [STALE] | Proposed remaining 4/6/10 h, UNCONFIRMED; historical J/R unchanged. | T-102 | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:27-69 — CreateEdgeAsync Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:95-124 — WouldCreateCycleAsync Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:55-68 — deferred weight check | CURRENT ESTIMATE NOT USABLE; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Confirmed predicate counterexample: abs(0.99-1)=0.01 is not greater than 0.015. T-099 preserved this deliberately; this does not reopen T-099. Weight semantics/negative acceptance stay T-103; 841 topology repair remains accepted. Runtime/complete-session proof still not executed/recovered here.
T-104 | M2-P2 | Not Started | REPLAY FOUNDATION IS NOT VERSIONED REPROJECTION | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The current projector skips an already existing MaterialUnit by site/code; it is not a proof that a changed mapping re-materializes previous output. Run history has resolved-target storage, but the existing orchestrator discards the resolver result before dispatch. REMAINS: On top of the T-261 executor, prove canonical row/run version provenance, idempotent accepted effects and rollback-to-version business equivalence. Reuse first-eight-PV/quarantine infrastructure; do not implement a second executor. | 14 [STALE] | Proposed remaining 8/14/22 h, UNCONFIRMED; historical J/R unchanged. | T-261 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:168-181 — existing-row skip Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-249 — ResolveDeclaredTargetAsync | CURRENT ESTIMATE NOT USABLE; TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING; DESCRIPTION CONTAINS RETIRED-ID HISTORY; EXECUTE SUCCESSOR CONTRACT, NOT A RETIRED ROW | T-261 owns first resolved-target runtime call and executor; T-104 owns row effects and rollback proof after it. Runtime/complete-session proof still not executed/recovered here.
T-106 | M2-P2 | Done | ORIGINAL CONTRACT CLOSED; EXPANDED RUNTIME OBLIGATIONS OPEN | 8b3eb5c89352a2779d87f9205700f19e7c9b3e25; a5451dbaf6b55183fe65e2c626c49fdef85bd986 | Target capability admission, target resolver, real blocked-run evidence, dependency traversal and historical foundation/corrective commits exist. Current source still validates schedules only as nonblank text, runs fixed worker loops, lacks Cancelled in the enum/runtime completion switch, accepts freshness without an age argument and can mark mixed failed batches Ok. REMAINS: Implement the v4.10.3 schedule contract/parser/due dispatch, explicit freshness policy, truthful aggregate outcomes and cancellation coordination. Reuse the original target/DAG work; T-261 commissions the shared executor/cancellation seam and this task consumes it, not a competing runtime. | 12 [STALE] | Proposed remaining 18/28/44 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Integration/Services/Jobs/JobDefinitionService.cs:275-297 — schedule validation Backend/PlantProcess.Workers/Worker.cs:72-108 — fixed cadence loops Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:33-39 — no age/tolerance input Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:85-91 — Satisfied result Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-146 — terminal-state switch Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:262-276 — import result mapping | CURRENT ESTIMATE NOT USABLE | Confirmed source boundaries, not executed incidents. No Cancelled result currently persists through CompleteAsync. No false claim that the original T-106 runner failed. T-261 owns executor implementation, first RecordResolvedTarget and common cancellation seam. T-106 owns schedule/DAG/outcome semantics; no double estimate of executor. Complete session/live HEAD proof remains outstanding.
T-107 | M2-P2 | Not Started | TIMERS EXIST; GOVERNED JOB POOLS NOT ESTABLISHED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The Worker has staggered timers and sequential awaits for import, data-quality, risk and delta. Separate telemetry buffers use bounded channels, but are not weighted job pools. Existing capability admission decides executability, not job-slot AND resource-capacity admission. REMAINS: Add actual bounded job queues/pool slots and dual-predicate resource admission, isolation of three ML lanes, backpressure and exact cancellation/release behavior; test saturation and interactive reservation without inventing production capacity constants. | 16 | Proposed remaining 12/20/32 h, UNCONFIRMED; historical J/R unchanged. | T-098; T-101; T-102; T-103; T-104 | Backend/PlantProcess.Workers/Worker.cs:72-108 — ExecuteAsync cadence Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:76-107 — family capability vs capacity | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | T-155/T-159 calibrate heavy-production constants later; no retraining or new scheduler here. Runtime/complete-session proof still not executed/recovered here.
T-108 | M2-P2 | Not Started | IMPLEMENTED DELTA FOUNDATION WITH CONFIRMED CORRECTNESS GAPS | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | A real delta reader/importer, row envelope and cursor persistence already exist; generic bulk staging rejects duplicate batch/source/row entries. The delta path directly creates a fresh batch/rows and uses a scalar cursor. The PostgreSQL query uses strict > plus LIMIT, MaxCursor parses under ambient culture, and incremental reads bypass the wrapper budget while GetBudget ignores profile/dataset. REMAINS: Implement total-order cursor/tie-key semantics for every supported incremental reader, typed invariant comparisons, per-source effective budget on incremental calls, durable checkpoint/replay identity and projection watermark handoff. Do not recreate source/staging infrastructure already present. | UNESTIMATED | Proposed remaining 22/34/52 h, UNCONFIRMED; historical J/R unchanged. | T-104 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — read-path selection Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — row/cursor handling Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:236-280 — source identity and MaxCursor Backend/PlantProcess.Infrastructure/Connectors/PostgreSql/PostgreSqlConnector.cs:181-206 — scalar LIMIT query Backend/PlantProcess.Application/Integration/Protection/ThrottlingDataSourceReader.cs:36-70 — unequal protection Backend/PlantProcess.Infrastructure/Integration/Protection/OptionsSourceLoadBudgetProvider.cs:21-24 — global budget Backend/PlantProcess.Infrastructure/Persistence/Configurations/Integration/StagingRecordConfiguration.cs:31-42 — existing within-batch uniqueness Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:58-73 — current weak continuation assertions | CURRENT ESTIMATE NOT USABLE | The old test checks only returned JSON array shape, not cursor values/exact IDs. Generic bulk-insert dedupe is not proof of delta-path cross-batch replay safety. Confirmed PostgreSQL tie mechanism; other providers require their own tests. T-106 owns Job aggregate status; T-101 B4 UI; T-109 consumes this watermark; no duplicate billing for those consumers. Runtime/complete-session proof still not executed/recovered here.
T-109 | M2-P2 | Not Started | REUSABLE CALCULATION FOUNDATION; DELTA CONSUMER NOT PROVEN | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The repository has source-delta infrastructure, ML refresh paths and pure analytical kernels, but the inspected analytical service paths do not show a commissioned consumer of the designed feature_refresh/analysis_scope watermark chain. Existing calculation code is reusable, not proof of bounded changed-entity execution. REMAINS: Consume T-108's committed batch/delta token, materialize changed subjects through governed relations, refresh bounded feature/analysis scope and telemetry, and emit the ML handoff. Prove late data and interrupted retries without a second cursor store. | 6 | Proposed remaining 6/10/18 h, UNCONFIRMED; historical J/R unchanged. | T-098; T-101; T-102; T-103; T-104; T-108 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-217 — available source delta boundary Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:85-113 — governed automated path | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | T-108 owns source/projection checkpoint; M3 materializers own full training artifacts. Runtime/complete-session proof still not executed/recovered here.
T-207 | M2-P2 | Done | SOURCE CORROBORATES CLOSED TRUTH CONTRACT | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | HistorianConnectorCapabilities explicitly declares real browse/read/subscription/session operations unavailable and returns named capability truth. This is a real honest-refusal foundation, not a production OPC implementation. REMAINS: No original T-207 reimplementation. New backend provider-list convergence belongs to expanded T-254; live OPC operations belong to T-224..T-226. | 6 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — HistorianConnectorCapabilities | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Runtime/complete-session proof still not executed/recovered here.
T-212 | M2-P2 | Not Started | AUTHORITY EXISTS; PRODUCTION QUERY CONSUMPTION GAP | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | SignalSemanticsResolver already resolves aggregation through the governed database function with AG01/type refusal and a DI registration. Current production reference census finds its definition/implementation/registration, but no widget/query service injection/call. Frontend aggregate binding copies declared metadata; it performs no analytics. REMAINS: Wire the existing semantics authority into Layer-A widget/query execution and consume the T-211 arithmetic contract. Preserve declared weighting/sampling/null rules, typed refusals and result evidence; do not implement a new aggregation authority. | 10 | Proposed remaining 6/9/14 h, UNCONFIRMED; historical J/R unchanged. | T-211; T-235 | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — ResolveAsync Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — not analytics mathematics | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | T-211 computes math; T-210 governs semantics; T-212 wires actual queries. Runtime/complete-session proof still not executed/recovered here.
T-213 | M2-P2 | Done | SOURCE CORROBORATES CLOSED PRODUCER | INHERITED WORKBOOK COMMIT: 2748c7fba8a5c4763bc19112ce57e484cea5b9bb — subject not recovered ¦ not independently re-verified from complete sessions in this review | CustomerAssessmentEndpoints exposes authorized assess/latest/version/diff operations and resolves tenant identity before service work. The service/normalization/history migration and tests are present. This is a reusable assessment authority, not an autonomous ingestion/projection executor. REMAINS: No new work within the accepted T-213 authority scope. Customer intake use within the real UI journey remains the consumer's acceptance, not reopening this producer. | 8 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Api/Endpoints/CustomerAssessmentEndpoints.cs:86-125 — assessment routes and tenant gate | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-224 | M2-P2 | Not Started | CONFIGURATION FOUNDATION ONLY; LIVE SESSION UNCOMMISSIONED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The current OPC connector only validates supplied endpoint/read-only configuration and explicitly refuses a requested live handshake. The separate capability authority says session security/certificate/trust handling is not implemented; there is no evidence that the advertised target session is commissioned. REMAINS: Implement real read-only OPC endpoint/session/certificate lifecycle on the customer-side collector, with governed trust references, security-policy rejection, reconnect and safe telemetry. Reuse configuration/capability contracts, not their success text as handshake proof. | 12 [STALE] | Proposed remaining 10/16/26 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration test Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — live capability declarations | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | T-225 browse/subscription; T-226 end-to-end data/recovery; T-266 design. No M3 deferral. Runtime/complete-session proof still not executed/recovered here.
T-225 | M2-P2 | Not Started | LIVE ACQUISITION OPERATIONS NOT COMMISSIONED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current truth explicitly marks tag browse, bounded value read and subscriptions unimplemented. The UI and supplied-tag hints do not establish real namespace traversal or monitored-item persistence. Session support is T-224's prerequisite. REMAINS: Build namespace browse, stable node identities, tag registration, bounded read/subscriptions and monitored-item lifecycle using the T-224 session and source-load policy; test partial browse, disconnect and invalid intervals. | 12 [STALE] | Proposed remaining 10/16/26 h, UNCONFIRMED; historical J/R unchanged. | T-224 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:76-95 — browse/read/subscription capability state Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:53-70 — metadata-only legacy claim | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Do not recreate session security or count T-266 graphics as real read proof. Runtime/complete-session proof still not executed/recovered here.
T-226 | M2-P2 | Not Started | SPOOL/TIME FOUNDATIONS; LIVE END-TO-END PROOF MISSING | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Historian mapping/legacy tag-history and edge-spool scaffolding exist, while real upstream OPC read/subscription operations remain unavailable. Those existing interfaces are useful but do not prove quality/timestamp preservation or replay into canonical data from a live session. REMAINS: Integrate source/server/ingest time and quality handling, spool/ack/reconnect/gap recovery and idempotent canonical replay using T-233/T-224/T-225; run controlled interruption and real-source evidence. | 12 [STALE] | Proposed remaining 10/16/28 h, UNCONFIRMED; historical J/R unchanged. | T-225; T-233 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — upstream live-operation boundary Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — existing time kernel | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | No new time-authority kernel; no reuse of demo telemetry as customer-source proof. Runtime/complete-session proof still not executed/recovered here.
T-232 | M2-P2 | Not Started | TARGET AUTHORITY NOT LOCATED IN SUPPLIED SNAPSHOT | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The supplied snapshot includes signal semantics and ordinary limits/parameter storage, but no production Performance Reference authority was located by class/table/name and consumer search. Existing semantics infrastructure is reusable; it is not the effective-dated reference precedence contract. REMAINS: Implement effective-dated reference persistence, precedence/provenance and governed projections consuming T-214; test overlapping definitions, missing direction/unit and deterministic read-back. Do not reimplement the T-214 decision kernel. | 6 | Proposed remaining 5/8/13 h, UNCONFIRMED; historical J/R unchanged. | T-214 | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — existing semantic infrastructure only | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | T-214 owns reference decision kernel; T-215 consumes BI projections; a negative symbol search alone is not live absence proof. Runtime/complete-session proof still not executed/recovered here.
T-233 | M2-P2 | In Progress | TIME KERNEL EXISTS; PERSISTENCE/CONSUMER WORK REMAINS | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | SourceTimeAuthorityKernel already resolves declared source/signal timestamps to uncertainty-bearing instants and refuses unauthorized time roles. The reviewed Domain/Infrastructure models do not contain the corresponding source/server timestamp authority fields/adapter, so kernel completion is not persistence completion. REMAINS: Persist declared time authority and observation provenance, bind acquisition/projector consumers to the existing kernel, and prove zone/offset/uncertainty conflict handling without machine-locale fallback. | 5 | Proposed remaining 5/8/14 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-97 — Resolve / ResolveAs Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:184-210 — current material time fields | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Do not charge T-216 kernel work again; OPC T-226 consumes the approved time contract. Runtime/complete-session proof still not executed/recovered here.
T-235 | M2-P2 | Not Started | KERNELS COMPLETE; CURRENT PRODUCTION INTEGRATION OPEN | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | OperationalTransitionKernel and TransitionAwarePoolingGuard contain actual regime classification and uncertainty-aware pooling refusal. Direct production reference census only finds kernel-to-kernel calls; it does not establish a persisted regime authority consumed by live statistics. REMAINS: Persist transition/stabilisation declarations and wire current M2 statistical/correlation pooling to the existing guard. Include source-time uncertainty and explicit undeclared-regime handling; prove the live path refuses mixed/uncertain populations. | 8 [STALE] | Proposed remaining 6/11/18 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Analytics.Core/Kernel/Regime/TransitionAwarePoolingGuard.cs:24-79 — Admit Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — time interpretation | CURRENT ESTIMATE NOT USABLE | Do not redo T-234/T-236; later broad engine convergence stays T-146. Runtime/complete-session proof still not executed/recovered here.
T-241 | M2-P2 | Done | SOURCE CORROBORATES CLOSED GRAPH CONTRACT | INHERITED WORKBOOK COMMIT: eb7fb2ab — subject not recovered ¦ not independently re-verified from complete sessions in this review | The shared graph semantics imports typed ports and one block-contract registry; the registry distinguishes implemented/evaluable/persistable capabilities. Those executable validation contracts are real foundation code, not proof of a commissioned job executor. REMAINS: Retain original typed-port/graph-validation closure. Any actual execution or visual-depth remainder belongs to T-245/T-261/T-265, not recreation of the T-241 graph model. | 10 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Frontend/PlantProcess.Web/src/authoring/graphSemantics.ts:22-40 — typed-port authority Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — capability separation | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-242 | M2-P2 | Done | CLOSED CONTRACT; DOWNSTREAM EXECUTION NOT IMPLIED | INHERITED WORKBOOK COMMIT: b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 — final: T-242 close governed aggregate and window block contracts ¦ not independently re-verified from complete sessions in this review | The block catalogue is centralized, typed and explicit about evaluable versus persistable behavior. Governed aggregation copies canonical metadata and refuses missing semantics; it deliberately computes no analytics. Non-placeable families must not be described as already commissioned product execution. REMAINS: Original algebra/catalogue/validation closure remains closed. Persistence/compilation/runtime integration is the relevant downstream work and must retain honest unavailable states until accepted. | 16 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — one catalogue and separate capabilities Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — handoff boundary Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:49-77 — AG01 behavior | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-243 | M2-P2 | Done | ORIGINAL REOPEN CLOSED; ADDITIONAL PUBLICATION INTEGRATION OPEN | 6f65bba1 (short; exact full SHA/date not recovered) | The authored board, governed output target, version history and reopen logic exist; the September 9 closure proves mocked-server reopen/edit behavior. Canvas publish calls the canonical definition writer and compatibility projector in a transaction, but does not call the existing relationship-publication authority. REMAINS: Only the added relationship-emission/atomicity/legacy-path convergence remains: derive declared relationships, publish through the existing service in the correct unit of work, and prove rollback/read-back. Preserve the saved-board implementation and its closure. | 12 [STALE] | Proposed remaining 5/9/15 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — canonical graph/board content Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:265-333 — publish transaction Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — existing publication seam | CURRENT ESTIMATE NOT USABLE | Do not implement a second relationship store. T-262 save-mapping concern is tracked once there, not charged again. Complete session/live HEAD proof remains outstanding.
T-244 | M2-P2 | Done | SOURCE CORROBORATES CLOSED SQL FOUNDATION | INHERITED WORKBOOK COMMIT: 4d32c6b10b4605aeb6e0705ad03537d563125652 — T-244 close canonical Canvas lifecycle and selection model ¦ not independently re-verified from complete sessions in this review | The current SQL-mode save uses canonical content and the shared safe-SQL/lifecycle path, and SQL publication derives a compatibility projection within the same transaction. This substantiates the earlier persistence/convergence foundation; it does not execute a governed projection job. REMAINS: Keep the original T-244 closure. The later projection-binding callback concern belongs to the T-262 consumer boundary, and runtime transformation execution belongs to T-261. | 14 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:173-205 — ForSql Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:297-333 — SQL publish path Frontend/PlantProcess.Web/src/api/canvasApi.ts:118-155 — SQL run/save API adapter | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Runtime/complete-session proof still not executed/recovered here.
T-245 | M2-P2 | Not Started | BINDING WORK NOT COMMISSIONED; REUSE PRODUCER CONTRACTS | 10Sep preflight at a5451dba; no T-245 closure commit in inspected output | Canvas has draft save, SQL preview, publish and reopen adapters; the job target resolver/capability descriptors exist. The current shell/API adapter has no commissioned bind-and-run flow consuming exact version/per-block runtime evidence, and CanonicalRefresh is explicitly unavailable. REMAINS: Implement the thin Canvas-to-job binding/launch/monitor/error/cancel surface over T-261's real executor, carry exact version and stable block IDs, and test unavailable-family refusal before launch. | 12 | Proposed remaining 6/10/16 h, UNCONFIRMED; historical J/R unchanged. | T-261; T-262 | Frontend/PlantProcess.Web/src/api/canvasApi.ts:111-155 — current save/preview/publish surface Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-124 — non-executable target families | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | T-261 owns executor and block-evidence storage, T-106 schedule/outcome policy; do not count those implementations again. Runtime/complete-session proof still not executed/recovered here.
T-247 | M2-P2 | Not Started | RELEASE ACCEPTANCE NOT EXECUTABLE BEFORE PRODUCERS | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Individual source/import/Canvas/BI surfaces and earlier demo/journey tests exist, but the supplied production snapshot explicitly refuses governed Transformation execution. The required same-binary customer path cannot be certified by the present source or Figma output alone. REMAINS: After producer closures, execute one customer-shaped real-source-to-canonical-to-BI/Assistant journey with immutable-version/retry/cancel/refusal/isolation evidence and zero customer-specific product diff. Budget acceptance coordination only; bugs remain with their owning tasks. | 12 | Proposed remaining 8/14/22 h, UNCONFIRMED; historical J/R unchanged. | T-104; T-108; T-125; T-211; T-212; T-235; T-245; T-254; T-258; T-262; T-265; T-266 | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — concrete broken journey seam Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:32-73 — earlier tests are not full new journey proof | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | No source-code or drawing count can close runtime acceptance; no duplicate budget for T-106/T-108/T-261 fixes. Runtime/complete-session proof still not executed/recovered here.
T-253 | M2-P2 | Done | SOURCE CORROBORATES CLOSED OUTPUT CONTRACT | Full commit not recovered | Canonical content carries one outputTarget; model marker/catalogue authority determines eligible targets and exposes fields. Existing graph/SQL hash and read-back behaviors are real. This is independent of current job executor availability. REMAINS: No new original output-target work. Preserve original 7a6f91f9 closure; downstream publication and executor consume that authority. | 12 | Proposed remaining 0/0/0 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — ForGraph outputTarget/board Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — strict compatibility | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Runtime/complete-session proof still not executed/recovered here.
T-254 | M2-P2 | In Progress | ORIGINAL SURFACES CLOSED; BACKEND CONVERGENCE REMAINDER | f8a35725c9b0d7fb5a0515c0103a72807a704a97 | The frontend/website runtime-truth convergence was closed at f8a35725. Current backend still has a separate ConnectorConfigurationService provider DTO list beside ConnectorProviderCatalog. Their OPC browse flags and membership/descriptions differ; configuration reads the former. REMAINS: Complete only the widened backend validation/catalogue convergence and regression tests ensuring profile validation, API truth, UI and website consume one result. Retain frontend/website original closure and absence-of-fallback evidence. | 6 [STALE] | Proposed remaining 2/4/7 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:17-39 — duplicate provider DTO source Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:81-102 — OPC flags Backend/PlantProcess.Application/Integration/Connectors/ConnectorProviderCatalog.cs:72-104 — second catalog OPC/SAP entries | CURRENT ESTIMATE NOT USABLE | No rewrite of T-207, no source availability invented from a certification flag. Runtime/complete-session proof still not executed/recovered here.
T-261 | M2-P2 | In Progress | HOST MUTATION HELD — T-100 final commit required | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit. REMAINS: Extract/reuse the compiler; implement resolver+executor, carry the pre-admission target into the real run, canonical row effects/idempotency/provenance and stable block evidence, common cancellation/status wiring; run Graph/SQL and failure/cancel proof on disposable DB. Include T-262 live Gate 0 once. HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | 12 | Proposed remaining 16/26/42 h, UNCONFIRMED; historical J/R unchanged. | T-262 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — admission before real run Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-276 — discarded resolution/dispatch Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — uncommissioned executor Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-149 — terminal lifecycle | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Do not implement a new schedule or PV taxonomy. Common cancellation seam billed once here; T-106 handles policy/endpoint coordination. Runtime/complete-session proof still not executed/recovered here. One bounded delta only after T-100 final SHA; no interim mutation or final migration allocation.
T-262 | M2-P2 | Done | ORIGINAL CONTRACT CLOSED; NARROW CONSUMER VERIFICATION OPEN | 86e1b677212195f191697ecdca7e9441b3dbde33 | The declaration, field catalogue, server type checker and Graph/SQL hash persistence exist and were committed GREEN at 86e1b677. A current consumer concern remains: doSaveSql reads projection/projectionBlocked but omits both from its useCallback dependency list; a mapping-only edit needs a direct shell regression test. Unknown-type/narrowing acceptance finding remains withdrawn. REMAINS: Do not rebuild the declaration. Reproduce the mapping-only SQL-save transition against the real shell, fix only any demonstrated stale callback, and run targeted field-map tests. Live definition-store Gate 0 is already assigned to T-261 Runner2, so it is not estimated again here. Final status remains current-scope open until this correction/acceptance is resolved. | UNESTIMATED | Proposed remaining 1/3/6 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:118-163 — immutable projection content Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — unknown/narrowing refusal Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:898-925 — doSaveSql callback inputs/dependencies | CURRENT ESTIMATE NOT USABLE | Suspected user-visible stale-save behavior; dependency omission is directly observed, but no live browser reproduction is claimed. Do not revive withdrawn type-compatibility finding. Do not reimplement the immutable declaration. Live definition-store Gate 0 is carried once in T-261 acceptance/estimate. This task's proposed 1/3/6h is the mapping-only SQL save concern and bounded verification, not another executor. Current composite status retained; closure ownership needs explicit reconciliation, not a fake missing-commit claim. Complete session/live HEAD proof remains outstanding.
T-148 | M2-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row61. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-215 | M2-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-214; T-232 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row62. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-222 | M2-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-215 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row63. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-258 | M2-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row64. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-137 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row65. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-168 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 16ea041a; 94ab4e40; 723b9434; 6aef283f; ef588f0c — multi-commit runtime/protocol/CI closure ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row66. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-169 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: a887c554 — T-169 Pack 1: typed columnar artifact contract, Parquet and Arrow IPC adapters, two hashes, B-03 hook ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row67. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-170 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 5a216483 — T-170 Chunked sequence-artifact library and bounded loader ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row68. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-171 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 95cc019c — Capability Profiler Pack 2 ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row69. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-172 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: d4321856 — T-172 MF-01 Process Encoder runtime behind a replaceable contract ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row70. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-173 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 00a14286 — T-173 MF-02 VectorSimilarityIndex with exact-Flat recall baseline ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row71. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-174 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: db033796 — T-174 MF-03 novelty runtime and honest refusal semantics ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row72. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-175 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 2413c6e1 — T-175 MF-04 supervised training runtime and mandatory simple baseline ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row73. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-176 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 08b54b61; 0a61ccfb — Calibration/explanation stability/promotion kernel + real TreeSHAP Pack 2 ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row74. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-177 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 502f8ca3; 502e0da9; bb4c5686 — T-177 multi-commit statistical-kernel closure ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row75. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-178 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: b8792516; b5dbf232 — remediation eligibility/can_accept kernel + corrective canonical precedence ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row76. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-179 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: d2bf1834 — T-179: deterministic Assistant tool planner ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row77. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-180 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: 87428c512c6d6d1ca2bf70a6a8b04aadc7a4cc3b — T-180: permission-first hybrid retrieval and deterministic evidence packer ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row78. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-181 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | INHERITED WORKBOOK COMMIT: eaa82b8b45fb1fdb4b406abfbe2809c5f6fc9cd5 — T-181: deterministic answer verifier and Q-01..Q-11 evaluation harness ¦ not independently re-verified from complete sessions in this review | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row79. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-182 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row80. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-211 | M2-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row81. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-214 | M2-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row82. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-217 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row83. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-218 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row84. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-219 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row85. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-220 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row86. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-221 | M2-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-233 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row87. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-223 | M2-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-214 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row88. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-234 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row89. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-236 | M2-P4 | Done | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row90. | DONE IN ACCEPTED WORKBOOK; COMMIT EVIDENCE NOT RECOVERED | Resolve source-history gaps before representing this as a fully verified current status.
T-237 | M2-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-235 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row91. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-112 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row92. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-113 | M2-P5 | Not Started | SOURCE REVIEWED — IMPLEMENTATION GAPS / RELEASE RUNTIME UNVERIFIED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Real credential resolution, authentication configuration and provider APIs exist. The resolver prioritises username/password in connection_options_json over a reference; the masking test exits successfully without the round-trip when setup fails. The development mint route already refuses outside Development. These facts narrow the repair: it is not a missing licence verifier or a blank-slate connector. REMAINS: Close accepted-input, persistence and response secret boundaries with sentinel tests; replace vacuous setup returns; validate the actual release-profile bootstrap/MFA/seed/legacy-route boundary and log/audit redaction. Preserve explicit development-only behaviour. | 8 [STALE] | Proposed remaining 12/20/32 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Infrastructure/Connectors/ConnectorCredentialResolver.cs:16-51 — Resolve Backend/tests/PlantProcess.Api.IntegrationTests/Security/T08ConnectorSecretMaskingIntegrationTests.cs:19-46 — Connector_password_is_masked_on_readback Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — dev route refusal | CURRENT ESTIMATE NOT USABLE; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | No real secret leak or live production exposure was reproduced. Original 8h covers less than the expanded scope. T-121 owns DI/quota logic; T-123 install/upgrade; this estimate covers their security gate, not reimplementation. Runtime/complete-session proof still not executed/recovered here.
T-114 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row94. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-115 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 4 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row95. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-119 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row96. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-120 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row97. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-121 | M2-P5 | Not Started | BOUNDED SOURCE REVIEW — METER/UI REMAINDER NEEDS DEEPER TRACE | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The strict VerifiedEd25519LicenseService and tier/feature checks exist. Production registration points to that implementation, while Application still registers a separate singleton ILicenseService. The dev mint route refuses outside Development. Commercial limits already have reusable code; the full customer-visible metering/quota workflow is not proven by these registrations. REMAINS: Reconcile to one effective licence authority, implement or complete the declared F2/F3 role/user meters and thresholds, and execute tamper/expiry/meter/no-lost-draft acceptance. Do not build a new signing authority or reclassify the development route as a production mint. | 16 [STALE] | Proposed remaining 10/18/30 h, UNCONFIRMED; historical J/R unchanged. | T-119 | Backend/PlantProcess.Api/SignedLicensing/VerifiedEd25519LicenseService.cs:10-60 — feature/tier authority Backend/PlantProcess.Api/Program.cs:725-744 — licence DI Backend/PlantProcess.Application/DependencyInjection.cs:58-63 — legacy DI Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — development guard | CURRENT ESTIMATE NOT USABLE; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Full metering implementation was not exhaustively traced; wider interval reflects that. Trust-root claims remain withdrawn. T-113 release profile gate; T-165 pricing/cost model, not licence enforcement. Runtime/complete-session proof still not executed/recovered here.
T-123 | M2-P5 | Not Started | BOUNDED SOURCE REVIEW — DEPLOYMENT EXECUTION UNVERIFIED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | A deploy entrypoint and migration/seed commands are already present. The inspected legacy entrypoint selects .env.dev and separates migrate/seed/demo verbs; a canonical migration ledger also exists. This demonstrates reusable deployment infrastructure, not certification that the production packaging chooses only the safe path. REMAINS: Converge the shipped install/upgrade path onto the canonical ledger, preserve populated data, prove failed-upgrade/rollback recovery and non-root runtime for the selected deployment. Audit actual production selection rather than deleting development tooling blindly. | 14 [STALE] | Proposed remaining 12/20/36 h, UNCONFIRMED; historical J/R unchanged. |  | deploy/scripts/ppiq.ps1:3-20 — command contract deploy/scripts/ppiq.ps1:44-63 — profile/path selection Backend/database/canonical-migration-order.json:1-20 — canonical ledger | CURRENT ESTIMATE NOT USABLE; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | No installation/upgrade/rollback was run. Hardware, privileges and environment wait time are excluded. T-113 security policy is consumed, not re-estimated here. Runtime/complete-session proof still not executed/recovered here.
T-124 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row100. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-125 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 14 | INHERITED ESTIMATE | T-107 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row101. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-126 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row102. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-150 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-115; T-123; T-124; T-125; T-126; T-212; T-215; T-222; T-223; T-226; T-227; T-247; T-254; T-255; T-257; T-258 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row103. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-227 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row104. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-255 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row105. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-257 | M2-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row106. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-110 | M3-P1 | Not Started | BOUNDED SOURCE REVIEW — ADVANCED RUNTIME GAP | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Existing delta import and versioned job/target contracts are reusable. The inspected importer operates on bounded calls but does not supply the complete general chunk-receipt/checkpoint/resume authority required by this task. Generic channel buffers and ML artifact chunks are not evidence of durable job-scope receipts. REMAINS: Implement persistent row/byte-bounded chunks, pinned inputs, receipt-atomic progress, interruption resume, deterministic merge and cumulative scan-budget abort. Reuse the M2 source-cursor/replay work rather than implementing it twice. | 24 [STALE] | Proposed remaining 16/28/44 h, UNCONFIRMED; historical J/R unchanged. | T-108; T-109 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — existing incremental reader use Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — batch/cursor persistence Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — existing admission/run boundary | CURRENT ESTIMATE NOT USABLE; DESCRIPTION CONTAINS RETIRED-ID HISTORY; EXECUTE SUCCESSOR CONTRACT, NOT A RETIRED ROW | General chunk engine absence is based on the inspected runtime paths and symbol census, not every historical script. T-108/109 M2 delta; T-155 measured thresholds; T-159 site certification. No waits/soak included. Runtime/complete-session proof still not executed/recovered here.
T-122 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-107; T-112; T-113; T-114; T-117; T-123 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row108. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-151 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row109. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-152 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row110. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-153 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-224; T-225; T-226; T-254 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row111. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-154 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row112. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-155 | M3-P1 | Not Started | SOURCE FOUNDATION REVIEWED — SITE MEASUREMENTS UNVERIFIED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | B-01..B-09 benchmark contracts and a selected-value guard already exist. The guard requires a measured real-subject Production envelope before a value is published. Those are useful measurement tools, not already-measured site capacities or scan-amplification limits. REMAINS: Integrate site workloads with those harnesses, collect training/batch/online latency and amplification evidence, and publish measured limits. Do not invent measured capacity from fixture outputs or replace the existing evidence contract. | 12 [STALE] | Proposed remaining 8/14/24 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:20-36 — benchmark metadata Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:32-75 — SelectedValueGuard | CURRENT ESTIMATE NOT USABLE; DESCRIPTION CONTAINS RETIRED-ID HISTORY; EXECUTE SUCCESSOR CONTRACT, NOT A RETIRED ROW | Focused engineer-hours only. Machine run/soak duration, data provisioning and site access excluded; re-estimate if hardware/workload changes. T-110 enforcement implementation and T-159 certification reruns are distinct. Runtime/complete-session proof still not executed/recovered here.
T-159 | M3-P1 | Not Started | FOUNDATION REVIEWED — CAPACITY CERTIFICATION NOT EXECUTED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The same benchmark envelope and real-subject/Production guards provide an existing basis for certification provenance. No C1-C4 run result on target site hardware was executed or observed in this source pass, so completed fixture tooling does not establish certification. REMAINS: Prepare reproducible C1-C4 workloads, consume T-155 calibration, exercise the T-110 negative controls, reconcile measured sizing examples and capture sign-off without accepting fixture data as production measurements. | 12 [STALE] | Proposed remaining 8/16/28 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:43-81 — evidence guard Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:65-90 — B-01..B-09 registry | CURRENT ESTIMATE NOT USABLE; DESCRIPTION CONTAINS RETIRED-ID HISTORY; EXECUTE SUCCESSOR CONTRACT, NOT A RETIRED ROW | Operational engineering effort only; elapsed soak duration and access waits explicitly excluded. No reimplementation of T-110 or calibration billed again from T-155. Runtime/complete-session proof still not executed/recovered here.
T-160 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row115. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-163 | M3-P1 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row116. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-116 | M3-P2 | Not Started | BOUNDED SOURCE REVIEW — ROUTE-WIDE CENSUS NOT COMPLETE | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current provenance resolution is a real service and still reads declared legacy/compatibility relations. Existing endpoints and guarded source lookups are reusable; spelling public/canon alone does not prove a broken fresh install. The migration requires a consumer inventory rather than a delete-first schema rewrite. REMAINS: Resolve every active old/new route and compatibility consumer, dual-serve only lawful semantic equivalents, test response/permission parity and keep historical handles readable before retiring consumers/objects. | 8 [STALE] | Proposed remaining 8/14/24 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:16-66 — provenance dispatch and run resolution Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:69-90 — source/dataset existence lookup | CURRENT ESTIMATE NOT USABLE; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | 544-route count is a task baseline, not a count remeasured in this pass; estimate contingent on full inventory. Do not remove compatibility objects before all live consumers and upgrade paths converge. Runtime/complete-session proof still not executed/recovered here.
T-117 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row118. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-127 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-121; T-196; T-197; T-198; T-199; T-200 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row119. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED; HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-149 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row120. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-161 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row121. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-162 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row122. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-194 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 6 | INHERITED ESTIMATE | T-117; T-127 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row123. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-196 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row124. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-197 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-119; T-198 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row125. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-198 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-119 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row126. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-199 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-124; T-198 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row127. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-200 | M3-P2 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-113; T-119 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row128. | HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING | Resolve source-history gaps before representing this as a fully verified current status.
T-156 | M3-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row129. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-166 | M3-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row130. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-228 | M3-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-134 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row131. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-229 | M3-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-134; T-228 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row132. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-230 | M3-P3 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-229 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row133. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-248 | M3-P3 | Not Started | BOUNDED SOURCE REVIEW — ALL 75 OUTCOMES NOT CERTIFIED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The shared authoring shell, immutable reopen/output mapping and associative state are real implementation. AssociativeContext models selected/possible/excluded/alternative states and calls the governed widget query. Thus the 75-outcome enterprise remainder is not a blank-slate BI build, and the existence of basic selection must not be overwritten by a visual-template omission. REMAINS: Complete the unfulfilled advanced outcome rows, native-grain drill, named/comparison states, concurrency recovery and server-owned persistence; wire G3/G6 consistently. Freeze the precise remaining matrix before code and reuse existing selection/history/validator behaviour. | 30 [STALE] | Proposed remaining 24/40/64 h, UNCONFIRMED; historical J/R unchanged. | T-148; T-228; T-245; T-257; T-267 | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:1-55 — state and query orchestration Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — reopen application | CURRENT ESTIMATE NOT USABLE | Full 75-row functional re-audit still required; estimate is a scope-budget proposal, not measured task duration. T-267 designs; T-248 implementation; T-249 release acceptance. Existing T-204 selection closure retained. Runtime/complete-session proof still not executed/recovered here.
T-263 | M3-P3 | Not Started | SOURCE REVIEWED — SUBSTANTIAL REPORT FOUNDATION / LIFECYCLE GAP | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Reporting endpoints already generate investigation/readiness reports and PDFs through IInvestigationReportService and readiness services. This is real reusable output infrastructure. It does not provide the complete E5 versioned report-definition, scheduled output and delivery-history lifecycle. REMAINS: Add governed report definition/version/sections/period, shared-job generation, output history, tenant-scoped download and delivery retries/audit; reuse existing PDF/evidence materialisation. Use the same scheduler, never a private report scheduler. | UNESTIMATED | Proposed remaining 16/26/42 h, UNCONFIRMED; historical J/R unchanged. | T-248 | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report routes Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:57-85 — existing report service/PDF path | CURRENT ESTIMATE NOT USABLE | T-106 scheduler and generic delivery components not recreated; fixtures alone cannot prove scheduled delivery. Runtime/complete-session proof still not executed/recovered here.
T-128 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-098; T-101; T-102; T-103; T-104; T-112; T-114 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row136. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-129 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-128; T-183 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row137. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-130 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-128; T-183 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row138. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-131 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-128 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row139. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-132 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-131 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row140. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-133 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-131; T-132; T-183 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row141. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-134 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-129; T-130; T-133; T-139; T-186 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row142. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-135 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-112; T-114; T-128; T-129; T-130; T-183 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row143. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-136 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-109; T-131; T-132; T-133 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row144. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-138 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-134; T-188 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row145. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-139 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-130; T-187 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row146. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-140 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-139 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row147. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-141 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-107; T-122; T-139; T-187 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row148. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-142 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE | T-131; T-132; T-139; T-140 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row149. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-143 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE | T-142 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row150. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-144 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE | T-143 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row151. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-145 | M3-P4 | Not Started | SOURCE REVIEWED — CANONICAL LOOP MISSING / LEGACY CONFLICT | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Phase8SuggestionOutcomeLoop takes caller-supplied BeforeValue/AfterValue, and its endpoint stores records in a process-wide ConcurrentDictionary. It is not the canonical outcome/feedback authority required by this task. Outcome arithmetic and presentation DTOs may inform migration, but cannot be credited as durable governed feedback. REMAINS: Implement canonical-only outcomes, durable evaluation/effectiveness records, intervention-aware metrics, feedback eligibility/concentration evidence and controlled Supervisor input. Retire the contradictory writer safely after replacement and preserve legitimate history. | 8 [STALE] | Proposed remaining 14/24/40 h, UNCONFIRMED; historical J/R unchanged. | T-144 | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — manual outcome DTO Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:66-90 — record calculation Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-48 — process-memory endpoints | CURRENT ESTIMATE NOT USABLE | Route mapping exists, but effective caller access in a deployed profile was not exercised. T-190 D6 cutover; T-113 M2 denial; no double price of the same endpoint removal. Runtime/complete-session proof still not executed/recovered here.
T-146 | M3-P4 | Not Started | SOURCE REVIEWED — PRIOR DEAD-FILE FINDING DISPROVEN | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | ManagedStatisticalComputeEngine already invokes BenjaminiHochberg and Bootstrap from StatisticalDiscipline.cs; AdvancedCorrelationComputeService uses EffectRanking, FDR, Bootstrap and stratification. The file is NOT dead. The separate T-177 KernelMethodSelector/GroupComparisonKernel remain referenced by tests rather than these inspected producers, so a narrower pairing/authority cutover remains. REMAINS: Wire the certified pairing/refusal kernel into real producers, align persistence/readiness/evidence and consolidate genuinely duplicate paths after consumer migration. Preserve the live discipline functions; do not delete StatisticalDiscipline.cs based on its filename or a zero-hit search for a nonexistent class. | 10 [STALE] | Proposed remaining 8/14/24 h, UNCONFIRMED; historical J/R unchanged. | T-128; T-129; T-147 | Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:49-62 — readiness/old selector Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:91-115 — live discipline calls Backend/PlantProcess.Application/Analytics/Advanced/AdvancedCorrelationComputeService.cs:117-137 — live ranking/FDR/bootstrap Backend/PlantProcess.Analytics.Core/Kernel/KernelMethodSelector.cs:27-57 — kernel pairing | CURRENT ESTIMATE NOT USABLE | Do not equate obsolete CorrelationService annotation with no live analytical engine. Existing functions and keyed engine registration are visible. T-186 persistent capability authority; this task consumes it and does not implement a second profile store. Runtime/complete-session proof still not executed/recovered here.
T-147 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-128; T-129 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row154. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-157 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row155. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-158 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row156. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-164 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-235; T-237 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row157. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-165 | M3-P4 | Not Started | BOUNDED SOURCE REVIEW — CALCULATOR NOT ESTABLISHED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The website pricing component renders configured licence-plan labels, prices and feature lists. It is not an input-driven infrastructure cost/price calculator, and benchmark evidence machinery exists separately. Therefore some display structure is reusable while measured commercial sizing logic remains unproven. REMAINS: Implement explicit units/currency/time assumptions, the separate infrastructure-cost and licence-price formulae, governed input validation and known-answer quote checks against measured capacity. | 12 [STALE] | Proposed remaining 8/14/24 h, UNCONFIRMED; historical J/R unchanged. |  | Website/PlantProcess.Website/src/components/proof/PricingLicenseMatrix.tsx:1-49 — plan display Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:17-26 — selected measured value identity | CURRENT ESTIMATE NOT USABLE | No current commercial prices or site measured sizing invented; public pricing display does not establish cost engine completion. T-121 entitlement differs from commercial pricing; T-155 supplies measurement constants. Runtime/complete-session proof still not executed/recovered here.
T-183 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-098; T-101; T-102; T-103; T-104; T-112; T-114 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row159. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-184 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-128; T-135; T-183 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row160. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-185 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-112; T-114; T-122; T-135; T-183 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row161. | TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | Resolve source-history gaps before representing this as a fully verified current status. Recover omitted start-gate prose; the original was truncated.
T-186 | M3-P4 | Not Started | SOURCE REVIEWED — KERNEL REUSABLE / PERSISTENCE AND WIRING GAP | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | CapabilityProfiler is a real pure kernel returning measured facts and eligibility/refusal states. It explicitly reads no database. Direct Profile-call census found test callers; persistence and production consumer commissioning are not established. This is integration work around an existing engine, not rebuilding profiling logic. REMAINS: Persist versioned outcome/grain/manifest-scoped profiles, connect governed prediction-point candidates/model-count limits and use one readiness authority for producers. Prove deterministic rich/sparse decisions and missing-data refusals. | 12 [STALE] | Proposed remaining 8/14/24 h, UNCONFIRMED; historical J/R unchanged. | T-128; T-129; T-135; T-183; T-195 | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:8-19 — pure kernel boundary Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:36-64 — profile calculation Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:69-96 — dimension assessment | CURRENT ESTIMATE NOT USABLE; TRUNCATED START-GATE PROSE — OMITTED CONDITIONS UNRESOLVED | T-171 kernel closed; do not reopen. T-146 consumes the commissioned authority. Runtime/complete-session proof still not executed/recovered here.
T-187 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-107; T-109; T-112; T-114; T-135; T-183; T-184; T-185; T-186; T-195 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row163. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-188 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-129; T-130; T-186; T-195 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row164. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-189 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-139; T-140; T-141; T-142; T-143 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row165. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-190 | M3-P4 | Not Started | BOUNDED SOURCE REVIEW — CANONICAL D6 CUTOVER UNVERIFIED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The legacy outcome endpoints provide a caller-entered/process-memory loop, not durable canonical D6 decisions. Related UI can be reused, but the inspected endpoint returns saved=true after a ConcurrentDictionary write, which must not be presented as canonical persistence. REMAINS: Bind the actual D6 controls to canonical eligibility and decision records, enforce can_accept on the server, preserve actor/reason history and cut over legacy routes with continuity/negative tests. | 12 [STALE] | Proposed remaining 8/14/24 h, UNCONFIRMED; historical J/R unchanged. | T-142; T-143; T-144; T-145 | Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-43 — legacy write path Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — caller outcome schema | CURRENT ESTIMATE NOT USABLE | T-145 owns outcome/effectiveness persistence; this task consumes it. M2 route denial owned by T-113. Runtime/complete-session proof still not executed/recovered here.
T-191 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-130; T-187 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row167. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-192 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-107; T-122; T-183; T-184; T-185; T-186; T-187; T-188; T-189; T-190; T-191 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row168. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-193 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-130; T-139; T-145; T-187 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row169. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-195 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 10 | INHERITED ESTIMATE | T-112; T-114 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row170. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-238 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-214 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row171. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-239 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 8 | INHERITED ESTIMATE | T-214; T-238 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row172. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-240 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-131; T-132; T-133; T-238; T-239 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row173. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-246 | M3-P4 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 11 | INHERITED ESTIMATE | T-130; T-187 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row174. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-264 | M3-P4 | Not Started | SOURCE REVIEWED — LEGACY DEMO IS NOT TARGET IMPLEMENTATION | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | P15BenchmarkingService exists, but builds anonymised industry demo bands from a stable base value and synthetic multipliers. That is not the required registry-driven internal plant benchmarking. Existing display/privacy ideas are reusable; demo bands must not be credited as measured internal comparisons. REMAINS: Implement registered population/period comparisons with real counts, BM01/BM02, direction-aware normalisation and context-comparable own-best practice; preserve evidence/export and tenant isolation. | UNESTIMATED | Proposed remaining 10/18/30 h, UNCONFIRMED; historical J/R unchanged. | T-214; T-240 | Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:17-35 — demo dashboard Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:50-85 — generated bands | CURRENT ESTIMATE NOT USABLE | No current customer benchmark output or exposure was executed here. T-214/T-240 semantics reused; no industry taxonomy or a second practice engine. Runtime/complete-session proof still not executed/recovered here.
T-167 | M3-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE |  | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row176. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-249 | M3-P5 | Not Started | FULL-SESSION RECONCILIATION NOT COMPLETED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | Current status/scope retained, not independently certified by all ten sessions. Structural/field checks executed. | 12 | INHERITED ESTIMATE | T-110; T-153; T-159; T-160; T-161; T-162; T-163; T-164; T-167; T-193; T-230; T-240; T-246; T-248; T-263; T-264; T-267 | Accepted v2.23.0 book workbook SHA256 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2; Backlog row177. | No cross-field fault detected by the defined mechanical checks; source-history verification remains separate. | Resolve source-history gaps before representing this as a fully verified current status.
T-265 | M2-P3 | Not Started | SOURCE + DELIVERED UI DATA REVIEWED — DESIGN DEPTH/PROTOTYPE NOT ACCEPTED | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The delivered UI dataset contains 40 pages, 87 dialogs and 607 scene descriptions plus a local importer explicitly labelled not run in Figma. Existing product code already handles immutable reopen and associative selections. This is a substantial starting inventory, but static nodes and populated coverage rows are not proof of the required prototype transitions. REMAINS: Complete the M2 semantic control/transition matrix, selected source/join/output inspector states, refused/recovery paths and labelled realistic fixtures; execute the specified native import/prototype checks and update only Chapters 3/4 MD+Word and workbook coverage. | UNESTIMATED | Proposed remaining 28/44/68 h, UNCONFIRMED; historical J/R unchanged. |  | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — existing associative control semantics Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — existing reopen model PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE. | CURRENT ESTIMATE NOT USABLE | No connected Figma run. No 607-frame count used as a percentage complete; whole UI interaction matrix not executed. T-266 OPC design; T-267 M3 design; runtime implementation remains its own task. Runtime/complete-session proof still not executed/recovered here.
T-266 | M2-P2 | Not Started | DESIGN TASK STILL OPEN; MOCKUP DOES NOT PROVE RUNTIME | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The source has historian configuration UI/API scaffolding and truthful unavailable operations, while the delivered visual package is a derived design. No native Figma execution or full target/current capability state interaction is established by current repository source. REMAINS: Design the named OPC profile/browse/read/subscription/quality/time/spool/replay flow and its unavailable states against T-224..T-226 contracts, integrate into Chapter3/4 and embedded Word images, and execute one observed design import/prototype check without claiming live OPC. | UNESTIMATED | Proposed remaining 6/10/16 h, UNCONFIRMED; historical J/R unchanged. |  | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — actual unavailable contract Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration interface | CURRENT ESTIMATE NOT USABLE | T-224..T-226 implement/live-certify; T-233 time authority; native design execution availability is a separate uncertainty. Runtime/complete-session proof still not executed/recovered here.
T-267 | M3-P3 | Not Started | BOUNDED SOURCE + UI INVENTORY REVIEW — M3 DESIGN REMAINDER | Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened. | The common UI dataset and existing selection/history mechanisms are reusable. Current UI Coverage deliberately separates M2 flows from M3 depth. Neither the inventory nor the native-importer code is evidence that M3 concurrency, version comparison, reports and advanced comparison prototypes were exercised. REMAINS: Design the complete M3 remainder against the existing 75-outcome matrix, producer contracts and accepted M2 flows, including advanced states, conflict/recovery, exports and G3/G6. Verify the native scenes and synchronize the two illustrated chapters. | UNESTIMATED | Proposed remaining 24/40/64 h, UNCONFIRMED; historical J/R unchanged. | T-265 | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — M2 behaviour to preserve Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report subset, not full E5 PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE. | CURRENT ESTIMATE NOT USABLE | Estimate excludes T-248 product implementation and T-249 product certification. No basic selection/clear deferred from M2; no duplicate generic frame batch treated as acceptance. Runtime/complete-session proof still not executed/recovered here.

## M2-P2 Review
Task ID | Task | Current status | Current implementation | Remaining work | Original scope hours | Remaining LOW h | Remaining BASE h | Remaining HIGH h | Estimate confidence | Original closure / later scope | Source references | Shared-work boundary | Evidence limit
T-095 | Relationship members, cardinality, grain conversion and preferred paths | Done | RelationshipService already validates ordered composite members, join/cardinality vocabulary and grain attribution, publishes through the store and returns read-back. The existing relationship infrastructure is real and must not be recreated. | No new implementation within the accepted original task scope is established here. Canvas publication wiring is owned by the later T-243 addition, not reopening this foundation. | 12 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e — subject not recovered | Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — PublishAsync Backend/PlantProcess.Application/Relationships/RelationshipService.cs:218-260 — ValidateDeclaration | T-243 consumes existing publication authority. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-096 | Path resolver, part 1: resolver core and the first eight consumers | Done | RelationshipResolver reads the published model, finds deterministic shortest/preferred paths, refuses ambiguous or missing paths and prevents automated use of unvalidated relationships. Existing join-planner consumers should be retained. | No new work is assigned to this closed convergence slice. Live downstream execution remains a separate consumer acceptance and is not proven by this source read. | 8 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | de243027073fc5e492d65e9f9845255342517510 — T-096 relationship resolver consumer convergence | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:34-113 — ResolveAsync Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-96 — ConsumerFamilies |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-097 | Path resolver, part 2: the remaining eight consumers and the regression suite | Done | The permanent consumer barrier names sixteen families and forbids private path authority while allowing intrinsic owning-key navigation. It explicitly covers future engine directories too: a barrier is not proof that all engines are commissioned. | Keep the original barrier task closed. New consumers must pass it; their runtime wiring belongs to their own integration tasks. | 6 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | 95220d1804493f8e7b80347fe3ed4de24741f9ec — T-097 relationship consumer barrier across all sixteen families | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:12-44 — barrier semantics Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-114 — consumer and forbidden-authority inventory |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-098 | Relationship Browser page and path evidence | Not Started | The relationship API already exposes list, entities, detail and validation, and the resolver/publication services exist. The reviewed frontend route/page sources contain no canonical Relationship Browser implementation. This is a UI/consumer task, not new relationship storage. | Build C6 list/detail/path/validation views against existing services, including ambiguity, preferred-path and refusal evidence; add frontend/API-contract tests and one runtime acceptance. | 12 | 6 | 9 | 14 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Api/Endpoints/Relationships/RelationshipEndpoints.cs:21-92 — MapRelationshipEndpoints Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:62-113 — path results | Do not duplicate T-095..T-097 or charge their work here. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-099 | Quarantine, part 1: the table, the reprocess API and the first eight PV classes | Done | MappingRowProjector contains PV01–PV08 row classification, existing-row replay behavior, shared mapping context and quarantine reprocess integration. Later owner-supplied closure and recovered transcript report the exact semantic commit and live targeted tests. | Zero remaining inside T-099's closed first-eight-PV scope. PV09–PV15, full replay/update semantics, monitoring and exact weight semantics remain with T-100/T-101/T-104/T-103. | 8 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af; parent 86e1b677212195f191697ecdca7e9441b3dbde33; 49/49,5/5,19/19; Gate O 899+1 inherited. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:141-181 — MapMaterialUnitAsync Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — bounded reprocess surface Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:3-20 — narrow topology correction |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-100 | Quarantine, part 2: the remaining seven PV classes and per-class tests | In Progress | Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | 6 | UNCONFIRMED | UNCONFIRMED | UNCONFIRMED | UNCONFIRMED — closure-only; 6/10/16 h superseded | Runner 1 reported GREEN; later fresh DB/constraint passed; live harness failed before classification; final commit not yet supplied. | USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | Worker 1/CENTRAL lock → T-100 final SHA → Worker 2 T-261 → T-245. | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design.
T-101 | Quarantine retry, reprocess and Mapping Health completion | Not Started | POST /api/quarantine/reprocess and row-level reprocess service exist; the endpoint explicitly leaves list/detail/Mapping Health to T-101. Existing C2/import views are reusable scaffolding, not the complete PV/drift/retry monitoring flow. | Add bounded list/detail by code/dataset/batch and source lineage, extend the existing reprocess path, persist/display mapped-column drift, and B4 batch/error/durable-cursor monitoring. Validate API, UI and failure recovery. | 12 | 12 | 18 | 28 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — MapQuarantineEndpoints Backend/PlantProcess.Application/Integration/Services/Staging/StagingRecordService.cs:85-110 — durable staging identity | T-106 owns run-outcome semantics; T-125 owns operational data/health; do not bill those twice. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-102 | Identity resolution across sources | Not Started | material_aliases storage and uniqueness exist. MappingRowProjector creates aliases and resolves a supplied alias, but resolves by AliasCode alone and selects the first material; material-code lookup similarly omits SiteId despite per-site uniqueness. Automatic collision-safe cross-source identity is not complete. | Reuse alias persistence; resolve by governed tenant/site/source/key scope, refuse ambiguity, reconcile two source identifiers into one material and prove idempotent re-import with same alias text across sources/sites. | 8 | 4 | 7 | 12 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:244-264 — MapMaterialAliasAsync Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:721-744 — ResolveMaterialIdAsync Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialAliasConfiguration.cs:27-36 — composite unique Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialUnitConfiguration.cs:43-47 — site/source uniqueness | Do not recreate alias tables or the full row projector. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-103 | Genealogy bidirectional walk hardening and weight proof | Not Started | GenealogyService already rejects self-edges, duplicate edges and cycles by traversal. Migration 841 repairs the deferred weight trigger's schema binding while deliberately preserving its old tolerance. The effective predicate uses abs(sum-1)>0.015, so 0.99 passes that predicate although this task requires rejection. | Retain cycle/self-edge implementation; prove DB direct-write cycle controls and both traversal directions, then reconcile exact declared weight semantics with the 0.015 inherited tolerance and add the explicit 0.99 negative case. | 6 | 4 | 6 | 10 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:27-69 — CreateEdgeAsync Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:95-124 — WouldCreateCycleAsync Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:55-68 — deferred weight check | Weight semantics/negative acceptance stay T-103; 841 topology repair remains accepted. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-104 | Projection provenance, exact-version stamping and idempotent reprojection | Not Started | The current projector skips an already existing MaterialUnit by site/code; it is not a proof that a changed mapping re-materializes previous output. Run history has resolved-target storage, but the existing orchestrator discards the resolver result before dispatch. | On top of the T-261 executor, prove canonical row/run version provenance, idempotent accepted effects and rollback-to-version business equivalence. Reuse first-eight-PV/quarantine infrastructure; do not implement a second executor. | 14 | 8 | 14 | 22 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:168-181 — existing-row skip Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-249 — ResolveDeclaredTargetAsync | T-261 owns first resolved-target runtime call and executor; T-104 owns row effects and rollback proof after it. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-106 | Canonical jobs: target/version, scheduling, dependencies, cancellation and outcome truth | In Progress | Target capability admission, target resolver, real blocked-run evidence, dependency traversal and historical foundation/corrective commits exist. Current source still validates schedules only as nonblank text, runs fixed worker loops, lacks Cancelled in the enum/runtime completion switch, accepts freshness without an age argument and can mark mixed failed batches Ok. | Implement the v4.10.3 schedule contract/parser/due dispatch, explicit freshness policy, truthful aggregate outcomes and cancellation coordination. Reuse the original target/DAG work; T-261 commissions the shared executor/cancellation seam and this task consumes it, not a competing runtime. | UNCONFIRMED | 18 | 28 | 44 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Original target/dependency contract has 8b3eb5c8 foundation and a5451dba corrective; their closure scope is not new schedule/cancel/freshness implementation. Preserve historical evidence; evaluate the later expanded scope separately. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobDefinitionService.cs:275-297 — schedule validation Backend/PlantProcess.Workers/Worker.cs:72-108 — fixed cadence loops Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:33-39 — no age/tolerance input Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:85-91 — Satisfied result Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-146 — terminal-state switch Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:262-276 — import result mapping | T-261 owns executor implementation, first RecordResolvedTarget and common cancellation seam. T-106 owns schedule/DAG/outcome semantics; no double estimate of executor. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-107 | Dual-predicate admission, bounded worker pools and the three ML execution lanes | Not Started | The Worker has staggered timers and sequential awaits for import, data-quality, risk and delta. Separate telemetry buffers use bounded channels, but are not weighted job pools. Existing capability admission decides executability, not job-slot AND resource-capacity admission. | Add actual bounded job queues/pool slots and dual-predicate resource admission, isolation of three ML lanes, backpressure and exact cancellation/release behavior; test saturation and interactive reservation without inventing production capacity constants. | 16 | 12 | 20 | 32 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Workers/Worker.cs:72-108 — ExecuteAsync cadence Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:76-107 — family capability vs capacity | T-155/T-159 calibrate heavy-production constants later; no retraining or new scheduler here. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-108 | End-to-end delta correctness: source cursor, load protection, replay and projection watermark | Not Started | A real delta reader/importer, row envelope and cursor persistence already exist; generic bulk staging rejects duplicate batch/source/row entries. The delta path directly creates a fresh batch/rows and uses a scalar cursor. The PostgreSQL query uses strict > plus LIMIT, MaxCursor parses under ambient culture, and incremental reads bypass the wrapper budget while GetBudget ignores profile/dataset. | Implement total-order cursor/tie-key semantics for every supported incremental reader, typed invariant comparisons, per-source effective budget on incremental calls, durable checkpoint/replay identity and projection watermark handoff. Do not recreate source/staging infrastructure already present. | UNCONFIRMED | 22 | 34 | 52 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — read-path selection Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — row/cursor handling Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:236-280 — source identity and MaxCursor Backend/PlantProcess.Infrastructure/Connectors/PostgreSql/PostgreSqlConnector.cs:181-206 — scalar LIMIT query Backend/PlantProcess.Application/Integration/Protection/ThrottlingDataSourceReader.cs:36-70 — unequal protection Backend/PlantProcess.Infrastructure/Integration/Protection/OptionsSourceLoadBudgetProvider.cs:21-24 — global budget Backend/PlantProcess.Infrastructure/Persistence/Configurations/Integration/StagingRecordConfiguration.cs:31-42 — existing within-batch uniqueness Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:58-73 — current weak continuation assertions | T-106 owns Job aggregate status; T-101 B4 UI; T-109 consumes this watermark; no duplicate billing for those consumers. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-109 | Delta-scoped feature refresh and analysis, with telemetry and ML hand-off | Not Started | The repository has source-delta infrastructure, ML refresh paths and pure analytical kernels, but the inspected analytical service paths do not show a commissioned consumer of the designed feature_refresh/analysis_scope watermark chain. Existing calculation code is reusable, not proof of bounded changed-entity execution. | Consume T-108's committed batch/delta token, materialize changed subjects through governed relations, refresh bounded feature/analysis scope and telemetry, and emit the ML handoff. Prove late data and interrupted retries without a second cursor store. | 6 | 6 | 10 | 18 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-217 — available source delta boundary Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:85-113 — governed automated path | T-108 owns source/projection checkpoint; M3 materializers own full training artifacts. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-207 | Connector capability truth: stop advertising unimplemented browse/read/subscription | Done | HistorianConnectorCapabilities explicitly declares real browse/read/subscription/session operations unavailable and returns named capability truth. This is a real honest-refusal foundation, not a production OPC implementation. | No original T-207 reimplementation. New backend provider-list convergence belongs to expanded T-254; live OPC operations belong to T-224..T-226. | 6 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Not recovered from reviewed sessions | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — HistorianConnectorCapabilities |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-212 | Integrate aggregation semantics into Layer-A widget/query execution | Not Started | SignalSemanticsResolver already resolves aggregation through the governed database function with AG01/type refusal and a DI registration. Current production reference census finds its definition/implementation/registration, but no widget/query service injection/call. Frontend aggregate binding copies declared metadata; it performs no analytics. | Wire the existing semantics authority into Layer-A widget/query execution and consume the T-211 arithmetic contract. Preserve declared weighting/sampling/null rules, typed refusals and result evidence; do not implement a new aggregation authority. | 10 | 6 | 9 | 14 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — ResolveAsync Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — not analytics mathematics | T-211 computes math; T-210 governs semantics; T-212 wires actual queries. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-213 | Customer Data Intake and Capability Assessment authority | Done | CustomerAssessmentEndpoints exposes authorized assess/latest/version/diff operations and resolves tenant identity before service work. The service/normalization/history migration and tests are present. This is a reusable assessment authority, not an autonomous ingestion/projection executor. | No new work within the accepted T-213 authority scope. Customer intake use within the real UI journey remains the consumer's acceptance, not reopening this producer. | 8 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | 2748c7fba8a5c4763bc19112ce57e484cea5b9bb — subject not recovered | Backend/PlantProcess.Api/Endpoints/CustomerAssessmentEndpoints.cs:86-125 — assessment routes and tenant gate |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-224 | Production OPC UA edge runtime: endpoint security, certificates and session lifecycle | Not Started | The current OPC connector only validates supplied endpoint/read-only configuration and explicitly refuses a requested live handshake. The separate capability authority says session security/certificate/trust handling is not implemented; there is no evidence that the advertised target session is commissioned. | Implement real read-only OPC endpoint/session/certificate lifecycle on the customer-side collector, with governed trust references, security-policy rejection, reconnect and safe telemetry. Reuse configuration/capability contracts, not their success text as handshake proof. | 12 | 10 | 16 | 26 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration test Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — live capability declarations | T-225 browse/subscription; T-226 end-to-end data/recovery; T-266 design. No M3 deferral. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-225 | Production OPC UA edge runtime: browse, tag registration, subscription and monitored items | Not Started | Current truth explicitly marks tag browse, bounded value read and subscriptions unimplemented. The UI and supplied-tag hints do not establish real namespace traversal or monitored-item persistence. Session support is T-224's prerequisite. | Build namespace browse, stable node identities, tag registration, bounded read/subscriptions and monitored-item lifecycle using the T-224 session and source-load policy; test partial browse, disconnect and invalid intervals. | 12 | 10 | 16 | 26 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:76-95 — browse/read/subscription capability state Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:53-70 — metadata-only legacy claim | Do not recreate session security or count T-266 graphics as real read proof. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-226 | Production OPC UA edge runtime: quality/timestamps, recovery and spool-to-canonical proof | Not Started | Historian mapping/legacy tag-history and edge-spool scaffolding exist, while real upstream OPC read/subscription operations remain unavailable. Those existing interfaces are useful but do not prove quality/timestamp preservation or replay into canonical data from a live session. | Integrate source/server/ingest time and quality handling, spool/ack/reconnect/gap recovery and idempotent canonical replay using T-233/T-224/T-225; run controlled interruption and real-source evidence. | 12 | 10 | 16 | 28 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — upstream live-operation boundary Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — existing time kernel | No new time-authority kernel; no reuse of demo telemetry as customer-source proof. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-232 | Persist Performance Reference authority and projections | Not Started | The supplied snapshot includes signal semantics and ordinary limits/parameter storage, but no production Performance Reference authority was located by class/table/name and consumer search. Existing semantics infrastructure is reusable; it is not the effective-dated reference precedence contract. | Implement effective-dated reference persistence, precedence/provenance and governed projections consuming T-214; test overlapping definitions, missing direction/unit and deterministic read-back. Do not reimplement the T-214 decision kernel. | 6 | 5 | 8 | 13 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — existing semantic infrastructure only | T-214 owns reference decision kernel; T-215 consumes BI projections; a negative symbol search alone is not live absence proof. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-233 | Persist Source Time Authority and observation timestamp provenance | Not Started | SourceTimeAuthorityKernel already resolves declared source/signal timestamps to uncertainty-bearing instants and refuses unauthorized time roles. The reviewed Domain/Infrastructure models do not contain the corresponding source/server timestamp authority fields/adapter, so kernel completion is not persistence completion. | Persist declared time authority and observation provenance, bind acquisition/projector consumers to the existing kernel, and prove zone/offset/uncertainty conflict handling without machine-locale fallback. | 5 | 5 | 8 | 14 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-97 — Resolve / ResolveAs Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:184-210 — current material time fields | Do not charge T-216 kernel work again; OPC T-226 consumes the approved time contract. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-235 | Persist transition/stabilisation authority and regime context | Not Started | OperationalTransitionKernel and TransitionAwarePoolingGuard contain actual regime classification and uncertainty-aware pooling refusal. Direct production reference census only finds kernel-to-kernel calls; it does not establish a persisted regime authority consumed by live statistics. | Persist transition/stabilisation declarations and wire current M2 statistical/correlation pooling to the existing guard. Include source-time uncertainty and explicit undeclared-regime handling; prove the live path refuses mixed/uncertain populations. | 8 | 6 | 11 | 18 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Analytics.Core/Kernel/Regime/TransitionAwarePoolingGuard.cs:24-79 — Admit Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — time interpretation | Do not redo T-234/T-236; later broad engine convergence stays T-146. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-241 | Canvas executable block contract, typed ports and graph validation | Done | The shared graph semantics imports typed ports and one block-contract registry; the registry distinguishes implemented/evaluable/persistable capabilities. Those executable validation contracts are real foundation code, not proof of a commissioned job executor. | Retain original typed-port/graph-validation closure. Any actual execution or visual-depth remainder belongs to T-245/T-261/T-265, not recreation of the T-241 graph model. | 10 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | eb7fb2ab — subject not recovered | Frontend/PlantProcess.Web/src/authoring/graphSemantics.ts:22-40 — typed-port authority Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — capability separation |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-242 | Canvas production block library: relational, arithmetic, logic, window and governed aggregate | Done | The block catalogue is centralized, typed and explicit about evaluable versus persistable behavior. Governed aggregation copies canonical metadata and refuses missing semantics; it deliberately computes no analytics. Non-placeable families must not be described as already commissioned product execution. | Original algebra/catalogue/validation closure remains closed. Persistence/compilation/runtime integration is the relevant downstream work and must retain honest unavailable states until accepted. | 16 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 — final: T-242 close governed aggregate and window block contracts | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — one catalogue and separate capabilities Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — handoff boundary Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:49-77 — AG01 behavior |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-243 | Canvas persistence, immutable versioning and reopen/edit round-trip | In Progress | The authored board, governed output target, version history and reopen logic exist; the September 9 closure proves mocked-server reopen/edit behavior. Canvas publish calls the canonical definition writer and compatibility projector in a transaction, but does not call the existing relationship-publication authority. | Only the added relationship-emission/atomicity/legacy-path convergence remains: derive declared relationships, publish through the existing service in the correct unit of work, and prove rollback/read-back. Preserve the saved-board implementation and its closure. | 12 | 5 | 9 | 15 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Original save/reopen journey committed 6f65bba186ecaccc8dbbdfc5eba830a9e1b3e933; executed tests drove the shell against mocked canonical responses. New relationship emission integration is later scope, not proof the original reopen task never completed. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — canonical graph/board content Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:265-333 — publish transaction Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — existing publication seam | Do not implement a second relationship store. T-262 save-mapping concern is tracked once there, not charged again. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-244 | SQL-mode production convergence: compile, validate, bounded dry-run and definition persistence | Done | The current SQL-mode save uses canonical content and the shared safe-SQL/lifecycle path, and SQL publication derives a compatibility projection within the same transaction. This substantiates the earlier persistence/convergence foundation; it does not execute a governed projection job. | Keep the original T-244 closure. The later projection-binding callback concern belongs to the T-262 consumer boundary, and runtime transformation execution belongs to T-261. | 14 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | 4d32c6b10b4605aeb6e0705ad03537d563125652 — T-244 close canonical Canvas lifecycle and selection model | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:173-205 — ForSql Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:297-333 — SQL publish path Frontend/PlantProcess.Web/src/api/canvasApi.ts:118-155 — SQL run/save API adapter |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-245 | Canvas-to-job compilation, binding, run monitor and per-block evidence | Not Started | Canvas has draft save, SQL preview, publish and reopen adapters; the job target resolver/capability descriptors exist. The current shell/API adapter has no commissioned bind-and-run flow consuming exact version/per-block runtime evidence, and CanonicalRefresh is explicitly unavailable. | Implement the thin Canvas-to-job binding/launch/monitor/error/cancel surface over T-261's real executor, carry exact version and stable block IDs, and test unavailable-family refusal before launch. | 12 | 6 | 10 | 16 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Frontend/PlantProcess.Web/src/api/canvasApi.ts:111-155 — current save/preview/publish surface Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-124 — non-executable target families | T-245 is QUEUED after T-261 accepted closure; no separate executor, block-evidence model or capability authority. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-247 | First-customer Day-1 Golden Journey and same-binary onboarding proof | Not Started | Individual source/import/Canvas/BI surfaces and earlier demo/journey tests exist, but the supplied production snapshot explicitly refuses governed Transformation execution. The required same-binary customer path cannot be certified by the present source or Figma output alone. | After producer closures, execute one customer-shaped real-source-to-canonical-to-BI/Assistant journey with immutable-version/retry/cancel/refusal/isolation evidence and zero customer-specific product diff. Budget acceptance coordination only; bugs remain with their owning tasks. | 12 | 8 | 14 | 22 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — concrete broken journey seam Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:32-73 — earlier tests are not full new journey proof | No source-code or drawing count can close runtime acceptance; no duplicate budget for T-106/T-108/T-261 fixes. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-253 | Shared authoring governed output-target canonical-content contract | Done | Canonical content carries one outputTarget; model marker/catalogue authority determines eligible targets and exposes fields. Existing graph/SQL hash and read-back behaviors are real. This is independent of current job executor availability. | No new original output-target work. Preserve original 7a6f91f9 closure; downstream publication and executor consume that authority. | 12 | 0 | 0 | 0 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | None | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — ForGraph outputTarget/board Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — strict compatibility |  | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-254 | Customer-facing connector capability truth convergence | In Progress | The frontend/website runtime-truth convergence was closed at f8a35725. Current backend still has a separate ConnectorConfigurationService provider DTO list beside ConnectorProviderCatalog. Their OPC browse flags and membership/descriptions differ; configuration reads the former. | Complete only the widened backend validation/catalogue convergence and regression tests ensuring profile validation, API truth, UI and website consume one result. Retain frontend/website original closure and absence-of-fallback evidence. | 6 | 2 | 4 | 7 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | f8a35725c9b0d7fb5a0515c0103a72807a704a97, historical accepted freeze. New scope is not a regression claim against the original. | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:17-39 — duplicate provider DTO source Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:81-102 — OPC flags Backend/PlantProcess.Application/Integration/Connectors/ConnectorProviderCatalog.cs:72-104 — second catalog OPC/SAP entries | No rewrite of T-207, no source availability invented from a certification flag. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-261 | Governed Transformation/Projection job executor and per-block runtime evidence seam | In Progress | The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit. | Extract/reuse the compiler; implement resolver+executor, carry the pre-admission target into the real run, canonical row effects/idempotency/provenance and stable block evidence, common cancellation/status wiring; run Graph/SQL and failure/cancel proof on disposable DB. Include T-262 live Gate 0 once. | 12 | 16 | 26 | 42 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Pasted markdown(20260914-190300).md:1-239 assigns first RecordResolvedTarget, cancellation seam and T-262 live Gate0 to T-261. No post-ca02b40e executor commit retrieved. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — admission before real run Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-276 — discarded resolution/dispatch Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — uncommissioned executor Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-149 — terminal lifecycle | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-262 | Governed projection declaration and canonical field-binding contract | In Progress | The declaration, field catalogue, server type checker and Graph/SQL hash persistence exist and were committed GREEN at 86e1b677. A current consumer concern remains: doSaveSql reads projection/projectionBlocked but omits both from its useCallback dependency list; a mapping-only edit needs a direct shell regression test. Unknown-type/narrowing acceptance finding remains withdrawn. | Do not rebuild the declaration. Reproduce the mapping-only SQL-save transition against the real shell, fix only any demonstrated stale callback, and run targeted field-map tests. Live definition-store Gate 0 is already assigned to T-261 Runner2, so it is not estimated again here. Final status remains current-scope open until this correction/acceptance is resolved. | UNCONFIRMED | 1 | 3 | 6 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | Original declaration delivered GREEN/COMMITTED at 86e1b677212195f191697ecdca7e9441b3dbde33. 12-Sep output: 24/24 declaration, 8/8 catalogue fields, 39/39 content, 404/404 authoring. Live definition-store integration explicitly not claimed. Later 14-Sep coordination assigns that proof to T-261 Runner 2 Gate 0. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:118-163 — immutable projection content Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — unknown/narrowing refusal Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:898-925 — doSaveSql callback inputs/dependencies | Do not reimplement the immutable declaration. Live definition-store Gate 0 is carried once in T-261 acceptance/estimate. This task's proposed 1/3/6h is the mapping-only SQL save concern and bounded verification, not another executor. Current composite status retained; closure ownership needs explicit reconciliation, not a fake missing-commit claim. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.
T-266 | Release-1 OPC-UA UI workflows and capability-truth design | Not Started | The source has historian configuration UI/API scaffolding and truthful unavailable operations, while the delivered visual package is a derived design. No native Figma execution or full target/current capability state interaction is established by current repository source. | Design the named OPC profile/browse/read/subscription/quality/time/spool/replay flow and its unavailable states against T-224..T-226 contracts, integrate into Chapter3/4 and embedded Word images, and execute one observed design import/prototype check without claiming live OPC. | UNCONFIRMED | 6 | 10 | 16 | REVIEW PROPOSAL — NOT CONFIRMED / NOT P80 | No implementation or native-Figma closure claimed. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — actual unavailable contract Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration interface | T-224..T-226 implement/live-certify; T-233 time authority; native design execution availability is a separate uncertainty. | 14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.

## Review 15Sep
PLANTPROCESS IQ ¦ BACKLOG CELL & EVIDENCE REVIEW
v2.23.0 retained •15September2026 • one workbook only • no Design, task-ID, release, scope or dependency-edge additions
LIMIT: the complete ten named sessions were not recovered. Source-bound corrections below are real; all statuses are not thereby fully verified.
Metric | All | M2 | M2-P2 | Interpretation | Basis | OPEN THE NAMED WORKSHEET TAB
Active tasks | 179 | 107 | 34 | Task set / releases preserved | Task-ID comparison against input | M2-P2 Review — 34 M2-P2 tasks: current vs historical delivery and hours
Done | 62 | 62 | 14 | Task closure ≠ release certification | T-099 preserved; no wholesale completion inference | Task Evidence 15Sep — All179 task decisions with source and unresolved action
In Progress | 3 | 3 | 3 | Partial current scope; not proof worker active now | T-254 original closed baseline + unproven extension | Estimate Review — Prior estimates and why they are no longer usable
Not Started | 114 | 42 | 17 | Preflight alone is not implementation | Other uncorroborated statuses retained explicitly | Cell Changes 15Sep — Before/after cell records and structural changes
Unusable/missing estimate | 31 | 18 | 14 | 8 missing/withdrawn +19 stale scope | Historical estimates retained. New UNCONFIRMED remaining proposals in Source Review/Backlog AV:AX. | Source Summary / Source Review — current implementation and remaining work, not just session claims.
Non-withdrawn scope hours | 1521 | 872 | 199 | Partial planning sum, not actual/remaining effort | Other inherited estimates not recalibrated by this review
Status: green Done • amber In Progress • grey Not Started • red Blocked. Amber hours: missing/stale/unconfirmed, not zero. Violet P80: historic forecast not supplied.
No open completion predecessor is not automatic permission to start: contract-ready handoffs, evidence and scoped start gates still apply.
EXACT TEN-SESSION COVERAGE — DO NOT CONFUSE FRAGMENTS WITH COMPLETE TRANSCRIPTS
Requested # | Exact session title | Complete transcript read? | Available material | Read operation / limit | Remaining requirement
1 | استكمال جلسة 10 سبتمبر | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
2 | 10-Sept-2026 | NO | Dated10Sep attachments:064052,102642,105308; contains selected session forwards, run outputs and instructions, not complete named session. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
3 | حالة المشروع الحالية | NO | Selected excerpts exist in the current conversation; full original session not available. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
4 | تحليل الجلسات الثماني | NO | Exact-title file found: تحليل الجلسات الثماني.txt;709bytes, only an earlier access-failure message. Not the session body. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
5 | 8-Sept-2026 | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
6 | تحليل الجلسات بالتفصيل | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
7 | نصائح وتعديلات التمرين | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
8 | إصلاح وتشغيل السكربت المركزي | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
9 | تحليل قواعد البيانات | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
10 | حكم مهمة T205 | NO | No complete transcript with this exact title was retrieved. Current workbook and fragments are not substitutes. | Files exact-title/content search + local inventory. Conversation-history retrieval returned an error. Source files.read/find worked for the listed attachments. | Obtain full exact transcript, then check later superseding decisions and scope before certifying every task status.
ALL ORIGINAL WORKSHEETS: EVERY STORED CELL SCANNED — SEMANTIC COVERAGE IS NOT IMPLIED
Worksheet | Stored cells | Populated cells | Formula cells | Review classification | Coverage / limitation
Current Authority | 366 | 61 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Backlog | 7920 | 6996 | 185 | CURRENT — STRUCTURAL/FIELD CHECKS | 179 rows / all44 original fields scanned. Evidence corrections source-bound for named tasks; all10-session semantics unresolved.
Release Plan | 510 | 133 | 70 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Worker Tracks | 2642 | 2521 | 2327 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Requirement Traceability | 170 | 151 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Dependency Graph | 2280 | 1800 | 1611 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Prior Baseline Archive | 712 | 445 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Governance | 270 | 106 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Method & Notes | 224 | 93 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Commit Ledger | 396 | 376 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Backlog Change Log | 312 | 297 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Verified Task Ledger | 1819 | 1648 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Phase Worker v220 | 264 | 205 | 2 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Dashboard v220 | 272 | 173 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Capability Map v1.1 | 1190 | 1109 | 702 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Retired Tasks v222 | 36 | 24 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Revision Changes v222 | 4949 | 2022 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Phase Worker v222 | 410 | 311 | 210 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Prior Notes v222 | 1224 | 306 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Dashboard v222 | 672 | 59 | 27 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Contract Handoffs | 182 | 182 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Estimate Review | 84 | 57 | 21 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Repair Changes v2221 | 5124 | 4508 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
External Prerequisites | 48 | 24 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Secondary Capability Links | 600 | 600 | 298 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
UI Coverage v223 | 2981 | 2981 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
UI Controls v223 | 2981 | 2981 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Changes v223 | 145 | 139 | 0 | HISTORICAL — PRESERVED | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
UI Delivery v223 | 222 | 71 | 24 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Book Register | 92 | 92 | 0 | CURRENT — STRUCTURAL/FIELD CHECKS | Values, formula references, styles, used ranges, metadata and cross-field consistency scanned; historical events not re-certified.
Book Validation | 88 | 87 | 9 | CURRENT — STRUCTURAL/FIELD CHECKS | Original14Sep consolidation results explicitly labelled historical; current15Sep checks are below.
RESIDUAL EVIDENCE / GOVERNANCE LIMITS
Full ten sessions | NOT COMPLETE | Exact titles retained in rows17–26. Accessible dated fragments are not substitutes for the missing transcripts.
T-262 current status | UNRESOLVED DISPOSITION | Producer contract GREEN/commit is proven; current row also requests integration closure. The incomplete integration cannot be silently waived or the prior GREEN erased.
Time estimates | 27 NOT USABLE | 8 missing/withdrawn/unconfirmed;19 have numeric old-scope figures that need re-estimation. No remaining-time guarantee.
Start gate prose | 15 OPEN TEXT GAPS | 17 original gate strings were truncated;2 belong to already-closed tasks,15 open tasks still need omitted text resolved. Full fragments preserved.
Task-ID epoch | REQUIRED CHECK | Older exports reuse task numbers for different programme scopes. Match identity plus semantic scope/date; a same-number old Done entry does not close today's task.
Runtime / Git | NOT EXECUTED | Reviewed source and stored executed outputs. No live product/test/database/browser certification or current Git ancestry executed here.
Status colors | FORMULA-DRIVEN | Colors map the current status field. They do not imply that all current statuses were freshly verified against ten complete sessions.
SAVED-WORKBOOK VALIDATION •22 PASS /3 OPEN • SOURCE-HISTORY GAPS ARE NOT PASSES
Check | Count | Result | Meaning / evidence boundary
Input workbook identity | 469445 | PASS | Current book v2.23.0 bytes; SHA in row108, not an older rejected fork.
Original worksheets scanned | 31 | PASS | 39185 stored /30558 populated cells;5486 formula cells. Structural scan, not full external factual verification.
Active task identities | 179 | PASS | Exact Task ID set preserved.
Release allocation | 179 | PASS | M2=107/M3=72; no task moved.
Description/acceptance scope | 179 | PASS | Original H/I text retained, not silently rewritten from generic knowledge.
Dependency triples M/N/AN | 179 | PASS | No row-shift or unilateral dependency edit.
Graph invariants | 0 | PASS | No self edges/cycles/undeclared dangling/M2->M3 completion edges; exact reverse precedences.
Dependency Graph cache matches | 179 | PASS | All179 rows; task/owner/status/dependencies/gate/contract fields checked.
Worker Tracks cache matches | 179 | PASS | All179 task-ID keyed views checked.
Capability map formulas/membership | 78 | PASS | Every primary/secondary/status/release count and listed-ID set checked.
Duplicate primary-secondary | 0 | PASS | Removed redundant T-254/L1.4 self-secondary; no scope dropped.
Numeric hours preserved | 179 | PASS | No fabricated estimate;19 stale originals remain visible, excluded from planning.
Estimate unresolved explicitly | 27 | PASS | 8 initially missing +19 stale. Future confirmed estimate state supported.
T-099 closure preserved | 1 | PASS | Final transcript now corroborated; inherited RED retained separately.
Status categorical values | 179 | PASS | 58Done/5InProgress/116NotStarted; only T-254 progress category corrected.
All saved cell style IDs | 313 | PASS | Every saved cell resolves to a valid style definition.
Status CF full extent | 179 | PASS | One exact status rule group; obsolete overlap removed.
Dropdown/numeric validation extent | 6 | PASS | No overlapping stale validation ranges; final rows covered.
Any saved Excel error cells | 0 | PASS | All cell types checked, not just a #REF regex. Unsupported HYPERLINK removed.
Historical archives unchanged | 10 | PASS | Original values/formula expressions preserved in history-only worksheets.
Table names | 13 | PASS | Unique Excel table names; current Backlog extent A1:AT180.
Validator negative controls | 3 | PASS | Injected self-edge, cross-release edge and broken reciprocal precedence each rejected.
Full requested session review | 0 | OPEN | Zero complete exact-title transcripts read. Selected attached execution evidence is clearly separated; rows17–26.
Current T-262 final disposition | 1 | OPEN | Contract GREEN recovered; needed integration acceptance still unexecuted/undispositioned. No false Done or no-SHA claim.
Open truncated gate text | 15 | OPEN | Omitted wording not manufactured. Exact fragments retained for resolution.
Input SHA256: 730b1c671f68790b47748a2bfbe885e06e9fc1ed3b2fb35376b5853af55c29a2
Net original-sheet value/formula differences: 2166; formatting/rule log records:539. All prior values are preserved in this workbook's log.

## Cell Changes 15Sep
Worksheet | Cell/range | Before | After | Reason (net differences, not product findings) | Evidence/basis
Current Authority | A1 | PPIQ BACKLOG v2.23.0 — UI design/workflow convergence | PPIQ BACKLOG v2.23.0 — cell/evidence review15Sep2026 | Current authority statement must match this specific review and its limits.
Current Authority | C4 | 2026-09-14 | 2026-09-15 | Current authority statement must match this specific review and its limits.
Current Authority | D4 | Supersedes both divergent v2.22.1 files. Baseline is the repaired 176-task workbook; adds T-265..T-267 without regressing closure or estimates. | Same task/scope version. This review corrects evidence, current labels, estimate usability and formatting; no tasks/releases/dependency edges added or removed. | Current authority statement must match this specific review and its limits.
Current Authority | C9 | Owner report received 2026-09-14 | Final14Sep terminal transcript inspected15Sep | Current authority statement must match this specific review and its limits.
Current Authority | D9 | CLOSED GREEN / COMMITTED; task-level closure, not release-wide GREEN. | CLOSED GREEN/COMMITTED; exact transcript corroborated. DefinitionKind known-red remains; not release-wideGREEN. | Current authority statement must match this specific review and its limits.
Current Authority | B10 | SOURCE PRESENT / UNCLOSED | CONTRACT GREEN COMMIT86e1b677; INTEGRATION UNVERIFIED | Current authority statement must match this specific review and its limits.
Current Authority | C10 | 2026-09-14 | Evidence from12Sep; reviewed15Sep | Current authority statement must match this specific review and its limits.
Current Authority | D10 | Status remains In Progress; no accepted closure SHA has been supplied. | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | Current authority statement must match this specific review and its limits.
Current Authority | B11 | 8 rows unestimated / withdrawn / unconfirmed | 27 unresolved estimates:8 missing/withdrawn/unconfirmed +19 stale scope | Current authority statement must match this specific review and its limits.
Current Authority | C11 | 2026-09-14 | 2026-09-15 | Current authority statement must match this specific review and its limits.
Current Authority | D11 | T-106/T-108 remain blank; T-262..T-264 remain unestimated; T-265..T-267 proposals are not accepted Hours or P80. | J/R preserve supplied historical values. AS/AT supply usable partial planning totals; AM=0 for missing/stale/unconfirmed values. No fabricated actual hours or remaining effort. | Current authority statement must match this specific review and its limits.
Current Authority | B12 | Backlog!A1:AR180 | Backlog!A1:AT180 | Current authority statement must match this specific review and its limits.
Current Authority | B14 | Workbook structure, formulas and dependency invariants | All-sheet cell/formula/style scan; bounded historical-source reconciliation | Current authority statement must match this specific review and its limits.
Current Authority | C14 | 2026-09-14 | 2026-09-15 | Current authority statement must match this specific review and its limits.
Current Authority | D14 | Not a new product runtime, live DB, repository or full-release certification. | All original31 worksheets structurally inspected. Full ten named session transcripts not recovered; current task statuses not all externally re-proven. See Review15Sep/Task Evidence15Sep. | Current authority statement must match this specific review and its limits.
Current Authority | A17 |  | 15Sep detailed review | Add a visible in-workbook entry, not an external file.
Current Authority | B17 |  | Review 15Sep — open the worksheet tab | Avoid an unsupported cached HYPERLINK formula; keep navigation usable by explicit tab name.
Current Authority | C17 |  | 2026-09-15 | Review date, not a delivery commitment.
Current Authority | D17 |  | M2-P2 view + all-task evidence + exact session coverage + cell changes are inside this workbook. No extra file in the Design Book. | Honor the single-backlog-file standard.
Backlog | AM1 | Has estimate | Usable scope estimate (1/0) | A numeric old-scope estimate is not automatically usable.
Backlog | AS1 |  | Usable planning hours | Exclude withdrawn/stale/unconfirmed scope figures from live planning.
Backlog | AT1 |  | Usable planning P80 h | P80 is not regenerated from a nominal multiplier.
Backlog | T2 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM2 | =IF(ISNUMBER(J2),1,0) | =IF(AND(ISNUMBER(J2),OR(AR2="INHERITED ESTIMATE",AR2="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS2 |  | =IF(AM2=1,J2,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT2 |  | =IF(AND(AM2=1,ISNUMBER(R2)),R2,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T3 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-086 + T-088 canonical migration order/runner/truth gate established FIRST. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM3 | =IF(ISNUMBER(J3),1,0) | =IF(AND(ISNUMBER(J3),OR(AR3="INHERITED ESTIMATE",AR3="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS3 |  | =IF(AM3=1,J3,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT3 |  | =IF(AND(AM3=1,ISNUMBER(R3)),R3,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T4 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-086 frozen M2 reference dataset; define canonical migration order before T-... | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM4 | =IF(ISNUMBER(J4),1,0) | =IF(AND(ISNUMBER(J4),OR(AR4="INHERITED ESTIMATE",AR4="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS4 |  | =IF(AM4=1,J4,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT4 |  | =IF(AND(AM4=1,ISNUMBER(R4)),R4,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T5 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-087 + T-088 canonical three-schema/migration authority green. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM5 | =IF(ISNUMBER(J5),1,0) | =IF(AND(ISNUMBER(J5),OR(AR5="INHERITED ESTIMATE",AR5="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS5 |  | =IF(AM5=1,J5,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT5 |  | =IF(AND(AM5=1,ISNUMBER(R5)),R5,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T6 | IN PROGRESS — T-089 complete. Full T-090 remains one task and one final commit. Worker 1 must deliver one self-contained standard PowerShell apply pack; no scope split and no manual .cs/SQL installation. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM6 | =IF(ISNUMBER(J6),1,0) | =IF(AND(ISNUMBER(J6),OR(AR6="INHERITED ESTIMATE",AR6="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS6 |  | =IF(AM6=1,J6,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT6 |  | =IF(AND(AM6=1,ISNUMBER(R6)),R6,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T7 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-090 all definition kinds bound to the canonical store. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM7 | =IF(ISNUMBER(J7),1,0) | =IF(AND(ISNUMBER(J7),OR(AR7="INHERITED ESTIMATE",AR7="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS7 |  | =IF(AM7=1,J7,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT7 |  | =IF(AND(AM7=1,ISNUMBER(R7)),R7,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T8 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-089 + T-090 canonical definition authority. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM8 | =IF(ISNUMBER(J8),1,0) | =IF(AND(ISNUMBER(J8),OR(AR8="INHERITED ESTIMATE",AR8="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS8 |  | =IF(AM8=1,J8,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT8 |  | =IF(AND(AM8=1,ISNUMBER(R8)),R8,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T9 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-092 registry/definition authority available; architecture term list is comm... | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM9 | =IF(ISNUMBER(J9),1,0) | =IF(AND(ISNUMBER(J9),OR(AR9="INHERITED ESTIMATE",AR9="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS9 |  | =IF(AM9=1,J9,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT9 |  | =IF(AND(AM9=1,ISNUMBER(R9)),R9,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T10 | IN PROGRESS — T-092/T-093/T-209 authorities are green. Three part-commits exist but no closure. Finish the second wire, frontend consumers and Wave-C proof under the same T-094 scope; do not reopen after closure. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM10 | =IF(ISNUMBER(J10),1,0) | =IF(AND(ISNUMBER(J10),OR(AR10="INHERITED ESTIMATE",AR10="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS10 |  | =IF(AM10=1,J10,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT10 |  | =IF(AND(AM10=1,ISNUMBER(R10)),R10,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T11 | Start immediately. No later M2 mutating work begins on the shared tree before this close. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM11 | =IF(ISNUMBER(J11),1,0) | =IF(AND(ISNUMBER(J11),OR(AR11="INHERITED ESTIMATE",AR11="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS11 |  | =IF(AM11=1,J11,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT11 |  | =IF(AND(AM11=1,ISNUMBER(R11)),R11,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T12 | T-201 committed/frozen baseline. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM12 | =IF(ISNUMBER(J12),1,0) | =IF(AND(ISNUMBER(J12),OR(AR12="INHERITED ESTIMATE",AR12="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS12 |  | =IF(AM12=1,J12,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT12 |  | =IF(AND(AM12=1,ISNUMBER(R12)),R12,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T13 | T-201; may run in parallel with T-202 on non-overlapping test files. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM13 | =IF(ISNUMBER(J13),1,0) | =IF(AND(ISNUMBER(J13),OR(AR13="INHERITED ESTIMATE",AR13="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS13 |  | =IF(AM13=1,J13,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT13 |  | =IF(AND(AM13=1,ISNUMBER(R13)),R13,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T14 | T-201; resolve current associative ownership first. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM14 | =IF(ISNUMBER(J14),1,0) | =IF(AND(ISNUMBER(J14),OR(AR14="INHERITED ESTIMATE",AR14="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS14 |  | =IF(AM14=1,J14,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT14 |  | =IF(AND(AM14=1,ISNUMBER(R14)),R14,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T15 | CLOSED GREEN 2026-08-30 at b7fcc890. Infrastructure gate certified. Do not rerun full T-205 Certify unless the T-205 gate/validator/watchdog/reaper/evidence contract itself changes. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM15 | =IF(ISNUMBER(J15),1,0) | =IF(AND(ISNUMBER(J15),OR(AR15="INHERITED ESTIMATE",AR15="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS15 |  | =IF(AM15=1,J15,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT15 |  | =IF(AND(AM15=1,ISNUMBER(R15)),R15,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T16 | T-201. Isolated architecture test files only until each product owner consumes findings. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM16 | =IF(ISNUMBER(J16),1,0) | =IF(AND(ISNUMBER(J16),OR(AR16="INHERITED ESTIMATE",AR16="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS16 |  | =IF(AM16=1,J16,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT16 |  | =IF(AND(AM16=1,ISNUMBER(R16)),R16,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T17 | T-201. May run in parallel with T-206; no production DB migration/DI. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM17 | =IF(ISNUMBER(J17),1,0) | =IF(AND(ISNUMBER(J17),OR(AR17="INHERITED ESTIMATE",AR17="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS17 |  | =IF(AM17=1,J17,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT17 |  | =IF(AND(AM17=1,ISNUMBER(R17)),R17,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T18 | T-208 only; no production DB dependency. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM18 | =IF(ISNUMBER(J18),1,0) | =IF(AND(ISNUMBER(J18),OR(AR18="INHERITED ESTIMATE",AR18="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS18 |  | =IF(AM18=1,J18,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT18 |  | =IF(AND(AM18=1,ISNUMBER(R18)),R18,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T19 | T-209 + T-090. Complete before T-092 exposes measures and before T-211 integration. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM19 | =IF(ISNUMBER(J19),1,0) | =IF(AND(ISNUMBER(J19),OR(AR19="INHERITED ESTIMATE",AR19="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS19 |  | =IF(AM19=1,J19,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT19 |  | =IF(AND(AM19=1,ISNUMBER(R19)),R19,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T20 | T-208 fixture; no canonical DB dependency. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM20 | =IF(ISNUMBER(J20),1,0) | =IF(AND(ISNUMBER(J20),OR(AR20="INHERITED ESTIMATE",AR20="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS20 |  | =IF(AM20=1,J20,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT20 |  | =IF(AND(AM20=1,ISNUMBER(R20)),R20,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T21 | T-090 + committed T-209 contract. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM21 | =IF(ISNUMBER(J21),1,0) | =IF(AND(ISNUMBER(J21),OR(AR21="INHERITED ESTIMATE",AR21="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS21 |  | =IF(AM21=1,J21,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT21 |  | =IF(AND(AM21=1,ISNUMBER(R21)),R21,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T22 | T-205 CLOSED GREEN at b7fcc890. Two read-only adjudication extracts are sufficient; no third diagnostic runner. Build one corrective pack, run narrow tests, then one normal full frontend suite. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM22 | =IF(ISNUMBER(J22),1,0) | =IF(AND(ISNUMBER(J22),OR(AR22="INHERITED ESTIMATE",AR22="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS22 |  | =IF(AM22=1,J22,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT22 |  | =IF(AND(AM22=1,ISNUMBER(R22)),R22,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T23 | PAUSED AFTER MACHINE INSTALL/CENSUS. T-260 is the immediate blocker because the designated fresh certification DB was proven to be built from an incomplete canonical path. Do not adjudicate the current fresh-DB 106/81 queue. Resume T-251 only after T-260 rebuilds `ppiq_acceptance_empty` correctly and produces a new census. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | Y23 |  | 7ba31f96f3810bdac734bd1850275a601503d34d | Recover an explicitly supplied closure anchor, not a guessed commit. | Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes.
Backlog | AM23 | =IF(ISNUMBER(J23),1,0) | =IF(AND(ISNUMBER(J23),OR(AR23="INHERITED ESTIMATE",AR23="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AP23 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Original catalogue closure explicitly frozen by CENTRAL. Retain Done; later catalogue/build changes do not retroactively erase this producer closure. Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes. | Restore omitted historical closure evidence. | Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes.
Backlog | AS23 |  | =IF(AM23=1,J23,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT23 |  | =IF(AND(AM23=1,ISNUMBER(R23)),R23,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T24 | P1 PROMOTION IN v2.20.0 — start immediately after T-251 closes. Certification infrastructure must stop touching shared/live databases before further database/runtime closure work. One task, one disposable-DB lifecycle; no mutation of ppiq_app/ppiq_presentation as fixtures. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM24 | =IF(ISNUMBER(J24),1,0) | =IF(AND(ISNUMBER(J24),OR(AR24="INHERITED ESTIMATE",AR24="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS24 |  | =IF(AM24=1,J24,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT24 |  | =IF(AND(AM24=1,ISNUMBER(R24)),R24,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T25 | Worker-1 local P1 sequence is T-251 → T-259 → T-252. T-256 starts only when BOTH T-252 and Worker-2 T-253 are CLOSED GREEN. If T-252 finishes first and T-253 is still open, STOP and return to CENTRAL for a disjoint Worker-1 lane; do not start T-256 partially and do not duplicate the projection-target predicate. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | Y25 |  | 36de9370 | T-262 terminal closure identifies its parent as T-256; preserve short evidence only. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AM25 | =IF(ISNUMBER(J25),1,0) | =IF(AND(ISNUMBER(J25),OR(AR25="INHERITED ESTIMATE",AR25="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AP25 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Inherited accepted Done state retained. T-262's terminal summary identifies parent36de9370 as T-256. This corroborates a commit anchor, not a rerun of T-256 gates. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | Separate short ancestry corroboration from full task runtime proof. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AS25 |  | =IF(AM25=1,J25,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT25 |  | =IF(AND(AM25=1,ISNUMBER(R25)),R25,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T26 | Worker-1 P1 sequence is now T-251 → T-259 → T-252 → T-256. Start only after T-251 closes; contract-only bounded task. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM26 | =IF(ISNUMBER(J26),1,0) | =IF(AND(ISNUMBER(J26),OR(AR26="INHERITED ESTIMATE",AR26="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS26 |  | =IF(AM26=1,J26,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT26 |  | =IF(AND(AM26=1,ISNUMBER(R26)),R26,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T27 | START NOW as the narrow blocker discovered by T-251. Pause catalogue adjudication; do not hand-classify the current 106/81 fresh-DB queue. Build/fix the canonical acceptance DB first, then resume T-251 on the corrected census. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM27 | =IF(ISNUMBER(J27),1,0) | =IF(AND(ISNUMBER(J27),OR(AR27="INHERITED ESTIMATE",AR27="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS27 |  | =IF(AM27=1,J27,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT27 |  | =IF(AND(AM27=1,ISNUMBER(R27)),R27,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T28 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-057 M1 relationship contract + T-089 + T-090 + T-094. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM28 | =IF(ISNUMBER(J28),1,0) | =IF(AND(ISNUMBER(J28),OR(AR28="INHERITED ESTIMATE",AR28="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS28 |  | =IF(AM28=1,J28,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT28 |  | =IF(AND(AM28=1,ISNUMBER(R28)),R28,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T29 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-095 canonical relationship publication/model complete. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM29 | =IF(ISNUMBER(J29),1,0) | =IF(AND(ISNUMBER(J29),OR(AR29="INHERITED ESTIMATE",AR29="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS29 |  | =IF(AM29=1,J29,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT29 |  | =IF(AND(AM29=1,ISNUMBER(R29)),R29,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T30 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-096 first resolver consumers green. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM30 | =IF(ISNUMBER(J30),1,0) | =IF(AND(ISNUMBER(J30),OR(AR30="INHERITED ESTIMATE",AR30="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS30 |  | =IF(AM30=1,J30,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT30 |  | =IF(AND(AM30=1,ISNUMBER(R30)),R30,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T31 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-060 M1 C6 surface + T-095 + T-096 + T-097. | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-060 M1 C6 surface + T-095 + T-096 + T-097. | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM31 | =IF(ISNUMBER(J31),1,0) | =IF(AND(ISNUMBER(J31),OR(AR31="INHERITED ESTIMATE",AR31="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS31 |  | =IF(AM31=1,J31,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT31 |  | =IF(AND(AM31=1,ISNUMBER(R31)),R31,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T32 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-087 canonical staging schema + T-089/T-090 definition_versions authority. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM32 | =IF(ISNUMBER(J32),1,0) | =IF(AND(ISNUMBER(J32),OR(AR32="INHERITED ESTIMATE",AR32="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AO32 | CLOSED GREEN / COMMITTED — owner-reported | CLOSED GREEN / COMMITTED — FINAL TRANSCRIPT CORROBORATED | No reopening and no release-wide claim. | Pasted text(20260914-134548).txt ¦ lines430-450; final gatesQ/R; COMMITca02b40ea1b69050a45cb35a3e1d64f15b1f66af; PARENT86e1b677212195f191697ecdca7e9441b3dbde33; live49/49, catalogue5/5, owned19/19; not release-wideGREEN.
Backlog | AP32 | Owner-provided final runner report in this conversation, received 14-Sep-2026; not independently rerun or verified against a live Git checkout here. Live acceptance 49/49; catalogue 5/5; owned contract 19/19; cleanup 6/6, survivors 0. Gate O: 900 = 899 passed + 1 exact inherited DefinitionKind RED; 900 unique testId and executionId. Exact staging/byte boundary passed; cleanup before one semantic commit. Task closure GREEN, not release-wide GREEN; canonical replay limitations remain separately tracked. | Final executed terminal transcript corroborates the owner-reported closure: 49/49 live,5/5 catalogue,19/19 owned;6/6 disposable DBs dropped;0survivors. GateO900=899passed+1exact inheritedDefinitionKindRED. Exact staging and one semantic commit proven. No live rerun performed in this review; no release-wideGREEN. Pasted text(20260914-134548).txt ¦ lines430-450; final gatesQ/R; COMMITca02b40ea1b69050a45cb35a3e1d64f15b1f66af; PARENT86e1b677212195f191697ecdca7e9441b3dbde33; live49/49, catalogue5/5, owned19/19; not release-wideGREEN. | Upgrade attribution from owner summary only to an available executed transcript; preserve SHA,parent,status and caveat. | Pasted text(20260914-134548).txt ¦ lines430-450; final gatesQ/R; COMMITca02b40ea1b69050a45cb35a3e1d64f15b1f66af; PARENT86e1b677212195f191697ecdca7e9441b3dbde33; live49/49, catalogue5/5, owned19/19; not release-wideGREEN.
Backlog | AS32 |  | =IF(AM32=1,J32,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT32 |  | =IF(AND(AM32=1,ISNUMBER(R32)),R32,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T33 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-099 canonical quarantine table/API and first eight PV classes. | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-099 canonical quarantine table/API and first eight PV classes. | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM33 | =IF(ISNUMBER(J33),1,0) | =IF(AND(ISNUMBER(J33),OR(AR33="INHERITED ESTIMATE",AR33="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS33 |  | =IF(AM33=1,J33,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT33 |  | =IF(AND(AM33=1,ISNUMBER(R33)),R33,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T34 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-061 final M1 API/page contract + T-099 + T-100 canonical quarantine impleme... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-061 final M1 API/page contract + T-099 + T-100 canonical quarantine impleme... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AJ34 | Inherited estimate; scope changed — re-estimation required v2.22.1 acceptance/ownership clarification; owner to review planning impact. | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM34 | =IF(ISNUMBER(J34),1,0) | =IF(AND(ISNUMBER(J34),OR(AR34="INHERITED ESTIMATE",AR34="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR34 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ34 vs AR34
Backlog | AS34 |  | =IF(AM34=1,J34,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT34 |  | =IF(AND(AM34=1,ISNUMBER(R34)),R34,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T35 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-087 canonical plant schema + T-095 relationship/material identity authority. | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 canonical plant schema + T-095 relationship/material identity authority. | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM35 | =IF(ISNUMBER(J35),1,0) | =IF(AND(ISNUMBER(J35),OR(AR35="INHERITED ESTIMATE",AR35="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS35 |  | =IF(AM35=1,J35,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT35 |  | =IF(AND(AM35=1,ISNUMBER(R35)),R35,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T36 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-095 + T-102 canonical relationship/identity authority. | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095 + T-102 canonical relationship/identity authority. | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AJ36 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM36 | =IF(ISNUMBER(J36),1,0) | =IF(AND(ISNUMBER(J36),OR(AR36="INHERITED ESTIMATE",AR36="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR36 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ36 vs AR36
Backlog | AS36 |  | =IF(AM36=1,J36,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT36 |  | =IF(AND(AM36=1,ISNUMBER(R36)),R36,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T37 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-090 canonical versioned mapping definitions + T-095 relationship authority ... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-090 canonical versioned mapping definitions + T-095 relationship authority ... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AJ37 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM37 | =IF(ISNUMBER(J37),1,0) | =IF(AND(ISNUMBER(J37),OR(AR37="INHERITED ESTIMATE",AR37="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR37 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ37 vs AR37
Backlog | AS37 |  | =IF(AM37=1,J37,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT37 |  | =IF(AND(AM37=1,ISNUMBER(R37)),R37,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | Y38 |  | 8b3eb5c89352a2779d87f9205700f19e7c9b3e25; a5451dbaf6b55183fe65e2c626c49fdef85bd986 | Exact full commits recovered from the final corrective transcript. | Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review.
Backlog | AI38 |  | Original corrective run returned GREEN with22 corrective,26 foundation,84 target-regression and15 architecture tests in24 owned paths;CENTRAL freeze after review. Later v2.22 schedule/cancel/freshness/outcome-truth scope is not closed by a10Sep run. Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review. | Keep capability evidence consistent with the recovered final output. | Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review.
Backlog | AM38 | =IF(ISNUMBER(J38),1,0) | =IF(AND(ISNUMBER(J38),OR(AR38="INHERITED ESTIMATE",AR38="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AO38 | In progress — closure not recorded | BASELINE COMMITS PROVEN; CURRENT WIDENED ACCEPTANCE OPEN | Separate historical producer evidence from current outstanding scope. | Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
Backlog | AP38 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Original corrective run returned GREEN with22 corrective,26 foundation,84 target-regression and15 architecture tests in24 owned paths;CENTRAL freeze after review. Later v2.22 schedule/cancel/freshness/outcome-truth scope is not closed by a10Sep run. Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review. | Do not lose a real committed baseline or promote it to closure of later scope. | Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review.
Backlog | AS38 |  | =IF(AM38=1,J38,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT38 |  | =IF(AND(AM38=1,ISNUMBER(R38)),R38,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T39 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-106 canonical job contract + T-095..T-105 canonical data/relationship path;... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 canonical job contract + T-095..T-105 canonical data/relationship path;... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM39 | =IF(ISNUMBER(J39),1,0) | =IF(AND(ISNUMBER(J39),OR(AR39="INHERITED ESTIMATE",AR39="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS39 |  | =IF(AM39=1,J39,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT39 |  | =IF(AND(AM39=1,ISNUMBER(R39)),R39,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM40 | =IF(ISNUMBER(J40),1,0) | =IF(AND(ISNUMBER(J40),OR(AR40="INHERITED ESTIMATE",AR40="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS40 |  | =IF(AM40=1,J40,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT40 |  | =IF(AND(AM40=1,ISNUMBER(R40)),R40,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T41 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-095..T-105; T-108 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-095..T-105; T-108 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM41 | =IF(ISNUMBER(J41),1,0) | =IF(AND(ISNUMBER(J41),OR(AR41="INHERITED ESTIMATE",AR41="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS41 |  | =IF(AM41=1,J41,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT41 |  | =IF(AND(AM41=1,ISNUMBER(R41)),R41,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T42 | T-201. Does not implement production OPC; truth-corrects the current connector contract only. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM42 | =IF(ISNUMBER(J42),1,0) | =IF(AND(ISNUMBER(J42),OR(AR42="INHERITED ESTIMATE",AR42="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS42 |  | =IF(AM42=1,J42,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT42 |  | =IF(AND(AM42=1,ISNUMBER(R42)),R42,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM43 | =IF(ISNUMBER(J43),1,0) | =IF(AND(ISNUMBER(J43),OR(AR43="INHERITED ESTIMATE",AR43="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS43 |  | =IF(AM43=1,J43,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT43 |  | =IF(AND(AM43=1,ISNUMBER(R43)),R43,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T44 | External gate: customer data structure received (expected 2-Sep-2026) + T-201/T-206 green. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM44 | =IF(ISNUMBER(J44),1,0) | =IF(AND(ISNUMBER(J44),OR(AR44="INHERITED ESTIMATE",AR44="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS44 |  | =IF(AM44=1,J44,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT44 |  | =IF(AND(AM44=1,ISNUMBER(R44)),R44,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM45 | =IF(ISNUMBER(J45),1,0) | =IF(AND(ISNUMBER(J45),OR(AR45="INHERITED ESTIMATE",AR45="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS45 |  | =IF(AM45=1,J45,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT45 |  | =IF(AND(AM45=1,ISNUMBER(R45)),R45,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM46 | =IF(ISNUMBER(J46),1,0) | =IF(AND(ISNUMBER(J46),OR(AR46="INHERITED ESTIMATE",AR46="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS46 |  | =IF(AM46=1,J46,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT46 |  | =IF(AND(AM46=1,ISNUMBER(R46)),R46,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM47 | =IF(ISNUMBER(J47),1,0) | =IF(AND(ISNUMBER(J47),OR(AR47="INHERITED ESTIMATE",AR47="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS47 |  | =IF(AM47=1,J47,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT47 |  | =IF(AND(AM47=1,ISNUMBER(R47)),R47,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM48 | =IF(ISNUMBER(J48),1,0) | =IF(AND(ISNUMBER(J48),OR(AR48="INHERITED ESTIMATE",AR48="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS48 |  | =IF(AM48=1,J48,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT48 |  | =IF(AND(AM48=1,ISNUMBER(R48)),R48,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM49 | =IF(ISNUMBER(J49),1,0) | =IF(AND(ISNUMBER(J49),OR(AR49="INHERITED ESTIMATE",AR49="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS49 |  | =IF(AM49=1,J49,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT49 |  | =IF(AND(AM49=1,ISNUMBER(R49)),R49,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ50 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM50 | =IF(ISNUMBER(J50),1,0) | =IF(AND(ISNUMBER(J50),OR(AR50="INHERITED ESTIMATE",AR50="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR50 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ50 vs AR50
Backlog | AS50 |  | =IF(AM50=1,J50,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT50 |  | =IF(AND(AM50=1,ISNUMBER(R50)),R50,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T51 | CLOSED — Release-1 Canvas prerequisite. Preserve evidence; do not reopen absent contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM51 | =IF(ISNUMBER(J51),1,0) | =IF(AND(ISNUMBER(J51),OR(AR51="INHERITED ESTIMATE",AR51="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS51 |  | =IF(AM51=1,J51,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT51 |  | =IF(AND(AM51=1,ISNUMBER(R51)),R51,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T52 | Release 1 MUST — execute after T-241 and T-210; must close before T-243/T-247. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM52 | =IF(ISNUMBER(J52),1,0) | =IF(AND(ISNUMBER(J52),OR(AR52="INHERITED ESTIMATE",AR52="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS52 |  | =IF(AM52=1,J52,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT52 |  | =IF(AND(AM52=1,ISNUMBER(R52)),R52,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | Y53 |  | 6f65bba1 | Replace missing/incorrect commit evidence with retrieved source; short hashes remain short. | Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
Backlog | AI53 |  | Executed ancestry proves the original board/history/reopen closure. Later v2.22 transactional relationship publication remains a separate outstanding acceptance slice. Do not reimplement the saved-board baseline. Exact full SHA/date not recovered. Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors. | Capability/task evidence must not continue saying the source is only present. | Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
Backlog | AJ53 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM53 | =IF(ISNUMBER(J53),1,0) | =IF(AND(ISNUMBER(J53),OR(AR53="INHERITED ESTIMATE",AR53="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AO53 | In progress — closure not recorded | BASELINE CLOSED; RELATIONSHIP-PUBLICATION EXTENSION UNPROVEN | Separate historical producer evidence from current outstanding scope. | Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
Backlog | AP53 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Executed ancestry proves the original board/history/reopen closure. Later v2.22 transactional relationship publication remains a separate outstanding acceptance slice. Do not reimplement the saved-board baseline. Exact full SHA/date not recovered. Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors. | State exactly what the retrieved evidence proves and does not prove. | Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
Backlog | AR53 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ53 vs AR53
Backlog | AS53 |  | =IF(AM53=1,J53,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT53 |  | =IF(AND(AM53=1,ISNUMBER(R53)),R53,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T54 | CLOSED — Release-1 Canvas prerequisite. Preserve evidence; do not reopen absent contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM54 | =IF(ISNUMBER(J54),1,0) | =IF(AND(ISNUMBER(J54),OR(AR54="INHERITED ESTIMATE",AR54="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS54 |  | =IF(AM54=1,J54,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT54 |  | =IF(AND(AM54=1,ISNUMBER(R54)),R54,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM55 | =IF(ISNUMBER(J55),1,0) | =IF(AND(ISNUMBER(J55),OR(AR55="INHERITED ESTIMATE",AR55="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AO55 | Not started — no completion claimed | PREFLIGHT EXECUTED; IMPLEMENTATION NOT STARTED / BLOCKED | Read-only T-245 preflight is not implementation or closure. | Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors.
Backlog | AS55 |  | =IF(AM55=1,J55,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT55 |  | =IF(AND(AM55=1,ISNUMBER(R55)),R55,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM56 | =IF(ISNUMBER(J56),1,0) | =IF(AND(ISNUMBER(J56),OR(AR56="INHERITED ESTIMATE",AR56="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS56 |  | =IF(AM56=1,J56,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT56 |  | =IF(AND(AM56=1,ISNUMBER(R56)),R56,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T57 | CURRENT / IN PROGRESS. Measured current main HEAD is `aa57a503` (T-242) and there is zero T-243 product-source work. T-243 is therefore reset to Not Started and will begin fresh after T-253. Before authoring, run `git merge-base --is-ancestor 4d32c6b10b4605aeb6e0705ad03537d563125652 HEAD`; continue only on exit 0. Unrelated Documentation/audit dirt may remain unstaged, but all T-253 owned product paths must be clean and the commit must stage only owned paths. Rename the untracked task-number preflight script to a semantic filename before any commit. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM57 | =IF(ISNUMBER(J57),1,0) | =IF(AND(ISNUMBER(J57),OR(AR57="INHERITED ESTIMATE",AR57="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS57 |  | =IF(AM57=1,J57,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT57 |  | =IF(AND(AM57=1,ISNUMBER(R57)),R57,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | K58 | Not Started | In Progress | Original delivery is closed; current widened task is partially delivered, not wholly Not Started. No claim that the new extension has started. | Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
Backlog | T58 | Start after T-253/T-243 checkpoint or while waiting for T-106, on disjoint DB-configuration/website truth files. | Original UI/website convergence is frozen at f8a35725. Only the v2.22 backend-provider-authority delta is outstanding. Consume T-207 and existing contracts on disjoint paths; column M remains the completion-prerequisite list. This is not permission to redo the closed UI/website scope. | Historical start instruction ignored an already-closed producer. | Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
Backlog | Y58 |  | f8a35725c9b0d7fb5a0515c0103a72807a704a97 | Replace missing/incorrect commit evidence with retrieved source; short hashes remain short. | Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
Backlog | AC58 | L1.4 |  | L1.4 is already the primary capability; remove duplicate self-secondary counting. | Backlog!AA58=L1.4 and AC58=L1.4
Backlog | AI58 |  | Original customer-facing connector convergence closed in 5 paths. Website typecheck not independently re-claimed in handover, not RED. v2.22 backend-provider-list extension has no new completion evidence; certify that delta only. Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension. | Capability/task evidence must not continue saying the source is only present. | Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
Backlog | AJ58 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM58 | =IF(ISNUMBER(J58),1,0) | =IF(AND(ISNUMBER(J58),OR(AR58="INHERITED ESTIMATE",AR58="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AO58 | Not started — no completion claimed | BASELINE CLOSED GREEN / FROZEN; LATER BACKEND EXTENSION UNPROVEN | Separate historical producer evidence from current outstanding scope. | Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
Backlog | AP58 | Inherited v2.22.0 intended record; no new runtime certification in this repair. | Original customer-facing connector convergence closed in 5 paths. Website typecheck not independently re-claimed in handover, not RED. v2.22 backend-provider-list extension has no new completion evidence; certify that delta only. Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension. | State exactly what the retrieved evidence proves and does not prove. | Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension.
Backlog | AR58 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ58 vs AR58
Backlog | AS58 |  | =IF(AM58=1,J58,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT58 |  | =IF(AND(AM58=1,ISNUMBER(R58)),R58,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM59 | =IF(ISNUMBER(J59),1,0) | =IF(AND(ISNUMBER(J59),OR(AR59="INHERITED ESTIMATE",AR59="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS59 |  | =IF(AM59=1,J59,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT59 |  | =IF(AND(AM59=1,ISNUMBER(R59)),R59,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | Y60 |  | 86e1b677212195f191697ecdca7e9441b3dbde33 | Replace missing/incorrect commit evidence with retrieved source; short hashes remain short. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AI60 | Source present / unclosed. Exact accepted closure commit and runtime acceptance are not supplied; existing implementation must not be recreated merely because closure is unverified. | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | Capability/task evidence must not continue saying the source is only present. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AM60 | =IF(ISNUMBER(J60),1,0) | =IF(AND(ISNUMBER(J60),OR(AR60="INHERITED ESTIMATE",AR60="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AO60 | SOURCE PRESENT / UNCLOSED — closure unverified | COMMITTED CONTRACT GREEN; CURRENT INTEGRATION ACCEPTANCE UNVERIFIED | Separate historical producer evidence from current outstanding scope. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AP60 | 14-Sep source export and current review establish source presence. No accepted closure SHA/run supplied; not counted Done. | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | State exactly what the retrieved evidence proves and does not prove. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AQ60 |  | 36de9370 | Record the recovered short parent without fabricating its suffix. | Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted.
Backlog | AS60 |  | =IF(AM60=1,J60,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT60 |  | =IF(AND(AM60=1,ISNUMBER(R60)),R60,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM61 | =IF(ISNUMBER(J61),1,0) | =IF(AND(ISNUMBER(J61),OR(AR61="INHERITED ESTIMATE",AR61="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS61 |  | =IF(AM61=1,J61,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT61 |  | =IF(AND(AM61=1,ISNUMBER(R61)),R61,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM62 | =IF(ISNUMBER(J62),1,0) | =IF(AND(ISNUMBER(J62),OR(AR62="INHERITED ESTIMATE",AR62="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS62 |  | =IF(AM62=1,J62,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT62 |  | =IF(AND(AM62=1,ISNUMBER(R62)),R62,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM63 | =IF(ISNUMBER(J63),1,0) | =IF(AND(ISNUMBER(J63),OR(AR63="INHERITED ESTIMATE",AR63="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS63 |  | =IF(AM63=1,J63,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT63 |  | =IF(AND(AM63=1,ISNUMBER(R63)),R63,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM64 | =IF(ISNUMBER(J64),1,0) | =IF(AND(ISNUMBER(J64),OR(AR64="INHERITED ESTIMATE",AR64="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS64 |  | =IF(AM64=1,J64,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT64 |  | =IF(AND(AM64=1,ISNUMBER(R64)),R64,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T65 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM65 | =IF(ISNUMBER(J65),1,0) | =IF(AND(ISNUMBER(J65),OR(AR65="INHERITED ESTIMATE",AR65="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS65 |  | =IF(AM65=1,J65,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT65 |  | =IF(AND(AM65=1,ISNUMBER(R65)),R65,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T66 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM66 | =IF(ISNUMBER(J66),1,0) | =IF(AND(ISNUMBER(J66),OR(AR66="INHERITED ESTIMATE",AR66="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS66 |  | =IF(AM66=1,J66,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT66 |  | =IF(AND(AM66=1,ISNUMBER(R66)),R66,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T67 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM67 | =IF(ISNUMBER(J67),1,0) | =IF(AND(ISNUMBER(J67),OR(AR67="INHERITED ESTIMATE",AR67="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS67 |  | =IF(AM67=1,J67,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT67 |  | =IF(AND(AM67=1,ISNUMBER(R67)),R67,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T68 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM68 | =IF(ISNUMBER(J68),1,0) | =IF(AND(ISNUMBER(J68),OR(AR68="INHERITED ESTIMATE",AR68="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS68 |  | =IF(AM68=1,J68,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT68 |  | =IF(AND(AM68=1,ISNUMBER(R68)),R68,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T69 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM69 | =IF(ISNUMBER(J69),1,0) | =IF(AND(ISNUMBER(J69),OR(AR69="INHERITED ESTIMATE",AR69="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS69 |  | =IF(AM69=1,J69,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT69 |  | =IF(AND(AM69=1,ISNUMBER(R69)),R69,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T70 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM70 | =IF(ISNUMBER(J70),1,0) | =IF(AND(ISNUMBER(J70),OR(AR70="INHERITED ESTIMATE",AR70="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS70 |  | =IF(AM70=1,J70,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT70 |  | =IF(AND(AM70=1,ISNUMBER(R70)),R70,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T71 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM71 | =IF(ISNUMBER(J71),1,0) | =IF(AND(ISNUMBER(J71),OR(AR71="INHERITED ESTIMATE",AR71="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS71 |  | =IF(AM71=1,J71,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT71 |  | =IF(AND(AM71=1,ISNUMBER(R71)),R71,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T72 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM72 | =IF(ISNUMBER(J72),1,0) | =IF(AND(ISNUMBER(J72),OR(AR72="INHERITED ESTIMATE",AR72="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS72 |  | =IF(AM72=1,J72,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT72 |  | =IF(AND(AM72=1,ISNUMBER(R72)),R72,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T73 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM73 | =IF(ISNUMBER(J73),1,0) | =IF(AND(ISNUMBER(J73),OR(AR73="INHERITED ESTIMATE",AR73="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS73 |  | =IF(AM73=1,J73,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT73 |  | =IF(AND(AM73=1,ISNUMBER(R73)),R73,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T74 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM74 | =IF(ISNUMBER(J74),1,0) | =IF(AND(ISNUMBER(J74),OR(AR74="INHERITED ESTIMATE",AR74="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS74 |  | =IF(AM74=1,J74,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT74 |  | =IF(AND(AM74=1,ISNUMBER(R74)),R74,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T75 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM75 | =IF(ISNUMBER(J75),1,0) | =IF(AND(ISNUMBER(J75),OR(AR75="INHERITED ESTIMATE",AR75="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS75 |  | =IF(AM75=1,J75,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT75 |  | =IF(AND(AM75=1,ISNUMBER(R75)),R75,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T76 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM76 | =IF(ISNUMBER(J76),1,0) | =IF(AND(ISNUMBER(J76),OR(AR76="INHERITED ESTIMATE",AR76="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS76 |  | =IF(AM76=1,J76,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT76 |  | =IF(AND(AM76=1,ISNUMBER(R76)),R76,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T77 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM77 | =IF(ISNUMBER(J77),1,0) | =IF(AND(ISNUMBER(J77),OR(AR77="INHERITED ESTIMATE",AR77="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS77 |  | =IF(AM77=1,J77,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT77 |  | =IF(AND(AM77=1,ISNUMBER(R77)),R77,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T78 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM78 | =IF(ISNUMBER(J78),1,0) | =IF(AND(ISNUMBER(J78),OR(AR78="INHERITED ESTIMATE",AR78="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS78 |  | =IF(AM78=1,J78,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT78 |  | =IF(AND(AM78=1,ISNUMBER(R78)),R78,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T79 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM79 | =IF(ISNUMBER(J79),1,0) | =IF(AND(ISNUMBER(J79),OR(AR79="INHERITED ESTIMATE",AR79="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS79 |  | =IF(AM79=1,J79,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT79 |  | =IF(AND(AM79=1,ISNUMBER(R79)),R79,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T80 | Closed — do not reopen without contradictory regression evidence. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM80 | =IF(ISNUMBER(J80),1,0) | =IF(AND(ISNUMBER(J80),OR(AR80="INHERITED ESTIMATE",AR80="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS80 |  | =IF(AM80=1,J80,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT80 |  | =IF(AND(AM80=1,ISNUMBER(R80)),R80,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM81 | =IF(ISNUMBER(J81),1,0) | =IF(AND(ISNUMBER(J81),OR(AR81="INHERITED ESTIMATE",AR81="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS81 |  | =IF(AM81=1,J81,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT81 |  | =IF(AND(AM81=1,ISNUMBER(R81)),R81,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM82 | =IF(ISNUMBER(J82),1,0) | =IF(AND(ISNUMBER(J82),OR(AR82="INHERITED ESTIMATE",AR82="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS82 |  | =IF(AM82=1,J82,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT82 |  | =IF(AND(AM82=1,ISNUMBER(R82)),R82,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T83 | T-208 fixture + T-216 frozen contract. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM83 | =IF(ISNUMBER(J83),1,0) | =IF(AND(ISNUMBER(J83),OR(AR83="INHERITED ESTIMATE",AR83="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS83 |  | =IF(AM83=1,J83,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT83 |  | =IF(AND(AM83=1,ISNUMBER(R83)),R83,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T84 | T-090 semantic definitions + T-208 fixture. Persistence waits for T-112/T-114; pure kernel may start earlier. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM84 | =IF(ISNUMBER(J84),1,0) | =IF(AND(ISNUMBER(J84),OR(AR84="INHERITED ESTIMATE",AR84="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS84 |  | =IF(AM84=1,J84,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT84 |  | =IF(AND(AM84=1,ISNUMBER(R84)),R84,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T85 | T-217 + T-218 + T-236. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM85 | =IF(ISNUMBER(J85),1,0) | =IF(AND(ISNUMBER(J85),OR(AR85="INHERITED ESTIMATE",AR85="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS85 |  | =IF(AM85=1,J85,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT85 |  | =IF(AND(AM85=1,ISNUMBER(R85)),R85,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T86 | T-219 + existing claim-class rules. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM86 | =IF(ISNUMBER(J86),1,0) | =IF(AND(ISNUMBER(J86),OR(AR86="INHERITED ESTIMATE",AR86="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS86 |  | =IF(AM86=1,J86,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT86 |  | =IF(AND(AM86=1,ISNUMBER(R86)),R86,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM87 | =IF(ISNUMBER(J87),1,0) | =IF(AND(ISNUMBER(J87),OR(AR87="INHERITED ESTIMATE",AR87="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS87 |  | =IF(AM87=1,J87,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT87 |  | =IF(AND(AM87=1,ISNUMBER(R87)),R87,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM88 | =IF(ISNUMBER(J88),1,0) | =IF(AND(ISNUMBER(J88),OR(AR88="INHERITED ESTIMATE",AR88="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS88 |  | =IF(AM88=1,J88,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT88 |  | =IF(AND(AM88=1,ISNUMBER(R88)),R88,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T89 | T-208 + T-209; may run in parallel with W1 canonical chain. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM89 | =IF(ISNUMBER(J89),1,0) | =IF(AND(ISNUMBER(J89),OR(AR89="INHERITED ESTIMATE",AR89="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS89 |  | =IF(AM89=1,J89,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT89 |  | =IF(AND(AM89=1,ISNUMBER(R89)),R89,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T90 | T-217 + T-234; may run while W1 canonical chain proceeds. | CLOSED BASELINE — no new start gate and no re-execution implied. Preserve accepted closure and clean owned scope; reopen only on a concrete, separately recorded regression. Downstream consumes the frozen contract. | A closed task must not show a current instruction to wait for historical Presentation RC. | Current accepted Backlog status; existing no-reopen governance.
Backlog | AM90 | =IF(ISNUMBER(J90),1,0) | =IF(AND(ISNUMBER(J90),OR(AR90="INHERITED ESTIMATE",AR90="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS90 |  | =IF(AM90=1,J90,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT90 |  | =IF(AND(AM90=1,ISNUMBER(R90)),R90,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM91 | =IF(ISNUMBER(J91),1,0) | =IF(AND(ISNUMBER(J91),OR(AR91="INHERITED ESTIMATE",AR91="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS91 |  | =IF(AM91=1,J91,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT91 |  | =IF(AND(AM91=1,ISNUMBER(R91)),R91,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T92 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-087/T-088 canonical migration authority available; establish FORCE RLS guar... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087/T-088 canonical migration authority available; establish FORCE RLS guar... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM92 | =IF(ISNUMBER(J92),1,0) | =IF(AND(ISNUMBER(J92),OR(AR92="INHERITED ESTIMATE",AR92="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS92 |  | =IF(AM92=1,J92,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT92 |  | =IF(AND(AM92=1,ISNUMBER(R92)),R92,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T93 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AJ93 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM93 | =IF(ISNUMBER(J93),1,0) | =IF(AND(ISNUMBER(J93),OR(AR93="INHERITED ESTIMATE",AR93="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR93 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ93 vs AR93
Backlog | AS93 |  | =IF(AM93=1,J93,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT93 |  | =IF(AND(AM93=1,ISNUMBER(R93)),R93,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T94 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-087 + T-089/T-090 + T-095/T-099 canonical Release 1 tables available; establish t... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-089/T-090 + T-095/T-099 canonical Release 1 tables available; establish t... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM94 | =IF(ISNUMBER(J94),1,0) | =IF(AND(ISNUMBER(J94),OR(AR94="INHERITED ESTIMATE",AR94="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS94 |  | =IF(AM94=1,J94,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT94 |  | =IF(AND(AM94=1,ISNUMBER(R94)),R94,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T95 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM95 | =IF(ISNUMBER(J95),1,0) | =IF(AND(ISNUMBER(J95),OR(AR95="INHERITED ESTIMATE",AR95="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS95 |  | =IF(AM95=1,J95,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT95 |  | =IF(AND(AM95=1,ISNUMBER(R95)),R95,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T96 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM96 | =IF(ISNUMBER(J96),1,0) | =IF(AND(ISNUMBER(J96),OR(AR96="INHERITED ESTIMATE",AR96="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS96 |  | =IF(AM96=1,J96,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT96 |  | =IF(AND(AM96=1,ISNUMBER(R96)),R96,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T97 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM97 | =IF(ISNUMBER(J97),1,0) | =IF(AND(ISNUMBER(J97),OR(AR97="INHERITED ESTIMATE",AR97="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS97 |  | =IF(AM97=1,J97,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT97 |  | =IF(AND(AM97=1,ISNUMBER(R97)),R97,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T98 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-119 role catalogue/enforcement + licence authority. | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 role catalogue/enforcement + licence authority. | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AJ98 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM98 | =IF(ISNUMBER(J98),1,0) | =IF(AND(ISNUMBER(J98),OR(AR98="INHERITED ESTIMATE",AR98="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR98 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ98 vs AR98
Backlog | AS98 |  | =IF(AM98=1,J98,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT98 |  | =IF(AND(AM98=1,ISNUMBER(R98)),R98,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T99 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AJ99 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM99 | =IF(ISNUMBER(J99),1,0) | =IF(AND(ISNUMBER(J99),OR(AR99="INHERITED ESTIMATE",AR99="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR99 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ99 vs AR99
Backlog | AS99 |  | =IF(AM99=1,J99,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT99 |  | =IF(AND(AM99=1,ISNUMBER(R99)),R99,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T100 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM100 | =IF(ISNUMBER(J100),1,0) | =IF(AND(ISNUMBER(J100),OR(AR100="INHERITED ESTIMATE",AR100="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS100 |  | =IF(AM100=1,J100,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT100 |  | =IF(AND(AM100=1,ISNUMBER(R100)),R100,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T101 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM101 | =IF(ISNUMBER(J101),1,0) | =IF(AND(ISNUMBER(J101),OR(AR101="INHERITED ESTIMATE",AR101="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS101 |  | =IF(AM101=1,J101,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT101 |  | =IF(AND(AM101=1,ISNUMBER(R101)),R101,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T102 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM102 | =IF(ISNUMBER(J102),1,0) | =IF(AND(ISNUMBER(J102),OR(AR102="INHERITED ESTIMATE",AR102="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS102 |  | =IF(AM102=1,J102,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT102 |  | =IF(AND(AM102=1,ISNUMBER(R102)),R102,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T103 | T-192 + T-148 exact route/shell inventory + T-194 API-alias retirement + all ... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-192 + T-148 exact route/shell inventory + T-194 API-alias retirement + all ... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM103 | =IF(ISNUMBER(J103),1,0) | =IF(AND(ISNUMBER(J103),OR(AR103="INHERITED ESTIMATE",AR103="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS103 |  | =IF(AM103=1,J103,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT103 |  | =IF(AND(AM103=1,ISNUMBER(R103)),R103,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM104 | =IF(ISNUMBER(J104),1,0) | =IF(AND(ISNUMBER(J104),OR(AR104="INHERITED ESTIMATE",AR104="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS104 |  | =IF(AM104=1,J104,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT104 |  | =IF(AND(AM104=1,ISNUMBER(R104)),R104,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM105 | =IF(ISNUMBER(J105),1,0) | =IF(AND(ISNUMBER(J105),OR(AR105="INHERITED ESTIMATE",AR105="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS105 |  | =IF(AM105=1,J105,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT105 |  | =IF(AND(AM105=1,ISNUMBER(R105)),R105,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM106 | =IF(ISNUMBER(J106),1,0) | =IF(AND(ISNUMBER(J106),OR(AR106="INHERITED ESTIMATE",AR106="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS106 |  | =IF(AM106=1,J106,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT106 |  | =IF(AND(AM106=1,ISNUMBER(R106)),R106,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ107 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM107 | =IF(ISNUMBER(J107),1,0) | =IF(AND(ISNUMBER(J107),OR(AR107="INHERITED ESTIMATE",AR107="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR107 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ107 vs AR107
Backlog | AS107 |  | =IF(AM107=1,J107,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT107 |  | =IF(AND(AM107=1,ISNUMBER(R107)),R107,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T108 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-106 + T-107 + T-112 + T-113 + T-114 + T-117; T-137/T-168 runtime contracts ... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-106 + T-107 + T-112 + T-113 + T-114 + T-117; T-137/T-168 runtime contracts ... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM108 | =IF(ISNUMBER(J108),1,0) | =IF(AND(ISNUMBER(J108),OR(AR108="INHERITED ESTIMATE",AR108="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS108 |  | =IF(AM108=1,J108,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT108 |  | =IF(AND(AM108=1,ISNUMBER(R108)),R108,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM109 | =IF(ISNUMBER(J109),1,0) | =IF(AND(ISNUMBER(J109),OR(AR109="INHERITED ESTIMATE",AR109="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS109 |  | =IF(AM109=1,J109,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT109 |  | =IF(AND(AM109=1,ISNUMBER(R109)),R109,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM110 | =IF(ISNUMBER(J110),1,0) | =IF(AND(ISNUMBER(J110),OR(AR110="INHERITED ESTIMATE",AR110="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS110 |  | =IF(AM110=1,J110,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT110 |  | =IF(AND(AM110=1,ISNUMBER(R110)),R110,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM111 | =IF(ISNUMBER(J111),1,0) | =IF(AND(ISNUMBER(J111),OR(AR111="INHERITED ESTIMATE",AR111="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS111 |  | =IF(AM111=1,J111,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT111 |  | =IF(AND(AM111=1,ISNUMBER(R111)),R111,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM112 | =IF(ISNUMBER(J112),1,0) | =IF(AND(ISNUMBER(J112),OR(AR112="INHERITED ESTIMATE",AR112="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS112 |  | =IF(AM112=1,J112,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT112 |  | =IF(AND(AM112=1,ISNUMBER(R112)),R112,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ113 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM113 | =IF(ISNUMBER(J113),1,0) | =IF(AND(ISNUMBER(J113),OR(AR113="INHERITED ESTIMATE",AR113="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR113 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ113 vs AR113
Backlog | AS113 |  | =IF(AM113=1,J113,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT113 |  | =IF(AND(AM113=1,ISNUMBER(R113)),R113,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ114 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM114 | =IF(ISNUMBER(J114),1,0) | =IF(AND(ISNUMBER(J114),OR(AR114="INHERITED ESTIMATE",AR114="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR114 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ114 vs AR114
Backlog | AS114 |  | =IF(AM114=1,J114,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT114 |  | =IF(AND(AM114=1,ISNUMBER(R114)),R114,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM115 | =IF(ISNUMBER(J115),1,0) | =IF(AND(ISNUMBER(J115),OR(AR115="INHERITED ESTIMATE",AR115="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS115 |  | =IF(AM115=1,J115,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT115 |  | =IF(AND(AM115=1,ISNUMBER(R115)),R115,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM116 | =IF(ISNUMBER(J116),1,0) | =IF(AND(ISNUMBER(J116),OR(AR116="INHERITED ESTIMATE",AR116="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS116 |  | =IF(AM116=1,J116,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT116 |  | =IF(AND(AM116=1,ISNUMBER(R116)),R116,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T117 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AJ117 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM117 | =IF(ISNUMBER(J117),1,0) | =IF(AND(ISNUMBER(J117),OR(AR117="INHERITED ESTIMATE",AR117="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR117 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ117 vs AR117
Backlog | AS117 |  | =IF(AM117=1,J117,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT117 |  | =IF(AND(AM117=1,ISNUMBER(R117)),R117,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T118 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: Release 1 dependency order | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: Release 1 dependency order | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM118 | =IF(ISNUMBER(J118),1,0) | =IF(AND(ISNUMBER(J118),OR(AR118="INHERITED ESTIMATE",AR118="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS118 |  | =IF(AM118=1,J118,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT118 |  | =IF(AND(AM118=1,ISNUMBER(R118)),R118,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T119 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: All Release 1 canonical-core/user-visible owners complete, including T-196/T-197/T-... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: All Release 1 canonical-core/user-visible owners complete, including T-196/T-197/T-... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM119 | =IF(ISNUMBER(J119),1,0) | =IF(AND(ISNUMBER(J119),OR(AR119="INHERITED ESTIMATE",AR119="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS119 |  | =IF(AM119=1,J119,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT119 |  | =IF(AND(AM119=1,ISNUMBER(R119)),R119,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM120 | =IF(ISNUMBER(J120),1,0) | =IF(AND(ISNUMBER(J120),OR(AR120="INHERITED ESTIMATE",AR120="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS120 |  | =IF(AM120=1,J120,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT120 |  | =IF(AND(AM120=1,ISNUMBER(R120)),R120,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM121 | =IF(ISNUMBER(J121),1,0) | =IF(AND(ISNUMBER(J121),OR(AR121="INHERITED ESTIMATE",AR121="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS121 |  | =IF(AM121=1,J121,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT121 |  | =IF(AND(AM121=1,ISNUMBER(R121)),R121,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM122 | =IF(ISNUMBER(J122),1,0) | =IF(AND(ISNUMBER(J122),OR(AR122="INHERITED ESTIMATE",AR122="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS122 |  | =IF(AM122=1,J122,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT122 |  | =IF(AND(AM122=1,ISNUMBER(R122)),R122,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T123 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-117 + T-127 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-117 + T-127 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM123 | =IF(ISNUMBER(J123),1,0) | =IF(AND(ISNUMBER(J123),OR(AR123="INHERITED ESTIMATE",AR123="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS123 |  | =IF(AM123=1,J123,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT123 |  | =IF(AND(AM123=1,ISNUMBER(R123)),R123,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T124 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-087 + T-094 + T-095 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-087 + T-094 + T-095 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM124 | =IF(ISNUMBER(J124),1,0) | =IF(AND(ISNUMBER(J124),OR(AR124="INHERITED ESTIMATE",AR124="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS124 |  | =IF(AM124=1,J124,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT124 |  | =IF(AND(AM124=1,ISNUMBER(R124)),R124,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T125 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-119 + T-198 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-119 + T-198 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM125 | =IF(ISNUMBER(J125),1,0) | =IF(AND(ISNUMBER(J125),OR(AR125="INHERITED ESTIMATE",AR125="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS125 |  | =IF(AM125=1,J125,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT125 |  | =IF(AND(AM125=1,ISNUMBER(R125)),R125,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T126 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-112 + T-114 + T-119 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-112 + T-114 + T-119 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM126 | =IF(ISNUMBER(J126),1,0) | =IF(AND(ISNUMBER(J126),OR(AR126="INHERITED ESTIMATE",AR126="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS126 |  | =IF(AM126=1,J126,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT126 |  | =IF(AND(AM126=1,ISNUMBER(R126)),R126,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T127 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-124 + T-198 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-124 + T-198 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM127 | =IF(ISNUMBER(J127),1,0) | =IF(AND(ISNUMBER(J127),OR(AR127="INHERITED ESTIMATE",AR127="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS127 |  | =IF(AM127=1,J127,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT127 |  | =IF(AND(AM127=1,ISNUMBER(R127)),R127,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T128 | WAIT for Presentation RC freeze/tag + clean index/worktree. Then: T-113 + T-119 | Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-113 + T-119 | Historical Presentation RC is not a new blocking workstream; preserve explicit producer requirements and clean-tree safety. | Current M2 scope; original T-086 baseline retained; Pasted text(20260910-105308).txt shows ancestry with unrelated non-product dirt retained.
Backlog | AM128 | =IF(ISNUMBER(J128),1,0) | =IF(AND(ISNUMBER(J128),OR(AR128="INHERITED ESTIMATE",AR128="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS128 |  | =IF(AM128=1,J128,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT128 |  | =IF(AND(AM128=1,ISNUMBER(R128)),R128,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM129 | =IF(ISNUMBER(J129),1,0) | =IF(AND(ISNUMBER(J129),OR(AR129="INHERITED ESTIMATE",AR129="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS129 |  | =IF(AM129=1,J129,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT129 |  | =IF(AND(AM129=1,ISNUMBER(R129)),R129,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM130 | =IF(ISNUMBER(J130),1,0) | =IF(AND(ISNUMBER(J130),OR(AR130="INHERITED ESTIMATE",AR130="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS130 |  | =IF(AM130=1,J130,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT130 |  | =IF(AND(AM130=1,ISNUMBER(R130)),R130,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM131 | =IF(ISNUMBER(J131),1,0) | =IF(AND(ISNUMBER(J131),OR(AR131="INHERITED ESTIMATE",AR131="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS131 |  | =IF(AM131=1,J131,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT131 |  | =IF(AND(AM131=1,ISNUMBER(R131)),R131,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM132 | =IF(ISNUMBER(J132),1,0) | =IF(AND(ISNUMBER(J132),OR(AR132="INHERITED ESTIMATE",AR132="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS132 |  | =IF(AM132=1,J132,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT132 |  | =IF(AND(AM132=1,ISNUMBER(R132)),R132,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM133 | =IF(ISNUMBER(J133),1,0) | =IF(AND(ISNUMBER(J133),OR(AR133="INHERITED ESTIMATE",AR133="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS133 |  | =IF(AM133=1,J133,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT133 |  | =IF(AND(AM133=1,ISNUMBER(R133)),R133,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ134 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM134 | =IF(ISNUMBER(J134),1,0) | =IF(AND(ISNUMBER(J134),OR(AR134="INHERITED ESTIMATE",AR134="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR134 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ134 vs AR134
Backlog | AS134 |  | =IF(AM134=1,J134,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT134 |  | =IF(AND(AM134=1,ISNUMBER(R134)),R134,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM135 | =IF(ISNUMBER(J135),1,0) | =IF(AND(ISNUMBER(J135),OR(AR135="INHERITED ESTIMATE",AR135="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS135 |  | =IF(AM135=1,J135,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT135 |  | =IF(AND(AM135=1,ISNUMBER(R135)),R135,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T136 | T-087..T-105 + T-112 + T-114 security/tenant hand-off. Outcome semantics from... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-087..T-105 + T-112 + T-114 security/tenant hand-off. Outcome semantics from... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM136 | =IF(ISNUMBER(J136),1,0) | =IF(AND(ISNUMBER(J136),OR(AR136="INHERITED ESTIMATE",AR136="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS136 |  | =IF(AM136=1,J136,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT136 |  | =IF(AND(AM136=1,ISNUMBER(R136)),R136,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM137 | =IF(ISNUMBER(J137),1,0) | =IF(AND(ISNUMBER(J137),OR(AR137="INHERITED ESTIMATE",AR137="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS137 |  | =IF(AM137=1,J137,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT137 |  | =IF(AND(AM137=1,ISNUMBER(R137)),R137,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM138 | =IF(ISNUMBER(J138),1,0) | =IF(AND(ISNUMBER(J138),OR(AR138="INHERITED ESTIMATE",AR138="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS138 |  | =IF(AM138=1,J138,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT138 |  | =IF(AND(AM138=1,ISNUMBER(R138)),R138,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM139 | =IF(ISNUMBER(J139),1,0) | =IF(AND(ISNUMBER(J139),OR(AR139="INHERITED ESTIMATE",AR139="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS139 |  | =IF(AM139=1,J139,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT139 |  | =IF(AND(AM139=1,ISNUMBER(R139)),R139,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM140 | =IF(ISNUMBER(J140),1,0) | =IF(AND(ISNUMBER(J140),OR(AR140="INHERITED ESTIMATE",AR140="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS140 |  | =IF(AM140=1,J140,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT140 |  | =IF(AND(AM140=1,ISNUMBER(R140)),R140,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM141 | =IF(ISNUMBER(J141),1,0) | =IF(AND(ISNUMBER(J141),OR(AR141="INHERITED ESTIMATE",AR141="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS141 |  | =IF(AM141=1,J141,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT141 |  | =IF(AND(AM141=1,ISNUMBER(R141)),R141,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T142 | T-090 definition authority + T-095/T-096 relationship resolver + available ca... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 definition authority + T-095/T-096 relationship resolver + available ca... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM142 | =IF(ISNUMBER(J142),1,0) | =IF(AND(ISNUMBER(J142),OR(AR142="INHERITED ESTIMATE",AR142="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS142 |  | =IF(AM142=1,J142,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT142 |  | =IF(AND(AM142=1,ISNUMBER(R142)),R142,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T143 | T-112 + T-114 + current Release 2 persistence tables (including T-128/T-129/T-130/T... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-112 + T-114 + current Release 2 persistence tables (including T-128/T-129/T-130/T... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM143 | =IF(ISNUMBER(J143),1,0) | =IF(AND(ISNUMBER(J143),OR(AR143="INHERITED ESTIMATE",AR143="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS143 |  | =IF(AM143=1,J143,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT143 |  | =IF(AND(AM143=1,ISNUMBER(R143)),R143,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM144 | =IF(ISNUMBER(J144),1,0) | =IF(AND(ISNUMBER(J144),OR(AR144="INHERITED ESTIMATE",AR144="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS144 |  | =IF(AM144=1,J144,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT144 |  | =IF(AND(AM144=1,ISNUMBER(R144)),R144,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM145 | =IF(ISNUMBER(J145),1,0) | =IF(AND(ISNUMBER(J145),OR(AR145="INHERITED ESTIMATE",AR145="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS145 |  | =IF(AM145=1,J145,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT145 |  | =IF(AND(AM145=1,ISNUMBER(R145)),R145,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM146 | =IF(ISNUMBER(J146),1,0) | =IF(AND(ISNUMBER(J146),OR(AR146="INHERITED ESTIMATE",AR146="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS146 |  | =IF(AM146=1,J146,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT146 |  | =IF(AND(AM146=1,ISNUMBER(R146)),R146,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM147 | =IF(ISNUMBER(J147),1,0) | =IF(AND(ISNUMBER(J147),OR(AR147="INHERITED ESTIMATE",AR147="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS147 |  | =IF(AM147=1,J147,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT147 |  | =IF(AND(AM147=1,ISNUMBER(R147)),R147,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM148 | =IF(ISNUMBER(J148),1,0) | =IF(AND(ISNUMBER(J148),OR(AR148="INHERITED ESTIMATE",AR148="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS148 |  | =IF(AM148=1,J148,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT148 |  | =IF(AND(AM148=1,ISNUMBER(R148)),R148,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM149 | =IF(ISNUMBER(J149),1,0) | =IF(AND(ISNUMBER(J149),OR(AR149="INHERITED ESTIMATE",AR149="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS149 |  | =IF(AM149=1,J149,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT149 |  | =IF(AND(AM149=1,ISNUMBER(R149)),R149,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM150 | =IF(ISNUMBER(J150),1,0) | =IF(AND(ISNUMBER(J150),OR(AR150="INHERITED ESTIMATE",AR150="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS150 |  | =IF(AM150=1,J150,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT150 |  | =IF(AND(AM150=1,ISNUMBER(R150)),R150,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM151 | =IF(ISNUMBER(J151),1,0) | =IF(AND(ISNUMBER(J151),OR(AR151="INHERITED ESTIMATE",AR151="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS151 |  | =IF(AM151=1,J151,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT151 |  | =IF(AND(AM151=1,ISNUMBER(R151)),R151,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ152 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM152 | =IF(ISNUMBER(J152),1,0) | =IF(AND(ISNUMBER(J152),OR(AR152="INHERITED ESTIMATE",AR152="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR152 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ152 vs AR152
Backlog | AS152 |  | =IF(AM152=1,J152,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT152 |  | =IF(AND(AM152=1,ISNUMBER(R152)),R152,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ153 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM153 | =IF(ISNUMBER(J153),1,0) | =IF(AND(ISNUMBER(J153),OR(AR153="INHERITED ESTIMATE",AR153="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR153 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ153 vs AR153
Backlog | AS153 |  | =IF(AM153=1,J153,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT153 |  | =IF(AND(AM153=1,ISNUMBER(R153)),R153,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T154 | T-090 canonical SM-06 binding + T-128/T-129 + T-177; complete BEFORE T-146 fi... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-090 canonical SM-06 binding + T-128/T-129 + T-177; complete BEFORE T-146 fi... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM154 | =IF(ISNUMBER(J154),1,0) | =IF(AND(ISNUMBER(J154),OR(AR154="INHERITED ESTIMATE",AR154="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS154 |  | =IF(AM154=1,J154,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT154 |  | =IF(AND(AM154=1,ISNUMBER(R154)),R154,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM155 | =IF(ISNUMBER(J155),1,0) | =IF(AND(ISNUMBER(J155),OR(AR155="INHERITED ESTIMATE",AR155="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS155 |  | =IF(AM155=1,J155,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT155 |  | =IF(AND(AM155=1,ISNUMBER(R155)),R155,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM156 | =IF(ISNUMBER(J156),1,0) | =IF(AND(ISNUMBER(J156),OR(AR156="INHERITED ESTIMATE",AR156="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS156 |  | =IF(AM156=1,J156,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT156 |  | =IF(AND(AM156=1,ISNUMBER(R156)),R156,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM157 | =IF(ISNUMBER(J157),1,0) | =IF(AND(ISNUMBER(J157),OR(AR157="INHERITED ESTIMATE",AR157="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS157 |  | =IF(AM157=1,J157,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT157 |  | =IF(AND(AM157=1,ISNUMBER(R157)),R157,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ158 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM158 | =IF(ISNUMBER(J158),1,0) | =IF(AND(ISNUMBER(J158),OR(AR158="INHERITED ESTIMATE",AR158="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR158 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ158 vs AR158
Backlog | AS158 |  | =IF(AM158=1,J158,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT158 |  | =IF(AND(AM158=1,ISNUMBER(R158)),R158,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T159 | T-089..T-105 canonical definition/relationship authority + T-112 + T-114 secu... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-089..T-105 canonical definition/relationship authority + T-112 + T-114 secu... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM159 | =IF(ISNUMBER(J159),1,0) | =IF(AND(ISNUMBER(J159),OR(AR159="INHERITED ESTIMATE",AR159="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS159 |  | =IF(AM159=1,J159,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT159 |  | =IF(AND(AM159=1,ISNUMBER(R159)),R159,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM160 | =IF(ISNUMBER(J160),1,0) | =IF(AND(ISNUMBER(J160),OR(AR160="INHERITED ESTIMATE",AR160="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS160 |  | =IF(AM160=1,J160,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT160 |  | =IF(AND(AM160=1,ISNUMBER(R160)),R160,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T161 | T-170 + T-183 + T-122 final object-storage/container path + T-112/T-114/T-135... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-170 + T-183 + T-122 final object-storage/container path + T-112/T-114/T-135... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AM161 | =IF(ISNUMBER(J161),1,0) | =IF(AND(ISNUMBER(J161),OR(AR161="INHERITED ESTIMATE",AR161="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS161 |  | =IF(AM161=1,J161,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT161 |  | =IF(AND(AM161=1,ISNUMBER(R161)),R161,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | T162 | T-171 + T-183 + T-128/T-129 + T-195 canonical readiness thresholds + T-135 se... | GATE PROSE INCOMPLETE — original text ends with an ellipsis. Do not infer omitted conditions. Column M lists completion prerequisites; AN/Contract Handoffs lists contract-only prerequisites. Full task acceptance in column I still applies. Recover the omitted prose before claiming this gate fully reconciled. Preserved original fragment: T-171 + T-183 + T-128/T-129 + T-195 canonical readiness thresholds + T-135 se... | Do not silently complete truncated engineering requirements. | Literal trailing ellipsis in original Backlog columnT; original preserved.
Backlog | AJ162 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM162 | =IF(ISNUMBER(J162),1,0) | =IF(AND(ISNUMBER(J162),OR(AR162="INHERITED ESTIMATE",AR162="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR162 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ162 vs AR162
Backlog | AS162 |  | =IF(AM162=1,J162,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT162 |  | =IF(AND(AM162=1,ISNUMBER(R162)),R162,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM163 | =IF(ISNUMBER(J163),1,0) | =IF(AND(ISNUMBER(J163),OR(AR163="INHERITED ESTIMATE",AR163="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS163 |  | =IF(AM163=1,J163,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT163 |  | =IF(AND(AM163=1,ISNUMBER(R163)),R163,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM164 | =IF(ISNUMBER(J164),1,0) | =IF(AND(ISNUMBER(J164),OR(AR164="INHERITED ESTIMATE",AR164="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS164 |  | =IF(AM164=1,J164,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT164 |  | =IF(AND(AM164=1,ISNUMBER(R164)),R164,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM165 | =IF(ISNUMBER(J165),1,0) | =IF(AND(ISNUMBER(J165),OR(AR165="INHERITED ESTIMATE",AR165="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS165 |  | =IF(AM165=1,J165,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT165 |  | =IF(AND(AM165=1,ISNUMBER(R165)),R165,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AJ166 | Inherited estimate; scope changed — re-estimation required | RE-ESTIMATE REQUIRED — J/R retain the prior-scope figures for traceability; excluded from usable planning totals. New full-scope and remaining-work estimates are not supplied. | Preserve historical figures without presenting them as current widened-scope estimates. | Current row explicitly records a v2.22 scope change.
Backlog | AM166 | =IF(ISNUMBER(J166),1,0) | =IF(AND(ISNUMBER(J166),OR(AR166="INHERITED ESTIMATE",AR166="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AR166 | INHERITED ESTIMATE | RE-ESTIMATE REQUIRED | AJ already declares changed scope; AR and totals must reflect that. | Backlog!AJ166 vs AR166
Backlog | AS166 |  | =IF(AM166=1,J166,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT166 |  | =IF(AND(AM166=1,ISNUMBER(R166)),R166,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM167 | =IF(ISNUMBER(J167),1,0) | =IF(AND(ISNUMBER(J167),OR(AR167="INHERITED ESTIMATE",AR167="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS167 |  | =IF(AM167=1,J167,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT167 |  | =IF(AND(AM167=1,ISNUMBER(R167)),R167,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM168 | =IF(ISNUMBER(J168),1,0) | =IF(AND(ISNUMBER(J168),OR(AR168="INHERITED ESTIMATE",AR168="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS168 |  | =IF(AM168=1,J168,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT168 |  | =IF(AND(AM168=1,ISNUMBER(R168)),R168,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM169 | =IF(ISNUMBER(J169),1,0) | =IF(AND(ISNUMBER(J169),OR(AR169="INHERITED ESTIMATE",AR169="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS169 |  | =IF(AM169=1,J169,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT169 |  | =IF(AND(AM169=1,ISNUMBER(R169)),R169,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM170 | =IF(ISNUMBER(J170),1,0) | =IF(AND(ISNUMBER(J170),OR(AR170="INHERITED ESTIMATE",AR170="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS170 |  | =IF(AM170=1,J170,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT170 |  | =IF(AND(AM170=1,ISNUMBER(R170)),R170,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM171 | =IF(ISNUMBER(J171),1,0) | =IF(AND(ISNUMBER(J171),OR(AR171="INHERITED ESTIMATE",AR171="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS171 |  | =IF(AM171=1,J171,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT171 |  | =IF(AND(AM171=1,ISNUMBER(R171)),R171,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM172 | =IF(ISNUMBER(J172),1,0) | =IF(AND(ISNUMBER(J172),OR(AR172="INHERITED ESTIMATE",AR172="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS172 |  | =IF(AM172=1,J172,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT172 |  | =IF(AND(AM172=1,ISNUMBER(R172)),R172,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM173 | =IF(ISNUMBER(J173),1,0) | =IF(AND(ISNUMBER(J173),OR(AR173="INHERITED ESTIMATE",AR173="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS173 |  | =IF(AM173=1,J173,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT173 |  | =IF(AND(AM173=1,ISNUMBER(R173)),R173,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM174 | =IF(ISNUMBER(J174),1,0) | =IF(AND(ISNUMBER(J174),OR(AR174="INHERITED ESTIMATE",AR174="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS174 |  | =IF(AM174=1,J174,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT174 |  | =IF(AND(AM174=1,ISNUMBER(R174)),R174,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM175 | =IF(ISNUMBER(J175),1,0) | =IF(AND(ISNUMBER(J175),OR(AR175="INHERITED ESTIMATE",AR175="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS175 |  | =IF(AM175=1,J175,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT175 |  | =IF(AND(AM175=1,ISNUMBER(R175)),R175,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM176 | =IF(ISNUMBER(J176),1,0) | =IF(AND(ISNUMBER(J176),OR(AR176="INHERITED ESTIMATE",AR176="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS176 |  | =IF(AM176=1,J176,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT176 |  | =IF(AND(AM176=1,ISNUMBER(R176)),R176,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM177 | =IF(ISNUMBER(J177),1,0) | =IF(AND(ISNUMBER(J177),OR(AR177="INHERITED ESTIMATE",AR177="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS177 |  | =IF(AM177=1,J177,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT177 |  | =IF(AND(AM177=1,ISNUMBER(R177)),R177,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM178 | =IF(ISNUMBER(J178),1,0) | =IF(AND(ISNUMBER(J178),OR(AR178="INHERITED ESTIMATE",AR178="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS178 |  | =IF(AM178=1,J178,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT178 |  | =IF(AND(AM178=1,ISNUMBER(R178)),R178,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM179 | =IF(ISNUMBER(J179),1,0) | =IF(AND(ISNUMBER(J179),OR(AR179="INHERITED ESTIMATE",AR179="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS179 |  | =IF(AM179=1,J179,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT179 |  | =IF(AND(AM179=1,ISNUMBER(R179)),R179,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AM180 | =IF(ISNUMBER(J180),1,0) | =IF(AND(ISNUMBER(J180),OR(AR180="INHERITED ESTIMATE",AR180="CONFIRMED ESTIMATE")),1,0) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AS180 |  | =IF(AM180=1,J180,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Backlog | AT180 |  | =IF(AND(AM180=1,ISNUMBER(R180)),R180,"") | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Release Plan | A1 | Release Plan — v2.23.0 ¦ known effort only; 8 unestimated/unconfirmed rows | Release Plan — v2.23.0 ¦ reviewed15Sep2026; partial non-withdrawn estimates only | Synchronize current metadata/labels with supported evidence or calculation.
Release Plan | I3 | Known scope h | Usable scope h | Synchronize current metadata/labels with supported evidence or calculation.
Release Plan | J3 | Known open h | Usable open scope h | Synchronize current metadata/labels with supported evidence or calculation.
Release Plan | K3 | Unestimated rows | Estimate unresolved rows | Synchronize current metadata/labels with supported evidence or calculation.
Release Plan | I4 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A4,Backlog!$C$2:$C$180,$C4) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A4,Backlog!$C$2:$C$180,$C4) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J4 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A4,Backlog!$C$2:$C$180,$C4,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A4,Backlog!$C$2:$C$180,$C4,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I5 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A5,Backlog!$C$2:$C$180,$C5) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A5,Backlog!$C$2:$C$180,$C5) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J5 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A5,Backlog!$C$2:$C$180,$C5,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A5,Backlog!$C$2:$C$180,$C5,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I6 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A6,Backlog!$C$2:$C$180,$C6) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A6,Backlog!$C$2:$C$180,$C6) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J6 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A6,Backlog!$C$2:$C$180,$C6,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A6,Backlog!$C$2:$C$180,$C6,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I7 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A7,Backlog!$C$2:$C$180,$C7) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A7,Backlog!$C$2:$C$180,$C7) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J7 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A7,Backlog!$C$2:$C$180,$C7,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A7,Backlog!$C$2:$C$180,$C7,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I8 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A8,Backlog!$C$2:$C$180,$C8) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A8,Backlog!$C$2:$C$180,$C8) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J8 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A8,Backlog!$C$2:$C$180,$C8,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A8,Backlog!$C$2:$C$180,$C8,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I9 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A9,Backlog!$C$2:$C$180,$C9) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A9,Backlog!$C$2:$C$180,$C9) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J9 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A9,Backlog!$C$2:$C$180,$C9,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A9,Backlog!$C$2:$C$180,$C9,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I10 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A10,Backlog!$C$2:$C$180,$C10) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A10,Backlog!$C$2:$C$180,$C10) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J10 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A10,Backlog!$C$2:$C$180,$C10,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A10,Backlog!$C$2:$C$180,$C10,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I11 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A11,Backlog!$C$2:$C$180,$C11) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A11,Backlog!$C$2:$C$180,$C11) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J11 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A11,Backlog!$C$2:$C$180,$C11,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A11,Backlog!$C$2:$C$180,$C11,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I12 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A12,Backlog!$C$2:$C$180,$C12) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A12,Backlog!$C$2:$C$180,$C12) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J12 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A12,Backlog!$C$2:$C$180,$C12,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A12,Backlog!$C$2:$C$180,$C12,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | I13 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A13,Backlog!$C$2:$C$180,$C13) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A13,Backlog!$C$2:$C$180,$C13) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Release Plan | J13 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,$A13,Backlog!$C$2:$C$180,$C13,Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,$A13,Backlog!$C$2:$C$180,$C13,Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G2 | Known estimate h | Usable estimate h | Synchronize current metadata/labels with supported evidence or calculation.
Worker Tracks | H2 | AI P80 h | Usable P80 h | Synchronize current metadata/labels with supported evidence or calculation.
Worker Tracks | G3 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D3,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D3,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D3,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D3,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H3 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D3,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D3,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D3,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D3,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G4 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D4,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D4,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D4,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D4,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H4 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D4,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D4,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D4,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D4,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G5 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D5,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D5,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D5,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D5,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H5 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D5,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D5,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D5,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D5,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G6 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D6,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D6,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D6,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D6,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H6 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D6,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D6,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D6,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D6,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G7 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D7,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D7,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D7,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D7,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H7 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D7,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D7,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D7,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D7,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G8 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D8,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D8,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D8,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D8,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H8 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D8,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D8,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D8,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D8,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G9 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D9,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D9,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D9,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D9,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H9 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D9,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D9,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D9,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D9,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G10 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D10,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D10,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D10,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D10,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H10 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D10,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D10,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D10,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D10,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G11 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D11,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D11,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D11,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D11,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H11 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D11,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D11,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D11,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D11,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G12 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D12,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D12,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D12,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D12,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H12 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D12,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D12,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D12,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D12,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G13 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D13,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D13,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D13,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D13,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H13 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D13,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D13,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D13,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D13,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G14 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D14,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D14,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D14,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D14,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H14 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D14,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D14,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D14,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D14,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G15 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D15,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D15,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D15,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D15,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H15 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D15,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D15,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D15,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D15,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G16 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D16,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D16,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D16,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D16,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H16 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D16,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D16,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D16,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D16,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G17 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D17,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D17,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D17,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D17,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H17 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D17,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D17,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D17,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D17,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G18 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D18,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D18,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D18,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D18,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H18 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D18,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D18,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D18,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D18,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G19 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D19,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D19,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D19,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D19,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H19 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D19,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D19,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D19,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D19,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G20 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D20,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D20,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D20,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D20,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H20 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D20,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D20,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D20,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D20,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G21 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D21,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D21,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D21,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D21,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H21 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D21,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D21,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D21,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D21,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G22 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D22,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D22,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D22,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D22,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H22 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D22,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D22,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D22,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D22,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G23 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D23,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D23,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D23,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D23,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H23 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D23,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D23,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D23,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D23,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G24 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D24,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D24,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D24,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D24,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H24 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D24,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D24,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D24,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D24,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G25 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D25,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D25,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D25,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D25,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H25 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D25,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D25,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D25,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D25,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G26 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D26,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D26,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D26,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D26,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H26 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D26,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D26,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D26,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D26,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G27 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D27,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D27,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D27,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D27,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H27 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D27,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D27,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D27,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D27,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G28 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D28,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D28,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D28,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D28,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H28 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D28,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D28,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D28,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D28,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G29 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D29,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D29,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D29,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D29,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H29 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D29,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D29,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D29,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D29,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G30 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D30,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D30,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D30,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D30,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H30 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D30,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D30,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D30,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D30,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G31 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D31,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D31,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D31,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D31,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H31 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D31,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D31,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D31,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D31,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G32 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D32,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D32,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D32,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D32,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H32 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D32,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D32,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D32,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D32,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G33 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D33,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D33,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D33,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D33,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H33 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D33,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D33,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D33,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D33,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G34 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D34,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D34,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D34,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D34,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H34 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D34,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D34,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D34,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D34,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G35 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D35,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D35,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D35,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D35,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H35 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D35,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D35,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D35,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D35,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G36 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D36,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D36,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D36,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D36,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H36 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D36,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D36,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D36,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D36,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G37 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D37,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D37,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D37,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D37,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H37 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D37,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D37,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D37,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D37,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G38 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D38,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D38,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D38,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D38,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H38 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D38,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D38,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D38,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D38,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G39 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D39,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D39,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D39,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D39,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H39 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D39,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D39,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D39,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D39,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G40 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D40,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D40,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D40,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D40,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H40 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D40,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D40,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D40,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D40,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G41 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D41,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D41,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D41,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D41,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H41 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D41,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D41,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D41,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D41,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G42 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D42,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D42,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D42,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D42,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H42 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D42,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D42,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D42,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D42,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G43 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D43,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D43,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D43,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D43,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H43 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D43,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D43,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D43,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D43,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G44 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D44,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D44,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D44,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D44,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H44 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D44,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D44,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D44,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D44,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G45 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D45,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D45,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D45,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D45,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H45 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D45,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D45,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D45,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D45,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G46 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D46,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D46,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D46,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D46,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H46 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D46,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D46,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D46,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D46,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G47 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D47,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D47,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D47,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D47,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H47 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D47,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D47,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D47,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D47,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G48 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D48,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D48,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D48,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D48,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H48 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D48,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D48,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D48,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D48,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G49 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D49,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D49,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D49,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D49,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H49 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D49,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D49,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D49,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D49,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G50 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D50,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D50,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D50,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D50,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H50 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D50,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D50,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D50,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D50,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G51 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D51,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D51,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D51,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D51,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H51 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D51,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D51,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D51,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D51,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G52 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D52,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D52,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D52,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D52,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H52 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D52,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D52,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D52,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D52,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G53 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D53,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D53,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D53,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D53,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H53 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D53,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D53,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D53,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D53,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G54 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D54,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D54,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D54,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D54,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H54 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D54,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D54,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D54,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D54,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G55 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D55,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D55,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D55,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D55,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H55 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D55,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D55,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D55,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D55,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G56 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D56,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D56,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D56,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D56,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H56 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D56,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D56,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D56,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D56,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G57 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D57,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D57,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D57,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D57,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H57 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D57,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D57,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D57,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D57,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G58 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D58,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D58,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D58,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D58,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H58 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D58,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D58,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D58,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D58,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G59 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D59,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D59,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D59,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D59,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H59 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D59,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D59,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D59,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D59,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G60 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D60,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D60,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D60,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D60,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H60 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D60,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D60,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D60,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D60,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G61 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D61,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D61,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D61,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D61,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H61 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D61,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D61,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D61,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D61,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G62 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D62,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D62,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D62,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D62,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H62 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D62,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D62,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D62,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D62,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G63 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D63,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D63,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D63,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D63,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H63 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D63,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D63,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D63,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D63,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G64 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D64,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D64,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D64,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D64,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H64 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D64,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D64,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D64,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D64,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G65 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D65,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D65,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D65,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D65,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H65 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D65,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D65,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D65,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D65,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G66 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D66,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D66,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D66,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D66,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H66 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D66,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D66,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D66,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D66,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G67 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D67,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D67,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D67,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D67,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H67 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D67,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D67,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D67,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D67,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G68 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D68,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D68,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D68,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D68,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H68 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D68,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D68,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D68,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D68,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G69 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D69,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D69,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D69,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D69,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H69 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D69,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D69,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D69,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D69,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G70 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D70,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D70,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D70,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D70,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H70 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D70,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D70,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D70,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D70,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G71 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D71,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D71,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D71,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D71,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H71 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D71,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D71,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D71,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D71,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G72 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D72,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D72,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D72,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D72,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H72 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D72,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D72,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D72,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D72,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G73 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D73,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D73,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D73,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D73,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H73 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D73,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D73,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D73,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D73,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G74 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D74,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D74,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D74,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D74,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H74 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D74,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D74,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D74,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D74,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G75 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D75,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D75,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D75,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D75,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H75 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D75,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D75,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D75,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D75,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G76 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D76,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D76,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D76,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D76,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H76 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D76,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D76,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D76,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D76,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G77 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D77,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D77,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D77,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D77,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H77 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D77,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D77,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D77,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D77,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G78 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D78,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D78,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D78,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D78,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H78 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D78,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D78,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D78,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D78,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G79 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D79,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D79,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D79,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D79,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H79 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D79,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D79,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D79,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D79,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G80 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D80,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D80,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D80,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D80,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H80 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D80,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D80,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D80,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D80,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G81 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D81,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D81,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D81,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D81,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H81 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D81,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D81,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D81,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D81,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G82 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D82,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D82,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D82,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D82,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H82 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D82,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D82,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D82,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D82,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G83 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D83,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D83,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D83,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D83,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H83 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D83,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D83,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D83,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D83,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G84 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D84,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D84,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D84,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D84,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H84 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D84,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D84,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D84,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D84,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G85 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D85,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D85,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D85,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D85,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H85 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D85,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D85,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D85,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D85,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G86 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D86,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D86,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D86,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D86,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H86 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D86,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D86,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D86,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D86,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G87 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D87,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D87,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D87,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D87,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H87 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D87,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D87,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D87,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D87,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G88 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D88,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D88,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D88,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D88,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H88 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D88,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D88,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D88,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D88,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G89 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D89,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D89,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D89,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D89,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H89 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D89,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D89,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D89,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D89,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G90 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D90,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D90,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D90,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D90,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H90 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D90,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D90,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D90,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D90,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G91 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D91,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D91,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D91,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D91,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H91 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D91,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D91,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D91,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D91,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G92 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D92,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D92,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D92,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D92,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H92 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D92,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D92,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D92,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D92,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G93 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D93,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D93,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D93,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D93,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H93 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D93,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D93,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D93,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D93,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G94 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D94,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D94,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D94,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D94,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H94 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D94,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D94,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D94,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D94,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G95 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D95,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D95,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D95,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D95,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H95 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D95,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D95,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D95,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D95,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G96 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D96,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D96,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D96,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D96,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H96 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D96,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D96,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D96,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D96,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G97 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D97,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D97,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D97,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D97,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H97 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D97,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D97,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D97,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D97,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G98 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D98,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D98,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D98,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D98,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H98 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D98,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D98,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D98,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D98,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G99 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D99,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D99,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D99,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D99,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H99 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D99,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D99,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D99,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D99,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G100 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D100,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D100,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D100,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D100,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H100 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D100,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D100,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D100,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D100,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G101 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D101,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D101,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D101,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D101,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H101 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D101,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D101,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D101,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D101,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G102 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D102,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D102,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D102,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D102,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H102 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D102,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D102,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D102,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D102,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G103 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D103,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D103,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D103,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D103,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H103 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D103,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D103,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D103,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D103,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G104 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D104,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D104,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D104,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D104,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H104 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D104,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D104,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D104,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D104,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G105 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D105,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D105,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D105,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D105,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H105 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D105,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D105,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D105,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D105,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G106 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D106,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D106,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D106,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D106,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H106 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D106,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D106,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D106,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D106,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G107 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D107,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D107,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D107,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D107,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H107 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D107,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D107,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D107,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D107,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G108 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D108,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D108,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D108,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D108,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H108 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D108,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D108,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D108,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D108,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G109 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D109,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D109,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D109,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D109,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H109 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D109,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D109,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D109,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D109,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G110 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D110,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D110,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D110,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D110,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H110 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D110,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D110,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D110,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D110,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G111 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D111,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D111,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D111,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D111,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H111 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D111,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D111,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D111,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D111,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G112 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D112,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D112,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D112,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D112,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H112 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D112,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D112,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D112,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D112,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G113 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D113,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D113,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D113,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D113,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H113 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D113,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D113,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D113,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D113,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G114 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D114,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D114,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D114,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D114,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H114 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D114,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D114,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D114,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D114,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G115 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D115,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D115,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D115,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D115,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H115 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D115,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D115,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D115,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D115,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G116 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D116,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D116,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D116,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D116,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H116 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D116,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D116,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D116,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D116,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G117 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D117,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D117,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D117,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D117,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H117 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D117,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D117,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D117,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D117,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G118 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D118,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D118,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D118,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D118,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H118 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D118,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D118,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D118,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D118,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G119 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D119,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D119,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D119,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D119,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H119 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D119,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D119,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D119,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D119,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G120 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D120,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D120,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D120,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D120,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H120 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D120,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D120,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D120,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D120,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G121 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D121,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D121,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D121,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D121,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H121 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D121,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D121,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D121,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D121,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G122 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D122,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D122,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D122,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D122,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H122 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D122,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D122,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D122,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D122,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G123 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D123,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D123,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D123,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D123,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H123 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D123,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D123,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D123,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D123,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G124 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D124,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D124,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D124,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D124,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H124 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D124,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D124,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D124,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D124,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G125 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D125,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D125,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D125,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D125,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H125 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D125,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D125,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D125,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D125,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G126 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D126,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D126,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D126,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D126,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H126 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D126,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D126,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D126,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D126,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G127 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D127,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D127,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D127,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D127,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H127 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D127,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D127,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D127,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D127,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G128 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D128,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D128,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D128,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D128,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H128 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D128,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D128,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D128,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D128,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G129 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D129,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D129,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D129,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D129,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H129 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D129,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D129,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D129,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D129,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G130 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D130,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D130,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D130,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D130,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H130 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D130,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D130,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D130,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D130,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G131 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D131,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D131,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D131,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D131,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H131 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D131,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D131,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D131,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D131,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G132 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D132,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D132,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D132,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D132,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H132 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D132,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D132,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D132,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D132,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G133 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D133,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D133,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D133,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D133,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H133 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D133,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D133,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D133,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D133,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G134 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D134,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D134,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D134,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D134,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H134 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D134,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D134,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D134,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D134,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G135 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D135,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D135,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D135,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D135,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H135 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D135,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D135,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D135,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D135,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G136 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D136,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D136,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D136,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D136,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H136 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D136,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D136,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D136,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D136,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G137 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D137,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D137,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D137,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D137,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H137 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D137,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D137,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D137,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D137,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G138 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D138,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D138,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D138,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D138,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H138 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D138,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D138,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D138,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D138,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G139 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D139,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D139,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D139,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D139,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H139 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D139,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D139,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D139,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D139,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G140 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D140,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D140,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D140,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D140,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H140 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D140,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D140,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D140,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D140,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G141 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D141,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D141,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D141,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D141,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H141 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D141,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D141,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D141,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D141,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G142 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D142,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D142,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D142,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D142,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H142 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D142,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D142,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D142,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D142,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G143 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D143,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D143,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D143,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D143,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H143 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D143,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D143,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D143,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D143,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G144 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D144,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D144,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D144,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D144,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H144 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D144,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D144,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D144,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D144,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G145 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D145,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D145,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D145,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D145,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H145 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D145,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D145,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D145,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D145,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G146 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D146,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D146,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D146,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D146,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H146 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D146,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D146,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D146,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D146,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G147 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D147,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D147,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D147,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D147,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H147 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D147,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D147,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D147,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D147,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G148 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D148,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D148,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D148,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D148,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H148 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D148,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D148,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D148,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D148,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G149 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D149,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D149,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D149,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D149,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H149 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D149,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D149,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D149,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D149,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G150 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D150,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D150,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D150,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D150,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H150 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D150,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D150,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D150,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D150,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G151 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D151,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D151,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D151,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D151,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H151 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D151,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D151,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D151,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D151,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G152 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D152,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D152,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D152,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D152,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H152 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D152,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D152,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D152,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D152,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G153 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D153,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D153,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D153,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D153,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H153 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D153,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D153,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D153,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D153,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G154 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D154,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D154,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D154,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D154,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H154 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D154,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D154,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D154,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D154,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G155 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D155,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D155,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D155,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D155,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H155 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D155,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D155,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D155,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D155,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G156 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D156,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D156,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D156,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D156,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H156 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D156,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D156,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D156,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D156,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G157 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D157,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D157,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D157,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D157,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H157 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D157,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D157,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D157,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D157,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G158 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D158,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D158,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D158,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D158,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H158 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D158,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D158,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D158,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D158,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G159 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D159,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D159,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D159,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D159,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H159 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D159,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D159,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D159,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D159,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G160 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D160,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D160,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D160,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D160,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H160 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D160,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D160,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D160,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D160,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G161 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D161,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D161,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D161,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D161,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H161 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D161,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D161,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D161,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D161,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G162 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D162,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D162,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D162,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D162,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H162 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D162,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D162,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D162,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D162,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G163 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D163,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D163,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D163,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D163,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H163 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D163,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D163,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D163,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D163,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G164 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D164,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D164,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D164,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D164,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H164 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D164,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D164,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D164,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D164,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G165 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D165,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D165,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D165,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D165,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H165 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D165,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D165,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D165,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D165,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G166 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D166,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D166,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D166,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D166,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H166 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D166,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D166,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D166,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D166,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G167 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D167,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D167,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D167,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D167,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H167 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D167,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D167,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D167,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D167,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G168 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D168,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D168,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D168,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D168,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H168 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D168,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D168,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D168,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D168,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G169 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D169,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D169,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D169,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D169,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H169 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D169,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D169,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D169,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D169,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G170 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D170,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D170,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D170,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D170,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H170 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D170,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D170,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D170,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D170,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G171 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D171,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D171,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D171,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D171,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H171 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D171,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D171,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D171,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D171,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G172 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D172,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D172,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D172,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D172,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H172 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D172,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D172,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D172,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D172,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G173 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D173,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D173,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D173,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D173,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H173 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D173,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D173,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D173,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D173,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G174 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D174,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D174,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D174,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D174,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H174 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D174,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D174,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D174,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D174,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G175 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D175,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D175,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D175,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D175,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H175 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D175,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D175,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D175,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D175,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G176 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D176,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D176,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D176,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D176,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H176 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D176,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D176,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D176,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D176,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G177 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D177,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D177,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D177,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D177,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H177 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D177,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D177,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D177,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D177,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G178 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D178,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D178,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D178,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D178,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H178 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D178,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D178,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D178,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D178,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G179 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D179,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D179,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D179,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D179,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H179 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D179,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D179,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D179,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D179,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G180 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D180,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D180,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D180,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D180,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H180 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D180,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D180,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D180,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D180,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | G181 | =IF(ISNUMBER(INDEX(Backlog!$J$2:$J$180,MATCH($D181,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$J$2:$J$180,MATCH($D181,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AS$2:$AS$180,MATCH($D181,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AS$2:$AS$180,MATCH($D181,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Worker Tracks | H181 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($D181,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($D181,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($D181,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($D181,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Requirement Traceability | A1 | Requirement Traceability — v2.22.1 ¦ mapping from current Backlog; unchanged Design v4.10.3 | Requirement Traceability — current Backlog v2.23.0 | Synchronize current metadata/labels with supported evidence or calculation.
Dependency Graph | F1 | AI P80 h | Usable P80 h | Synchronize current metadata/labels with supported evidence or calculation.
Dependency Graph | F2 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A2,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A2,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A2,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A2,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F3 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A3,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A3,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A3,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A3,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F4 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A4,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A4,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A4,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A4,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F5 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A5,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A5,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A5,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A5,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F6 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A6,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A6,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A6,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A6,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F7 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A7,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A7,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A7,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A7,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F8 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A8,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A8,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A8,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A8,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F9 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A9,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A9,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A9,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A9,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F10 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A10,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A10,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A10,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A10,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F11 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A11,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A11,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A11,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A11,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F12 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A12,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A12,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A12,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A12,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F13 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A13,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A13,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A13,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A13,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F14 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A14,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A14,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A14,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A14,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F15 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A15,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A15,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A15,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A15,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F16 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A16,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A16,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A16,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A16,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F17 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A17,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A17,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A17,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A17,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F18 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A18,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A18,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A18,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A18,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F19 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A19,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A19,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A19,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A19,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F20 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A20,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A20,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A20,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A20,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F21 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A21,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A21,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A21,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A21,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F22 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A22,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A22,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A22,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A22,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F23 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A23,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A23,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A23,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A23,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F24 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A24,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A24,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A24,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A24,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F25 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A25,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A25,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A25,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A25,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F26 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A26,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A26,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A26,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A26,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F27 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A27,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A27,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A27,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A27,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F28 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A28,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A28,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A28,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A28,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F29 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A29,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A29,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A29,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A29,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F30 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A30,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A30,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A30,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A30,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F31 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A31,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A31,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A31,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A31,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F32 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A32,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A32,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A32,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A32,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F33 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A33,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A33,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A33,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A33,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F34 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A34,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A34,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A34,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A34,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F35 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A35,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A35,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A35,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A35,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F36 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A36,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A36,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A36,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A36,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F37 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A37,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A37,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A37,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A37,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F38 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A38,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A38,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A38,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A38,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F39 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A39,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A39,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A39,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A39,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F40 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A40,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A40,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A40,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A40,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F41 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A41,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A41,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A41,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A41,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F42 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A42,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A42,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A42,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A42,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F43 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A43,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A43,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A43,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A43,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F44 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A44,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A44,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A44,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A44,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F45 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A45,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A45,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A45,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A45,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F46 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A46,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A46,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A46,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A46,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F47 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A47,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A47,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A47,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A47,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F48 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A48,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A48,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A48,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A48,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F49 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A49,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A49,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A49,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A49,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F50 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A50,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A50,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A50,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A50,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F51 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A51,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A51,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A51,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A51,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F52 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A52,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A52,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A52,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A52,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F53 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A53,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A53,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A53,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A53,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F54 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A54,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A54,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A54,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A54,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F55 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A55,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A55,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A55,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A55,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F56 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A56,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A56,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A56,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A56,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F57 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A57,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A57,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A57,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A57,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F58 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A58,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A58,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A58,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A58,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F59 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A59,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A59,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A59,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A59,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F60 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A60,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A60,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A60,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A60,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F61 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A61,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A61,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A61,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A61,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F62 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A62,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A62,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A62,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A62,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F63 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A63,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A63,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A63,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A63,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F64 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A64,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A64,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A64,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A64,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F65 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A65,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A65,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A65,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A65,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F66 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A66,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A66,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A66,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A66,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F67 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A67,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A67,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A67,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A67,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F68 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A68,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A68,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A68,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A68,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F69 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A69,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A69,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A69,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A69,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F70 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A70,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A70,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A70,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A70,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F71 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A71,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A71,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A71,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A71,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F72 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A72,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A72,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A72,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A72,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F73 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A73,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A73,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A73,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A73,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F74 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A74,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A74,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A74,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A74,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F75 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A75,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A75,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A75,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A75,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F76 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A76,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A76,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A76,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A76,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F77 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A77,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A77,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A77,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A77,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F78 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A78,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A78,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A78,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A78,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F79 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A79,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A79,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A79,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A79,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F80 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A80,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A80,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A80,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A80,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F81 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A81,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A81,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A81,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A81,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F82 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A82,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A82,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A82,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A82,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F83 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A83,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A83,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A83,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A83,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F84 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A84,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A84,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A84,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A84,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F85 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A85,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A85,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A85,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A85,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F86 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A86,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A86,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A86,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A86,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F87 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A87,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A87,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A87,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A87,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F88 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A88,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A88,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A88,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A88,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F89 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A89,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A89,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A89,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A89,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F90 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A90,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A90,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A90,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A90,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F91 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A91,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A91,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A91,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A91,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F92 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A92,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A92,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A92,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A92,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F93 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A93,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A93,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A93,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A93,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F94 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A94,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A94,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A94,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A94,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F95 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A95,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A95,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A95,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A95,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F96 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A96,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A96,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A96,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A96,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F97 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A97,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A97,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A97,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A97,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F98 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A98,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A98,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A98,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A98,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F99 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A99,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A99,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A99,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A99,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F100 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A100,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A100,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A100,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A100,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F101 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A101,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A101,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A101,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A101,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F102 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A102,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A102,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A102,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A102,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F103 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A103,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A103,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A103,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A103,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F104 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A104,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A104,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A104,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A104,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F105 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A105,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A105,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A105,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A105,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F106 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A106,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A106,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A106,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A106,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F107 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A107,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A107,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A107,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A107,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F108 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A108,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A108,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A108,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A108,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F109 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A109,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A109,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A109,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A109,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F110 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A110,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A110,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A110,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A110,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F111 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A111,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A111,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A111,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A111,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F112 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A112,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A112,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A112,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A112,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F113 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A113,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A113,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A113,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A113,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F114 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A114,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A114,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A114,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A114,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F115 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A115,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A115,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A115,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A115,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F116 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A116,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A116,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A116,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A116,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F117 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A117,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A117,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A117,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A117,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F118 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A118,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A118,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A118,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A118,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F119 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A119,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A119,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A119,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A119,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F120 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A120,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A120,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A120,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A120,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F121 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A121,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A121,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A121,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A121,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F122 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A122,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A122,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A122,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A122,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F123 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A123,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A123,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A123,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A123,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F124 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A124,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A124,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A124,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A124,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F125 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A125,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A125,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A125,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A125,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F126 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A126,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A126,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A126,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A126,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F127 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A127,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A127,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A127,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A127,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F128 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A128,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A128,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A128,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A128,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F129 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A129,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A129,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A129,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A129,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F130 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A130,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A130,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A130,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A130,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F131 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A131,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A131,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A131,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A131,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F132 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A132,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A132,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A132,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A132,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F133 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A133,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A133,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A133,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A133,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F134 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A134,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A134,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A134,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A134,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F135 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A135,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A135,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A135,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A135,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F136 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A136,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A136,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A136,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A136,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F137 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A137,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A137,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A137,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A137,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F138 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A138,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A138,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A138,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A138,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F139 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A139,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A139,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A139,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A139,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F140 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A140,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A140,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A140,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A140,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F141 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A141,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A141,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A141,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A141,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F142 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A142,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A142,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A142,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A142,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F143 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A143,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A143,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A143,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A143,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F144 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A144,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A144,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A144,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A144,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F145 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A145,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A145,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A145,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A145,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F146 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A146,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A146,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A146,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A146,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F147 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A147,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A147,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A147,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A147,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F148 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A148,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A148,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A148,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A148,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F149 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A149,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A149,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A149,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A149,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F150 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A150,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A150,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A150,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A150,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F151 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A151,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A151,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A151,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A151,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F152 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A152,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A152,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A152,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A152,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F153 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A153,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A153,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A153,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A153,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F154 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A154,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A154,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A154,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A154,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F155 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A155,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A155,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A155,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A155,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F156 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A156,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A156,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A156,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A156,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F157 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A157,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A157,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A157,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A157,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F158 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A158,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A158,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A158,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A158,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F159 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A159,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A159,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A159,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A159,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F160 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A160,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A160,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A160,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A160,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F161 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A161,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A161,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A161,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A161,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F162 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A162,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A162,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A162,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A162,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F163 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A163,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A163,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A163,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A163,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F164 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A164,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A164,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A164,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A164,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F165 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A165,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A165,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A165,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A165,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F166 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A166,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A166,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A166,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A166,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F167 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A167,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A167,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A167,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A167,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F168 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A168,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A168,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A168,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A168,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F169 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A169,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A169,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A169,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A169,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F170 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A170,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A170,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A170,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A170,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F171 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A171,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A171,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A171,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A171,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F172 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A172,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A172,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A172,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A172,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F173 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A173,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A173,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A173,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A173,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F174 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A174,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A174,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A174,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A174,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F175 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A175,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A175,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A175,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A175,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F176 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A176,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A176,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A176,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A176,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F177 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A177,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A177,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A177,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A177,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F178 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A178,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A178,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A178,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A178,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F179 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A179,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A179,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A179,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A179,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dependency Graph | F180 | =IF(ISNUMBER(INDEX(Backlog!$R$2:$R$180,MATCH($A180,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$R$2:$R$180,MATCH($A180,Backlog!$A$2:$A$180,0)),"") | =IF(ISNUMBER(INDEX(Backlog!$AT$2:$AT$180,MATCH($A180,Backlog!$A$2:$A$180,0))),INDEX(Backlog!$AT$2:$AT$180,MATCH($A180,Backlog!$A$2:$A$180,0)),"") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Method & Notes | A1 | Method and Notes — v2.22.1 | Method and Notes — v2.23.0 ¦15Sep2026 evidence reconciliation | Synchronize current metadata/labels with supported evidence or calculation.
Method & Notes | B19 | Historical 08-Sep checkpoint superseded. Current Backlog records T-243 In Progress/source-present; not automatically closed. T-253 accepted work remains preserved. | T-243 baseline closure6f65bba1 is proven by an executed10Sep ancestry report. Its later transactional relationship-publication extension remains unverified. Do not relabel the original work as merely source-present. | Synchronize current metadata/labels with supported evidence or calculation.
Method & Notes | B38 | Backlog, Current Authority and current generated views are v2.22.1. v220 summaries and Prior/Retired/previous-revision sheets are immutable historical snapshots. | Current execution views use Backlog v2.23.0. Historical v220/Prior/Retired/previous-revision sheets preserve past states, not current truth. | Synchronize current metadata/labels with supported evidence or calculation.
Method & Notes | B41 | Owner-provided final runner report in this conversation, received 14-Sep-2026; not independently rerun or verified against a live Git checkout here. Live acceptance 49/49; catalogue 5/5; owned contract 19/19; cleanup 6/6, survivors 0. Gate O: 900 = 899 passed + 1 exact inherited DefinitionKind RED; 900 unique testId and executionId. Exact staging/byte boundary passed; cleanup before one semantic commit. Task closure GREEN, not release-wide GREEN; canonical replay limitations remain separately tracked. | Final executed terminal transcript corroborates the owner-reported closure: 49/49 live,5/5 catalogue,19/19 owned;6/6 disposable DBs dropped;0survivors. GateO900=899passed+1exact inheritedDefinitionKindRED. Exact staging and one semantic commit proven. No live rerun performed in this review; no release-wideGREEN. Pasted text(20260914-134548).txt ¦ lines430-450; final gatesQ/R; COMMITca02b40ea1b69050a45cb35a3e1d64f15b1f66af; PARENT86e1b677212195f191697ecdca7e9441b3dbde33; live49/49, catalogue5/5, owned19/19; not release-wideGREEN. | Synchronize current metadata/labels with supported evidence or calculation.
Method & Notes | B42 | In Progress is the execution category. Evidence state is SOURCE PRESENT / UNCLOSED. No commit timestamp or successful closure is invented. | T-262 producer contract GREEN committed86e1b677; live integration explicitly unexecuted. Current expanded acceptance remains open pending disposition; no claim that the producer lacks a SHA. | Synchronize current metadata/labels with supported evidence or calculation.
Method & Notes | B45 | T-106 16h and T-108 8h are archived, not current totals. Their P80 values are also withdrawn; blank means unknown, not zero. | J/R hold supplied scope estimates, not measured actual time.8 entries have no accepted numeric estimate;19 additional changed-scope rows are stale. AS/AT exclude all27 from live planning sums. No remaining-hours forecast is certified. | Make estimate policy consistent across rows and dashboards.
Method & Notes | A48 |  | Historical closure versus current scope | Add status semantics.
Method & Notes | B48 |  | Progress is not execution readiness. Current In Progress may combine a closed baseline with an unstarted extension. Preserve both facts in Task Evidence15Sep; do not infer an active worker or release certification from the status color. | Add explicit, non-misleading status semantics.
Commit Ledger | A45 |  | T-106 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | B45 |  | P2 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | C45 |  | Worker 3 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | D45 |  | 8b3eb5c89352a2779d87f9205700f19e7c9b3e25; a5451dbaf6b55183fe65e2c626c49fdef85bd986 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | E45 |  | Canonical jobs: target/version, scheduling, dependencies, cancellation and outcome truth | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | G45 |  | Exact Git timestamp not recovered; dated source is observation evidence. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | H45 |  | Source-bound terminal/central/ancestry evidence; not a live repository rerun. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | I45 |  | Original corrective run returned GREEN with22 corrective,26 foundation,84 target-regression and15 architecture tests in24 owned paths;CENTRAL freeze after review. Later v2.22 schedule/cancel/freshness/outcome-truth scope is not closed by a10Sep run. Pasted text(20260910-102642).txt ¦ lines244-261, T-106 FINAL RESULT: corrective COMMITTED GREEN a5451dbaf6b55183fe65e2c626c49fdef85bd986; foundation8b3eb5c89352a2779d87f9205700f19e7c9b3e25;22corrective,26foundation,84target-regression,15architecture tests;24owned paths;CENTRAL freeze after review. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | A46 |  | T-243 | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | B46 |  | P2 | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | C46 |  | Worker 2 | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | D46 |  | 6f65bba1 | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | E46 |  | Canvas persistence, immutable versioning and reopen/edit round-trip | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | G46 |  | Exact Git timestamp not recovered; source document date is evidence date, not commit time. | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | H46 |  | Executed transcript/closure excerpt; no live Git verification in this review. | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | I46 |  | Executed ancestry proves the original board/history/reopen closure. Later v2.22 transactional relationship publication remains a separate outstanding acceptance slice. Do not reimplement the saved-board baseline. Exact full SHA/date not recovered. Pasted text(20260910-105308).txt ¦ executed preflight at 2026-09-10 13:30:05, lines39-58; T-243 closure 6f65bba1 is an ancestor; T-106 a5451dba and 8b3eb5c8 also ancestors. | Recover commit evidence by Task ID without manufacturing timestamps. | T-243
Commit Ledger | A47 |  | T-254 | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | B47 |  | P2 | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | C47 |  | Worker 2 | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | D47 |  | f8a35725c9b0d7fb5a0515c0103a72807a704a97 | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | E47 |  | Customer-facing connector capability truth convergence | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | G47 |  | Exact Git timestamp not recovered; source document date is evidence date, not commit time. | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | H47 |  | Executed transcript/closure excerpt; no live Git verification in this review. | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | I47 |  | Original customer-facing connector convergence closed in 5 paths. Website typecheck not independently re-claimed in handover, not RED. v2.22 backend-provider-list extension has no new completion evidence; certify that delta only. Pasted text(20260910-064052).txt ¦ T-254 CLOSED GREEN/FROZEN section; f8a35725c9b0d7fb5a0515c0103a72807a704a97. Historical frontend/website scope, not later backend-list extension. | Recover commit evidence by Task ID without manufacturing timestamps. | T-254
Commit Ledger | A48 |  | T-262 | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | B48 |  | P2 | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | C48 |  | Worker 2 | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | D48 |  | 86e1b677212195f191697ecdca7e9441b3dbde33 | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | E48 |  | Governed projection declaration and canonical field-binding contract | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | G48 |  | Exact Git timestamp not recovered; source document date is evidence date, not commit time. | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | H48 |  | Executed transcript/closure excerpt; no live Git verification in this review. | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | I48 |  | Producer declaration is committed with backend24/24, catalogue8/8, content39/39 and authoring404/404; parent36de9370 (short). Live definition-store integration is explicitly not executed. Current row asks for needed integration closure: retain In Progress pending that disposition, but withdraw the false 'no accepted SHA/run supplied' statement. No producer rewrite. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | Recover commit evidence by Task ID without manufacturing timestamps. | T-262
Commit Ledger | A49 |  | T-251 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | B49 |  | P1 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | C49 |  | Worker 1 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | D49 |  | 7ba31f96f3810bdac734bd1850275a601503d34d | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | E49 |  | Physical database catalogue, naming authority and zero-unknown schema dictionary | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | G49 |  | Exact Git timestamp not recovered; dated source is observation evidence. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | H49 |  | Source-bound terminal/central/ancestry evidence; not a live repository rerun. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | I49 |  | Original catalogue closure explicitly frozen by CENTRAL. Retain Done; later catalogue/build changes do not retroactively erase this producer closure. Pasted text(20260910-064052).txt lines139-146: CENTRAL states T-251 CLOSED GREEN7ba31f96f3810bdac734bd1850275a601503d34d; later T-245 preflight observes its catalogue changes. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | A50 |  | T-256 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | B50 |  | P1 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | C50 |  | Worker 1 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | D50 |  | 36de9370 | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | E50 |  | Runtime genericity and three-schema consumer convergence | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | G50 |  | Exact Git timestamp not recovered; dated source is observation evidence. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | H50 |  | Source-bound terminal/central/ancestry evidence; not a live repository rerun. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Commit Ledger | I50 |  | Inherited accepted Done state retained. T-262's terminal summary identifies parent36de9370 as T-256. This corroborates a commit anchor, not a rerun of T-256 gates. Pasted text(20260912-074928).txt ¦ lines1229-1243; T-262 GREEN committed86e1b677212195f191697ecdca7e9441b3dbde33; parent36de9370; live definition-store integration explicitly unexecuted. | Task-ID keyed recovery of lost evidence. | Source references in columnI.
Capability Map v1.1 | K4 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A4) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A4) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L4 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A4,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A4,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K5 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A5) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A5) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L5 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A5,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A5,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K6 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A6) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A6) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L6 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A6,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A6,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K7 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A7) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A7) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L7 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A7,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A7,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | M7 | =TEXTJOIN("; ",TRUE,IFERROR(INDEX(Backlog!$A$2:$A$180,MATCH("T-254",Backlog!$A$2:$A$180,0)),""),IFERROR(INDEX(Backlog!$A$2:$A$180,MATCH("T-153",Backlog!$A$2:$A$180,0)),""),IFERROR(INDEX(Backlog!$A$2:$A$180,MATCH("T-266",Backlog!$A$2:$A$180,0)),"")) | =TEXTJOIN("; ",TRUE,IFERROR(INDEX(Backlog!$A$2:$A$180,MATCH("T-153",Backlog!$A$2:$A$180,0)),""),IFERROR(INDEX(Backlog!$A$2:$A$180,MATCH("T-266",Backlog!$A$2:$A$180,0)),"")) | Rebuild capability membership from current primary/secondary IDs; remove duplicate primary-secondary link.
Capability Map v1.1 | K8 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A8) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A8) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L8 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A8,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A8,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K9 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A9) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A9) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L9 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A9,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A9,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K10 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A10) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A10) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L10 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A10,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A10,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K11 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A11) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A11) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L11 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A11,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A11,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K12 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A12) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A12) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L12 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A12,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A12,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K13 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A13) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A13) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L13 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A13,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A13,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K14 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A14) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A14) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L14 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A14,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A14,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K15 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A15) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A15) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L15 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A15,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A15,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K16 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A16) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A16) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L16 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A16,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A16,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K17 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A17) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A17) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L17 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A17,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A17,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K18 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A18) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A18) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L18 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A18,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A18,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K19 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A19) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A19) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L19 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A19,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A19,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K20 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A20) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A20) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L20 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A20,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A20,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K21 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A21) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A21) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L21 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A21,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A21,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K22 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A22) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A22) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L22 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A22,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A22,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K23 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A23) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A23) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L23 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A23,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A23,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K24 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A24) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A24) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L24 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A24,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A24,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K25 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A25) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A25) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L25 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A25,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A25,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K26 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A26) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A26) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L26 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A26,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A26,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K27 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A27) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A27) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L27 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A27,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A27,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K28 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A28) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A28) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L28 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A28,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A28,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K29 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A29) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A29) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L29 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A29,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A29,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K30 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A30) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A30) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L30 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A30,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A30,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K31 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A31) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A31) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L31 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A31,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A31,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K32 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A32) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A32) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L32 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A32,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A32,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K33 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A33) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A33) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L33 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A33,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A33,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K34 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A34) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A34) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L34 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A34,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A34,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K35 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A35) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A35) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L35 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A35,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A35,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K36 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A36) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A36) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L36 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A36,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A36,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K37 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A37) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A37) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L37 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A37,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A37,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K38 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A38) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A38) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L38 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A38,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A38,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K39 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A39) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A39) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L39 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A39,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A39,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K40 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A40) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A40) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L40 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A40,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A40,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K41 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A41) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A41) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L41 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A41,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A41,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K42 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A42) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A42) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L42 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A42,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A42,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K43 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A43) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A43) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L43 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A43,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A43,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K44 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A44) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A44) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L44 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A44,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A44,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K45 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A45) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A45) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L45 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A45,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A45,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K46 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A46) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A46) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L46 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A46,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A46,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K47 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A47) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A47) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L47 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A47,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A47,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K48 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A48) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A48) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L48 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A48,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A48,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K49 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A49) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A49) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L49 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A49,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A49,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K50 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A50) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A50) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L50 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A50,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A50,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K51 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A51) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A51) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L51 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A51,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A51,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K52 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A52) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A52) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L52 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A52,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A52,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K53 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A53) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A53) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L53 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A53,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A53,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K54 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A54) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A54) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L54 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A54,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A54,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K55 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A55) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A55) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L55 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A55,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A55,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K56 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A56) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A56) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L56 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A56,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A56,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K57 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A57) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A57) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L57 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A57,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A57,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K58 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A58) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A58) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L58 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A58,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A58,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K59 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A59) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A59) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L59 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A59,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A59,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K60 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A60) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A60) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L60 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A60,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A60,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K61 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A61) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A61) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L61 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A61,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A61,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K62 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A62) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A62) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L62 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A62,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A62,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K63 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A63) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A63) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L63 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A63,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A63,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K64 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A64) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A64) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L64 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A64,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A64,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K65 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A65) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A65) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L65 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A65,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A65,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K66 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A66) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A66) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L66 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A66,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A66,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K67 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A67) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A67) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L67 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A67,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A67,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K68 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A68) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A68) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L68 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A68,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A68,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K69 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A69) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A69) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L69 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A69,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A69,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K70 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A70) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A70) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L70 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A70,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A70,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K71 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A71) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A71) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L71 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A71,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A71,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K72 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A72) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A72) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L72 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A72,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A72,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K73 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A73) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A73) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L73 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A73,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A73,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K74 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A74) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A74) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L74 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A74,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A74,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K75 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A75) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A75) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L75 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A75,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A75,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K76 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A76) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A76) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L76 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A76,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A76,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K77 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A77) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A77) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L77 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A77,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A77,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K78 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A78) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A78) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L78 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A78,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A78,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K79 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A79) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A79) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L79 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A79,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A79,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K80 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A80) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A80) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L80 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A80,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A80,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | K81 | =COUNTIF('Secondary Capability Links'!$B$2:$B$150,A81) | =COUNTIF('Secondary Capability Links'!$B$2:$B$149,A81) | Keep counts on exact regenerated membership extent.
Capability Map v1.1 | L81 | =COUNTIFS('Secondary Capability Links'!$B$2:$B$150,A81,'Secondary Capability Links'!$C$2:$C$150,"Done") | =COUNTIFS('Secondary Capability Links'!$B$2:$B$149,A81,'Secondary Capability Links'!$C$2:$C$149,"Done") | Keep counts on exact regenerated membership extent.
Phase Worker v222 | A1 | Phase × Worker — v2.23.0 ¦ blanks are unknown effort, never zero | Phase × Worker — v2.23.0 ¦ reviewed15Sep2026; not an actual/remaining-hours ledger | Synchronize current metadata/labels with supported evidence or calculation.
Phase Worker v222 | G2 | Known scope h | Usable scope h | Synchronize current metadata/labels with supported evidence or calculation.
Phase Worker v222 | H2 | Known done h | Done scope h | Synchronize current metadata/labels with supported evidence or calculation.
Phase Worker v222 | I2 | Known open h | Open scope h | Synchronize current metadata/labels with supported evidence or calculation.
Phase Worker v222 | J2 | Unestimated rows | Estimate unresolved | Synchronize current metadata/labels with supported evidence or calculation.
Phase Worker v222 | G3 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A3,Backlog!$C$2:$C$180,B3,Backlog!$L$2:$L$180,C3) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A3,Backlog!$C$2:$C$180,B3,Backlog!$L$2:$L$180,C3) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H3 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A3,Backlog!$C$2:$C$180,B3,Backlog!$L$2:$L$180,C3,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A3,Backlog!$C$2:$C$180,B3,Backlog!$L$2:$L$180,C3,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G4 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A4,Backlog!$C$2:$C$180,B4,Backlog!$L$2:$L$180,C4) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A4,Backlog!$C$2:$C$180,B4,Backlog!$L$2:$L$180,C4) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H4 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A4,Backlog!$C$2:$C$180,B4,Backlog!$L$2:$L$180,C4,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A4,Backlog!$C$2:$C$180,B4,Backlog!$L$2:$L$180,C4,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G5 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A5,Backlog!$C$2:$C$180,B5,Backlog!$L$2:$L$180,C5) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A5,Backlog!$C$2:$C$180,B5,Backlog!$L$2:$L$180,C5) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H5 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A5,Backlog!$C$2:$C$180,B5,Backlog!$L$2:$L$180,C5,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A5,Backlog!$C$2:$C$180,B5,Backlog!$L$2:$L$180,C5,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G6 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A6,Backlog!$C$2:$C$180,B6,Backlog!$L$2:$L$180,C6) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A6,Backlog!$C$2:$C$180,B6,Backlog!$L$2:$L$180,C6) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H6 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A6,Backlog!$C$2:$C$180,B6,Backlog!$L$2:$L$180,C6,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A6,Backlog!$C$2:$C$180,B6,Backlog!$L$2:$L$180,C6,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G7 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A7,Backlog!$C$2:$C$180,B7,Backlog!$L$2:$L$180,C7) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A7,Backlog!$C$2:$C$180,B7,Backlog!$L$2:$L$180,C7) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H7 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A7,Backlog!$C$2:$C$180,B7,Backlog!$L$2:$L$180,C7,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A7,Backlog!$C$2:$C$180,B7,Backlog!$L$2:$L$180,C7,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G8 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A8,Backlog!$C$2:$C$180,B8,Backlog!$L$2:$L$180,C8) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A8,Backlog!$C$2:$C$180,B8,Backlog!$L$2:$L$180,C8) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H8 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A8,Backlog!$C$2:$C$180,B8,Backlog!$L$2:$L$180,C8,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A8,Backlog!$C$2:$C$180,B8,Backlog!$L$2:$L$180,C8,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G9 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A9,Backlog!$C$2:$C$180,B9,Backlog!$L$2:$L$180,C9) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A9,Backlog!$C$2:$C$180,B9,Backlog!$L$2:$L$180,C9) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H9 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A9,Backlog!$C$2:$C$180,B9,Backlog!$L$2:$L$180,C9,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A9,Backlog!$C$2:$C$180,B9,Backlog!$L$2:$L$180,C9,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G10 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A10,Backlog!$C$2:$C$180,B10,Backlog!$L$2:$L$180,C10) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A10,Backlog!$C$2:$C$180,B10,Backlog!$L$2:$L$180,C10) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H10 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A10,Backlog!$C$2:$C$180,B10,Backlog!$L$2:$L$180,C10,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A10,Backlog!$C$2:$C$180,B10,Backlog!$L$2:$L$180,C10,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G11 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A11,Backlog!$C$2:$C$180,B11,Backlog!$L$2:$L$180,C11) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A11,Backlog!$C$2:$C$180,B11,Backlog!$L$2:$L$180,C11) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H11 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A11,Backlog!$C$2:$C$180,B11,Backlog!$L$2:$L$180,C11,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A11,Backlog!$C$2:$C$180,B11,Backlog!$L$2:$L$180,C11,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G12 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A12,Backlog!$C$2:$C$180,B12,Backlog!$L$2:$L$180,C12) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A12,Backlog!$C$2:$C$180,B12,Backlog!$L$2:$L$180,C12) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H12 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A12,Backlog!$C$2:$C$180,B12,Backlog!$L$2:$L$180,C12,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A12,Backlog!$C$2:$C$180,B12,Backlog!$L$2:$L$180,C12,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G13 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A13,Backlog!$C$2:$C$180,B13,Backlog!$L$2:$L$180,C13) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A13,Backlog!$C$2:$C$180,B13,Backlog!$L$2:$L$180,C13) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H13 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A13,Backlog!$C$2:$C$180,B13,Backlog!$L$2:$L$180,C13,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A13,Backlog!$C$2:$C$180,B13,Backlog!$L$2:$L$180,C13,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G14 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A14,Backlog!$C$2:$C$180,B14,Backlog!$L$2:$L$180,C14) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A14,Backlog!$C$2:$C$180,B14,Backlog!$L$2:$L$180,C14) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H14 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A14,Backlog!$C$2:$C$180,B14,Backlog!$L$2:$L$180,C14,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A14,Backlog!$C$2:$C$180,B14,Backlog!$L$2:$L$180,C14,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G15 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A15,Backlog!$C$2:$C$180,B15,Backlog!$L$2:$L$180,C15) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A15,Backlog!$C$2:$C$180,B15,Backlog!$L$2:$L$180,C15) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H15 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A15,Backlog!$C$2:$C$180,B15,Backlog!$L$2:$L$180,C15,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A15,Backlog!$C$2:$C$180,B15,Backlog!$L$2:$L$180,C15,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G16 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A16,Backlog!$C$2:$C$180,B16,Backlog!$L$2:$L$180,C16) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A16,Backlog!$C$2:$C$180,B16,Backlog!$L$2:$L$180,C16) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H16 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A16,Backlog!$C$2:$C$180,B16,Backlog!$L$2:$L$180,C16,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A16,Backlog!$C$2:$C$180,B16,Backlog!$L$2:$L$180,C16,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G17 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A17,Backlog!$C$2:$C$180,B17,Backlog!$L$2:$L$180,C17) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A17,Backlog!$C$2:$C$180,B17,Backlog!$L$2:$L$180,C17) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H17 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A17,Backlog!$C$2:$C$180,B17,Backlog!$L$2:$L$180,C17,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A17,Backlog!$C$2:$C$180,B17,Backlog!$L$2:$L$180,C17,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G18 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A18,Backlog!$C$2:$C$180,B18,Backlog!$L$2:$L$180,C18) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A18,Backlog!$C$2:$C$180,B18,Backlog!$L$2:$L$180,C18) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H18 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A18,Backlog!$C$2:$C$180,B18,Backlog!$L$2:$L$180,C18,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A18,Backlog!$C$2:$C$180,B18,Backlog!$L$2:$L$180,C18,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G19 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A19,Backlog!$C$2:$C$180,B19,Backlog!$L$2:$L$180,C19) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A19,Backlog!$C$2:$C$180,B19,Backlog!$L$2:$L$180,C19) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H19 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A19,Backlog!$C$2:$C$180,B19,Backlog!$L$2:$L$180,C19,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A19,Backlog!$C$2:$C$180,B19,Backlog!$L$2:$L$180,C19,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G20 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A20,Backlog!$C$2:$C$180,B20,Backlog!$L$2:$L$180,C20) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A20,Backlog!$C$2:$C$180,B20,Backlog!$L$2:$L$180,C20) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H20 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A20,Backlog!$C$2:$C$180,B20,Backlog!$L$2:$L$180,C20,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A20,Backlog!$C$2:$C$180,B20,Backlog!$L$2:$L$180,C20,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G21 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A21,Backlog!$C$2:$C$180,B21,Backlog!$L$2:$L$180,C21) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A21,Backlog!$C$2:$C$180,B21,Backlog!$L$2:$L$180,C21) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H21 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A21,Backlog!$C$2:$C$180,B21,Backlog!$L$2:$L$180,C21,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A21,Backlog!$C$2:$C$180,B21,Backlog!$L$2:$L$180,C21,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G22 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A22,Backlog!$C$2:$C$180,B22,Backlog!$L$2:$L$180,C22) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A22,Backlog!$C$2:$C$180,B22,Backlog!$L$2:$L$180,C22) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H22 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A22,Backlog!$C$2:$C$180,B22,Backlog!$L$2:$L$180,C22,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A22,Backlog!$C$2:$C$180,B22,Backlog!$L$2:$L$180,C22,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G23 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A23,Backlog!$C$2:$C$180,B23,Backlog!$L$2:$L$180,C23) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A23,Backlog!$C$2:$C$180,B23,Backlog!$L$2:$L$180,C23) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H23 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A23,Backlog!$C$2:$C$180,B23,Backlog!$L$2:$L$180,C23,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A23,Backlog!$C$2:$C$180,B23,Backlog!$L$2:$L$180,C23,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G24 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A24,Backlog!$C$2:$C$180,B24,Backlog!$L$2:$L$180,C24) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A24,Backlog!$C$2:$C$180,B24,Backlog!$L$2:$L$180,C24) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H24 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A24,Backlog!$C$2:$C$180,B24,Backlog!$L$2:$L$180,C24,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A24,Backlog!$C$2:$C$180,B24,Backlog!$L$2:$L$180,C24,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G25 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A25,Backlog!$C$2:$C$180,B25,Backlog!$L$2:$L$180,C25) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A25,Backlog!$C$2:$C$180,B25,Backlog!$L$2:$L$180,C25) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H25 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A25,Backlog!$C$2:$C$180,B25,Backlog!$L$2:$L$180,C25,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A25,Backlog!$C$2:$C$180,B25,Backlog!$L$2:$L$180,C25,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G26 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A26,Backlog!$C$2:$C$180,B26,Backlog!$L$2:$L$180,C26) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A26,Backlog!$C$2:$C$180,B26,Backlog!$L$2:$L$180,C26) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H26 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A26,Backlog!$C$2:$C$180,B26,Backlog!$L$2:$L$180,C26,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A26,Backlog!$C$2:$C$180,B26,Backlog!$L$2:$L$180,C26,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G27 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A27,Backlog!$C$2:$C$180,B27,Backlog!$L$2:$L$180,C27) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A27,Backlog!$C$2:$C$180,B27,Backlog!$L$2:$L$180,C27) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H27 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A27,Backlog!$C$2:$C$180,B27,Backlog!$L$2:$L$180,C27,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A27,Backlog!$C$2:$C$180,B27,Backlog!$L$2:$L$180,C27,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G28 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A28,Backlog!$C$2:$C$180,B28,Backlog!$L$2:$L$180,C28) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A28,Backlog!$C$2:$C$180,B28,Backlog!$L$2:$L$180,C28) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H28 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A28,Backlog!$C$2:$C$180,B28,Backlog!$L$2:$L$180,C28,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A28,Backlog!$C$2:$C$180,B28,Backlog!$L$2:$L$180,C28,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G29 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A29,Backlog!$C$2:$C$180,B29,Backlog!$L$2:$L$180,C29) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A29,Backlog!$C$2:$C$180,B29,Backlog!$L$2:$L$180,C29) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H29 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A29,Backlog!$C$2:$C$180,B29,Backlog!$L$2:$L$180,C29,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A29,Backlog!$C$2:$C$180,B29,Backlog!$L$2:$L$180,C29,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G30 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A30,Backlog!$C$2:$C$180,B30,Backlog!$L$2:$L$180,C30) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A30,Backlog!$C$2:$C$180,B30,Backlog!$L$2:$L$180,C30) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H30 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A30,Backlog!$C$2:$C$180,B30,Backlog!$L$2:$L$180,C30,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A30,Backlog!$C$2:$C$180,B30,Backlog!$L$2:$L$180,C30,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G31 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A31,Backlog!$C$2:$C$180,B31,Backlog!$L$2:$L$180,C31) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A31,Backlog!$C$2:$C$180,B31,Backlog!$L$2:$L$180,C31) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H31 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A31,Backlog!$C$2:$C$180,B31,Backlog!$L$2:$L$180,C31,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A31,Backlog!$C$2:$C$180,B31,Backlog!$L$2:$L$180,C31,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | G32 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A32,Backlog!$C$2:$C$180,B32,Backlog!$L$2:$L$180,C32) | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A32,Backlog!$C$2:$C$180,B32,Backlog!$L$2:$L$180,C32) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Phase Worker v222 | H32 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,A32,Backlog!$C$2:$C$180,B32,Backlog!$L$2:$L$180,C32,Backlog!$K$2:$K$180,"Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,A32,Backlog!$C$2:$C$180,B32,Backlog!$L$2:$L$180,C32,Backlog!$K$2:$K$180,"Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dashboard v222 | A2 | Repaired baseline preserved • 3 UI design tasks added • Design v4.10.3 • No new product completion | 15Sep2026 evidence/cell review • historical closure separated from widened scope • source-history review incomplete | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | E6 | Includes owner-reported T-099 closure | T-099 final terminal transcript corroborated | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | E7 | T-262 remains source-present / unclosed | Partial current scopes; see baseline/extension evidence | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | A9 | Known scope hours | Usable scope estimates | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | B9 | =SUMIF(Backlog!$B$2:$B$180,"M2",Backlog!$J$2:$J$180) | =SUMIF(Backlog!$B$2:$B$180,"M2",Backlog!$AS$2:$AS$180) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dashboard v222 | C9 | =SUMIF(Backlog!$B$2:$B$180,"M3",Backlog!$J$2:$J$180) | =SUMIF(Backlog!$B$2:$B$180,"M3",Backlog!$AS$2:$AS$180) | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dashboard v222 | E9 | Partial sum: eight estimates unresolved | Partial estimate sum; stale and missing figures excluded | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | A10 | Known open hours | Usable open estimates | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | B10 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,"M2",Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,"M2",Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dashboard v222 | C10 | =SUMIFS(Backlog!$J$2:$J$180,Backlog!$B$2:$B$180,"M3",Backlog!$K$2:$K$180,"<>Done") | =SUMIFS(Backlog!$AS$2:$AS$180,Backlog!$B$2:$B$180,"M3",Backlog!$K$2:$K$180,"<>Done") | Use only non-withdrawn planning estimates; keep raw J/R visible in Backlog.
Dashboard v222 | E10 | Not a remaining-time commitment | Scope estimates, not measured hours remaining | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | A11 | Unestimated rows | Estimates unresolved | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | E11 | T-106 / T-108 / T-262–T-267 | 27:8 missing/withdrawn +19 stale-scope figures | Synchronize current metadata/labels with supported evidence or calculation.
Dashboard v222 | A19 | Use v2.23.0. Both earlier v2.22.1 forks are superseded; no product functionality is implied by design-task counts. | v2.23.0 • reviewed15Sep2026. Cell checks do not replace ten-session evidence; see Review15Sep. | Do not overclaim audit completeness.
Estimate Review | F1 | Current hours | Recorded hours (may be stale) | Avoid labelling retained historical numbers current usable hours.
Estimate Review | A10 |  | T-101 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B10 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C10 |  | 2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D10 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E10 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A10,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A10,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F10 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A10,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A10,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G10 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A10,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A10,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A11 |  | T-103 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B11 |  | 6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C11 |  | 0.9 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D11 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E11 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A11,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A11,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F11 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A11,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A11,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G11 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A11,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A11,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A12 |  | T-104 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B12 |  | 14 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C12 |  | 1.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D12 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E12 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A12,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A12,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F12 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A12,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A12,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G12 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A12,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A12,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A13 |  | T-235 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B13 |  | 8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C13 |  | 3.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D13 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E13 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A13,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A13,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F13 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A13,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A13,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G13 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A13,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A13,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A14 |  | T-243 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B14 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C14 |  | 4.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D14 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E14 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A14,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A14,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F14 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A14,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A14,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G14 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A14,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A14,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A15 |  | T-254 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B15 |  | 6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C15 |  | 2.55 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D15 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E15 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A15,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A15,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F15 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A15,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A15,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G15 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A15,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A15,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A16 |  | T-113 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B16 |  | 8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C16 |  | 1.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D16 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E16 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A16,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A16,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F16 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A16,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A16,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G16 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A16,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A16,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A17 |  | T-121 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B17 |  | 16 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C17 |  | 1.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D17 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E17 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A17,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A17,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F17 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A17,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A17,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G17 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A17,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A17,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A18 |  | T-123 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B18 |  | 14 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C18 |  | 3.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D18 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E18 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A18,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A18,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F18 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A18,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A18,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G18 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A18,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A18,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A19 |  | T-110 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B19 |  | 24 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C19 |  | 1.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D19 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E19 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A19,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A19,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F19 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A19,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A19,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G19 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A19,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A19,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A20 |  | T-155 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B20 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C20 |  | 4.32 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D20 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E20 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A20,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A20,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F20 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A20,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A20,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G20 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A20,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A20,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A21 |  | T-159 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B21 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C21 |  | 4.32 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D21 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E21 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A21,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A21,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F21 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A21,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A21,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G21 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A21,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A21,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A22 |  | T-116 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B22 |  | 8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C22 |  | 1.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D22 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E22 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A22,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A22,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F22 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A22,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A22,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G22 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A22,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A22,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A23 |  | T-248 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B23 |  | 30 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C23 |  | 11.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D23 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E23 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A23,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A23,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F23 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A23,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A23,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G23 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A23,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A23,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A24 |  | T-145 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B24 |  | 8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C24 |  | 1.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D24 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E24 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A24,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A24,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F24 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A24,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A24,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G24 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A24,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A24,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A25 |  | T-146 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B25 |  | 10 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C25 |  | 1.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D25 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E25 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A25,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A25,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F25 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A25,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A25,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G25 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A25,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A25,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A26 |  | T-165 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B26 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C26 |  | 7.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D26 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E26 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A26,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A26,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F26 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A26,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A26,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G26 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A26,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A26,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A27 |  | T-186 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B27 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C27 |  | 1.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D27 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E27 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A27,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A27,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F27 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A27,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A27,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G27 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A27,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A27,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | A28 |  | T-190 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | B28 |  | 12 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | C28 |  | 2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | D28 |  | STALE SCOPE — retained in Backlog J/R as historical figures; not valid for current widened scope or remaining-time forecast. | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | E28 |  | =IF(INDEX(Backlog!$L$2:$L$180,MATCH($A28,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$L$2:$L$180,MATCH($A28,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | F28 |  | =IF(INDEX(Backlog!$J$2:$J$180,MATCH($A28,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$J$2:$J$180,MATCH($A28,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Estimate Review | G28 |  | =IF(INDEX(Backlog!$AR$2:$AR$180,MATCH($A28,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$AR$2:$AR$180,MATCH($A28,Backlog!$A$2:$A$180,0))) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C2 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A2,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A2,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A2,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D2 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A2,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A2,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A2,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C3 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A3,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A3,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A3,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D3 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A3,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A3,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A3,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C4 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A4,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A4,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A4,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D4 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A4,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A4,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A4,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C5 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A5,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A5,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A5,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D5 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A5,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A5,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A5,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C6 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A6,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A6,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A6,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D6 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A6,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A6,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A6,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C7 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A7,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A7,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A7,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D7 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A7,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A7,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A7,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C8 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A8,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A8,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A8,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D8 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A8,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A8,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A8,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C9 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A9,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A9,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A9,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D9 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A9,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A9,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A9,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C10 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A10,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A10,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A10,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D10 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A10,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A10,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A10,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C11 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A11,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A11,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A11,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D11 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A11,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A11,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A11,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C12 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A12,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A12,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A12,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D12 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A12,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A12,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A12,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C13 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A13,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A13,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A13,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D13 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A13,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A13,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A13,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C14 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A14,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A14,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A14,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D14 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A14,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A14,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A14,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C15 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A15,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A15,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A15,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D15 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A15,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A15,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A15,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C16 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A16,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A16,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A16,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D16 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A16,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A16,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A16,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C17 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A17,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A17,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A17,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D17 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A17,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A17,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A17,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C18 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A18,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A18,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A18,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D18 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A18,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A18,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A18,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C19 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A19,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A19,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A19,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D19 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A19,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A19,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A19,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C20 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A20,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A20,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A20,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D20 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A20,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A20,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A20,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C21 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A21,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A21,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A21,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D21 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A21,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A21,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A21,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C22 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A22,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A22,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A22,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D22 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A22,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A22,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A22,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C23 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A23,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A23,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A23,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D23 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A23,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A23,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A23,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C24 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A24,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A24,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A24,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D24 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A24,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A24,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A24,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C25 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A25,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A25,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A25,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D25 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A25,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A25,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A25,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C26 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A26,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A26,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A26,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D26 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A26,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A26,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A26,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C27 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A27,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A27,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A27,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D27 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A27,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A27,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A27,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C28 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A28,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A28,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A28,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D28 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A28,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A28,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A28,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C29 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A29,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A29,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A29,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D29 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A29,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A29,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A29,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C30 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A30,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A30,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A30,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D30 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A30,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A30,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A30,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C31 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A31,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A31,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A31,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D31 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A31,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A31,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A31,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C32 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A32,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A32,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A32,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D32 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A32,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A32,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A32,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C33 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A33,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A33,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A33,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D33 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A33,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A33,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A33,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C34 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A34,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A34,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A34,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D34 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A34,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A34,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A34,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C35 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A35,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A35,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A35,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D35 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A35,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A35,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A35,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C36 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A36,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A36,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A36,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D36 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A36,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A36,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A36,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C37 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A37,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A37,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A37,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D37 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A37,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A37,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A37,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C38 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A38,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A38,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A38,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D38 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A38,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A38,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A38,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C39 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A39,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A39,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A39,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D39 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A39,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A39,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A39,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C40 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A40,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A40,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A40,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D40 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A40,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A40,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A40,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C41 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A41,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A41,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A41,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D41 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A41,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A41,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A41,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C42 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A42,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A42,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A42,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D42 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A42,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A42,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A42,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C43 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A43,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A43,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A43,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D43 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A43,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A43,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A43,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C44 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A44,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A44,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A44,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D44 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A44,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A44,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A44,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C45 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A45,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A45,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A45,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D45 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A45,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A45,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A45,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C46 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A46,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A46,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A46,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D46 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A46,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A46,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A46,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A47 | T-254 | T-261 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B47 | L1.4 | L3.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C47 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A47,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A47,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A47,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D47 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A47,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A47,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A47,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B48 | L3.8 | L2.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C48 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A48,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A48,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A48,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D48 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A48,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A48,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A48,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A49 | T-261 | T-262 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B49 | L2.6 | L2.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C49 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A49,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A49,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A49,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D49 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A49,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A49,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A49,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B50 | L2.3 | L3.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C50 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A50,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A50,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A50,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D50 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A50,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A50,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A50,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A51 | T-262 | T-215 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B51 | L3.6 | L3.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C51 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A51,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A51,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A51,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D51 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A51,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A51,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A51,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A52 | T-215 | T-258 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C52 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A52,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A52,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A52,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D52 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A52,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A52,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A52,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A53 | T-258 | T-168 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B53 | L3.4 | L8.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C53 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A53,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A53,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A53,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D53 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A53,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A53,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A53,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A54 | T-168 | T-180 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B54 | L8.4 | L4.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C54 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A54,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A54,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A54,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D54 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A54,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A54,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A54,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A55 | T-180 | T-181 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B55 | L4.5 | L5.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C55 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A55,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A55,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A55,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D55 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A55,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A55,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A55,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A56 | T-181 | T-182 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B56 | L5.8 | L4.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C56 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A56,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A56,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A56,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D56 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A56,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A56,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A56,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B57 | L4.5 | L4.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C57 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A57,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A57,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A57,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D57 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A57,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A57,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A57,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A58 | T-182 | T-211 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B58 | L4.8 | L5.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C58 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A58,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A58,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A58,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D58 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A58,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A58,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A58,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A59 | T-211 | T-221 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B59 | L5.3 | L5.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C59 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A59,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A59,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A59,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D59 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A59,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A59,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A59,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A60 | T-221 | T-223 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B60 | L5.5 | L10.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C60 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A60,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A60,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A60,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D60 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A60,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A60,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A60,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B61 | L10.3 | L9.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C61 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A61,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A61,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A61,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D61 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A61,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A61,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A61,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A62 | T-223 | T-236 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B62 | L9.1 | L4.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C62 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A62,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A62,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A62,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D62 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A62,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A62,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A62,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B63 | L4.2 | L10.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C63 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A63,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A63,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A63,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D63 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A63,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A63,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A63,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A64 | T-236 | T-115 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B64 | L10.3 | L8.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C64 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A64,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A64,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A64,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D64 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A64,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A64,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A64,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A65 | T-115 | T-121 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B65 | L8.2 | L7.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C65 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A65,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A65,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A65,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D65 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A65,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A65,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A65,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A66 | T-121 | T-123 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B66 | L7.4 | L8.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C66 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A66,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A66,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A66,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D66 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A66,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A66,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A66,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A67 | T-123 | T-125 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B67 | L8.3 | L1.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C67 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A67,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A67,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A67,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D67 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A67,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A67,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A67,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A68 | T-125 | T-126 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B68 | L1.7 | L8.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C68 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A68,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A68,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A68,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D68 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A68,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A68,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A68,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A69 | T-126 | T-257 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B69 | L8.8 | L8.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C69 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A69,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A69,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A69,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D69 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A69,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A69,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A69,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A70 | T-257 | T-110 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B70 | L8.2 | L8.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C70 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A70,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A70,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A70,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D70 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A70,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A70,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A70,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A71 | T-110 | T-152 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B71 | L8.4 | L8.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C71 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A71,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A71,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A71,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D71 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A71,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A71,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A71,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A72 | T-152 | T-153 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B72 | L8.8 | L1.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C72 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A72,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A72,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A72,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D72 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A72,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A72,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A72,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A73 | T-153 | T-155 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B73 | L1.4 | L8.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C73 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A73,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A73,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A73,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D73 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A73,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A73,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A73,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A74 | T-155 | T-159 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B74 | L8.4 | L8.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C74 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A74,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A74,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A74,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D74 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A74,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A74,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A74,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A75 | T-159 | T-162 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B75 | L8.5 | L7.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C75 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A75,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A75,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A75,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D75 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A75,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A75,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A75,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A76 | T-162 | T-156 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B76 | L7.5 | L2.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C76 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A76,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A76,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A76,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D76 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A76,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A76,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A76,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A77 | T-156 | T-248 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B77 | L2.2 | L3.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C77 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A77,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A77,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A77,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D77 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A77,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A77,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A77,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B78 | L3.1 | L3.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C78 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A78,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A78,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A78,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D78 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A78,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A78,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A78,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B79 | L3.3 | L3.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C79 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A79,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A79,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A79,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D79 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A79,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A79,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A79,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B80 | L3.4 | L3.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C80 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A80,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A80,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A80,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D80 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A80,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A80,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A80,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B81 | L3.5 | L3.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C81 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A81,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A81,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A81,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D81 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A81,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A81,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A81,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B82 | L3.6 | L3.9 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C82 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A82,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A82,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A82,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D82 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A82,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A82,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A82,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B83 | L3.9 | L6.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C83 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A83,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A83,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A83,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D83 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A83,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A83,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A83,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A84 | T-248 | T-263 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B84 | L6.7 | L2.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C84 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A84,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A84,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A84,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D84 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A84,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A84,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A84,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B85 | L2.6 | L6.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C85 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A85,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A85,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A85,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D85 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A85,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A85,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A85,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A86 | T-263 | T-128 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B86 | L6.4 | L9.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C86 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A86,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A86,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A86,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D86 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A86,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A86,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A86,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A87 | T-128 | T-129 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B87 | L9.5 | L4.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C87 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A87,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A87,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A87,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D87 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A87,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A87,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A87,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B88 | L4.2 | L4.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C88 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A88,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A88,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A88,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D88 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A88,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A88,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A88,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A89 | T-129 | T-134 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B89 | L4.4 | L3.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C89 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A89,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A89,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A89,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D89 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A89,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A89,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A89,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A90 | T-134 | T-141 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B90 | L3.4 | L8.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C90 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A90,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A90,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A90,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D90 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A90,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A90,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A90,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A91 | T-141 | T-144 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B91 | L8.6 | L9.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C91 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A91,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A91,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A91,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D91 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A91,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A91,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A91,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A92 | T-144 | T-145 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B92 | L9.4 | L9.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C92 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A92,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A92,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A92,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D92 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A92,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A92,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A92,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B93 | L9.6 | L6.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C93 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A93,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A93,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A93,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D93 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A93,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A93,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A93,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B94 | L6.4 | L9.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C94 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A94,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A94,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A94,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D94 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A94,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A94,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A94,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A95 | T-145 | T-147 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B95 | L9.8 | L4.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C95 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A95,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A95,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A95,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D95 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A95,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A95,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A95,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A96 | T-147 | T-157 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B96 | L4.2 | L4.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C96 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A96,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A96,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A96,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D96 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A96,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A96,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A96,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B97 | L4.4 | L4.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C97 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A97,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A97,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A97,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D97 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A97,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A97,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A97,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A98 | T-157 | T-165 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B98 | L4.7 | L7.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C98 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A98,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A98,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A98,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D98 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A98,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A98,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A98,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A99 | T-165 | T-183 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B99 | L7.7 | L5.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C99 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A99,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A99,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A99,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D99 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A99,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A99,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A99,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A100 | T-183 | T-186 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B100 | L5.5 | L4.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C100 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A100,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A100,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A100,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D100 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A100,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A100,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A100,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A101 | T-186 | T-187 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B101 | L4.8 | L4.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C101 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A101,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A101,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A101,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D101 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A101,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A101,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A101,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B102 | L4.5 | L4.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C102 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A102,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A102,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A102,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D102 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A102,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A102,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A102,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A103 | T-187 | T-188 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B103 | L4.8 | L4.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C103 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A103,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A103,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A103,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D103 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A103,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A103,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A103,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B104 | L4.1 | L4.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C104 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A104,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A104,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A104,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D104 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A104,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A104,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A104,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A105 | T-188 | T-189 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B105 | L4.2 | L3.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C105 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A105,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A105,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A105,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D105 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A105,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A105,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A105,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A106 | T-189 | T-190 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B106 | L3.4 | L9.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C106 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A106,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A106,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A106,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D106 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A106,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A106,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A106,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B107 | L9.3 | L9.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C107 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A107,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A107,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A107,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D107 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A107,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A107,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A107,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A108 | T-190 | T-192 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B108 | L9.4 | L4.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C108 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A108,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A108,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A108,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D108 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A108,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A108,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A108,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B109 | L4.3 | L4.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C109 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A109,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A109,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A109,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D109 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A109,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A109,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A109,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B110 | L4.8 | L5.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C110 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A110,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A110,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A110,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D110 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A110,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A110,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A110,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A111 | T-192 | T-193 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B111 | L5.8 | L4.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C111 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A111,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A111,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A111,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D111 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A111,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A111,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A111,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A112 | T-193 | T-238 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B112 | L4.8 | L10.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C112 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A112,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A112,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A112,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D112 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A112,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A112,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A112,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A113 | T-238 | T-240 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B113 | L10.1 | L6.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C113 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A113,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A113,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A113,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D113 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A113,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A113,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A113,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A114 | T-240 | T-246 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B114 | L6.2 | L4.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C114 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A114,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A114,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A114,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D114 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A114,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A114,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A114,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B115 | L4.2 | L4.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C115 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A115,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A115,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A115,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D115 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A115,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A115,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A115,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A116 | T-246 | T-264 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B116 | L4.7 | L9.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C116 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A116,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A116,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A116,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D116 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A116,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A116,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A116,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B117 | L9.1 | L4.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C117 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A117,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A117,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A117,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D117 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A117,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A117,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A117,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A118 | T-264 | T-167 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B118 | L4.6 | L8.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C118 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A118,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A118,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A118,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D118 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A118,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A118,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A118,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A119 | T-167 | T-265 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B119 | L8.8 | L1.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C119 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A119,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A119,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A119,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D119 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A119,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A119,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A119,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B120 | L1.1 | L1.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C120 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A120,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A120,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A120,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D120 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A120,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A120,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A120,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B121 | L1.2 | L1.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C121 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A121,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A121,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A121,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D121 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A121,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A121,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A121,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B122 | L1.3 | L1.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C122 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A122,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A122,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A122,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D122 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A122,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A122,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A122,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B123 | L1.7 | L2.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C123 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A123,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A123,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A123,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D123 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A123,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A123,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A123,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B124 | L2.2 | L2.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C124 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A124,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A124,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A124,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D124 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A124,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A124,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A124,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B125 | L2.3 | L2.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C125 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A125,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A125,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A125,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D125 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A125,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A125,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A125,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B126 | L2.6 | L2.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C126 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A126,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A126,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A126,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D126 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A126,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A126,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A126,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B127 | L2.7 | L3.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C127 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A127,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A127,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A127,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D127 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A127,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A127,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A127,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B128 | L3.2 | L3.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C128 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A128,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A128,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A128,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D128 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A128,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A128,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A128,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B129 | L3.3 | L3.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C129 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A129,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A129,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A129,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D129 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A129,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A129,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A129,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B130 | L3.5 | L3.6 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C130 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A130,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A130,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A130,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D130 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A130,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A130,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A130,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B131 | L3.6 | L3.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C131 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A131,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A131,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A131,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D131 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A131,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A131,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A131,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B132 | L3.7 | L5.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C132 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A132,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A132,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A132,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D132 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A132,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A132,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A132,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B133 | L5.2 | L6.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C133 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A133,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A133,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A133,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D133 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A133,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A133,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A133,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B134 | L6.1 | L6.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C134 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A134,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A134,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A134,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D134 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A134,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A134,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A134,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A135 | T-265 | T-266 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B135 | L6.7 | L1.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C135 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A135,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A135,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A135,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D135 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A135,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A135,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A135,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B136 | L1.4 | L1.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C136 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A136,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A136,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A136,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D136 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A136,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A136,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A136,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B137 | L1.1 | L1.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C137 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A137,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A137,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A137,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D137 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A137,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A137,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A137,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B138 | L1.5 | L6.8 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C138 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A138,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A138,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A138,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D138 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A138,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A138,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A138,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A139 | T-266 | T-267 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B139 | L6.8 | L3.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C139 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A139,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A139,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A139,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D139 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A139,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A139,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A139,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B140 | L3.1 | L3.2 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C140 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A140,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A140,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A140,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D140 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A140,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A140,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A140,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B141 | L3.2 | L3.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C141 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A141,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A141,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A141,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D141 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A141,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A141,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A141,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B142 | L3.3 | L3.9 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C142 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A142,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A142,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A142,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D142 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A142,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A142,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A142,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B143 | L3.9 | L6.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C143 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A143,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A143,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A143,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D143 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A143,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A143,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A143,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B144 | L6.5 | L6.7 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C144 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A144,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A144,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A144,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D144 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A144,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A144,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A144,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B145 | L6.7 | L7.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C145 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A145,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A145,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A145,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D145 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A145,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A145,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A145,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B146 | L7.4 | L9.3 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C146 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A146,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A146,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A146,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D146 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A146,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A146,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A146,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B147 | L9.3 | L9.5 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C147 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A147,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A147,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A147,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D147 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A147,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A147,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A147,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B148 | L9.5 | L10.1 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C148 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A148,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A148,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A148,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D148 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A148,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A148,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A148,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B149 | L10.1 | L10.4 | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C149 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A149,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A149,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$K$2:$K$180,MATCH(A149,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D149 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A149,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A149,Backlog!$A$2:$A$180,0))) | =INDEX(Backlog!$B$2:$B$180,MATCH(A149,Backlog!$A$2:$A$180,0)) | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | A150 | T-267 |  | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | B150 | L10.4 |  | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | C150 | =IF(INDEX(Backlog!$K$2:$K$180,MATCH($A150,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$K$2:$K$180,MATCH($A150,Backlog!$A$2:$A$180,0))) |  | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Secondary Capability Links | D150 | =IF(INDEX(Backlog!$B$2:$B$180,MATCH($A150,Backlog!$A$2:$A$180,0))="","",INDEX(Backlog!$B$2:$B$180,MATCH($A150,Backlog!$A$2:$A$180,0))) |  | Derived-view/estimate membership or explicitly added review metadata; no task-order join. | See Review15Sep and source-bound Task Evidence15Sep.
Book Validation | A1 | Check | 14Sep book-consolidation check (historical) | Old PASS values were true of the prior consolidation, not this new cell audit.
Book Validation | F1 | Preserved task totals | Current task totals (formula) | Live counters distinguished from historical checks.
Backlog | K2 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J2 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R2 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K3 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J3 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R3 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K4 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J4 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R4 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K5 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J5 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R5 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K6 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J6 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R6 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K7 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J7 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R7 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K8 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J8 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R8 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K9 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J9 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R9 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K10 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J10 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R10 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K11 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J11 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R11 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K12 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J12 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R12 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K13 [FORMAT] | Source style index 100 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J13 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R13 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K14 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J14 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R14 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K15 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J15 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R15 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K16 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J16 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R16 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K17 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J17 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R17 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K18 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J18 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R18 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K19 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J19 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R19 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K20 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J20 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R20 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K21 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J21 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R21 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K22 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J22 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R22 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K23 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J23 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R23 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K24 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J24 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R24 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K25 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J25 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R25 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K26 [FORMAT] | Source style index 104 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J26 [FORMAT] | Source style index 108 | Saved style index 273 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R26 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K27 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J27 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R27 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K28 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J28 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R28 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K29 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J29 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R29 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K30 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J30 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R30 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K31 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J31 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R31 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K32 [FORMAT] | Source style index 202 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J32 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R32 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K33 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J33 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R33 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K34 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J34 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R34 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K35 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J35 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R35 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K36 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J36 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R36 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K37 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J37 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R37 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K38 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J38 [FORMAT] | Source style index 198 | Saved style index 274 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R38 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K39 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J39 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R39 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K40 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J40 [FORMAT] | Source style index 198 | Saved style index 274 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R40 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K41 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J41 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R41 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K42 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J42 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R42 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K43 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J43 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R43 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K44 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J44 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R44 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K45 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J45 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R45 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K46 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J46 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R46 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K47 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J47 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R47 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K48 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J48 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R48 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K49 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J49 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R49 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K50 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J50 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R50 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K51 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J51 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R51 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K52 [FORMAT] | Source style index 104 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J52 [FORMAT] | Source style index 108 | Saved style index 273 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R52 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K53 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J53 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R53 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K54 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J54 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R54 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K55 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J55 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R55 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K56 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J56 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R56 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K57 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J57 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R57 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K58 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J58 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R58 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K59 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J59 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R59 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K60 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J60 [FORMAT] | Source style index 198 | Saved style index 274 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R60 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K61 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J61 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R61 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K62 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J62 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R62 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K63 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J63 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R63 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K64 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J64 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R64 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K65 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J65 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R65 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K66 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J66 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R66 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K67 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J67 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R67 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K68 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J68 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R68 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K69 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J69 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R69 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K70 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J70 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R70 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K71 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J71 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R71 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K72 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J72 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R72 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K73 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J73 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R73 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K74 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J74 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R74 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K75 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J75 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R75 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K76 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J76 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R76 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K77 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J77 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R77 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K78 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J78 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R78 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K79 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J79 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R79 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K80 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J80 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R80 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K81 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J81 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R81 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K82 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J82 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R82 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K83 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J83 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R83 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K84 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J84 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R84 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K85 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J85 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R85 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K86 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J86 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R86 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K87 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J87 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R87 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K88 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J88 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R88 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K89 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J89 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R89 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K90 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J90 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R90 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K91 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J91 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R91 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K92 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J92 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R92 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K93 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J93 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R93 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K94 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J94 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R94 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K95 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J95 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R95 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K96 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J96 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R96 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K97 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J97 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R97 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K98 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J98 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R98 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K99 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J99 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R99 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K100 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J100 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R100 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K101 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J101 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R101 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K102 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J102 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R102 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K103 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J103 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R103 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K104 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J104 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R104 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K105 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J105 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R105 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K106 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J106 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R106 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K107 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J107 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R107 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K108 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J108 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R108 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K109 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J109 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R109 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K110 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J110 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R110 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K111 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J111 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R111 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K112 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J112 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R112 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K113 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J113 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R113 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K114 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J114 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R114 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K115 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J115 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R115 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K116 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J116 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R116 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K117 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J117 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R117 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K118 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J118 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R118 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K119 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J119 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R119 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K120 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J120 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R120 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K121 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J121 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R121 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K122 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J122 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R122 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K123 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J123 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R123 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K124 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J124 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R124 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K125 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J125 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R125 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K126 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J126 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R126 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K127 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J127 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R127 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K128 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J128 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R128 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K129 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J129 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R129 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K130 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J130 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R130 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K131 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J131 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R131 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K132 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J132 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R132 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K133 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J133 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R133 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K134 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J134 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R134 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K135 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J135 [FORMAT] | Source style index 198 | Saved style index 274 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R135 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K136 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J136 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R136 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K137 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J137 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R137 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K138 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J138 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R138 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K139 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J139 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R139 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K140 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J140 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R140 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K141 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J141 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R141 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K142 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J142 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R142 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K143 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J143 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R143 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K144 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J144 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R144 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K145 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J145 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R145 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K146 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J146 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R146 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K147 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J147 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R147 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K148 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J148 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R148 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K149 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J149 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R149 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K150 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J150 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R150 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K151 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J151 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R151 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K152 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J152 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R152 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K153 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J153 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R153 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K154 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J154 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R154 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K155 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J155 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R155 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K156 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J156 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R156 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K157 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J157 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R157 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K158 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J158 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R158 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K159 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J159 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R159 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K160 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J160 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R160 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K161 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J161 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R161 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K162 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J162 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R162 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K163 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J163 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R163 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K164 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J164 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R164 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K165 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J165 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R165 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K166 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J166 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R166 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K167 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J167 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R167 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K168 [FORMAT] | Source style index 98 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J168 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R168 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K169 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J169 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R169 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K170 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J170 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R170 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K171 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J171 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R171 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K172 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J172 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R172 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K173 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J173 [FORMAT] | Source style index 106 | Saved style index 271 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R173 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K174 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J174 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R174 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K175 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J175 [FORMAT] | Source style index 198 | Saved style index 274 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R175 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K176 [FORMAT] | Source style index 104 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J176 [FORMAT] | Source style index 108 | Saved style index 273 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R176 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K177 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J177 [FORMAT] | Source style index 107 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R177 [FORMAT] | Source style index 195 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K178 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J178 [FORMAT] | Source style index 101 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R178 [FORMAT] | Source style index 101 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K179 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J179 [FORMAT] | Source style index 101 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R179 [FORMAT] | Source style index 101 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | K180 [FORMAT] | Source style index 101 | Saved style index 270 | Status fill now follows status text through four conditional rules; static color removed. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | J180 [FORMAT] | Source style index 101 | Saved style index 272 | Estimate number formatting and unusable-estimate conditional highlight. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | R180 [FORMAT] | Source style index 101 | Saved style index 272 | P80 formatting; unusable estimate amber; missing inherited P80 violet. | Style index is package-local, not evidence of semantic change by itself; saved CF ranges verified.
Backlog | Conditional formatting | B2:B166;K2:K166;K2:K173;Y2:Y168 | K2:K180;B2:B180;J2:J180;R2:R180;AR2:AR180 | Replace overlapping/truncated groups with full-range current rules. | Independent OOXML read-back.
Backlog | Data validations | 5 overlapping/truncated categorical ranges | K2:K180;B2:B180;C2:C180;J2:J180;R2:R180;AR2:AR180 | 6 non-overlapping full-range validations; last task rows included. | Independent OOXML read-back.
Backlog | AU1:BB180 | No implementation-specific remaining estimate columns | 51 linked source reviews + low/base/high remainder; 128 explicit unreviewed | Separate actual remaining scope from historical task Hours/P80 | Source Review; Source Evidence; 14-Sep snapshot
Backlog | H153 | Use the schema-independent statistical kernel from T-177 to converge the runtime onto one readiness-gated engine and retire the direct-SQL/superseded compute paths. Persist method, aligned population/group sizes, effect size, p-value, FDR/q-value, gate evidence and truthful exclusion reason. This is the production wiring/cutover task; do not perform it before M1 presentation continuity is frozen. v2.22.0 — Converge production statistical methods and discipline onto the accepted authorities; absorb/retire duplicate StatisticalDiscipline code only after all consumer and test obligations move. No performance/style-only rewrite. | Use the schema-independent statistical kernel from T-177 to converge the runtime onto one readiness-gated engine and retire the direct-SQL/superseded compute paths. Persist method, aligned population/group sizes, effect size, p-value, FDR/q-value, gate evidence and truthful exclusion reason. This is the production wiring/cutover task; do not perform it before M1 presentation continuity is frozen. v2.22.0 — Converge production statistical methods and discipline onto the accepted authorities; StatisticalDiscipline.cs contains currently consumed EffectRanking, BenjaminiHochberg, Stratification and Bootstrap functions and is not dead code. Converge only measured duplicate execution authorities after consumer and test obligations move; preserve these live discipline functions. No performance/style-only rewrite. | Withdraw unsupported dead-file diagnosis; preserve live discipline functions | ManagedStatisticalComputeEngine.cs:91-115; AdvancedCorrelationComputeService.cs:117-137
M2-P2 Review | A1:N35 | History-only bounded review | All 34 P2 source traces, remaining scope and estimates | Source-level audit requested by owner | 51-record Source Review data, Task ID lookup
Task Evidence 15Sep | 51 Task-ID selected rows | Historical-only conclusion | Implementation evidence and remaining scope | Do not erase original closures or claim new runtime tests | Source Evidence
Estimate Review | A32:H84 | No current remaining breakdown | 51 proposed low/base/high remaining work estimates | Budget estimates unconfirmed; not P80 or actual hours | Bottom-up work packages; overlapping ownership separated
Current Authority | B11:D17 | Previous cell-review coverage | New source-review/estimate boundaries | Explicit coverage and limitations | Source Summary
Backlog | CurrentBacklogTable | A1:AT180 | A1:BB180 | Include new linked columns without shifting task rows | Task-ID alignment checks on final XLSX
Review 15Sep | F10;H10 | No new remaining estimates | Source proposals now available, unconfirmed | Preserve old audit while disclosing new work | Source Review
Backlog | K33 | [['Not Started']] | In Progress | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AO33 | [['Not started — no completion claimed']] | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AP33 | [['Inherited v2.22.0 intended record; no new runtime certification in this repair.']] | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. Expected Runner-2 parent (not an observed commit parent): 4e0f1219ddbac3163bafe7ce510b62520683a77c | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | T33 | [['Use the accepted M1 regression baseline; require empty index and clean owned paths, preserving unrelated user work. Then: T-099 canonical quarantine table/API and first eight PV classes.']] | RUNNER-1 CANDIDATE IS PRESENT; DO NOT RERUN RUNNER 1 or require a clean owned tree relative to HEAD. Resume from the exact handoff/postimages. Resume v1.0.1 is issued; success is not yet reported. Validate HEAD against the handoff and all owned postimage hashes before continuing. Expected parent supplied for closure is 4e0f1219ddbac3163bafe7ce510b62520683a77c; do not substitute the older T-099-only HEAD. If the exact gates fail, stop and report without manual resets, cleanup of unrelated work, or a fresh mutation pack. Worker 1/CENTRAL retains the execution lock through T-100 final commit; Worker 2 remains held. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | U33 | [['Own canonical DB/backend/security/API/infra. No W2-owned UI/admin task files and no W3 ML/Assistant runtime.']] | Worker 1 is the recorded execution owner; CENTRAL-assisted delivery. Preserve the existing T-100 candidate and unrelated dirty work. Exclusive shared repository mutation lock until T-100 is committed. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | V33 | [['Commit before downstream consumer starts; consumer must use the contract, not redesign producer-owned semantics.']] | Release Worker 2 only after T-100 final commit SHA and closure evidence. The successor consumes PROJECTION_* declaration, PV01..PV15 row-validation and JOB_EXEC_* runtime boundaries without duplication. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | I33 | [['Fifteen fixtures, fifteen codes, fifteen passing tests. A test that enumerates the PV enum and fails if any member has no fixture.']] | Distinct governed validation codes and fixture coverage must equal PV01..PV15 exactly. At least 15 classification fixtures; additional regression fixtures for an existing code are allowed. The completeness ratchet fails for an unproved enum member, not for duplicate display names or extra same-code tests. Live PostgreSQL proof executes every PV class; PV15 quarantine→cross-batch reference arrival→bounded reprocess passes; PV13 .60+.40=1.00 must not be quarantined. Exact live constraint, canonical migration order, disposable cleanup and exact single-commit closure required. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AR33 | [['INHERITED ESTIMATE']] | RE-ESTIMATE REQUIRED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AJ33 | [['Inherited baseline estimate']] | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AY33 | [['UNCONFIRMED REVIEW ESTIMATE - not P80 or elapsed']] | UNCONFIRMED — closure-only remaining effort; prior 6/10/16 h superseded | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | BB33 | [['14-Sep-2026 snapshot; later closure evidence separate; no live HEAD verification']] | 14-Sep snapshot supplemented by latest 15-Sep user-reported runner progress; no current-HEAD or runner-byte verification | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | M59 | [['T-106; T-241; T-242; T-243; T-099; T-262']] | T-106; T-241; T-242; T-243; T-099; T-262; T-100 | Latest CENTRAL order makes T-100 final commit the explicit predecessor of T-261 | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | N33 | [['T-101; T-107; T-109; T-128; T-183']] | T-101; T-107; T-109; T-128; T-183; T-261 | Reciprocal of T-100→T-261 dependency, keyed by Task ID | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | T59 | [['Consume accepted producer contracts; remaining dependencies: T-106; T-241; T-242; T-243; T-099; T-262. No private scheduler/definition authority. Source-present is not closure proof.\n\nv2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns.']] | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AO59 | [['In progress — closure not recorded']] | SEMANTIC CONTRACT/PACKAGE IN PROGRESS; HOST MUTATION HELD PENDING T-100 COMMIT | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AP59 | [['Inherited v2.22.0 intended record; no new runtime certification in this repair.']] | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | U59 | [['Own the governed Transformation/Projection executor, job-runtime adapter/evidence seam and targeted tests. Do not redesign Canvas authoring, T-106 capability authority, scheduling, definition lifecycle or frontend UX.']] | Worker 2 owns executor/runtime work, but holds no mutation permission until T-100 commits. Preserve the shared producer frontier; one bounded delta only after the final SHA. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | V59 | [['T-245 consumes the committed executor. Stable board.nodes[].id remains canonical block identity; T-106 remains the job capability/target/version authority.']] | After T-100 commits: one bounded delta, then T-261 Runner 1/2; after T-261 closes proceed to T-245. No second compiler, capability policy, run store or block-evidence authority. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | T55 | [['Consume accepted producer contracts; remaining dependencies: T-243; T-244; T-106; T-261. No private scheduler/definition authority. Source-present is not closure proof.\n\nv2.22.1 — Completion prerequisites are the task IDs in column M; contract-only predecessors, if any, are exclusively in column AN. Do not use the rejected v2.22.0 positional columns.']] | QUEUED after T-261 closure; current mutation sequence is T-099 → T-100 → T-261 → T-245. T-245 consumes the proven executor/runtime and per-block evidence, never recreates them. Retain all listed canonical prerequisite contracts. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Backlog | AO55 | [['PREFLIGHT EXECUTED; IMPLEMENTATION NOT STARTED / BLOCKED']] | QUEUED — T-261 NOT CLOSED; NO NEW IMPLEMENTATION OR LIVE RUN CLAIM | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | B7 | [['FIRST EIGHT PRESENT; REMAINING EXECUTION NOT ESTABLISHED']] | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | C7 | [['The shared row projector, refusal model, quarantine storage and first-eight-PV tests already exist. Production ProjectionValidationCode call-site census in the supplied backend contains PV01–PV08; enum/catalogue presence alone is not PV09–PV15 execution.']] | Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | D7 | [['Implement and prove remaining seven PV outcomes using the existing projector/context/quarantine boundary, with positive and per-code negative cases and inherited-boundary regressions.']] | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | E7 | [['Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership\nBackend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern']] | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | Preserve prior source findings while recording later reported progress | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | F7 | [[6]] | UNCONFIRMED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | G7 | [[10]] | UNCONFIRMED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | H7 | [[16]] | UNCONFIRMED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | I7 | [['Remaining validators 3/5/8 + per-class tests 2/4/6 + packaging/closure 1/1/2. No new quarantine engine.']] | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | J7 | [[None]] | Latest update is reported evidence, not a fresh source/host read. Live classification failed to start; it did not establish a PV product failure. Resume v1.0.1's fix is issued but not verified here. No new commit SHA. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | K7 | [[None]] | T-099 remains CLOSED GREEN at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af; T-100 Runner 1 completed by report, final closure pending. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | L7 | [['T-099 closed; no duplicate declaration/runtime failure vocabulary from T-261/T-262.']] | Worker 1/CENTRAL owns the current mutation lock. T-261/Worker 2 waits for T-100 commit. Existing candidate must be preserved; no duplicate projector or PV authority. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | B33 | [['CONTRACTS PRESENT; EXECUTOR NOT APPLIED IN PROVIDED SNAPSHOT']] | CONTRACTS PRESENT; EXECUTOR NOT APPLIED IN PROVIDED SNAPSHOT LATEST: HELD PENDING T-100 COMMIT | Preserve prior source findings while recording later reported progress | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | C33 | [['The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit.']] | The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit. Latest user report retains the semantic design but forbids host mutation until T-100 SHA. No new applied T-261 candidate is evidenced here. | Preserve prior source findings while recording later reported progress | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | L33 | [['Do not implement a new schedule or PV taxonomy. Common cancellation seam billed once here; T-106 handles policy/endpoint coordination.']] | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Review | J33 | [[None]] | Latest reset supersedes old T-099→T-261→T-100 sequencing. StorageTopologyMap/manifest must be read during the single post-T100 delta; no migration number fixed now. | Preserve prior source findings while recording later reported progress | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | C7 | [['Not Started']] | In Progress | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | D7 | [['The shared row projector, refusal model, quarantine storage and first-eight-PV tests already exist. Production ProjectionValidationCode call-site census in the supplied backend contains PV01–PV08; enum/catalogue presence alone is not PV09–PV15 execution.']] | Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | E7 | [['Implement and prove remaining seven PV outcomes using the existing projector/context/quarantine boundary, with positive and per-code negative cases and inherited-boundary regressions.']] | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | J7 | [['REVIEW PROPOSAL — NOT CONFIRMED / NOT P80']] | UNCONFIRMED — closure-only; 6/10/16 h superseded | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | K7 | [['Inherited v2.22.0 intended record; no new runtime certification in this repair.']] | Runner 1 reported GREEN; later fresh DB/constraint passed; live harness failed before classification; final commit not yet supplied. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | L7 | [['Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership\nBackend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern']] | USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | M7 | [['T-099 closed; no duplicate declaration/runtime failure vocabulary from T-261/T-262.']] | Worker 1/CENTRAL lock → T-100 final SHA → Worker 2 T-261 → T-245. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | N7 | [['14-Sep-2026 supplied repository snapshot; later verified session evidence cited separately; No .NET/product DB/browser suite executed in this continuation; test source and cited historical executions distinguished.']] | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | M33 | [['Do not implement a new schedule or PV taxonomy. Common cancellation seam billed once here; T-106 handles policy/endpoint coordination.']] | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
M2-P2 Review | M29 | [['T-261 owns executor and block-evidence storage, T-106 schedule/outcome policy; do not count those implementations again.']] | T-245 is QUEUED after T-261 accepted closure; no separate executor, block-evidence model or capability authority. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | D33 | [['FIRST EIGHT PRESENT; REMAINING EXECUTION NOT ESTABLISHED']] | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | E33 | [['Accepted workbook state retained; no new task-specific closure recovered. This is not proof that no work happened.']] | Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | F33 | [['The shared row projector, refusal model, quarantine storage and first-eight-PV tests already exist. Production ProjectionValidationCode call-site census in the supplied backend contains PV01–PV08; enum/catalogue presence alone is not PV09–PV15 execution.\nREMAINS: Implement and prove remaining seven PV outcomes using the existing projector/context/quarantine boundary, with positive and per-code negative cases and inherited-boundary regressions.']] | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | H33 | [['Proposed remaining 6/10/16 h, UNCONFIRMED; historical J/R unchanged.']] | Prior 6/10/16 h superseded; closure-only effort UNCONFIRMED. Reported implementation and unit gates are not charged again. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | J33 | [['Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership\nBackend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern']] | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | K33 | [['HISTORICAL PRESENTATION WAIT REPLACED BY CURRENT BASELINE/GATE WORDING']] | Previous Not Started and PV01..PV08-only current-state wording superseded by reported Runner-1 implementation. No Done/commit inference. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | L33 | [['\nT-099 closed; no duplicate declaration/runtime failure vocabulary from T-261/T-262.\nRuntime/complete-session proof still not executed/recovered here.']] | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | D59 | [['CONTRACTS PRESENT; EXECUTOR NOT APPLIED IN PROVIDED SNAPSHOT']] | HOST MUTATION HELD — T-100 final commit required | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | F59 | [['The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit.\nREMAINS: Extract/reuse the compiler; implement resolver+executor, carry the pre-admission target into the real run, canonical row effects/idempotency/provenance and stable block evidence, common cancellation/status wiring; run Graph/SQL and failure/cancel proof on disposable DB. Include T-262 live Gate 0 once.']] | The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit. REMAINS: Extract/reuse the compiler; implement resolver+executor, carry the pre-admission target into the real run, canonical row effects/idempotency/provenance and stable block evidence, common cancellation/status wiring; run Graph/SQL and failure/cancel proof on disposable DB. Include T-262 live Gate 0 once. HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance. | Preserve prior source findings while recording later reported progress | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | L59 | [['\nDo not implement a new schedule or PV taxonomy. Common cancellation seam billed once here; T-106 handles policy/endpoint coordination.\nRuntime/complete-session proof still not executed/recovered here.']] | Do not implement a new schedule or PV taxonomy. Common cancellation seam billed once here; T-106 handles policy/endpoint coordination. Runtime/complete-session proof still not executed/recovered here. One bounded delta only after T-100 final SHA; no interim mutation or final migration allocation. | Preserve prior source findings while recording later reported progress | Latest owner-supplied runner/hold update; no new live execution claimed
Task Evidence 15Sep | I59 | [['=TEXTJOIN("; ",TRUE,IF(INDEX(Backlog!$K$2:$K$180,MATCH("T-099",Backlog!$A$2:$A$180,0))="Done","","T-099"),IF(INDEX(Backlog!$K$2:$K$180,MATCH("T-106",Backlog!$A$2:$A$180,0))="Done","","T-106"),IF(INDEX(Backlog!$K$2:$K$180,MATCH("T-241",Backlog!$A$2:$A$180,0))="Done","","T-241"),IF(INDEX(Backlog!$K$2:$K$180,MATCH("T-242",Backlog!$A$2:$A$180,0))="Done","","T-242"),IF(INDEX(Backlog!$K$2:$K$180,MATCH("T-243",Backlog!$A$2:$A$180,0))="Done","","T-243"),IF(INDEX(Backlog!$K$2:$K$180,MATCH("T-262",Backlog!$A$2:$A$180,0))="Done","","T-262"))']] | T-262 | Derived from current saved task/evidence inputs | Latest owner-supplied runner/hold update; no new live execution claimed
Estimate Review | B39 | [['FIRST EIGHT PRESENT; REMAINING EXECUTION NOT ESTABLISHED']] | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Estimate Review | F39 | [['Remaining validators 3/5/8 + per-class tests 2/4/6 + packaging/closure 1/1/2. No new quarantine engine.\nT-099 closed; no duplicate declaration/runtime failure vocabulary from T-261/T-262.']] | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Estimate Review | G39 | [['Implement and prove remaining seven PV outcomes using the existing projector/context/quarantine boundary, with positive and per-code negative cases and inherited-boundary regressions.']] | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Estimate Review | H39 | [['Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership\nBackend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern']] | Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | A27 | [[None]] | T-261 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | B27 | [[None]] | T-100 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | C27 | [[None]] | M2 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | D27 | [[None]] | M2 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | E27 | [[None]] | COMPLETION + MUTATION LOCK — NOT CONTRACT-ONLY | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | F27 | [[None]] | Final T-100 commit SHA; exact closure/cleanup evidence; then one bounded delta over shared producer/runtime/migration surfaces. PROJECTION_* / PV01..PV15 / JOB_EXEC_* boundaries preserved. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Contract Handoffs | G27 | [[None]] | HELD — Runner 1 GREEN and DB build reported; live certification/commit not yet supplied. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D4 | [['Same task/scope version. This review corrects evidence, current labels, estimate usability and formatting; no tasks/releases/dependency edges added or removed.']] | Same v2.23.0 task/scope version. Latest owner-reported runner progress and CENTRAL sequence are recorded. T-100→T-261 predecessor and reciprocal link updated by Task ID; no new task, feature, release or Design change. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B11 | [['27 historical estimates not usable; 51 remaining-work proposals now recorded']] | 28 historical scope estimates unusable; 51 reviews, 50 numeric remainder proposals + 1 unpriced closure remainder | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D11 | [['J/R and historical AS/AT preserved. AV:AX are source-derived low/base/high remaining engineer-hour proposals, UNCONFIRMED and NOT P80; unreviewed work remains blank, not zero.']] | T-100 historical J/R retained but unusable; previous 6/10/16 remaining proposal is superseded by reported implementation. UNCONFIRMED closure-only remainder excluded from numerical subtotals, not zero. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | A19 | [[None]] | Current mutation order | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B19 | [[None]] | T-099 → T-100 → T-261 → T-245 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | C19 | [[None]] | Latest owner update /15-Sep-2026 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D19 | [[None]] | Supersedes T-099→T-261→T-100; Worker 2 held pending final T-100 SHA. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | A20 | [[None]] | T-100 stage | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B20 | [[None]] | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | C20 | [[None]] | USER-REPORTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D20 | [[None]] | Not independently rerun or source-verified; no T-100 commit recorded. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | A21 | [[None]] | T-261 permission | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B21 | [[None]] | HELD PENDING T-100 COMMIT | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | C21 | [[None]] | Worker 2 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D21 | [[None]] | No host mutation/final anchors/migration number. One bounded delta only after SHA. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | A22 | [[None]] | Latest issued recovery artifact | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B22 | [[None]] | Resume-ProjectionQuarantineCompletion_1.0.1.ps1 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | C22 | [[None]] | Not executed/verified here | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D22 | [[None]] | 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | A23 | [[None]] | T-100 expected closure parent | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B23 | [[None]] | 4e0f1219ddbac3163bafe7ce510b62520683a77c | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | C23 | [[None]] | EXPECTED, NOT OBSERVED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D23 | [[None]] | Verify against Runner-1 handoff/current HEAD. Do not overwrite an actual commit/parent ledger until commit occurs. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | A24 | [[None]] | Evidence distinction | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | B24 | [[None]] | DB bootstrap/constraint is not live classification | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | C24 | [[None]] | USER-REPORTED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Current Authority | D24 | [[None]] | 110/110 SQL and 264 tables reported; harness stopped before live fixtures. Cleanup means certification DB must be rebuilt by recovery runner. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A2 | [['v2.23.0 maintained · Source snapshot 14-Sep-2026 · review 15-Sep-2026 · NOT live-HEAD or release certification']] | v2.23.0 maintained · 14-Sep source snapshot + latest 15-Sep USER-REPORTED T-100 runner progress · not live-HEAD certification | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A3 | [['51 scoped source assessments: all 34 M2-P2 + 17 other changed-estimate tasks. Full transcripts of the ten named sessions remain unavailable.']] | 51 source assessments remain; T-100 updated from later reported runner progress. 50 have numeric remainder proposals; T-100 closure-only remainder is UNCONFIRMED. Full ten-session coverage remains incomplete. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B7 | [['=COUNT(Backlog!$AW$2:$AW$180)']] | 51 | Derived from current saved task/evidence inputs | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | E6 | [['Task set and current status preserved']] | 179 tasks retained; T-100 Not Started→In Progress only | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | E9 | [['Reviewed subset only; focused nominal engineer-hours']] | Incomplete subtotal; excludes T-100 UNCONFIRMED closure remainder and unreviewed tasks | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | E10 | [['Unconfirmed work breakdown, NOT measured AI P80']] | Not a release forecast or P80; excludes unpriced T-100 remainder | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | E11 | [['Includes uncertainty; excludes site waits/elapsed soak']] | Does not bound T-100 closure effort; estimate not supplied | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A12 | [['Originally invalid/missing estimates reviewed']] | Unusable historical scope estimates with source review | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A15 | [['Low/base/high are new engineering review proposals for remaining work, not recovered session facts, owner-confirmed estimates or elapsed time.']] | Numeric low/base/high values remain unconfirmed engineering proposals. T-100's previous 6/10/16 was superseded by reported implementation and is now UNCONFIRMED closure-only, not zero. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A19 | [["The supplied repository dump is dated 14-Sep. Changes on the user's machine after that snapshot cannot be inferred from this workbook."]] | Source dump remains 14-Sep. Later T-100 progress is owner-reported, not inspected live source. No inference that issued recovery scripts already passed. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A34 | [['23 saved-XLSX checks passed; 3 injected faults detected. OPEN items are stated below and are not converted to PASS.']] | Historical validation below concerns the prior source-review artifact; current runner-update validation is recorded from row 70. Historical checks are not re-claimed as fresh product proof. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A53 | [['M2-P2 totals 194 / 316 / 511']] | HISTORICAL: M2-P2 estimates before T-100 runner update = 194/316/511 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C53 | [['Saved XLSX read-back']] | Prior source-review XLSX, not current totals | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A54 | [['Review totals 416 / 694 / 1133']] | HISTORICAL: all reviewed estimates before T-100 update = 416/694/1133 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C54 | [['Saved XLSX read-back']] | Prior source-review XLSX, not current totals | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A55 | [['Statuses retained 58/5/116']] | HISTORICAL: statuses before T-100 update = 58/5/116 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C55 | [['Saved XLSX read-back']] | Prior source-review XLSX, not current counts | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D66 | [['51 remaining-work estimates are unconfirmed proposals, not calibrated P80.']] | 50 numeric remainder proposals remain unconfirmed; T-100 closure-only remainder is unpriced. Historical Hours/P80 are not remaining work. | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A70 | [[None]] | LATEST T-100 RUNNER / LOCK UPDATE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B70 | [[None]] | Result | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C70 | [[None]] | Evidence class | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D70 | [[None]] | Detail | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A71 | [[None]] | 179 tasks / M2 107 / M3 72 retained | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B71 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C71 | [[None]] | Workbook structure | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D71 | [[None]] | No task/release changes | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A72 | [[None]] | Current status counts | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B72 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C72 | [[None]] | Workbook values | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D72 | [[None]] | 58 Done / 6 In Progress / 115 Not Started | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A73 | [[None]] | T-100 progress, not closure | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B73 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C73 | [[None]] | User report recorded | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D73 | [[None]] | Runner1 GREEN, build/constraint passed; live harness blocked; no commit invented | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A74 | [[None]] | T-100→T-261 and reciprocal edge | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B74 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C74 | [[None]] | Current owner instruction | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D74 | [[None]] | Backlog, Dependency Graph and Worker Tracks must agree by Task ID | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A75 | [[None]] | No self edges / cycles / M2-on-M3 | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B75 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C75 | [[None]] | Workbook dependency checks | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D75 | [[None]] | Five external prerequisite IDs retained | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A76 | [[None]] | T-099 frozen record preserved | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B76 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C76 | [[None]] | Preserved closure evidence | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D76 | [[None]] | Commit/parent/status unchanged | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A77 | [[None]] | T-100 proposed remainder | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B77 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C77 | [[None]] | Forecast hygiene | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D77 | [[None]] | UNCONFIRMED; prior 6/10/16 kept in change history; unknown is not zero | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A78 | [[None]] | Current M2-P2 numeric subtotal | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B78 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C78 | [[None]] | Incomplete subtotal | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D78 | [[None]] | 188/306/495, PLUS unknown T-100 closure effort | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A79 | [[None]] | Current reviewed numeric subtotal | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B79 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C79 | [[None]] | Incomplete subtotal | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D79 | [[None]] | 410/684/1117, PLUS unknown T-100 closure effort | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A80 | [[None]] | Source-review coverage | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B80 | [[None]] | CHECK ON SAVED FILE | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C80 | [[None]] | Assessment count, not time count | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D80 | [[None]] | 51 reviewed scopes; 34 M2-P2; 128 still unreviewed | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | A81 | [[None]] | Latest recovery runner execution | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | B81 | [[None]] | NOT OBSERVED | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | C81 | [[None]] | Explicit runtime boundary | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed
Source Summary | D81 | [[None]] | Resume v1.0.1 issued by report; success not reported and no script executed here | Latest user-supplied T-100/T-261 runner report and CENTRAL sequencing reset | Latest owner-supplied runner/hold update; no new live execution claimed

## Source Review
Task ID | Source verdict | Current implementation | Remaining scope | Code evidence | Remaining low h | Remaining base h | Remaining high h | Estimate basis | Risks / qualification | Historical scope | Ownership boundary
T-095 | SOURCE CORROBORATES CLOSED FOUNDATION | RelationshipService already validates ordered composite members, join/cardinality vocabulary and grain attribution, publishes through the store and returns read-back. The existing relationship infrastructure is real and must not be recreated. | No new implementation within the accepted original task scope is established here. Canvas publication wiring is owned by the later T-243 addition, not reopening this foundation. | Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — PublishAsync Backend/PlantProcess.Application/Relationships/RelationshipService.cs:218-260 — ValidateDeclaration | 0 | 0 | 0 | Closed original scope; zero remaining here does not certify downstream Canvas integration. |  | 554d1ac02af122fdeb7ca54b1dd35bac0c76f23e — subject not recovered | T-243 consumes existing publication authority.
T-096 | SOURCE CORROBORATES CLOSED FOUNDATION | RelationshipResolver reads the published model, finds deterministic shortest/preferred paths, refuses ambiguous or missing paths and prevents automated use of unvalidated relationships. Existing join-planner consumers should be retained. | No new work is assigned to this closed convergence slice. Live downstream execution remains a separate consumer acceptance and is not proven by this source read. | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:34-113 — ResolveAsync Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-96 — ConsumerFamilies | 0 | 0 | 0 | Original resolver/convergence closure retained; no rebuilding cost. |  | de243027073fc5e492d65e9f9845255342517510 — T-096 relationship resolver consumer convergence
T-097 | SOURCE CORROBORATES CLOSED GUARD | The permanent consumer barrier names sixteen families and forbids private path authority while allowing intrinsic owning-key navigation. It explicitly covers future engine directories too: a barrier is not proof that all engines are commissioned. | Keep the original barrier task closed. New consumers must pass it; their runtime wiring belongs to their own integration tasks. | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:12-44 — barrier semantics Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs:55-114 — consumer and forbidden-authority inventory | 0 | 0 | 0 | No remaining original implementation; avoid counting unwired later engines against this completed guard. |  | 95220d1804493f8e7b80347fe3ed4de24741f9ec — T-097 relationship consumer barrier across all sixteen families
T-098 | REUSABLE BACKEND PRESENT; CANONICAL UI NOT LOCATED | The relationship API already exposes list, entities, detail and validation, and the resolver/publication services exist. The reviewed frontend route/page sources contain no canonical Relationship Browser implementation. This is a UI/consumer task, not new relationship storage. | Build C6 list/detail/path/validation views against existing services, including ambiguity, preferred-path and refusal evidence; add frontend/API-contract tests and one runtime acceptance. | Backend/PlantProcess.Api/Endpoints/Relationships/RelationshipEndpoints.cs:21-92 — MapRelationshipEndpoints Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:62-113 — path results | 6 | 9 | 14 | UI 4/6/9 + contract/negative tests 1/2/3 + targeted closure 1/1/2. Reuse all relationship producer work. |  |  | Do not duplicate T-095..T-097 or charge their work here.
T-099 | CLOSED SCOPE PRESERVED; SOURCE CORROBORATES | MappingRowProjector contains PV01–PV08 row classification, existing-row replay behavior, shared mapping context and quarantine reprocess integration. Later owner-supplied closure and recovered transcript report the exact semantic commit and live targeted tests. | Zero remaining inside T-099's closed first-eight-PV scope. PV09–PV15, full replay/update semantics, monitoring and exact weight semantics remain with T-100/T-101/T-104/T-103. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:141-181 — MapMaterialUnitAsync Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — bounded reprocess surface Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:3-20 — narrow topology correction | 0 | 0 | 0 | T-099 CLOSED GREEN at ca02b40e; its inherited DefinitionKind RED is not a reason to budget a rewrite. |  | ca02b40ea1b69050a45cb35a3e1d64f15b1f66af; parent 86e1b677212195f191697ecdca7e9441b3dbde33; 49/49,5/5,19/19; Gate O 899+1 inherited.
T-100 | RUNNER 1 GREEN REPORTED / DB BUILD PASSED / LIVE HARNESS BLOCKED / UNCOMMITTED | Reported Runner 1 v1.0.5 completed: Backend build GREEN, integration-project build GREEN, 20/20 targeted unit tests, PPIQ_T100_RUNNER1_HANDOFF.json written; no staging, commit or DB mutation in Runner 1. Later certification reportedly executed 110/110 canonical SQL scripts, built a fresh disposable DB with 264 tables, and verified the constraint is exactly PV01..PV15. That run failed in harness setup BEFORE live classification; its disposable certification DB was cleaned up. No T-100 commit or live PV01..PV15 pass has been supplied. | Use the issued Resume v1.0.1 against the existing verified Runner-1 handoff/postimages; do not rerun Runner 1. Rebuild the cleaned disposable certification DB, verify all actual fixture PPIQ_* environment inputs, execute live PV01..PV15 coverage (additional same-code regression fixtures allowed), prove PV15 quarantine→reference arrival→bounded reprocess, and prove the PV13 .60+.40 valid case. Run the completeness and canonical-migration-order gates; prove named disposable cleanup/zero survivors and protected-database safety; exact owned staging, one semantic commit, expected-parent/path-set/index/owned/unrelated proof. Resume outcome is NOT YET REPORTED. | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-13 — ownership Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:630-690 — existing validation pattern Latest owner-supplied conversation update, received 15-Sep-2026; runner/host logs and script bytes were not independently inspected in this workbook update. This supersedes the earlier 14-Sep source-only T-100 estimate, not the frozen Design. USER-REPORTED: Runner1_1.0.5 SHA256 75B6C7DE78E0A677701BFEDF1EC70D4D1499C8168193B35D503CF26DF76DC7AA; Runner2_1.0.0 SHA256 9C29E607B52114DE680131A0FDE0F840D7CC56D3642FA09F73FD2AB5A7B3D493; Resume-ProjectionQuarantineCompletion_1.0.1.ps1 SHA256 5F6668258E8CAC517793B825AF712C8D8C9355F8CE9C0C69FBC5CAFCBDCB80E6. Names/hashes recorded as supplied, NOT locally verified. Script hashes are not commit IDs. | UNCONFIRMED | UNCONFIRMED | UNCONFIRMED | SUPERSEDED: prior remaining LOW/BASE/HIGH 6/10/16 h included validators and unit tests now reported complete. Do not charge that implementation again. Closure-only remaining effort (harness recovery, live certification, cleanup, commit proof) is UNCONFIRMED, not zero; no invented elapsed time or calibrated P80. Preserve J/R as historical scope values, excluded from usable totals. | Latest update is reported evidence, not a fresh source/host read. Live classification failed to start; it did not establish a PV product failure. Resume v1.0.1's fix is issued but not verified here. No new commit SHA. | T-099 remains CLOSED GREEN at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af; T-100 Runner 1 completed by report, final closure pending. | Worker 1/CENTRAL owns the current mutation lock. T-261/Worker 2 waits for T-100 commit. Existing candidate must be preserved; no duplicate projector or PV authority.
T-101 | PARTIAL REUSE; CURRENT EXPANDED SCOPE OPEN | POST /api/quarantine/reprocess and row-level reprocess service exist; the endpoint explicitly leaves list/detail/Mapping Health to T-101. Existing C2/import views are reusable scaffolding, not the complete PV/drift/retry monitoring flow. | Add bounded list/detail by code/dataset/batch and source lineage, extend the existing reprocess path, persist/display mapped-column drift, and B4 batch/error/durable-cursor monitoring. Validate API, UI and failure recovery. | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs:8-33 — MapQuarantineEndpoints Backend/PlantProcess.Application/Integration/Services/Staging/StagingRecordService.cs:85-110 — durable staging identity | 12 | 18 | 28 | Read API/filter/detail 3/4/6 + B4/C2/C3 UI 4/6/10 + drift/retry integration 3/5/8 + tests/closure 2/3/4. |  |  | T-106 owns run-outcome semantics; T-125 owns operational data/health; do not bill those twice.
T-102 | EXISTING ALIAS FOUNDATION; IDENTITY-SAFETY GAP | material_aliases storage and uniqueness exist. MappingRowProjector creates aliases and resolves a supplied alias, but resolves by AliasCode alone and selects the first material; material-code lookup similarly omits SiteId despite per-site uniqueness. Automatic collision-safe cross-source identity is not complete. | Reuse alias persistence; resolve by governed tenant/site/source/key scope, refuse ambiguity, reconcile two source identifiers into one material and prove idempotent re-import with same alias text across sources/sites. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:244-264 — MapMaterialAliasAsync Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:721-744 — ResolveMaterialIdAsync Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialAliasConfiguration.cs:27-36 — composite unique Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialUnitConfiguration.cs:43-47 — site/source uniqueness | 4 | 7 | 12 | Scope-safe lookup/merge 2/4/7 + ambiguity/idempotency tests 1/2/4 + closure 1/1/1. | Source-proven ambiguity mechanism: storage permits shared AliasCode across materials/sources; reader selects first by alias alone. No live wrong-material incident asserted. |  | Do not recreate alias tables or the full row projector.
T-103 | SUBSTANTIAL FOUNDATION; ACCEPTANCE-CONTRACT MISMATCH | GenealogyService already rejects self-edges, duplicate edges and cycles by traversal. Migration 841 repairs the deferred weight trigger's schema binding while deliberately preserving its old tolerance. The effective predicate uses abs(sum-1)>0.015, so 0.99 passes that predicate although this task requires rejection. | Retain cycle/self-edge implementation; prove DB direct-write cycle controls and both traversal directions, then reconcile exact declared weight semantics with the 0.015 inherited tolerance and add the explicit 0.99 negative case. | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:27-69 — CreateEdgeAsync Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs:95-124 — WouldCreateCycleAsync Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql:55-68 — deferred weight check | 4 | 6 | 10 | Weight-contract correction 1/2/3 + direct-DB/traversal negatives 2/3/5 + closure 1/1/2. Existing cycle logic is not new work. | Confirmed predicate counterexample: abs(0.99-1)=0.01 is not greater than 0.015. T-099 preserved this deliberately; this does not reopen T-099. |  | Weight semantics/negative acceptance stay T-103; 841 topology repair remains accepted.
T-104 | REPLAY FOUNDATION IS NOT VERSIONED REPROJECTION | The current projector skips an already existing MaterialUnit by site/code; it is not a proof that a changed mapping re-materializes previous output. Run history has resolved-target storage, but the existing orchestrator discards the resolver result before dispatch. | On top of the T-261 executor, prove canonical row/run version provenance, idempotent accepted effects and rollback-to-version business equivalence. Reuse first-eight-PV/quarantine infrastructure; do not implement a second executor. | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:168-181 — existing-row skip Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-249 — ResolveDeclaredTargetAsync | 8 | 14 | 22 | Row-version/provenance integration 3/5/8 + replay/rollback semantics 3/6/10 + negative tests/closure 2/3/4. |  |  | T-261 owns first resolved-target runtime call and executor; T-104 owns row effects and rollback proof after it.
T-106 | ORIGINAL CONTRACT CLOSED; EXPANDED RUNTIME OBLIGATIONS OPEN | Target capability admission, target resolver, real blocked-run evidence, dependency traversal and historical foundation/corrective commits exist. Current source still validates schedules only as nonblank text, runs fixed worker loops, lacks Cancelled in the enum/runtime completion switch, accepts freshness without an age argument and can mark mixed failed batches Ok. | Implement the v4.10.3 schedule contract/parser/due dispatch, explicit freshness policy, truthful aggregate outcomes and cancellation coordination. Reuse the original target/DAG work; T-261 commissions the shared executor/cancellation seam and this task consumes it, not a competing runtime. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobDefinitionService.cs:275-297 — schedule validation Backend/PlantProcess.Workers/Worker.cs:72-108 — fixed cadence loops Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:33-39 — no age/tolerance input Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs:85-91 — Satisfied result Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-146 — terminal-state switch Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:262-276 — import result mapping | 18 | 28 | 44 | Schedule/parser/due-work 8/12/18 + freshness/outcome policy 4/6/10 + cancellation consumer integration 2/4/6 + targeted service/DB tests and runner 4/6/10. Original completed contracts excluded. | Confirmed source boundaries, not executed incidents. No Cancelled result currently persists through CompleteAsync. No false claim that the original T-106 runner failed. | Original target/dependency contract has 8b3eb5c8 foundation and a5451dba corrective; their closure scope is not new schedule/cancel/freshness implementation. Preserve historical evidence; evaluate the later expanded scope separately. | T-261 owns executor implementation, first RecordResolvedTarget and common cancellation seam. T-106 owns schedule/DAG/outcome semantics; no double estimate of executor.
T-107 | TIMERS EXIST; GOVERNED JOB POOLS NOT ESTABLISHED | The Worker has staggered timers and sequential awaits for import, data-quality, risk and delta. Separate telemetry buffers use bounded channels, but are not weighted job pools. Existing capability admission decides executability, not job-slot AND resource-capacity admission. | Add actual bounded job queues/pool slots and dual-predicate resource admission, isolation of three ML lanes, backpressure and exact cancellation/release behavior; test saturation and interactive reservation without inventing production capacity constants. | Backend/PlantProcess.Workers/Worker.cs:72-108 — ExecuteAsync cadence Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:76-107 — family capability vs capacity | 12 | 20 | 32 | Pool/admission implementation 6/10/16 + lane/worker integration 3/5/8 + saturation/cancel/closure tests 3/5/8. |  |  | T-155/T-159 calibrate heavy-production constants later; no retraining or new scheduler here.
T-108 | IMPLEMENTED DELTA FOUNDATION WITH CONFIRMED CORRECTNESS GAPS | A real delta reader/importer, row envelope and cursor persistence already exist; generic bulk staging rejects duplicate batch/source/row entries. The delta path directly creates a fresh batch/rows and uses a scalar cursor. The PostgreSQL query uses strict > plus LIMIT, MaxCursor parses under ambient culture, and incremental reads bypass the wrapper budget while GetBudget ignores profile/dataset. | Implement total-order cursor/tie-key semantics for every supported incremental reader, typed invariant comparisons, per-source effective budget on incremental calls, durable checkpoint/replay identity and projection watermark handoff. Do not recreate source/staging infrastructure already present. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — read-path selection Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — row/cursor handling Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:236-280 — source identity and MaxCursor Backend/PlantProcess.Infrastructure/Connectors/PostgreSql/PostgreSqlConnector.cs:181-206 — scalar LIMIT query Backend/PlantProcess.Application/Integration/Protection/ThrottlingDataSourceReader.cs:36-70 — unequal protection Backend/PlantProcess.Infrastructure/Integration/Protection/OptionsSourceLoadBudgetProvider.cs:21-24 — global budget Backend/PlantProcess.Infrastructure/Persistence/Configurations/Integration/StagingRecordConfiguration.cs:31-42 — existing within-batch uniqueness Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:58-73 — current weak continuation assertions | 22 | 34 | 52 | Tuple contract+reader adaptations 8/12/18 + budget enforcement 4/6/9 + durable staging/replay+projection token 5/8/13 + adverse-boundary tests/closure 5/8/12. | The old test checks only returned JSON array shape, not cursor values/exact IDs. Generic bulk-insert dedupe is not proof of delta-path cross-batch replay safety. Confirmed PostgreSQL tie mechanism; other providers require their own tests. |  | T-106 owns Job aggregate status; T-101 B4 UI; T-109 consumes this watermark; no duplicate billing for those consumers.
T-109 | REUSABLE CALCULATION FOUNDATION; DELTA CONSUMER NOT PROVEN | The repository has source-delta infrastructure, ML refresh paths and pure analytical kernels, but the inspected analytical service paths do not show a commissioned consumer of the designed feature_refresh/analysis_scope watermark chain. Existing calculation code is reusable, not proof of bounded changed-entity execution. | Consume T-108's committed batch/delta token, materialize changed subjects through governed relations, refresh bounded feature/analysis scope and telemetry, and emit the ML handoff. Prove late data and interrupted retries without a second cursor store. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-217 — available source delta boundary Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs:85-113 — governed automated path | 6 | 10 | 18 | Scope resolution/integration 3/5/9 + telemetry/handoff 1/2/4 + idempotent/late-data tests 2/3/5. |  |  | T-108 owns source/projection checkpoint; M3 materializers own full training artifacts.
T-207 | SOURCE CORROBORATES CLOSED TRUTH CONTRACT | HistorianConnectorCapabilities explicitly declares real browse/read/subscription/session operations unavailable and returns named capability truth. This is a real honest-refusal foundation, not a production OPC implementation. | No original T-207 reimplementation. New backend provider-list convergence belongs to expanded T-254; live OPC operations belong to T-224..T-226. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — HistorianConnectorCapabilities | 0 | 0 | 0 | Closed honesty contract retained; separate future live acquisition. |  | Not recovered from reviewed sessions
T-212 | AUTHORITY EXISTS; PRODUCTION QUERY CONSUMPTION GAP | SignalSemanticsResolver already resolves aggregation through the governed database function with AG01/type refusal and a DI registration. Current production reference census finds its definition/implementation/registration, but no widget/query service injection/call. Frontend aggregate binding copies declared metadata; it performs no analytics. | Wire the existing semantics authority into Layer-A widget/query execution and consume the T-211 arithmetic contract. Preserve declared weighting/sampling/null rules, typed refusals and result evidence; do not implement a new aggregation authority. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — ResolveAsync Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — not analytics mathematics | 6 | 9 | 14 | Query integration 3/5/8 + known-answer/refusal tests 2/3/4 + closure 1/1/2. |  |  | T-211 computes math; T-210 governs semantics; T-212 wires actual queries.
T-213 | SOURCE CORROBORATES CLOSED PRODUCER | CustomerAssessmentEndpoints exposes authorized assess/latest/version/diff operations and resolves tenant identity before service work. The service/normalization/history migration and tests are present. This is a reusable assessment authority, not an autonomous ingestion/projection executor. | No new work within the accepted T-213 authority scope. Customer intake use within the real UI journey remains the consumer's acceptance, not reopening this producer. | Backend/PlantProcess.Api/Endpoints/CustomerAssessmentEndpoints.cs:86-125 — assessment routes and tenant gate | 0 | 0 | 0 | Original producer closure retained; no duplicate intake engine. |  | 2748c7fba8a5c4763bc19112ce57e484cea5b9bb — subject not recovered
T-224 | CONFIGURATION FOUNDATION ONLY; LIVE SESSION UNCOMMISSIONED | The current OPC connector only validates supplied endpoint/read-only configuration and explicitly refuses a requested live handshake. The separate capability authority says session security/certificate/trust handling is not implemented; there is no evidence that the advertised target session is commissioned. | Implement real read-only OPC endpoint/session/certificate lifecycle on the customer-side collector, with governed trust references, security-policy rejection, reconnect and safe telemetry. Reuse configuration/capability contracts, not their success text as handshake proof. | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration test Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — live capability declarations | 10 | 16 | 26 | Session/client/trust implementation 5/8/13 + collector lifecycle 2/4/7 + negative/security/closure tests 3/4/6. Vendor access delays excluded. |  |  | T-225 browse/subscription; T-226 end-to-end data/recovery; T-266 design. No M3 deferral.
T-225 | LIVE ACQUISITION OPERATIONS NOT COMMISSIONED | Current truth explicitly marks tag browse, bounded value read and subscriptions unimplemented. The UI and supplied-tag hints do not establish real namespace traversal or monitored-item persistence. Session support is T-224's prerequisite. | Build namespace browse, stable node identities, tag registration, bounded read/subscriptions and monitored-item lifecycle using the T-224 session and source-load policy; test partial browse, disconnect and invalid intervals. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:76-95 — browse/read/subscription capability state Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:53-70 — metadata-only legacy claim | 10 | 16 | 26 | Browse/registration 3/5/8 + monitored-item/read lifecycle 4/6/10 + limits/refusal/closure tests 3/5/8. |  |  | Do not recreate session security or count T-266 graphics as real read proof.
T-226 | SPOOL/TIME FOUNDATIONS; LIVE END-TO-END PROOF MISSING | Historian mapping/legacy tag-history and edge-spool scaffolding exist, while real upstream OPC read/subscription operations remain unavailable. Those existing interfaces are useful but do not prove quality/timestamp preservation or replay into canonical data from a live session. | Integrate source/server/ingest time and quality handling, spool/ack/reconnect/gap recovery and idempotent canonical replay using T-233/T-224/T-225; run controlled interruption and real-source evidence. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:84-95 — upstream live-operation boundary Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — existing time kernel | 10 | 16 | 28 | Quality/time/canonical adapter 3/5/9 + spool/ack/recovery 4/6/11 + interruption/replay acceptance 3/5/8. |  |  | No new time-authority kernel; no reuse of demo telemetry as customer-source proof.
T-232 | TARGET AUTHORITY NOT LOCATED IN SUPPLIED SNAPSHOT | The supplied snapshot includes signal semantics and ordinary limits/parameter storage, but no production Performance Reference authority was located by class/table/name and consumer search. Existing semantics infrastructure is reusable; it is not the effective-dated reference precedence contract. | Implement effective-dated reference persistence, precedence/provenance and governed projections consuming T-214; test overlapping definitions, missing direction/unit and deterministic read-back. Do not reimplement the T-214 decision kernel. | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs:30-74 — existing semantic infrastructure only | 5 | 8 | 13 | Persistence/resolution adapter 2/4/7 + projections/refusal tests 2/3/4 + closure 1/1/2. |  |  | T-214 owns reference decision kernel; T-215 consumes BI projections; a negative symbol search alone is not live absence proof.
T-233 | TIME KERNEL EXISTS; PERSISTENCE/CONSUMER WORK REMAINS | SourceTimeAuthorityKernel already resolves declared source/signal timestamps to uncertainty-bearing instants and refuses unauthorized time roles. The reviewed Domain/Infrastructure models do not contain the corresponding source/server timestamp authority fields/adapter, so kernel completion is not persistence completion. | Persist declared time authority and observation provenance, bind acquisition/projector consumers to the existing kernel, and prove zone/offset/uncertainty conflict handling without machine-locale fallback. | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-97 — Resolve / ResolveAs Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs:184-210 — current material time fields | 5 | 8 | 14 | Persistence/API adapter 2/3/6 + consumer binding 1/2/4 + ambiguity/timezone tests/closure 2/3/4. |  |  | Do not charge T-216 kernel work again; OPC T-226 consumes the approved time contract.
T-235 | KERNELS COMPLETE; CURRENT PRODUCTION INTEGRATION OPEN | OperationalTransitionKernel and TransitionAwarePoolingGuard contain actual regime classification and uncertainty-aware pooling refusal. Direct production reference census only finds kernel-to-kernel calls; it does not establish a persisted regime authority consumed by live statistics. | Persist transition/stabilisation declarations and wire current M2 statistical/correlation pooling to the existing guard. Include source-time uncertainty and explicit undeclared-regime handling; prove the live path refuses mixed/uncertain populations. | Backend/PlantProcess.Analytics.Core/Kernel/Regime/TransitionAwarePoolingGuard.cs:24-79 — Admit Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs:26-66 — time interpretation | 6 | 11 | 18 | Persistence/regime adapter 2/4/7 + live-statistics integration 2/4/6 + adversarial tests/closure 2/3/5. |  |  | Do not redo T-234/T-236; later broad engine convergence stays T-146.
T-241 | SOURCE CORROBORATES CLOSED GRAPH CONTRACT | The shared graph semantics imports typed ports and one block-contract registry; the registry distinguishes implemented/evaluable/persistable capabilities. Those executable validation contracts are real foundation code, not proof of a commissioned job executor. | Retain original typed-port/graph-validation closure. Any actual execution or visual-depth remainder belongs to T-245/T-261/T-265, not recreation of the T-241 graph model. | Frontend/PlantProcess.Web/src/authoring/graphSemantics.ts:22-40 — typed-port authority Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — capability separation | 0 | 0 | 0 | Closed graph contract; zero original remainder. |  | eb7fb2ab — subject not recovered
T-242 | CLOSED CONTRACT; DOWNSTREAM EXECUTION NOT IMPLIED | The block catalogue is centralized, typed and explicit about evaluable versus persistable behavior. Governed aggregation copies canonical metadata and refuses missing semantics; it deliberately computes no analytics. Non-placeable families must not be described as already commissioned product execution. | Original algebra/catalogue/validation closure remains closed. Persistence/compilation/runtime integration is the relevant downstream work and must retain honest unavailable states until accepted. | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts:13-45 — one catalogue and separate capabilities Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:1-9 — handoff boundary Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts:49-77 — AG01 behavior | 0 | 0 | 0 | Closed library/contract scope, not all future execution. Do not convert missing downstream execution into a new T-242 estimate. |  | b93c7a58; fc029aa44ac0079be05d623c73414b7fd9f05590; aa57a503411abeeff38ef346ba8801c7742c7926 — final: T-242 close governed aggregate and window block contracts
T-243 | ORIGINAL REOPEN CLOSED; ADDITIONAL PUBLICATION INTEGRATION OPEN | The authored board, governed output target, version history and reopen logic exist; the September 9 closure proves mocked-server reopen/edit behavior. Canvas publish calls the canonical definition writer and compatibility projector in a transaction, but does not call the existing relationship-publication authority. | Only the added relationship-emission/atomicity/legacy-path convergence remains: derive declared relationships, publish through the existing service in the correct unit of work, and prove rollback/read-back. Preserve the saved-board implementation and its closure. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — canonical graph/board content Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:265-333 — publish transaction Backend/PlantProcess.Application/Relationships/RelationshipService.cs:145-217 — existing publication seam | 5 | 9 | 15 | Declared relationship adapter 2/4/7 + atomic/rollback and compatibility tests 2/4/6 + closure 1/1/2. Reopen board work costs zero here. |  | Original save/reopen journey committed 6f65bba186ecaccc8dbbdfc5eba830a9e1b3e933; executed tests drove the shell against mocked canonical responses. New relationship emission integration is later scope, not proof the original reopen task never completed. | Do not implement a second relationship store. T-262 save-mapping concern is tracked once there, not charged again.
T-244 | SOURCE CORROBORATES CLOSED SQL FOUNDATION | The current SQL-mode save uses canonical content and the shared safe-SQL/lifecycle path, and SQL publication derives a compatibility projection within the same transaction. This substantiates the earlier persistence/convergence foundation; it does not execute a governed projection job. | Keep the original T-244 closure. The later projection-binding callback concern belongs to the T-262 consumer boundary, and runtime transformation execution belongs to T-261. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:173-205 — ForSql Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs:297-333 — SQL publish path Frontend/PlantProcess.Web/src/api/canvasApi.ts:118-155 — SQL run/save API adapter | 0 | 0 | 0 | Closed SQL validation/persistence scope only. |  | 4d32c6b10b4605aeb6e0705ad03537d563125652 — T-244 close canonical Canvas lifecycle and selection model
T-245 | BINDING WORK NOT COMMISSIONED; REUSE PRODUCER CONTRACTS | Canvas has draft save, SQL preview, publish and reopen adapters; the job target resolver/capability descriptors exist. The current shell/API adapter has no commissioned bind-and-run flow consuming exact version/per-block runtime evidence, and CanonicalRefresh is explicitly unavailable. | Implement the thin Canvas-to-job binding/launch/monitor/error/cancel surface over T-261's real executor, carry exact version and stable block IDs, and test unavailable-family refusal before launch. | Frontend/PlantProcess.Web/src/api/canvasApi.ts:111-155 — current save/preview/publish surface Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-124 — non-executable target families | 6 | 10 | 16 | Binding/API/UI 3/5/8 + evidence/cancel views 1/2/4 + integration/negative tests 2/3/4. |  |  | T-261 owns executor and block-evidence storage, T-106 schedule/outcome policy; do not count those implementations again.
T-247 | RELEASE ACCEPTANCE NOT EXECUTABLE BEFORE PRODUCERS | Individual source/import/Canvas/BI surfaces and earlier demo/journey tests exist, but the supplied production snapshot explicitly refuses governed Transformation execution. The required same-binary customer path cannot be certified by the present source or Figma output alone. | After producer closures, execute one customer-shaped real-source-to-canonical-to-BI/Assistant journey with immutable-version/retry/cancel/refusal/isolation evidence and zero customer-specific product diff. Budget acceptance coordination only; bugs remain with their owning tasks. | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — concrete broken journey seam Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs:32-73 — earlier tests are not full new journey proof | 8 | 14 | 22 | Fixture/setup/data preparation 2/4/6 + actual connected acceptance and evidence 4/7/11 + triage/replay/closure 2/3/5; remediation implementation excluded. |  |  | No source-code or drawing count can close runtime acceptance; no duplicate budget for T-106/T-108/T-261 fixes.
T-253 | SOURCE CORROBORATES CLOSED OUTPUT CONTRACT | Canonical content carries one outputTarget; model marker/catalogue authority determines eligible targets and exposes fields. Existing graph/SQL hash and read-back behaviors are real. This is independent of current job executor availability. | No new original output-target work. Preserve original 7a6f91f9 closure; downstream publication and executor consume that authority. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:106-163 — ForGraph outputTarget/board Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — strict compatibility | 0 | 0 | 0 | Original target authority closed; no duplicate estimate. |  | None
T-254 | ORIGINAL SURFACES CLOSED; BACKEND CONVERGENCE REMAINDER | The frontend/website runtime-truth convergence was closed at f8a35725. Current backend still has a separate ConnectorConfigurationService provider DTO list beside ConnectorProviderCatalog. Their OPC browse flags and membership/descriptions differ; configuration reads the former. | Complete only the widened backend validation/catalogue convergence and regression tests ensuring profile validation, API truth, UI and website consume one result. Retain frontend/website original closure and absence-of-fallback evidence. | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:17-39 — duplicate provider DTO source Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs:81-102 — OPC flags Backend/PlantProcess.Application/Integration/Connectors/ConnectorProviderCatalog.cs:72-104 — second catalog OPC/SAP entries | 2 | 4 | 7 | Backend authority extraction/delegation 1/2/4 + consumer mismatch tests/closure 1/2/3. Original frontend/website work excluded. |  | f8a35725c9b0d7fb5a0515c0103a72807a704a97, historical accepted freeze. New scope is not a regression claim against the original. | No rewrite of T-207, no source availability invented from a certification flag.
T-261 | CONTRACTS PRESENT; EXECUTOR NOT APPLIED IN PROVIDED SNAPSHOT LATEST: HELD PENDING T-100 COMMIT | The source has the graph compiler nested in VisualMapperEndpoints, exact target resolution and a RecordResolvedTarget domain seam. The orchestrator discards resolved values and dispatches only by enum; CanonicalRefresh remains false and no executor implementation is commissioned. September 14 instructions are authored/held plans, not an applied commit. Latest user report retains the semantic design but forbids host mutation until T-100 SHA. No new applied T-261 candidate is evidenced here. | Extract/reuse the compiler; implement resolver+executor, carry the pre-admission target into the real run, canonical row effects/idempotency/provenance and stable block evidence, common cancellation/status wiring; run Graph/SQL and failure/cancel proof on disposable DB. Include T-262 live Gate 0 once. | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — admission before real run Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:210-276 — discarded resolution/dispatch Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs:109-115 — uncommissioned executor Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs:127-149 — terminal lifecycle | 16 | 26 | 42 | Compiler/dispatch 3/5/8 + executor/write/evidence 6/10/17 + cancellation integration 2/3/5 + Graph/SQL/live Gate0/replay/cancel tests and closure 5/8/12. | Latest reset supersedes old T-099→T-261→T-100 sequencing. StorageTopologyMap/manifest must be read during the single post-T100 delta; no migration number fixed now. | Pasted markdown(20260914-190300).md:1-239 assigns first RecordResolvedTarget, cancellation seam and T-262 live Gate0 to T-261. No post-ca02b40e executor commit retrieved. | HELD PENDING T-100 COMMIT. Latest CENTRAL reset supersedes T-099→T-261→T-100. Current mutation order: T-099 → T-100 → T-261 → T-245. T-099 is closed frozen ancestry at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af. No Worker-2 host mutation, staging, commit, final preimage hashes, final migration number, census, interim runner or re-anchoring before CENTRAL supplies the final T-100 SHA. After it arrives, one bounded delta over changed owned paths, shared DI/DbContext/topology/manifest, committed projection-validation contracts, current runtime surfaces and actual migration frontier; then re-anchor T-261. Other prerequisite acceptance remains applicable; receipt of the SHA does not itself prove runtime acceptance.
T-262 | ORIGINAL CONTRACT CLOSED; NARROW CONSUMER VERIFICATION OPEN | The declaration, field catalogue, server type checker and Graph/SQL hash persistence exist and were committed GREEN at 86e1b677. A current consumer concern remains: doSaveSql reads projection/projectionBlocked but omits both from its useCallback dependency list; a mapping-only edit needs a direct shell regression test. Unknown-type/narrowing acceptance finding remains withdrawn. | Do not rebuild the declaration. Reproduce the mapping-only SQL-save transition against the real shell, fix only any demonstrated stale callback, and run targeted field-map tests. Live definition-store Gate 0 is already assigned to T-261 Runner2, so it is not estimated again here. Final status remains current-scope open until this correction/acceptance is resolved. | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs:118-163 — immutable projection content Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs:128-145 — unknown/narrowing refusal Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:898-925 — doSaveSql callback inputs/dependencies | 1 | 3 | 6 | Real-shell reproduction 1/1/2 + bounded callback correction if confirmed 0/1/2 + focused regression/closure 0/1/2. Consumer Gate0 cost counted in T-261. | Suspected user-visible stale-save behavior; dependency omission is directly observed, but no live browser reproduction is claimed. Do not revive withdrawn type-compatibility finding. | Original declaration delivered GREEN/COMMITTED at 86e1b677212195f191697ecdca7e9441b3dbde33. 12-Sep output: 24/24 declaration, 8/8 catalogue fields, 39/39 content, 404/404 authoring. Live definition-store integration explicitly not claimed. Later 14-Sep coordination assigns that proof to T-261 Runner 2 Gate 0. | Do not reimplement the immutable declaration. Live definition-store Gate 0 is carried once in T-261 acceptance/estimate. This task's proposed 1/3/6h is the mapping-only SQL save concern and bounded verification, not another executor. Current composite status retained; closure ownership needs explicit reconciliation, not a fake missing-commit claim.
T-113 | SOURCE REVIEWED — IMPLEMENTATION GAPS / RELEASE RUNTIME UNVERIFIED | Real credential resolution, authentication configuration and provider APIs exist. The resolver prioritises username/password in connection_options_json over a reference; the masking test exits successfully without the round-trip when setup fails. The development mint route already refuses outside Development. These facts narrow the repair: it is not a missing licence verifier or a blank-slate connector. | Close accepted-input, persistence and response secret boundaries with sentinel tests; replace vacuous setup returns; validate the actual release-profile bootstrap/MFA/seed/legacy-route boundary and log/audit redaction. Preserve explicit development-only behaviour. | Backend/PlantProcess.Infrastructure/Connectors/ConnectorCredentialResolver.cs:16-51 — Resolve Backend/tests/PlantProcess.Api.IntegrationTests/Security/T08ConnectorSecretMaskingIntegrationTests.cs:19-46 — Connector_password_is_masked_on_readback Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — dev route refusal | 12 | 20 | 32 | Credential boundary+tests 5/8/13; profile/route guards 4/7/11; redaction/deployment verification 3/5/8. | No real secret leak or live production exposure was reproduced. Original 8h covers less than the expanded scope. |  | T-121 owns DI/quota logic; T-123 install/upgrade; this estimate covers their security gate, not reimplementation.
T-121 | BOUNDED SOURCE REVIEW — METER/UI REMAINDER NEEDS DEEPER TRACE | The strict VerifiedEd25519LicenseService and tier/feature checks exist. Production registration points to that implementation, while Application still registers a separate singleton ILicenseService. The dev mint route refuses outside Development. Commercial limits already have reusable code; the full customer-visible metering/quota workflow is not proven by these registrations. | Reconcile to one effective licence authority, implement or complete the declared F2/F3 role/user meters and thresholds, and execute tamper/expiry/meter/no-lost-draft acceptance. Do not build a new signing authority or reclassify the development route as a production mint. | Backend/PlantProcess.Api/SignedLicensing/VerifiedEd25519LicenseService.cs:10-60 — feature/tier authority Backend/PlantProcess.Api/Program.cs:725-744 — licence DI Backend/PlantProcess.Application/DependencyInjection.cs:58-63 — legacy DI Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs:51-62 — development guard | 10 | 18 | 30 | DI and entitlement reconciliation 2/3/5; meters/quota surfaces 5/10/17; acceptance/negative tests 3/5/8. | Full metering implementation was not exhaustively traced; wider interval reflects that. Trust-root claims remain withdrawn. |  | T-113 release profile gate; T-165 pricing/cost model, not licence enforcement.
T-123 | BOUNDED SOURCE REVIEW — DEPLOYMENT EXECUTION UNVERIFIED | A deploy entrypoint and migration/seed commands are already present. The inspected legacy entrypoint selects .env.dev and separates migrate/seed/demo verbs; a canonical migration ledger also exists. This demonstrates reusable deployment infrastructure, not certification that the production packaging chooses only the safe path. | Converge the shipped install/upgrade path onto the canonical ledger, preserve populated data, prove failed-upgrade/rollback recovery and non-root runtime for the selected deployment. Audit actual production selection rather than deleting development tooling blindly. | deploy/scripts/ppiq.ps1:3-20 — command contract deploy/scripts/ppiq.ps1:44-63 — profile/path selection Backend/database/canonical-migration-order.json:1-20 — canonical ledger | 12 | 20 | 36 | Path/ledger convergence 4/7/12; populated-upgrade/rollback tests 5/8/15; clean-host profile/non-root proof 3/5/9. | No installation/upgrade/rollback was run. Hardware, privileges and environment wait time are excluded. |  | T-113 security policy is consumed, not re-estimated here.
T-110 | BOUNDED SOURCE REVIEW — ADVANCED RUNTIME GAP | Existing delta import and versioned job/target contracts are reusable. The inspected importer operates on bounded calls but does not supply the complete general chunk-receipt/checkpoint/resume authority required by this task. Generic channel buffers and ML artifact chunks are not evidence of durable job-scope receipts. | Implement persistent row/byte-bounded chunks, pinned inputs, receipt-atomic progress, interruption resume, deterministic merge and cumulative scan-budget abort. Reuse the M2 source-cursor/replay work rather than implementing it twice. | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:120-151 — existing incremental reader use Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs:173-205 — batch/cursor persistence Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs:61-85 — existing admission/run boundary | 16 | 28 | 44 | Chunk/receipt persistence 6/10/16; resume/merge/enforcement 6/11/17; interruption/parallelism tests 4/7/11. | General chunk engine absence is based on the inspected runtime paths and symbol census, not every historical script. |  | T-108/109 M2 delta; T-155 measured thresholds; T-159 site certification. No waits/soak included.
T-155 | SOURCE FOUNDATION REVIEWED — SITE MEASUREMENTS UNVERIFIED | B-01..B-09 benchmark contracts and a selected-value guard already exist. The guard requires a measured real-subject Production envelope before a value is published. Those are useful measurement tools, not already-measured site capacities or scan-amplification limits. | Integrate site workloads with those harnesses, collect training/batch/online latency and amplification evidence, and publish measured limits. Do not invent measured capacity from fixture outputs or replace the existing evidence contract. | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:20-36 — benchmark metadata Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:32-75 — SelectedValueGuard | 8 | 14 | 24 | Workload/hook setup 3/5/8; measurement orchestration/analysis 3/5/9; governed result publication 2/4/7. | Focused engineer-hours only. Machine run/soak duration, data provisioning and site access excluded; re-estimate if hardware/workload changes. |  | T-110 enforcement implementation and T-159 certification reruns are distinct.
T-159 | FOUNDATION REVIEWED — CAPACITY CERTIFICATION NOT EXECUTED | The same benchmark envelope and real-subject/Production guards provide an existing basis for certification provenance. No C1-C4 run result on target site hardware was executed or observed in this source pass, so completed fixture tooling does not establish certification. | Prepare reproducible C1-C4 workloads, consume T-155 calibration, exercise the T-110 negative controls, reconcile measured sizing examples and capture sign-off without accepting fixture data as production measurements. | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:43-81 — evidence guard Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs:65-90 — B-01..B-09 registry | 8 | 16 | 28 | Profile preparation 3/6/10; certification operation/analysis 3/6/11; reconciliation/sign-off evidence 2/4/7. | Operational engineering effort only; elapsed soak duration and access waits explicitly excluded. |  | No reimplementation of T-110 or calibration billed again from T-155.
T-116 | BOUNDED SOURCE REVIEW — ROUTE-WIDE CENSUS NOT COMPLETE | Current provenance resolution is a real service and still reads declared legacy/compatibility relations. Existing endpoints and guarded source lookups are reusable; spelling public/canon alone does not prove a broken fresh install. The migration requires a consumer inventory rather than a delete-first schema rewrite. | Resolve every active old/new route and compatibility consumer, dual-serve only lawful semantic equivalents, test response/permission parity and keep historical handles readable before retiring consumers/objects. | Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:16-66 — provenance dispatch and run resolution Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs:69-90 — source/dataset existence lookup | 8 | 14 | 24 | Consumer/route inventory 3/5/8; safe dual routing and consumer convergence 3/5/9; parity/negative tests 2/4/7. | 544-route count is a task baseline, not a count remeasured in this pass; estimate contingent on full inventory. |  | Do not remove compatibility objects before all live consumers and upgrade paths converge.
T-248 | BOUNDED SOURCE REVIEW — ALL 75 OUTCOMES NOT CERTIFIED | The shared authoring shell, immutable reopen/output mapping and associative state are real implementation. AssociativeContext models selected/possible/excluded/alternative states and calls the governed widget query. Thus the 75-outcome enterprise remainder is not a blank-slate BI build, and the existence of basic selection must not be overwritten by a visual-template omission. | Complete the unfulfilled advanced outcome rows, native-grain drill, named/comparison states, concurrency recovery and server-owned persistence; wire G3/G6 consistently. Freeze the precise remaining matrix before code and reuse existing selection/history/validator behaviour. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:1-55 — state and query orchestration Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — reopen application | 24 | 40 | 64 | Remaining outcome mapping 4/6/10; advanced UI/runtime integration 14/24/38; parity/accessibility/recovery acceptance 6/10/16. | Full 75-row functional re-audit still required; estimate is a scope-budget proposal, not measured task duration. |  | T-267 designs; T-248 implementation; T-249 release acceptance. Existing T-204 selection closure retained.
T-263 | SOURCE REVIEWED — SUBSTANTIAL REPORT FOUNDATION / LIFECYCLE GAP | Reporting endpoints already generate investigation/readiness reports and PDFs through IInvestigationReportService and readiness services. This is real reusable output infrastructure. It does not provide the complete E5 versioned report-definition, scheduled output and delivery-history lifecycle. | Add governed report definition/version/sections/period, shared-job generation, output history, tenant-scoped download and delivery retries/audit; reuse existing PDF/evidence materialisation. Use the same scheduler, never a private report scheduler. | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report routes Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:57-85 — existing report service/PDF path | 16 | 26 | 42 | Definition/editor/history 6/10/16; job/output/delivery integration 6/10/16; permission/empty/fidelity/retry tests 4/6/10. |  |  | T-106 scheduler and generic delivery components not recreated; fixtures alone cannot prove scheduled delivery.
T-145 | SOURCE REVIEWED — CANONICAL LOOP MISSING / LEGACY CONFLICT | Phase8SuggestionOutcomeLoop takes caller-supplied BeforeValue/AfterValue, and its endpoint stores records in a process-wide ConcurrentDictionary. It is not the canonical outcome/feedback authority required by this task. Outcome arithmetic and presentation DTOs may inform migration, but cannot be credited as durable governed feedback. | Implement canonical-only outcomes, durable evaluation/effectiveness records, intervention-aware metrics, feedback eligibility/concentration evidence and controlled Supervisor input. Retire the contradictory writer safely after replacement and preserve legitimate history. | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — manual outcome DTO Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:66-90 — record calculation Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-48 — process-memory endpoints | 14 | 24 | 40 | Canonical persistence/evaluation 6/10/17; feedback/poisoning/escalation rules 5/8/13; migration/negative tests 3/6/10. | Route mapping exists, but effective caller access in a deployed profile was not exercised. |  | T-190 D6 cutover; T-113 M2 denial; no double price of the same endpoint removal.
T-146 | SOURCE REVIEWED — PRIOR DEAD-FILE FINDING DISPROVEN | ManagedStatisticalComputeEngine already invokes BenjaminiHochberg and Bootstrap from StatisticalDiscipline.cs; AdvancedCorrelationComputeService uses EffectRanking, FDR, Bootstrap and stratification. The file is NOT dead. The separate T-177 KernelMethodSelector/GroupComparisonKernel remain referenced by tests rather than these inspected producers, so a narrower pairing/authority cutover remains. | Wire the certified pairing/refusal kernel into real producers, align persistence/readiness/evidence and consolidate genuinely duplicate paths after consumer migration. Preserve the live discipline functions; do not delete StatisticalDiscipline.cs based on its filename or a zero-hit search for a nonexistent class. | Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:49-62 — readiness/old selector Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs:91-115 — live discipline calls Backend/PlantProcess.Application/Analytics/Advanced/AdvancedCorrelationComputeService.cs:117-137 — live ranking/FDR/bootstrap Backend/PlantProcess.Analytics.Core/Kernel/KernelMethodSelector.cs:27-57 — kernel pairing | 8 | 14 | 24 | Pairing/result-contract cutover 3/5/9; producer/persistence convergence 3/5/8; known-answer/refusal regression 2/4/7. | Do not equate obsolete CorrelationService annotation with no live analytical engine. Existing functions and keyed engine registration are visible. |  | T-186 persistent capability authority; this task consumes it and does not implement a second profile store.
T-165 | BOUNDED SOURCE REVIEW — CALCULATOR NOT ESTABLISHED | The website pricing component renders configured licence-plan labels, prices and feature lists. It is not an input-driven infrastructure cost/price calculator, and benchmark evidence machinery exists separately. Therefore some display structure is reusable while measured commercial sizing logic remains unproven. | Implement explicit units/currency/time assumptions, the separate infrastructure-cost and licence-price formulae, governed input validation and known-answer quote checks against measured capacity. | Website/PlantProcess.Website/src/components/proof/PricingLicenseMatrix.tsx:1-49 — plan display Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs:17-26 — selected measured value identity | 8 | 14 | 24 | Formula/input authority 3/5/8; sales calculator surface/integration 3/5/9; known-answer/refusal tests 2/4/7. | No current commercial prices or site measured sizing invented; public pricing display does not establish cost engine completion. |  | T-121 entitlement differs from commercial pricing; T-155 supplies measurement constants.
T-186 | SOURCE REVIEWED — KERNEL REUSABLE / PERSISTENCE AND WIRING GAP | CapabilityProfiler is a real pure kernel returning measured facts and eligibility/refusal states. It explicitly reads no database. Direct Profile-call census found test callers; persistence and production consumer commissioning are not established. This is integration work around an existing engine, not rebuilding profiling logic. | Persist versioned outcome/grain/manifest-scoped profiles, connect governed prediction-point candidates/model-count limits and use one readiness authority for producers. Prove deterministic rich/sparse decisions and missing-data refusals. | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:8-19 — pure kernel boundary Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:36-64 — profile calculation Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs:69-96 — dimension assessment | 8 | 14 | 24 | Persistence/versioning 3/5/9; point/governor/consumer integration 3/5/8; deterministic/negative tests 2/4/7. |  |  | T-171 kernel closed; do not reopen. T-146 consumes the commissioned authority.
T-190 | BOUNDED SOURCE REVIEW — CANONICAL D6 CUTOVER UNVERIFIED | The legacy outcome endpoints provide a caller-entered/process-memory loop, not durable canonical D6 decisions. Related UI can be reused, but the inspected endpoint returns saved=true after a ConcurrentDictionary write, which must not be presented as canonical persistence. | Bind the actual D6 controls to canonical eligibility and decision records, enforce can_accept on the server, preserve actor/reason history and cut over legacy routes with continuity/negative tests. | Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs:16-43 — legacy write path Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs:12-38 — caller outcome schema | 8 | 14 | 24 | Canonical DTO/permission wiring 3/5/9; D6 state/history cutover 3/5/8; continuity/tampering tests 2/4/7. |  |  | T-145 owns outcome/effectiveness persistence; this task consumes it. M2 route denial owned by T-113.
T-264 | SOURCE REVIEWED — LEGACY DEMO IS NOT TARGET IMPLEMENTATION | P15BenchmarkingService exists, but builds anonymised industry demo bands from a stable base value and synthetic multipliers. That is not the required registry-driven internal plant benchmarking. Existing display/privacy ideas are reusable; demo bands must not be credited as measured internal comparisons. | Implement registered population/period comparisons with real counts, BM01/BM02, direction-aware normalisation and context-comparable own-best practice; preserve evidence/export and tenant isolation. | Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:17-35 — demo dashboard Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs:50-85 — generated bands | 10 | 18 | 30 | Registry/comparison service 4/7/12; result surface/evidence/export 3/6/10; BM01/BM02/tenant tests 3/5/8. | No current customer benchmark output or exposure was executed here. |  | T-214/T-240 semantics reused; no industry taxonomy or a second practice engine.
T-265 | SOURCE + DELIVERED UI DATA REVIEWED — DESIGN DEPTH/PROTOTYPE NOT ACCEPTED | The delivered UI dataset contains 40 pages, 87 dialogs and 607 scene descriptions plus a local importer explicitly labelled not run in Figma. Existing product code already handles immutable reopen and associative selections. This is a substantial starting inventory, but static nodes and populated coverage rows are not proof of the required prototype transitions. | Complete the M2 semantic control/transition matrix, selected source/join/output inspector states, refused/recovery paths and labelled realistic fixtures; execute the specified native import/prototype checks and update only Chapters 3/4 MD+Word and workbook coverage. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — existing associative control semantics Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx:333-403 — existing reopen model PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE. | 28 | 44 | 68 | Semantic/fixture mapping 6/10/15; connected M2 flows 16/24/37; native import/RTL/focus/Word synchronization 6/10/16. | No connected Figma run. No 607-frame count used as a percentage complete; whole UI interaction matrix not executed. |  | T-266 OPC design; T-267 M3 design; runtime implementation remains its own task.
T-266 | DESIGN TASK STILL OPEN; MOCKUP DOES NOT PROVE RUNTIME | The source has historian configuration UI/API scaffolding and truthful unavailable operations, while the delivered visual package is a derived design. No native Figma execution or full target/current capability state interaction is established by current repository source. | Design the named OPC profile/browse/read/subscription/quality/time/spool/replay flow and its unavailable states against T-224..T-226 contracts, integrate into Chapter3/4 and embedded Word images, and execute one observed design import/prototype check without claiming live OPC. | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs:61-108 — actual unavailable contract Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs:24-72 — configuration interface | 6 | 10 | 16 | Flow/state specification 2/4/6 + detailed visual/prototype integration 2/3/5 + semantic acceptance/handoff 2/3/5. No backend implementation counted. |  |  | T-224..T-226 implement/live-certify; T-233 time authority; native design execution availability is a separate uncertainty.
T-267 | BOUNDED SOURCE + UI INVENTORY REVIEW — M3 DESIGN REMAINDER | The common UI dataset and existing selection/history mechanisms are reusable. Current UI Coverage deliberately separates M2 flows from M3 depth. Neither the inventory nor the native-importer code is evidence that M3 concurrency, version comparison, reports and advanced comparison prototypes were exercised. | Design the complete M3 remainder against the existing 75-outcome matrix, producer contracts and accepted M2 flows, including advanced states, conflict/recovery, exports and G3/G6. Verify the native scenes and synchronize the two illustrated chapters. | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx:8-36 — M2 behaviour to preserve Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs:10-33 — existing report subset, not full E5 PPIQ_UI_Figma_v4.10.3.zip!UI_Figma/UI_Design_Data.json: pages40/dialogs87/scenes607; figma_status explicitly states importer not executed. UI Controls v223: PENDING SEMANTIC TRACE. | 24 | 40 | 64 | M3 requirement/producer mapping 5/8/13; advanced connected flows 14/24/38; native/RTL/coverage/chapter checks 5/8/13. | Estimate excludes T-248 product implementation and T-249 product certification. |  | No basic selection/clear deferred from M2; no duplicate generic frame batch treated as acceptance.

## Source Evidence
Task ID | Repository path | Symbol | First line | Last line | Source excerpt | Export + recorded original SHA256 | Evidence type
T-095 | Backend/PlantProcess.Application/Relationships/RelationshipService.cs | PublishAsync | 145 | 217 | IReadOnlyList<RelationshipEntityDto> entities = counts .Select(pair => new RelationshipEntityDto(pair.Key, pair.Value)) .ToList(); return ApplicationResult<IReadOnlyList<RelationshipEntityDto>>.Success(entities); } public async Task<ApplicationResult<IReadOnlyList<RelationshipDto>>> PublishAsync( RelationshipPublicationRequest request, CancellationToken cancellationToken) { if (request is null) return Fail("A publication carries at least one declaration."); if (!_tenantAccessor.TryGetTenantId(out var tenantId)) return Fail("No tenant on the caller; a relationship cannot be published without one."); if (request.SourceDefinitionId == Guid.Empty) return Fail("A relationship must name the definition that published it."); if (request.SourceDefinitionVersion <= 0) return Fail("A relationship must name the definition VERSION that published it, so a historical result stays explainable after the model changes."); if (request.Relationships is null ¦¦ request.Relationships.Count == 0) return Fail("A publication with no declarations is not a publication."); foreach (var declaration in request.Relationships) { var refusal = Validate(declaration); if (refusal is not null) return Fail(refusal); } var effectiveFromUtc = DateTime.UtcNow; // Republication supersedes rather than deletes. The prior emission is // retired first so the unique code is free, and its rows stay readable. await _store.RetireByDefinitionAsync(tenantId, request.SourceDefinitionId, effectiveFromUtc, cancellationToken); foreach (var declaration in request.Relationships) { await _store.UpsertAsync( tenantId, declaration, request.SourceDefinitionId, request.SourceDefinitionVersion, effectiveFromUtc, cancellationToken); } // Returned by reading BACK, never by echoing the request. An emission // that cannot be read is not a publication, and echoing would hide that. var published = await _store.ReadPublishedAsync(tenantId, null, cancellationToken); var emitted = published .Where(r => r.SourceDefinitionId == request.SourceDefinitionId && r.SourceDefinitionVersion == request.SourceDefinitionVersion) .ToList(); return ApplicationResult<IReadOnlyList<RelationshipDto>>.Success(emitted); } public async Task<ApplicationResult<int>> RetireByDefinitionAsync( Guid sourceDefinitionId, CancellationToken cancellationToken) { if (!_tenantAccessor.TryGetTenantId(out var tenantId)) return ApplicationResult<int>.Failure( ApplicationError.Validation("No tenant on the caller.")); var retired = await _store.RetireByDefinitionAsync( tenantId, sourceDefinitionId, DateTime.UtcNow, cancellationToken); return ApplicationResult<int>.Success(retired); } /// <summary> /// Publication-time rules. Each refusal names its code and says what is /// wrong in a sentence, because the person reading it is a plant engineer /// looking at their own declaration, not a developer reading a stack trace. /// </summary> | 01_Backend_Core_14Sep2026_104846.txt 4235F89FCF67C0C7E9749A40E3845E1BDF4A0A56FBB8CAE6925832EBFF19E6AE | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-095 | Backend/PlantProcess.Application/Relationships/RelationshipService.cs | ValidateDeclaration | 218 | 260 | private static string? Validate(RelationshipDeclaration d) { if (d is null) return "A null declaration cannot be published."; if (string.IsNullOrWhiteSpace(d.RelationshipCode)) return "A relationship needs a code."; if (string.IsNullOrWhiteSpace(d.LeftEntity) ¦¦ string.IsNullOrWhiteSpace(d.RightEntity)) return $"{RelationshipPublicationCodes.UnknownVocabulary}: a relationship needs an entity on both sides."; if (string.IsNullOrWhiteSpace(d.GrainLeft) ¦¦ string.IsNullOrWhiteSpace(d.GrainRight)) return $"{RelationshipPublicationCodes.UnknownVocabulary}: a relationship needs a declared grain on both sides, so a cross-grain join is recognised as one."; if (!RelationshipJoinTypes.All.Contains(d.JoinType, StringComparer.Ordinal)) return $"{RelationshipPublicationCodes.UnknownVocabulary}: '{d.JoinType}' is not a join type."; if (!RelationshipCardinalities.All.Contains(d.Cardinality, StringComparer.Ordinal)) return $"{RelationshipPublicationCodes.UnknownVocabulary}: '{d.Cardinality}' is not a cardinality."; if (d.AttributionRule is not null && !RelationshipAttributionRules.All.Contains(d.AttributionRule, StringComparer.Ordinal)) return $"{RelationshipPublicationCodes.UnknownVocabulary}: '{d.AttributionRule}' is not an attribution rule."; var convertsGrain = !string.Equals(d.GrainLeft, d.GrainRight, StringComparison.Ordinal); if (convertsGrain && (d.AttributionRule is null ¦¦ string.Equals(d.AttributionRule, RelationshipAttributionRules.None, StringComparison.Ordinal))) { return $"{RelationshipPublicationCodes.GrainConversionWithoutAttribution}: this relationship converts grain from '{d.GrainLeft}' to '{d.GrainRight}' and must declare how a parent's value is divided across children."; } if (d.Members is null ¦¦ d.Members.Count == 0) return $"{RelationshipPublicationCodes.MembersOutOfOrderOrIncomplete}: a relationship needs at least one key pair."; var orders = d.Members.Select(m => m.MemberOrder).OrderBy(o => o).ToArray(); for (var i = 0; i < orders.Length; i++) { if (orders[i] != i) return $"{RelationshipPublicationCodes.MembersOutOfOrderOrIncomplete}: composite key members must be contiguous from 0; got [{string.Join(", ", orders)}]. Order matters because real plants key on two or three columns."; } foreach (var member in d.Members) { if (string.IsNullOrWhiteSpace(member.LeftColumn) ¦¦ string.IsNullOrWhiteSpace(member.RightColumn)) return $"{RelationshipPublicationCodes.MembersOutOfOrderOrIncomplete}: key member {member.MemberOrder} is missing a column on one side."; // The canonical executor runs equality members. A comparison it cannot run // must not be publishable: a relationship the product accepts and its only | 01_Backend_Core_14Sep2026_104846.txt 4235F89FCF67C0C7E9749A40E3845E1BDF4A0A56FBB8CAE6925832EBFF19E6AE | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-096 | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs | ResolveAsync | 34 | 113 | public async Task<ApplicationResult<RelationshipResolutionDto>> ResolveAsync( string fromEntity, string toEntity, string purpose, CancellationToken cancellationToken) { if (string.IsNullOrWhiteSpace(fromEntity) ¦¦ string.IsNullOrWhiteSpace(toEntity)) return Invalid("A resolution needs an entity on both sides."); if (string.IsNullOrWhiteSpace(purpose)) return Invalid("A resolution needs a purpose: an unproven relationship is usable by exploration and not by anything automated, and that cannot be decided without knowing who is asking."); if (!RelationshipConsumerPurposes.All.Contains(purpose, StringComparer.Ordinal)) return Invalid($"'{purpose}' is not a declared consumer purpose."); var published = await _relationships.GetPublishedAsync(null, cancellationToken); if (published.IsFailure) return ApplicationResult<RelationshipResolutionDto>.Failure(published.Error!); var from = fromEntity.Trim(); var to = toEntity.Trim(); if (string.Equals(from, to, StringComparison.Ordinal)) { // An entity joins to itself without a relationship. Saying so is not // the same as claiming a path exists. return Ok(new RelationshipResolutionDto( from, to, purpose, true, Array.Empty<RelationshipPathStepDto>(), false, null, null, Array.Empty<string>())); } var edges = BuildEdges(published.Value!); var candidates = FindShortestPaths(edges, from, to); if (candidates.Count == 0) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.NoPath, $"No declared relationship path connects '{from}' to '{to}'. The model has to say how two things relate before anything may join them.", Array.Empty<string>())); } var names = candidates.Select(Describe).ToList(); var chosen = candidates.Count == 1 ? candidates[0] : ChoosePreferred(candidates); if (chosen is null) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.AmbiguousPath, $"'{from}' reaches '{to}' by more than one declared path and none is marked preferred. Both are named rather than one being chosen, because the answer would otherwise depend on which was looked at first: {string.Join(" ¦ ", names)}.", names)); } // RL02. Exploration is manual and may traverse an unproven relationship. // Everything else is automated, and an automated consumer that trains, // scores or projects across an unproven join produces a result nobody // can defend. if (RelationshipConsumerPurposes.IsAutomated(purpose)) { var unproven = chosen .Where(e => !string.Equals(e.Relationship.ValidationState, RelationshipValidationStates.Validated, StringComparison.Ordinal)) .Select(e => e.Relationship.RelationshipCode) .OrderBy(c => c, StringComparer.Ordinal) .ToList(); if (unproven.Count > 0) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.UnprovenRelationship, $"The path from '{from}' to '{to}' runs through {string.Join(", ", unproven)}, which nobody has proven against real data. '{purpose}' is automated, so it may not use it; manual exploration still may.", names)); } } var steps = chosen .Select(e => new RelationshipPathStepDto(e.Relationship.Id, e.From, e.To)) .ToList(); return Ok(new RelationshipResolutionDto( from, to, purpose, true, steps, chosen.Any(e => e.Relationship.IsGrainConverting), null, null, names)); | 01_Backend_Core_14Sep2026_104846.txt CF80A487057CE68B75618A7589B5A47CF690DBAFE59835EC9A1CB8B36D67EC9D | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-096 | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs | ConsumerFamilies | 55 | 96 | private static readonly IReadOnlyDictionary<string, string[]> ConsumerFamilies = new Dictionary<string, string[]>(StringComparer.Ordinal) { // Routed by T-096. ["Projection"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Dimensions" }, ["QueryCompiler"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["AssociativeFiltering"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["DrillDown"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["DrillThrough"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["Genealogy"] = new[] { @"Backend\PlantProcess.Application\Services\Materials" }, ["StatisticalAnalysis"] = new[] { @"Backend\PlantProcess.Application\Analytics\Services" }, ["Correlation"] = new[] { @"Backend\PlantProcess.Application\Analytics\Engines", @"Backend\PlantProcess.Application\Analytics\Advanced" }, // Covered by T-097. ["FeatureEngineering"] = new[] { @"Backend\PlantProcess.Application\Analytics\Services", @"Backend\PlantProcess.Application\Analytics\Interfaces" }, ["ModelTraining"] = new[] { @"Backend\PlantProcess.Application\Analytics\Training" }, ["Prediction"] = new[] { @"Backend\PlantProcess.Application\Analytics\Contracts", @"Backend\PlantProcess.Application\Analytics\Prediction" }, ["PracticeLearning"] = new[] { @"Backend\PlantProcess.Application\Analytics\Practice" }, ["RemediationSearch"] = new[] { @"Backend\PlantProcess.Application\Analytics\Remediation" }, ["ValueCalculation"] = new[] { @"Backend\PlantProcess.Application\Analytics\Value" }, ["Assistant"] = new[] { @"Backend\PlantProcess.Application\Assistant", @"Backend\PlantProcess.Application\AssistantRuntime" }, ["Evidence"] = new[] { @"Backend\PlantProcess.Application\Provenance", @"Backend\PlantProcess.Application\Analytics\Value" } | 03_Backend_Tests_14Sep2026_104846.txt 1AA9C082D30D7D1BD76D13D90909F94F1347D7EAEA4C5C7FFC816BED7C0EFA38 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-097 | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs | barrier semantics | 12 | 44 | /// <summary> /// The permanent barrier. Sixteen consumer families, one path authority, and no lawful /// way for a seventeenth idea to appear. /// /// T-096 removed the second path authority and routed the first eight families through /// the canonical one. This finishes the job for the remaining eight and, more /// importantly, makes the arrangement durable: the failure this guards against is not a /// mistake anyone is making today, it is the one a future author makes six months from /// now when a join is needed and the resolver seems like a detour. /// /// WHAT IS FORBIDDEN, and only this: /// /// reaching relationship persistence directly; /// injecting the relationship store; /// searching for a path; /// choosing a preferred path; /// inferring a relationship from names; /// reading foreign-key metadata to decide how two subjects connect; /// quietly joining anyway after the authority has refused. /// /// WHAT IS EXPLICITLY ALLOWED, because forbidding it would be absurd: /// /// intrinsic navigation on a row's own owning key; /// fixed joins between known canonical entities; /// lookups by an identity already resolved; /// packaging and hashing evidence. /// /// That distinction is the whole difficulty. A consumer that writes /// `x.MaterialUnitId == materialUnitId` has not chosen anything - the key is the row's /// own. A consumer that works out WHICH key connects two subjects has chosen, and that /// decision belongs to the relationship model where a plant can publish, prefer and /// retire it. The guard below is written to catch the second without ever flagging the /// first, because a barrier that cries wolf is a barrier someone eventually deletes. | 03_Backend_Tests_14Sep2026_104846.txt 1AA9C082D30D7D1BD76D13D90909F94F1347D7EAEA4C5C7FFC816BED7C0EFA38 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-097 | Backend/tests/PlantProcess.Architecture.Tests/RelationshipConsumerBarrierTests.cs | consumer and forbidden-authority inventory | 55 | 114 | private static readonly IReadOnlyDictionary<string, string[]> ConsumerFamilies = new Dictionary<string, string[]>(StringComparer.Ordinal) { // Routed by T-096. ["Projection"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Dimensions" }, ["QueryCompiler"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["AssociativeFiltering"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["DrillDown"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["DrillThrough"] = new[] { @"Backend\PlantProcess.Application\Dashboarding\Services\Queries" }, ["Genealogy"] = new[] { @"Backend\PlantProcess.Application\Services\Materials" }, ["StatisticalAnalysis"] = new[] { @"Backend\PlantProcess.Application\Analytics\Services" }, ["Correlation"] = new[] { @"Backend\PlantProcess.Application\Analytics\Engines", @"Backend\PlantProcess.Application\Analytics\Advanced" }, // Covered by T-097. ["FeatureEngineering"] = new[] { @"Backend\PlantProcess.Application\Analytics\Services", @"Backend\PlantProcess.Application\Analytics\Interfaces" }, ["ModelTraining"] = new[] { @"Backend\PlantProcess.Application\Analytics\Training" }, ["Prediction"] = new[] { @"Backend\PlantProcess.Application\Analytics\Contracts", @"Backend\PlantProcess.Application\Analytics\Prediction" }, ["PracticeLearning"] = new[] { @"Backend\PlantProcess.Application\Analytics\Practice" }, ["RemediationSearch"] = new[] { @"Backend\PlantProcess.Application\Analytics\Remediation" }, ["ValueCalculation"] = new[] { @"Backend\PlantProcess.Application\Analytics\Value" }, ["Assistant"] = new[] { @"Backend\PlantProcess.Application\Assistant", @"Backend\PlantProcess.Application\AssistantRuntime" }, ["Evidence"] = new[] { @"Backend\PlantProcess.Application\Provenance", @"Backend\PlantProcess.Application\Analytics\Value" } }; /// <summary> /// Each token is a way of deciding a semantic path, and none of them is a way of /// following a key you were given. They are matched against comment-stripped source /// so that describing the rule is never mistaken for breaking it. /// </summary> private static readonly (string Token, string Why)[] ForbiddenTokens = { ("plant_relationships", "reads relationship persistence directly"), ("plant_relationship_members", "reads relationship persistence directly"), ("plant_relationship_paths", "reads relationship persistence directly"), ("IRelationshipStore", "injects the relationship store instead of depending on the resolver"), ("NpgsqlRelationshipStore", "names the concrete relationship store"), ("GetForeignKeys(", "reads foreign-key metadata to decide how two subjects connect"), ("IsPreferredPath", "decides preference itself; preference is governed data"), ("ShortestPath", "searches for a path instead of asking for one"), ("BreadthFirst", "searches for a path instead of asking for one") | 03_Backend_Tests_14Sep2026_104846.txt 1AA9C082D30D7D1BD76D13D90909F94F1347D7EAEA4C5C7FFC816BED7C0EFA38 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-098 | Backend/PlantProcess.Api/Endpoints/Relationships/RelationshipEndpoints.cs | MapRelationshipEndpoints | 21 | 92 | public static class RelationshipEndpoints { public static IEndpointRouteBuilder MapRelationshipEndpoints(this IEndpointRouteBuilder app) { var group = app .MapGroup("/api/relationships") .RequireAuthorization() .WithTags("Relationships"); group.MapGet("/", async ( string? entity, IRelationshipService service, CancellationToken cancellationToken) => { var result = await service.GetPublishedAsync(entity, cancellationToken); return result.IsSuccess ? Results.Ok(result.Value) : Results.Problem(title: result.Error!.Code, detail: result.Error!.Message, statusCode: StatusCodes.Status400BadRequest); }); group.MapGet("/entities", async ( IRelationshipService service, CancellationToken cancellationToken) => { var result = await service.GetEntitiesAsync(cancellationToken); return result.IsSuccess ? Results.Ok(result.Value) : Results.Problem(title: result.Error!.Code, detail: result.Error!.Message, statusCode: StatusCodes.Status400BadRequest); }); group.MapGet("/{id:guid}", async ( Guid id, IRelationshipService service, CancellationToken cancellationToken) => { var result = await service.GetByIdAsync(id, cancellationToken); if (result.IsSuccess) return Results.Ok(result.Value); return result.Error!.Type == PlantProcess.Application.Common.Results.ApplicationErrorType.NotFound ? Results.NotFound(new { code = result.Error!.Code, message = result.Error!.Message }) : Results.Problem(title: result.Error!.Code, detail: result.Error!.Message, statusCode: StatusCodes.Status400BadRequest); }); group.MapPost("/{id:guid}/validate", async ( Guid id, IRelationshipValidationService validation, CancellationToken cancellationToken) => { // The body is empty on purpose. The server derives the state from evidence; // a request that could name the state it wanted would be a way to assert // proof without producing it. try { var result = await validation.ValidateAsync(id, cancellationToken); if (result.IsSuccess) return Results.Ok(result.Value); return result.Error!.Type == PlantProcess.Application.Common.Results.ApplicationErrorType.NotFound ? Results.NotFound(new { code = result.Error!.Code, message = result.Error!.Message }) : Results.Problem(title: result.Error!.Code, detail: result.Error!.Message, statusCode: StatusCodes.Status400BadRequest); } catch (RelationshipPlanExecutionException unexecutable) { // The relationship could not be evaluated against the mapped model. Nothing // was persisted; the plant is told which member did not map. return Results.Problem( title: RelationshipPlanExecutionException.Reason, detail: unexecutable.Message, statusCode: StatusCodes.Status422UnprocessableEntity); } }); return app; | 01_Backend_Core_14Sep2026_104846.txt 9245F5C2BBB60A7C3B387815B560A3FFC8DAECD3F2986937167BBDDAAB1C3945 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-098 | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs | path results | 62 | 113 | var edges = BuildEdges(published.Value!); var candidates = FindShortestPaths(edges, from, to); if (candidates.Count == 0) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.NoPath, $"No declared relationship path connects '{from}' to '{to}'. The model has to say how two things relate before anything may join them.", Array.Empty<string>())); } var names = candidates.Select(Describe).ToList(); var chosen = candidates.Count == 1 ? candidates[0] : ChoosePreferred(candidates); if (chosen is null) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.AmbiguousPath, $"'{from}' reaches '{to}' by more than one declared path and none is marked preferred. Both are named rather than one being chosen, because the answer would otherwise depend on which was looked at first: {string.Join(" ¦ ", names)}.", names)); } // RL02. Exploration is manual and may traverse an unproven relationship. // Everything else is automated, and an automated consumer that trains, // scores or projects across an unproven join produces a result nobody // can defend. if (RelationshipConsumerPurposes.IsAutomated(purpose)) { var unproven = chosen .Where(e => !string.Equals(e.Relationship.ValidationState, RelationshipValidationStates.Validated, StringComparison.Ordinal)) .Select(e => e.Relationship.RelationshipCode) .OrderBy(c => c, StringComparer.Ordinal) .ToList(); if (unproven.Count > 0) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.UnprovenRelationship, $"The path from '{from}' to '{to}' runs through {string.Join(", ", unproven)}, which nobody has proven against real data. '{purpose}' is automated, so it may not use it; manual exploration still may.", names)); } } var steps = chosen .Select(e => new RelationshipPathStepDto(e.Relationship.Id, e.From, e.To)) .ToList(); return Ok(new RelationshipResolutionDto( from, to, purpose, true, steps, chosen.Any(e => e.Relationship.IsGrainConverting), null, null, names)); | 01_Backend_Core_14Sep2026_104846.txt CF80A487057CE68B75618A7589B5A47CF690DBAFE59835EC9A1CB8B36D67EC9D | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-099 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs | MapMaterialUnitAsync | 141 | 181 | private async Task<RowProjectionOutcome> MapMaterialUnitAsync( MappingDefinition mapping, RowReader reader, StagingRecord stagingRecord, MappingExecutionContext context, bool previewOnly, CancellationToken cancellationToken) { var materialCode = reader.RequiredString("MaterialCode"); var materialUnitType = reader.RequiredString("MaterialUnitType"); var siteRaw = reader.OptionalString("SiteId") ?? reader.OptionalString("SiteCode"); if (reader.Failed) return Refused(reader); var siteId = await ResolveSiteIdAsync(reader, siteRaw, cancellationToken); if (reader.Failed) return Refused(reader); // PV07 against the governed catalogue, never against a list written here. var typeRefusal = await ClassifyMaterialUnitTypeAsync(materialUnitType!, cancellationToken); if (typeRefusal is not null) return RowProjectionOutcome.Quarantined(typeRefusal); var duplicate = context.ClaimBusinessKey($"MaterialUnit¦{siteId}¦{materialCode}", stagingRecord.RowNumber); if (duplicate.HasValue) return RowProjectionOutcome.Quarantined(DuplicateInExecution("MaterialUnit", materialCode!, duplicate.Value)); var existing = await _dbContext.MaterialUnits .AsNoTracking() .Where(x => x.SiteId == siteId && x.MaterialCode == materialCode) .Select(x => x.Id) .FirstOrDefaultAsync(cancellationToken); if (existing != Guid.Empty) { // Lawful idempotency preserved: the existing contract skips, and // turning that into PV04 would quarantine correct re-projection. if (!previewOnly) stagingRecord.MarkSkipped($"MaterialUnit already exists: {materialCode}."); return RowProjectionOutcome.Skipped(existing, "MaterialUnit", $"MaterialUnit already exists: {materialCode}."); | 01_Backend_Core_14Sep2026_104846.txt B17144B6986CDC3690CA0373BBD642AAE6EFD487FC10D631B831D3C45A537699 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-099 | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs | bounded reprocess surface | 8 | 33 | /// PPIQ T-099. The bounded reprocess surface, and nothing else. /// /// T-099 owns POST /api/quarantine/reprocess only. List, detail, dismiss and /// Mapping Health are T-101's, and adding them here early would put unproven /// product surface in front of a customer. /// </summary> public static class QuarantineEndpoints { public static IEndpointRouteBuilder MapQuarantineEndpoints(this IEndpointRouteBuilder app) { var group = app.MapGroup("/api/quarantine") .WithTags("Quarantine"); group.MapPost("/reprocess", ReprocessAsync); return app; } private static async Task<IResult> ReprocessAsync( ReprocessQuarantineRequest request, [FromServices] IProjectionQuarantineReprocessService service, CancellationToken cancellationToken) { var result = await service.ReprocessAsync(request.QuarantineId, request.TenantCode, cancellationToken); return result.ToHttpResult(value => Results.Ok(value)); | 01_Backend_Core_14Sep2026_104846.txt 60DA2F4A57AEA693A515FBE3DEA0441023938C9C3BBB631DB7D30C1F842446C7 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-099 | Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql | narrow topology correction | 3 | 20 | -- PPIQ T-099 (owned by CENTRAL ruling of 13-Sep-2026, option b). -- -- WHAT WAS WRONG. 550 created the deferred constraint trigger -- ppiq_genealogy_edge_weight_guard_after_change on public.genealogy_edges with -- a plpgsql body that reads FROM public.genealogy_edges by name. When the T-090 -- storage topology convergence relocated the table to ppiq_plant, the trigger -- followed the table, as triggers do, but the function body kept the old -- schema-qualified name. On any database built from the canonical path every -- INSERT, UPDATE or DELETE on genealogy_edges therefore fails at COMMIT with -- 42P01 relation "public.genealogy_edges" does not exist. The first canonical -- from-zero insert of a GenealogyEdge in the repository's history was T-099's -- PV04 live gate, which is how this surfaced. -- -- THE FIX. The function now reads from the relation the trigger actually fired -- on, TG_TABLE_SCHEMA.TG_TABLE_NAME, so it follows the table under any future -- placement instead of hard-coding one. Semantics are otherwise unchanged: the -- same aggregate, the same tolerance, the same exception text, RETURN NULL. -- Nothing else from 550 is touched. The trigger is not recreated. | 02_Backend_Database_14Sep2026_104846.txt A9F5DF32B340D7BE3C37AD111F229894834924F789E8AEA7AFE6BFAAE0FCBC9F | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-100 | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs | ownership | 8 | 13 | /// PPIQ T-099. The bounded reprocess surface, and nothing else. /// /// T-099 owns POST /api/quarantine/reprocess only. List, detail, dismiss and /// Mapping Health are T-101's, and adding them here early would put unproven /// product surface in front of a customer. /// </summary> | 01_Backend_Core_14Sep2026_104846.txt 60DA2F4A57AEA693A515FBE3DEA0441023938C9C3BBB631DB7D30C1F842446C7 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-100 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs | existing validation pattern | 630 | 690 | /// PV07. The catalogue decides, not this file. When the catalogue carries no /// active entry the product has not yet governed this vocabulary, and /// refusing every row against an empty catalogue would be a false refusal. /// </summary> private async Task<RowValidationRefusal?> ClassifyMaterialUnitTypeAsync(string materialUnitType, CancellationToken cancellationToken) { var governed = await _dbContext.MaterialUnitTypeDefinitions .AsNoTracking() .AnyAsync(x => x.IsActive, cancellationToken); if (!governed) return null; var registered = await _dbContext.MaterialUnitTypeDefinitions .AsNoTracking() .AnyAsync(x => x.IsActive && x.MaterialUnitTypeCode == materialUnitType, cancellationToken); if (registered) return null; return new RowValidationRefusal( ProjectionValidationCode.PV07, $"Material unit type '{materialUnitType}' is not registered in the governed material unit type catalogue.", materialUnitType); } /// <summary> /// PV08. The governed parameter definition is the unit authority. A /// definition that declares no unit governs nothing, so a supplied unit is /// lawful there. /// </summary> private async Task<RowValidationRefusal?> ClassifyUnitOfMeasureAsync( Guid parameterDefinitionId, string? suppliedUnit, CancellationToken cancellationToken) { if (string.IsNullOrWhiteSpace(suppliedUnit)) return null; var governedUnit = await _dbContext.ParameterDefinitions .AsNoTracking() .Where(x => x.Id == parameterDefinitionId) .Select(x => x.UnitOfMeasure) .FirstOrDefaultAsync(cancellationToken); if (string.IsNullOrWhiteSpace(governedUnit)) return null; if (string.Equals(governedUnit, suppliedUnit, StringComparison.OrdinalIgnoreCase)) return null; return new RowValidationRefusal( ProjectionValidationCode.PV08, $"Unit '{suppliedUnit}' is not the governed unit '{governedUnit}' for this parameter definition.", suppliedUnit); } private static RowValidationRefusal DuplicateInExecution(string entityName, string key, int ownerRowNumber) => new(ProjectionValidationCode.PV05, $"Row {ownerRowNumber} in this execution already declares the same governed {entityName} business key.", key); | 01_Backend_Core_14Sep2026_104846.txt B17144B6986CDC3690CA0373BBD642AAE6EFD487FC10D631B831D3C45A537699 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-101 | Backend/PlantProcess.Api/Endpoints/Quarantine/QuarantineEndpoints.cs | MapQuarantineEndpoints | 8 | 33 | /// PPIQ T-099. The bounded reprocess surface, and nothing else. /// /// T-099 owns POST /api/quarantine/reprocess only. List, detail, dismiss and /// Mapping Health are T-101's, and adding them here early would put unproven /// product surface in front of a customer. /// </summary> public static class QuarantineEndpoints { public static IEndpointRouteBuilder MapQuarantineEndpoints(this IEndpointRouteBuilder app) { var group = app.MapGroup("/api/quarantine") .WithTags("Quarantine"); group.MapPost("/reprocess", ReprocessAsync); return app; } private static async Task<IResult> ReprocessAsync( ReprocessQuarantineRequest request, [FromServices] IProjectionQuarantineReprocessService service, CancellationToken cancellationToken) { var result = await service.ReprocessAsync(request.QuarantineId, request.TenantCode, cancellationToken); return result.ToHttpResult(value => Results.Ok(value)); | 01_Backend_Core_14Sep2026_104846.txt 60DA2F4A57AEA693A515FBE3DEA0441023938C9C3BBB631DB7D30C1F842446C7 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-101 | Backend/PlantProcess.Application/Integration/Services/Staging/StagingRecordService.cs | durable staging identity | 85 | 110 | var exists = await _dbContext.StagingRecords.AnyAsync(x => x.ImportBatchId == command.ImportBatchId && x.SourceObjectName == command.SourceObjectName.Trim() && x.RowNumber == row.RowNumber, cancellationToken); if (exists) { rejected.Add(new StagingRecordBulkRejectedRow(row.RowNumber, "Staging record already exists for this import batch/source object/row number.")); continue; } var stagingRecord = new StagingRecord( importBatchId: command.ImportBatchId, sourceObjectName: command.SourceObjectName, rowNumber: row.RowNumber, rawJson: row.RawJson, isSynthetic: command.Metadata.IsSynthetic, sourceSystem: command.Metadata.SourceSystem, sourceRecordId: row.SourceRecordId ?? command.Metadata.SourceRecordId); _dbContext.StagingRecords.Add(stagingRecord); accepted++; } await _dbContext.SaveChangesAsync(cancellationToken); | 01_Backend_Core_14Sep2026_104846.txt 265AC37E0713AB1B6EFFE4C1CCA8A7D7E6DF29A479D81004D6E050811904CA65 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-102 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs | MapMaterialAliasAsync | 244 | 264 | var duplicate = context.ClaimBusinessKey($"MaterialAlias¦{materialId}¦{aliasCode}¦{sourceSystem}", stagingRecord.RowNumber); if (duplicate.HasValue) return RowProjectionOutcome.Quarantined(DuplicateInExecution("MaterialAlias", aliasCode!, duplicate.Value)); var exists = await _dbContext.MaterialAliases .AsNoTracking() .AnyAsync(x => x.MaterialUnitId == materialId && x.AliasCode == aliasCode && x.SourceSystem == sourceSystem, cancellationToken); if (exists) { if (!previewOnly) stagingRecord.MarkSkipped($"MaterialAlias already exists: {aliasCode}."); return RowProjectionOutcome.Skipped(materialId, "MaterialAlias", $"MaterialAlias already exists: {aliasCode}."); } var alias = new MaterialAlias(materialId!.Value, aliasCode!, sourceSystem, aliasType, stagingRecord.IsSynthetic); if (!previewOnly) { _dbContext.MaterialAliases.Add(alias); stagingRecord.MarkMapped(alias.Id, "MaterialAlias"); | 01_Backend_Core_14Sep2026_104846.txt B17144B6986CDC3690CA0373BBD642AAE6EFD487FC10D631B831D3C45A537699 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-102 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs | ResolveMaterialIdAsync | 721 | 744 | var materialCode = reader.OptionalString(materialCodeField); if (!string.IsNullOrWhiteSpace(materialCode)) { var id = await _dbContext.MaterialUnits .AsNoTracking() .Where(x => x.MaterialCode == materialCode) .Select(x => x.Id) .FirstOrDefaultAsync(cancellationToken); if (id != Guid.Empty) return id; } var aliasCode = reader.OptionalString(aliasCodeField); if (!string.IsNullOrWhiteSpace(aliasCode)) { var id = await _dbContext.MaterialAliases .AsNoTracking() .Where(x => x.AliasCode == aliasCode) .Select(x => x.MaterialUnitId) .FirstOrDefaultAsync(cancellationToken); if (id != Guid.Empty) return id; | 01_Backend_Core_14Sep2026_104846.txt B17144B6986CDC3690CA0373BBD642AAE6EFD487FC10D631B831D3C45A537699 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-102 | Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialAliasConfiguration.cs | composite unique | 27 | 36 | builder.HasIndex(x => x.MaterialUnitId); builder.HasIndex(x => x.AliasCode); builder.HasIndex(x => x.SourceSystem); builder.HasIndex(x => new { x.MaterialUnitId, x.AliasCode, x.SourceSystem }).IsUnique(); | 01_Backend_Core_14Sep2026_104846.txt 459B290721ED85AA7B6A3A065CEA9F1CDB1308B115F17DDA29237371FC877712 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-102 | Backend/PlantProcess.Infrastructure/Persistence/Configurations/Materials/MaterialUnitConfiguration.cs | site/source uniqueness | 43 | 47 | builder.HasIndex(x => new { x.SiteId, x.MaterialCode }).IsUnique(); builder.HasIndex(x => new { x.SourceSystem, x.SourceRecordId }) .IsUnique() .HasFilter("source_system IS NOT NULL AND source_record_id IS NOT NULL"); | 01_Backend_Core_14Sep2026_104846.txt BA5AB7A87CF5FA3E04B721836720896FC61E27ABF9C3E9352D06E6BE8293C6D1 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-103 | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs | CreateEdgeAsync | 27 | 69 | if (command.ParentMaterialUnitId == Guid.Empty) return ApplicationResult<Guid>.Failure(ApplicationError.Validation("Parent material unit ID is required.")); if (command.ChildMaterialUnitId == Guid.Empty) return ApplicationResult<Guid>.Failure(ApplicationError.Validation("Child material unit ID is required.")); if (command.ParentMaterialUnitId == command.ChildMaterialUnitId) return ApplicationResult<Guid>.Failure(ApplicationError.BusinessRule("A material cannot be its own parent.")); if (string.IsNullOrWhiteSpace(command.RelationshipType)) return ApplicationResult<Guid>.Failure(ApplicationError.Validation("Relationship type is required.")); var parentExists = await _dbContext.MaterialUnits .AnyAsync(x => x.Id == command.ParentMaterialUnitId, cancellationToken); if (!parentExists) return ApplicationResult<Guid>.Failure(ApplicationError.NotFound("Parent material unit does not exist.")); var childExists = await _dbContext.MaterialUnits .AnyAsync(x => x.Id == command.ChildMaterialUnitId, cancellationToken); if (!childExists) return ApplicationResult<Guid>.Failure(ApplicationError.NotFound("Child material unit does not exist.")); var duplicate = await _dbContext.GenealogyEdges.AnyAsync(x => x.ParentMaterialUnitId == command.ParentMaterialUnitId && x.ChildMaterialUnitId == command.ChildMaterialUnitId && x.RelationshipType == command.RelationshipType.Trim(), cancellationToken); if (duplicate) return ApplicationResult<Guid>.Failure(ApplicationError.Conflict("Genealogy edge already exists.")); var createsCycle = await WouldCreateCycleAsync( command.ParentMaterialUnitId, command.ChildMaterialUnitId, cancellationToken); if (createsCycle) { return ApplicationResult<Guid>.Failure( ApplicationError.BusinessRule("Genealogy edge would create a material genealogy cycle.")); } | 01_Backend_Core_14Sep2026_104846.txt 19DA9E460A2D722F88729C13B7BBB49CE70DDF5D9F0577D70A44A2C096503D98 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-103 | Backend/PlantProcess.Application/Services/Materials/GenealogyService.cs | WouldCreateCycleAsync | 95 | 124 | private async Task<bool> WouldCreateCycleAsync( Guid parentMaterialUnitId, Guid childMaterialUnitId, CancellationToken cancellationToken) { var visited = new HashSet<Guid>(); var queue = new Queue<Guid>(); queue.Enqueue(parentMaterialUnitId); while (queue.Count > 0) { var current = queue.Dequeue(); if (!visited.Add(current)) continue; if (current == childMaterialUnitId) return true; var parents = await _dbContext.GenealogyEdges .AsNoTracking() .Where(x => x.ChildMaterialUnitId == current) .Select(x => x.ParentMaterialUnitId) .ToListAsync(cancellationToken); foreach (var parent in parents) queue.Enqueue(parent); } return false; | 01_Backend_Core_14Sep2026_104846.txt 19DA9E460A2D722F88729C13B7BBB49CE70DDF5D9F0577D70A44A2C096503D98 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-103 | Backend/database/scripts/841_genealogy_edge_weight_guard_topology_parity.sql | deferred weight check | 55 | 68 | -- Read the relation this trigger fired on, wherever the governed -- topology has placed it. Never a hard-coded schema. EXECUTE format( 'SELECT child_material_unit_id, sum(contribution_weight) ' ' FROM %%I.%%I ' ' WHERE COALESCE(is_deleted, false) = false ' ' GROUP BY child_material_unit_id ' 'HAVING abs(sum(contribution_weight) - 1.0) > 0.015 ' ' LIMIT 1', TG_TABLE_SCHEMA, TG_TABLE_NAME) INTO bad_child, bad_sum; IF bad_child IS NOT NULL THEN RAISE EXCEPTION 'Genealogy contribution weights must sum to 1.0 per child. child=%%, sum=%%', bad_child, bad_sum; | 02_Backend_Database_14Sep2026_104846.txt A9F5DF32B340D7BE3C37AD111F229894834924F789E8AEA7AFE6BFAAE0FCBC9F | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-104 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs | existing-row skip | 168 | 181 | var existing = await _dbContext.MaterialUnits .AsNoTracking() .Where(x => x.SiteId == siteId && x.MaterialCode == materialCode) .Select(x => x.Id) .FirstOrDefaultAsync(cancellationToken); if (existing != Guid.Empty) { // Lawful idempotency preserved: the existing contract skips, and // turning that into PV04 would quarantine correct re-projection. if (!previewOnly) stagingRecord.MarkSkipped($"MaterialUnit already exists: {materialCode}."); return RowProjectionOutcome.Skipped(existing, "MaterialUnit", $"MaterialUnit already exists: {materialCode}."); | 01_Backend_Core_14Sep2026_104846.txt B17144B6986CDC3690CA0373BBD642AAE6EFD487FC10D631B831D3C45A537699 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-104 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs | ResolveDeclaredTargetAsync | 210 | 249 | private async Task<ApplicationResult> ResolveDeclaredTargetAsync( JobDefinition job, CancellationToken cancellationToken) { if (!job.TargetDefinitionId.HasValue) { ApplicationResult<JobTargetResolution> none = await _targetResolver.ResolveAsync(job.JobType, null, cancellationToken); return none.IsFailure ? ApplicationResult.Failure(none.Error!) : ApplicationResult.Success(); } if (string.IsNullOrWhiteSpace(job.TargetDefinitionKind) ¦¦ !job.TargetVersionPolicy.HasValue) { return ApplicationResult.Failure(ApplicationError.Validation( "Job " + job.JobCode + " declares a target identity without a kind or a version policy, " + "so nothing can say which definition version it would run.")); } DefinitionKind kind; if (!Enum.TryParse(job.TargetDefinitionKind, false, out kind) ¦¦ !Enum.IsDefined(typeof(DefinitionKind), kind)) { return ApplicationResult.Failure(ApplicationError.Validation( "Job " + job.JobCode + " declares target kind '" + job.TargetDefinitionKind + "', which is not a canonical definition kind.")); } var reference = new JobTargetReference { Kind = kind, DefinitionId = job.TargetDefinitionId.Value, VersionPolicy = job.TargetVersionPolicy.Value, PinnedVersion = job.TargetDefinitionVersion, ParametersJson = job.TargetParametersJson }; ApplicationResult<JobTargetResolution> resolved = await _targetResolver.ResolveAsync(job.JobType, reference, cancellationToken); return resolved.IsFailure ? ApplicationResult.Failure(resolved.Error!) : ApplicationResult.Success(); | 01_Backend_Core_14Sep2026_104846.txt 825F46CF07A7504EA2BA2BAF66046C9E9A5157B693030F33D8916500E2B64564 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-106 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobDefinitionService.cs | schedule validation | 275 | 297 | private static ApplicationError? ValidateCreateRequest(CreateJobDefinitionRequest request) { if (string.IsNullOrWhiteSpace(request.JobCode)) return ApplicationError.Validation("Job code is required."); if (string.IsNullOrWhiteSpace(request.JobName)) return ApplicationError.Validation("Job name is required."); if (string.IsNullOrWhiteSpace(request.ScheduleExpression)) return ApplicationError.Validation("Schedule expression is required."); return null; } private static ApplicationError? ValidateUpdateRequest(UpdateJobDefinitionRequest request) { if (string.IsNullOrWhiteSpace(request.JobName)) return ApplicationError.Validation("Job name is required."); if (string.IsNullOrWhiteSpace(request.ScheduleExpression)) return ApplicationError.Validation("Schedule expression is required."); return null; | 01_Backend_Core_14Sep2026_104846.txt 68C31E779469792A74EB43E366E2C04CB857A93B4C3485B67F5C9A414B2C731D | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-106 | Backend/PlantProcess.Workers/Worker.cs | fixed cadence loops | 72 | 108 | // ── Initial delays (stagger jobs to avoid startup burst) ────────────── var nextImportRun = DateTimeOffset.UtcNow.AddSeconds(10); var nextScanRun = DateTimeOffset.UtcNow.AddSeconds(30); var nextRiskRun = DateTimeOffset.UtcNow.AddSeconds(60); var nextDeltaRun = DateTimeOffset.UtcNow.AddSeconds(15); // ← NEW while (!stoppingToken.IsCancellationRequested) { var now = DateTimeOffset.UtcNow; if (importEnabled && now >= nextImportRun) { await RunImportQueueProcessorJobAsync(importMaxBatches, importRowsPerBatch, stoppingToken); nextImportRun = DateTimeOffset.UtcNow.AddSeconds(importIntervalSeconds); } if (scanEnabled && now >= nextScanRun) { await RunDataQualityScanJobAsync(scanMaxCandidatesPerRule, stoppingToken); nextScanRun = DateTimeOffset.UtcNow.AddSeconds(scanIntervalSeconds); } if (riskEnabled && now >= nextRiskRun) { await RunRiskScoringJobAsync(riskType, riskMaxMaterials, stoppingToken); nextRiskRun = DateTimeOffset.UtcNow.AddSeconds(riskIntervalSeconds); } // ── NEW ──────────────────────────────────────────────────────────── if (deltaEnabled && now >= nextDeltaRun) { await RunDeltaImportJobAsync(deltaMaxDatasets, deltaMaxRowsPerDataset, stoppingToken); nextDeltaRun = DateTimeOffset.UtcNow.AddSeconds(deltaIntervalSeconds); } // ────────────────────────────────────────────────────────────────── await Task.Delay(TimeSpan.FromSeconds(5), stoppingToken); | 01_Backend_Core_14Sep2026_104846.txt D54B2A4C455961B4ED1AFFD0ABA16909B3D6865E2AF201D4E9A28A055EC88842 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-106 | Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs | no age/tolerance input | 33 | 39 | public static JobDependencyOutcome Evaluate( Guid dependsOnJobDefinitionId, bool isRequired, int? pinnedVersion, Guid? upstreamRunId, JobRunStatus? upstreamStatus, int? upstreamVersion) | 01_Backend_Core_14Sep2026_104846.txt B1583B5EF379E0A155A29490C9618563D6E197265CA356649ED53EC0AA720F4A | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-106 | Backend/PlantProcess.Application/Jobs/Dependencies/JobDependencyEvaluator.cs | Satisfied result | 85 | 91 | // stale_accepted would be produced here, and is not. The edge declares a // staleness tolerance but the design declares no authority that permits // accepting a stale upstream, so this runtime never claims that state. return new JobDependencyOutcome( dependsOnJobDefinitionId, upstreamRunId, JobDependencyResolution.Satisfied, false, pinnedVersion, upstreamVersion, "Upstream job " + dependsOnJobDefinitionId + " completed successfully."); | 01_Backend_Core_14Sep2026_104846.txt B1583B5EF379E0A155A29490C9618563D6E197265CA356649ED53EC0AA720F4A | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-106 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs | terminal-state switch | 127 | 146 | switch (finalStatus) { case JobRunStatus.Ok: history.MarkSucceeded(message, resultSummaryJson); job.MarkSucceeded(history.DurationMs, history.CompletedAtUtc); break; case JobRunStatus.Failed: history.MarkFailed(failureReason ?? message ?? "Job failed.", resultSummaryJson); job.MarkFailed(history.FailureReason ?? "Job failed.", history.DurationMs, history.CompletedAtUtc); break; case JobRunStatus.Timeout: history.MarkTimedOut(failureReason ?? message ?? "Job timed out.", resultSummaryJson); job.MarkTimedOut(history.FailureReason ?? "Job timed out.", history.DurationMs, history.CompletedAtUtc); break; default: return ApplicationResult<JobRunHistoryDto>.Failure( ApplicationError.Validation("Final job status must be Ok, Failed, or Timeout.")); | 01_Backend_Core_14Sep2026_104846.txt DE73F04C71484D78FCDD19EAE2A1ACF618E1A9F36E97B88CB0FC118F2F565DF9 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-106 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs | import result mapping | 262 | 276 | case JobDefinitionType.DbLinkImport: { var result = await _importBatchQueueProcessorService.ProcessPendingBatchesAsync( maxBatches: 10, rowsPerBatch: 5000, stopOnFirstError: false, runDataQualityScan: false, cancellationToken); if (result.IsFailure ¦¦ result.Value is null) { return RunNowExecutionResult.Failed( result.Error?.Message ?? "Import queue processing failed."); } return RunNowExecutionResult.Ok( $"Import queue completed. Scanned={result.Value.BatchesScanned}, Completed={result.Value.BatchesCompleted}, Failed={result.Value.BatchesFailed}.", JsonSerializer.Serialize(result.Value)); | 01_Backend_Core_14Sep2026_104846.txt 825F46CF07A7504EA2BA2BAF66046C9E9A5157B693030F33D8916500E2B64564 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-107 | Backend/PlantProcess.Workers/Worker.cs | ExecuteAsync cadence | 72 | 108 | // ── Initial delays (stagger jobs to avoid startup burst) ────────────── var nextImportRun = DateTimeOffset.UtcNow.AddSeconds(10); var nextScanRun = DateTimeOffset.UtcNow.AddSeconds(30); var nextRiskRun = DateTimeOffset.UtcNow.AddSeconds(60); var nextDeltaRun = DateTimeOffset.UtcNow.AddSeconds(15); // ← NEW while (!stoppingToken.IsCancellationRequested) { var now = DateTimeOffset.UtcNow; if (importEnabled && now >= nextImportRun) { await RunImportQueueProcessorJobAsync(importMaxBatches, importRowsPerBatch, stoppingToken); nextImportRun = DateTimeOffset.UtcNow.AddSeconds(importIntervalSeconds); } if (scanEnabled && now >= nextScanRun) { await RunDataQualityScanJobAsync(scanMaxCandidatesPerRule, stoppingToken); nextScanRun = DateTimeOffset.UtcNow.AddSeconds(scanIntervalSeconds); } if (riskEnabled && now >= nextRiskRun) { await RunRiskScoringJobAsync(riskType, riskMaxMaterials, stoppingToken); nextRiskRun = DateTimeOffset.UtcNow.AddSeconds(riskIntervalSeconds); } // ── NEW ──────────────────────────────────────────────────────────── if (deltaEnabled && now >= nextDeltaRun) { await RunDeltaImportJobAsync(deltaMaxDatasets, deltaMaxRowsPerDataset, stoppingToken); nextDeltaRun = DateTimeOffset.UtcNow.AddSeconds(deltaIntervalSeconds); } // ────────────────────────────────────────────────────────────────── await Task.Delay(TimeSpan.FromSeconds(5), stoppingToken); | 01_Backend_Core_14Sep2026_104846.txt D54B2A4C455961B4ED1AFFD0ABA16909B3D6865E2AF201D4E9A28A055EC88842 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-107 | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs | family capability vs capacity | 76 | 107 | public sealed class JobExecutionCapabilityAuthority : IJobExecutionCapabilityAuthority { private static readonly JobDefinitionType[] Executable = { JobDefinitionType.DbLinkImport, JobDefinitionType.DataQualityScan, JobDefinitionType.RiskScoring }; public IReadOnlyList<JobDefinitionType> ExecutableFamilies => Executable; public JobExecutionCapability Describe(JobDefinitionType jobType) { switch (jobType) { case JobDefinitionType.DbLinkImport: return new JobExecutionCapability( jobType, true, JobTargetRequirement.NotUsed, null, "Import queue execution is commissioned in this runtime. Its governing input " + "identity is source, dataset and connection authority, not the definition store."); case JobDefinitionType.DataQualityScan: return new JobExecutionCapability( jobType, true, JobTargetRequirement.NotUsed, null, "Data quality scanning is commissioned in this runtime. Current authority maps " + "this legacy family to no canonical definition kind."); case JobDefinitionType.RiskScoring: return new JobExecutionCapability( jobType, true, JobTargetRequirement.NotUsed, null, "Risk scoring is commissioned in this runtime. Current authority maps this " + "legacy family to no canonical definition kind."); | 01_Backend_Core_14Sep2026_104846.txt CEA3131502C263934EAD3A5775261B458CAD649FFE554E7F6B7ADD064FE2A5B6 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs | read-path selection | 120 | 151 | if (!string.IsNullOrWhiteSpace(effectiveCursorFieldName)) { var request = new DataSourceIncrementalReadRequest( dataset.ConnectionProfileId, dataset.Id, dataset.SourceObjectName, dataset.SourceSchemaName, effectiveCursorFieldName, dataset.LastCursorValue, maxRows, dataset.DatasetOptionsJson); rows = await reader.ReadRowsSinceKeyAsync( profile, dataset, request, cancellationToken); } else { rows = await reader.ReadRowsAsync( profile, dataset, new DataSourceReadRequest( dataset.ConnectionProfileId, dataset.Id, dataset.SourceObjectName, dataset.SourceSchemaName, maxRows, dataset.DatasetOptionsJson), cancellationToken); } | 01_Backend_Core_14Sep2026_104846.txt F78DD6FE12FA8F98014A67D7F34256C3EB1C36F5BF9BBB620D1A10F4F9683774 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs | row/cursor handling | 173 | 205 | string? maxCursorValue = dataset.LastCursorValue; foreach (var row in rows) { var rawJson = JsonSerializer.Serialize(row.Values); var sourceRecordId = TryGetSourceRecordId( row, effectiveCursorFieldName, rowNumber); _dbContext.StagingRecords.Add(new StagingRecord( importBatchId: batch.Id, sourceObjectName: dataset.SourceObjectName, rowNumber: rowNumber, rawJson: rawJson, isSynthetic: false, sourceSystem: profile.ProviderType, sourceRecordId: sourceRecordId)); var candidateCursor = TryGetCursorValue(row, effectiveCursorFieldName); if (!string.IsNullOrWhiteSpace(candidateCursor)) maxCursorValue = MaxCursor(maxCursorValue, candidateCursor); rowNumber++; } batch.MarkCompleted(rows.Count); if (rows.Count > 0) dataset.UpdateLastCursorValue(maxCursorValue); dataset.ScheduleNextRunAfterSuccess(); | 01_Backend_Core_14Sep2026_104846.txt F78DD6FE12FA8F98014A67D7F34256C3EB1C36F5BF9BBB620D1A10F4F9683774 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs | source identity and MaxCursor | 236 | 280 | private static string TryGetSourceRecordId( DataSourceRow row, string? cursorFieldName, int rowNumber) { var cursor = TryGetCursorValue(row, cursorFieldName); return !string.IsNullOrWhiteSpace(cursor) ? cursor : rowNumber.ToString(); } private static string? TryGetCursorValue( DataSourceRow row, string? cursorFieldName) { if (string.IsNullOrWhiteSpace(cursorFieldName)) return null; if (!row.Values.TryGetValue(cursorFieldName, out var value)) return null; return value?.ToString(); } private static string? MaxCursor(string? current, string candidate) { if (string.IsNullOrWhiteSpace(current)) return candidate; if (decimal.TryParse(current, out var currentNumber) && decimal.TryParse(candidate, out var candidateNumber)) { return candidateNumber > currentNumber ? candidate : current; } if (DateTime.TryParse(current, out var currentDate) && DateTime.TryParse(candidate, out var candidateDate)) { return candidateDate > currentDate ? candidate : current; } return string.Compare(candidate, current, StringComparison.OrdinalIgnoreCase) > 0 ? candidate : current; | 01_Backend_Core_14Sep2026_104846.txt F78DD6FE12FA8F98014A67D7F34256C3EB1C36F5BF9BBB620D1A10F4F9683774 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Infrastructure/Connectors/PostgreSql/PostgreSqlConnector.cs | scalar LIMIT query | 181 | 206 | public async Task<IReadOnlyList<DataSourceRow>> ReadRowsSinceKeyAsync( ConnectionProfile connectionProfile, SourceDatasetDefinition datasetDefinition, DataSourceIncrementalReadRequest request, CancellationToken cancellationToken) { if (string.IsNullOrWhiteSpace(request.CursorFieldName)) { throw new InvalidOperationException("CursorField is required for PostgreSQL incremental reads."); } var schemaName = SafeIdentifier(datasetDefinition.SourceSchemaName ?? connectionProfile.SchemaName ?? "public"); var tableName = SafeIdentifier(datasetDefinition.SourceObjectName); var cursorField = SafeIdentifier(request.CursorFieldName); var limit = Math.Clamp(request.Limit <= 0 ? 1000 : request.Limit, 1, 5000); var sql = $"SELECT * FROM \"{schemaName}\".\"{tableName}\" " + (string.IsNullOrWhiteSpace(request.LastCursorValue) ? string.Empty : $"WHERE \"{cursorField}\" > @lastCursor ") + $"ORDER BY \"{cursorField}\" ASC " + "LIMIT @limit;"; return await ExecuteReadAsync(connectionProfile, sql, command => { if (!string.IsNullOrWhiteSpace(request.LastCursorValue)) { command.Parameters.Add(new NpgsqlParameter("lastCursor", NpgsqlTypes.NpgsqlDbType.Unknown) { Value = request.LastCursorValue }); } command.Parameters.AddWithValue("limit", limit); }, cancellationToken); | 01_Backend_Core_14Sep2026_104846.txt 49AD494C707A03B848E2731EDB26245FB56B73C46A2EA7484323622263DFD477 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Application/Integration/Protection/ThrottlingDataSourceReader.cs | unequal protection | 36 | 70 | public async Task<IReadOnlyList<DataSourceRow>> ReadRowsAsync( ConnectionProfile connectionProfile, SourceDatasetDefinition datasetDefinition, DataSourceReadRequest request, CancellationToken cancellationToken) { var sourceKey = request.ConnectionProfileId.ToString(); var now = DateTime.UtcNow; var budget = _budgetProvider.GetBudget(connectionProfile, datasetDefinition); var queriesInLastMinute = _rateLimiter.CountWithinLastMinute(sourceKey, now); var decision = SourceLoadProtectionPolicy.Evaluate( new SourceQueryRequest( HasRowLimit: request.Limit > 0, RequestedRowLimit: request.Limit, QueriesInLastMinute: queriesInLastMinute, NowUtc: TimeOnly.FromDateTime(now)), budget); if (!decision.Allowed) { throw new SourceLoadRejectedException(decision); } _rateLimiter.Record(sourceKey, now); return await _inner.ReadRowsAsync(connectionProfile, datasetDefinition, request, cancellationToken); } public Task<IReadOnlyList<DataSourceRow>> ReadRowsSinceKeyAsync( ConnectionProfile connectionProfile, SourceDatasetDefinition datasetDefinition, DataSourceIncrementalReadRequest request, CancellationToken cancellationToken) { return _inner.ReadRowsSinceKeyAsync(connectionProfile, datasetDefinition, request, cancellationToken); } | 01_Backend_Core_14Sep2026_104846.txt F394E1D04C447E69F847EA69BE84FC4CF2C926C832145673BFD8690F63EBA825 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Infrastructure/Integration/Protection/OptionsSourceLoadBudgetProvider.cs | global budget | 21 | 24 | public SourceLoadBudget GetBudget(ConnectionProfile? connectionProfile, SourceDatasetDefinition? datasetDefinition) { return _options.CurrentValue.ToBudget(); } | 01_Backend_Core_14Sep2026_104846.txt 16C34774CBD8458200343D2ADF91A1DEDBDF05606357DB5CCE580C96F8334125 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/PlantProcess.Infrastructure/Persistence/Configurations/Integration/StagingRecordConfiguration.cs | existing within-batch uniqueness | 31 | 42 | builder.HasOne<ImportBatch>() .WithMany() .HasForeignKey(x => x.ImportBatchId) .OnDelete(DeleteBehavior.Restrict); builder.HasIndex(x => x.ImportBatchId); builder.HasIndex(x => new { x.ImportBatchId, x.IsProcessed }); builder.HasIndex(x => new { x.ImportBatchId, x.ProcessingStatus }); builder.HasIndex(x => new { x.ImportBatchId, x.SourceObjectName, x.RowNumber }).IsUnique(); builder.HasIndex(x => x.CanonicalEntityId); builder.UsePostgresXminConcurrencyToken(); | 01_Backend_Core_14Sep2026_104846.txt D4A0266CD34314BB3355A545CC79B236A23A49F83C2B77B07EDB9FCFB626EF3E | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-108 | Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs | current weak continuation assertions | 58 | 73 | public async Task TwoStageDeltaImport_MaxRowsSmallBatch_DoesNotBreakWatermarks_WhenOptInEnabled() { if (!IsEnabled()) return; using var client = await CreateAuthenticatedClientAsync(); await AssertSuccessAsync(await client.PostAsync("/admin/two-stage-import/provision-baseline", null), "provision-baseline"); var smallBatch = await PostRunAsync(client, "/admin/two-stage-import/stage1/run", maxRows: 3, timeoutSeconds: 30, maxMinutes: 1); var resumeBatch = await PostRunAsync(client, "/admin/two-stage-import/stage1/run", maxRows: 3, timeoutSeconds: 30, maxMinutes: 1); smallBatch.RootElement.TryGetProperty("rows", out var smallRows).Should().BeTrue(); resumeBatch.RootElement.TryGetProperty("rows", out var resumeRows).Should().BeTrue(); smallRows.ValueKind.Should().Be(JsonValueKind.Array); resumeRows.ValueKind.Should().Be(JsonValueKind.Array); } | 03_Backend_Tests_14Sep2026_104846.txt 1AAD7C1413F4FC64C0050229103B2BA8DF14DAD371D190B11BEC9E1826BEA405 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-109 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs | available source delta boundary | 173 | 217 | string? maxCursorValue = dataset.LastCursorValue; foreach (var row in rows) { var rawJson = JsonSerializer.Serialize(row.Values); var sourceRecordId = TryGetSourceRecordId( row, effectiveCursorFieldName, rowNumber); _dbContext.StagingRecords.Add(new StagingRecord( importBatchId: batch.Id, sourceObjectName: dataset.SourceObjectName, rowNumber: rowNumber, rawJson: rawJson, isSynthetic: false, sourceSystem: profile.ProviderType, sourceRecordId: sourceRecordId)); var candidateCursor = TryGetCursorValue(row, effectiveCursorFieldName); if (!string.IsNullOrWhiteSpace(candidateCursor)) maxCursorValue = MaxCursor(maxCursorValue, candidateCursor); rowNumber++; } batch.MarkCompleted(rows.Count); if (rows.Count > 0) dataset.UpdateLastCursorValue(maxCursorValue); dataset.ScheduleNextRunAfterSuccess(); _logger.LogInformation( "Delta import completed for dataset {DatasetCode}. Rows={Rows}, NextRunAtUtc={NextRunAtUtc}", dataset.DatasetCode, rows.Count, dataset.NextRunAtUtc); return new DeltaDatasetResult( dataset.Id.ToString(), dataset.DatasetCode, rows.Count, null); | 01_Backend_Core_14Sep2026_104846.txt F78DD6FE12FA8F98014A67D7F34256C3EB1C36F5BF9BBB620D1A10F4F9683774 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-109 | Backend/PlantProcess.Application/Relationships/RelationshipResolver.cs | governed automated path | 85 | 113 | // RL02. Exploration is manual and may traverse an unproven relationship. // Everything else is automated, and an automated consumer that trains, // scores or projects across an unproven join produces a result nobody // can defend. if (RelationshipConsumerPurposes.IsAutomated(purpose)) { var unproven = chosen .Where(e => !string.Equals(e.Relationship.ValidationState, RelationshipValidationStates.Validated, StringComparison.Ordinal)) .Select(e => e.Relationship.RelationshipCode) .OrderBy(c => c, StringComparer.Ordinal) .ToList(); if (unproven.Count > 0) { return Ok(Refuse(from, to, purpose, RelationshipRefusalCodes.UnprovenRelationship, $"The path from '{from}' to '{to}' runs through {string.Join(", ", unproven)}, which nobody has proven against real data. '{purpose}' is automated, so it may not use it; manual exploration still may.", names)); } } var steps = chosen .Select(e => new RelationshipPathStepDto(e.Relationship.Id, e.From, e.To)) .ToList(); return Ok(new RelationshipResolutionDto( from, to, purpose, true, steps, chosen.Any(e => e.Relationship.IsGrainConverting), null, null, names)); | 01_Backend_Core_14Sep2026_104846.txt CF80A487057CE68B75618A7589B5A47CF690DBAFE59835EC9A1CB8B36D67EC9D | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-207 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs | HistorianConnectorCapabilities | 61 | 108 | public static class HistorianConnectorCapabilities { public const string NotExecutableCode = "OT01"; public const string NotExecutableMessage = "This connector operation is declared but not executable in this build. " + "It returns no value rather than a placeholder."; public const string ConfigurationValidation = "configurationValidation"; public const string MappingHintsFromSuppliedTagPaths = "mappingHintsFromSuppliedTagPaths"; public const string TagBrowse = "tagBrowse"; public const string BoundedRead = "boundedRead"; public const string Subscription = "subscription"; public const string LiveVendorHandshake = "liveVendorHandshake"; public static readonly IReadOnlyList<ConnectorCapability> All = new[] { new ConnectorCapability( ConfigurationValidation, true, "The /test-connection route validates the supplied endpoint and read-only posture and returns no measurement."), new ConnectorCapability( MappingHintsFromSuppliedTagPaths, true, "The /mapping-hints route classifies tag paths the caller supplied. It never supplies tag paths of its own."), new ConnectorCapability( TagBrowse, false, "Real OPC UA namespace browse is not yet implemented."), new ConnectorCapability( BoundedRead, false, "Real OPC UA value acquisition is not yet implemented."), new ConnectorCapability( Subscription, false, "Real OPC UA monitored items and subscriptions are not yet implemented."), new ConnectorCapability( LiveVendorHandshake, false, "Real OPC UA session security, certificate and trust handling is not yet implemented.") }; public static bool IsExecutable(string name) { foreach (var capability in All) { if (string.Equals(capability.Name, name, StringComparison.Ordinal)) { return capability.Executable; } } return false; | 01_Backend_Core_14Sep2026_104846.txt A45C75DF4E4C2C493195ACC5F08E46E668AF1094AC977729092C961E1AA55790 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-212 | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs | ResolveAsync | 30 | 74 | public async Task<ApplicationResult<ResolvedAggregation>> ResolveAsync( Guid tenantId, Guid parameterId, Guid? kpiBindingId, AggregationKind? requested, CancellationToken cancellationToken) { var connection = await OpenAsync(cancellationToken); await using var command = Command( "SELECT resolved_kind, resolution_source, refusal_code, refusal_message, signal_kind, sampling_basis, " + "weight_basis, semantics_version FROM ppiq_meta.resolve_aggregation_semantics(@tenant, @parameter, @binding, @requested);", connection); command.Parameters.Add(new NpgsqlParameter("tenant", NpgsqlDbType.Uuid) { Value = tenantId }); command.Parameters.Add(new NpgsqlParameter("parameter", NpgsqlDbType.Uuid) { Value = parameterId }); command.Parameters.Add(new NpgsqlParameter("binding", NpgsqlDbType.Uuid) { Value = kpiBindingId.HasValue ? kpiBindingId.Value : (object)DBNull.Value }); command.Parameters.Add(new NpgsqlParameter("requested", NpgsqlDbType.Varchar) { Value = requested.HasValue ? requested.Value.ToString() : (object)DBNull.Value }); await using var reader = await command.ExecuteReaderAsync(cancellationToken); if (!await reader.ReadAsync(cancellationToken)) { return ApplicationResult<ResolvedAggregation>.Failure(ApplicationError.Validation( AggregationRefusal.SemanticsUndeclared + ": the resolver returned no row.")); } var refusal = reader.IsDBNull(2) ? null : reader.GetString(2); if (refusal is not null) { // The message carries everything ruling 17 asks a failure to name: // parameter, signal kind, sampling basis, requested method, source. var detail = reader.IsDBNull(3) ? string.Empty : reader.GetString(3); var message = refusal + ": " + detail + " [parameter=" + parameterId + " signal=" + (reader.IsDBNull(4) ? "none" : reader.GetString(4)) + " sampling=" + (reader.IsDBNull(5) ? "none" : reader.GetString(5)) + " requested=" + (requested.HasValue ? requested.Value.ToString() : "none") + " source=" + reader.GetString(1) + "]"; return ApplicationResult<ResolvedAggregation>.Failure(ApplicationError.Validation(message)); | 01_Backend_Core_14Sep2026_104846.txt 51509BFC035F69D886A1F448B119075421412EB1E6BE62CA879F6BA03D05C801 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-212 | Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts | not analytics mathematics | 1 | 9 | // Governed aggregate/window binding for Canvas. // // This module owns NO aggregation vocabulary and NO window catalogue. // It consumes canonical metadata/options produced elsewhere and copies only // published authority into node data. Missing aggregation is AG01. Nothing // silently becomes Average, and nothing invents a window. // // T-245 later compiles these validated declarations onto governed runtime // contracts. This module deliberately performs no analytics mathematics. | 04_Frontend_App_14Sep2026_104846.txt FA679E784FE6955D66CB844F2B02D3D81AE4CCB5CE40E3C879A70D824E3C0885 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-213 | Backend/PlantProcess.Api/Endpoints/CustomerAssessmentEndpoints.cs | assessment routes and tenant gate | 86 | 125 | public static class CustomerAssessmentEndpoints { public const string BasePath = "/api/onboarding/assessments"; // The tenant reader is stateless and delegates to the existing tenancy // authority. It is held here rather than injected, because an // interface-typed handler parameter that is not a registered service // makes ASP.NET Core infer it as a request body: two inferred bodies // on POST and an inferred body on GET both throw while the endpoint // table is built, which fails host startup - and every test sharing // that host then reports a disposed service provider. Nothing about // the reader's semantics changed; only how the handlers reach it. private static readonly ICustomerAssessmentTenantReader Tenants = new CustomerAssessmentTenantReader(); public static IEndpointRouteBuilder MapCustomerAssessmentEndpoints(this IEndpointRouteBuilder routes) { RouteGroupBuilder group = routes.MapGroup(BasePath).RequireAuthorization(); group.MapPost("/", AssessAsync); group.MapGet("/{lineageCode}/latest", LatestAsync); group.MapGet("/{lineageCode}/versions/{versionNumber:int}", VersionAsync); group.MapGet("/{lineageCode}/diff", DiffAsync); return routes; } private static async Task<IResult> AssessAsync( HttpContext context, CustomerAssessmentRequest request, [FromServices] ICustomerAssessmentService service, CancellationToken cancellationToken) { Guid tenantId; if (!Tenants.TryResolve(context, out tenantId) ¦¦ tenantId == Guid.Empty) { return Results.Forbid(); } if (request == null ¦¦ request.Intake == null) { | 01_Backend_Core_14Sep2026_104846.txt F31F40CD8F585BFC6B17C3038DA79F96F6C80D13ECE838648DE52939A7A868F9 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-224 | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs | configuration test | 24 | 72 | public Task<DataSourceConnectionTestResult> TestConnectionAsync( ConnectionProfile connectionProfile, CancellationToken cancellationToken) { try { cancellationToken.ThrowIfCancellationRequested(); var endpointUrl = FirstNonEmpty( connectionProfile.ApiBaseUrl, GetJsonString(connectionProfile.ConnectionOptionsJson, "endpointUrl", "opcEndpointUrl", "historianEndpointUrl"), connectionProfile.HostName); if (string.IsNullOrWhiteSpace(endpointUrl)) return Task.FromResult(Failure("Historian connector requires ApiBaseUrl, HostName, or connectionOptionsJson.endpointUrl.")); var namespaceUri = FirstNonEmpty( GetJsonString(connectionProfile.ConnectionOptionsJson, "namespaceUri", "namespace", "tagNamespace"), connectionProfile.SchemaName); var readOnly = GetJsonBool(connectionProfile.ConnectionOptionsJson, "readOnly") ?? connectionProfile.ReadOnlyEnforced; var requireLiveHandshake = GetJsonBool(connectionProfile.ConnectionOptionsJson, "requireLiveHandshake") ?? false; if (!readOnly) return Task.FromResult(Failure("Historian connector is read-only. Set readOnly=true / ReadOnlyEnforced=true.")); if (requireLiveHandshake) return Task.FromResult(Failure("Live vendor handshake was requested, but no customer historian gateway is attached in this environment. Configuration is not marked as reachable.")); var metadata = new Dictionary<string, string?> { ["providerType"] = ProviderType, ["mode"] = "read-only-gateway", ["endpointUrl"] = endpointUrl, ["namespaceUri"] = namespaceUri, ["readOnly"] = readOnly.ToString(CultureInfo.InvariantCulture), ["supportsTagBrowse"] = "true", ["supportsBoundedRead"] = "true", ["supportsMappingHints"] = "true", ["liveHandshake"] = "environment-specific" }; _lastError = null; return Task.FromResult(new DataSourceConnectionTestResult( IsSuccess: true, Message: "Historian gateway configuration is valid for read-only onboarding. Live vendor handshake remains environment-specific.", TestedAtUtc: DateTime.UtcNow, Metadata: metadata)); | 01_Backend_Core_14Sep2026_104846.txt D9953F23C2E7C2E841D49E46901D3EAD698C03423ACAF6C2D2FEB2250523B314 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-224 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs | live capability declarations | 84 | 95 | new ConnectorCapability( TagBrowse, false, "Real OPC UA namespace browse is not yet implemented."), new ConnectorCapability( BoundedRead, false, "Real OPC UA value acquisition is not yet implemented."), new ConnectorCapability( Subscription, false, "Real OPC UA monitored items and subscriptions are not yet implemented."), new ConnectorCapability( LiveVendorHandshake, false, "Real OPC UA session security, certificate and trust handling is not yet implemented.") | 01_Backend_Core_14Sep2026_104846.txt A45C75DF4E4C2C493195ACC5F08E46E668AF1094AC977729092C961E1AA55790 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-225 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs | browse/read/subscription capability state | 76 | 95 | public static readonly IReadOnlyList<ConnectorCapability> All = new[] { new ConnectorCapability( ConfigurationValidation, true, "The /test-connection route validates the supplied endpoint and read-only posture and returns no measurement."), new ConnectorCapability( MappingHintsFromSuppliedTagPaths, true, "The /mapping-hints route classifies tag paths the caller supplied. It never supplies tag paths of its own."), new ConnectorCapability( TagBrowse, false, "Real OPC UA namespace browse is not yet implemented."), new ConnectorCapability( BoundedRead, false, "Real OPC UA value acquisition is not yet implemented."), new ConnectorCapability( Subscription, false, "Real OPC UA monitored items and subscriptions are not yet implemented."), new ConnectorCapability( LiveVendorHandshake, false, "Real OPC UA session security, certificate and trust handling is not yet implemented.") | 01_Backend_Core_14Sep2026_104846.txt A45C75DF4E4C2C493195ACC5F08E46E668AF1094AC977729092C961E1AA55790 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-225 | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs | metadata-only legacy claim | 53 | 70 | var metadata = new Dictionary<string, string?> { ["providerType"] = ProviderType, ["mode"] = "read-only-gateway", ["endpointUrl"] = endpointUrl, ["namespaceUri"] = namespaceUri, ["readOnly"] = readOnly.ToString(CultureInfo.InvariantCulture), ["supportsTagBrowse"] = "true", ["supportsBoundedRead"] = "true", ["supportsMappingHints"] = "true", ["liveHandshake"] = "environment-specific" }; _lastError = null; return Task.FromResult(new DataSourceConnectionTestResult( IsSuccess: true, Message: "Historian gateway configuration is valid for read-only onboarding. Live vendor handshake remains environment-specific.", | 01_Backend_Core_14Sep2026_104846.txt D9953F23C2E7C2E841D49E46901D3EAD698C03423ACAF6C2D2FEB2250523B314 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-226 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs | upstream live-operation boundary | 84 | 95 | new ConnectorCapability( TagBrowse, false, "Real OPC UA namespace browse is not yet implemented."), new ConnectorCapability( BoundedRead, false, "Real OPC UA value acquisition is not yet implemented."), new ConnectorCapability( Subscription, false, "Real OPC UA monitored items and subscriptions are not yet implemented."), new ConnectorCapability( LiveVendorHandshake, false, "Real OPC UA session security, certificate and trust handling is not yet implemented.") | 01_Backend_Core_14Sep2026_104846.txt A45C75DF4E4C2C493195ACC5F08E46E668AF1094AC977729092C961E1AA55790 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-226 | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs | existing time kernel | 26 | 66 | public static SourceTimeResolution Resolve( SourceTimeAuthorityRegistry registry, string? sourceKey, string? signalKey, RawSourceTime raw) { ArgumentNullException.ThrowIfNull(registry); ArgumentNullException.ThrowIfNull(raw); if (!registry.TryGetSignal(sourceKey, signalKey, out var declaration) ¦¦ declaration is null) { return Refuse(SourceTimeCodes.SignalNotDeclared); } var offset = ResolveOffset(declaration, raw, out var localValue, out var offsetCode); if (offset is null) { return Refuse(offsetCode); } if (!SourceTimeAuthorityRegistry.IsOffsetInRange(offset.Value)) { return Refuse(SourceTimeCodes.OffsetDeclarationConflict); } var instant = new DateTimeOffset( DateTime.SpecifyKind(localValue, DateTimeKind.Unspecified), offset.Value); return new SourceTimeResolution( IsResolved: true, new TemporalInstant( instant, declaration.Role, declaration.SourceKey, declaration.SignalKey, declaration.Uncertainty), SourceTimeCodes.TimeResolved, TerminalState.Finding, ExclusionAttribution.None); | 01_Backend_Core_14Sep2026_104846.txt 3B93B5E6473747838D639C016E970CC96D29F28B56F7A9199E9C1B2282B2BF14 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-232 | Backend/PlantProcess.Infrastructure/Definitions/Semantics/SignalSemanticsResolver.cs | existing semantic infrastructure only | 30 | 74 | public async Task<ApplicationResult<ResolvedAggregation>> ResolveAsync( Guid tenantId, Guid parameterId, Guid? kpiBindingId, AggregationKind? requested, CancellationToken cancellationToken) { var connection = await OpenAsync(cancellationToken); await using var command = Command( "SELECT resolved_kind, resolution_source, refusal_code, refusal_message, signal_kind, sampling_basis, " + "weight_basis, semantics_version FROM ppiq_meta.resolve_aggregation_semantics(@tenant, @parameter, @binding, @requested);", connection); command.Parameters.Add(new NpgsqlParameter("tenant", NpgsqlDbType.Uuid) { Value = tenantId }); command.Parameters.Add(new NpgsqlParameter("parameter", NpgsqlDbType.Uuid) { Value = parameterId }); command.Parameters.Add(new NpgsqlParameter("binding", NpgsqlDbType.Uuid) { Value = kpiBindingId.HasValue ? kpiBindingId.Value : (object)DBNull.Value }); command.Parameters.Add(new NpgsqlParameter("requested", NpgsqlDbType.Varchar) { Value = requested.HasValue ? requested.Value.ToString() : (object)DBNull.Value }); await using var reader = await command.ExecuteReaderAsync(cancellationToken); if (!await reader.ReadAsync(cancellationToken)) { return ApplicationResult<ResolvedAggregation>.Failure(ApplicationError.Validation( AggregationRefusal.SemanticsUndeclared + ": the resolver returned no row.")); } var refusal = reader.IsDBNull(2) ? null : reader.GetString(2); if (refusal is not null) { // The message carries everything ruling 17 asks a failure to name: // parameter, signal kind, sampling basis, requested method, source. var detail = reader.IsDBNull(3) ? string.Empty : reader.GetString(3); var message = refusal + ": " + detail + " [parameter=" + parameterId + " signal=" + (reader.IsDBNull(4) ? "none" : reader.GetString(4)) + " sampling=" + (reader.IsDBNull(5) ? "none" : reader.GetString(5)) + " requested=" + (requested.HasValue ? requested.Value.ToString() : "none") + " source=" + reader.GetString(1) + "]"; return ApplicationResult<ResolvedAggregation>.Failure(ApplicationError.Validation(message)); | 01_Backend_Core_14Sep2026_104846.txt 51509BFC035F69D886A1F448B119075421412EB1E6BE62CA879F6BA03D05C801 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-233 | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs | Resolve / ResolveAs | 26 | 97 | public static SourceTimeResolution Resolve( SourceTimeAuthorityRegistry registry, string? sourceKey, string? signalKey, RawSourceTime raw) { ArgumentNullException.ThrowIfNull(registry); ArgumentNullException.ThrowIfNull(raw); if (!registry.TryGetSignal(sourceKey, signalKey, out var declaration) ¦¦ declaration is null) { return Refuse(SourceTimeCodes.SignalNotDeclared); } var offset = ResolveOffset(declaration, raw, out var localValue, out var offsetCode); if (offset is null) { return Refuse(offsetCode); } if (!SourceTimeAuthorityRegistry.IsOffsetInRange(offset.Value)) { return Refuse(SourceTimeCodes.OffsetDeclarationConflict); } var instant = new DateTimeOffset( DateTime.SpecifyKind(localValue, DateTimeKind.Unspecified), offset.Value); return new SourceTimeResolution( IsResolved: true, new TemporalInstant( instant, declaration.Role, declaration.SourceKey, declaration.SignalKey, declaration.Uncertainty), SourceTimeCodes.TimeResolved, TerminalState.Finding, ExclusionAttribution.None); } /// <summary> /// Resolve a raw timestamp and require that the signal was declared to answer a /// particular question. The role is verified against the declaration, never imposed /// on it. /// </summary> public static SourceTimeResolution ResolveAs( SourceTimeAuthorityRegistry registry, string? sourceKey, string? signalKey, TimeRole requiredRole, RawSourceTime raw) { ArgumentNullException.ThrowIfNull(registry); if (!registry.TryGetSignal(sourceKey, signalKey, out var declaration) ¦¦ declaration is null) { return Refuse(SourceTimeCodes.SignalNotDeclared); } if (declaration.Role != requiredRole) { // Arrival time is always available and almost never the answer. A product // that substitutes it produces a complete, plausible, wrong timeline. return Refuse(requiredRole == TimeRole.Effective ? SourceTimeCodes.EffectiveTimeUnavailable : SourceTimeCodes.RoleNotAuthorised); } return Resolve(registry, sourceKey, signalKey, raw); | 01_Backend_Core_14Sep2026_104846.txt 3B93B5E6473747838D639C016E970CC96D29F28B56F7A9199E9C1B2282B2BF14 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-233 | Backend/PlantProcess.Application/Integration/Services/Mapping/MappingRowProjector.cs | current material time fields | 184 | 210 | var productFamily = reader.OptionalString("ProductFamily"); var gradeOrRecipe = reader.OptionalString("GradeOrRecipe"); var sourceRecordId = reader.OptionalString("SourceRecordId"); var startUtc = reader.OptionalDateTime("ProductionStartUtc"); var endUtc = reader.OptionalDateTime("ProductionEndUtc"); var offsetMinutes = reader.OptionalInt("PlantUtcOffsetMinutes"); var timeZoneId = reader.OptionalString("PlantTimeZoneId"); if (reader.Failed) return Refused(reader); var material = new MaterialUnit( materialCode: materialCode!, materialUnitType: materialUnitType!, siteId: siteId!.Value, productFamily: productFamily, gradeOrRecipe: gradeOrRecipe, isSynthetic: stagingRecord.IsSynthetic, sourceSystem: stagingRecord.SourceSystem ?? mapping.SourceSystem, sourceRecordId: stagingRecord.SourceRecordId ?? sourceRecordId); if (startUtc.HasValue) { material.SetProductionWindow( startUtc.Value, endUtc, TimeSpan.FromMinutes(offsetMinutes ?? 0), timeZoneId ?? "UTC"); | 01_Backend_Core_14Sep2026_104846.txt B17144B6986CDC3690CA0373BBD642AAE6EFD487FC10D631B831D3C45A537699 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-235 | Backend/PlantProcess.Analytics.Core/Kernel/Regime/TransitionAwarePoolingGuard.cs | Admit | 24 | 79 | public static PoolingAdmission Admit( OperationalTransitionRegistry registry, string? scopeKey, IReadOnlyList<RegimeScopedSample> samples, StabilisationObservation observation) { ArgumentNullException.ThrowIfNull(registry); ArgumentNullException.ThrowIfNull(samples); ArgumentNullException.ThrowIfNull(observation); if (samples.Count == 0 ¦¦ samples.Any(s => s is null)) { // An empty population is not a population that agrees with itself. Returning // an admission here would let a downstream statistic report a confident // answer computed from nothing. return Refuse(PoolingGuardCodes.EmptyPopulation, 0); } if (!DeclaredKey.TryNormalise(scopeKey, out var scope)) { return Refuse(OperationalTransitionCodes.ScopeNotDeclared, samples.Count); } if (samples.Any(s => !string.Equals(Normalise(s.ScopeKey), scope, StringComparison.Ordinal))) { // Samples from different scopes have different declared transitions, so a // single regime verdict would not mean anything. return Refuse(PoolingGuardCodes.HeterogeneousScope, samples.Count); } var regimes = new List<OperationalRegime>(); foreach (var sample in samples) { var atPoint = registry.IsScopeDeclared(scope) ? OperationalTransitionKernel.ClassifyInstant(registry, scope, sample.Instant.Instant, observation) : null; if (atPoint is null ¦¦ !atPoint.IsDecided) { // The regime classifier's refusal is the guard's refusal. Nothing here // second-guesses it. return Refuse(atPoint?.Code ?? OperationalTransitionCodes.ScopeNotDeclared, samples.Count); } var earliest = OperationalTransitionKernel.ClassifyInstant(registry, scope, sample.Instant.EarliestPossible, observation); var latest = OperationalTransitionKernel.ClassifyInstant(registry, scope, sample.Instant.LatestPossible, observation); if (!earliest.IsDecided) return Refuse(earliest.Code, samples.Count); if (!latest.IsDecided) return Refuse(latest.Code, samples.Count); if (earliest.Regime != atPoint.Regime ¦¦ latest.Regime != atPoint.Regime) { // This sample could have been taken on either side of a changeover. Which // side its point estimate happens to land on is not evidence. return Refuse(PoolingGuardCodes.SampleRegimeTemporallyUncertain, samples.Count); | 01_Backend_Core_14Sep2026_104846.txt 4395CEFB50AAC94D6917511AE5E2A68E42A123B30E4A123E8ED9FBAA09A00209 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-235 | Backend/PlantProcess.Analytics.Core/Kernel/Time/SourceTimeAuthorityKernel.cs | time interpretation | 26 | 66 | public static SourceTimeResolution Resolve( SourceTimeAuthorityRegistry registry, string? sourceKey, string? signalKey, RawSourceTime raw) { ArgumentNullException.ThrowIfNull(registry); ArgumentNullException.ThrowIfNull(raw); if (!registry.TryGetSignal(sourceKey, signalKey, out var declaration) ¦¦ declaration is null) { return Refuse(SourceTimeCodes.SignalNotDeclared); } var offset = ResolveOffset(declaration, raw, out var localValue, out var offsetCode); if (offset is null) { return Refuse(offsetCode); } if (!SourceTimeAuthorityRegistry.IsOffsetInRange(offset.Value)) { return Refuse(SourceTimeCodes.OffsetDeclarationConflict); } var instant = new DateTimeOffset( DateTime.SpecifyKind(localValue, DateTimeKind.Unspecified), offset.Value); return new SourceTimeResolution( IsResolved: true, new TemporalInstant( instant, declaration.Role, declaration.SourceKey, declaration.SignalKey, declaration.Uncertainty), SourceTimeCodes.TimeResolved, TerminalState.Finding, ExclusionAttribution.None); | 01_Backend_Core_14Sep2026_104846.txt 3B93B5E6473747838D639C016E970CC96D29F28B56F7A9199E9C1B2282B2BF14 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-241 | Frontend/PlantProcess.Web/src/authoring/graphSemantics.ts | typed-port authority | 22 | 40 | import { FILTER_OPERATORS, MATH_OPERATORS, isUnaryFilterOperator, fieldDisplayName, hasResolvableLineage, type FieldLineage, } from "./operatorContract"; import type { DerivedSpec, FilterSpec, MapperGraph, SelectSpec, StagedDataset, } from "@/api/canvasApi"; // Port typing lives in the canvas layer and is pure, so the refusal set can // use it without pulling any React into this module. import { inferPortType, portsCompatible, type PortType } from "@/canvas/ports"; import { parameterValueProblem } from "./blockParameters"; import { contractForKind } from "./blockRegistry"; /** * A field as the BOARD sees it. * * FieldLineage, frozen in T-033a, describes a PHYSICAL field: origin table, * origin column, SQL type, display identity. A DERIVED column is a real field * of the downstream dataset - it has a name and a known type - but it has no | 04_Frontend_App_14Sep2026_104846.txt 7F3AC3414B1A2CB82B36999804E4C04BB324CB52F297402848500231B4D69A9F | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-241 | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts | capability separation | 13 | 45 | // T-242 Stage 3. THE REGISTRY IS NOW THE ONLY BLOCK CATALOGUE. // // It previously shared that job with four hardcoded maps in the authoring // shell - an addable-id list, a block-id-to-kind map, a kind-to-title map and // a seed ternary - so adding one family meant editing four places that could // disagree with each other and with this file. A row here is now the whole // declaration: identity, kind, title, ports, group, starting parameters and // what the product can actually DO with the block. export interface BlockGroupDefinition { id: string; label: string; /** Section 5.2.14 - the advanced set is collapsed by default, never hidden. */ advanced: boolean; } /** * WHAT THE PRODUCT CAN DO WITH A BLOCK, stated as separate facts rather than * one overloaded boolean nobody can define a year later. * * implemented its behaviour and validation exist; * evaluable the deterministic block algebra can compute it; * persistable the canonical save/version/reopen path can REPRESENT it. * * These are independent. A relational block is implemented and persistable but * not evaluable, because its meaning is a SELECT the server runs. A compute * block is implemented and evaluable but not yet persistable, because the * transformation representation cannot carry it. */ export interface BlockCapabilities { readonly evaluable: boolean; readonly persistable: boolean; } | 04_Frontend_App_14Sep2026_104846.txt BF4E22FC0ABF9F26AF3B9DCDBA1428BCBCE3198B7D009C828055AF54B95D0C85 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-242 | Frontend/PlantProcess.Web/src/authoring/blockRegistry.ts | one catalogue and separate capabilities | 13 | 45 | // T-242 Stage 3. THE REGISTRY IS NOW THE ONLY BLOCK CATALOGUE. // // It previously shared that job with four hardcoded maps in the authoring // shell - an addable-id list, a block-id-to-kind map, a kind-to-title map and // a seed ternary - so adding one family meant editing four places that could // disagree with each other and with this file. A row here is now the whole // declaration: identity, kind, title, ports, group, starting parameters and // what the product can actually DO with the block. export interface BlockGroupDefinition { id: string; label: string; /** Section 5.2.14 - the advanced set is collapsed by default, never hidden. */ advanced: boolean; } /** * WHAT THE PRODUCT CAN DO WITH A BLOCK, stated as separate facts rather than * one overloaded boolean nobody can define a year later. * * implemented its behaviour and validation exist; * evaluable the deterministic block algebra can compute it; * persistable the canonical save/version/reopen path can REPRESENT it. * * These are independent. A relational block is implemented and persistable but * not evaluable, because its meaning is a SELECT the server runs. A compute * block is implemented and evaluable but not yet persistable, because the * transformation representation cannot carry it. */ export interface BlockCapabilities { readonly evaluable: boolean; readonly persistable: boolean; } | 04_Frontend_App_14Sep2026_104846.txt BF4E22FC0ABF9F26AF3B9DCDBA1428BCBCE3198B7D009C828055AF54B95D0C85 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-242 | Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts | handoff boundary | 1 | 9 | // Governed aggregate/window binding for Canvas. // // This module owns NO aggregation vocabulary and NO window catalogue. // It consumes canonical metadata/options produced elsewhere and copies only // published authority into node data. Missing aggregation is AG01. Nothing // silently becomes Average, and nothing invents a window. // // T-245 later compiles these validated declarations onto governed runtime // contracts. This module deliberately performs no analytics mathematics. | 04_Frontend_App_14Sep2026_104846.txt FA679E784FE6955D66CB844F2B02D3D81AE4CCB5CE40E3C879A70D824E3C0885 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-242 | Frontend/PlantProcess.Web/src/authoring/governedBlockBinding.ts | AG01 behavior | 49 | 77 | export function bindGovernedAggregate( metadata: CanonicalRegistryMetadata, measureCode: string, ): GovernedAggregateBinding { const code = clean(measureCode); const measures = Array.isArray(metadata.measures) ? metadata.measures : []; const measure = measures.find((item) => clean(item.code) === code); if (!measure) { return { ok: false, refusal: { code: "MEASURE_AUTHORITY_UNDECLARED", message: "The selected measure is not published by canonical registry metadata.", }, }; } const refusal = (Array.isArray(metadata.refusals) ? metadata.refusals : []) .find((item) => clean(item.code) === code && clean(item.errorCode) === "AG01"); const aggregation = clean(measure.aggregation); if (refusal ¦¦ aggregation.length === 0) { return { ok: false, refusal: { code: "AG01", message: clean(refusal?.message) ¦¦ "aggregation_semantics_undeclared", }, | 04_Frontend_App_14Sep2026_104846.txt FA679E784FE6955D66CB844F2B02D3D81AE4CCB5CE40E3C879A70D824E3C0885 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-243 | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs | canonical graph/board content | 106 | 163 | public static string ForGraph(string graphJson, string outputTarget) { if (string.IsNullOrWhiteSpace(outputTarget)) { throw new ArgumentException( "A governed output target is required. It is never defaulted.", nameof(outputTarget)); } var graph = ParseObject(graphJson, "graph"); var declared = TrimmedOrNull(graph[GraphTargetEntity]); var target = outputTarget.Trim(); // T-243. The browser sends the board INSIDE the graph payload, because that is // the one blob the existing session draft carries and this task introduces no // second transport. It is lifted out here so the stored graph stays the clean // execution shape the SQL generator reads, and the board stands on its own. JsonNode? board = null; if (graph[RootBoard] is JsonNode authored) { board = authored.DeepClone(); graph.Remove(RootBoard); } if (declared is not null && !string.Equals(declared, target, StringComparison.Ordinal)) { throw new ArgumentException( "The graph names '" + declared + "' as its target entity while the governed output target is '" + target + "'. One definition cannot carry two output identities.", nameof(outputTarget)); } // T-262. The declaration rides inside the graph payload for the same reason the // board does: the session draft is one blob and this task introduces no second // transport. It is lifted to the root so the stored graph stays the clean // execution shape, and the declaration stands beside it as its own fact. JsonNode? projection = null; if (graph[RootProjection] is JsonNode declared2) { projection = declared2.DeepClone(); graph.Remove(RootProjection); } var root = new JsonObject { ["graph"] = Canonicalise(graph), [RootOutputTarget] = target, ["representation"] = RepresentationGraph, }; if (board is not null) { root[RootBoard] = Canonicalise(board); } if (projection is not null) { root[RootProjection] = Canonicalise(projection); } | 01_Backend_Core_14Sep2026_104846.txt 247AF15F98CF2A8AF8C4C2FE634C9A55738829B1DE435C5BBC417D1F0B82A347 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-243 | Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs | publish transaction | 265 | 333 | await using var transaction = await _db.Database.BeginTransactionAsync(cancellationToken); var published = await _writer.PublishAsync(definitionId, versionNumber, cancellationToken); if (published.IsFailure) { await transaction.RollbackAsync(cancellationToken); return ApplicationResult<CanvasDefinitionVersion>.Failure(published.Error!); } var version = published.Value!; var representation = CanvasDefinitionContent.Read(version.ContentJson); try { var connection = (NpgsqlConnection)_db.Database.GetDbConnection(); var npgsqlTransaction = (NpgsqlTransaction)transaction.GetDbTransaction(); if (representation.Representation == CanvasDefinitionContent.RepresentationGraph) { if (handles.SessionId is null) { await transaction.RollbackAsync(cancellationToken); return Refuse("A graph definition cannot be published without its session handle for the execution projection."); } await _projection.ProjectGraphVersionAsync( connection, npgsqlTransaction, tenantId, handles.SessionId.Value, version.VersionNumber, representation.GraphJson ?? "{}", handles.PublishedBy ?? "canvas", cancellationToken); } else { // Built as a JsonObject rather than an anonymous type. The // forked graph is already JSON text, and a nullable // JsonElement in an anonymous object has no inferable common // type with null - it is a value type. Composing the node // keeps the absent case genuinely absent instead of emitting // a null the projection would have to interpret. var projectionNode = new JsonObject { ["body"] = "sql", ["sql"] = representation.Sql, ["canonicalDefinitionId"] = definitionId.ToString(), ["canonicalVersion"] = version.VersionNumber, }; if (!string.IsNullOrWhiteSpace(representation.ForkedFromGraphJson)) { projectionNode["forkedFromGraph"] = JsonNode.Parse(representation.ForkedFromGraphJson); } var definitionJson = projectionNode.ToJsonString(); await _projection.ProjectSqlVersionAsync( connection, npgsqlTransaction, definitionCode.Trim(), handles.DisplayName, handles.CanonicalEntity, version.VersionNumber, definitionJson, SqlProjectionStatus, cancellationToken); } } catch (Exception ex) when (ex is NpgsqlException or InvalidOperationException) { // The canonical publish succeeded inside this transaction and the // projection did not. Neither survives: that is the whole point. await transaction.RollbackAsync(cancellationToken); return ApplicationResult<CanvasDefinitionVersion>.Failure(ApplicationError.Infrastructure( "Published nothing. The execution projection failed and the canonical publish was rolled back with it: " + ex.Message)); | 01_Backend_Core_14Sep2026_104846.txt BBB6A7BC44D5A51F537E5142EBA51F450F12BB3F6D0C29673346F587A1F4802B | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-243 | Backend/PlantProcess.Application/Relationships/RelationshipService.cs | existing publication seam | 145 | 217 | IReadOnlyList<RelationshipEntityDto> entities = counts .Select(pair => new RelationshipEntityDto(pair.Key, pair.Value)) .ToList(); return ApplicationResult<IReadOnlyList<RelationshipEntityDto>>.Success(entities); } public async Task<ApplicationResult<IReadOnlyList<RelationshipDto>>> PublishAsync( RelationshipPublicationRequest request, CancellationToken cancellationToken) { if (request is null) return Fail("A publication carries at least one declaration."); if (!_tenantAccessor.TryGetTenantId(out var tenantId)) return Fail("No tenant on the caller; a relationship cannot be published without one."); if (request.SourceDefinitionId == Guid.Empty) return Fail("A relationship must name the definition that published it."); if (request.SourceDefinitionVersion <= 0) return Fail("A relationship must name the definition VERSION that published it, so a historical result stays explainable after the model changes."); if (request.Relationships is null ¦¦ request.Relationships.Count == 0) return Fail("A publication with no declarations is not a publication."); foreach (var declaration in request.Relationships) { var refusal = Validate(declaration); if (refusal is not null) return Fail(refusal); } var effectiveFromUtc = DateTime.UtcNow; // Republication supersedes rather than deletes. The prior emission is // retired first so the unique code is free, and its rows stay readable. await _store.RetireByDefinitionAsync(tenantId, request.SourceDefinitionId, effectiveFromUtc, cancellationToken); foreach (var declaration in request.Relationships) { await _store.UpsertAsync( tenantId, declaration, request.SourceDefinitionId, request.SourceDefinitionVersion, effectiveFromUtc, cancellationToken); } // Returned by reading BACK, never by echoing the request. An emission // that cannot be read is not a publication, and echoing would hide that. var published = await _store.ReadPublishedAsync(tenantId, null, cancellationToken); var emitted = published .Where(r => r.SourceDefinitionId == request.SourceDefinitionId && r.SourceDefinitionVersion == request.SourceDefinitionVersion) .ToList(); return ApplicationResult<IReadOnlyList<RelationshipDto>>.Success(emitted); } public async Task<ApplicationResult<int>> RetireByDefinitionAsync( Guid sourceDefinitionId, CancellationToken cancellationToken) { if (!_tenantAccessor.TryGetTenantId(out var tenantId)) return ApplicationResult<int>.Failure( ApplicationError.Validation("No tenant on the caller.")); var retired = await _store.RetireByDefinitionAsync( tenantId, sourceDefinitionId, DateTime.UtcNow, cancellationToken); return ApplicationResult<int>.Success(retired); } /// <summary> /// Publication-time rules. Each refusal names its code and says what is /// wrong in a sentence, because the person reading it is a plant engineer /// looking at their own declaration, not a developer reading a stack trace. /// </summary> | 01_Backend_Core_14Sep2026_104846.txt 4235F89FCF67C0C7E9749A40E3845E1BDF4A0A56FBB8CAE6925832EBFF19E6AE | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-244 | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs | ForSql | 173 | 205 | public static string ForSql( string normalisedSql, string? forkedFromGraphJson, string outputTarget, string? projectionDeclarationJson = null) { if (string.IsNullOrWhiteSpace(normalisedSql)) { throw new ArgumentException("Authored SQL is required.", nameof(normalisedSql)); } // T-253. Before this task the SQL target reached the store only as a projection // handle, which the lifecycle contract itself states is outside the hash. It // could not survive a version and reopen could not return it. It is canonical // content now. if (string.IsNullOrWhiteSpace(outputTarget)) { throw new ArgumentException( "A governed output target is required. It is never defaulted.", nameof(outputTarget)); } var root = new JsonObject { [RootOutputTarget] = outputTarget.Trim(), ["representation"] = RepresentationSql, ["sql"] = normalisedSql, }; if (!string.IsNullOrWhiteSpace(forkedFromGraphJson)) { root["forkedFromGraph"] = Canonicalise(ParseObject(forkedFromGraphJson, "forkedFromGraph")); } | 01_Backend_Core_14Sep2026_104846.txt 247AF15F98CF2A8AF8C4C2FE634C9A55738829B1DE435C5BBC417D1F0B82A347 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-244 | Backend/PlantProcess.Infrastructure/Definitions/Canvas/CanvasDefinitionLifecycleService.cs | SQL publish path | 297 | 333 | else { // Built as a JsonObject rather than an anonymous type. The // forked graph is already JSON text, and a nullable // JsonElement in an anonymous object has no inferable common // type with null - it is a value type. Composing the node // keeps the absent case genuinely absent instead of emitting // a null the projection would have to interpret. var projectionNode = new JsonObject { ["body"] = "sql", ["sql"] = representation.Sql, ["canonicalDefinitionId"] = definitionId.ToString(), ["canonicalVersion"] = version.VersionNumber, }; if (!string.IsNullOrWhiteSpace(representation.ForkedFromGraphJson)) { projectionNode["forkedFromGraph"] = JsonNode.Parse(representation.ForkedFromGraphJson); } var definitionJson = projectionNode.ToJsonString(); await _projection.ProjectSqlVersionAsync( connection, npgsqlTransaction, definitionCode.Trim(), handles.DisplayName, handles.CanonicalEntity, version.VersionNumber, definitionJson, SqlProjectionStatus, cancellationToken); } } catch (Exception ex) when (ex is NpgsqlException or InvalidOperationException) { // The canonical publish succeeded inside this transaction and the // projection did not. Neither survives: that is the whole point. await transaction.RollbackAsync(cancellationToken); return ApplicationResult<CanvasDefinitionVersion>.Failure(ApplicationError.Infrastructure( "Published nothing. The execution projection failed and the canonical publish was rolled back with it: " + ex.Message)); | 01_Backend_Core_14Sep2026_104846.txt BBB6A7BC44D5A51F537E5142EBA51F450F12BB3F6D0C29673346F587A1F4802B | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-244 | Frontend/PlantProcess.Web/src/api/canvasApi.ts | SQL run/save API adapter | 118 | 155 | export type RunSqlResult = { status: string; rowCount: number; columns: string[]; rows: unknown[][]; message: string; errorCode: string ¦ null; sql: string ¦ null; appliedRowLimit: number; // T-036. The database's own type per column, from the reader's metadata. // Optional: the refusal and failure paths have no columns to describe, and a // client built before this landed is still a valid client. The browser NEVER // infers a type from a sample value. columnDetails?: AuthoredColumn[] ¦ null; }; export type SaveSqlVersionResult = { saved: boolean; versionNumber: number; id: string ¦ null; message: string; errorCode: string ¦ null; }; export const runAuthoredSql = (sql: string, rowLimit = 100) => apiClient.post<RunSqlResult>("/api/prep/sql/run", { sql, rowLimit }); // T-253. THE GOVERNED OUTPUT TARGET. // // outputTarget is the canonical identity a definition writes to and it is REQUIRED. // canonicalEntity survives only as the legacy execution-projection handle; it is not // an alternative way to say the same thing, and the shell no longer sends it. export const saveSqlVersion = (body: { code: string; displayName: string; canonicalEntity?: string ¦ null; outputTarget: string; sql: string; forkedFromGraph: unknown; // T-262. A statement declares what it writes exactly as a board does. Omitted is // refused by the server with a typed code, never defaulted into something plausible. projection?: CanvasProjectionDeclaration ¦ null; }) => apiClient.post<SaveSqlVersionResult>("/api/prep/sql/versions", body); export type OutputTargetsResult = { source: string; note?: string; targets: string[]; }; // The names come from the mapped model plus the Domain projection-target marker. The // browser keeps no list of its own: an empty answer is shown as an empty picker, never // backfilled with something plausible. export const listOutputTargets = () => apiClient.get<OutputTargetsResult>("/api/prep/authoring/output-targets"); export const publishVersion = (sessionId: string) => | 04_Frontend_App_14Sep2026_104846.txt 1A78D625E9830536FE54D260C9E3CE5A62B92B3AF5B5E7F1735A5EE8541308E2 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-245 | Frontend/PlantProcess.Web/src/api/canvasApi.ts | current save/preview/publish surface | 111 | 155 | export const saveGraph = (sessionId: string, graph: MapperGraph) => apiClient.post<{ ok: boolean }>(`${BASE}/sessions/${sessionId}/graph`, graph); export const runDryRun = (sessionId: string) => apiClient.post<DryRunResult>(`${BASE}/sessions/${sessionId}/dry-run`, {}); // M1-19. SQL authoring. Both calls go through public.ppiq_resolve_safe_sql on // the server before anything is executed or stored - the client never gets a // path that skips the validator, which is the whole constraint of the task. export type AuthoredColumn = { name: string; databaseType: string }; export type RunSqlResult = { status: string; rowCount: number; columns: string[]; rows: unknown[][]; message: string; errorCode: string ¦ null; sql: string ¦ null; appliedRowLimit: number; // T-036. The database's own type per column, from the reader's metadata. // Optional: the refusal and failure paths have no columns to describe, and a // client built before this landed is still a valid client. The browser NEVER // infers a type from a sample value. columnDetails?: AuthoredColumn[] ¦ null; }; export type SaveSqlVersionResult = { saved: boolean; versionNumber: number; id: string ¦ null; message: string; errorCode: string ¦ null; }; export const runAuthoredSql = (sql: string, rowLimit = 100) => apiClient.post<RunSqlResult>("/api/prep/sql/run", { sql, rowLimit }); // T-253. THE GOVERNED OUTPUT TARGET. // // outputTarget is the canonical identity a definition writes to and it is REQUIRED. // canonicalEntity survives only as the legacy execution-projection handle; it is not // an alternative way to say the same thing, and the shell no longer sends it. export const saveSqlVersion = (body: { code: string; displayName: string; canonicalEntity?: string ¦ null; outputTarget: string; sql: string; forkedFromGraph: unknown; // T-262. A statement declares what it writes exactly as a board does. Omitted is // refused by the server with a typed code, never defaulted into something plausible. projection?: CanvasProjectionDeclaration ¦ null; }) => apiClient.post<SaveSqlVersionResult>("/api/prep/sql/versions", body); export type OutputTargetsResult = { source: string; note?: string; targets: string[]; }; // The names come from the mapped model plus the Domain projection-target marker. The // browser keeps no list of its own: an empty answer is shown as an empty picker, never // backfilled with something plausible. export const listOutputTargets = () => apiClient.get<OutputTargetsResult>("/api/prep/authoring/output-targets"); export const publishVersion = (sessionId: string) => | 04_Frontend_App_14Sep2026_104846.txt 1A78D625E9830536FE54D260C9E3CE5A62B92B3AF5B5E7F1735A5EE8541308E2 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-245 | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs | non-executable target families | 109 | 124 | case JobDefinitionType.CanonicalRefresh: return new JobExecutionCapability( jobType, false, JobTargetRequirement.Required, DefinitionKind.Transformation, "Governed projection execution is not commissioned in this runtime. The only " + "path this family reaches processes the generic import queue and does not " + "execute the declared transformation version, so it is not advertised as " + "executable. Existing schedules and history remain readable."); case JobDefinitionType.MlParamsVsDefects: case JobDefinitionType.MlParamsVsDowntime: case JobDefinitionType.MlParamsVsKpis: case JobDefinitionType.MlWeeklyFull: return new JobExecutionCapability( jobType, false, JobTargetRequirement.Required, DefinitionKind.Model, "The learning family " + jobType + " declares a governed model target, and no " + "executor for it is commissioned in this runtime."); | 01_Backend_Core_14Sep2026_104846.txt CEA3131502C263934EAD3A5775261B458CAD649FFE554E7F6B7ADD064FE2A5B6 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-247 | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs | concrete broken journey seam | 109 | 115 | case JobDefinitionType.CanonicalRefresh: return new JobExecutionCapability( jobType, false, JobTargetRequirement.Required, DefinitionKind.Transformation, "Governed projection execution is not commissioned in this runtime. The only " + "path this family reaches processes the generic import queue and does not " + "execute the declared transformation version, so it is not advertised as " + "executable. Existing schedules and history remain readable."); | 01_Backend_Core_14Sep2026_104846.txt CEA3131502C263934EAD3A5775261B458CAD649FFE554E7F6B7ADD064FE2A5B6 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-247 | Backend/tests/PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs | earlier tests are not full new journey proof | 32 | 73 | public async Task TwoStageDeltaImport_Stage1Stage2AndFullCycle_AreIdempotent_WhenOptInEnabled() { if (!IsEnabled()) return; using var client = await CreateAuthenticatedClientAsync(); await AssertSuccessAsync(await client.PostAsync("/admin/two-stage-import/provision-baseline", null), "provision-baseline"); var firstStage1 = await PostRunAsync(client, "/admin/two-stage-import/stage1/run", maxRows: 25, timeoutSeconds: 30, maxMinutes: 1); var secondStage1 = await PostRunAsync(client, "/admin/two-stage-import/stage1/run", maxRows: 25, timeoutSeconds: 30, maxMinutes: 1); var firstStage2 = await PostRunAsync(client, "/admin/two-stage-import/stage2/run", maxRows: 25, timeoutSeconds: 30, maxMinutes: 1); var fullCycle1 = await PostRunAsync(client, "/admin/two-stage-import/run-full-cycle", maxRows: 50, timeoutSeconds: 45, maxMinutes: 2); var fullCycle2 = await PostRunAsync(client, "/admin/two-stage-import/run-full-cycle", maxRows: 50, timeoutSeconds: 45, maxMinutes: 2); firstStage1.RootElement.GetProperty("stage").GetString().Should().Be("Stage1DeltaImport"); secondStage1.RootElement.GetProperty("stage").GetString().Should().Be("Stage1DeltaImport"); firstStage2.RootElement.GetProperty("stage").GetString().Should().Be("Stage2CanonicalRefresh"); fullCycle1.RootElement.GetProperty("stage").GetString().Should().Be("TwoStageFullCycle"); fullCycle2.RootElement.GetProperty("stage").GetString().Should().Be("TwoStageFullCycle"); var overview = await ReadJsonAsync(await client.GetAsync("/admin/two-stage-import/overview"), "overview-after-full-cycle"); overview.RootElement.TryGetProperty("sourceTables", out var sourceTables).Should().BeTrue(); sourceTables.ValueKind.Should().Be(JsonValueKind.Array); } [SkippableFact] public async Task TwoStageDeltaImport_MaxRowsSmallBatch_DoesNotBreakWatermarks_WhenOptInEnabled() { if (!IsEnabled()) return; using var client = await CreateAuthenticatedClientAsync(); await AssertSuccessAsync(await client.PostAsync("/admin/two-stage-import/provision-baseline", null), "provision-baseline"); var smallBatch = await PostRunAsync(client, "/admin/two-stage-import/stage1/run", maxRows: 3, timeoutSeconds: 30, maxMinutes: 1); var resumeBatch = await PostRunAsync(client, "/admin/two-stage-import/stage1/run", maxRows: 3, timeoutSeconds: 30, maxMinutes: 1); smallBatch.RootElement.TryGetProperty("rows", out var smallRows).Should().BeTrue(); resumeBatch.RootElement.TryGetProperty("rows", out var resumeRows).Should().BeTrue(); smallRows.ValueKind.Should().Be(JsonValueKind.Array); resumeRows.ValueKind.Should().Be(JsonValueKind.Array); } | 03_Backend_Tests_14Sep2026_104846.txt 1AAD7C1413F4FC64C0050229103B2BA8DF14DAD371D190B11BEC9E1826BEA405 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-253 | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs | ForGraph outputTarget/board | 106 | 163 | public static string ForGraph(string graphJson, string outputTarget) { if (string.IsNullOrWhiteSpace(outputTarget)) { throw new ArgumentException( "A governed output target is required. It is never defaulted.", nameof(outputTarget)); } var graph = ParseObject(graphJson, "graph"); var declared = TrimmedOrNull(graph[GraphTargetEntity]); var target = outputTarget.Trim(); // T-243. The browser sends the board INSIDE the graph payload, because that is // the one blob the existing session draft carries and this task introduces no // second transport. It is lifted out here so the stored graph stays the clean // execution shape the SQL generator reads, and the board stands on its own. JsonNode? board = null; if (graph[RootBoard] is JsonNode authored) { board = authored.DeepClone(); graph.Remove(RootBoard); } if (declared is not null && !string.Equals(declared, target, StringComparison.Ordinal)) { throw new ArgumentException( "The graph names '" + declared + "' as its target entity while the governed output target is '" + target + "'. One definition cannot carry two output identities.", nameof(outputTarget)); } // T-262. The declaration rides inside the graph payload for the same reason the // board does: the session draft is one blob and this task introduces no second // transport. It is lifted to the root so the stored graph stays the clean // execution shape, and the declaration stands beside it as its own fact. JsonNode? projection = null; if (graph[RootProjection] is JsonNode declared2) { projection = declared2.DeepClone(); graph.Remove(RootProjection); } var root = new JsonObject { ["graph"] = Canonicalise(graph), [RootOutputTarget] = target, ["representation"] = RepresentationGraph, }; if (board is not null) { root[RootBoard] = Canonicalise(board); } if (projection is not null) { root[RootProjection] = Canonicalise(projection); } | 01_Backend_Core_14Sep2026_104846.txt 247AF15F98CF2A8AF8C4C2FE634C9A55738829B1DE435C5BBC417D1F0B82A347 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-253 | Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs | strict compatibility | 128 | 145 | public static bool IsCompatible(string? sourceType, string? targetType) { var source = FamilyOf(sourceType); var target = FamilyOf(targetType); if (source == Family.Unknown ¦¦ target == Family.Unknown) { return false; } if (source != target) { // Integer into decimal is the one cross-family widening that cannot lose a // value. Everything else - text into number, number into text, date into // text - needs an authored conversion, not an assumption. return source == Family.Integer && target == Family.Decimal; } if (target == Family.Integer) { return RankOf(IntegerRank, sourceType) <= RankOf(IntegerRank, targetType); } | 01_Backend_Core_14Sep2026_104846.txt FF480A92BB3252C2E534718EF6F77F2E46AD1FFA231C210C5059ADEC5D996E38 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-254 | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs | duplicate provider DTO source | 17 | 39 | public IReadOnlyList<ProviderTypeDto> GetProviderTypes() { return new List<ProviderTypeDto> { new( "Csv", "CSV Snapshot", "Available now. Reads CSV snapshot exports into the PlantProcess IQ raw staging layer.", IsAvailableNow: ProviderAvailability.IsAvailableNow("Csv"), RequiresSecretReference: false, SupportsSchemaDiscovery: true, SupportsSnapshotImport: true, SupportsIncrementalImport: false), new( "Excel", "Excel Snapshot", "Available now. Reads Excel workbook/sheet snapshots into the PlantProcess IQ raw staging layer.", IsAvailableNow: ProviderAvailability.IsAvailableNow("Excel"), RequiresSecretReference: false, SupportsSchemaDiscovery: true, SupportsSnapshotImport: true, SupportsIncrementalImport: false), | 01_Backend_Core_14Sep2026_104846.txt 4A10A7107F55716CC0B80A0E55C87FB91CA06520CEA655886BBABC9BBEAADDA1 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-254 | Backend/PlantProcess.Application/Integration/Services/Connectors/ConnectorConfigurationService.ProviderTypes.001.GetProviderTypes.cs | OPC flags | 81 | 102 | new( "RestApi", "REST API Snapshot", "Planned API snapshot connector. Not part of the current demo-ready connector set.", IsAvailableNow: ProviderAvailability.IsAvailableNow("RestApi"), RequiresSecretReference: true, SupportsSchemaDiscovery: false, SupportsSnapshotImport: true, SupportsIncrementalImport: true), new( "OpcUaHistorian", "OPC-UA / Historian", "Future historian/live-data connector. Not part of the current demo-ready connector set.", IsAvailableNow: ProviderAvailability.IsAvailableNow("OpcUaHistorian"), RequiresSecretReference: true, SupportsSchemaDiscovery: false, SupportsSnapshotImport: false, SupportsIncrementalImport: true) }; } } | 01_Backend_Core_14Sep2026_104846.txt 4A10A7107F55716CC0B80A0E55C87FB91CA06520CEA655886BBABC9BBEAADDA1 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-254 | Backend/PlantProcess.Application/Integration/Connectors/ConnectorProviderCatalog.cs | second catalog OPC/SAP entries | 72 | 104 | new ProviderTypeDto( ProviderType: "Sap", DisplayName: "SAP", Description: "Read-only connector for SAP source systems.", IsAvailableNow: ProviderAvailability.IsAvailableNow("Sap"), RequiresSecretReference: true, SupportsSchemaDiscovery: true, SupportsSnapshotImport: true, SupportsIncrementalImport: true), new ProviderTypeDto( ProviderType: "RestApi", DisplayName: "REST API Snapshot", Description: "Reads snapshots from REST endpoints.", IsAvailableNow: ProviderAvailability.IsAvailableNow("RestApi"), RequiresSecretReference: true, SupportsSchemaDiscovery: false, SupportsSnapshotImport: true, SupportsIncrementalImport: true), // PPIQ_PACK_E2_GA_HISTORIAN_PROVIDER new ProviderTypeDto( ProviderType: "OpcUaHistorian", DisplayName: "OPC-UA / Historian Gateway", Description: "Read-only gateway for OPC-UA historians and tag archives.", IsAvailableNow: ConnectorCertification.IsCertified("OpcUaHistorian"), RequiresSecretReference: true, SupportsSchemaDiscovery: true, SupportsSnapshotImport: false, SupportsIncrementalImport: true) }; } } | 01_Backend_Core_14Sep2026_104846.txt BA307EC6BCE0A14F42049859F75B9087495014676C4E6E822CF956D96BF140BB | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-261 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs | admission before real run | 61 | 85 | // CAPABILITY FIRST, AND NOTHING BEFORE IT. An unsupported family never // opens a run record and never reaches an executor, so no side effect - // not one import batch - can be attributed to a request the runtime // cannot honour. ApplicationResult admitted = JobRunAdmission.Admit(job, _capability); if (admitted.IsFailure) return ApplicationResult<JobActionResponseDto>.Failure(admitted.Error!); ApplicationResult targetOk = await ResolveDeclaredTargetAsync(job, cancellationToken); if (targetOk.IsFailure) return ApplicationResult<JobActionResponseDto>.Failure(targetOk.Error!); var run = await _jobRuntimeService.StartAsync( job.JobCode, triggerSource: "ManualRunNow", triggeredBy: requestedBy ?? "Admin", correlationId: correlationId ?? Guid.NewGuid().ToString("N"), cancellationToken); if (run.IsFailure ¦¦ run.Value is null) return ApplicationResult<JobActionResponseDto>.Failure(run.Error!); try { var executionResult = await ExecuteJobAsync(job.JobType, cancellationToken); | 01_Backend_Core_14Sep2026_104846.txt 825F46CF07A7504EA2BA2BAF66046C9E9A5157B693030F33D8916500E2B64564 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-261 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs | discarded resolution/dispatch | 210 | 276 | private async Task<ApplicationResult> ResolveDeclaredTargetAsync( JobDefinition job, CancellationToken cancellationToken) { if (!job.TargetDefinitionId.HasValue) { ApplicationResult<JobTargetResolution> none = await _targetResolver.ResolveAsync(job.JobType, null, cancellationToken); return none.IsFailure ? ApplicationResult.Failure(none.Error!) : ApplicationResult.Success(); } if (string.IsNullOrWhiteSpace(job.TargetDefinitionKind) ¦¦ !job.TargetVersionPolicy.HasValue) { return ApplicationResult.Failure(ApplicationError.Validation( "Job " + job.JobCode + " declares a target identity without a kind or a version policy, " + "so nothing can say which definition version it would run.")); } DefinitionKind kind; if (!Enum.TryParse(job.TargetDefinitionKind, false, out kind) ¦¦ !Enum.IsDefined(typeof(DefinitionKind), kind)) { return ApplicationResult.Failure(ApplicationError.Validation( "Job " + job.JobCode + " declares target kind '" + job.TargetDefinitionKind + "', which is not a canonical definition kind.")); } var reference = new JobTargetReference { Kind = kind, DefinitionId = job.TargetDefinitionId.Value, VersionPolicy = job.TargetVersionPolicy.Value, PinnedVersion = job.TargetDefinitionVersion, ParametersJson = job.TargetParametersJson }; ApplicationResult<JobTargetResolution> resolved = await _targetResolver.ResolveAsync(job.JobType, reference, cancellationToken); return resolved.IsFailure ? ApplicationResult.Failure(resolved.Error!) : ApplicationResult.Success(); } private async Task<RunNowExecutionResult> ExecuteJobAsync( JobDefinitionType jobType, CancellationToken cancellationToken) { switch (jobType) { // CanonicalRefresh is deliberately absent. Its case used to sit here // beside DbLinkImport and processed the same generic queue, which is // not execution of a governed transformation version. The capability // authority now refuses it before this method is reached, and the // default below makes any disagreement loud instead of silent. case JobDefinitionType.DbLinkImport: { var result = await _importBatchQueueProcessorService.ProcessPendingBatchesAsync( maxBatches: 10, rowsPerBatch: 5000, stopOnFirstError: false, runDataQualityScan: false, cancellationToken); if (result.IsFailure ¦¦ result.Value is null) { return RunNowExecutionResult.Failed( result.Error?.Message ?? "Import queue processing failed."); } return RunNowExecutionResult.Ok( $"Import queue completed. Scanned={result.Value.BatchesScanned}, Completed={result.Value.BatchesCompleted}, Failed={result.Value.BatchesFailed}.", JsonSerializer.Serialize(result.Value)); | 01_Backend_Core_14Sep2026_104846.txt 825F46CF07A7504EA2BA2BAF66046C9E9A5157B693030F33D8916500E2B64564 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-261 | Backend/PlantProcess.Application/Jobs/Execution/JobExecutionCapability.cs | uncommissioned executor | 109 | 115 | case JobDefinitionType.CanonicalRefresh: return new JobExecutionCapability( jobType, false, JobTargetRequirement.Required, DefinitionKind.Transformation, "Governed projection execution is not commissioned in this runtime. The only " + "path this family reaches processes the generic import queue and does not " + "execute the declared transformation version, so it is not advertised as " + "executable. Existing schedules and history remain readable."); | 01_Backend_Core_14Sep2026_104846.txt CEA3131502C263934EAD3A5775261B458CAD649FFE554E7F6B7ADD064FE2A5B6 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-261 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRuntimeService.cs | terminal lifecycle | 127 | 149 | switch (finalStatus) { case JobRunStatus.Ok: history.MarkSucceeded(message, resultSummaryJson); job.MarkSucceeded(history.DurationMs, history.CompletedAtUtc); break; case JobRunStatus.Failed: history.MarkFailed(failureReason ?? message ?? "Job failed.", resultSummaryJson); job.MarkFailed(history.FailureReason ?? "Job failed.", history.DurationMs, history.CompletedAtUtc); break; case JobRunStatus.Timeout: history.MarkTimedOut(failureReason ?? message ?? "Job timed out.", resultSummaryJson); job.MarkTimedOut(history.FailureReason ?? "Job timed out.", history.DurationMs, history.CompletedAtUtc); break; default: return ApplicationResult<JobRunHistoryDto>.Failure( ApplicationError.Validation("Final job status must be Ok, Failed, or Timeout.")); } await _dbContext.SaveChangesAsync(cancellationToken); | 01_Backend_Core_14Sep2026_104846.txt DE73F04C71484D78FCDD19EAE2A1ACF618E1A9F36E97B88CB0FC118F2F565DF9 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-262 | Backend/PlantProcess.Application/Definitions/Canvas/CanvasDefinitionContent.cs | immutable projection content | 118 | 163 | // T-243. The browser sends the board INSIDE the graph payload, because that is // the one blob the existing session draft carries and this task introduces no // second transport. It is lifted out here so the stored graph stays the clean // execution shape the SQL generator reads, and the board stands on its own. JsonNode? board = null; if (graph[RootBoard] is JsonNode authored) { board = authored.DeepClone(); graph.Remove(RootBoard); } if (declared is not null && !string.Equals(declared, target, StringComparison.Ordinal)) { throw new ArgumentException( "The graph names '" + declared + "' as its target entity while the governed output target is '" + target + "'. One definition cannot carry two output identities.", nameof(outputTarget)); } // T-262. The declaration rides inside the graph payload for the same reason the // board does: the session draft is one blob and this task introduces no second // transport. It is lifted to the root so the stored graph stays the clean // execution shape, and the declaration stands beside it as its own fact. JsonNode? projection = null; if (graph[RootProjection] is JsonNode declared2) { projection = declared2.DeepClone(); graph.Remove(RootProjection); } var root = new JsonObject { ["graph"] = Canonicalise(graph), [RootOutputTarget] = target, ["representation"] = RepresentationGraph, }; if (board is not null) { root[RootBoard] = Canonicalise(board); } if (projection is not null) { root[RootProjection] = Canonicalise(projection); } | 01_Backend_Core_14Sep2026_104846.txt 247AF15F98CF2A8AF8C4C2FE634C9A55738829B1DE435C5BBC417D1F0B82A347 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-262 | Backend/PlantProcess.Application/Definitions/Canvas/ProjectionTypeCompatibility.cs | unknown/narrowing refusal | 128 | 145 | public static bool IsCompatible(string? sourceType, string? targetType) { var source = FamilyOf(sourceType); var target = FamilyOf(targetType); if (source == Family.Unknown ¦¦ target == Family.Unknown) { return false; } if (source != target) { // Integer into decimal is the one cross-family widening that cannot lose a // value. Everything else - text into number, number into text, date into // text - needs an authored conversion, not an assumption. return source == Family.Integer && target == Family.Decimal; } if (target == Family.Integer) { return RankOf(IntegerRank, sourceType) <= RankOf(IntegerRank, targetType); } | 01_Backend_Core_14Sep2026_104846.txt FF480A92BB3252C2E534718EF6F77F2E46AD1FFA231C210C5059ADEC5D996E38 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-262 | Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx | doSaveSql callback inputs/dependencies | 898 | 925 | const doSaveSql = useCallback(async () => { try { // T-253. The statement carries the SAME governed identity the board does. The // legacy canonicalEntity handle is no longer sent from here at all: it named a // physical relation, which was never what a definition writes to. if (outputTargetRefusal) { logError(name, outputTargetRefusal); return; } // T-262. Saving a governed version is the same boundary Publish is. Run SQL // remains open while the mapping is being authored. if (projectionBlocked) { setProjectionRefusal(projectionBlocked); logError(name, projectionBlocked); return; } const r = await saveSqlVersion({ code: name.replace(/[^A-Za-z0-9_]+/g, "_").toLowerCase() ¦¦ "sql_definition", displayName: name, outputTarget, sql: sqlText, forkedFromGraph: forkedGraph, projection, }); if (r.saved) { logSuccess(name, r.message, "version " + r.versionNumber); } else { logError(name, r.message); } } catch (e) { logError(name, describeThrownAction(e)); } }, [name, sqlText, forkedGraph, outputTarget, outputTargetRefusal, logError, logSuccess]); | 04_Frontend_App_14Sep2026_104846.txt 57750D130D30FC330C4D4A15E63CAC95C69CFD026A6F73EC8F3A9CD9E1924736 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-113 | Backend/PlantProcess.Infrastructure/Connectors/ConnectorCredentialResolver.cs | Resolve | 16 | 51 | public static Credentials Resolve(string? connectionOptionsJson, string? secretReference, string providerLabel) { if (!string.IsNullOrWhiteSpace(connectionOptionsJson) && connectionOptionsJson.Trim() != "{}") { try { using var doc = JsonDocument.Parse(connectionOptionsJson); var root = doc.RootElement; var u = TryGet(root, "username") ?? TryGet(root, "user"); var p = TryGet(root, "password"); if (!string.IsNullOrWhiteSpace(u) && p is not null) { return new Credentials(u!, p!); } } catch (JsonException) { throw new InvalidOperationException( providerLabel + " connection_options_json is not valid JSON; cannot resolve credentials."); } } if (!string.IsNullOrWhiteSpace(secretReference)) { var u = Environment.GetEnvironmentVariable(secretReference!); var p = Environment.GetEnvironmentVariable(secretReference + "_PASSWORD"); if (!string.IsNullOrWhiteSpace(u) && p is not null) { return new Credentials(u!, p!); } } throw new InvalidOperationException( providerLabel + " connection failed: no credentials resolved. Provide connection_options_json " + "with username and password, or a secret_reference resolving to REF and REF_PASSWORD " + "environment variables. The connector will not inherit the host account identity."); | 01_Backend_Core_14Sep2026_104846.txt 93A40F4BB733FD739E33350C746822CCF49804393802C9A82DC1940045BA8477 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-113 | Backend/tests/PlantProcess.Api.IntegrationTests/Security/T08ConnectorSecretMaskingIntegrationTests.cs | Connector_password_is_masked_on_readback | 19 | 46 | [SkippableFact] public async Task Connector_password_is_masked_on_readback() { using var client = await CreateAuthenticatedClientAsync(); var create = await client.PostAsJsonAsync("/admin/connectors/connection-profiles", new { name = "t08-mask-probe", providerType = "PostgreSql", host = "127.0.0.1", port = 5432, database = "t08probe", username = "t08user", password = PlaintextSecret }); if (!create.IsSuccessStatusCode) return; // exact create shape differs here -> no-op var created = await create.Content.ReadFromJsonAsync<JsonElement>(); string? id = created.TryGetProperty("id", out var idProp) ? idProp.GetString() : null; if (string.IsNullOrWhiteSpace(id)) return; var read = await client.GetAsync($"/admin/connectors/connection-profiles/{id}"); read.IsSuccessStatusCode.Should().BeTrue(); var body = await read.Content.ReadAsStringAsync(); body.Should().NotContain(PlaintextSecret, "the plaintext connector secret must never be serialized back to the client"); | 03_Backend_Tests_14Sep2026_104846.txt 5C1F9DE8F3E6D7528092AB2EAA6CE796531C75087597AAF68B4ED6DC964D0865 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-113 | Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs | dev route refusal | 51 | 62 | group.MapPost("/dev/create-license", async ( [FromBody] CreateDevLicenseRequest request, NpgsqlDataSource dataSource, HttpContext http, IHostEnvironment hostEnvironment, CancellationToken cancellationToken) => { // P2-T01: dev-only license minting. Never expose outside Development. if (!hostEnvironment.IsDevelopment()) { return Results.NotFound(); } | 01_Backend_Core_14Sep2026_104846.txt 7080A63116796D48D7EBEE5511006B081C7F46CA09B648893D3EF382739CCB98 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-121 | Backend/PlantProcess.Api/SignedLicensing/VerifiedEd25519LicenseService.cs | feature/tier authority | 10 | 60 | public sealed class VerifiedEd25519LicenseService : ILicenseService { private static readonly IReadOnlyDictionary<LicenseFeature, LicenseTier> RequiredTierByFeature = new Dictionary<LicenseFeature, LicenseTier> { [LicenseFeature.ReadOnlySourceRegistry] = LicenseTier.Light, [LicenseFeature.CsvImport] = LicenseTier.Light, [LicenseFeature.ExcelImport] = LicenseTier.Light, [LicenseFeature.PostgreSqlConnector] = LicenseTier.Pro, [LicenseFeature.SqlServerConnector] = LicenseTier.Enterprise, [LicenseFeature.OracleConnector] = LicenseTier.Enterprise, [LicenseFeature.MySqlConnector] = LicenseTier.Enterprise, [LicenseFeature.RestApiConnector] = LicenseTier.Enterprise, [LicenseFeature.OpcUaHistorianConnector] = LicenseTier.Enterprise, [LicenseFeature.DbLinkConfiguration] = LicenseTier.Light, [LicenseFeature.DumpStagingRetention] = LicenseTier.Light, [LicenseFeature.SourceSnapshotImport] = LicenseTier.Light, [LicenseFeature.IncrementalImport] = LicenseTier.Pro, [LicenseFeature.SchemaSqlViewBuilder] = LicenseTier.Pro, [LicenseFeature.CrossSourceJoinExecution] = LicenseTier.Pro, [LicenseFeature.KpiViewBuilder] = LicenseTier.ProPlus, [LicenseFeature.SchemaPreviewExecution] = LicenseTier.Pro, [LicenseFeature.MappingExecution] = LicenseTier.Pro, [LicenseFeature.WidgetScriptLayer] = LicenseTier.ProPlus, [LicenseFeature.DashboardPageBuilder] = LicenseTier.Light, [LicenseFeature.DashboardWidgetBuilder] = LicenseTier.Light, [LicenseFeature.DashboardLayoutPersistence] = LicenseTier.Light, [LicenseFeature.DataQualityBasicScan] = LicenseTier.Light, [LicenseFeature.DataQualityFullScan] = LicenseTier.Pro, [LicenseFeature.RiskDashboardView] = LicenseTier.Pro, [LicenseFeature.RiskDashboardContributors] = LicenseTier.ProPlus, [LicenseFeature.CorrelationManualRun] = LicenseTier.Pro, [LicenseFeature.CorrelationScheduledRun] = LicenseTier.ProPlus, [LicenseFeature.InvestigationWorkflow] = LicenseTier.ProPlus, [LicenseFeature.MlWorkspacePreview] = LicenseTier.ProPlus, [LicenseFeature.MlLearningJobs] = LicenseTier.ProPlus, [LicenseFeature.SuggestionRecommendation] = LicenseTier.ProPlus, [LicenseFeature.BasicInvestigationReportPdf] = LicenseTier.Pro, [LicenseFeature.FullGenealogyReportPdf] = LicenseTier.ProPlus, [LicenseFeature.BrandedReportPdf] = LicenseTier.Enterprise | 01_Backend_Core_14Sep2026_104846.txt F161FA32314EB4BA58247BEFF03FF6F3F64722C589F50D06FA37E265388DC43F | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-121 | Backend/PlantProcess.Api/Program.cs | licence DI | 725 | 744 | builder.Services.AddV5AssistantGateway(builder.Configuration); builder.Services.AddAssistant(); // T-057. The relationship vertical: store, service and publication seam. // Fully qualified deliberately - a composition root should not acquire a // using for a namespace it references once. PlantProcess.Infrastructure.Relationships.RelationshipInfrastructureExtensions.AddRelationshipInfrastructure(builder.Services); // PPIQ_API_STARTUP_SERVICE_INFERENCE_FIX: // Register Phase 09/10 application services used by Minimal API endpoint handlers. // Without this, ASP.NET cannot infer parameters named "service" and API startup fails. builder.Services.AddScoped<IPrivateModelGatewayTransport, NoopPrivateModelGatewayTransport>(); builder.Services.AddScoped<PrivateModelGatewayService>(); builder.Services.AddScoped<ConnectorBehaviourCertificationService>(); builder.Services.AddScoped<ILicenseService, VerifiedEd25519LicenseService>(); builder.AddPpiqTestMode(); // PPIQ-T022 (validates + refuses in Production without accept-risk) | 01_Backend_Core_14Sep2026_104846.txt 81846040EF8FE25181817A9F167CC9A727AE1946E340B8B4385CF7F5E8974897 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-121 | Backend/PlantProcess.Application/DependencyInjection.cs | legacy DI | 58 | 63 | // Commercial license / feature enforcement services.AddOptions<LicenseOptions>() .BindConfiguration(LicenseOptions.SectionName) .Validate(options => !string.IsNullOrWhiteSpace(options.Tier), "PlantProcess:License:Tier is required."); services.AddSingleton<ILicenseService, LicenseService>(); | 01_Backend_Core_14Sep2026_104846.txt D2AB8EE19071BB139AA2EC400F7BADFC272BA1218A042EF57453BE49B1707134 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-121 | Backend/PlantProcess.Api/SignedLicensing/V5SignedLicensingEndpoints.cs | development guard | 51 | 62 | group.MapPost("/dev/create-license", async ( [FromBody] CreateDevLicenseRequest request, NpgsqlDataSource dataSource, HttpContext http, IHostEnvironment hostEnvironment, CancellationToken cancellationToken) => { // P2-T01: dev-only license minting. Never expose outside Development. if (!hostEnvironment.IsDevelopment()) { return Results.NotFound(); } | 01_Backend_Core_14Sep2026_104846.txt 7080A63116796D48D7EBEE5511006B081C7F46CA09B648893D3EF382739CCB98 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-123 | deploy/scripts/ppiq.ps1 | command contract | 3 | 20 | # deploy/scripts/ppiq.ps1 - single entrypoint for PlantProcess IQ local + server orchestration. # # ppiq.ps1 <command> [-Server] [-NoSources] # # up start API + web (local: dotnet/npm on host ; -Server: full compose stack) # up-sources start the demo source containers # migrate apply Backend/database/scripts/*.sql in order, idempotent (ON_ERROR_STOP=1) # seed apply Backend/database/seed/*.sql in order (if present) # demo up-sources + migrate + seed + up (full seeded stack, zero manual env) # test dotnet test + vitest run # e2e playwright test # reset down + tear down container volumes # down stop API/web + stop sources # status show running components # help this text # # All config is read from deploy/compose/.env.dev. No verb requires a hand-set environment variable. # On the laptop the app DB is NATIVE postgres on localhost:5432; only the demo sources are containers. | 07_Tools_Validation_Misc_14Sep2026_104846.txt 7E7FCBD5CF51B86CD8C5DD421487E64C8928DA50F77CD40D3B03A3583743C17C | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-123 | deploy/scripts/ppiq.ps1 | profile/path selection | 44 | 63 | $ComposeBase = 'deploy/compose/docker-compose.yml' $ComposeLocal = 'deploy/compose/docker-compose.local.yml' $ComposeServer = 'deploy/compose/docker-compose.server.yml' $ComposeSources = 'deploy/compose/docker-compose.sources.yml' $EnvFile = 'deploy/compose/.env.dev' $Project = 'plantprocessiq' $ApiProj = 'Backend/PlantProcess.Api' $WebDir = 'Frontend/PlantProcess.Web' $MigrationsDir = 'Backend/database/scripts' $SeedDir = 'Backend/database/seed' $RunDir = Join-Path $ScriptDir '.ppiq-run' # ---- helpers ------------------------------------------------------------------------------------- function Say($m){ Write-Host ("ppiq> " + $m) -ForegroundColor Cyan } function Die($m){ Write-Host ("ppiq: " + $m) -ForegroundColor Red; exit 1 } function Assert-Exit($what){ if($LASTEXITCODE -ne 0){ Die ($what + " failed (exit " + $LASTEXITCODE + ")") } } function Import-DotEnv { $f = Join-Path $RepoRoot $EnvFile if(-not (Test-Path $f)){ Die ($EnvFile + " not found - run the M1-T01/T02 setup first") } | 07_Tools_Validation_Misc_14Sep2026_104846.txt 7E7FCBD5CF51B86CD8C5DD421487E64C8928DA50F77CD40D3B03A3583743C17C | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-123 | Backend/database/canonical-migration-order.json | canonical ledger | 1 | 20 | { "artifact": "canonical-migration-order", "purpose": "The single ordered path that builds a database from zero. A script outside this path is never replayed as part of a build.", "generatedAtUtc": "2026-09-09T21:20:11Z", "baselineCommit": "f8a35725c9b0d7fb5a0515c0103a72807a704a97", "dispositions": [ "Canonical", "HistoricalRepair", "Superseded", "FixtureOnly", "DeferredWithReason" ], "rules": [ "The path is tiered: EF migrations, then Backend/database/scripts, then Backend/database/views.", "Each folder numbers from its own 000, so ordinals are compared only within a tier.", "Explicit adjudication beats filename heuristics. Every override records its reason.", "A dependant does not run until its predecessor postcondition is proven.", "Exactly one ordered path exists. This file is it.", "Every SQL file carries exactly one disposition. There is no unknown state.", "A new script joins this manifest in the same commit that creates it.", | 02_Backend_Database_14Sep2026_104846.txt 1F0E9A1DEC31F10BE7034CF00038C4AB36E2681F91E0B429E6D232F08F23E10D | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-110 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs | existing incremental reader use | 120 | 151 | if (!string.IsNullOrWhiteSpace(effectiveCursorFieldName)) { var request = new DataSourceIncrementalReadRequest( dataset.ConnectionProfileId, dataset.Id, dataset.SourceObjectName, dataset.SourceSchemaName, effectiveCursorFieldName, dataset.LastCursorValue, maxRows, dataset.DatasetOptionsJson); rows = await reader.ReadRowsSinceKeyAsync( profile, dataset, request, cancellationToken); } else { rows = await reader.ReadRowsAsync( profile, dataset, new DataSourceReadRequest( dataset.ConnectionProfileId, dataset.Id, dataset.SourceObjectName, dataset.SourceSchemaName, maxRows, dataset.DatasetOptionsJson), cancellationToken); } | 01_Backend_Core_14Sep2026_104846.txt F78DD6FE12FA8F98014A67D7F34256C3EB1C36F5BF9BBB620D1A10F4F9683774 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-110 | Backend/PlantProcess.Application/Integration/Services/SourceSystems/DeltaImportExecutionService.cs | batch/cursor persistence | 173 | 205 | string? maxCursorValue = dataset.LastCursorValue; foreach (var row in rows) { var rawJson = JsonSerializer.Serialize(row.Values); var sourceRecordId = TryGetSourceRecordId( row, effectiveCursorFieldName, rowNumber); _dbContext.StagingRecords.Add(new StagingRecord( importBatchId: batch.Id, sourceObjectName: dataset.SourceObjectName, rowNumber: rowNumber, rawJson: rawJson, isSynthetic: false, sourceSystem: profile.ProviderType, sourceRecordId: sourceRecordId)); var candidateCursor = TryGetCursorValue(row, effectiveCursorFieldName); if (!string.IsNullOrWhiteSpace(candidateCursor)) maxCursorValue = MaxCursor(maxCursorValue, candidateCursor); rowNumber++; } batch.MarkCompleted(rows.Count); if (rows.Count > 0) dataset.UpdateLastCursorValue(maxCursorValue); dataset.ScheduleNextRunAfterSuccess(); | 01_Backend_Core_14Sep2026_104846.txt F78DD6FE12FA8F98014A67D7F34256C3EB1C36F5BF9BBB620D1A10F4F9683774 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-110 | Backend/PlantProcess.Application/Integration/Services/Jobs/JobRunOrchestratorService.cs | existing admission/run boundary | 61 | 85 | // CAPABILITY FIRST, AND NOTHING BEFORE IT. An unsupported family never // opens a run record and never reaches an executor, so no side effect - // not one import batch - can be attributed to a request the runtime // cannot honour. ApplicationResult admitted = JobRunAdmission.Admit(job, _capability); if (admitted.IsFailure) return ApplicationResult<JobActionResponseDto>.Failure(admitted.Error!); ApplicationResult targetOk = await ResolveDeclaredTargetAsync(job, cancellationToken); if (targetOk.IsFailure) return ApplicationResult<JobActionResponseDto>.Failure(targetOk.Error!); var run = await _jobRuntimeService.StartAsync( job.JobCode, triggerSource: "ManualRunNow", triggeredBy: requestedBy ?? "Admin", correlationId: correlationId ?? Guid.NewGuid().ToString("N"), cancellationToken); if (run.IsFailure ¦¦ run.Value is null) return ApplicationResult<JobActionResponseDto>.Failure(run.Error!); try { var executionResult = await ExecuteJobAsync(job.JobType, cancellationToken); | 01_Backend_Core_14Sep2026_104846.txt 825F46CF07A7504EA2BA2BAF66046C9E9A5157B693030F33D8916500E2B64564 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-155 | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs | benchmark metadata | 20 | 36 | public sealed record BenchmarkDefinition { public required string BenchmarkId { get; init; } public required string Title { get; init; } public required string Question { get; init; } public required string Method { get; init; } public required string Decides { get; init; } public required string DecisionOwner { get; init; } public required string DefinitionSource { get; init; } /// <summary>The task owning the model-specific measurement hook for this benchmark.</summary> public required string HookOwner { get; init; } /// <summary>The domain kind of the thing this benchmark measures.</summary> public required string SubjectKind { get; init; } public required IReadOnlyList<MetricFamily> ApplicableFamilies { get; init; } | 07_Tools_Validation_Misc_14Sep2026_104846.txt 65CDF66B2DC435F755674C5F5EDB44FC4EF6F082D17FB74F4925C3275535FEF9 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-155 | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs | SelectedValueGuard | 32 | 75 | public static class SelectedValueGuard { public static bool TryPublish( BenchmarkEnvelope evidence, string metricName, MetricAggregation aggregation, out SelectedBenchmarkValue? selected, out string refusalReason) { selected = null; if (evidence is null) { refusalReason = "no evidence envelope was supplied"; return false; } string? invariant = evidence.Validate(); if (invariant is not null) { refusalReason = "evidence envelope is invalid: " + invariant; return false; } if (evidence.TerminalState != BenchmarkTerminalState.Measured) { refusalReason = "evidence terminal state is " + evidence.TerminalState + "; a selected value requires a Measured result"; return false; } if (evidence.Subject.FixtureKind != SubjectFixtureKind.RealSubject) { refusalReason = "evidence was produced by a " + evidence.Subject.FixtureKind + "; a fixture verifies the harness and never establishes a product value"; return false; } if (evidence.Scope != MeasurementScope.Production) { refusalReason = "evidence scope is " + evidence.Scope + "; a selected value requires a Production measurement"; return false; | 07_Tools_Validation_Misc_14Sep2026_104846.txt 70B5B58321B414CF47DF5486616D1C28016D7661C36F8E50921DCEBD3D08F8DF | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-159 | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs | evidence guard | 43 | 81 | if (evidence is null) { refusalReason = "no evidence envelope was supplied"; return false; } string? invariant = evidence.Validate(); if (invariant is not null) { refusalReason = "evidence envelope is invalid: " + invariant; return false; } if (evidence.TerminalState != BenchmarkTerminalState.Measured) { refusalReason = "evidence terminal state is " + evidence.TerminalState + "; a selected value requires a Measured result"; return false; } if (evidence.Subject.FixtureKind != SubjectFixtureKind.RealSubject) { refusalReason = "evidence was produced by a " + evidence.Subject.FixtureKind + "; a fixture verifies the harness and never establishes a product value"; return false; } if (evidence.Scope != MeasurementScope.Production) { refusalReason = "evidence scope is " + evidence.Scope + "; a selected value requires a Production measurement"; return false; } if (!evidence.TryGetMetric(metricName, aggregation, out MetricValue metric)) { refusalReason = "evidence carries no metric '" + metricName + "' at aggregation " + aggregation + "; an absent metric is not zero"; | 07_Tools_Validation_Misc_14Sep2026_104846.txt 70B5B58321B414CF47DF5486616D1C28016D7661C36F8E50921DCEBD3D08F8DF | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-159 | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkCatalogue.cs | B-01..B-09 registry | 65 | 90 | public static class BenchmarkCatalogue { public const string B01 = "B-01"; public const string B02 = "B-02"; public const string B03 = "B-03"; public const string B04 = "B-04"; public const string B05 = "B-05"; public const string B06 = "B-06"; public const string B07 = "B-07"; public const string B08 = "B-08"; public const string B09 = "B-09"; /// <summary>The register the frozen definitions came from.</summary> public const string FrozenRegister = "PPIQ_Backlog_v2_10_1_12Aug2026"; /// <summary> /// Every decision the register names is a product-owner ruling. A benchmark /// supplies evidence for it and never takes it. /// </summary> public const string ProductOwnerRuling = "product-owner ruling"; private static readonly string[] AllIds = { B01, B02, B03, B04, B05, B06, B07, B08, B09 }; private static readonly Dictionary<string, BenchmarkDefinition> Definitions = Build(); public static IReadOnlyList<string> AllBenchmarkIds => AllIds; | 07_Tools_Validation_Misc_14Sep2026_104846.txt 65CDF66B2DC435F755674C5F5EDB44FC4EF6F082D17FB74F4925C3275535FEF9 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-116 | Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs | provenance dispatch and run resolution | 16 | 66 | public async Task<ProvenanceResolution> ResolveAsync(ProvenanceHandle handle, CancellationToken cancellationToken) { if (handle is null ¦¦ string.IsNullOrWhiteSpace(handle.Id)) return ProvenanceResolution.Missing(handle ?? new ProvenanceHandle(ProvenanceKind.Finding, "<null>"), "Handle or id was empty."); try { return handle.Kind switch { ProvenanceKind.Finding or ProvenanceKind.JobRun => await ResolveRunOrRiskAsync(handle, cancellationToken), ProvenanceKind.SourceTable => await ResolveSourceTableAsync(handle, cancellationToken), ProvenanceKind.Dataset => await ResolveDatasetAsync(handle, cancellationToken), ProvenanceKind.DocumentSection => await ResolveDocumentAsync(handle, cancellationToken), ProvenanceKind.WidgetResult => await ResolveWidgetResultAsync(handle, cancellationToken), _ => ProvenanceResolution.Missing(handle, "Unknown provenance kind.") }; } catch { return ProvenanceResolution.Missing(handle, "Provenance could not be verified (resolver error)."); } } private async Task<ProvenanceResolution> ResolveRunOrRiskAsync(ProvenanceHandle handle, CancellationToken ct) { if (!Guid.TryParse(handle.Id, out var id)) return ProvenanceResolution.Missing(handle, "Finding/JobRun id is not a GUID."); await using (var runCmd = _dataSource.CreateCommand("SELECT 1 FROM ppiq_meta.ml_correlation_compute_runs WHERE id = @id")) { runCmd.Parameters.AddWithValue("id", id); if (await runCmd.ExecuteScalarAsync(ct) is not null) return ProvenanceResolution.Live(handle, $"ml_correlation_compute_runs:{id}"); } await using (var riskCmd = _dataSource.CreateCommand( "SELECT COALESCE(mu.is_synthetic, false) FROM ppiq_plant.risk_scores rs " + "JOIN ppiq_plant.material_units mu ON mu.id = rs.material_unit_id WHERE rs.id = @id")) { riskCmd.Parameters.AddWithValue("id", id); await using var reader = await riskCmd.ExecuteReaderAsync(ct); if (await reader.ReadAsync(ct)) { var synthetic = !await reader.IsDBNullAsync(0, ct) && reader.GetBoolean(0); return synthetic ? ProvenanceResolution.Seed(handle, $"risk_scores:{id}") : ProvenanceResolution.Live(handle, $"risk_scores:{id}"); } } return ProvenanceResolution.Missing(handle, "No finding/job-run/risk artifact matched the handle."); | 01_Backend_Core_14Sep2026_104846.txt 200B6557FBC58B18847CE3D9F2BA4D68D4C7DBB9270E68581D2353232EEB1915 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-116 | Backend/PlantProcess.Infrastructure/Provenance/NpgsqlProvenanceResolver.cs | source/dataset existence lookup | 69 | 90 | private async Task<ProvenanceResolution> ResolveSourceTableAsync(ProvenanceHandle handle, CancellationToken ct) { var parts = handle.Id.Split('.', 2); var schema = parts.Length == 2 ? parts[0] : "public"; var table = parts.Length == 2 ? parts[1] : parts[0]; await using var cmd = _dataSource.CreateCommand( "SELECT 1 FROM information_schema.tables WHERE table_schema = @s AND table_name = @t"); cmd.Parameters.AddWithValue("s", schema); cmd.Parameters.AddWithValue("t", table); return await cmd.ExecuteScalarAsync(ct) is not null ? ProvenanceResolution.Live(handle, $"{schema}.{table}") : ProvenanceResolution.Missing(handle, $"Source table '{schema}.{table}' does not exist."); } private async Task<ProvenanceResolution> ResolveDatasetAsync(ProvenanceHandle handle, CancellationToken ct) { await using var cmd = _dataSource.CreateCommand( "SELECT 1 FROM information_schema.tables WHERE table_name = @t " + "UNION SELECT 1 FROM information_schema.views WHERE table_name = @t"); cmd.Parameters.AddWithValue("t", handle.Id); | 01_Backend_Core_14Sep2026_104846.txt 200B6557FBC58B18847CE3D9F2BA4D68D4C7DBB9270E68581D2353232EEB1915 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-248 | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx | state and query orchestration | 1 | 55 | import { createContext, useCallback, useContext, useEffect, useMemo, useRef, useState, type ReactNode } from "react"; import { apiClient } from "../api/http"; import { useDashboardFilters } from "./DashboardFilterContext"; import { productApi } from "../api/productApiClient"; import { buildAssociativeFields, type AssocField } from "./associativeFields"; import { composeEffectiveFilters, toRequestFilters } from "./effectiveQueryFilters"; /** M2-37 associative engine (Qlik spec S0), client-orchestrated: * possible-set per field = the existing, registry-validated widget query for * that field's dimension, with the current selections MINUS the field's own * (so alternatives inside a field stay selectable - the Qlik semantic). * all-set = the same query, unfiltered, cached at mount. * excluded = all minus possible. selected = the field's current filter value. */ /** T-048. The four states Chapter 4 5.1.3 requires. * * ALTERNATIVE is not a weaker "possible". It means: this field already has a * selection, and this value is the road not taken - still reachable in one * click, and excluded from nothing. Collapsing it into "possible" hides which * field the reader is currently steering by. */ export type ValueState = "selected" ¦ "possible" ¦ "excluded" ¦ "alternative"; export type FieldAssoc = { field: AssocField; available: boolean; loading: boolean; all: string[]; states: Map<string, ValueState>; possibleCount: number; }; type Ctx = { enabled: boolean; setEnabled: (v: boolean) => void; fields: FieldAssoc[]; toggleValue: (fieldKey: string, value: string) => void; }; const AssociativeCtx = createContext<Ctx ¦ null>(null); export const useAssociative = () => { const c = useContext(AssociativeCtx); if (!c) throw new Error("useAssociative outside provider"); return c; }; type QueryRow = Record<string, unknown>; async function dimensionValues(dimension: string, measureCode: string, filters: Record<string, unknown>): Promise<string[] ¦ null> { try { const res = await apiClient.post<{ rows?: QueryRow[]; data?: QueryRow[] }>( "/analytics/dashboard/widgets/query", { widgetType: "chart", chartType: "bar", dimensionCode: dimension, measureCode, parameterCode: null, filters, options: { maxRows: 500, rawRowLimit: 500, sortDirection: "desc", includeWarnings: false }, | 04_Frontend_App_14Sep2026_104846.txt 1CECF013ACABE4EC5D2F048119E21829C61726E26D152B943278D4FA0991BE56 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-248 | Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx | reopen application | 333 | 403 | + " under another purpose would be judged by the wrong palette and the wrong rules." + " Open it from its own authoring surface."); return; } setNodes(r.board.nodes.map((n) => ({ id: n.id, type: n.kind, position: { x: n.position.x, y: n.position.y }, data: n.data, })) as Node[]); setEdges(r.board.edges.map((e, i) => ({ id: "reopened-" + i, source: e.source, target: e.target, sourceHandle: e.sourceHandle ?? undefined, targetHandle: e.targetHandle ?? undefined, })) as Edge[]); if (r.graph?.name) { setName(r.graph.name); } if (r.outputTarget) { setOutputTarget(r.outputTarget); } // T-262. Restored EXACTLY, or recorded as absent. A version written before // declarations existed carries none, and nothing is reconstructed for it: the // inspector says so and the author maps it into a new version. setProjection(r.projection ?? null); setReopenedWithoutProjection(!r.projection); setProjectionRefusal(null); setOpenVersion(r.versionNumber); logSuccess(name, "Reopened version " + r.versionNumber + ".", r.board.nodes.length + " block(s), " + r.board.edges.length + " connection(s), target " + (r.outputTarget ?? "none") + ", hash " + r.definitionHash); }, [name, purpose, setNodes, setEdges, logSuccess, logWarning]); // Choosing a version from history. READ-ONLY: it restores what was authored and // never rewrites it. Publishing after reopening an older version creates a NEW // version through the canonical lifecycle - rollback forward, never in place. const doReopen = useCallback(async (code: string, version: number) => { try { applyReopenedDefinition(await reopenDefinition(code, version)); } catch (e) { logError(name, describeThrownAction(e)); } }, [name, applyReopenedDefinition, logError]); // T-243 CLOSURE. SAVE, CLOSE, COME BACK TOMORROW. // // Before this the shell only learned its canonical code as a by-product of // publishing, so history existed for the session that created it and vanished with // the tab. Opening with an existing code is the other half of persistence: the // definition is fetched from the canonical store and nothing else - no localStorage, // no cached board, no reconstruction from the compiled query. // ONCE PER DEFINITION, NOT ONCE PER RENDER IDENTITY. // // The first version of this effect depended on applyReopenedDefinition, which is a // useCallback over name. Restoring a definition SETS name, so the callback got a new // identity, the effect re-ran, and it reopened the current version - silently undoing // a historical version the author had just chosen. The board snapped back to current // and looked like the picker had done nothing. // // A ref keyed on the code fixes it and states the intent: opening an existing // definition happens once, and after that the author owns the board. const openedDefinitionRef = useRef<string ¦ null>(null); useEffect(() => { if (!initialDefinitionCode) { return; } if (openedDefinitionRef.current === initialDefinitionCode) { return; } | 04_Frontend_App_14Sep2026_104846.txt 57750D130D30FC330C4D4A15E63CAC95C69CFD026A6F73EC8F3A9CD9E1924736 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-263 | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs | existing report routes | 10 | 33 | public static IEndpointRouteBuilder MapReportingEndpoints(this IEndpointRouteBuilder app) { var reports = app.MapGroup("/reports") .WithTags("Reports") .RequireAuthorization("PlantProcessViewer"); reports.MapGet("/materials/{materialUnitId:guid}/investigation", GetInvestigationReportAsync) .WithSummary("Get material investigation report"); reports.MapGet("/materials/{materialUnitId:guid}/investigation/pdf", GetInvestigationPdfAsync) .WithSummary("Export material investigation report as PDF"); reports.MapPost("/readiness-assessment", CreateReadinessReportAsync) .WithSummary("Create commercial readiness report") .WithDescription("Generates a 7-dimension commercial readiness report for Data Diagnostic assessment."); reports.MapGet("/readiness-assessment", GetReadinessReportAsync) .WithSummary("Get commercial readiness report"); reports.MapPost("/readiness-assessment/pdf", CreateReadinessPdfAsync) .WithSummary("Export commercial readiness report as PDF"); reports.MapGet("/readiness-assessment/pdf", GetReadinessPdfAsync) .WithSummary("Download commercial readiness report PDF"); | 01_Backend_Core_14Sep2026_104846.txt B814E486C8958B432341FB69887E98028F96A23AC0E05D6F8B283019B9AC0C1C | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-263 | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs | existing report service/PDF path | 57 | 85 | private static async Task<IResult> GetInvestigationReportAsync( Guid materialUnitId, [Microsoft.AspNetCore.Mvc.FromServices] IInvestigationReportService service, HttpContext httpContext, CancellationToken cancellationToken) { var result = await service.BuildMaterialInvestigationReportAsync( materialUnitId, httpContext.User?.Identity?.Name, cancellationToken); return result.ToHttpResult(value => Results.Ok(value)); } private static async Task<IResult> GetInvestigationPdfAsync( Guid materialUnitId, [Microsoft.AspNetCore.Mvc.FromServices] IInvestigationReportService service, HttpContext httpContext, CancellationToken cancellationToken) { var result = await service.BuildMaterialInvestigationPdfAsync( materialUnitId, httpContext.User?.Identity?.Name, cancellationToken); return result.ToHttpResult(value => Results.File( value.Content, value.ContentType, value.FileName)); | 01_Backend_Core_14Sep2026_104846.txt B814E486C8958B432341FB69887E98028F96A23AC0E05D6F8B283019B9AC0C1C | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-145 | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs | manual outcome DTO | 12 | 38 | public sealed record Phase8SuggestionOutcomeInput( string RecommendationId, string ActionTaken, string OutcomeKpi, decimal? BeforeValue, decimal? AfterValue, bool LowerIsBetter, IReadOnlyList<string>? EvidenceRefs, string Actor, string? Comment); public sealed record Phase8SuggestionOutcomeRecord( Guid OutcomeId, string RecommendationId, string ActionTaken, string OutcomeKpi, decimal? BeforeValue, decimal? AfterValue, decimal? Delta, string OutcomeDirection, decimal Confidence, string Actor, DateTimeOffset RecordedAtUtc, IReadOnlyList<string> EvidenceRefs, string OutcomeCaveat, string ValueLoopCaveat, bool CausalClaimMade); | 01_Backend_Core_14Sep2026_104846.txt 527170E4E18EC61D7C3418FE0D69BB75D832DE1D46E711A7A1A48566AB853B00 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-145 | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs | record calculation | 66 | 90 | public static Phase8SuggestionOutcomeRecord RecordOutcome(Phase8SuggestionOutcomeInput input) { ArgumentNullException.ThrowIfNull(input); if (string.IsNullOrWhiteSpace(input.RecommendationId)) throw new InvalidOperationException("RecommendationId is required."); if (string.IsNullOrWhiteSpace(input.ActionTaken)) throw new InvalidOperationException("ActionTaken is required."); var delta = input.BeforeValue.HasValue && input.AfterValue.HasValue ? input.AfterValue.Value - input.BeforeValue.Value : (decimal?)null; var direction = DetermineDirection(input.BeforeValue, input.AfterValue, input.LowerIsBetter); var confidence = DetermineConfidence(input); return new Phase8SuggestionOutcomeRecord( OutcomeId: Guid.NewGuid(), RecommendationId: input.RecommendationId.Trim(), ActionTaken: input.ActionTaken.Trim(), OutcomeKpi: Normalize(input.OutcomeKpi, "quality_risk"), BeforeValue: input.BeforeValue, AfterValue: input.AfterValue, Delta: delta, | 01_Backend_Core_14Sep2026_104846.txt 527170E4E18EC61D7C3418FE0D69BB75D832DE1D46E711A7A1A48566AB853B00 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-145 | Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs | process-memory endpoints | 16 | 48 | private static readonly ConcurrentDictionary<Guid, Phase8SuggestionOutcomeRecord> Outcomes = new(); public static IEndpointRouteBuilder MapPhase8SuggestionOutcomeLoopEndpoints(this IEndpointRouteBuilder app) { var group = app.MapGroup("/api/phase8") .WithTags("Phase 8 Suggestion Outcome Loop") .RequireAuthorization(); group.MapPost("/suggestions/outcomes/actioned", ([FromBody] Phase8SuggestionOutcomeInput request) => { var record = Phase8SuggestionOutcomeLoop.RecordOutcome(request); Outcomes[record.OutcomeId] = record; return Results.Ok(new { saved = true, record.OutcomeId, record.RecommendationId, record.OutcomeDirection, record.Confidence, record.CausalClaimMade, record.OutcomeCaveat, valueLoop = new { appearsInValueLoop = true, record.ValueLoopCaveat } }); }); group.MapGet("/suggestions/outcomes", () => { return Results.Ok(Outcomes.Values.OrderByDescending(x => x.RecordedAtUtc).ToArray()); | 01_Backend_Core_14Sep2026_104846.txt 892D6A4753E4F88CBB09FA032DE83A0D232346B994EEC258E06F01E344C43A04 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-146 | Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs | readiness/old selector | 49 | 62 | var readiness = ReadinessGate.Evaluate(matrix.Readiness, _thresholds); if (!readiness.CanRun) { await _sink.WriteAsync(runId, request, Array.Empty<AnalysisFinding>(), cancellationToken); var blocked = string.Join("; ", readiness.Dimensions.Where(d => d.State == ReadinessState.Blocked).Select(d => d.Reason)); return new CorrelationComputeResult(runId, 0, EngineKey, "Blocked", $"Readiness gate blocked the analysis. {blocked}"); } var outcome = matrix.Outcome; var prelim = new List<(FeatureColumn Col, AnalysisMethod Method, double Effect, double P, int N, double[] Px, double[] Py, bool Binary)>(); foreach (var col in matrix.Parameters) { var choice = MethodSelector.Select(col.Type, VariableType.Numeric); // outcome is numeric | 01_Backend_Core_14Sep2026_104846.txt 7E74634C64283FF43FCDACC81F59A3689727EA58605DEA081E9C3510661F72A6 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-146 | Backend/PlantProcess.Analytics.Engine/ManagedStatisticalComputeEngine.cs | live discipline calls | 91 | 115 | var fdr = BenjaminiHochberg.Adjust(prelim.Select(x => x.P).ToList(), _fdrQ); var findings = new List<AnalysisFinding>(prelim.Count); for (int i = 0; i < prelim.Count; i++) { var item = prelim[i]; var verdict = fdr[i]; double lo = 0, hi = 0, cons = 0; bool stable = false; if (verdict.Significant) { Func<IReadOnlyList<double>, IReadOnlyList<double>, double> stat = item.Binary ? (a, b) => { var v = Stats.Pearson(a, b); return double.IsNaN(v) ? 0.0 : v; } : (a, b) => { var v = Stats.Spearman(a, b); return double.IsNaN(v) ? 0.0 : v; }; var boot = Bootstrap.Stability(item.Px, item.Py, stat, iterations: 500, seed: 20260602UL); lo = boot.Lower; hi = boot.Upper; cons = boot.SignConsistency; stable = boot.Stable; } findings.Add(new AnalysisFinding( item.Col.Code, item.Method, item.Effect, item.P, verdict.QValue, verdict.Significant, item.N, lo, hi, cons, stable)); } var ranked = findings.OrderByDescending(f => Math.Abs(f.EffectSize)).ToList(); // rank by effect, never p await _sink.WriteAsync(runId, request, ranked, cancellationToken); | 01_Backend_Core_14Sep2026_104846.txt 7E74634C64283FF43FCDACC81F59A3689727EA58605DEA081E9C3510661F72A6 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-146 | Backend/PlantProcess.Application/Analytics/Advanced/AdvancedCorrelationComputeService.cs | live ranking/FDR/bootstrap | 117 | 137 | // ---- P3-04: rank by EFFECT, then Benjamini-Hochberg FDR ---- var findings = kept.Select(c => new Finding(c.FeatureKey, c.Effect, c.PValue, c.Method.ToString(), c.SampleSize)).ToList(); var ranked = EffectRanking.RankByEffect(findings); var fdr = BenjaminiHochberg.Adjust(ranked.Select(f => f.PValue).ToList(), request.FdrQ); var byKey = kept.ToDictionary(c => c.FeatureKey); var results = new List<AdvancedFinding>(ranked.Count); for (int i = 0; i < ranked.Count; i++) { var c = byKey[ranked[i].Id]; var q = fdr[i]; var boot = Bootstrap.Stability(c.X, c.Y, c.Stat, request.BootstrapIterations, seed: Seed); var (survives, sreason) = EvaluateStrata(c, ds); // PPIQ_REALIZATION_T044_FINDING_TRANSPARENCY_EVIDENCE: each finding carries c.SampleSize, c.Dropped, survives/sreason and provenance. results.Add(new AdvancedFinding( c.FeatureKey, c.Method, c.Rationale, c.Effect, q.PValue, q.QValue, q.Significant, c.SampleSize, boot.SignConsistency, boot.Lower, boot.Upper, boot.Stable, survives, sreason, c.Dropped, $"finding:{runId:N}:{c.FeatureKey}", AdvancedAnalysisResult.DefaultCaveat)); | 01_Backend_Core_14Sep2026_104846.txt 32CBB3F1D498416130C96300E949F9553EFBEC86A2211A63E5524A8BF65CC7FC | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-146 | Backend/PlantProcess.Analytics.Core/Kernel/KernelMethodSelector.cs | kernel pairing | 27 | 57 | public static class KernelMethodSelector { public static KernelPairingChoice Classify(VariableType a, VariableType b) { bool aNum = a == VariableType.Numeric; bool bNum = b == VariableType.Numeric; bool aCat = a == VariableType.Categorical ¦¦ a == VariableType.Binary; bool bCat = b == VariableType.Categorical ¦¦ b == VariableType.Binary; if (aNum && bNum) return Supported(KernelPairing.NumericNumeric, "Numeric/numeric: rank correlation path, unchanged from the existing selector."); if ((a == VariableType.Binary && bNum) ¦¦ (aNum && b == VariableType.Binary)) return Supported(KernelPairing.BinaryNumeric, "Binary/numeric: point-biserial path, unchanged from the existing selector."); if ((aNum && b == VariableType.Categorical) ¦¦ (a == VariableType.Categorical && bNum)) return Supported(KernelPairing.NumericCategorical, "Numeric/categorical: assumption-aware one-way ANOVA with Kruskal-Wallis fallback."); if (aCat && bCat) return Supported(KernelPairing.CategoricalCategorical, "Categorical/categorical: Cramer's V path, unchanged from the existing selector."); return new KernelPairingChoice( KernelPairing.Unsupported, false, StatisticalExclusionReason.UnsupportedMethodPairing, ExclusionAttribution.Method, $"No enabled statistical method exists for the variable-type pair ({a},{b}). " + "This is a limitation of the available method set, not a property of the data."); | 01_Backend_Core_14Sep2026_104846.txt 59B8B14C480AF182459349F4649309A86D734889F26774C60A57A0E61E5A7FA1 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-165 | Website/PlantProcess.Website/src/components/proof/PricingLicenseMatrix.tsx | plan display | 1 | 49 | import { licensePlans } from "../../content/phase1WebsiteProof"; export function PricingLicenseMatrix() { return ( <section className="website-section pricing-section" id="pricing"> <div className="section-kicker">Pricing and license logic</div> <div className="section-heading-row"> <div> <h2>Start where you are. Expand when the value is proven on your data.</h2> <p> The commercial packaging mirrors the product gating: number of data sources, feature depth, users, refresh cadence and enterprise controls. One deposit, one subscription, no hidden line items. </p> </div> </div> <div className="pricing-grid"> {licensePlans.map((plan) => ( <article className={`pricing-card pricing-card--${plan.code}`} key={plan.code}> <div className="pricing-card__top"> <span> {plan.name} {plan.recommended ? " (Recommended)" : ""} </span> <strong>{plan.monthlyPrice}</strong> </div> <p>{plan.idealFor}</p> <dl> <div> <dt>Deposit</dt> <dd>{plan.deposit}</dd> </div> <div> <dt>Data sources</dt> <dd>{plan.sources}</dd> </div> <div> <dt>Users</dt> <dd>{plan.users}</dd> </div> <div> <dt>Connectors</dt> <dd>{plan.connectors}</dd> </div> </dl> | 08_Website_14Sep2026_104846.txt D0B4AFBD9EA1938C8D2708C1AF8DF48BA8791525BC6CD5F338396492ACE04439 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-165 | Backend/PlantProcess.ML.Runtime/Benchmarks/BenchmarkManifest.cs | selected measured value identity | 17 | 26 | public sealed record SelectedBenchmarkValue { public required string BenchmarkId { get; init; } public required string MetricName { get; init; } public required double Value { get; init; } public required string Unit { get; init; } public required MetricAggregation Aggregation { get; init; } public required string EvidenceExperimentId { get; init; } public required string EvidenceGitCommit { get; init; } } | 07_Tools_Validation_Misc_14Sep2026_104846.txt 70B5B58321B414CF47DF5486616D1C28016D7661C36F8E50921DCEBD3D08F8DF | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-186 | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs | pure kernel boundary | 8 | 19 | /// <summary> /// Industry-neutral capability profiler. Measures what the available data can actually /// support, and returns the measured facts with every decision. /// <para> /// Three rules govern the whole class: /// a single-level context dimension is collapsed, not an error; /// absent genealogy removes only capabilities that genuinely need genealogy; /// missing outcomes remove only capabilities that genuinely need labelled outcomes. /// </para> /// <para> /// Reads no database, holds no connection, knows no customer vocabulary. /// </para> | 01_Backend_Core_14Sep2026_104846.txt 45F8DFAB405875F88A4A86E16072B041BE405B08B482CD8FCD27B1F286F7C752 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-186 | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs | profile calculation | 36 | 64 | public static CapabilityProfile Profile(CapabilityProfilerInput input) { var dimensions = ProfileDimensions(input.ContextDimensions); var eligibleDimensionCount = dimensions.Count(d => d.Status == DimensionStatus.Eligible); var populationFacts = new List<MeasuredFact> { MeasuredFact.AtLeast("analytical_units", input.AnalyticalUnitCount, MinUnitsForStatistics, "units"), MeasuredFact.AtLeast("history_span", input.HistorySpanDays, MinHistoryDays, "days"), MeasuredFact.Informational("declared_outcomes", input.Outcomes.Count, "count"), MeasuredFact.Informational("eligible_context_dimensions", eligibleDimensionCount, "count"), MeasuredFact.Informational("collapsed_context_dimensions", dimensions.Count(d => d.Status == DimensionStatus.Collapsed), "count"), MeasuredFact.Informational("process_positions", input.Genealogy.ProcessPositionCount, "count") }; var capabilities = new List<CapabilityVerdict> { EvaluateStatistics(input), EvaluateSimilarity(input), EvaluateNovelty(input), EvaluateSupervisedPrediction(input), EvaluatePracticeLearning(input) }; var practice = capabilities.First(c => c.Capability == CapabilityCode.PracticeLearning); capabilities.Add(EvaluateRemediation(input, practice, eligibleDimensionCount)); return new CapabilityProfile(capabilities, dimensions, input.Genealogy.Strength, populationFacts); | 01_Backend_Core_14Sep2026_104846.txt 45F8DFAB405875F88A4A86E16072B041BE405B08B482CD8FCD27B1F286F7C752 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-186 | Backend/PlantProcess.Analytics.Core/Kernel/Capability/CapabilityProfiler.cs | dimension assessment | 69 | 96 | private static IReadOnlyList<DimensionVerdict> ProfileDimensions( IReadOnlyList<ContextDimensionObservation> observed) { var verdicts = new List<DimensionVerdict>(); foreach (var d in observed ?? new List<ContextDimensionObservation>()) { if (d.ObservedLevelCount <= 0) { verdicts.Add(new DimensionVerdict(d.DimensionCode, d.ObservedLevelCount, DimensionStatus.Absent, d.IsVariantDimension, "The dimension is declared but no level was observed in the population.")); continue; } if (d.ObservedLevelCount == 1) { verdicts.Add(new DimensionVerdict(d.DimensionCode, 1, DimensionStatus.Collapsed, d.IsVariantDimension, "One effective level. The dimension is removed from the eligible set and " + "cannot condition an analysis. This is not an error: an installation with " + "a single level of this dimension is a normal installation.")); continue; } verdicts.Add(new DimensionVerdict(d.DimensionCode, d.ObservedLevelCount, DimensionStatus.Eligible, d.IsVariantDimension, "Two or more effective levels. The dimension can condition an analysis.")); } | 01_Backend_Core_14Sep2026_104846.txt 45F8DFAB405875F88A4A86E16072B041BE405B08B482CD8FCD27B1F286F7C752 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-190 | Backend/PlantProcess.Api/Endpoints/Assistant/Phase8SuggestionOutcomeLoopEndpoints.cs | legacy write path | 16 | 43 | private static readonly ConcurrentDictionary<Guid, Phase8SuggestionOutcomeRecord> Outcomes = new(); public static IEndpointRouteBuilder MapPhase8SuggestionOutcomeLoopEndpoints(this IEndpointRouteBuilder app) { var group = app.MapGroup("/api/phase8") .WithTags("Phase 8 Suggestion Outcome Loop") .RequireAuthorization(); group.MapPost("/suggestions/outcomes/actioned", ([FromBody] Phase8SuggestionOutcomeInput request) => { var record = Phase8SuggestionOutcomeLoop.RecordOutcome(request); Outcomes[record.OutcomeId] = record; return Results.Ok(new { saved = true, record.OutcomeId, record.RecommendationId, record.OutcomeDirection, record.Confidence, record.CausalClaimMade, record.OutcomeCaveat, valueLoop = new { appearsInValueLoop = true, record.ValueLoopCaveat } }); | 01_Backend_Core_14Sep2026_104846.txt 892D6A4753E4F88CBB09FA032DE83A0D232346B994EEC258E06F01E344C43A04 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-190 | Backend/PlantProcess.Application/AssistantRuntime/Phase8SuggestionOutcomeLoop.cs | caller outcome schema | 12 | 38 | public sealed record Phase8SuggestionOutcomeInput( string RecommendationId, string ActionTaken, string OutcomeKpi, decimal? BeforeValue, decimal? AfterValue, bool LowerIsBetter, IReadOnlyList<string>? EvidenceRefs, string Actor, string? Comment); public sealed record Phase8SuggestionOutcomeRecord( Guid OutcomeId, string RecommendationId, string ActionTaken, string OutcomeKpi, decimal? BeforeValue, decimal? AfterValue, decimal? Delta, string OutcomeDirection, decimal Confidence, string Actor, DateTimeOffset RecordedAtUtc, IReadOnlyList<string> EvidenceRefs, string OutcomeCaveat, string ValueLoopCaveat, bool CausalClaimMade); | 01_Backend_Core_14Sep2026_104846.txt 527170E4E18EC61D7C3418FE0D69BB75D832DE1D46E711A7A1A48566AB853B00 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-264 | Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs | demo dashboard | 17 | 35 | public P15BenchmarkDashboardResponse BuildDemoDashboard() { var request = BuildDemoRequest(); var benchmark = Benchmark(request, cohortSize: 12); var suppressed = Benchmark(BuildDemoRequest(minimumCohortSize: 8), cohortSize: 3); return new P15BenchmarkDashboardResponse { Status = "Ready", Message = "Cross-plant and industry benchmark dashboard generated from anonymized aggregate demo bands.", GeneratedAtUtc = DateTimeOffset.UtcNow, TenantId = request.TenantId, PlantId = request.PlantId, IndustryCode = request.IndustryCode, Benchmarks = new[] { benchmark, suppressed }, MetricCards = BuildMetricCards(benchmark), BestPractices = BuildBestPractices(request.IndustryCode), PrivacyGuards = DefaultPrivacyGuards() }; | 01_Backend_Core_14Sep2026_104846.txt 98C1A4BBDEF04EBB5FDB7F9C10D60A917B1DFD41E26C6BE989965F5ACFD4DB17 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-264 | Backend/PlantProcess.Application/Advisory/P15BenchmarkingService.cs | generated bands | 50 | 85 | public P15BenchmarkResponse Benchmark(P15BenchmarkRequest request, int cohortSize) { var privacy = P15AdvisoryHonestyPolicy.ValidateBenchmarkVisibility(request, cohortSize); if (!privacy.IsAllowed) { return new P15BenchmarkResponse { MetricCode = request.MetricCode, IndustryCode = request.IndustryCode, Visibility = P15BenchmarkVisibility.SuppressedMinimumCohort, Message = "Benchmark suppressed because the anonymized cohort is below minimum privacy threshold.", Band = null, PrivacyGuards = DefaultPrivacyGuards().Append("Suppressed below minimum cohort size.").ToArray() }; } var baseValue = BuildStableBaseValue(request); var band = new P15BenchmarkBand { BandCode = $"band-{Sanitize(request.IndustryCode)}-{Sanitize(request.MetricCode)}", P10 = Round(baseValue * 0.82m), P25 = Round(baseValue * 0.91m), P50 = Round(baseValue), P75 = Round(baseValue * 1.10m), P90 = Round(baseValue * 1.22m), CohortSize = cohortSize, Visibility = P15BenchmarkVisibility.Visible }; return new P15BenchmarkResponse { MetricCode = request.MetricCode, IndustryCode = request.IndustryCode, Visibility = P15BenchmarkVisibility.Visible, Message = "Benchmark visible as anonymized aggregate band only. No identifiable cross-tenant rows are exposed.", Band = band, | 01_Backend_Core_14Sep2026_104846.txt 98C1A4BBDEF04EBB5FDB7F9C10D60A917B1DFD41E26C6BE989965F5ACFD4DB17 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-265 | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx | existing associative control semantics | 8 | 36 | /** M2-37 associative engine (Qlik spec S0), client-orchestrated: * possible-set per field = the existing, registry-validated widget query for * that field's dimension, with the current selections MINUS the field's own * (so alternatives inside a field stay selectable - the Qlik semantic). * all-set = the same query, unfiltered, cached at mount. * excluded = all minus possible. selected = the field's current filter value. */ /** T-048. The four states Chapter 4 5.1.3 requires. * * ALTERNATIVE is not a weaker "possible". It means: this field already has a * selection, and this value is the road not taken - still reachable in one * click, and excluded from nothing. Collapsing it into "possible" hides which * field the reader is currently steering by. */ export type ValueState = "selected" ¦ "possible" ¦ "excluded" ¦ "alternative"; export type FieldAssoc = { field: AssocField; available: boolean; loading: boolean; all: string[]; states: Map<string, ValueState>; possibleCount: number; }; type Ctx = { enabled: boolean; setEnabled: (v: boolean) => void; fields: FieldAssoc[]; toggleValue: (fieldKey: string, value: string) => void; | 04_Frontend_App_14Sep2026_104846.txt 1CECF013ACABE4EC5D2F048119E21829C61726E26D152B943278D4FA0991BE56 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-265 | Frontend/PlantProcess.Web/src/authoring/SharedAuthoringShell.tsx | existing reopen model | 333 | 403 | + " under another purpose would be judged by the wrong palette and the wrong rules." + " Open it from its own authoring surface."); return; } setNodes(r.board.nodes.map((n) => ({ id: n.id, type: n.kind, position: { x: n.position.x, y: n.position.y }, data: n.data, })) as Node[]); setEdges(r.board.edges.map((e, i) => ({ id: "reopened-" + i, source: e.source, target: e.target, sourceHandle: e.sourceHandle ?? undefined, targetHandle: e.targetHandle ?? undefined, })) as Edge[]); if (r.graph?.name) { setName(r.graph.name); } if (r.outputTarget) { setOutputTarget(r.outputTarget); } // T-262. Restored EXACTLY, or recorded as absent. A version written before // declarations existed carries none, and nothing is reconstructed for it: the // inspector says so and the author maps it into a new version. setProjection(r.projection ?? null); setReopenedWithoutProjection(!r.projection); setProjectionRefusal(null); setOpenVersion(r.versionNumber); logSuccess(name, "Reopened version " + r.versionNumber + ".", r.board.nodes.length + " block(s), " + r.board.edges.length + " connection(s), target " + (r.outputTarget ?? "none") + ", hash " + r.definitionHash); }, [name, purpose, setNodes, setEdges, logSuccess, logWarning]); // Choosing a version from history. READ-ONLY: it restores what was authored and // never rewrites it. Publishing after reopening an older version creates a NEW // version through the canonical lifecycle - rollback forward, never in place. const doReopen = useCallback(async (code: string, version: number) => { try { applyReopenedDefinition(await reopenDefinition(code, version)); } catch (e) { logError(name, describeThrownAction(e)); } }, [name, applyReopenedDefinition, logError]); // T-243 CLOSURE. SAVE, CLOSE, COME BACK TOMORROW. // // Before this the shell only learned its canonical code as a by-product of // publishing, so history existed for the session that created it and vanished with // the tab. Opening with an existing code is the other half of persistence: the // definition is fetched from the canonical store and nothing else - no localStorage, // no cached board, no reconstruction from the compiled query. // ONCE PER DEFINITION, NOT ONCE PER RENDER IDENTITY. // // The first version of this effect depended on applyReopenedDefinition, which is a // useCallback over name. Restoring a definition SETS name, so the callback got a new // identity, the effect re-ran, and it reopened the current version - silently undoing // a historical version the author had just chosen. The board snapped back to current // and looked like the picker had done nothing. // // A ref keyed on the code fixes it and states the intent: opening an existing // definition happens once, and after that the author owns the board. const openedDefinitionRef = useRef<string ¦ null>(null); useEffect(() => { if (!initialDefinitionCode) { return; } if (openedDefinitionRef.current === initialDefinitionCode) { return; } | 04_Frontend_App_14Sep2026_104846.txt 57750D130D30FC330C4D4A15E63CAC95C69CFD026A6F73EC8F3A9CD9E1924736 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-266 | Backend/PlantProcess.Api/PlantConnectors/V5GaHistorianConnectorEndpoints.cs | actual unavailable contract | 61 | 108 | public static class HistorianConnectorCapabilities { public const string NotExecutableCode = "OT01"; public const string NotExecutableMessage = "This connector operation is declared but not executable in this build. " + "It returns no value rather than a placeholder."; public const string ConfigurationValidation = "configurationValidation"; public const string MappingHintsFromSuppliedTagPaths = "mappingHintsFromSuppliedTagPaths"; public const string TagBrowse = "tagBrowse"; public const string BoundedRead = "boundedRead"; public const string Subscription = "subscription"; public const string LiveVendorHandshake = "liveVendorHandshake"; public static readonly IReadOnlyList<ConnectorCapability> All = new[] { new ConnectorCapability( ConfigurationValidation, true, "The /test-connection route validates the supplied endpoint and read-only posture and returns no measurement."), new ConnectorCapability( MappingHintsFromSuppliedTagPaths, true, "The /mapping-hints route classifies tag paths the caller supplied. It never supplies tag paths of its own."), new ConnectorCapability( TagBrowse, false, "Real OPC UA namespace browse is not yet implemented."), new ConnectorCapability( BoundedRead, false, "Real OPC UA value acquisition is not yet implemented."), new ConnectorCapability( Subscription, false, "Real OPC UA monitored items and subscriptions are not yet implemented."), new ConnectorCapability( LiveVendorHandshake, false, "Real OPC UA session security, certificate and trust handling is not yet implemented.") }; public static bool IsExecutable(string name) { foreach (var capability in All) { if (string.Equals(capability.Name, name, StringComparison.Ordinal)) { return capability.Executable; } } return false; | 01_Backend_Core_14Sep2026_104846.txt A45C75DF4E4C2C493195ACC5F08E46E668AF1094AC977729092C961E1AA55790 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-266 | Backend/PlantProcess.Infrastructure/Connectors/Historian/OpcUaHistorianConnector.cs | configuration interface | 24 | 72 | public Task<DataSourceConnectionTestResult> TestConnectionAsync( ConnectionProfile connectionProfile, CancellationToken cancellationToken) { try { cancellationToken.ThrowIfCancellationRequested(); var endpointUrl = FirstNonEmpty( connectionProfile.ApiBaseUrl, GetJsonString(connectionProfile.ConnectionOptionsJson, "endpointUrl", "opcEndpointUrl", "historianEndpointUrl"), connectionProfile.HostName); if (string.IsNullOrWhiteSpace(endpointUrl)) return Task.FromResult(Failure("Historian connector requires ApiBaseUrl, HostName, or connectionOptionsJson.endpointUrl.")); var namespaceUri = FirstNonEmpty( GetJsonString(connectionProfile.ConnectionOptionsJson, "namespaceUri", "namespace", "tagNamespace"), connectionProfile.SchemaName); var readOnly = GetJsonBool(connectionProfile.ConnectionOptionsJson, "readOnly") ?? connectionProfile.ReadOnlyEnforced; var requireLiveHandshake = GetJsonBool(connectionProfile.ConnectionOptionsJson, "requireLiveHandshake") ?? false; if (!readOnly) return Task.FromResult(Failure("Historian connector is read-only. Set readOnly=true / ReadOnlyEnforced=true.")); if (requireLiveHandshake) return Task.FromResult(Failure("Live vendor handshake was requested, but no customer historian gateway is attached in this environment. Configuration is not marked as reachable.")); var metadata = new Dictionary<string, string?> { ["providerType"] = ProviderType, ["mode"] = "read-only-gateway", ["endpointUrl"] = endpointUrl, ["namespaceUri"] = namespaceUri, ["readOnly"] = readOnly.ToString(CultureInfo.InvariantCulture), ["supportsTagBrowse"] = "true", ["supportsBoundedRead"] = "true", ["supportsMappingHints"] = "true", ["liveHandshake"] = "environment-specific" }; _lastError = null; return Task.FromResult(new DataSourceConnectionTestResult( IsSuccess: true, Message: "Historian gateway configuration is valid for read-only onboarding. Live vendor handshake remains environment-specific.", TestedAtUtc: DateTime.UtcNow, Metadata: metadata)); | 01_Backend_Core_14Sep2026_104846.txt D9953F23C2E7C2E841D49E46901D3EAD698C03423ACAF6C2D2FEB2250523B314 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-267 | Frontend/PlantProcess.Web/src/state/AssociativeContext.tsx | M2 behaviour to preserve | 8 | 36 | /** M2-37 associative engine (Qlik spec S0), client-orchestrated: * possible-set per field = the existing, registry-validated widget query for * that field's dimension, with the current selections MINUS the field's own * (so alternatives inside a field stay selectable - the Qlik semantic). * all-set = the same query, unfiltered, cached at mount. * excluded = all minus possible. selected = the field's current filter value. */ /** T-048. The four states Chapter 4 5.1.3 requires. * * ALTERNATIVE is not a weaker "possible". It means: this field already has a * selection, and this value is the road not taken - still reachable in one * click, and excluded from nothing. Collapsing it into "possible" hides which * field the reader is currently steering by. */ export type ValueState = "selected" ¦ "possible" ¦ "excluded" ¦ "alternative"; export type FieldAssoc = { field: AssocField; available: boolean; loading: boolean; all: string[]; states: Map<string, ValueState>; possibleCount: number; }; type Ctx = { enabled: boolean; setEnabled: (v: boolean) => void; fields: FieldAssoc[]; toggleValue: (fieldKey: string, value: string) => void; | 04_Frontend_App_14Sep2026_104846.txt 1CECF013ACABE4EC5D2F048119E21829C61726E26D152B943278D4FA0991BE56 | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.
T-267 | Backend/PlantProcess.Api/Endpoints/Reporting/ReportingEndpoints.cs | existing report subset, not full E5 | 10 | 33 | public static IEndpointRouteBuilder MapReportingEndpoints(this IEndpointRouteBuilder app) { var reports = app.MapGroup("/reports") .WithTags("Reports") .RequireAuthorization("PlantProcessViewer"); reports.MapGet("/materials/{materialUnitId:guid}/investigation", GetInvestigationReportAsync) .WithSummary("Get material investigation report"); reports.MapGet("/materials/{materialUnitId:guid}/investigation/pdf", GetInvestigationPdfAsync) .WithSummary("Export material investigation report as PDF"); reports.MapPost("/readiness-assessment", CreateReadinessReportAsync) .WithSummary("Create commercial readiness report") .WithDescription("Generates a 7-dimension commercial readiness report for Data Diagnostic assessment."); reports.MapGet("/readiness-assessment", GetReadinessReportAsync) .WithSummary("Get commercial readiness report"); reports.MapPost("/readiness-assessment/pdf", CreateReadinessPdfAsync) .WithSummary("Export commercial readiness report as PDF"); reports.MapGet("/readiness-assessment/pdf", GetReadinessPdfAsync) .WithSummary("Download commercial readiness report PDF"); | 01_Backend_Core_14Sep2026_104846.txt B814E486C8958B432341FB69887E98028F96A23AC0E05D6F8B283019B9AC0C1C | INSPECTED SOURCE; original-file line range. Export SHA recorded, not independently re-hashed original bytes.

## Source Summary
PLANTPROCESS IQ ¦ IMPLEMENTATION-BOUND BACKLOG REVIEW
v2.23.0 maintained · 14-Sep source snapshot + latest 15-Sep USER-REPORTED T-100 runner progress · not live-HEAD certification
51 source assessments remain; T-100 updated from later reported runner progress. 50 have numeric remainder proposals; T-100 closure-only remainder is UNCONFIRMED. Full ten-session coverage remains incomplete.
Metric | All backlog | M2 | M2-P2 | Interpretation
Active tasks | 187 | 115 | 42 | 179 tasks retained; T-100 Not Started→In Progress only
Source-reviewed tasks | 59 | 46 | 42 | Assessment coverage, not product completion
Not source-reviewed this pass | 128 | 69 | 0 | Unknown work is NOT zero remaining time
Proposed remaining LOW h | 374 | 214 | 152 | Incomplete subtotal; excludes T-100 UNCONFIRMED closure remainder and unreviewed tasks
Proposed remaining BASE h | 626 | 350 | 248 | Not a release forecast or P80; excludes unpriced T-100 remainder
Proposed remaining HIGH h | 1021 | 565 | 399 | Does not bound T-100 closure effort; estimate not supplied
Unusable historical scope estimates with source review | 39 | 26 | 22 | Historical scope estimates remain unchanged in J/R
READ THIS BEFORE USING THE HOURS
Numeric low/base/high values remain unconfirmed engineering proposals. T-100's previous 6/10/16 was superseded by reported implementation and is now UNCONFIRMED closure-only, not zero.
Existing Hours / AI Guarded P80 remain historical inputs. Do not add scope Hours to the new remaining-work estimates.
No whole-project or delivery-date forecast is asserted: 128 task scopes have not been source-reviewed in this pass.
Shared seams are allocated once: T-261 executor/common cancellation/T-262 Gate 0; T-106 policies; T-104 row provenance; T-101 monitoring UI.
Source dump remains 14-Sep. Later T-100 progress is owner-reported, not inspected live source. No inference that issued recovery scripts already passed.
No .NET build, product PostgreSQL test or live browser/Figma execution was available here. Isolated logical probes below are not those tests.
Complete session text remains unrecovered for all ten named sessions. Their excerpts/attachments help provenance but cannot prove no later decision exists.
T-099 remains Done at ca02b40ea1b69050a45cb35a3e1d64f15b1f66af, parent 86e1b677212195f191697ecdca7e9441b3dbde33. Known inherited RED is not a reopened task.
T-262 original closure is evidenced. The later shared Gate 0 belongs to T-261 Runner 2; reconcile completion-gate ownership separately from source-authoring readiness.
Probe / correction | Task | Expected | Observed | Verdict | Evidence level | Action | Scope
Weight 0.99 | T-103 | Reject per task acceptance | SQL tolerance 0.015 admits 0.99 | Logical mismatch | Inspected predicate + Python arithmetic | Correct/validate T-103 weight semantics | Do not reopen T-099 topology fix
Scalar cursor ties | T-108 | Read all 10 across cap=3 | Scalar simulation 3/10; tuple 10/10 | Counterexample | Source query + isolated Python simulation | Total-order cursor + durable replay | No customer incident asserted
Alias namespace | T-102 | Unique namespace-aware resolution | Two legal composite records match alias-only | Ambiguity mechanism | Schema + predicate + constructed rows | Constrain or refuse ambiguity | No live wrong resolution asserted
Discipline file is live | T-146 | Preserve current consumers | FDR/bootstrap/ranking live calls exist | Prior dead-file finding disproven | Direct source call sites | Do not delete on filename search | Converge method kernel only
SQL mapping-only save | T-262 | Latest accepted mapping saved | Callback omits projection dependencies | Suspected behaviour | Dependency-array source trace | Real shell mapping-only regression test | Not claimed reproduced in browser
WHERE TO READ: Source Review = 51 records; Source Evidence = 129 excerpts; M2-P2 Review = all 34 P2 tasks; Review 15Sep = ten-session ledger.
Historical validation below concerns the prior source-review artifact; current runner-update validation is recorded from row 70. Historical checks are not re-claimed as fresh product proof.
Check | Result | Scope | Notes
179 unique task IDs retained | PASS | Saved XLSX read-back
Protected task fields unchanged | PASS | Saved XLSX read-back | []
Only T-146 description clarification | PASS | Saved XLSX read-back | ['T-146']
No self-dependency / self-precede | PASS | Saved XLSX read-back | []
Only five declared external predecessors | PASS | Saved XLSX read-back | ['T-032', 'T-035', 'T-036', 'T-057', 'T-064']
Must Precede reciprocal | PASS | Saved XLSX read-back | []
No M2 completion dependency on M3 | PASS | Saved XLSX read-back | []
Completion graph acyclic | PASS | Saved XLSX read-back
Dependency Graph matches saved Backlog | PASS | Saved XLSX read-back | []
Worker Tracks matches saved Backlog | PASS | Saved XLSX read-back | []
51 substantive source records | PASS | Saved XLSX read-back
All 34 M2-P2 source records present | PASS | Saved XLSX read-back
Unknown remainder never zero | PASS | Saved XLSX read-back
All linked remaining estimates match source data | PASS | Saved XLSX read-back | []
Lower <= base <= upper | PASS | Saved XLSX read-back
All 27 invalid historical estimates have remainder review | PASS | Saved XLSX read-back
HISTORICAL: M2-P2 estimates before T-100 runner update = 194/316/511 | PASS | Prior source-review XLSX, not current totals
HISTORICAL: all reviewed estimates before T-100 update = 416/694/1133 | PASS | Prior source-review XLSX, not current totals
HISTORICAL: statuses before T-100 update = 58/5/116 | PASS | Prior source-review XLSX, not current counts | Counter({'Not Started': 116, 'Done': 58, 'In Progress': 5})
T-099 closure and parent preserved | PASS | Saved XLSX read-back
No cached Excel formula errors | PASS | Saved XLSX read-back | []
All original sheets retained | PASS | Saved XLSX read-back
No new official task IDs or release changes | PASS | Saved XLSX read-back
Self dependency | PASS | Validator negative control | Injected error was detected
M2 dependent on M3 | PASS | Validator negative control | Injected error was detected
Remaining estimate divergence | PASS | Validator negative control | Injected error was detected
Ten full session transcripts | OPEN | Access boundary | No full transcript claimed. Source files and selected dated attachments were actually read.
Live source HEAD after 14-Sep | OPEN | Snapshot boundary | No local Git repository/remote HEAD verification. Later implementation may alter remaining estimates.
Remaining 128 task source scopes | OPEN | Review coverage | Retained in coverage ledger; no new zero-time or Done inference.
Worker confirmation of estimates | OPEN | Forecast boundary | 50 numeric remainder proposals remain unconfirmed; T-100 closure-only remainder is unpriced. Historical Hours/P80 are not remaining work.
LATEST T-100 RUNNER / LOCK UPDATE | Result | Evidence class | Detail
179 tasks / M2 107 / M3 72 retained | PASS — saved-XLSX check | Workbook structure | No task/release changes
Current status counts | PASS — saved-XLSX check | Workbook values | 58 Done / 6 In Progress / 115 Not Started
T-100 progress, not closure | PASS — saved-XLSX check | User report recorded | Runner1 GREEN, build/constraint passed; live harness blocked; no commit invented
T-100→T-261 and reciprocal edge | PASS — saved-XLSX check | Current owner instruction | Backlog, Dependency Graph and Worker Tracks must agree by Task ID
No self edges / cycles / M2-on-M3 | PASS — saved-XLSX check | Workbook dependency checks | Five external prerequisite IDs retained
T-099 frozen record preserved | PASS — saved-XLSX check | Preserved closure evidence | Commit/parent/status unchanged
T-100 proposed remainder | PASS — saved-XLSX check | Forecast hygiene | UNCONFIRMED; prior 6/10/16 kept in change history; unknown is not zero
Current M2-P2 numeric subtotal | PASS — saved-XLSX check | Incomplete subtotal | 188/306/495, PLUS unknown T-100 closure effort
Current reviewed numeric subtotal | PASS — saved-XLSX check | Incomplete subtotal | 410/684/1117, PLUS unknown T-100 closure effort
Source-review coverage | PASS — saved-XLSX check | Assessment count, not time count | 51 reviewed scopes; 34 M2-P2; 128 still unreviewed
Latest recovery runner execution | NOT OBSERVED | Explicit runtime boundary | Resume v1.0.1 issued by report; success not reported and no script executed here