## Go-Live Backlog
Task ID | Task Name | Phase | Track | Module | Submodule | Severity | Description | Acceptance Criteria | Task Type | Effort (h)
Phase 1 · Deploy stability & safe test profiles
T-01 | Converge to ONE canonical deploy stack | Phase 1 · Deploy stability & safe test profiles | Deploy | Infrastructure | Docker/Compose/Caddy | Critical | The server runs (or has run) parallel Docker stacks; only one (compose project 'plantprocessiq', containers ppiq-app-*) is what Caddy actually serves. Eliminate every orphan. (1) Make Infrastructure/deploy/docker-compose.demo.yml the single canonical file: connection key MUST be ConnectionStrings__PlantProcessDb (NOT __DefaultConnection); add a 64-char PlantProcess__Auth__SigningKey wired from deploy/compose/.env; add the admin user from env (IsBootstrapAdmin=false); add PLANTPROCESS_ALLOWED_ORIGINS; restore the caddy service block lost in the T208 overwrite; pin ASPNETCORE_URLS and the Caddy upstream to the SAME port; bind Postgres to 127.0.0.1. (2) Write deploy/server/converge-canonical-stack.sh that backs up, deletes the ppiq-demo project and every plantprocess-* orphan container/network (volumes NEVER touched), keeps plantprocessiq. (3) Write deploy/server/probe-canonical.sh hitting /health, /auth/login, and /analytics/dashboard/definitions. Run on the server over SSH. | On a clean server checkout: `bash converge-canonical-stack.sh` leaves exactly one compose project (plantprocessiq) and zero plantprocess-* containers (assert via `docker compose ls` and `docker ps`). `bash probe-canonical.sh` returns 200 on all three probes and every ppiq-* container shows RestartCount=0. A git push triggers a deploy that serves the new build at the public URL with NO manual intervention. | hardening | 16
T-02 | Rebuild Jenkins pipeline to the exact agreed sequence | Phase 1 · Deploy stability & safe test profiles | Deploy | Deploy | CI/CD | Critical | Replace the legacy Jenkinsfile so the pipeline does ONLY: checkout (preserving server .env/Caddyfile) -> sweep stale processes -> `dotnet test Backend` (BLOCKING) -> `npm run test` (BLOCKING) -> `npm run e2e` against an ephemeral CI stack (BLOCKING) -> migrate the main Postgres app DB + the 8 demo/source DBs -> seed demo data -> build -> recreate the canonical live stack in place with a health gate + automatic rollback to :previous. NOTHING else (no extra lint-only stages, no enumeration). Provide the four helper scripts (sweep-stale.sh, ci-e2e-stack.sh, migrate-and-seed.sh, deploy-canonical.sh). Set the demo-source service names in the two CONFIG blocks via `docker compose config --services`. Configure the Jenkins job as 'Pipeline script from SCM', branch main. | Break one backend test, push: pipeline goes RED and stages migrate/seed/deploy DO NOT run (verify in Jenkins stage view). Revert, push: pipeline goes GREEN and the new build is live, health-gated. Confirm no `--list` and no `catchError(buildResult:'SUCCESS')` anywhere in the Jenkinsfile. The CiPipelineTruthGateTests architecture test passes against the new file. | hardening | 14
T-03 | Switchable run/test profiles (local + server) | Phase 1 · Deploy stability & safe test profiles | Hardening | Backend | TestMode/Auth/License | Critical | Make it possible to exercise EVERY auth/license combination locally and on the server with NO code edit and NO hand-editing the DB. Bind a PPIQ_TESTMODE options section: SeedUsers (seeds one user per role: Admin/Executive/ProcessEngineer/Operator with fixed documented passwords via the existing PlantProcess:Auth:Users path), ForceTier (upserts demo_runtime_settings['license.defaultTier'] = Light¦Pro¦ProPlus¦Enterprise via the SAME resolution the demo seed uses), and a /admin/testmode-status echo. A pure guard class REFUSES any active switch in Production unless PPIQ_TESTMODE__IExplicitlyAcceptRisk=true, logging loudly. Provide a docker-compose.testmode.yml overlay and docs/TESTMODE.md. NOTE the canonical tier member is 'Light' not 'Lite' — normalize 'Lite'->'Light' so legacy env values keep working. | With SeedUsers=true the reviewer logs in as each of the 4 roles and confirms a different page/edit scope. With ForceTier=Light the gated features disappear and with ForceTier=Enterprise they return — WITH NO reseed and NO code edit, just an app-api restart. A unit test proves the guard throws in Production with an active switch and no accept-risk flag, and allows it in Development. /admin/testmode-status returns the active toggles. | new feature | 12
T-04 | CI cannot be skipped — truth-gate test + skip register | Phase 1 · Deploy stability & safe test profiles | Testing | Testing | Architecture tests | Very Important | Add CiPipelineTruthGateTests to PlantProcess.Architecture.Tests: it statically parses the Jenkinsfile and FAILS if `dotnet test`/`npm run test`/`npm run e2e` is missing, wrapped in catchError(SUCCESS), invoked with --list, or ordered AFTER migrate/seed/deploy. Because it runs inside `dotnet test`, the pipeline polices its own definition. Add Backend/tests/TESTS.md documenting every registered SkippableFact skip (audit-immutability tests etc.) with justification. | The test is GREEN against the new Jenkinsfile and goes RED if any gate line is removed (prove by temporarily deleting `dotnet test` and asserting failure, then restoring). TESTS.md lists each skip with its env-condition and reason; a reviewer can confirm no skip hides a regression. | test | 8
Phase 2 · Security & per-endpoint authorization
T-05 | Gate the proof/certification endpoint surface out of Production | Phase 2 · Security & per-endpoint authorization | Hardening | Security | Endpoint authorization | Critical | Program.cs registers ~7 internal diagnostic endpoint groups UNGATED: MapAdminProofEndpoints, MapP03P04CompletionProofEndpoints, MapPhase2LifecycleProofEndpoints, MapV5LicenseResolverProofEndpoints, MapV5IdentityRuntimeCertificationEndpoints, MapV5ConnectorRuntimeCertificationEndpoints, MapV5PrivateModelGatewayCertificationEndpoints. Move ALL of them into ONE block gated by `if (app.Environment.IsDevelopment() ¦¦ Configuration['PPIQ_DIAGNOSTIC_ENDPOINTS']=='true')`. WHITELIST MapP15HonestyCertificationEndpoints (it is a customer-facing trust surface — keep it in Production). Write an architecture guard test that fails if any Proof/Certification registration sits outside the gate (except the whitelist). | In a Production build (ASPNETCORE_ENVIRONMENT=Production, no diagnostic flag) every gated route returns 404 — assert via integration test enumerating EndpointDataSource. The honesty-certification route still returns 200. The guard test goes RED if a proof endpoint is moved back outside the gate. Swagger in Production shows no proof/certification machinery. | hardening | 12
T-06 | Per-endpoint authorization matrix proof (RBAC + tenant) | Phase 2 · Security & per-endpoint authorization | Hardening | Security | RBAC/Tenant | Critical | Prove every endpoint/page/job/tool checks role + entitlement and is tenant-safe. Enumerate all endpoints from EndpointDataSource; assert each non-anonymous route carries an authorization requirement; build a matrix test that, for each role (Admin/Executive/Engineer/Operator/Viewer), asserts allowed routes return 2xx and forbidden routes return 403. Add a cross-tenant test: a user from tenant A requesting tenant B's data gets 403/empty. Fix any unguarded admin surface found. | An integration test enumerates EVERY route and fails if any non-anonymous endpoint lacks an auth requirement. The role matrix test is green by identity. A cross-tenant request returns 403 or an empty set (never another tenant's rows) — proven by a dedicated test that seeds two tenants. | hardening | 14
T-07 | Audit log immutability + sensitive-action coverage | Phase 2 · Security & per-endpoint authorization | Hardening | Security | Audit | Very Important | Ensure every sensitive action (login, role change, license change, mapping publish, connector credential change, data export) writes an append-only audit event. Enable the audit-immutability tests by provisioning PPIQ_AUDIT_TRIGGER_TEST_CONNECTION in CI so the currently-skipped SkippableFacts actually run. Verify the DB trigger blocks UPDATE/DELETE on audit rows. Add coverage for export and connector-credential-change events. | The audit-immutability tests run (not skipped) in CI and pass: an attempt to UPDATE or DELETE an audit row raises the DB-level block. A test performs each sensitive action and asserts a corresponding immutable audit row exists with actor, timestamp, and target. | hardening | 12
T-08 | Connector credential masking + secrets-at-rest audit | Phase 2 · Security & per-endpoint authorization | Hardening | Security | Secrets | Important | Confirm and lock down: source credentials are stored encrypted, masked on read-back in every connector admin response, and never serialized to the browser or logs. Add a test that creates a connector with a secret, reads it back via the API, and asserts the secret is masked. Grep-guard test that fails if a credential field is returned unmasked from any connector DTO. | A test creates a DB-link with a password, GETs it back, and asserts the password field is masked (e.g. '****'). A second test asserts no connector response DTO contains a plaintext secret. Logs from a sync contain no credential. | hardening | 8
Phase 3 · No silent failure, provider truth & standardization
T-09 | No silent failure — migrate raw error strings to retryable boundaries | Phase 3 · No silent failure, provider truth & standardization | Hardening | FrontEnd | Error boundaries | Critical | 23 raw 'could not load'/'failed to load' strings remain in the frontend. Replace each with the standard DataFetchBoundary error state (branded, retryable). Wrap every data-fetching page/widget that currently lacks a boundary. Ensure one failing widget cannot blank a page. Eliminate all unhandled promise rejections on the demo path. Use the existing ErrorBoundary.tsx + DataFetchBoundary primitives — do not invent new ones. | An e2e spec forces ONE widget's data endpoint to 500 and asserts: a contained branded error with a working Retry renders in that widget, the rest of the page stays interactive, and the console shows ZERO unhandled rejections; clicking Retry recovers without a full reload. A grep test asserts no raw 'could not load' string remains outside the boundary component. | bug fix | 12
T-10 | Provider availability single-source + duplicate-route gate | Phase 3 · No silent failure, provider truth & standardization | Hardening | Backend | Connectors/Routing | Very Important | IsAvailableNow is decided by literals in multiple provider arrays (truth dashboard, configuration service, catalog). Create ONE ProviderAvailability.IsAvailableNow(providerType): Csv/Excel->true, all others->ConnectorCertification.IsCertified (env-gated). Replace every literal with a call to it. Add an architecture test forbidding IsAvailableNow literals outside ProviderAvailability. Separately add a duplicate-route contract test that enumerates EndpointDataSource and fails if any route pattern+method is registered twice (silent shadowing). | The literal-forbidding test passes (lists any offender on failure). Flipping PPIQ_CONNECTOR_CERTIFIED_<PROVIDER> changes availability in ALL three surfaces together (proven by a test). The duplicate-route test is green and would fail if two endpoints shared a pattern+method. | refactor | 10
T-11 | Standardize every button/table/tab across all pages | Phase 3 · No silent failure, provider truth & standardization | Hardening | FrontEnd | Design system | Very Important | Enforce the StandardButton/StandardTable/StandardTabs primitives EVERYWHERE. Sweep every page (especially Material Investigation: search code, search, load investigation, calculate risk, PDF report buttons) and replace any bespoke button/table/tab with the standard component. Pin with snapshot tests so a regression to bespoke markup fails CI. Confirm icon-only buttons carry a full aria-label. | A vitest/architecture test scans page components and fails if a raw <button>/<table> is used where a Standard* primitive exists. Visual snapshots for every variant/size/state are committed and green. Manual: every button on Material Investigation matches the standard and performs its action. | refactor | 14
T-12 | No dead button — full action-matrix enumeration | Phase 3 · No silent failure, provider truth & standardization | Hardening | Testing | E2E action coverage | Critical | Enumerate every actionable control on every page and sub-page (buttons, calculate, load, min/max, filter, sort, export, navigation) into an action matrix, and write e2e coverage that clicks each and asserts it performs its function (a state change, a request, a navigation) — never a no-op. This is the literal 'no dead button on the demo path' gate. | An e2e action-matrix spec covers every page on the demo path; each control asserts an observable effect. The suite fails if any covered control no-ops. A coverage report lists every page and its action count. Zero dead buttons on the demo path. | test | 16
Phase 4 · Demo dataset & build-through-HMI
T-13 | Complete the 8-source demo dataset at realistic scale | Phase 4 · Demo dataset & build-through-HMI | Demo | Database | Demo sources | Critical | Finish the deterministic demo generator (Backend/tools/generate_demo_dataset.py, seeded) so it produces the full 1-month flat-steel dataset: ~630 heats, ~5,600 coils, QA on every 3rd coil (up to 2/coil for difficult grades), across all 8 sources — melt-shop PostgreSQL (EAF/LF: equipment+counters, heats summary/sample/result/component, additives, steps, oxygen/argon/electricity params), caster Oracle (Heat/Slab/Sequence/Sample tables with HeatID/Ladle/Tundish/Mould/Sequence/Slab/Strand linkage), HSM Oracle (rolling params, slab->coil), PKL MSSQL, Yard Excel, downtime MySQL (equipment-stop vs production-impact, the 5 reason classes), Parsytec MySQL (surface defects at HSM exit), QA Excel. Include deliberate imperfection so it looks real. Tag all seeded rows origin='seed'. | Running the generator yields the exact counts (assert 630 heats, ~5,600 coils within tolerance, QA cadence). The genealogy chain is internally consistent (every coil traces to a slab to a heat). A test asserts every seeded row carries origin='seed'. The downtime data contains both an absorbed equipment stop (no production impact) and a short stop causing long production impact (the water-pump case). | new feature | 18
T-14 | Build the entire demo from empty through the HMI (no hardcoding) | Phase 4 · Demo dataset & build-through-HMI | Demo | FrontEnd | Workflow proof | Critical | Prove Principle 1: starting from an empty app, perform EVERY step through the HMI only — create the 8 DB links, select tables, set cadence, author the mapping views/joins (including the cross-source key reconciliation), define KPIs as SQL views, create pages, drag-drop widgets, bind them to data, add a script-layer transform, configure and run the jobs. NO hardcoded page or widget. Record the run. Fix every bug encountered (this is where real-user bugs surface). | A recorded clean dry-run exists showing the full demo built from empty via HMI only. A one-click readiness check passes. No hardcoded page/widget is used (grep/architecture check). Every step that a customer would perform works without a source-code edit. | hardening | 20
T-15 | Genealogy golden thread — both directions on customer keys | Phase 4 · Demo dataset & build-through-HMI | Workflow | Backend | Genealogy | Very Important | Make the single most convincing demo moment work end-to-end: from a surface defect on a finished coil, walk back to the melt chemistry, AND forward from a heat to its coils/defects — on the CUSTOMER's own key names, reconciling C-0044170 (HSM Oracle) ≡ 44170 (Parsytec MySQL) via the business-key dictionary. Ensure the recursive area/equipment model and the genealogy edge table with cycle/orphan detection back it. | A test/e2e walks coil C-0044170 to its heat chemistry AND a heat forward to its coils+defects, using the customer key names, across all relevant sources. A bad/missing key produces a typed error, not a silent gap. Cycle and orphan detection are tested. | new feature | 16
Phase 5 · Intelligence correctness (values/analysis/suggestions)
T-16 | Correlation engine golden-set validation (recover true, reject spurious) | Phase 5 · Intelligence correctness (values/analysis/suggestions) | AI+ML | AI+ML | Correlation/L4 stats | Critical | The L4 methods exist (Spearman, mutual information, Lasso, VIF, bootstrap) under FDR. Build a golden synthetic dataset with KNOWN true signals and KNOWN spurious correlations; assert the engine recovers the true signals and REJECTS the spurious ones under Benjamini-Hochberg FDR + stratification by visible confounders. Every finding must state its population. This is the guard that the analysis is correct, not just present. | On the golden set the engine reports the planted true drivers and does NOT report the planted spurious ones (assert precisely). Every reported finding includes its population/exclusions. Removing FDR control makes the test fail (proving FDR is actually applied). | test | 18
T-17 | Value engine correctness + abstain path | Phase 5 · Intelligence correctness (values/analysis/suggestions) | AI+ML | AI+ML | Value engine | Very Important | The value engine reproduces the doctrine fixture (200 t/month x EUR 140/210/280 = EUR 28k/42k/56k bounded range, 'not a guaranteed saving'). Harden it: every input is drill-throughable to its source finding/job/dataset; downtime uses production-impact minutes (not raw equipment-stopped minutes) where appropriate; when inputs are insufficient the engine ABSTAINS rather than inventing a number. Add the per-tenant cost table. | A test reproduces the EUR 28k/42k/56k bounded range on demo data and asserts each input resolves to an evidence handle. A second test feeds insufficient inputs and asserts the engine returns Abstained=true with no fabricated number. A downtime-costing test asserts production-impact minutes are used for the water-pump case. | hardening | 14
T-18 | Assistant no-fabrication guard — zero uncited numbers | Phase 5 · Intelligence correctness (values/analysis/suggestions) | AI+ML | AI+ML | Grounding | Critical | The grounding contract must reject, before display, any assistant sentence containing a number without a resolvable evidence handle, and any causal phrasing ('caused by', 'root cause'). Harden and test it: feed the assistant prompts designed to elicit an uncited number or a causal claim and assert they are blocked or rewritten to 'suspected contributor' with a citation. On a transition coil the assistant must answer with weighted shared attribution, never a single fabricated heat. | An adversarial test suite feeds 10+ prompts trying to make the assistant emit an uncited number or a causal claim; ALL are blocked or safely rewritten. A transition-coil question returns weighted attribution (e.g. H-3361 ~70% / H-3362 ~30%). No assistant response on the demo path contains a number without a handle. | hardening | 14
Phase 6 · WOW UX, interactivity & performance
T-19 | Widget interactivity — filters, sorting, heatmap, drag/min/max | Phase 6 · WOW UX, interactivity & performance | Hardening | FrontEnd | Widgets/Charts | Very Important | Make every widget/chart dynamic and interactive: filters and sorting actually re-query/re-render; the heatmap renders and interacts correctly (hover, select, drill); drag/move/min/max behave on the page builder. Restore/confirm virtualization for large tables (threshold ~1000). Fix any widget that is visually present but functionally disconnected. | An e2e spec applies a filter and a sort to each chart type and asserts the data changes; interacts with the heatmap and asserts a drill/selection effect; drags and min/max a widget and asserts the layout persists. A large table (>1000 rows) renders virtualized with a summary, not every row. | hardening | 16
T-20 | Performance budgets + progress states (no hang/lag) | Phase 6 · WOW UX, interactivity & performance | Hardening | FrontEnd | Performance | Important | Enforce performance budgets at demo scale: no hang/lag; any load >~400ms shows a loading state with progress; large datasets stream/paginate. Profile the heaviest dashboard and the correlation result page; fix the slowest queries (add indexes where the analysis flags missing ones). Ensure long jobs show progress in the Jobs Monitor. | A perf test asserts the heaviest dashboard interactive-loads within the budget at demo scale; any longer load shows a progress indicator (asserted in e2e). No UI freeze during a correlation run. The Jobs Monitor shows live progress for a long job. | hardening | 12
T-21 | Cross-browser + responsive + visual-regression pass | Phase 6 · WOW UX, interactivity & performance | Hardening | Testing | Visual/Responsive | Important | Confirm the app and website render correctly at multiple screen sizes, on the major browsers, over http and https, and re-flow properly. Add/repair the visual-regression spec (visual.spec.ts) and run it on at least two browser engines and two viewport sizes. Fix any layout break. | visual.spec.ts passes on two engines (Chromium + one other) at desktop and tablet widths with no unexpected diffs. A manual matrix confirms the login, dashboard, and one investigation page render correctly on the major browsers with no overflow/clipping. | test | 12
T-22 | WOW polish pass — first-impression surfaces | Phase 6 · WOW UX, interactivity & performance | Web | FrontEnd | UI/UX polish | Important | Make the first 3 surfaces a customer sees unforgettable: the login, the executive dashboard, and the genealogy/investigation page. Apply the Dark Industrial system precisely (full-bleed #050B18, panel #0B1730, cyan glow accents, status colors), add tasteful motion (loading shimmer, chart enter animations), perfect spacing/alignment, and a confident empty/readiness state. No off-palette colors. This is the WOW/WaW effect. | A design review against the brand token reference passes for the 3 surfaces (exact hex, Inter+JetBrains Mono, heading scale). The readiness/empty states look intentional, not broken. A first-time viewer reaches 'request a demo' impression — validated by the brand-identity e2e (dimension7-brand-identity.spec.ts) passing. | modification | 14
Phase 7 · Feature honesty, license scoping & website
T-23 | Hide or honestly-state every not-ready feature | Phase 7 · Feature honesty, license scoping & website | Hardening | FrontEnd | Feature flags | Critical | Inventory every feature/page/widget that is not demo-ready (incomplete, unstable, or unbuilt — e.g. unfinished connectors, the historian GA path, any half-built analysis). For each: either hide it behind a flag, or show an honest 'coming soon / collecting data / not certified for this source' state. A customer must NEVER click into a broken or empty feature. Pair with the connector Truth Contract (a not-certified connector says so). Include disabling/guarding any unstable connector path, any half-built analysis page, and any experimental widget so the demo surface is 100% trustworthy. | A walkthrough of every nav item and feature finds NO broken/empty/dead destination — each is either fully working or honestly labelled. A test asserts not-certified connectors render the honest state, not a 'ready' claim. The forbidden-claim honesty-lint passes (no 'live Oracle ready today'). | hardening | 16
T-24 | License tier toggle — features appear/disappear live | Phase 7 · Feature honesty, license scoping & website | AI+ML | Backend | Licensing | Very Important | Wire RequireLicenseFeature onto the headline gated surfaces so toggling tier visibly changes available features (Enterprise->Pro removes some; Light shows the locked overlay). Entitlements come ONLY from the signed token / runtime tier resolution, never an editable row. The FE shows a LockedFeatureOverlay for a gated feature, not a raw 403. Use the T-03 ForceTier to demonstrate. | With ForceTier=Light, the reviewer hits a gated surface and sees a LockedFeatureOverlay (not a raw error); with ForceTier=Enterprise the same surface works — no reseed, just a restart. An integration test enumerates the gated routes and asserts the license filter + feature are wired. A guard test pins the wiring so a removed paywall fails CI. | new feature | 14
Phase 8 · Role scoping, brand & go-live rehearsal
T-25 | Role-scoped views — executive vs engineer vs operator vs admin | Phase 8 · Role scoping, brand & go-live rehearsal | Workflow | FrontEnd | RBAC UX | Important | Ensure each role sees a meaningfully different scope: executive = KPIs/ROI/value trends; process engineer = investigation/correlation/dashboards; operator = read dashboards + acknowledge; admin = configuration. Hide nav items and edit affordances outside a role's scope. Back it with the FE LicenseContext/role context so the menu reflects the logged-in role. | Logging in as each of the 4 seeded roles (T-03) shows a different, correct nav and a different edit capability — asserted by an e2e per role. An engineer cannot see admin configuration pages; an operator cannot edit a dashboard. No role sees a control it may not use. | modification | 16
Phase 7 · Feature honesty, license scoping & website
T-26 | Website honesty-lint + 5-product completeness + CTA | Phase 7 · Feature honesty, license scoping & website | Web | Web | Website | Very Important | Finish the website as the first salesperson. Confirm all 5 products (PlantProcess IQ, MES, QES, Yard & Warehouse, Energy Management) each have description, benefit, visuals, licensing, and a Golden-Rule CTA. Run an automated honesty-lint that fails the build on any forbidden claim ('guaranteed root cause','AI-powered prediction','production-ready AI','live Oracle/MSSQL ready today','we replace MES/L2/SCADA/BI'). Wire a working inquiry/lead-capture CTA. Confirm exact brand tokens. | The honesty-lint passes with zero forbidden phrases (and fails if one is injected). All 5 product pages render with their required sections. The CTA captures a lead (asserted by an e2e that submits the form and confirms capture). A brand audit matches the token reference exactly. | new feature | 16
Phase 8 · Role scoping, brand & go-live rehearsal
T-27 | Logo variant set + report/PDF light-mode brand | Phase 8 · Role scoping, brand & go-live rehearsal | Web | Web | Brand assets | Normal | Produce the full logo variant set (full horizontal, icon/favicon, stacked) in color/dark/light/mono, industry-neutral connected-node mark. Switch all PDF/report deliverables to the light-mode surface (#F4F6F8) with the brand header/footer maintained. Replace any steel-only or boxed logo usage. | All logo variants exist and are used in the correct contexts (favicon present, mono on light surfaces). A generated PDF report renders in light mode with the brand header/footer. No prohibited logo treatment (rotated/recolored/stretched/boxed) remains. | new feature | 12
T-28 | Go-live rehearsal — full demo dry run + regression freeze | Phase 8 · Role scoping, brand & go-live rehearsal | Demo | Testing | Go-live | Critical | Run the complete customer demo end-to-end on the server build exactly as it will be presented: build-through-HMI, the golden thread, a correlation run, the value euro range, the license toggle, role views, and the surprise-question playbook (general/license/user-role/AI-ML). Capture and fix every defect. Freeze: full backend suite + vitest + e2e all green; tag the release. | A recorded full dry-run on the SERVER build completes with zero errors/crashes/dead buttons and answers every surprise question honestly on the live build. `dotnet test Backend`, `npm run test`, and `npm run e2e` are all green at the tagged release commit. A rollback to the previous tag is verified. | test | 18

## Phase Summary
Phase | Tasks | Effort (h) | In 45–65h band? | Deployable milestone
Phase 1 · Deploy stability & safe test profiles | 4 | 50 | YES | Every git push deploys the one canonical stack, health-gated; reviewer can log in as any role/tier with no code edit.
Phase 2 · Security & per-endpoint authorization | 4 | 46 | YES | Procurement-safe: no diagnostic endpoints in prod, every route authz-checked, cross-tenant proven 403, audit immutable.
Phase 3 · No silent failure, provider truth & standardization | 4 | 52 | YES | No 'could not load' anywhere; one failing widget never blanks a page; every button/table standardized.
Phase 4 · Demo dataset & build-through-HMI | 3 | 54 | YES | The full 8-source demo builds from empty through the HMI; the golden thread walks both directions on customer keys.
Phase 5 · Intelligence correctness (values/analysis/suggestions) | 3 | 46 | YES | Correlation recovers true/rejects spurious under FDR; value euro range reproduces & abstains; assistant emits zero uncited numbers.
Phase 6 · WOW UX, interactivity & performance | 4 | 54 | YES | Filters/sort/heatmap/drag all live; no hang at demo scale; cross-browser clean; the 3 first-impression surfaces WOW.
Phase 7 · Feature honesty, license scoping & website | 3 | 46 | YES | No broken/empty feature reachable; tier toggle changes features live; the website sells with a working CTA and clean honesty-lint.
Phase 8 · Role scoping, brand & go-live rehearsal | 3 | 46 | YES | Each role sees its correct scope; full logo+PDF brand set; full server dry-run green; release tagged with verified rollback.
TOTAL | 28 | 394 |  | 8 phases · priority-ordered · each ends deployable