## Read Me
PlantProcess IQ - Product Backlog v11
v11 hard-enforces the GENERIC-ONLY RED LINE in V2/V3
THE RED LINE (permanent doctrine)
The product is 100% generic + industry-agnostic - installable/sellable to ANY industry (steel, pharma, food, mineral water, paper) with ZERO code change, only mappings. NEVER hardcoded/prepared/tailored to a dataset.
HOW v11 ENFORCES IT
- V1 J5 flagged TEMPORARY / V1-ONLY (hardcoded demo-shape Stage-2 accepted only to hit 1 Jul).
- V2 'ERADICATE hardcoded Stage-2' = Critical: zero dataset-specific branches may remain; generic projector consumes no-code mappings; the 8 demo sources become SEED MAPPINGS, not code.
- V2 NEW Critical 'Generic-Only CI gate': build FAILS if any demo schema/table/column/type literal appears in the core/canonical path. Allowlisted only in seed/demo-mapping fixtures.
- V3 multi-industry datasets reframed as PROOF: same image ingests a 2nd + 3rd industry; git diff shows only config/mappings; CI gate stays green.
After V2's eradication + gate, future dataset-specific hardcoding turns the build RED - the red line becomes self-policing, like the existing CI truth-gate.
Unchanged: V1 = the 7-step journey walk. Aims (Roadmap v5): V1 procurement 1 Jul, V2 engineers/CEOs 14 Jul, V3/V4 production-real.

## Backlog
PlantProcess IQ - Product Backlog v11 . GENERIC-ONLY red line enforced in V2/V3
Task ID | Version | Phase | Task Name | Persona(s) | Sub-criterion lifted | Gate | Track | Module | Severity | Status | % done | Description | Validation / Acceptance | Task Type | Effort (h) | Remaining (h) | Prereq | Old ID (v10)
V1-01 | V1 | V1-P1 Stable environment (nothing breaks) | Local dev reproducibility: EF-first + PGCLIENTENCODING + design-time factory (MERGED) | A1,A4 | A1-2, A1-10 | G9 | Environment | Infra | Critical | MOSTLY-DONE | 80% |  |  | refactor | 6 | 1.2 | - | V1-01
V1-02 | V1 | V1-P1 Stable environment (nothing breaks) | Delete env/profiles/local.env (leaks plantprocess123) + rotate | A1,A2 | A2-5 | G12 | Environment | Security | Critical | NEW | 10% |  |  | hardening | 3 | 2.7 | - | V1-02
V1-03 | V1 | V1-P1 Stable environment (nothing breaks) | Commit LOCAL test config — fix the clean-machine failures (server suite already green) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 40% |  |  | hardening | 5 | 3 | V1-01 | V1-03
V1-04 | V1 | V1-P1 Stable environment (nothing breaks) | Persistent infra Caddyfile + correct route targets [NEW 26-Jun] | A2,A4 | A4-9 | G9 | Infra | Infra | Very important | NEW | 0% |  |  | hardening | 6 | 6 | - | V2-13
V1-05 | V1 | V1-P1 Stable environment (nothing breaks) | Harden .env<->Postgres-volume password coupling + provisioning resilience [NEW 26-Jun] | A4 | A4-9 | G9 | Infra | Infra | Important | NEW | 0% |  |  | hardening | 5 | 5 | - | V2-14
V1-06 | V1 | V1-P1 Stable environment (nothing breaks) | Spamhaus / outbound-mail relay remediation (relay + SPF/DKIM/PTR + block 25) | A4, A6 | A6.10 CTA/lead capture | G9 | hardening | Infra | Very important | NEW | 0% |  |  | hardening | 5 | 5 |  | (new)
V1-07 | V1 | V1-P1 Stable environment (nothing breaks) | Phase gate: clean checkout boots seeded + green twice + SERVER deploy green | A1,A4 | A1-2, A1-9 | G9 | Environment | Deploy | Critical | NEW | 30% |  |  | verification | 4 | 2.8 | V1-01, V1-03, V1-04 | V1-07
V1-08 | V1 | V1-P1 Stable environment (nothing breaks) | Wire website CTA to a real inbox (CODE DONE — commit + SMTP + relay) | A6 | A6-10 | G8 | Web | Web | Very important | MOSTLY-DONE | 65% |  |  | feature | 4 | 1.4 | - | V1-18
V1-09 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Rebuild mapping/genealogy/safe-SQL foundation (demo-minimum, model-first) [P0 — biggest real gap] | A3,A4 | A3-5, A4-2, A4-6 | G2 | Workflow | Database | Critical | NEW | 80% |  |  | feature | 4 | 0.8 | V1-01 | V1-04
V1-10 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Verify genealogy both directions on C-0044170 live | A3 | A3-5 | G2 | Workflow | FrontEnd | Critical | PARTIAL | 85% |  |  | verification | 2 | 0.3 | V1-04 | V1-05
V1-11 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Verify transition-coil weighted attribution (70/30) live | A3 | A3-8 | G15 | Workflow | FrontEnd | Very important | PARTIAL | 80% |  |  | verification | 2 | 0.4 | V1-04 | V1-06
V1-12 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | App boots under Playwright (no early webServer exit) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 55% |  |  | hardening | 5 | 2.2 | V1-01 | V1-08
V1-13 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | One-click readiness check passes live | A4 | A4-7 | G7 | Workflow | Backend | Critical | PARTIAL | 50% |  |  | feature | 5 | 2.5 | V1-04 | V1-09
V1-14 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Verify every demo-path button live (click-through) + commit the action-matrix | A3 | A3-1, A3-3 | G6 | Workflow | FrontEnd | Critical | MOSTLY-DONE | 75% |  |  | verification | 3 | 0.8 | V1-04 | V1-10
V1-15 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Demo-path robustness fault gate - no crash from user/license/docker/DB | A3, A4 | A3.2 e2e no crash · A4.9 operational resilience | G6 | demo | Testing | Critical | NEW | 0% |  |  | test | 6 | 6 |  | (new)
V1-16 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Record the clean dry-run video (insurance) — Karim-owned | A3,A5 | A3-2 | G7 | Demo | Docs | Critical | NEW | 0% |  |  | content | 3 | 3 | V1-10 | V1-11
V1-17 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J1 - Auto-login lands on a working home (sysadmin, no login page) | A4, A3 | A2.4 token/session | G12 | workflow | FrontEnd | Important | PARTIAL | 70% |  |  | test | 2 | 0.6 |  | (new)
V1-18 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J2 - Connect + select the demo data source(s) via the DB Configuration tab | A4, A3 | A4.1 source onboarding HMI | G1 | workflow | FrontEnd | Critical | PARTIAL | 60% |  |  | test | 4 | 1.6 |  | (new)
V1-19 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J3 - Run Stage-1 import to staging + see it in Jobs Monitor + job log | A4, A3 | A4.4 Jobs Monitor | G1 | workflow | FrontEnd | Critical | PARTIAL | 50% |  |  | test | 4 | 2 |  | (new)
V1-20 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J4 - No-code Mapper UI loads the demo staging schema and previews/joins/filters | A4, A3 | A3.4 widget/mapping config | G2 | workflow | FrontEnd | Critical | PARTIAL | 50% |  |  | test | 6 | 3 |  | (new)
V1-21 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J5 - Run Stage-2 canonical refresh + monitor + log (TEMP demo shapes - V1 ONLY) | A4, A3 | A4.4 Jobs Monitor | G2 | workflow | FrontEnd | Critical | PARTIAL | 50% | GENERIC-ONLY RED LINE: the hardcoded demo-shape projection used here is a TEMPORARY V1-ONLY measure to hit 1 Jul and MUST be eradicated in V2 (see the V2 generic-projector task). |  | test | 4 | 2 |  | (new)
V1-22 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J6 - Build/open a dashboard + widget bound to the freshly-imported canonical data | A4, A3 | A3.1 zero dead buttons | G3 | workflow | FrontEnd | Critical | PARTIAL | 40% |  |  | test | 6 | 3.6 |  | (new)
V1-23 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J7 - Run a correlation / inspection + read grounded results on the imported data | A4, A3 | A3.7 correlation honest | G4 | workflow | FrontEnd | Critical | PARTIAL | 50% |  |  | test | 5 | 2.5 |  | (new)
V1-24 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J-WALK - End-to-end journey walk under induced faults (the no-dead-end gate) | A4, A3 | A3.2 e2e no crash | G6 | workflow | Testing | Critical | NEW | 0% |  |  | test | 6 | 6 |  | (new)
V1-25 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the 9-step demo script (DELIVERED — fill 2 placeholders) | A5 | C5 | G7 | Demo | Docs | Very important | MOSTLY-DONE | 80% |  |  | content | 2 | 0.4 | V1-11 | V1-12
V1-26 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the ROI model + slide (DELIVERED — fill real price) | A5 | A5-1, A5-7 | G5 | Web | Docs | Very important | MOSTLY-DONE | 80% |  |  | content | 4 | 0.8 | - | V1-13
V1-27 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the founder credibility pack (DELIVERED as 09-founder doc — fill background) | A5 | A5-10 | - | Web | Docs | Very important | MOSTLY-DONE | 80% |  |  | content | 2 | 0.4 | - | V1-14
V1-28 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Pitch deck (10-12 slides, on-brand) | A5,A6 | A6-1 | G8 | Web | Docs | Very important | NEW | 0% |  |  | content | 4 | 4 | - | V1-15
V1-29 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the pilot offer (DELIVERED as 08-pilot doc — fill price/customer) | A5 | A5-7 | - | Web | Docs | Very important | MOSTLY-DONE | 80% |  |  | content | 2 | 0.4 | - | V1-16
V1-30 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Cut the 2-3 minute demo video (blueprint delivered) | A6 | A6-10 | G8 | Web | Docs | Important | NEW | 0% |  |  | content | 3 | 3 | V1-11 | V1-17
V2-01 | V2 | V2-P3 Value engine & justified numbers | Wire + prove the Value Engine LIVE on demo data (engine already built) | A5, A3 | A5.1 quantified value · A5.7 price-to-value | G5 | AI+ML | Backend | Critical | PARTIAL | 70% |  |  | new feature | 10 | 3 |  | (new)
V2-02 | V2 | V2-P3 Value engine & justified numbers | Extend the grounding contract to ALL widgets (render-time uncited-number gate) | A5, A3 | A5.4 trustworthy AI · A3.6 population stated | G4 | AI+ML | Backend | Very important | PARTIAL | 55% |  |  | hardening | 8 | 3.6 |  | (new)
V2-03 | V2 | V2-P3 Value engine & justified numbers | Wire + expose L4 statistics LIVE (Spearman/MI/Lasso/VIF/bootstrap/FDR already built) | A3 | A3.7 correlation/ML honest | G4 | AI+ML | Backend | Very important | PARTIAL | 70% |  |  | test | 6 | 1.8 |  | (new)
V2-04 | V2 | V2-P3 Value engine & justified numbers | Sharpen AI/ML results: calibration, effect-size ranking, stratified quality | A3 | A3-7 | G4 | AI+ML | AI+ML | Very important | NEW | 0% |  |  | feature | 12 | 12 | V1-04 | V2-17
V2-05 | V2 | V2-P3 Value engine & justified numbers | Impressive evidence-ranked suggestion engine (deterministic, euro impact) | A3,A5 | A5-1 | G4 | AI+ML | AI+ML | Very important | PARTIAL | 55% |  |  | feature | 10 | 4.5 | V1-04 | V2-18
V2-06 | V2 | V2-P3 Value engine & justified numbers | Assistant eval harness + model-version governance gate | A2,A5 | A5-4 | G13 | AI+ML | Testing | Important | NEW | 0% |  |  | feature | 6 | 6 | - | V2-19
V2-07 | V2 | V2-P4 Completeness + performance/speed | Full backend+frontend suite green twice on clean machine (local) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 30% |  |  | hardening | 10 | 7 | V1-03 | V2-01
V2-08 | V2 | V2-P4 Completeness + performance/speed | Standardize all native buttons onto StandardButton | A1,A3 | A3-3 | G6 | FrontEnd | FrontEnd | Important | PARTIAL | 10% |  |  | refactor | 14 | 12.6 | V2-04 | V2-02
V2-09 | V2 | V2-P4 Completeness + performance/speed | E2E action-matrix enumerating every demo-path control (CI gate) | A1,A3 | A1-5, A3-1 | G6 | Testing | Testing | Very important | PARTIAL | 40% |  |  | feature | 8 | 4.8 | V1-10 | V2-03
V2-10 | V2 | V2-P4 Completeness + performance/speed | Visual-regression harness (baseline + diff gate) | A3,A6 | A3-3, A6-8 | G6 | Testing | Testing | Important | NEW | 0% |  |  | feature | 6 | 6 | - | V2-04
V2-11 | V2 | V2-P4 Completeness + performance/speed | Performance-at-scale validation (630/5,600, virtualized tables) | A3 | A3-9 | G6 | FrontEnd | Testing | Important | NEW | 0% |  |  | feature | 8 | 8 | - | V3-10
V2-12 | V2 | V2-P4 Completeness + performance/speed | Real lead-capture backend (form->DB row+email via relay, e2e asserts) | A6 | A6-10 | G8 | Web | Backend | Important | PARTIAL | 30% |  |  | feature | 6 | 4.2 | V1-18 | V2-22
V2-13 | V2 | V2-P5 Role/license/AI-boundary depth | MFA step-up for admin accounts | A2 | A2-4 | G12 | Security | Backend | Very important | NEW | 0% |  |  | feature | 8 | 8 | - | V2-07
V2-14 | V2 | V2-P5 Role/license/AI-boundary depth | Deepen license tiers: caps enforced + expiry/grace + admin governance | A5 | A5-3 | G12 | Security | Backend | Very important | PARTIAL | 20% |  |  | feature | 12 | 9.6 | - | V2-08
V2-15 | V2 | V2-P5 Role/license/AI-boundary depth | Real production Ed25519 license signing key (Option-1 -> Option-3) [NEW 26-Jun] | A2,A5 | A2-5, A5-3 | G12 | Security | Security | Very important | NEW | 0% |  |  | feature | 10 | 10 | - | V2-09
V2-16 | V2 | V2-P5 Role/license/AI-boundary depth | Full RBAC role-scope live across 6 roles | A5 | A5-2 | G5 | Security | Backend | Very important | PARTIAL | 55% |  |  | feature | 10 | 4.5 | - | V2-10
V2-17 | V2 | V2-P5 Role/license/AI-boundary depth | Wire DataBoundaryPolicy into assistant dispatch (no-egress live) | A2 | A2-8 | G13 | AI+ML | Backend | Very important | PARTIAL | 50% |  |  | feature | 7 | 3.5 | - | V2-20
V2-18 | V2 | V2-P6 Documentation (screenshots) + web | User guide: embed app screenshots into the delivered 02-capabilities narrative | A3 | A3-2 | - | Docs | Docs | Important | MOSTLY-DONE | 70% |  |  | content | 6 | 1.8 | V1-11 | V2-23
V2-19 | V2 | V2-P6 Documentation (screenshots) + web | Install runbook: embed screenshots into the delivered 03-architecture narrative | A4 | A4-9 | G9 | Docs | Docs | Important | MOSTLY-DONE | 70% |  |  | content | 8 | 2.4 | - | V2-24
V2-20 | V2 | V2-P6 Documentation (screenshots) + web | Admin/Operator guide: screenshots + two-admin model (05-onboarding delivered) | A4 | A4-1 | - | Docs | Docs | Important | MOSTLY-DONE | 70% |  |  | content | 10 | 3 | - | V2-25
V2-21 | V2 | V2-P6 Documentation (screenshots) + web | Security whitepaper (DELIVERED as 04-security doc — verify + publish) | A2 | A2-1 | G12 | Docs | Docs | Important | MOSTLY-DONE | 85% |  |  | content | 6 | 0.9 | - | V2-26
V2-22 | V2 | V2-P6 Documentation (screenshots) + web | API reference | A1 | A1-7 | - | Docs | Docs | Normal | NEW | 0% |  |  | content | 4 | 4 | - | V2-27
V2-23 | V2 | V2-P6 Documentation (screenshots) + web | Pricing & license-tiers PAGE (web) — content delivered in 07-editions doc | A5,A6 | A6-7 | G8 | Web | Web | Important | MOSTLY-DONE | 70% |  |  | content | 5 | 1.5 | - | V2-16
V2-24 | V2 | V2-P6 Documentation (screenshots) + web | Naming golden-rule pass: rename phase/task-named artifacts | A1 | A1-4 | - | Docs | Database | Important | NEW | 0% |  |  | refactor | 18 | 18 | - | V2-28
V2-25 | V2 | V2-P4 Completeness + performance/speed | System logging to rolling file (systemLog_<day>_<hr>.log, hourly) | A1, A4 | A4.9 operational resilience | G9 | hardening | Backend | Very important | PARTIAL | 30% |  |  | hardening | 6 | 4.2 |  | (new)
V2-26 | V2 | V2-P4 Completeness + performance/speed | Job + Data operational logging to rolling files (JobLog/DataLog_<day>_<hr>.log) | A4 | A4.4 Jobs Monitor | G9 | hardening | Backend | Very important | NEW | 0% |  |  | new feature | 8 | 8 |  | (new)
V2-27 | V2 | V2-P5 Role/license/AI-boundary depth | In-app Log tab on every page (filter by job type / name / severity / day) | A4, A3 | A4.4 Jobs Monitor | G6 | workflow | FrontEnd | Important | NEW | 0% |  |  | new feature | 10 | 10 |  | (new)
V2-28 | V2 | V2-P3 Value engine & justified numbers | ERADICATE hardcoded Stage-2; generic projector consumes no-code mappings (RED LINE) | A3, A1 | A1.6 generic/any-DB | G2 | workflow | Backend | Critical | NEW | 0% |  | ZERO hardcoded dataset-specific branches remain in ppiq_run_stage2_canonical_refresh (no src_*, no heat_no/coil_id/piece_id, no 'Heat'/'Slab'/'Coil', no 'FlatSteel', no 'Europe/Berlin'). A NEW non-demo source shape, mapped only in the no-code UI, projects into canonical with no code change. The 8 demo sources run as SEED MAPPINGS and the demo journey is byte-for-byte unchanged (C-0044170 + 0.70/0.30 regress green). The genericity CI gate (sibling task) passes. A mapping missing a required canonical field fails loudly with a typed error. | new feature | 20 | 20 |  | (new)
V2-29 | V2 | V2-P4 Completeness + performance/speed | Generic-Only CI gate - build FAILS on any dataset/industry-specific identifier in core | A1, A3 | A1.6 generic/any-DB | G10 | hardening | Testing | Critical | NEW | 0% | Make the Generic-Only red line ENFORCEABLE (same spirit as the CI truth-gate). Add an architecture test + CI lint that scans the core/canonical/projection/import path (Domain, Application, the SQL functions under database/scripts, the connectors' canonical mapping) and FAILS the build on any dataset/industry-specific literal: demo schema/table names (src_meltshop_pg, src_hsm_oracle_shape, ...), demo column names (heat_no, coil_id, piece_id, steel_grade, ...), industry type literals ('Heat','Slab','Coil','FlatSteel'), or hardcoded plant constants ('Europe/Berlin', fixed UTC offsets). Allow them ONLY inside seed-data / demo-mapping fixtures (explicit allowlist path). This keeps the product generic forever. | Re-introducing a hardcoded demo identifier into the canonical projection path turns the build RED (negative test). The gate runs in Jenkins and blocks merge. Seed/demo-mapping fixtures are allowlisted and pass. After V2's eradication task, the gate is GREEN on the real code. | hardening | 6 | 6
V3-01 | V3 | V3-P7 Deep security & ops hardening | Enforce RLS on core tables (decide tenant_id; non-superuser app role) | A2 | A2-6 | G12 | Security | Database | Very important | PARTIAL | 40% |  |  | feature | 10 | 6 | - | V2-11
V3-02 | V3 | V3-P7 Deep security & ops hardening | Encryption at rest: staging/canonical/credential-vault | A2 | A2-9 | G12 | Security | Infra | Important | NEW | 0% |  |  | hardening | 6 | 6 | - | V2-12
V3-03 | V3 | V3-P7 Deep security & ops hardening | Move Jenkins to a separate Docker network from the app project [NEW 26-Jun] | A2 | A2-10 | G12 | Infra | Infra | Normal | NEW | 0% |  |  | hardening | 4 | 4 | V2-13 | V2-15
V3-04 | V3 | V3-P7 Deep security & ops hardening | Wire SourceLoadProtectionPolicy into the live query path | A2 | A2-3 | G11 | Security | Backend | Very important | PARTIAL | 50% |  |  | feature | 7 | 3.5 | - | V2-21
V3-05 | V3 | V3-P7 Deep security & ops hardening | Nightly full-suite CI job (cron) | A1 | A1-5 | G9 | Testing | Deploy | Very important | PARTIAL | 30% |  |  | feature | 6 | 4.2 | V2-01 | V2-05
V3-06 | V3 | V3-P7 Deep security & ops hardening | Health dashboard (suite/e2e pass-rate, flaky count) | A1 | A1-5 | G9 | Testing | Web | Normal | NEW | 0% |  |  | feature | 5 | 5 | V2-05 | V2-06
V3-07 | V3 | V3-P7 Deep security & ops hardening | HasDefaultSchema -> ppiq_meta/ppiq_plant for EF entities | A1 | A1-3 | - | Database | Database | Normal | NEW | 0% |  |  | refactor | 4 | 4 | - | V2-29
V3-08 | V3 | V3-P8 Multi-industry & generic | Second-industry demo dataset (paper/board line) + mapping templates | A1,A3 | A3-11 | G3 | Demo | Database | Very important | NEW | 0% | PROOF of the Generic-Only red line: install the UNCHANGED product for a 2nd industry (pharmaceuticals or food & beverage) - only mappings/config differ, ZERO code change. | Same image, no code diff: ingests the new-industry dataset via no-code mappings and produces working dashboards + a correlation result; git diff shows only config/seed-mapping changes; the Generic-Only CI gate stays green. | feature | 14 | 14 | V1-04 | V3-01
V3-09 | V3 | V3-P8 Multi-industry & generic | Third-industry demo dataset (food & beverage) + tier configs | A1,A3 | A3-11 | G3 | Demo | Database | Very important | NEW | 0% | PROOF of the Generic-Only red line: install the UNCHANGED product for a 3rd industry (mineral water or paper manufacturing) - only mappings/config differ, ZERO code change. | Same image, no code diff: ingests the new-industry dataset via no-code mappings and produces working dashboards + a correlation result; git diff shows only config/seed-mapping changes; the Generic-Only CI gate stays green. | feature | 12 | 12 | V3-01 | V3-02
V3-10 | V3 | V3-P8 Multi-industry & generic | Generic canonical-mapping template library + no-code visual-mapper polish | A1,A4 | A4-2 | G2 | Workflow | FrontEnd | Very important | NEW | 0% |  |  | feature | 12 | 12 | V1-04 | V3-03
V3-11 | V3 | V3-P8 Multi-industry & generic | Demo dataset polish + per-industry scripted reset | A3 | A3-11 | G7 | Demo | Deploy | Important | PARTIAL | 60% |  |  | feature | 6 | 2.4 | V3-01 | V3-04
V3-12 | V3 | V3-P8 Multi-industry & generic | Historian connector to GA (behavioural-tested) | A1,A2 | A2-2 | G1 | Workflow | Backend | Very important | NEW | 0% |  |  | feature | 12 | 12 | - | V3-05
V3-13 | V3 | V3-P8 Multi-industry & generic | One-command customer-install package (per-industry overlay) | A4 | A4-9 | G9 | Infra | Deploy | Very important | NEW | 0% |  |  | feature | 8 | 8 | V2-13 | V3-06
V3-14 | V3 | V3-P9 Accessibility, i18n & scale | WCAG 2.1 AA light theme + contrast audit | A6 | A6-9 | G14 | FrontEnd | FrontEnd | Important | NEW | 0% |  |  | feature | 10 | 10 | - | V3-07
V3-15 | V3 | V3-P9 Accessibility, i18n & scale | Arabic RTL + locale/units/timezone switching per user | A6 | A6-9 | G14 | FrontEnd | FrontEnd | Important | NEW | 0% |  |  | feature | 8 | 8 | V3-09 | V3-08
V3-16 | V3 | V3-P9 Accessibility, i18n & scale | i18n as resource files (.resx/JSON) + fix mojibake | A1 | A1-1 | G14 | FrontEnd | Backend | Important | NEW | 0% |  |  | refactor | 8 | 8 | - | V3-09
V3-17 | V3 | V3-P9 Accessibility, i18n & scale | Soak job (24-72h synthetic load on demo path) | A4 | A4-9 | G9 | Testing | Testing | Important | NEW | 0% |  |  | feature | 8 | 8 | - | V3-11
V3-18 | V3 | V3-P9 Accessibility, i18n & scale | Real-domain TLS cutover (off sslip.io) [NEW 26-Jun] | A2,A6 | A6-6 | G9 | Infra | Deploy | Important | NEW | 0% |  |  | hardening | 6 | 6 | V2-13 | V3-12
V3-19 | V3 | V3-P9 Accessibility, i18n & scale | QES product page to depth | A6 | A6-7 | G8 | Web | Web | Optional | NEW | 0% |  |  | content | 7 | 7 | - | V3-13
V3-20 | V3 | V3-P9 Accessibility, i18n & scale | Energy Management product page to depth | A6 | A6-7 | G8 | Web | Web | Optional | NEW | 0% |  |  | content | 7 | 7 | - | V3-14
V3-21 | V3 | V3-P7 Deep security & ops hardening | Multi-tenancy: tenant column on material_units + tenant-parameterized canonical layer + RLS | A2, A1 | A2.6 tenant isolation | G12 | hardening | Database | Very important | NEW | 0% |  |  | hardening | 16 | 16 |  | (new)
V3-22 | V3 | V3-P7 Deep security & ops hardening | i18n-harden the honesty + grounding gates (structural, not English keywords) | A5, A2 | A5.4 trustworthy AI | G4 | hardening | Backend | Important | NEW | 0% |  |  | hardening | 8 | 8 |  | (new)
V3-23 | V3 | V3-P7 Deep security & ops hardening | Log retention, size caps & optional forwarding (ops policy) | A4, A2 | A4.9 operational resilience | G9 | hardening | Infra | Normal | NEW | 0% |  |  | hardening | 4 | 4 |  | (new)
V4-01 | V4 | V4-P10 Ops / HA + OT | Backup/restore drill (verified restore, recorded) | A4 | A4-9 | G9 | Infra | Deploy | Very important | NEW | 0% |  |  | feature | 8 | 8 | - | V4-01
V4-02 | V4 | V4-P10 Ops / HA + OT | Verify deploy rollback to :previous | A4 | A4-9 | G9 | Infra | Deploy | Important | NEW | 30% |  |  | verification | 5 | 3.5 | - | V4-02
V4-03 | V4 | V4-P10 Ops / HA + OT | Time-series store (hypertables, compression, retention) | A4 | A4-8 | G9 | Infra | Database | Very important | NEW | 0% |  |  | feature | 12 | 12 | - | V4-03
V4-04 | V4 | V4-P10 Ops / HA + OT | Deployable OT-safe edge agent (one-way push) | A2 | A2-2 | G11 | Infra | Backend | Very important | NEW | 0% |  |  | feature | 12 | 12 | - | V4-04
V4-05 | V4 | V4-P10 Ops / HA + OT | Human-approved advisory write-back (business workflow, never OT) | A5 | A5-9 | G5 | Backend | Backend | Very important | NEW | 0% |  |  | feature | 10 | 10 | - | V4-05
V4-06 | V4 | V4-P10 Ops / HA + OT | Enforce performance budgets in CI | A1 | A1-2 | G6 | Testing | Testing | Important | NEW | 0% |  |  | feature | 6 | 6 | - | V4-06
V4-07 | V4 | V4-P10 Ops / HA + OT | Load-test at reference-plant scale | A4 | A4-9 | G9 | Testing | Testing | Very important | NEW | 0% |  |  | feature | 8 | 8 | - | V4-07
V4-08 | V4 | V4-P11 Compliance + ops | Start SOC 2 Type II observation window | A2 | A2-9 | G16 | Docs | Security | Very important | NEW | 0% |  |  | content | 10 | 10 | - | V4-08
V4-09 | V4 | V4-P11 Compliance + ops | ISO 27001 mapping + sensitive-data catalog | A2 | A2-9 | G16 | Docs | Security | Important | NEW | 0% |  |  | content | 8 | 8 | - | V4-09
V4-10 | V4 | V4-P11 Compliance + ops | GxP / 21 CFR Part 11 pack (audit trail, e-signature) | A2 | A2-9 | G16 | Docs | Security | Optional | NEW | 0% |  |  | content | 12 | 12 | - | V4-10
V4-11 | V4 | V4-P11 Compliance + ops | Public status page | A4 | A4-9 | - | Web | Web | Normal | NEW | 0% |  |  | content | 4 | 4 | - | V4-11
V4-12 | V4 | V4-P11 Compliance + ops | AI triage loop (agent drafts fix PRs, human-approved) | A1 | A1-5 | - | AI+ML | Testing | Important | NEW | 0% |  |  | feature | 10 | 10 | - | V4-12
V4-13 | V4 | V4-P11 Compliance + ops | Recorded certified dry-run (one-click readiness on video) | A4 | A4-7 | G7 | Demo | Docs | Very important | NEW | 0% |  |  | content | 4 | 4 | V1-09 | V4-13
V4-14 | V4 | V4-P11 Compliance + ops | Consolidate full operator/admin/security docs | A4 | A4-9 | - | Docs | Docs | Important | NEW | 30% |  |  | content | 8 | 5.6 | V2-24 | V4-14
V4-15 | V4 | V4-P12 Business / reference | Incorporate (UG/GmbH) + imprint | A5 | - | - | Web | Docs | Very important | NEW | 0% |  |  | content | 8 | 8 | - | V4-15
V4-16 | V4 | V4-P12 Business / reference | Pilot contract + MNDA + DPA templates | A5 | - | - | Docs | Docs | Very important | NEW | 0% |  |  | content | 8 | 8 | - | V4-16
V4-17 | V4 | V4-P12 Business / reference | Target list + outreach sequence (PSI network) | A5 | - | - | Web | Docs | Very important | NEW | 0% |  |  | content | 10 | 10 | - | V4-17
V4-18 | V4 | V4-P12 Business / reference | Convert presentation customer into a signed paid pilot | A5 | - | - | Web | Docs | Critical | NEW | 0% |  |  | content | 12 | 12 | V1-16 | V4-18
V4-19 | V4 | V4-P12 Business / reference | Prove ROI on the customer's real data (pilot deliverable) | A5 | A5-1 | G5 | AI+ML | AI+ML | Critical | NEW | 0% |  |  | feature | 8 | 8 | V4-18 | V4-19
V4-20 | V4 | V4-P12 Business / reference | Run the paid pilot | A4,A5 | - | - | Workflow | Backend | Critical | NEW | 0% |  |  | feature | 20 | 20 | V4-18 | V4-20
V4-21 | V4 | V4-P12 Business / reference | Convert pilot to a signed contract | A5 | - | - | Web | Docs | Critical | NEW | 0% |  |  | content | 12 | 12 | V4-20 | V4-21
V4-22 | V4 | V4-P12 Business / reference | Produce the case study / reference | A5 | - | - | Web | Docs | Very important | NEW | 0% |  |  | content | 6 | 6 | V4-21 | V4-22
V4-23 | V4 | V4-P12 Business / reference | Viability arrangement (hire / escrow+BCP / partner) | A5 | - | - | Web | Docs | Very important | NEW | 0% |  |  | content | 12 | 12 | - | V4-23
V4-24 | V4 | V4-P12 Business / reference | Support SLA offering | A4 | - | - | Docs | Docs | Important | NEW | 0% |  |  | content | 5 | 5 | - | V4-24
V4-25 | V4 | V4-P12 Business / reference | Funding / partnership decision | A5 | - | - | Web | Docs | Normal | NEW | 0% |  |  | content | 4 | 4 | - | V4-25

## Version Summary
Version Summary v11
Version | Tasks | Scope (h) | Remaining (h)
V1 | 30 | 122 | 73.4
V2 | 29 | 258 | 188.9
V3 | 23 | 188 | 175.1
V4 | 25 | 222 | 218.1
TOTAL | 107 | 790 | 655.5