## Read Me
PlantProcess IQ — Product Backlog v6
Versioned release plan. Operationalizes PPIQ_Product_Roadmap_v4, the Identity & Topology v4 reference, the Aspects of Review v4 rubric, the 26-Jun deploy-pipeline session, AND the customer documentation suite (index + 01-09) confirmed delivered.
WHAT CHANGED FROM v5 (this revision)
1. CLEAN SEQUENTIAL NUMBERING. Task IDs now run V1-01, V1-02, V1-03 ... with no gaps. The named tasks from v5 (V2-PROD-KEY, V2-CADDY, V2-ENVLOCK, V2-JENKINS-NET, V3-TLS) are folded into the numeric sequence in their phase. The old ID is shown in the Reassessment sheet so nothing is lost.
2. DOCUMENTATION SUITE RECONCILED. The delivered customer docs (01-product-overview, 02-platform-capabilities, 03-architecture-and-deployment, 04-security-and-data-protection, 05-data-onboarding, 06-analytics-methodology, 07-editions-and-licensing, 08-pilot-offer, 09-founder-and-company) are mapped to their backlog tasks. Docs with no placeholders are REMOVED as done; docs gated only on your price/customer inputs are MOSTLY-DONE (artifact delivered, awaiting your input) and kept on the plan so the placeholder is not lost.
3. COLLATERAL band re-scored from the handover: V1-14 (demo script) and V1-15 (ROI model/slide) DELIVERED -> MOSTLY-DONE; V1-16 (founder pack = 09-founder doc) and the old V1-19 (pilot offer = 08-pilot doc) MOSTLY-DONE; the old V1-18 (one-page brief = 01-overview) and V1-21 (IQ page, DONE per handover) REMOVED; V1-22 (lead email CODE DONE) bumped.
4. Carried from v5: V1-03/V1-04 removed (compose convergence + conn key done on the server); the local-reproducibility merge; the server deploy/sysadmin/Enterprise-activation substrate recorded done; the five NEW infra/license tasks added (now numbered).
5. Carried UNCHANGED: the lost genealogy/safe-SQL foundation (still P0, the headline bottleneck), the live demo proofs, and the V2-V4 depth/enterprise plan.
THE FOUR VERSIONS
V1 · First Release — Presentation-Ready (<100 h). Server deploy substrate GREEN + the doc suite largely delivered; what remains is the genealogy foundation, the live demo proofs/recording, the deck, and the price-gated commercial docs.
V2 · Product Depth. License + user-role depth, the real production signing key, sharper AI/ML + suggestion engine, the full test harness, infra hardening (persistent Caddy, password preservation, Jenkins network). NOTE: the written docs (user/install/admin/security/API/pricing) are now largely covered by the delivered suite - the residual V2 doc tasks are screenshot-embedding + keeping them current.
V3 · Generic & Multi-Industry. Paper + food datasets, generic mapper, historian GA, real-domain TLS, accessibility (WCAG light + Arabic RTL), scale.
V4 · Enterprise & Reference. HA/restore, OT-safe edge agent, human-approved advisory write-back, SOC 2 / ISO / GxP, and the pilot -> proven-ROI -> signed-contract -> case-study arc.
HOW TO READ A ROW
Each task carries the Persona(s) and the exact Sub-criterion it lifts, the Doctrine v7 Gate it serves, a junior-dev-actionable Description, and a hard reproducible Acceptance check (never 'build passes'). Status/% done is assessed against the 26-Jun code + deploy reality + the delivered doc suite.
LOCAL vs SERVER (carried from Identity v4)
Both environments are first-class. LOCAL (laptop) is for daily dev/test/troubleshooting; SERVER (Hetzner VPS) is for releases/the demo. Server topology is TWO compose projects: app=ppiq-app, infra=plantprocessiq (never merged). Never delete /var/lib/ppiq-preserve/.env (Postgres password coupling).
NAMING LAW (permanent)
No task creates an artifact named with phase/task/version-phase codes. The naming-pass task renames the existing offenders (incl. 301/302-style SQL still carrying p01_p02). Task IDs here (V1-07 etc.) are backlog handles, never artifact names.
SCORE BANDS
Critical <55 · Needs work 55-69 · Solid 70-84 · Strong 85+ ¦ Status: REMOVED >=85% · MOSTLY-DONE 65-84% · PARTIAL <65% · NEW 0%
HONESTY NOTE (carried into every version)
A green deploy pipeline is INFRASTRUCTURE, not product value, and a delivered DOCUMENT is not a proven demo. The headline persona score (A3 Process/Quality Engineer) is gated on the value engine + live HMI signal (the genealogy foundation V1-07 and the live demo proofs), which are still the real bottleneck. The deploy win and the doc suite do not move the headline.

## Backlog
PlantProcess IQ — Product Backlog v6 · clean sequential numbering · re-scored vs 26-Jun deploy + delivered doc suite · V1<100h
Task ID | Version | Phase | Task Name | Persona(s) | Sub-criterion lifted | Gate | Track | Module | Severity | Status | % done | Description (junior-dev-actionable) | Validation / Acceptance (hard, reproducible) | Task Type | Effort (h) | Prereq | Old ID (v5)
V1-01 | V1 | V1-P1 Reproducible env | Local dev reproducibility: EF-first + PGCLIENTENCODING + design-time factory (MERGED) | A1,A4 | A1-2, A1-10 | G9 | Environment | Infra | Critical | MOSTLY-DONE | 80% | MERGES old V1-01+V1-02 and the LOCAL residue of V1-03. The SERVER path is already green (the pipeline runs EF in a sibling before the numbered SQL, handles encoding, and uses ConnectionStrings__PlantProcessDb). Remaining is LOCAL-only and small: (a) fold `dotnet ef database update` into the start of `ppiq.ps1 migrate`/`demo`; (b) export PGCLIENTENCODING=UTF8 before every psql in ppiq.ps1; (c) rewrite PlantProcessDesignTimeDbContextFactory to read ConnectionStrings__PlantProcessDb -> PLANTPROCESS_DESIGNTIME_CONNECTION_STRING -> PLANTPROCESS_DB with an honest error; (d) converge the LOCAL compose remnants (delete duplicate demo-sources fleet + Infrastructure/deploy/docker-compose.demo.yml). Commit so the two session env-vars are no longer needed locally. | From a clean LOCAL DB, `ppiq.ps1 demo` provisions one-shot (EF schema -> SQL decoration -> app on :5063) with ZERO hand-set env vars, twice. grep finds no duplicate demo compose. Evidence: clean-run terminal log + grep. | refactor | 6 | - | V1-01+V1-02 (merged)
V1-02 | V1 | V1-P1 Reproducible env | Delete env/profiles/local.env (leaks plantprocess123) + rotate | A1,A2 | A2-5 | G12 | Environment | Security | Critical | NEW | 10% | Remove env/profiles/local.env (it carries IsBootstrapAdmin=true and the literal plantprocess123) and rotate any key that ever touched it. Keep only deploy/compose/.env.dev (container-local creds) and the git-ignored server /var/lib/ppiq-preserve/.env. Also strip the stale 4-user set from appsettings.Development.json so it stops shadowing the canonical five locally. | grep finds zero `plantprocess123` and zero `IsBootstrapAdmin=true` in the repo; the startup guard still passes; a bare `dotnet run` shows the canonical five users. Evidence: grep output + boot log. | hardening | 3 | - | V1-05
V1-03 | V1 | V1-P1 Reproducible env | Commit LOCAL test config — fix the clean-machine failures (server suite already green) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 40% | The SERVER pipeline already runs the backend (~567) and frontend (202) suites green. The remaining gap is the LOCAL clean-machine path: author committed appsettings.Test.json (DSN + 64-char signing key + a real admin + PPIQ_FORCE_EXTERNAL_API_TEST_HOST) and wire Do-Test so WebApplicationFactory boots the host and finds the DB without per-run env vars. This was the documented cause of the local 83 reds. | `ppiq.ps1 test` exits 0 TWICE on a fresh LOCAL checkout (no hand-set vars). Evidence: two consecutive green run logs. | hardening | 5 | V1-01 | V1-06
V1-04 | V1 | V1-P1 Reproducible env | Rebuild mapping/genealogy/safe-SQL foundation (demo-minimum, model-first) [P0 — biggest real gap] | A3,A4 | A3-5, A4-2, A4-6 | G2 | Workflow | Database | Critical | NEW | 5% | NOT touched by the deploy session or the docs work - still the largest real gap. The foundation is lost (no clean git copy): ppiq_business_key_definitions, canonical_business_keys, canonical_mapping_versions, the canonical genealogy tables, ppiq_walk_genealogy and ppiq_resolve_safe_sql are gone; only genealogy_edges (EF) survives. Rebuild the DEMO-MINIMUM set model-first: entities + IEntityTypeConfiguration for the business-key/canonical-mapping tables; the recursive walk + cycle/orphan validators + the safe-SQL resolver in a thin SQL migration. Scope to what the demo thread needs; defer full mapping-lifecycle hardening to V2. Name everything descriptively (no p03_p04). | On the demo dataset, ppiq_walk_genealogy(C-0044170) returns the full coil->melt chain both directions; a bad mapping returns a typed error and rolls back; the un-quarantined 311/321 validators are green. Evidence: psql output + green migration. | feature | 18 | V1-01 | V1-07
V1-05 | V1 | V1-P1 Reproducible env | Verify genealogy both directions on C-0044170 live | A3 | A3-5 | G2 | Workflow | FrontEnd | Critical | PARTIAL | 20% | With the foundation rebuilt, walk C-0044170 coil->melt and melt->coils in the running HMI, confirming the Material Investigation evidence panel renders both directions on the customer's own keys. | Recorded walk: both directions resolve on the demo data, no stall. Evidence: clip in the dry-run. | verification | 4 | V1-04 | V1-08
V1-06 | V1 | V1-P1 Reproducible env | Verify transition-coil weighted attribution (70/30) live | A3 | A3-8 | G15 | Workflow | FrontEnd | Very important | PARTIAL | 30% | Confirm a casting-transition coil reports weighted (e.g. 70/30) attribution across two heats (H-3361/H-3362) with the population/exclusions shown, never a single fabricated heat. The backend test is already green; the live HMI clip is owed. | A transition coil renders weighted provenance + stated population live. Evidence: clip. | verification | 3 | V1-04 | V1-09
V1-07 | V1 | V1-P1 Reproducible env | Phase gate: clean checkout boots seeded + green twice + SERVER deploy green | A1,A4 | A1-2, A1-9 | G9 | Environment | Deploy | Critical | NEW | 30% | End-of-phase regression. LOCAL: clean clone -> `ppiq.ps1 reset && ppiq.ps1 demo` boots the seeded stack; `ppiq.ps1 test` green twice; genealogy walk resolves; capture the `seed exit=0` line. SERVER: confirm `git push` -> Jenkins `plantprocessiq-deploy` reaches PIPELINE GREEN (already true at build #96; the gate is to keep it green after the foundation/test work lands). Seals V1-P1 as deployable in both environments. | All LOCAL gates pass on a fresh machine, scripted, with seed exit=0; the SERVER pipeline is green on the same commit. Evidence: one combined run log + the green Jenkins build. | verification | 4 | V1-01, V1-03, V1-04 | V1-PT1
V1-08 | V1 | V1-P2 Live demo + collateral | App boots under Playwright (no early webServer exit) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 55% | Fix playwright config so webServer starts the API+web and waits for :5063/:5173 instead of exiting early; run at least one real spec against the booted app. | `ppiq.ps1 e2e` starts the app and runs >=1 spec to green. Evidence: Playwright HTML report. | hardening | 5 | V1-01 | V1-10
V1-09 | V1 | V1-P2 Live demo + collateral | One-click readiness check passes live | A4 | A4-7 | G7 | Workflow | Backend | Critical | PARTIAL | 50% | Make the readiness surface return green (sources healthy, counts match, jobs ready) in one call on the seeded stack. | Readiness endpoint returns all-green on the demo data, shown live. Evidence: screenshot + clip. | feature | 5 | V1-04 | V1-11
V1-10 | V1 | V1-P2 Live demo + collateral | Verify every demo-path button live (click-through) + commit the action-matrix | A3 | A3-1, A3-3 | G6 | Workflow | FrontEnd | Critical | MOSTLY-DONE | 75% | Per the handover the action-matrix is DONE 20/20 green (i18n-safe structural guard + truthful data-disabled-reason in phase9ActionMatrix.ts / phase9-action-matrix.spec.ts / MaterialAnalyticsPages.tsx / DemoAnalyticsPages / StandardTable) but the COMMIT is pending and the live click-through on the server demo URL is the remaining proof. Commit the five files; click every control on the 9-step path in the running HMI. (Full StandardButton migration is the V2 task.) | The action-matrix files are committed; every button on the 9-step script performs its action live; 0 unhandled rejections on the path. Evidence: recorded run + commit hash. | verification | 3 | V1-04 | V1-12
V1-11 | V1 | V1-P2 Live demo + collateral | Record the clean dry-run video (insurance) — Karim-owned | A3,A5 | A3-2 | G7 | Demo | Docs | Critical | NEW | 0% | Per the handover this CANNOT be AI-done. Record an MP4 of the full 9-step walk on the seeded stack against the live server demo URL (app.178.105.152.180.sslip.io) logged in as sysadmin - the pilot acceptance artifact and the backup if live ever fails. Blocks the demo-reel cut. | MP4 exists; no dead click; matches the script. Evidence: the file. | content | 3 | V1-10 | V1-13
V1-12 | V1 | V1-P2 Live demo + collateral | Finalize the 9-step demo script (DELIVERED — fill 2 placeholders) | A5 | C5 | G7 | Demo | Docs | Very important | MOSTLY-DONE | 80% | Per the handover the script PlantProcess-IQ-Live-Demo-Script.md is DELIVERED (connect->map->build page->...). Remaining: fill the 2 placeholders (roadmap specifics + your real per-plant price) and rehearse it cold once, including the surprise-question answers (incl. the new 'do you ship a customer-usable admin?' -> no; only the sysadmin support account, customer admin added at commissioning). | You run it cold once end-to-end with the placeholders filled. Evidence: the script doc + a rehearsal note. | content | 2 | V1-11 | V1-14
V1-13 | V1 | V1-P2 Live demo + collateral | Finalize the ROI model + slide (DELIVERED — fill real price) | A5 | A5-1, A5-7 | G5 | Web | Docs | Very important | MOSTLY-DONE | 80% | Per the handover PlantProcess-IQ-ROI-Model.xlsx + PlantProcess-IQ-ROI-Slide.pptx are DELIVERED (base case EUR 480,000/yr vs a EUR 300k placeholder price; labelled projected-not-proven). Remaining: replace the placeholder price with your real per-plant price and re-verify the figure still exceeds it. Also fits the 07-editions-and-licensing doc (which carries [[PER_PLANT_ACV_RANGE]]). | The model + slide carry a defensible EUR/yr number against your real price, assumptions stated, tied to the demo finding. Evidence: the files. | content | 4 | - | V1-15
V1-14 | V1 | V1-P2 Live demo + collateral | Finalize the founder credibility pack (DELIVERED as 09-founder doc — fill background) | A5 | A5-10 | - | Web | Docs | Very important | MOSTLY-DONE | 80% | The customer doc 09-founder-and-company.md is DELIVERED and on-brand. Remaining: fill [[YEARS]] and [[BACKGROUND_DETAIL]] (your 14 yrs PSI Metals / SMS / EzzSteel, named plants/processes), [[COMPANY_LOCATION]], [[CONTACT_NAME_AND_EMAIL]], [[WEBSITE_URL]]; optionally produce the one-slide version placed before the offer slide. | The doc (and optional slide) has your named plants + contact filled; on-brand. Evidence: the file. | content | 2 | - | V1-16
V1-15 | V1 | V1-P2 Live demo + collateral | Pitch deck (10-12 slides, on-brand) | A5,A6 | A6-1 | G8 | Web | Docs | Very important | NEW | 0% | Problem -> why BI fails -> evidence-grade approach -> LIVE DEMO -> value -> honest boundary -> read-only/OT-safe -> credibility -> pilot offer. <=12 slides, brand palette. The narrative content largely exists across the delivered docs (01-overview, 06-methodology, 04-security, 08-pilot, 09-founder) - assemble into a deck and produce the logo/brand variant set. | Rehearsed once; <=12 slides; on-brand. Evidence: the file. | content | 4 | - | V1-17
V1-16 | V1 | V1-P2 Live demo + collateral | Finalize the pilot offer (DELIVERED as 08-pilot doc — fill price/customer) | A5 | A5-7 | - | Web | Docs | Very important | MOSTLY-DONE | 80% | The customer doc 08-pilot-offer.md is DELIVERED (read-only, time-boxed, fee-credited-on-conversion; scope/success/commercials tables). Remaining: fill [[PILOT_FEE]] (lean EUR30k for the first), [[CONVERSION_TARGET]] (the EUR120k/yr figure), [[CUSTOMER_NAME]], [[PILOT_DURATION]], and the source/target-question specifics per prospect. | One offer with the price + conversion figure + ask filled for a named prospect. Evidence: the file. | content | 2 | - | V1-19
V1-17 | V1 | V1-P2 Live demo + collateral | Cut the 2-3 minute demo video (blueprint delivered) | A6 | A6-10 | G8 | Web | Docs | Important | NEW | 0% | Per the handover the cut sheet PlantProcess-IQ-Demo-Reel-CutSheet.md is DELIVERED (2:45 EDL + VO + export + 'no dead click' QC). The MP4 render is yours and depends on the V1-13 recording. | 2-3 min MP4; no dead click. Evidence: the file. | content | 3 | V1-11 | V1-20
V1-18 | V1 | V1-P2 Live demo + collateral | Wire website CTA to a real inbox (CODE DONE — commit + SMTP + relay) | A6 | A6-10 | G8 | Web | Web | Very important | MOSTLY-DONE | 65% | Per the handover the lead-email CODE is DONE and builds clean (V5OutboundLeadSystemEndpoints.cs TrySendLeadEmailAsync; env PlantProcess__Lead__Smtp__*; form POSTs to /api/v5/outbound/leads). Remaining: COMMIT it; supply live SMTP env; do a real-send test. IMPORTANT: route via an authenticated transactional relay (587/465) with SPF+DKIM+PTR and outbound port 25 blocked - never send from the VPS IP (Hetzner/Spamhaus notice). (Hardened backend + e2e assert is the separate V2 task.) | A test submit lands in your inbox/DB via the relay; Spamhaus web-checker shows the IP not listing. Evidence: the received lead + checker screenshot + commit hash. | feature | 4 | - | V1-22
V2-01 | V2 | V2-P3 Stability + UI | Full backend+frontend suite green twice on clean machine (local) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 30% | Server suite is green; close the LOCAL clean-machine path so the whole backend+frontend suite runs green twice on a fresh checkout with no hand-set vars. Builds on the local test-config task. | Both suites exit 0 twice on a fresh local machine. Evidence: two green logs. | hardening | 10 | V1-03 | V2-01
V2-02 | V2 | V2-P3 Stability + UI | Standardize all native buttons onto StandardButton | A1,A3 | A3-3 | G6 | FrontEnd | FrontEnd | Important | PARTIAL | 10% | ~151 native buttons not on StandardButton. Migrate all to the standard component so styling is uniform current AND future (the Material-Investigation mismatch class is standardized away, not patched once). | A scan shows 0 native buttons outside StandardButton; visual-regression green. Evidence: scan + diff. | refactor | 14 | V2-04 | V2-02
V2-03 | V2 | V2-P3 Stability + UI | E2E action-matrix enumerating every demo-path control (CI gate) | A1,A3 | A1-5, A3-1 | G6 | Testing | Testing | Very important | PARTIAL | 40% | The action-matrix spec exists and is 20/20 green (handover); promote it to a BLOCKING CI gate that enumerates every control on every demo-path page and runs on push. | The action-matrix spec is green and blocking in CI. Evidence: the spec + CI run. | feature | 8 | V1-10 | V2-03
V2-04 | V2 | V2-P3 Stability + UI | Visual-regression harness (baseline + diff gate) | A3,A6 | A3-3, A6-8 | G6 | Testing | Testing | Important | NEW | 0% | Capture a baseline of every demo-path page and gate PRs on a pixel/DOM diff so styling never silently drifts. | A deliberate style change fails the diff gate; an intended change updates the baseline. Evidence: CI run. | feature | 6 | - | V2-04
V2-05 | V2 | V2-P3 Stability + UI | Nightly full-suite CI job (cron) | A1 | A1-5 | G9 | Testing | Deploy | Very important | PARTIAL | 30% | The deploy pipeline runs on push; add a scheduled nightly job that runs the FULL backend+frontend+e2e suite and reports flaky tests, independent of pushes. | A nightly run exists and reports pass-rate + flaky count. Evidence: the cron job + a nightly report. | feature | 6 | V2-01 | V2-05
V2-06 | V2 | V2-P3 Stability + UI | Health dashboard (suite/e2e pass-rate, flaky count) | A1 | A1-5 | G9 | Testing | Web | Normal | NEW | 0% | A small dashboard surfacing suite pass-rate, e2e pass-rate, and flaky-test count over time. | The dashboard renders current + trend from real runs. Evidence: the page. | feature | 5 | V2-05 | V2-06
V2-07 | V2 | V2-P4 License + Role + Security | MFA step-up for admin accounts | A2 | A2-4 | G12 | Security | Backend | Very important | NEW | 0% | TOTP/WebAuthn step-up enforced for admin roles per the identity doctrine. (sysadmin is the support account; MFA applies to any admin-capable login.) | An admin action triggers an MFA step-up live; non-admin does not. Evidence: test + clip. | feature | 8 | - | V2-07
V2-08 | V2 | V2-P4 License + Role + Security | Deepen license tiers: caps enforced + expiry/grace + admin governance | A5 | A5-3 | G12 | Security | Backend | Very important | PARTIAL | 20% | The signed-token activation works (proven on the server with Enterprise). Deepen ENFORCEMENT: seat/source/env caps actually enforced from the token; expiry -> warnings -> configurable read-only grace -> read-only (data never destroyed); soft-vs-hard caps; admin governance to add/manage seats. The 07-editions-and-licensing doc already describes the intended model. | Toggling a tier visibly adds/removes features AND enforces a cap live; an expired token enters grace then read-only. Evidence: tamper test + clips. | feature | 12 | - | V2-08
V2-09 | V2 | V2-P4 License + Role + Security | Real production Ed25519 license signing key (Option-1 -> Option-3) [NEW 26-Jun] | A2,A5 | A2-5, A5-3 | G12 | Security | Security | Very important | NEW | 0% | NEW from the 26-Jun session. The demo activates Enterprise with the DEV Ed25519 key (kid ppiq-dev-ed25519), registered only when PPIQ_PRESENTATION=on. For real customers: generate a REAL production Ed25519 signing keypair (kept in a secret store, never in git), sign per-customer/per-tier tokens with it, register the real public key through the canonical licensing/ops flow (not the dev fixture), and ensure the dev key is NEVER shipped/registered in a real customer Production. ALSO: real customer frontend builds must NOT bake VITE_SMOKE_* (demo credentials) into the bundle - gate the demo auto-login to the demo host only. | A real-key-signed per-customer token activates on a clean 'customer' install with PPIQ_PRESENTATION off and NO dev key registered; grep shows the dev key + VITE_SMOKE_* absent from a customer build. Evidence: activation log + grep. | feature | 10 | - | V2-PROD-KEY
V2-10 | V2 | V2-P4 License + Role + Security | Full RBAC role-scope live across 6 roles | A5 | A5-2 | G5 | Security | Backend | Very important | PARTIAL | 55% | Owner/Plant-Admin/Data-Engineer/Engineer/Operator/Viewer-Executive: enforce per-role view/edit scope on every page/endpoint and prove it across all six logins. (Server identity is DB-backed app_users; sysadmin is the owner.) | Authorization matrix green by identity; each role sees only its scope live. Evidence: matrix test + clips. | feature | 10 | - | V2-09
V2-11 | V2 | V2-P4 License + Role + Security | Enforce RLS on core tables (decide tenant_id; non-superuser app role) | A2 | A2-6 | G12 | Security | Database | Very important | PARTIAL | 40% | Decide deliberately (RLS-scoped core vs single-tenant-per-deploy). If multi-tenant: add tenant_id to the core EF entities model-first, run the app under a non-superuser role so RLS is actually enforced (locally ppiq_dev is bypassrls), and prove cross-tenant 403/empty. NOTE: ppiq_ed25519_license_public_keys already demonstrates forced RLS - use it as the pattern. | Cross-tenant access returns 403/empty live under a non-superuser role. Evidence: RlsTenantIsolation test green + clip. | feature | 10 | - | V2-10
V2-12 | V2 | V2-P4 License + Role + Security | Encryption at rest: staging/canonical/credential-vault | A2 | A2-9 | G12 | Security | Infra | Important | NEW | 0% | Encryption at rest for the app DB and the source-credential vault; document the key management. The 04-security doc already states this as a design property - implement + verify it. | At-rest encryption is on and verified; credentials are encrypted in the vault. Evidence: config + verification. | hardening | 6 | - | V2-11
V2-13 | V2 | V2-P4 License + Role + Security | Persistent infra Caddyfile + correct route targets [NEW 26-Jun] | A2,A4 | A4-9 | G9 | Infra | Infra | Very important | NEW | 0% | NEW from the 26-Jun session. The live infra Caddyfile is an orphaned inode (host bind source deleted) with STALE targets (plantprocess-app-web, plantprocess-website) that don't match the real containers (plantprocess-web, plantprocess-api); app.* still serves 200 but it's fragile and hot-reloads are non-persistent. Re-establish a persistent host-bound Caddyfile in the infra project with CORRECT targets, so routes survive a Caddy recreate. Do NOT recreate ppiq-caddy until this lands. | After recreating ppiq-caddy, app.*/api.*/website.* all route to the correct live containers; the Caddyfile is host-bound and survives a restart. Evidence: docker exec cat + curl matrix. | hardening | 6 | - | V2-CADDY
V2-14 | V2 | V2-P4 License + Role + Security | Harden .env<->Postgres-volume password coupling + provisioning resilience [NEW 26-Jun] | A4 | A4-9 | G9 | Infra | Infra | Important | NEW | 0% | NEW from the 26-Jun session. Two small hardenings: (1) make ensure-runtime-env.sh PRESERVE POSTGRES_PASSWORD across a stale-key regeneration (today a regen rotates it and diverges from the existing Postgres volume -> 28P01); document the rule that /var/lib/ppiq-preserve/.env must not be deleted, and if it is, the volume must be wiped in the same step. (2) Wrap FirstRunProvisioningHostedService provisioning in try/catch so a provisioning failure logs but never crashes the API at startup. | A simulated stale-key regen keeps the same POSTGRES_PASSWORD and the API still connects; an induced provisioning error is logged and the API still starts. Evidence: regen log + fault-injection test. | hardening | 5 | - | V2-ENVLOCK
V2-15 | V2 | V2-P4 License + Role + Security | Move Jenkins to a separate Docker network from the app project [NEW 26-Jun] | A2 | A2-10 | G12 | Infra | Infra | Normal | NEW | 0% | NEW from the 26-Jun session. Today ppiq-jenkins and the app project share network reachability via the edge alias. Move Jenkins onto its own network so the CI/CD agent is isolated from the app stack (defense in depth), keeping only the Caddy fronting it. | Jenkins runs on a dedicated network; the app stack cannot reach Jenkins by name; deploys still work. Evidence: network inspect + a green deploy. | hardening | 4 | V2-13 | V2-JENKINS-NET
V2-16 | V2 | V2-P4 License + Role + Security | Pricing & license-tiers PAGE (web) — content delivered in 07-editions doc | A5,A6 | A6-7 | G8 | Web | Web | Important | MOSTLY-DONE | 70% | The CONTENT exists: 07-editions-and-licensing.md states the editions, the signed-entitlement model, renewal, and caps. Remaining: render it as a public web page on the marketing site (honesty-lint green) and fill [[PER_PLANT_ACV_RANGE]]/[[FLEET_ACV_RANGE]] with your real numbers. | The page lists all four tiers with grants/renewal/caps; honesty-lint green; ACV ranges filled. Evidence: the page. | content | 5 | - | V2-12
V2-17 | V2 | V2-P5 AI/ML quality | Sharpen AI/ML results: calibration, effect-size ranking, stratified quality | A3 | A3-7 | G4 | AI+ML | AI+ML | Very important | NEW | 0% | Improve the learning output: calibrated scores, effect-size (not just p-value) ranking, stratified quality by visible confounders, under BH-FDR - framed as suspected contributors. The 06-analytics-methodology doc already commits to this posture. | On the golden dataset, true signals are recovered and spurious rejected under FDR; results show effect size + stratification. Evidence: golden-set test + clip. | feature | 12 | V1-04 | V2-13
V2-18 | V2 | V2-P5 AI/ML quality | Impressive evidence-ranked suggestion engine (deterministic, euro impact) | A3,A5 | A5-1 | G4 | AI+ML | AI+ML | Very important | PARTIAL | 55% | Deterministic, MD5-stable suggestions ranked by evidence + euro impact, workflow-bound with RBAC, surfaced in SuggestionCardsPanel - the 'told me something I didn't know, and proved it' moment. | Suggestions render with population, method, evidence handle and a euro range; reproducible IDs. Evidence: test + clip. | feature | 10 | V1-04 | V2-14
V2-19 | V2 | V2-P5 AI/ML quality | Assistant eval harness + model-version governance gate | A2,A5 | A5-4 | G13 | AI+ML | Testing | Important | NEW | 0% | An eval harness that gates assistant regressions and a model-version governance gate (no uncited number, citations resolve). | The harness fails on an injected uncited-number regression; passes clean. Evidence: the harness + CI. | feature | 6 | - | V2-15
V2-20 | V2 | V2-P5 AI/ML quality | Wire DataBoundaryPolicy into assistant dispatch (no-egress live) | A2 | A2-8 | G13 | AI+ML | Backend | Very important | PARTIAL | 50% | Route every assistant call through the gateway so only question + scoped evidence leaves; honour a per-tenant no-egress toggle (self-hosted default). The 04-security doc commits to this. | Self-hosted mode leaks nothing; private-endpoint sends only question+evidence; toggle proven. Evidence: test + capture. | feature | 7 | - | V2-16
V2-21 | V2 | V2-P5 AI/ML quality | Wire SourceLoadProtectionPolicy into the live query path | A2 | A2-3 | G11 | Security | Backend | Very important | PARTIAL | 50% | Enforce the per-source impact budget on a real query path so an over-budget query is throttled, not just policy-defined. | An over-budget query is throttled live. Evidence: test + clip. | feature | 7 | - | V2-17
V2-22 | V2 | V2-P5 AI/ML quality | Real lead-capture backend (form->DB row+email via relay, e2e asserts) | A6 | A6-10 | G8 | Web | Backend | Important | PARTIAL | 30% | Harden the CTA path into a real backend: validated submit -> stored row + email (via the authenticated relay, never the VPS IP), with an e2e test asserting the row. Builds on the V1 lead-email code. | e2e asserts a lead row + email on submit through the relay. Evidence: the test. | feature | 6 | V1-18 | V2-18
V2-23 | V2 | V2-P6 Docs + hygiene | User guide: embed app screenshots into the delivered 02-capabilities narrative | A3 | A3-2 | - | Docs | Docs | Important | MOSTLY-DONE | 70% | The narrative user guide is DELIVERED (02-platform-capabilities.md + index walk the platform feature by feature, zero placeholders). Remaining: capture real app screenshots from the live demo and embed them inline + a 9-step walkthrough section. | The guide carries screenshots matching the current UI alongside the delivered narrative. Evidence: the doc. | content | 6 | V1-11 | V2-19
V2-24 | V2 | V2-P6 Docs + hygiene | Install runbook: embed screenshots into the delivered 03-architecture narrative | A4 | A4-9 | G9 | Docs | Docs | Important | MOSTLY-DONE | 70% | The deployment narrative is DELIVERED (03-architecture-and-deployment.md covers SaaS/dedicated/on-prem/air-gapped). Remaining: add the concrete server runbook (infra plantprocessiq + app ppiq-app, the git-push pipeline, .env/secret handling, sysadmin first-login) WITH screenshots, cross-referencing Identity & Topology v4. | A clean machine reaches a working login by following the runbook only. Evidence: the runbook + a clean-follow log. | content | 8 | - | V2-20
V2-25 | V2 | V2-P6 Docs + hygiene | Admin/Operator guide: screenshots + two-admin model (05-onboarding delivered) | A4 | A4-1 | - | Docs | Docs | Important | MOSTLY-DONE | 70% | The onboarding/integration narrative is DELIVERED (05-data-onboarding-and-integration.md). Remaining: an admin/operator guide with screenshots covering source onboarding, mapping, jobs monitor, schema-drift, and the two-admin model (sysadmin vs the customer admin added at commissioning). | The guide covers each admin task with screenshots. Evidence: the doc. | content | 10 | - | V2-21
V2-26 | V2 | V2-P6 Docs + hygiene | Security whitepaper (DELIVERED as 04-security doc — verify + publish) | A2 | A2-1 | G12 | Docs | Docs | Important | MOSTLY-DONE | 85% | The security/procurement brief is DELIVERED (04-security-and-data-protection.md: read-only, identity incl. the two-admin model, secrets, isolation, encryption, audit, AI data boundary - each a design property). Remaining: confirm every stated control matches the shipped code (some are V2 enforcement tasks above) and add the Spamhaus-safe mail posture; then publish. | Each control in the doc maps to shipped behavior or a tracked task; mail posture added. Evidence: the doc + a control-to-code map. | content | 6 | - | V2-22
V2-27 | V2 | V2-P6 Docs + hygiene | API reference | A1 | A1-7 | - | Docs | Docs | Normal | NEW | 0% | Generate/author an API reference for the public endpoints (auth, licensing ed25519 activate/current with the licenseJws field, readiness, /api/v5/outbound/leads, etc.). | The reference lists each endpoint with request/response shapes (correct field names). Evidence: the doc. | content | 4 | - | V2-23
V2-28 | V2 | V2-P6 Docs + hygiene | Naming golden-rule pass: rename phase/task-named artifacts | A1 | A1-4 | - | Docs | Database | Important | NEW | 0% | ~193 files carry phase/task tokens (p03_p04, phase8, T042, _v6_, hotfix). This includes the production SQL still named 301_p01_p02_authstore_compatibility_bridge.sql, 302_p02_*, 300_p01_p02_*, 500_v5_p01_*, etc. Rename to descriptive names and update references; preserve only ordered-migration numeric prefixes (strip the embedded phase label). The ppiq-app project rename is already done. | The phase/task-token grep returns 0 (outside ordered-prefix migrations); build + tests green; the server deploy stays green after the renames. Evidence: grep + green build + green deploy. | refactor | 18 | - | V2-24
V2-29 | V2 | V2-P6 Docs + hygiene | HasDefaultSchema -> ppiq_meta/ppiq_plant for EF entities | A1 | A1-3 | - | Database | Database | Normal | NEW | 0% | Add HasDefaultSchema mapping so EF tables land in ppiq_meta/ppiq_plant instead of public, realising the app-metadata vs customer-data split. | `\dt ppiq_meta.*` and `ppiq_plant.*` list the EF tables after migrate. Evidence: psql output. | refactor | 4 | - | V2-25
V3-01 | V3 | V3-P7 Multi-industry data | Second-industry demo dataset (paper/board line) + mapping templates | A1,A3 | A3-11 | G3 | Demo | Database | Very important | NEW | 0% | A paper/board demo dataset (sources + fixtures) and mapping templates, built entirely through the HMI like the steel demo - proving the generic mandate the docs claim. | The paper demo builds from empty via HMI; a genealogy thread resolves on its keys. Evidence: clip. | feature | 14 | V1-04 | V3-01
V3-02 | V3 | V3-P7 Multi-industry data | Third-industry demo dataset (food & beverage) + tier configs | A1,A3 | A3-11 | G3 | Demo | Database | Very important | NEW | 0% | A food & beverage demo dataset + per-tier configs, same HMI-only build. | The F&B demo builds from empty via HMI. Evidence: clip. | feature | 12 | V3-01 | V3-02
V3-03 | V3 | V3-P7 Multi-industry data | Generic canonical-mapping template library + no-code visual-mapper polish | A1,A4 | A4-2 | G2 | Workflow | FrontEnd | Very important | NEW | 0% | A reusable template library + polish on the no-code visual mapper so the common case needs zero SQL across industries. | A non-developer maps a new source via templates + drag-drop, no SQL. Evidence: clip. | feature | 12 | V1-04 | V3-03
V3-04 | V3 | V3-P7 Multi-industry data | Demo dataset polish + per-industry scripted reset | A3 | A3-11 | G7 | Demo | Deploy | Important | PARTIAL | 60% | Polish each demo dataset and add a one-command scripted reset per industry so any prospect sees the same clean story. | One command resets+reseeds an industry to a known state. Evidence: run log. | feature | 6 | V3-01 | V3-04
V3-05 | V3 | V3-P7 Multi-industry data | Historian connector to GA (behavioural-tested) | A1,A2 | A2-2 | G1 | Workflow | Backend | Very important | NEW | 0% | Take one historian connector (e.g. OPC-UA) to GA with behavioural certification tests. | The historian connector passes behavioural certification + links live. Evidence: test + clip. | feature | 12 | - | V3-05
V3-06 | V3 | V3-P7 Multi-industry data | One-command customer-install package (per-industry overlay) | A4 | A4-9 | G9 | Infra | Deploy | Very important | NEW | 0% | Package a one-command customer install with a per-industry overlay, building on the green server pipeline + PPIQ_SITE_HOST host-derivation. | A fresh host installs + reaches login with one command + an overlay. Evidence: clean-install log. | feature | 8 | V2-13 | V3-06
V3-07 | V3 | V3-P8 Accessibility + scale | WCAG 2.1 AA light theme + contrast audit | A6 | A6-9 | G14 | FrontEnd | FrontEnd | Important | NEW | 0% | A WCAG 2.1 AA light theme + contrast audit across the app. | An automated WCAG audit passes AA; the light theme renders. Evidence: audit report. | feature | 10 | - | V3-07
V3-08 | V3 | V3-P8 Accessibility + scale | Arabic RTL + locale/units/timezone switching per user | A6 | A6-9 | G14 | FrontEnd | FrontEnd | Important | NEW | 0% | Arabic RTL layout + per-user locale/units/timezone switching. | Switching to Arabic re-flows RTL correctly; units/timezone follow the user. Evidence: clip. | feature | 8 | V3-09 | V3-08
V3-09 | V3 | V3-P8 Accessibility + scale | i18n as resource files (.resx/JSON) + fix mojibake | A1 | A1-1 | G14 | FrontEnd | Backend | Important | NEW | 0% | Move i18n out of SQL inserts (420/425/610) into resource files; fix the encoding-damaged strings. | Strings load from resource files; no mojibake; the SQL i18n inserts are retired. Evidence: diff + render. | refactor | 8 | - | V3-09
V3-10 | V3 | V3-P8 Accessibility + scale | Performance-at-scale validation (630/5,600, virtualized tables) | A3 | A3-9 | G6 | FrontEnd | Testing | Important | NEW | 0% | Validate no hang/lag at demo scale; virtualize large tables; progress indicators on long loads. | At ~630 heats/~5,600 coils, no hang; tables virtualize; long loads show progress. Evidence: measured run. | feature | 8 | - | V3-10
V3-11 | V3 | V3-P8 Accessibility + scale | Soak job (24-72h synthetic load on demo path) | A4 | A4-9 | G9 | Testing | Testing | Important | NEW | 0% | A 24-72h synthetic-load soak against the demo path to catch leaks/instability. | A 24h+ soak completes with no leak/regression. Evidence: soak report. | feature | 8 | - | V3-11
V3-12 | V3 | V3-P8 Accessibility + scale | Real-domain TLS cutover (off sslip.io) [NEW 26-Jun] | A2,A6 | A6-6 | G9 | Infra | Deploy | Important | NEW | 0% | NEW from the 26-Jun session. The demo runs on 178.105.152.180.sslip.io with host-derived URLs (PPIQ_SITE_HOST). To move to a real domain: set PPIQ_SITE_HOST=<domain>, CADDY_AUTO_HTTPS=on, ACME_EMAIL=<addr>, point real DNS, and let Caddy issue real certs - all URLs + CORS follow automatically. | The app/api/website serve on the real domain over valid public TLS; CORS allows the real origins. Evidence: cert + curl. | hardening | 6 | V2-13 | V3-TLS
V3-13 | V3 | V3-P8 Accessibility + scale | QES product page to depth | A6 | A6-7 | G8 | Web | Web | Optional | NEW | 0% | Take the QES product page to full depth (was 'coming soon'). | The QES page is complete; honesty-lint green. Evidence: the page. | content | 7 | - | V3-12
V3-14 | V3 | V3-P8 Accessibility + scale | Energy Management product page to depth | A6 | A6-7 | G8 | Web | Web | Optional | NEW | 0% | Take the Energy Management product page to full depth. | The Energy page is complete; honesty-lint green. Evidence: the page. | content | 7 | - | V3-13
V4-01 | V4 | V4-P9 Ops/HA + OT | Backup/restore drill (verified restore, recorded) | A4 | A4-9 | G9 | Infra | Deploy | Very important | NEW | 0% | Drill a full backup + verified restore of the app DB; record it. Closes the restore half of A4-9/G9 the deploy session did not. | A restore from backup reaches a working login; recorded. Evidence: the recording. | feature | 8 | - | V4-01
V4-02 | V4 | V4-P9 Ops/HA + OT | Verify deploy rollback to :previous | A4 | A4-9 | G9 | Infra | Deploy | Important | NEW | 30% | The pipeline already tags :previous and rolls back on a failed health gate. Verify it end-to-end by inducing a health-gate failure and confirming the rollback restores service. | An induced bad deploy rolls back to :previous and service stays up. Evidence: pipeline log. | verification | 5 | - | V4-02
V4-03 | V4 | V4-P9 Ops/HA + OT | Time-series store (hypertables, compression, retention) | A4 | A4-8 | G9 | Infra | Database | Very important | NEW | 0% | Introduce a time-series store (hypertables/columnar, compression, downsampling, retention) for high-frequency parameters. | Parameter data lands in the time-series store with compression + retention. Evidence: schema + query. | feature | 12 | - | V4-03
V4-04 | V4 | V4-P9 Ops/HA + OT | Deployable OT-safe edge agent (one-way push) | A2 | A2-2 | G11 | Infra | Backend | Very important | NEW | 0% | Build a deployable Edge Collector that pushes one-way from the DMZ; the core never connects into OT. The docs already describe this model. | The agent pushes one-way; no inbound path to OT; load within budget. Evidence: deploy + capture. | feature | 12 | - | V4-04
V4-05 | V4 | V4-P9 Ops/HA + OT | Human-approved advisory write-back (business workflow, never OT) | A5 | A5-9 | G5 | Backend | Backend | Very important | NEW | 0% | Advisory write-back into business workflow (case/action tracking) with human approval - never a setpoint/command to control. | An approved advisory creates a tracked action; no OT write path exists. Evidence: workflow + code-search. | feature | 10 | - | V4-05
V4-06 | V4 | V4-P9 Ops/HA + OT | Enforce performance budgets in CI | A1 | A1-2 | G6 | Testing | Testing | Important | NEW | 0% | Add performance budgets as CI gates so regressions fail the build. | A deliberate perf regression fails CI. Evidence: CI run. | feature | 6 | - | V4-06
V4-07 | V4 | V4-P9 Ops/HA + OT | Load-test at reference-plant scale | A4 | A4-9 | G9 | Testing | Testing | Very important | NEW | 0% | Load-test at realistic reference-plant scale (well beyond demo scale). | The system holds at reference scale within budget. Evidence: load report. | feature | 8 | - | V4-07
V4-08 | V4 | V4-P10 Compliance + ops | Start SOC 2 Type II observation window | A2 | A2-9 | G16 | Docs | Security | Very important | NEW | 0% | Begin the SOC 2 Type II observation window (controls evidenced over time). | The observation window is open with controls evidenced. Evidence: the tracker. | content | 10 | - | V4-08
V4-09 | V4 | V4-P10 Compliance + ops | ISO 27001 mapping + sensitive-data catalog | A2 | A2-9 | G16 | Docs | Security | Important | NEW | 0% | Map controls to ISO 27001 and catalog sensitive data. | The mapping + catalog exist. Evidence: the docs. | content | 8 | - | V4-09
V4-10 | V4 | V4-P10 Compliance + ops | GxP / 21 CFR Part 11 pack (audit trail, e-signature) | A2 | A2-9 | G16 | Docs | Security | Optional | NEW | 0% | A GxP / 21 CFR Part 11 pack where required (audit trail + e-signature). | The pack evidences audit trail + e-signature. Evidence: the docs. | content | 12 | - | V4-10
V4-11 | V4 | V4-P10 Compliance + ops | Public status page | A4 | A4-9 | - | Web | Web | Normal | NEW | 0% | A public status page for the hosted service. | The status page reflects real health. Evidence: the page. | content | 4 | - | V4-11
V4-12 | V4 | V4-P10 Compliance + ops | AI triage loop (agent drafts fix PRs, human-approved) | A1 | A1-5 | - | AI+ML | Testing | Important | NEW | 0% | An AI triage loop where an agent drafts fix PRs from failing tests, human-approved. | The loop drafts a PR for an injected failure; human merges. Evidence: the PR. | feature | 10 | - | V4-12
V4-13 | V4 | V4-P10 Compliance + ops | Recorded certified dry-run (one-click readiness on video) | A4 | A4-7 | G7 | Demo | Docs | Very important | NEW | 0% | A recorded certified dry-run showing one-click readiness green - the reference acceptance artifact. | The recording shows readiness green end-to-end. Evidence: the file. | content | 4 | V1-09 | V4-13
V4-14 | V4 | V4-P10 Compliance + ops | Consolidate full operator/admin/security docs | A4 | A4-9 | - | Docs | Docs | Important | NEW | 30% | Consolidate the delivered doc suite (01-09) + the screenshot-embedded guides into one coherent, cross-linked, versioned doc set. | One consolidated doc set, cross-linked. Evidence: the docs. | content | 8 | V2-24 | V4-14
V4-15 | V4 | V4-P11 Business/Reference | Incorporate (UG/GmbH) + imprint | A5 | - | - | Web | Docs | Very important | NEW | 0% | Incorporate the company (UG/GmbH) and add the legal imprint. | The entity exists + imprint published. Evidence: the registration. | content | 8 | - | V4-15
V4-16 | V4 | V4-P11 Business/Reference | Pilot contract + MNDA + DPA templates | A5 | - | - | Docs | Docs | Very important | NEW | 0% | Pilot contract, mutual NDA, and DPA templates ready to sign (the 08-pilot doc is the commercial offer; these are the legal instruments). | The three templates exist + reviewed. Evidence: the files. | content | 8 | - | V4-16
V4-17 | V4 | V4-P11 Business/Reference | Target list + outreach sequence (PSI network) | A5 | - | - | Web | Docs | Very important | NEW | 0% | A target list + outreach sequence leveraging your PSI/SMS network. | The list + sequence exist + first touches sent. Evidence: the tracker. | content | 10 | - | V4-17
V4-18 | V4 | V4-P11 Business/Reference | Convert presentation customer into a signed paid pilot | A5 | - | - | Web | Docs | Critical | NEW | 0% | Convert the presentation prospect into a signed paid pilot (using the delivered 08-pilot offer with your price filled). | A signed pilot agreement exists. Evidence: the signature. | content | 12 | V1-16 | V4-18
V4-19 | V4 | V4-P11 Business/Reference | Prove ROI on the customer's real data (pilot deliverable) | A5 | A5-1 | G5 | AI+ML | AI+ML | Critical | NEW | 0% | On the customer's real data, prove a bounded ROI - the pilot deliverable. | A proven (not projected) euro figure on the customer's data. Evidence: the report. | feature | 8 | V4-18 | V4-19
V4-20 | V4 | V4-P11 Business/Reference | Run the paid pilot | A4,A5 | - | - | Workflow | Backend | Critical | NEW | 0% | Run the paid pilot end-to-end on the customer's environment. | The pilot completes its scope. Evidence: the pilot log. | feature | 20 | V4-18 | V4-20
V4-21 | V4 | V4-P11 Business/Reference | Convert pilot to a signed contract | A5 | - | - | Web | Docs | Critical | NEW | 0% | Convert the completed pilot into a signed annual contract. | A signed contract exists. Evidence: the signature. | content | 12 | V4-20 | V4-21
V4-22 | V4 | V4-P11 Business/Reference | Produce the case study / reference | A5 | - | - | Web | Docs | Very important | NEW | 0% | Produce a case study / reference from the pilot customer. | A published case study + a reference contact. Evidence: the file. | content | 6 | V4-21 | V4-22
V4-23 | V4 | V4-P11 Business/Reference | Viability arrangement (hire / escrow+BCP / partner) | A5 | - | - | Web | Docs | Very important | NEW | 0% | Close the bus-factor objection: a hire, source escrow + BCP, or a partner. | A viability arrangement is in place. Evidence: the agreement. | content | 12 | - | V4-23
V4-24 | V4 | V4-P11 Business/Reference | Support SLA offering | A4 | - | - | Docs | Docs | Important | NEW | 0% | A support SLA offering (tiers, response times). | The SLA offering exists. Evidence: the doc. | content | 5 | - | V4-24
V4-25 | V4 | V4-P11 Business/Reference | Funding / partnership decision | A5 | - | - | Web | Docs | Normal | NEW | 0% | Decide funding/partnership direction. | A decision recorded. Evidence: the note. | content | 4 | - | V4-25

## Reassessment
Reassessment · v5 ID -> v6 ID + decision, with the reason (numbering + docs)
v5 Task ID | v6 Task ID | Status in v6 | Reason
V1-01 + V1-02 | V1-01 | MOSTLY-DONE 80% | Merged (local reproducibility); server path already green.
V1-05 | V1-02 | NEW 10% | Renumbered; local hygiene (local.env leak + stale appsettings users).
V1-06 | V1-03 | PARTIAL 40% | Renumbered; LOCAL clean-machine 'green twice' is the remaining gate.
V1-07 | V1-04 | NEW 5% (P0) | Renumbered; the lost genealogy/safe-SQL foundation - still the headline bottleneck.
V1-08 / V1-09 | V1-05 / V1-06 | PARTIAL | Renumbered; live genealogy + transition-coil clips owed (backend green).
V1-PT1 | V1-07 | NEW 30% | Renumbered; phase gate now also asserts the server deploy stays green + seed exit=0.
V1-10 / V1-11 | V1-08 / V1-09 | PARTIAL | Renumbered; Playwright boot + one-click readiness clips owed.
V1-12 | V1-10 | MOSTLY-DONE 75% | Action-matrix DONE 20/20 per handover; COMMIT + live click-through remain.
V1-13 | V1-11 | NEW 0% | Renumbered; record the MP4 - Karim-owned, cannot be AI-done.
V1-14 | V1-12 | MOSTLY-DONE 80% | Demo script DELIVERED (handover); fill 2 placeholders + rehearse.
V1-15 | V1-13 | MOSTLY-DONE 80% | ROI model+slide DELIVERED (handover, EUR480k/yr); fill real price.
V1-16 | V1-14 | MOSTLY-DONE 80% | Founder pack DELIVERED as 09-founder doc; fill [[YEARS]]/[[BACKGROUND]]/contact.
V1-17 | V1-15 | NEW 0% | Renumbered; pitch deck - content exists across docs, assemble into a deck.
V1-18 | (removed) | REMOVED 85% | One-page brief DELIVERED as 01-product-overview.md (zero placeholders). Moved to Completed.
V1-19 | V1-16 | MOSTLY-DONE 80% | Pilot offer DELIVERED as 08-pilot doc; fill [[PILOT_FEE]]/[[CONVERSION]]/[[CUSTOMER]].
V1-20 | V1-17 | NEW 0% | Renumbered; demo-reel cut sheet DELIVERED; MP4 render is Karim's (needs V1-11).
V1-21 | (removed) | REMOVED 95% | IQ page DONE per handover (content+build green). Moved to Completed.
V1-22 | V1-18 | MOSTLY-DONE 65% | Lead-email CODE DONE per handover; commit + SMTP + relay remain.
V2-01..V2-06 | V2-01..V2-06 | PARTIAL/NEW | Renumbered in place; stability/UI harness; V2-03 bumped (action-matrix exists).
V2-07 | V2-07 | NEW 0% | MFA - renumbered.
V2-08 | V2-08 | PARTIAL 20% | Tier cap enforcement - renumbered.
V2-PROD-KEY | V2-09 | NEW 0% | NUMBERED: real production Ed25519 signing key (Option-1->Option-3).
V2-09 / V2-10 | V2-10 / V2-11 | PARTIAL | RBAC + RLS - renumbered.
V2-11 | V2-12 | NEW 0% | Encryption at rest - renumbered.
V2-CADDY | V2-13 | NEW 0% | NUMBERED: persistent infra Caddyfile + correct targets.
V2-ENVLOCK | V2-14 | NEW 0% | NUMBERED: .env/volume password preservation + provisioning try/catch.
V2-JENKINS-NET | V2-15 | NEW 0% | NUMBERED: Jenkins on a separate Docker network.
V2-12 | V2-16 | MOSTLY-DONE 70% | Pricing page CONTENT delivered as 07-editions doc; render + fill ACV.
V2-13..V2-18 | V2-17..V2-22 | PARTIAL/NEW | AI/ML + lead backend - renumbered; methodology already committed in 06-doc.
V2-19..V2-23 | V2-23..V2-27 | MOSTLY-DONE / NEW | Doc tasks renumbered AND re-scored: user/install/admin/security narratives DELIVERED (02/03/05/04 docs) -> MOSTLY-DONE (embed screenshots); API ref still NEW.
V2-24 / V2-25 | V2-28 / V2-29 | NEW 0% | Naming pass + HasDefaultSchema - renumbered.
V3-* (incl. V3-TLS) | V3-01..V3-14 | NEW/PARTIAL | Renumbered in place; V3-TLS numbered as V3-11.
V4-* | V4-01..V4-25 | NEW/PARTIAL | Renumbered in place; V4-18 now cites the delivered 08-pilot offer.

## Version Summary
Version Summary · effort + the floor each version lifts (v6)
Version | Theme | Tasks | Effort (h) | < 100 h? | Defining outcome (deployable) | Personas it lifts | Floor after
V1 | First Release — Presentation-Ready | 18 | 80 | YES — 80 h | Server deploy GREEN + doc suite delivered; remaining = genealogy foundation + live demo proofs/recording + deck + price-gated docs | A3,A5,A6 (the demo-gating lenses) | ~70-76
V2 | Product Depth — license/role · AI-ML · tests · docs · infra-hardening | 29 | 229 | - | Suite green twice, MFA + tier/role depth, REAL production license key, persistent Caddy, sharper AI + suggestions, docs w/ screenshots | A1,A2,A5 to Solid | ~75-80
V3 | Generic & Multi-Industry | 14 | 126 | - | Paper + food datasets, generic mapper, historian GA, real-domain TLS, WCAG + RTL, scale | A1,A3,A4,A6 generic depth | ~76-82
V4 | Enterprise & Reference | 25 | 222 | - | HA + OT agent + advisory write-back + SOC2/ISO + signed pilot + case study | A2,A4,A5 enterprise + reference | ~80+
TOTAL |  | 86 | 657

## Phase Summary
Phase Summary · each phase deployable; V2-V4 phases ~45-65 h (v6)
Phase | Version | Tasks | Effort (h) | 45-65 h band?
V1-P1 Reproducible env | V1 | 7 | 43 | lean 43 (server substrate already green)
V1-P2 Live demo + collateral | V1 | 11 | 37 | lean 37 (much collateral delivered as docs)
V2-P3 Stability + UI | V2 | 6 | 49 | in band
V2-P4 License + Role + Security | V2 | 10 | 76 | heavy 76 (absorbs the 3 NEW infra-hardening + production-key tasks)
V2-P5 AI/ML quality | V2 | 6 | 48 | in band
V2-P6 Docs + hygiene | V2 | 7 | 56 | in band (doc tasks now screenshot-embedding, not authoring)
V3-P7 Multi-industry data | V3 | 6 | 64 | in band
V3-P8 Accessibility + scale | V3 | 8 | 62 | in band
V4-P9 Ops/HA + OT | V4 | 7 | 61 | in band
V4-P10 Compliance + ops | V4 | 7 | 56 | in band
V4-P11 Business/Reference | V4 | 11 | 105 | heavy 105 (business arc, irreducible)
V1 is now 80 h (down from v5's 87 h): the deploy session closed the heavy substrate and the customer doc suite (01-09) absorbed most of the collateral authoring, so several V1-P2 items dropped to MOSTLY-DONE (fill placeholders / embed screenshots) or were removed. V2-P4 runs heavy (76 h) because it absorbs the three NEW infra-hardening tasks plus the real production signing key. Each phase ends deployable.

## Completed (Removed)
Completed (Removed) · tasks >=85% done — taken off the active plan (v6)
Old ID | Task | % done | Evidence (this session / docs / prior) | Residual work moved to
M1-T02 | Author committed .env.dev (local-only, non-secret) | 95% | Identity v4 sec.4.1: .env.dev carries the 5 role users, the token-free 68-char signing key and ConnectionStrings__PlantProcessDb. | V1-02 fixes the local.env leak that lived alongside it.
M1-T03 | Two-schema migration 000_schemas.sql | 85% | Schemas ppiq_meta + ppiq_plant created (Identity v4 sec.2.2). | Residual: EF tables still land in public -> V2-29 (HasDefaultSchema).
M1-T04 | Demo-sources compose + committed fixtures (8 sources) | 90% | Identity v4 sec.5.1: docker-compose.sources.yml + 630 heats/5,670 coils/... seeded. | Residual: delete the DUPLICATE fleet -> folded into V1-01.
M1-T05 | Seed one user per role via config | 95% | Identity v4 sec.4.1: 5 role users in .env.dev (LOCAL); Argon2id on load; bootstrap disabled. | Residual: delete the stale 4-user set -> V1-02.
M1-T06 | Dev Ed25519 license keypair + per-tier tokens | 95% | Identity v4 sec.6: light/pro/proplus/enterprise tokens minted; all 5 checks green. | Tier-cap ENFORCEMENT -> V2-17; REAL production key -> V2-18.
V1-03 (v5) | Converge to ONE canonical compose + delete orphaned/duplicate fleets | 90% | 26-Jun: server converged to TWO deliberate projects (app=ppiq-app, infra=plantprocessiq); the project-name collision that reaped Jenkins is fixed; Caddy via Option 1. | Residual LOCAL compose convergence -> merged into V1-01.
V1-04 (v5) | Fix connection-string key __DefaultConnection -> __PlantProcessDb | 95% | 26-Jun: the server uses ConnectionStrings__PlantProcessDb end-to-end on the green pipeline. | None — closed.
V1-18 (v5) | One-page product brief (light-surface PDF) | 85% | DELIVERED as 01-product-overview.md (problem/solution/boundary; zero placeholders). | Optional: render the .md as a brand light-surface PDF for the leave-behind.
V1-21 (v5) | Sharpen the IQ product page; others 'coming soon' | 95% | Handover sec.10: content+build green (validate:content=0, tagline=0, build=0); coming-soon positioning layer added; honesty-lint fix in flight. | Confirm the audit-green paste-back -> then fully closed.
SERVER-DEPLOY | Server deploy pipeline GREEN end-to-end (build/test/migrate/seed/deploy-in-place/health-gate+rollback/presentation smoke) | 90% | 26-Jun: Jenkins plantprocessiq-deploy build #96 GREEN; two-project split; the app-project rename stopped --remove-orphans reaping Jenkins. | Residual hardening -> V2-22/V2-23/V2-24, V4-02.
SYSADMIN | Permanent sysadmin first-run provisioning (support-only owner; no customer admin in the image) | 90% | 26-Jun: FirstRunProvisioningHostedService rewritten + registered; only sysadmin in app_users; test users removed from production 301. | Residual resilience (try/catch) -> V2-23.
ENT-ACTIVATE | Enterprise license activation in the demo (Ed25519, licenseJws field, dev-key demo-gated) | 90% | 26-Jun: stage-9 smoke activates Enterprise; dev key registered only when PPIQ_PRESENTATION=on. | Option-1 -> Option-3 real production key -> V2-18.
FE-WIRING | Frontend public-host wiring (VITE build args + host-derived URLs/CORS from PPIQ_SITE_HOST) so the demo UI loads + logs in | 90% | 26-Jun: web Dockerfile + compose pass VITE_SMOKE_*; generator derives VITE_API_BASE_URL/CORS from one PPIQ_SITE_HOST; UI loginable. | Real-domain TLS cutover -> V3-11; remove baked demo creds from real customer builds -> V2-18.
DOCS-CORE | Customer documentation suite (index + 01-product-overview, 02-platform-capabilities, 03-architecture, 04-security, 05-data-onboarding, 06-analytics-methodology) | 90% | Delivered .md set, version 1.0, zero placeholders - covers product overview, capability reference, architecture/deployment, security/procurement brief, integration guide, and methodology/trust. | Screenshot embedding + keeping current -> V2-24/V2-25/V2-26/V2-27 (the V2 doc tasks, now MOSTLY-DONE).