## READ ME - Board Laws
PPIQ PRODUCT BACKLOG v27 - CLEAN EPOCH (22-Jul-2026)
LAW 1 - ONLY OPEN WORK EXISTS | Done tasks are deleted, never archived on the board. History lives in git and in the v25/v26 files. If a task reaches done, it is removed in the next save.
LAW 2 - NO PARTIAL STATUS | A partially finished task is rewritten as its remaining part only, with the estimate recalculated for that remainder. Description and validation always read as 0%-done work.
LAW 3 - IDS RESTART, SEQUENTIAL, PRIORITY-ORDERED | IDs count from M1-01 with no gaps. Within a phase, a lower number means higher priority. Old v25/v26 IDs are retired; where useful, the old ID is noted inside the description as lineage.
LAW 4 - PHASES ARE P1..Pn, NOTHING NAMED-ONLY | M1-P1 is the first phase of M1, M2-P1 the first of M2. No phase exists without a sequence number.
LAW 5 - PHASE SIZE 40-65 HOURS, CRITICAL FIRST | Each phase is a 40-65h block. More critical phases come earlier.
LAW 6 - EVERY PHASE ENDS PUSHABLE | A phase must end with the trunk in a non-broken state: all gates green (npx tsc -b, npm test architecture suite, dotnet build), no half-wired feature reachable from the UI. Features may be incomplete only behind a toggle or an unreachable route.
LAW 7 - JUNIOR-READY TEXT | Every description and validation is written so a developer with zero project background can execute it: file paths, commands, endpoints, and exact acceptance checks included.
PHASE MAP | M1-P1 Demo Lock & Impress (63h) -> push -> PRESENTATION. M2-P1 Working Version Core (60h). M2-P2 Enterprise & Infrastructure (56h). M2-P3 Catalogue & Canvas Completion (49h). M3-P1 Market Proof (44h).
OWNER KEY | Claude = delivered as a PowerShell apply pack you run. Karim = only you can do it (browser, rehearsal, server). Both = pack + your verification.
STANDING GATES | Frontend: npx tsc -b AND npx vitest run src/test/architecture (PPIQ-T11 + UI ratchet; StandardP2* primitives only, no inline style objects). Backend: dotnet build with the API STOPPED (a running API locks the dll -> CS2012).

## M1 Board
ID | Phase | Task | Priority | Type | Owner | Est h | Description (junior-ready) | Validation / acceptance (junior-ready)
M1-P1 |  | DEMO LOCK & IMPRESS - 63h. Ends with: consolidated pass green, four new impress beats live, deck + rehearsals done, trunk pushed.
M1-01 | M1-P1 | Wire-ups: canvas endpoints, canvas routes, website sections | Critical | wiring | Karim | 2 | Three manual insertions the apply packs printed but did not auto-patch. (1) In Backend\PlantProcess.Api\Program.cs add the line app.MapVisualMapperEndpoints(); next to the other app.Map*Endpoints() calls (search for MapDevSeedEndpoints to find the block). (2) In Frontend\PlantProcess.Web\src\App.tsx add two lazy imports (VisualJoinCanvasPage from ./pages/Prep/VisualJoinCanvasPage, AnalysisToolboxPage from ./pages/Analysis/AnalysisToolboxPage) and two routes: /prep/canvas and /analysis/toolbox, plus nav entries "Join Canvas" (under DATA INTEGRATION) and "Analysis Toolbox" (under ANALYTICS) in the nav component. (3) In Website\PlantProcess.Website\src (separate app) import and render in NewHomePage: ArchitectureFlowScroll after the hero, GoldenThreadScroll after the packs, then IntegrationEcosystem, then RoiCalculator demoHref="#request-demo" above RequestDemoForm; also import ./styles/motion-roi.css once. Restart the API afterwards. | Open /prep/canvas and /analysis/toolbox: both render with no 404 and no console errors. GET /api/prep/visual-mapper/datasets returns JSON (not 404) with a bearer token. The public site home page shows the two scroll-drawn SVGs, the ecosystem grid and the ROI calculator. API restarted.
M1-02 | M1-P1 | Run the consolidated test pass | Critical | validation | Karim | 3 | Execute PPIQ_Consolidated_Test_Pass.md end to end in one sitting (~45 min plus notes). It covers: the 9-surface demo path, workspace interactions (switcher, cross-filter, clone/remove, drilldown), the associative panel with its psql truth-check, both canvases, the new chart types, the findings count (expect 320), and the website. Grade every line [P]/[B]/[X], fill every blank, screenshot each part. Finish with npm run build and npm test in Frontend\PlantProcess.Web and record any NEW failures only. | The checklist document is fully graded and saved with screenshots. Every [X] has a one-line defect note (they become M1-03 scope). The psql truth-checks are filled with matching numbers or the mismatch is noted. npm run build zero errors; architecture tests pass.
M1-03 | M1-P1 | Defect buffer: fix everything the pass surfaced | Critical | defect fix | Both | 6 | Reserved capacity. Feed the [X] and mismatch list from M1-02 back and each becomes a targeted apply pack. Expected small items based on known risks: associative fields showing n/a (rename the dimensionCode in Frontend\PlantProcess.Web\src\state\associativeFields.ts to the registry name), findings page empty while SQL says 320 (the API session tenant does not match ppiq_current_tenant() - fix the tenant claim or the session GUC the API sets), a widget dimension missing from src\state\widgetSelectionMap.ts, dry-run column-name mismatch in VisualMapperEndpoints.cs against script 540. | Re-run only the failed checklist lines (not the whole pass): all previously-[X] lines now grade [P] or are removed from the demo path. Gates green. Commit per fix with the checklist line named in the message.
M1-04 | M1-P1 | IMPRESS: live readiness-gate panel - make the honest engine visible | High | feature | Claude | 8 | The engine refuses to compute when data cannot support an answer, but that refusal is invisible - a text message only. Build a GateReadinessPanel that shows it as instrumentation. Backend already exposes it: GET /analytics/advanced/readiness/gates?outcomeKey=&grain=&windowDays= (client fn getAnalysisReadinessGates in Frontend\PlantProcess.Web\src\api\advancedAnalysis.ts returns readyCount/partialCount/blockedCount + gates[]). Create src\components\analysis\GateReadinessPanel.tsx: one row per gate dimension with a horizontal bar (CSS width classes bucketed 0-10, NO inline styles - the UI ratchet forbids style={{}}), status chip READY (green #2ce6a2) / PARTIAL (amber) / BLOCKED (ember), and the verdict sentence with the run id when blocked. Use StandardP2* primitives only. Mount it on the analysis/statistics page above the run button, refreshing when outcome/grain/window change. Deliver as an apply pack gated by tsc -b + architecture tests. | Open the analysis page: the panel renders one bar per gate dimension with live numbers from the endpoint. Change the outcome -> the panel refetches. When the engine blocks, the panel shows which dimension blocked and the message with a run id - the demo sentence "watch it refuse" now has a picture. Gates green; no inline styles (npm test architecture suite passes).
M1-05 | M1-P1 | IMPRESS: finding -> genealogy thread jump | High | feature | Claude | 6 | Close the story loop: a correlation finding about a material should jump straight into the genealogy walk. On the findings page (component that lists ml_correlation_results_v2 rows via AdvancedResultsEndpoints), make each row clickable: navigate to the existing genealogy search route with the query prefilled (inspect the genealogy page for its URL pattern - it reads a search param such as ?q= or ?materialCode=; reuse exactly what exists, do not invent a new route). If the finding carries a feature_key like process.superheat_c, show it as a subtitle on the genealogy header via location state so the presenter can say "this defect, this coil, this upstream cause". Keyboard accessible (row is a StandardP2Button or has role=link). | Click any finding row -> the genealogy page opens with the search prefilled and results shown; back button returns to findings with scroll position intact. One rehearsed sentence exists for the demo: finding -> click -> lineage on screen in under 5 seconds. Gates green.
M1-06 | M1-P1 | IMPRESS: true XY scatter - parameter vs outcome point cloud | High | feature | Claude | 10 | The current scatter is category-vs-measure. Build the real thing for the statistics page: pick parameter X and outcome/parameter Y, see the point cloud at coil grain. Backend: new endpoint GET /analytics/advanced/scatter?xKey=&yKey=&grain=&windowDays=&limit= in Backend\PlantProcess.Api\Endpoints\Analytics\ (new file, follow AdvancedResultsEndpoints.cs for auth/tenant pattern), reading the ml feature store: join the feature values for xKey and yKey per material unit, LIMIT default 2000, both keys validated against the existing feature catalog (reject unknown keys with a 400 listing valid keys - never free-text SQL). Add the route prefix to PlantAccessControl.cs next to the /analytics anchors (the committed M1-22 pattern). Frontend: src\components\analysis\XyScatter.tsx using recharts ScatterChart with numeric X and Y axes, density-friendly dot size, a fitted trend line (simple least squares computed client-side), and axis pickers (StandardP2Select) fed from the feature catalog endpoint. Mount on the statistics page next to the M1-04 panel. | Pick superheat_c as X and a defect outcome as Y: a genuine point cloud renders with a trend line; swapping keys refetches; an unknown key returns the 400 with valid keys (shows the safety story). psql spot-check: the number of points equals the endpoint limit or the join row count. dotnet build + tsc -b + architecture tests green.
M1-07 | M1-P1 | IMPRESS: canvas layer 2 - Filter and Derive nodes | High | feature | Claude | 10 | Extend the visual join canvas beyond the happy path so the live authoring act shows real transformation. Frontend (Frontend\PlantProcess.Web\src\canvas\): add two BlockNode kinds to the palette of VisualJoinCanvasPage - FILTER (fields: column picker fed from the connected dataset node, operator select limited to = <> < > >= <= LIKE, value input) and DERIVE (fields: new column name, expression built from a numeric column picker + operator + - * / + second column-or-constant; no free text SQL). The graph payload gains filters[] and derived[] arrays. Backend (VisualMapperEndpoints.cs BuildSafeSelect): apply filters as parameterised WHERE predicates (values ALWAYS as Npgsql parameters, never concatenated; operators from a whitelist; columns validated against the dataset catalog) and derived columns as safe SELECT expressions from the same whitelist. Reject anything outside the whitelist with a recorded rejected_by_safe_sql dry-run row - the same honest refusal the product shows everywhere. | On /prep/canvas: wire two tables, add a FILTER (e.g. superheat_c > 30) -> Preview row count drops accordingly (verify with a psql count using the same predicate); add a DERIVE (e.g. width_mm * thickness_mm) -> the preview shows the new column with correct values; type an operator outside the whitelist is impossible in the UI, and a hand-crafted bad payload via the API returns the safe-sql rejection. Publish still produces a version row containing filters and derived in mapping_definition. All gates green.
M1-08 | M1-P1 | IMPRESS: associative tri-state inside the real filter dropdowns | High | feature | Claude | 6 | The associative panel proves the engine; now put the same green-white-grey inside the filter bar users already touch. Locate the global filter bar component (search Frontend\PlantProcess.Web\src for the component rendering the workspace filter selects - it consumes useDashboardFilters). For each dropdown whose field exists in src\state\associativeFields.ts, read the value states from AssociativeContext (the provider already mounts on the workspace page; expose a useAssociativeStates(fieldKey) helper that returns the Map or null when the provider is absent) and style options: selected green, possible normal, excluded greyed with a struck style - excluded stays selectable (Qlik pivot semantics). Native <option> styling is limited: acceptable v1 is a text prefix for excluded options plus CSS color where the browser honours it; do NOT replace the select with a custom widget in this task. Behind the same panel toggle. | With one material selected, open the Defect dropdown: impossible defects are visibly de-emphasised (colour and/or prefix), possible ones normal; picking an excluded value pivots the selection exactly like the panel chips. Toggling the associative view off restores plain dropdowns. Architecture tests still green (no raw controls added - the existing selects are inside the filter bar component already counted in the baseline; you are only adding classes/props).
M1-09 | M1-P1 | IMPRESS: risk heat map beat on the Risk workspace | Medium | feature | Both | 4 | Give the "prediction" story a visual anchor using shipped machinery only: on the RISK_INTELLIGENCE workspace add one saved widget configured as chartType=heatmap, dimensionCode=riskClass (or equipment if riskClass renders thin), measureCode=riskScore, titled "Risk intensity by class". Create it through the existing widget-builder UI (no code) so it persists as a definition row; the M2-38 heatmap renderer and the M2-43 selection map do the rest - clicking a hot cell filters the workspace by that risk class. Claude supplies the exact builder field values; Karim clicks them in. | The Risk workspace shows the heat grid with visible intensity differences; clicking the hottest cell filters every widget on the page and the associative panel re-shades; the widget survives reload. One demo sentence written: "the intensity you see is computed risk - click it and the whole floor follows".
M1-10 | M1-P1 | Deck upgrade: replace Design badges with live screenshots | High | content | Karim | 4 | The v26 deck carried three vision slides badged "Pilot Milestone - Design" for canvas, associative and catalogue. All three are now real. Rebuild those slides with screenshots from the M1-02 certified pass: the join canvas with a wired cross-source join and a preview table; the associative panel mid-selection (green/white/grey visible); a pareto + heatmap pair on a workspace. Keep the badge ONLY on anything still design-stage (none expected). Re-run the honesty-lint: every claim slide names a run id, batch id or screenshot; no metric without its evidence beside it. Add one new slide "The honest engine" using the M1-04 gate panel screenshot. | Deck walk matches the rehearsal order exactly; the three former vision slides show real product screenshots dated from the certified pass; honesty-lint green (zero claims without evidence artifacts); the gate-panel slide present.
M1-11 | M1-P1 | Dress rehearsal x2 with contingency card, then phase push | Critical | execution | Karim | 4 | Run the full meeting script twice, timed, on the presentation database: opening frame -> disclosure sentence -> connections -> live registration -> genealogy walk -> workspaces (drag, cross-filter, associative selection, pareto/heatmap switch) -> canvas live join with filter node -> findings -> click-through to genealogy (M1-05) -> gate panel + honest-abstain sentence -> assistant cited answer -> close. Target under 40 minutes. Contingency card: one line per step for source-down / API-down / widget-dead ("the same honesty you get in production" family). No code changes after run 2. Then the phase push: git add -A, commit "M1-P1 demo lock", push to the server. | Two timed runs logged under 40 minutes each; run 2 shows zero red banners; the contingency card exists with a line per step; the push is on the server and a fresh clone builds green (tsc -b, architecture tests, dotnet build).
|  | PHASE TOTAL |  |  |  | 63

## M2 Board
ID | Phase | Task | Priority | Type | Owner | Est h | Description (junior-ready) | Validation / acceptance (junior-ready)
M2-P1 |  | WORKING VERSION CORE - 60h. Ends with: users/licensing live, engine completing runs with a citable metric, spec-A backend complete, journey green end-to-end. Push at end.
M2-01 | M2-P1 | Users, roles and licensing administration | Critical | feature | Claude | 14 | The product runs on one bootstrap admin. Build the admin surface for real installs. Backend: the auth model already carries users/permissions (PlantAccessControl.cs consumes permission strings such as analysis.execute); add endpoints under /api/admin/users for list/create/deactivate/reset-password and role assignment from a fixed role catalog (Admin, Engineer, Viewer) mapping to the existing permission strings; add a licenses table (seats, expiry, plan) with a middleware check that returns 402-style honest messaging when exceeded. Frontend: an Admin > Users page (StandardP2Table + forms) and a Licence card showing seats used/total and expiry. Everything deny-by-default: new routes into the PlantAccessControl matrix with an admin.users permission. | Create a Viewer user via the UI, log in as them: analysis run button is absent/disabled and POST /ml/foundation/compute/correlation returns 403; the Admin page is invisible to them. Licence card shows correct counts; setting seats below current users shows the honest limit message without breaking login. Gates green; matrix change committed.
M2-02 | M2-P1 | Engine ceiling: from honest-abstain to completed runs with a citable metric | Critical | engine | Both | 10 | Lineage: the engine currently blocks inside AdvancedCorrelationComputeService even at 100% completeness; the reasons are discarded at the DTO (NpgsqlAdvancedResultWriter.cs line ~40 keeps only the message). Step 1 (Karim, 15 min): run one compute with the API console visible and paste the AdvancedCorrelationComputeService verdict lines - that names the internal wall. Step 2 (Claude): fix that specific gate cause (expected: a per-window sample rule or an outcome-class threshold reading the pre-742 grain) as a product-code fix with a migration if data-shaped. Step 3: surface the full reason list in the DTO instead of message-only (add reasons[] to the result payload and show them in the M1-04 panel). Step 4: with completed runs, compute the citable headline (the historical 9.3x class ratio) fresh, and store the run id beside it - the deck may only use the number with that run id printed. | A governed run reaches status Completed on the presentation database; findings gain new rows (results count rises above 320); the gate panel shows all dimensions green for that run; the citable metric exists as number + run id in the deck notes. The blocked path still works (prove by shrinking windowDays until it refuses).
M2-03 | M2-P1 | Spec-A backend completion: mappings, templates, business keys full CRUD | High | backend | Claude | 12 | Script 540 created the artifact tables; the canvas uses sessions/dry-runs/versions. Complete the HTTP surface for the rest so the prep builder matches the Part-A spec: endpoints for template save/load (a reusable graph without data), business-key designation per dataset (which columns identify a row - feeds join suggestions), canonical-target column mapping (dataset column -> canonical entity field, validated against the canonical schema catalog), and version lifecycle transitions validate -> publish -> rollback (rolled_back_from_version_id is already in the table). All under /api/prep/visual-mapper (already in the access matrix). Extend the canvas UI: a right-panel Mapping tab listing canonical fields with source-column pickers, and a Versions tab with the lifecycle buttons. | Author a mapping on the canvas: designate business keys, map three columns to canonical fields, validate, publish, then roll back to the previous version - each transition visible in ppiq_visual_mapper_versions with correct statuses. Saving a template and instantiating it on new tables reproduces the graph. Gates green.
M2-04 | M2-P1 | Journey rail: every step green on the working version | High | validation | Both | 8 | The 15-step rail must report a genuinely green journey without faked steps. Walk each step against its real backing signal, fix the step detectors that read stale sources (several read counts that moved during the M1/M2 work), and where a step is legitimately not yet exercised on a fresh install, the rail shows the honest pending state rather than red. Claude patches detectors as packs; Karim walks and confirms each lamp. | On the presentation database every rail step is green; on a FRESH empty database the rail shows pending (not red, not fake-green) for unexercised steps. Screenshot both states for the deck appendix.
M2-05 | M2-P1 | Alerting productization + supervisor v1 loop | Medium | feature | Claude | 10 | Two closing pieces of the intelligence loop. Alerting: rule CRUD exists on AlertingPage; add scheduled evaluation (a hosted background service running rules every N minutes writing plant_data_log rows) with per-rule enable/disable and last-run status shown in the UI. Supervisor: v1 of the weekly loop - a job that reads the latest findings, writes one ml_knowledge_base_items row summarising them (top finding, effect, run id), and renders it on the Supervisor page - replacing the empty state with the first real report. No fabricated content: if there are no findings, the report says so. | Create two rules, wait one scheduler cycle (or trigger manually): plant_data_log gains rows and the alert list renders them with timestamps; disabling a rule stops it. The Supervisor page shows a real generated report row citing an actual run id; on an empty findings set it shows the honest none-yet report. Gates green.
M2-06 | M2-P1 | Phase push + regression pass | Critical | execution | Karim | 6 | Close the phase: run the consolidated checklist Parts 2-6 once against the new features (users, engine-completed run, mapping lifecycle, journey, alerting/supervisor), fix-or-note, then git add -A; commit "M2-P1 working version core"; push. Verify a clean clone builds. | Checklist delta graded with zero [X]; push on the server; fresh clone: npm ci + npx tsc -b + npm test + dotnet build all green.
0
M2-P2 |  | ENTERPRISE & INFRASTRUCTURE - 56h. Ends with: containerized deploy from CI, config hygiene done, security hardening verified. Push at end.
M2-07 | M2-P2 | CI truth gates: tests execute, never enumerate | Critical | infra | Claude | 8 | Lineage: the audit found frontend test scripts using --list (enumeration, not execution) in package.json (phase9:matrix) and tools/ci/validate-real-ui-gates.cjs. Replace every --list invocation with real execution in CI profile, wire vitest + the playwright smoke set into the Jenkins pipeline stages, and make CiPipelineTruthGateTests actually fail the build when a catchError/SUCCESS pattern or --list reappears (extend its regexes to scan the pipeline files). Document expected runtimes so slow suites are split, not skipped. | Jenkins run shows real test execution counts (N passed) for unit, architecture and smoke stages; deliberately breaking one architecture rule in a branch fails the pipeline; grep for "-- --list" across the repo returns only the truth-gate test itself. Committed.
M2-08 | M2-P2 | Config hygiene: no hardcoded server, no bootstrap admin in shipped profiles | Critical | infra | Claude | 8 | Lineage: audit found 15 hardcoded references to the staging IP 178.105.152.180 across deploy scripts/docs and IsBootstrapAdmin=true in local.env AND presentation.env. Parameterise: one PPIQ_PUBLIC_HOST variable consumed by post-deploy-smoke.sh, ensure-runtime-env.sh, verify-server-exposure.sh, Invoke-CleanMachineDeployAcceptance.ps1 and the docs (docs keep ONE example value clearly marked as example). Bootstrap admin: allowed only in local.env; presentation and any customer profile get it false with a first-run admin-creation path (reuse M2-01 users endpoint + a one-time setup token printed to the server log). | grep for the IP returns only the single documented example line; starting the API with the presentation profile has no bootstrap admin and the first-run setup flow creates the initial admin; clean-machine acceptance script runs against a host passed as a parameter. Committed.
M2-09 | M2-P2 | Docker + Jenkins + cloud deployment path | Critical | infra | Both | 18 | Make the deploy reproducible: docker-compose for api + frontend + postgres with named volumes and healthchecks; the database initialised by the rebuild script chain (including the [1b] engine-migration step) on first boot; Jenkins pipeline stages build -> test (M2-07 gates) -> image build -> push -> deploy to the server -> post-deploy smoke (parameterised host from M2-08). Secrets via environment, never in the repo. Karim provides server access and runs the first supervised deploy; Claude delivers compose files, Jenkinsfile changes and runbooks as packs. | From a clean server: one pipeline run produces a reachable app over https, the smoke script passes, and the journey rail shows the honest fresh-install pending states. A second run is idempotent. Runbook exists covering rollback (previous image tag).
M2-10 | M2-P2 | Security hardening pass | High | security | Claude | 10 | Verify and close the audit WARNs: dev-seed endpoints must be dev-only (the ProductionDevEndpointGuardTests pattern exists - run it against a Release build artifact and add a runtime assert that MapDevSeedEndpoints throws outside Development); RLS audit across all tenant tables (list every table with tenant_id, confirm ENABLE+FORCE and a policy equal to the ml_correlation pattern, add missing ones as a migration); auth token lifetime + refresh review; rate limiting on auth endpoints; dependency audit (npm audit + dotnet list package --vulnerable) with fixes or documented acceptances. | Release build refuses to map dev-seed (test proves it); an RLS report table in the log shows every tenant table policied; npm/dotnet audits show zero criticals or a signed-off exception list; auth endpoints rate-limited (429 on a burst test). Committed.
M2-11 | M2-P2 | Website production deploy + real contact wiring | Medium | infra | Both | 6 | Ship the enhanced site: build the Website app, containerize alongside the product (or static-host), wire the RequestDemoForm to a real destination (mail relay or a stored-lead endpoint with email notification), replace the placeholder contact@sou-industrial.com with the real address everywhere (grep to verify), add basic privacy-respecting analytics, and confirm the no-negative-content rule on final copy. | The site is reachable on the public host over https; submitting the demo form delivers a message to the real inbox; grep finds zero placeholder addresses; Lighthouse >= 90 on performance and accessibility; final copy shows zero unfinished/blocker language.
M2-12 | M2-P2 | Phase push + clean-machine acceptance | Critical | execution | Karim | 6 | Close the phase with the deploy proof: run the clean-machine acceptance against the parameterised host, capture the report, push the trunk. | Acceptance report saved with all checks green; push on the server; the deployed instance is the one the acceptance ran against.
0
M2-P3 |  | CATALOGUE & CANVAS COMPLETION - 49h. Ends with: full chart catalogue, canvas at spec, associative optimised. Push at end.
M2-13 | M2-P3 | Full chart catalogue: box plot, gauge, waterfall, combo | High | feature | Claude | 14 | Complete the Part-B S2 list on the ChartExtras foundation: BOX PLOT (needs quartiles - add a stats mode to the widget query or a dedicated /analytics/dashboard/widgets/box endpoint computing min/p25/median/p75/max per dimension server-side), GAUGE (single-value vs target bands, StandardP2 + SVG arcs with CSS classes), WATERFALL (signed contributions from a dimension query), COMBO (bar + line dual measure - requires the query to accept secondaryMeasureCode; extend the DTO + validation service + registry compat rules). Each type: registry entry, switcher availability rule, selection contract via the M2-43 map, and the same conformance discipline (no inline styles - bucket everything). | Each new type renders from a saved definition, responds to clicks per its dimension, respects the safety registry (incompatible measures absent from the switcher), and persists after reload. Box-plot numbers match a psql percentile_cont spot-check. All gates green.
M2-14 | M2-P3 | Canvas at spec: SQL-mode toggle, templates UI, mockup-parity review | High | feature | Claude | 12 | Finish spec-A S16: an SQL tab on the canvas showing the exact server-built SELECT for the current graph (read-only display first; an advanced editable mode may only submit through the safe-sql validator and records rejections honestly), the templates gallery (list/instantiate/delete from M2-03 endpoints), keyboard and touch polish (delete edge, duplicate node, fit view), and a side-by-side review of the shipped canvas against the three M1-15 mockups - divergences listed and either fixed or accepted in writing. | The SQL tab shows the same query the dry-run executed (byte-compare against the recorded dry-run SQL); an intentionally dangerous edited SQL is rejected and recorded; templates round-trip; the mockup-parity list exists with every divergence dispositioned. Gates green.
M2-15 | M2-P3 | Associative engine optimisation: one-call state endpoint | Medium | performance | Claude | 10 | The panel currently fires one widget-query per field per change (8 calls). Build POST /analytics/dashboard/associative/state accepting the current filters and returning all fields possible-sets + counts in one round trip (server loops the same registry-validated query internals; no new SQL surface), with an ETag/hash so unchanged states return 304. Swap AssociativeContext to the single call with the per-field fallback kept behind a flag. Target: full re-shade under 300 ms on the presentation dataset. | Network tab shows ONE state call per selection change; re-shade completes under 300 ms (measure with the Performance panel, record the number); repeating the same selection returns 304; the fallback flag still works. Gates green.
M2-16 | M2-P3 | Drilldown everywhere + saved investigation trails | Medium | feature | Claude | 8 | Extend the M2-43 drawer: from any drilldown, "pin" the payload to an investigation trail (a per-user list persisted via a small endpoint) so a demo or a real root-cause session can retrace its steps; render the trail as a breadcrumb rail with jump-back. Add drilldown support to the new chart types from M2-13. | Pin three drilldowns across different widgets, reload, reopen the trail: all three restore and jump back to their filter states. New chart types open the drawer. Gates green.
M2-17 | M2-P3 | Phase push | Critical | execution | Karim | 5 | Consolidated delta pass over M2-P3 features, fix-or-note, push. | Delta checklist zero [X]; push on the server; clean clone green.

## M3 Board
ID | Phase | Task | Priority | Type | Owner | Est h | Description (junior-ready) | Validation / acceptance (junior-ready)
M3-P1 |  | MARKET PROOF - 44h. Ends with: second-industry proof, pilot kit, case study. Push at end.
M3-01 | M3-P1 | Second-industry proof on the generic core | Critical | proof | Both | 20 | Prove industry-agnostic beyond steel: pick a second vertical (aluminium or paper are closest structurally), source or emulate a realistic dataset (Claude generates the emulated multi-source set exactly like the steel one: 3-4 source systems, genealogy, parameters, quality events), register it through the product ONLY via the UI/DB-link path (no hand-loading - the point is the generic ETL), run the engine, and capture the findings. Zero schema hardcoding may be touched; any place the core assumes steel becomes a defect with its own fix task. | A second tenant/database shows the full journey green on the new industry; at least one completed correlation finding exists with its run id; a written list of any steel-assumptions found (target: zero code changes needed); screenshots for sales material.
M3-02 | M3-P1 | Pilot onboarding kit | High | content | Claude | 12 | Everything a new plant needs for week one: prerequisites checklist (network, read-only DB accounts, server sizing), the connector setup guide per source type (Oracle, SQL Server, MySQL, PostgreSQL, REST, files) with screenshots from the real UI, the security one-pager for their IT/OT (read-only enforcement, RLS, on-prem), and the day-1 to day-14 pilot plan template with the acceptance metrics agreed up front. | A colleague who has never seen the product follows the kit against a fresh deploy and reaches first imported data without asking a question; the security one-pager answers the standard IT objections; the pilot plan template has measurable acceptance criteria fields.
M3-03 | M3-P1 | Case study + evidence-grade sales material | High | content | Both | 12 | Turn the emulated-plant journey into the sales narrative: a written case study (problem -> connection -> genealogy -> finding -> value) where every number carries its run id or screenshot, a 3-minute screen recording of the certified demo path, and the ROI worked example using the calculator with the case-study numbers. All material follows the website rule: no blockers, no unfinished language, benefit-led. | Case study PDF with every claim evidenced; the recording plays the certified path without cuts hiding failures; the ROI example reproduces in the public calculator. Reviewed against the no-negative-content rule line by line.