## Backlog
PPIQ PRODUCT BACKLOG v22 - fresh IDs, standalone (12-Jul-2026). M1=presentation (every journey step showable + website/slides, 16-Jul). M2=hardening (rules.txt 100%). M3=post-customer-comments.
ID | Milestone | Phase | Group | Task Name | Severity | Type | Module | Description | Validation | Est (h) | Origin
M1-01 | M1 | M1-P1 | G2 Assistant | Assistant answers for real: CanonicalChunkProducer + POST /api/assistant/reindex | Critical | new feature | Backend | Journey step 15 must SHOW an answer. Build chunk producer (DATASET chunks from SourceDatasetDefinitions/mappings/connectors; DOC chunks from honesty contract; FINDING chunks from ml_correlation_results_v2), register AssistantRetrievalIndexBuildService inside AddAssistant(), add POST /api/assistant/reindex in the same MapGroup (inherits auth+matrix). ReindexAsync owns its connection (no ambient EF scope); never refresh from /ask; no synthetic chunks. | reindex -> 200, chunkCount>=20. Ask 'which source tables are registered?' -> isRefusal=false, >=1 citation resolving to a real row. Predictive question -> refusal. Viewer sees no engineer-scoped chunk. | 10 | CARRIED v21 M1-09
M1-02 | M1 | M1-P1 | G12 UX | Jobs Monitor shows all four journey job types honestly | Critical | modification | Frontend+Backend | Steps 2/5/9/12 need visible schedule+monitor. Surface the Arch-A schedule board (source-schedule-board) beside loading (projector runs), analysis (governed runs) and AI+ML, each with last-run/outcome/duration/rows. Honest empty states; zero fabricated status. | All four types visible in one monitor with real last-run data; a dataset registered via Surface-1 appears within one worker tick. | 3 | CARRIED v21 M1-10
M1-03 | M1 | M1-P1 | G1 Import | Taxonomy is imported plant data: DefectCatalog + ParameterDefinition projector targets | Critical | new feature | Backend | Clarified Rule 2: defect/parameter taxonomy arrives via DB-link, never hand-inserted. Add MapDefectCatalogAsync (code-keyed upsert) + MapParameterDefinitionAsync + two MapOneRowAsync router cases. Rig gains meltshop_defect_definitions + meltshop_param_definitions; import them FIRST (resolvers need them). | Fresh DB: register+map+import definition tables -> defect_catalogs/parameter_definitions populated with source_system=postgresql; then observations+QEs project clean. Zero PPIQ_CONFIG rows remain. | 3 | NEW audit A1-C2/A3-C2
M1-04 | M1 | M1-P1 | G10 Surface-1 | Step-4 demo path: data-prep UI authors a MappingDefinition the projector consumes | Critical | new feature | Frontend+Backend | M1-14 finding: the mapping panel drives canonical_schema_views, not the projector. Presentation needs the user to CLICK step 4. Minimal honest form in Data Integration: pick import batch -> pick target entity -> field map grid (source column or const:) -> Save creates MappingDefinition -> Execute projects. No visual polish (M2/M3). | In the HMI only: author mapping for a staged object -> mapping_definitions row created THROUGH the UI -> execute -> canonical rows grow, staging flips Mapped. | 6 | NEW audit A9-C2 (M1-14 wiring)
M1-05 | M1 | M1-P1 | G3 Engine | Supervisor job v0 (step 14, honest minimal): weekly job that writes a real revision report | Very important | new feature | Backend | Step 14 must be presentable WITHOUT fabrication. v0 = a real scheduled job (weekly) that reads ml_correlation_results_v2 + job history and writes a supervisor_report row (findings count, drift notes, recommended window changes) to the KB (ppiq_ml_upsert_kb_item). Full self-tuning engine stays M2 keystone. | Job visible in Jobs Monitor with schedule; manual trigger writes one real report row; report renders on a simple page. Nothing claims auto-tuning. | 4 | NEW audit A10-C4/step-14
M1-06 | M1 | M1-P1 | G12 UX | 4th low-code UI v0: plant-data-log / threshold alerting (demo-grade) | Very important | new feature | Frontend+Backend | Audit A9-C1: the 4th journey UI is absent entirely. v0 = alert_rules table (parameter_code, comparator, limit, severity), evaluation job that scans new parameter_observations and writes plant_data_log rows, plus a log page with rule-create form. Routing/chemistry rule types + email/webhook delivery = M2. | Create a rule (e.g. thermal.true_superheat > 36) in the UI -> next evaluation run writes log rows for the rigged high-superheat heats -> log page shows them with rule+material+value. | 6 | NEW audit A9-C1
M1-07 | M1 | M1-P1 | G16 Demo | Arch-B frontend removal (Two-Stage page, client, route, nav, types) | Very important | cleanup | Frontend | Backend unreachable since C.1a; remove the orphaned surface so no screen-share shows dead Architecture-B UI: TwoStageImportMonitorPanel(+implementation), twoStageImport.api.ts, route, nav entry, type exports, productApiClient method. Vite build gate. | npm build green; no route/nav mentions two-stage; grep clean in src. | 1.5 | CARRIED C.1b
M1-08 | M1 | M1-P1 | G0 Runtime | DB snapshot, C.2 purge, full re-import (taxonomy first), clean engine re-run | Critical | data ops | Backend | Sequence is fixed: snapshot ppiq_app -> purge seed/ladder data (38,346 units, 35,906 edges, PPIQ_CONFIG rows, demo site rename), drop src_* schemas + stage1/2 functions + retire 204 generator feed -> re-import EVERYTHING via DB-link (definitions -> readings -> defects; other sources as time allows) -> re-run M1-08 pristine. Purge writes an audit record of what it removed. | material_units contains ONLY source_system=postgresql rows; feature refresh reads zero demo rows; governed run rediscovers superheat->defect with q<0.01 on purely imported data; snapshot restorable. | 4 | CARRIED C.2 + audit A7
M1-09 | M1 | M1-P1 | G3 Engine | Finding read hygiene: latest-run view + odds ratio + population surfaced | Very important | modification | Backend | Audit A3-C3/A10-R1: results_v2 shows duplicate rows across runs; deck needs 9.5x. Add latest-run-per-job read view (dedup) and extend the finding payload with odds_ratio + population counts beside effect/q. | Finding list shows one row per feature/outcome (latest run); superheat finding displays OR~9.5 with q-value. | 2 | NEW audit A10-R1/R3
M1-10 | M1 | M1-P1 | G12 UX | Production error shape: stop leaking LINQ trees / stack traces to clients | Very important | bug fix | Backend | Seen twice live: 500s return full EF expression trees + stack traces. Map exceptions to {title,errorCode,traceId} in non-dev; details stay in logs. | Force a 500 -> client body contains no namespaces/stack frames; traceId matches log entry. | 1.5 | NEW audit A9-R5
M1-11 | M1 | M1-P2 | G16 Demo | Consolidated HMI walk: 9-surface check + full 15-step journey click-through | Critical | verification | Testing | First human browser pass (old M1-02 + M1-14 S1/S2/S3 merged): 9-row 09-Jul checklist PLUS one end-to-end journey walk (connect -> register -> import -> map(UI) -> load -> widget bind -> analysis -> finding -> alert log -> assistant answer). Screenshot per step. | Checklist committed under docs/, every row PASS with dated screenshot; any FAIL becomes a numbered bug BEFORE rehearsal. | 3 | CARRIED M1-02+M1-14 (merged)
M1-12 | M1 | M1-P2 | G0 Runtime | Demo continuity: archive loadA.sql.gz + loader off-laptop; registry truth queries | Critical | verification | Tooling | Untracked master dataset on one laptop. Archive both files durably (record location); paste git ls-files proof + the two source_table_dump_registry queries. | Archive location recorded in session log; both outputs pasted. | 0.5 | CARRIED v21 M1-04
M1-13 | M1 | M1-P2 | G0 Runtime | ppiq.ps1 API readiness poll (5063) | Nice to have | modification | Tooling | Two-anchor pack: poll /health until listening instead of fixed sleep. | ppiq.ps1 start waits for 200 then proceeds. | 0.5 | CARRIED v21 M1-11
M1-14 | M1 | M1-P2 | G16 Demo | Dress rehearsal: full journey on the purged, imported-only plant | Critical | verification | Testing | Run the exact 16-Jul script twice end-to-end on the post-C.2 state, timed, with fallback notes per step (source-down / API-down contingency). | Two clean timed runs; contingency sheet exists; no step depends on unpurged data. | 3 | CARRIED v21 M1-12
M1-15 | M1 | M1-P2 | G6 Docs | Website + slide deck updated to the proven story | Critical | content | Website | Money slide: organic discovery (effect 0.924, q=0.0001, OR~9.5, honest null control). Publish the Three Product Rules; 'grounded assistant' wording (no LLM claim); supervisor = roadmap framing; taxonomy-imports-too story. | Deck walk matches what the rehearsal actually shows; honesty-lint green; website carries rules + discovery. | 4 | CARRIED v21 M1-13 + audit A6
M1-16 | M1 | M1-P2 | G10 Surface-1 | Register page final step: explicit job binding (from-mapping + schedule-now) | Nice to have | modification | Frontend | Small M1-05b remainder: wire the page's final step to import-jobs/from-mapping + schedule-now so step 2 is clickable (register already schedules implicitly). | Clicking finish shows the scheduled job and next-run time. | 1 | CARRIED M1-05b
M1-17 | M1 | M1-P1 | G12 UX | Journey progress affordance: in-product 'step X of 15' guide | Very important | new feature | Frontend | Audit A9-C4: each surface is competent in isolation but nothing tells the user where they are in the 15-step journey or what is next. Add a persistent, lightweight journey rail/breadcrumb (Connect -> Schedule -> Import -> Prepare -> Load -> Dashboards -> Analysis -> Findings -> Alerts -> Assistant) that highlights the current step and links to the next action. Demo-critical for a JOURNEY pitch; read-only reflection of state, no backend logic beyond 'what exists so far'. | A new user with no verbal guidance can reach step 10 by following the in-product affordance; current step is visually indicated on every journey surface. | 2 | NEW audit A9-C4
M2-01 | M2 | M2-P1 | G3 Engine | Supervisor engine (step 14 keystone): jobs improve each other + weekly deep revision | Critical | new feature | Backend | Full implementation with guardrails: may tune job configs/feature windows/thresholds; must NEVER weaken readiness gates, refusal logic or evidence; every adjustment logged before/after with justification; consumes KB + results_v2 + job telemetry; feeds adjusted configs back to analysis/ML jobs. | After two supervised cycles, at least one job config adjusted with logged justification and measurably improved metric; gate-weakening attempt is impossible by construction (test). | 16 | NEW keystone (audit A10-C4)
M2-02 | M2 | M2-P1 | G2 Assistant | Real LLM binding behind IAssistantModel (on-prem Ollama + optional hosted) | Critical | new feature | Backend | Swap-in implementations beside ExtractiveAssistantModel; config-selected per install; answers remain retrieval-grounded + cited; refusal-first preserved; assistant reads engine via existing tools and writes NOTHING except audit log. | Same eval set answered by both models; citations still resolve; predictive questions still refuse; latency budget documented. | 10 | NEW audit A10-C1
M2-03 | M2 | M2-P1 | G0 Runtime | Bounded-parallelism job executor (100+ jobs) | Critical | architecture | Backend | Channel<JobRequest> + N consumers; per-class pools (import/analysis/ML); statement timeouts + per-class work_mem; NOTIFY wakeups; job telemetry (duration/rows) persisted. | 100 defined jobs across classes complete a full cycle with bounded drift; no pool exhaustion; telemetry populated. | 12 | NEW audit A10-C5/A11
M2-04 | M2 | M2-P1 | G3 Engine | Statistics method registry: Spearman, chi-square, ANOVA/Mann-Whitney + Surface-3 picker | Critical | new feature | Backend+Frontend | Beyond basic Pearson: registry of methods with applicability rules (numeric-numeric, categorical, groups); Surface-3 lets the user pick; all results keep q-value discipline. | Each method produces a verified result on the rigged set (chi-square finds a planted categorical driver; Spearman survives injected outliers). | 10 | NEW audit A10-C2
M2-05 | M2 | M2-P1 | G10 Surface-1 | Step-4 full no-code data preparation (per-view Loading jobs + prep/load unification) | Critical | new feature | Frontend+Backend | Productize the demo path: visual field-map editor, filters/linking/grouping, SchemaView->MappingDefinition relationship decided and implemented, per-view Loading jobs auto-created (old M2-04), monitorable. | A non-developer maps a NEW source to canonical entirely in the HMI incl. schedule; journey steps 4-6 clickable start to end. | 12 | CARRIED M2-04 + M1-14 outcome
M2-06 | M2 | M2-P1 | G12 UX | 4th UI complete: routing-deviation + chemistry-range rules, email/webhook delivery | Critical | new feature | Frontend+Backend | Extend v0: rule types (threshold/routing deviation vs genealogy expectations/chemistry range vs expected_min_max), delivery channels, ack workflow, rule audit. | Each rule type fires on a crafted case; email+webhook delivered; ack recorded. | 12 | NEW audit A9-C1 full
M2-07 | M2 | M2-P2 | G1 Import | Range validation on ingest (expected_min/max) + time-series observation support | Very important | modification | Backend | Validate observations against parameter_definitions ranges (typed warning, not silent); prove multi-reading-per-unit time series through the pipeline; partition strategy ready (below). | Out-of-range reading produces a visible data-quality issue; 10-readings/heat series imports+projects+correlates. | 5 | NEW audit A3-R3/R4
M2-08 | M2 | M2-P2 | G0 Runtime | Scale foundations: partition observations/features (monthly+BRIN), incremental feature refresh, PgBouncer, restore drill | Critical | architecture | Backend | Pre-pilot infra musts from sizing model v1: declarative partitions, refresh becomes per-batch incremental, PgBouncer transaction mode, one full backup-restore drill documented. | Medium-profile synthetic load (7.5M obs) refreshes incrementally in bounded time; restore drill signed off. | 10 | NEW audit A11-C1..C4
M2-09 | M2 | M2-P2 | G14 Security | Roles/users vs journey: role catalog, named policies, MFA verify, SCIM finish-or-fence, user mgmt UX | Critical | modification | Backend+Frontend | Replace '?? viewer' fallback + literals with a role catalog; verify MFA enrolment; finish or fence SSO/SCIM (CS0162); user create/assign flows match journey. | Role matrix documented+tested per surface; MFA walk recorded; SCIM either passing tests or disabled with a flag. | 8 | NEW audit A2-R1/R2/R5
M2-10 | M2 | M2-P2 | G14 Security | Licensing production-grade: tier->feature matrix, production Ed25519 keypair, gated-endpoint tests | Critical | modification | Backend | Document Standard/Pro Plus/Enterprise -> LicenseFeature codes; rotate off dev keypair (Option 3); test one gated endpoint per tier incl. ML/chatbot gating per journey. | Matrix published; dev token rejected in prod mode; per-tier tests green. | 5 | NEW audit A8-C1/C2/C3
M2-11 | M2 | M2-P2 | G15 Governance | Close out-of-band paths: staging-reset endpoint, purge audit records, source_system allow-list, staging retention, deletion UX | Very important | modification | Backend | Everything an auditor flagged: admin endpoint replaces psql resets; projector accepts only registered connector source_systems; Mapped staging archived >90d; is_deleted flows exercised via UI. | No documented workflow requires psql; allow-list test rejects a foreign source_system; retention job visible in monitor. | 5 | NEW audit A7
M2-12 | M2 | M2-P2 | G3 Engine | Engine plumbing completion: job_log mapper errors, site-config timezone, KB as assistant tool, readiness reasons in UI | Very important | modification | Backend+Frontend | Four logged refinements: typed field errors into job_log; projector tz/offset from Site; ppiq_ml_search_kb registered as assistant tool #4; Surface-3 shows blocking reasons. | Each visible in one demo pass on a broken-on-purpose mapping and a blocked run. | 3 | CARRIED refinements
M2-13 | M2 | M2-P3 | G4 Quality | CI truth gates + test debt: same-table CREATE gate, seed NOT-NULL gate, register/const/binding tests, assistant guard+factory tests | Very important | testing | Backend | The two deferred gates plus this week's uncovered seams (register upsert, const: branch, execute query-binding, AddAssistant guard + WebApplicationFactory resolution). | All gates red on injected violations, green on main; new tests in CI. | 6 | CARRIED + audit A1-C4/C5
M2-14 | M2 | M2-P3 | G12 UX | Journey UX hardening: progress guide, mapping surfaces renamed by outcome, i18n/RTL verified, widget lite-SQL click-tools | Very important | modification | Frontend | In-product 'step X of 15' affordance; 'Prepare views' vs 'Load to plant data'; real Arabic RTL pass; group-by/filter click-builders in the widget wizard. | New-user walk without verbal guidance reaches step 10; RTL screenshots approved. | 6 | NEW audit A9-R1..R4
M2-15 | M2 | M2-P3 | G14 Security | Ops/security residue: secrets story, mail/Spamhaus remediation, mojibake+phase-name cleanup | Nice to have | cleanup | Mixed | Secrets manager pattern for installs; SPF/DKIM/PTR + relay 587; 6 mojibake .cs files; Phase8/9 dirs renamed. | Deliverability test passes; grep clean on phase tokens; no plaintext secrets in repo. | 4 | CARRIED deferred list
M3-01 | M3 | M3-P1 | G5 Feedback | Customer-comment intake from 16-Jul: log, triage, re-prioritize M3 | Critical | process | Product | Every comment from the meeting becomes a numbered row here with severity and owner; M3 scope is finalized from this list within 48h of the meeting. | Comment log committed; M3 plan v1 published. | 2 | NEW
M3-02 | M3 | M3-P1 | G10 Surface-1 | Visual mapper polish + mapping templates library | Very important | enhancement | Frontend | Drag-drop field mapping, per-industry starter templates shipped as emulation fixtures (never code branches). | A new industry source mapped from a template in <10 min by a non-developer. | 8 | CARRIED v21 M3-10
M3-03 | M3 | M3-P1 | G3 Engine | 3rd UI drag-and-drop analysis toolbox | Very important | enhancement | Frontend | Draggable method/parameter components over the M2 method registry; saved analyses shareable. | User composes a two-method analysis by drag-drop; result matches scripted equivalent. | 10 | NEW audit A10-C3
M3-04 | M3 | M3-P1 | G0 Runtime | Large-profile scale: analytics read replica, partition automation, load test at 60M obs/yr | Very important | architecture | Backend | Per sizing model v1 Large row; automated partition creation; correlation on replica. | Synthetic Large load meets documented latency budgets. | 10 | NEW audit A11
M3-05 | M3 | M3-P1 | G1 Import | Connector expansion per customer landscape (files/API/historians as required) | Very important | new feature | Backend | Scoped from customer comments: e.g. CSV/file drop, REST, OPC-UA historian - each as a new IDataSourceReader family, zero core changes. | New connector imports through the unchanged pipeline. | 8 | NEW placeholder
M3-06 | M3 | M3-P1 | G13 Deploy | HA + multi-plant deployment hardening | Nice to have | architecture | Infra | Failover story, per-plant isolation review, installer runbook (sysadmin auto-provision, Customer Admin manual per Golden Rule). | Documented install executes on a clean VM end-to-end. | 8 | NEW audit A8-C5

## Phase Summary
PHASE SUMMARY - PPIQ Backlog v22 (computed, standalone)
Milestone | Phase | Tasks | Hours | Critical
M1 | M1-P1 | 11 | 43 | 5
M1 | M1-P2 | 6 | 12 | 4
M2 | M2-P1 | 6 | 72 | 6
M2 | M2-P2 | 6 | 36 | 3
M2 | M2-P3 | 3 | 16 | 0
M3 | M3-P1 | 6 | 46 | 1
TOTAL |  | 38 | 225 | 19