## Task List
PlantProcess IQ — Phase-Grouped Task List (v12 · 31 May 2026 · Intelligence-Architecture-Aligned)
110 tasks across 14 phases. v12 aligns the backlog to the Intelligence Architecture (AI & ML Design, companion to Product Vision v2.0): every data / ML / widget / assistant task is anchored to one of the six pipeline layers (L1 Ingest -> L2 Describe -> L3 Feature Store -> L4 Correlate -> L5 Reason -> L6 Advise) and to its owning component, with the honesty boundary stated per task — computation flows up; only L6 may use a language model, and it phrases, never computes. NEW in v12: the Value Model from §5 ('Proving the Money') is first-class — a deterministic impact engine (T296), per-tenant cost inputs (T297) and an evidence-first ROI presentation contract (T298) added to P08 — plus a new 'Architecture Map' sheet mapping all six layers and the 17-component responsibility matrix to their owning phases/tasks, and added Value/Honesty rows in the Test Matrix. Inherits the 31-May 15:25 execution state (Phase-0 four-wave delivery); IDs stable; execution order = row order.
Task ID | Task Name | Phase ID | Severity | Track | Module | Submodule | Description | Task Type | Validation | Status | Completion % | Effort (hrs)
P00 — Test Foundation: Audit, Repair, Cover & Gate ¦ 12 tasks ¦ 96 hrs PRIORITY ZERO — the trust layer the rest of v9 stands on. You cannot harden, enhance, or ship confidently on a suite that does not reflect reality. This phase scans every backend unit, frontend unit, integration, and e2e test plus all validation scripts; deletes the no-ops and duplicates; repairs the stale/brittle ones so they assert REAL behaviour at the current status; adds tests for every uncovered critical area; converts behavioural validation scripts into real tests; and finally turns the trustworthy suite into a red-on-regression gate with a coverage ratchet. EXIT STATE (healthy): one command per stack runs a deterministic suite that mirrors real behaviour, coverage is measured and ratcheted, the suite gates CI, and the Test Register records every delete/modify/add decision.
PPIQ-T300 | Establish the test taxonomy, coverage baseline & CI reporting spine | P00 | critical | Track 2 — Hardening | Infrastructure | Test Strategy / Coverage | FOUNDATION for everything that follows. Before changing individual tests, stand up the measurement and reporting spine so 'tested' becomes verifiable, not asserted. WORK: (1) Define the test taxonomy and what each layer owns: Domain unit (pure logic, no IO), Application unit (services with mocked ports), Infrastructure integration (real Postgres via Testcontainers/compose, connectors, audit immutability), API integration (WebApplicationFactory + real DB, auth, endpoints), Frontend unit (Vitest: components/hooks/state/api-clients), Frontend e2e (Playwright: real flows), Visual + a11y (Playwright). (2) Turn on coverage collection on both stacks — .NET via coverlet/`--collect:"XPlat Code Coverage"` with a Cobertura report, frontend via Vitest V8 coverage — and publish both as CI artifacts with a coverage summary. (3) Establish a baseline number per layer and per critical module (auth, connectors, schema-mapping, delta-import, ML learning core, risk scorer, page builder) and record it as the Phase-0 starting point. (4) Make the whole suite runnable with one command per stack and wire both into Jenkins as reported (not yet gating) stages. v11 status: P00A established the test-run scripts, structural/no-console/UI gates and the register-maintenance spine; coverage tooling and taxonomy are in place. | Enhancement | 1) `dotnet test` produces a Cobertura coverage report and `npm run test:coverage` produces a V8 report, both archived in CI. 2) A coverage summary table (per project + per critical module) is generated and stored as the Phase-0 baseline. 3) The taxonomy is documented (one paragraph per layer: what it owns, what it must NOT do). 4) One command runs each stack's full suite locally and in CI. | Done | 100% | 6
PPIQ-T301 | Audit & triage every existing test against the real 31-May behaviour (the Test Register) | P00 | critical | Track 2 — Hardening | Infrastructure | Test Audit / Triage | Produce and execute the authoritative triage of all ~26 backend tests, ~17 frontend unit/integration tests, and ~35 e2e specs against the CURRENT application behaviour. The companion 'Test Register' sheet in this workbook is the line-by-line output of this task and its execution checklist. WORK: For each existing test, classify it as DELETE (obsolete, duplicated, or a no-op smoke), MODIFY (real intent but stale assertions, weak coverage, brittle selectors, or testing a mock instead of behaviour), or KEEP (already a strong, behaviour-true test). Specifically: remove the four `*TestEnvironmentTests` no-ops (`true.Should().BeTrue()`) once real coverage exists in their project; collapse overlapping phase-N e2e specs (phase1-*, phase2-*, phase56-*, phase78-*) that assert the same routes/flows into consolidated, behaviour-named specs; and upgrade thin specs (8–33 line placeholders such as phase02-data-lifecycle-contract, page-builder-v7, phase56-primary-flows, route-smoke) into real assertions. Each MODIFY entry states exactly what changes and why; each DELETE entry states what now covers it. v11 status: P00A executed the register maintenance/triage; dispositions reconciled and the diagnostic imports fixed. | Enhancement | 1) Every existing test file has a recorded disposition (DELETE / MODIFY / KEEP) with a one-line rationale (see the Test Register). 2) All DELETE items are removed and the suite still builds and passes. 3) No remaining `true.Should().BeTrue()`-style no-op survives. 4) The count of overlapping phase-N e2e specs is reduced and the survivors are named by behaviour, not phase number. | Done | 100% | 8
PPIQ-T302 | Backend unit coverage for uncovered Application/Domain logic | P00 | very important | Track 2 — Hardening | App Backend | Unit Tests / Application & Domain | Close the backend UNIT gaps for pure logic that today has no coverage, matching real behaviour as of 31-May. TARGET (uncovered or thin today): the additive RiskScoreService contribution decomposition (contributions sum exactly to the score; explanation shape); FeatureEngineeringService derived-feature math (cev, true_superheat, casting speed delta, residency, shift bucketing) on known inputs; QualityLabelBuilderService label derivation; MlReadinessService gate logic (ready vs under-powered thresholds); the SafeSql policy edge cases beyond what SafeSqlPolicyTests covers (CTE, nested subqueries, cross-tenant attempts); WidgetQueryExpressionService expression validation/safety; LicenseService tier-feature resolution corner cases. Use deterministic fixtures; no database (those belong to integration). v11 status: P00B delivered the backend unit tests: RiskScoreServiceTests, FeatureEngineeringServiceTests, MlReadinessServiceTests, QualityLabelBuilderServiceTests; SafeSqlPolicy extended. | New Feature | 1) RiskScoreService has a unit test proving exact additive decomposition on a known vector. 2) FeatureEngineeringService derived features are asserted against hand-computed expected values. 3) MlReadinessService gate thresholds are covered both sides of the boundary. 4) New SafeSql cases (CTE/nested/cross-tenant) are rejected. 5) Coverage for the Application project rises measurably above the T300 baseline. | Done | 100% | 10
PPIQ-T303 | Backend integration tests on real Postgres for data, ML, and security paths | P00 | very important | Track 2 — Hardening | App Backend | Integration Tests / Postgres | Add API + Infrastructure INTEGRATION tests that run against a real Postgres (Testcontainers or the demo compose) so the data lifecycle, the ML core, and security are proven end-to-end, not by source-text regex. TARGET: (1) ML learning core — apply 200_/201_/204_, run `ppiq_ml_seed_phase45_golden_dataset()` then `ppiq_ml_run_learning_job_v1`, and assert it RECOVERS the injected correlations with correct effect-size sign/magnitude, produces Benjamini-Hochberg q-values, and REJECTS spurious pairs under FDR (this replaces the static validate-v7-phase04-phase05 checks with behaviour). (2) Delta import — cold load then incremental, simulated mid-batch crash → resume with no duplicates, schema-drift detection. (3) Schema-mapping resolver — the three named errors (NoSuchView/NoSuchColumn/InvalidAggregateForType) and SafeSqlValidator blocking on generated join SQL, against a live schema. (4) Auth — login gate matrix (empty/bootstrap-collision/valid/role/bad-key) at the API. (5) Audit-log immutability already has a strong test — keep and extend with the new audit surfaces. v11 status: P00B delivered MlLearningCoreIntegrationTests, AuthGateMatrixTests and SchemaConfigurationSafety extensions on real Postgres. Remaining: delta-import crash/resume integration and the Worker ML-scheduling test. | New Feature | 1) An integration test runs the ML learning job on the golden dataset and asserts recovery + FDR rejection (no regex on SQL text). 2) Delta-import crash/resume yields zero duplicates and a correct cursor. 3) Resolver returns the three typed errors and blocks malicious join SQL. 4) The auth gate matrix is asserted at the API with a real token. 5) These run in CI against a real Postgres. | Partial | 80% | 12
PPIQ-T304 | Frontend unit/component coverage for uncovered UI logic & Standard* contract | P00 | very important | Track 2 — Hardening | App Frontend | Unit Tests / Vitest | Close frontend UNIT gaps with Vitest, matching real component behaviour. Today only a handful of components/hooks are covered. TARGET: the apiClient retry/backoff + auth-failure mapping (T280/T281 behaviour — assert bounded attempts and that 401/403/500/network produce distinct outcomes); AuthContext bootstrap logic (no infinite re-login on failure); the LicenseContext tier gating; the full Standard* contract (StandardButton/Table/Tabs/Fields/Surface/DataFetchBoundary/ErrorBoundary — every variant and state in the UI Standards Reference, including the forbidden-phrase guard and the 'Refreshing X…' pattern); the widget-builder expression step validation; and the page-builder layout state reducer. Mock the network at the boundary; do not hit a real API. v11 status: P00C delivered the frontend behavioural tests: apiClient.retry-backoff, AuthContext.bootstrap, LicenseContext.gating, DataFetchBoundary, pageBuilderReducer; vitest env + architecture baseline fixed. | New Feature | 1) apiClient tests prove retries are capped with backoff and that each HTTP status maps to its intended outcome. 2) AuthContext cannot enter an infinite re-login loop on a failing bootstrap. 3) Every Standard* component has variant+state coverage and a snapshot where appropriate. 4) The forbidden-phrase guard is unit-asserted. 5) Frontend coverage rises measurably above the T300 baseline. | Done | 100% | 10
PPIQ-T305 | E2E coverage for the real critical journeys (consolidated, behaviour-named) | P00 | very important | Track 2 — Hardening | App Frontend | E2E / Playwright | Rebuild the e2e layer around the REAL critical journeys, consolidating the overlapping phase-N specs into durable, behaviour-named flows and adding the journeys that are missing. TARGET JOURNEYS (each from a clean login, no hardcoding): (a) Auth & shell — login as each persona, route-refresh survival, no fake 'connection failed'. (b) Data lifecycle — configure a DB link from the HMI → schedule a job → import → see data (the Track-3 Golden-Rule flow). (c) Page builder — create a page, drop+bind+script a widget, save, reload, it persists. (d) Inspection→analysis — run an inspection job and view its generated page (once P06 lands). (e) License toggle — switch Enterprise→Pro and watch a feature disappear. (f) Resilience — backend-outage handling shows retry UI, never a fake failure. Consolidate phase1-*/phase2-*/phase56-* duplicates into these. Keep auth-matrix, golden-path, dashboard-refresh-filter, hardening-matrix as the strong survivors and align them. v11 status: P00D mapped phase-named specs into canonical journeys (golden-path, dashboard-refresh, security-hardening, page-builder) per P00D_E2E_Consolidation_Map.json; a11y + license-select-label specs fixed; e2eadmin harness wired. P06/P09 journeys explicitly deferred until those routes exist. | New Feature | 1) Each critical journey has exactly one authoritative, behaviour-named spec that runs green against the real app. 2) The data-lifecycle and page-builder journeys configure everything from the HMI (no hardcoded pages/data). 3) Overlapping phase-N specs are removed or merged; the e2e suite is smaller and clearer. 4) The suite runs in CI on chromium (and the responsive/multibrowser spec covers the rest). | Partial | 75% | 10
PPIQ-T306 | Convert behavioural validation scripts into real tests; keep structural ones as gates | P00 | important | Track 2 — Hardening | Infrastructure | Validation → Test Migration | Resolve the ~25 validation scripts (tools/validation/*, scripts/*.mjs, Frontend tools/*) into the test suite. The principle: a script that asserts BEHAVIOUR becomes a real test; a script that only checks file/structure stays a lightweight CI gate. WORK (see the Test Register for the per-script decision): (1) TRANSFER-TO-TEST the behavioural validators — e.g. validate-v7-phase04-phase05-acceptance (→ the ML integration test in T303), validate-t208-exposure (→ a deploy/network test or scripted scan), validate-api-client-policy / validate-standard-imports / validate-forbidden-copy / validate-no-console-in-src (→ Vitest+ESLint rules already partly exist; make them assertions), validate-sql-script-hygiene (→ an integration test that applies all scripts under ON_ERROR_STOP=1 on a fresh DB and asserts BOM-free + clean apply). (2) KEEP-AS-GATE the pure structure/acceptance file-existence scripts, but point each at the real test it now corresponds to so they stop being the sole source of truth. (3) RETIRE superseded per-phase acceptance scripts whose intent is fully covered by a real test. v11 status: P00B/P00D added SqlScriptHygieneApplyTests (apply-all under ON_ERROR_STOP), the SQL BOM strip, and drift-fix scripts 206/207; behavioural validators migrated, structural ones kept as gates. | Enhancement | 1) Every behavioural validator has either become a real test or is explicitly retired with its replacement named (Test Register). 2) The ML, exposure, and SQL-hygiene checks now run as real tests, not source-text regex. 3) Remaining validators are pure structure gates and are documented as such. 4) CI references the tests, not the scripts, for behavioural truth. | Done | 100% | 6
PPIQ-T307 | Make the suite the gate: deterministic, fast, and red-on-regression | P00 | important | Track 2 — Hardening | Infrastructure | CI / Test Gating | Turn the now-trustworthy suite into the enforcement mechanism for the rest of v9, so later phases cannot silently regress. WORK: (1) Promote the reported stages from T300 to GATING — unit (both stacks) and the fast integration/e2e subset must pass for a green build; the heavy e2e/visual set runs nightly. (2) Stabilise flakiness: deterministic seeds, fixed Playwright waits (no arbitrary sleeps), Testcontainers lifecycle, and a quarantine lane for any genuinely flaky spec with an owner. (3) Set a coverage RATCHET (coverage may not drop below the T300 baseline; new critical modules require their own tests). (4) Document the contributor workflow: how to run, where tests live per layer, and the rule that a feature task is not Done until its tests are green. v11 status: P00A/P00D added the wave validators and e2e governance (consolidation map + future deferrals). Remaining: promote to hard CI gating with a coverage ratchet and a quarantine lane across 3 clean runs. | Enhancement | 1) A failing unit/integration/fast-e2e test turns the build red and blocks merge. 2) The suite is deterministic across 3 consecutive CI runs (no flakes outside the quarantine lane). 3) Coverage cannot regress below the baseline (ratchet enforced). 4) The contributor testing workflow is documented and referenced from the UI-Standards onboarding. | Partial | 60% | 5
PPIQ-T308 | Performance & load test layer with explicit thresholds | P00 | very important | Track 2 — Hardening | Infrastructure | Performance / Load | Stand up a performance and load test layer that enforces the Track-2 promise — 'endpoints can't hang or lag; long ones show progress' — as measured thresholds, not hope. Runs against demo-scale data (≥5,600 coils ≈ one month). WORK: (1) Add a perf harness (k6 or a dedicated xUnit perf project) hitting the heavy reads — dashboard widget queries, material investigation, correlation results — and assert p95 latency budgets (see the Test Matrix Perf rows). (2) Add EXPLAIN-based assertions that critical queries use their indexes (no seq-scan regression) and that the demo-scale dataset is present for the run. (3) Assert every endpoint expected to exceed ~2s exposes a progress percentage and that a global request timeout makes 'hang forever' impossible. (4) Add a concurrency test (e.g. 50 concurrent dashboard reads) that must sustain without error/timeout. (5) Include the external Postgres-exposure scan (5432 closed) as a security-perf gate. Publish a perf report artifact in CI; run the heavy set nightly, a fast subset per build. v11 status: Only the empty PlantProcess.PerformanceTests project scaffold exists; no real p95/EXPLAIN/concurrency thresholds yet. This is the main remaining Phase-0 build. | New Feature | 1) p95 budgets are asserted for dashboard, investigation, and correlation reads on demo-scale data and fail the build when breached. 2) EXPLAIN checks confirm index usage on the critical queries. 3) Every >2s endpoint exposes progress; a global timeout prevents indefinite hangs (tested). 4) A 50-concurrent-read test sustains without error. 5) Perf report archived in CI. | Not Started | 5% | 8
PPIQ-T309 | ML/AI honesty-contract test group (first-class) | P00 | very important | Track 2 — Hardening | App Backend | ML / Honesty Guardrail Tests | ARCHITECTURE · The single rule that spans all six layers (Intelligence Architecture §1, §6). Computation flows up; language only appears at the very top — L1–L5 are deterministic and testable (numbers from SQL and C#, never a model); only L6 introduces an LLM and it may not invent a figure. This honesty-contract suite is the strongest answer to 'is your AI a black box?' in a customer security review. Make the honesty contract — the thing that protects you in front of a customer — a first-class, enumerated test group rather than a footnote. The analytical core is deterministic and in-house; the LLM is the VOICE, never the brain; every finding is evidence-qualified. WORK (see the Test Matrix Honesty rows): (1) Serializer/validator tests that REJECT any ML/assistant finding lacking effective-n, q-value, effect size, or an evidence link. (2) Tests that REJECT forbidden claims ('prediction','predicts','guaranteed root cause','AI-powered prediction','production-ready AI') on ML/assistant surfaces and ACCEPT the approved vocabulary. (3) An instrumented assertion that NO LLM/network call occurs in the statistical compute path. (4) A test proving the API narrative provider receives ONLY abstracted findings (no raw plant rows / PII). (5) A test proving the app runs fully offline on the local/null provider (narration degrades gracefully). (6) Grounding tests (activate once the assistant T232 exists) that every figure in an answer traces to a tool result or retrieved evidence. v11 status: A website ConnectorHonestyBlock exists, and the ML integration test touches noise rejection, but the first-class honesty-contract test group (forbidden-claim rejection, mandatory evidence fields, no-LLM-in-compute, abstracted-findings-only) is not yet its own suite. | New Feature | 1) A finding missing n/q/effect-size/evidence-link is rejected by a test. 2) A forbidden claim fails a test; approved vocabulary passes. 3) The compute path is proven LLM-free by instrumentation. 4) Only abstracted findings reach the external provider (asserted). 5) Offline run on the local provider passes. 6) Grounding tests are in place (skipped-until-ready for the assistant). | Partial | 25% | 6
PPIQ-T310 | Connector behavioural integration tests across all six sources | P00 | very important | Track 2 — Hardening | App Backend | Integration Tests / Connectors | Prove every connector against a REAL source (the demo-sources compose containers + CSV/Excel golden files), not by source-text checks. Each of the six connectors shares one behavioural contract (see the Test Matrix Connectors rows). WORK: For CSV, Excel, MySQL, Oracle, PostgreSQL, and MSSQL: (1) connect with valid config (success) and with a bad host/credential (typed failure, bounded — no hang); (2) schema discovery returns the expected tables/columns from the demo source; (3) delta read returns only rows beyond the incremental cursor; (4) native→canonical type mapping is correct for numeric/text/date/bool; (5) connection timeout is bounded with a clear error. Plus: ConnectorConfigurationService round-trips an encrypted config with secrets masked, and the factory returns the right connector per type. These reuse the demo-source containers stood up in P02 (T245). v11 status: CsvConnectorSmokeTests and ExcelConnectorSmokeTests are present; the MySQL/Oracle/PostgreSQL/MSSQL behavioural tests (connect/schema/delta/type-mapping/timeout) against the demo-source containers are still to add. | New Feature | 1) All six connectors pass connect/schema/delta/type-mapping/timeout against live demo sources (or golden files for CSV/Excel). 2) Bad credentials/host yield a typed, bounded failure (no infinite wait). 3) Connector config round-trips with masked secrets. 4) The factory maps source type → connector correctly. 5) The suite runs in CI against the demo-sources compose. | Partial | 35% | 8
PPIQ-T311 | Endpoint authorization matrix & API contract tests for every group | P00 | very important | Track 2 — Hardening | App Backend | Security / Contract Tests | Enumerate and assert the authorization matrix for EVERY endpoint group (admin + ML + domain), plus baseline API contract guarantees, so an accidental missing [Authorize] or a broken response shape is caught immediately (see the Test Matrix Endpoint-Authorization and Contract rows). WORK: (1) For each endpoint group (admin-overview/jobs-monitor/schema-mapping/two-stage/license/phase1/phase2/widgets/users/demo-lifecycle/diagnostics and /api/ml/*, /api/correlation, /api/risk-score, /api/dashboards, /api/materials, /api/process, /api/quality, /api/reporting, /api/plant-layout, /api/data-quality) assert the 3-identity outcome (anon=401/403, operator per design, admin=200) and that removing an [Authorize] fails the probe. (2) Contract tests: every mapped endpoint appears in OpenAPI; errors return RFC7807 problem-details (status+title), never a bare 500; oversized/malformed payloads → 400. (3) Emit a matrix artifact and wire it red-on-deviation. This generalises the existing auth-matrix spec to the whole surface. v11 status: AuthGateMatrixTests covers the login matrix; the full per-endpoint-group authorization matrix and the RFC-7807/contract assertions across every group are still to complete. | New Feature | 1) Every endpoint group has a 3-identity authorization assertion; removing an [Authorize] turns the build red. 2) Every mapped endpoint is present in the OpenAPI document. 3) Errors are RFC7807 problem-details, not bare 500s. 4) Malformed/oversized payloads return 400. 5) The matrix artifact is archived per deploy. | Partial | 40% | 7
P01 — Stabilize: Build-Green, Auth & Deploy Reliability ¦ 14 tasks ¦ 26 hrs FOUNDATION — highest priority and demo-protection. The app must build in CI, migrate cleanly, start reliably, log in deterministically, and expose nothing it shouldn't. This phase bundles the build-green hotfixes with EVERY auth/deploy/network bug surfaced during the login & deployment saga, so the whole reliability story lands together (not scattered across later phases). EXIT STATE (healthy): a green pipeline end-to-end; a fresh machine one-shots to a working admin login; the server has no public database port; and StartupConfigurationValidator blocks dev secrets under Production.
PPIQ-T201 | Fix Jenkins npm build failure (Node unavailable, exit 127) | P01 | critical | Track 2 — Hardening | Infrastructure | CI / Build Agent | ALREADY IN PLACE (30-May audit): Jenkinsfile runs UI gates inside node:20-alpine (npm ci + validate:phase5-phase6:strict); self-check check('PPIQ-T201',/node:20/). This capability is implemented — the task here is to CONFIRM it, not rebuild it. Reference scope / behaviour: The pipeline still fails at stage '2b. Phase 5/6 UI quality gates' with 'npm: not found' (exit 127): npm ci runs directly on `agent any` with no Node runtime. Run the UI gates inside a Node container (docker run --rm -v "$PWD":/app -w /app node:20-alpine sh -c 'npm ci && npm run validate:phase5-phase6:strict ...'), OR configure the Jenkins NodeJS tool ('node20') and wrap the stage in tools{ nodejs 'node20' }, OR install Node on the agent and ensure it is on the non-interactive PATH. Stages 3-5 must stop being skipped. | Bug Fix | Confirm (do NOT re-implement): 1) A full pipeline run reaches 'Build images' and 'Recreate containers' without the npm step failing. 2) `npm ci` and the validate/test:visual/test:a11y scripts run with a pinned Node 20. 3) A green build is produced end to end. 4) The fix is committed in the Jenkinsfile, not applied ad hoc on the agent. | Done | 100% | 2
PPIQ-T202 | Reconcile migration 117 audit-table schema (still broken) | P01 | critical | Track 2 — Hardening | Database | Migration / Widget Audit | ALREADY IN PLACE (30-May audit): Script 117 (mod 30-May 16:18) now DROP TABLE IF EXISTS dashboard_widget_expression_audit then CREATE with created_at_utc + canonical EF columns + 2 indexes + verification SELECT. This capability is implemented — the task here is to CONFIRM it, not rebuild it. Reference scope / behaviour: Script 117 still uses CREATE TABLE IF NOT EXISTS for dashboard_widget_expression_audit with created_at_utc, but 113 already created that table with executed_at_utc — so IF NOT EXISTS is a no-op, created_at_utc never lands, and the index on it fails (silently, under ON_ERROR_STOP=0). The audit layer is on the stale schema. Replace 117's body with DROP TABLE IF EXISTS dashboard_widget_expression_audit; then CREATE TABLE with the EF-entity schema (id, dashboard_widget_definition_id, expression_version smallint, validation_status smallint, validation_message, query_expression, advanced_expression_json jsonb, created_at_utc) + the index. Make 113 and 117 not both CREATE the same table (113 becomes guard-only or canonical). Apply on the Hetzner staging clone. | Bug Fix | Confirm (do NOT re-implement): 1) Fresh Postgres 17 + ordered scripts apply with zero errors and the audit table has created_at_utc. 2) Re-apply on the staging clone is clean. 3) EF reads/writes against the audit table succeed (smallint enum + created_at_utc). 4) Exactly one migration CREATEs the table. | Done | 100% | 2
PPIQ-T203 | Switch SQL migration runner to ON_ERROR_STOP=1 | P01 | very important | Track 2 — Hardening | Infrastructure | CI / Migration Safety | ALREADY IN PLACE (30-May audit): Jenkins 'Apply SQL scripts' stage uses psql -v ON_ERROR_STOP=1; self-check check('PPIQ-T203',/ON_ERROR_STOP=1/). PS verify scripts also use it. This capability is implemented — the task here is to CONFIRM it, not rebuild it. Reference scope / behaviour: The Jenkins 'Apply SQL scripts' stage runs psql with ON_ERROR_STOP=0, so a rolled-back migration (e.g. 117) reports success and the deploy proceeds onto a half-migrated schema. After T202 is fixed, change the runner to ON_ERROR_STOP=1 so any failing migration fails the build loudly. Audit the existing scripts first to ensure none rely on the permissive mode. | Bug Fix | Confirm (do NOT re-implement): 1) Runner uses ON_ERROR_STOP=1. 2) A deliberately broken script in a scratch branch turns the build red at the migration stage. 3) The full ordered script set still applies clean on a fresh DB and on staging. 4) No script depends on error-swallowing. | Done | 100% | 1.5
PPIQ-T288 | Investigate the SQL syntax error seen during script application | P01 | normal | Track 2 — Hardening | Database | Migration / Script Hygiene | STARTING POINT (31-May audit — already built): 202_/203_ ML compute hotfix scripts added (the earlier compute stub/syntax issues addressed); BOM guard intent present. WHAT REMAINS — the actual work of this task: Confirm the full ordered script set applies clean under ON_ERROR_STOP=1 on fresh + staging; add the CI BOM guard if not yet enforced. FULL REFERENCE SPEC: A SQL syntax error was observed during one script-application run (flagged in the prior deploy session, separate from the 117 audit-table fix). Locate the offending statement, fix it, and ensure the full ordered script set applies cleanly under ON_ERROR_STOP=1 on a fresh DB and on the staging clone. Add the BOM-guard so re-introduced BOMs (recurred 3x) can't silently break a script again. | Bug Fix | 1) The specific syntax error is identified and fixed. 2) Full ordered scripts apply with zero errors on fresh + staging under ON_ERROR_STOP=1. 3) BOM guard in CI rejects any script with a UTF-8 BOM. 4) The previously BOM-stripped files (116 sql, vite.config.ts) are committed. | Partial | 60% | 2
PPIQ-T205 | Verify standard-import ESLint block is an enforced Jenkins gate | P01 | important | Track 2 — Hardening | Infrastructure | CI / Quality Gate | ALREADY IN PLACE (30-May audit): validate-forbidden-copy + non-standard-import sweeps wired in Jenkins stage 2c; self-check asserts forbidden-phrase guard and Standard* enforcement; eslint config contains the rule. This capability is implemented — the task here is to CONFIRM it, not rebuild it. Reference scope / behaviour: Closes the residual of v4 PPIQ-T106. The forbidden-phrase sweep and auth-matrix are referenced in Jenkins stage 2c, but confirm the non-standard-import rule (no native <button>/<input>/<select>/<table>/<textarea> in src/pages¦features; no import from src/hardening/*) actually fails the build, not just warns. Wire pnpm/npm lint as a failing stage with a clear offender list and canonical-replacement hint; add the pre-commit hook. | Enhancement | Confirm (do NOT re-implement): 1) A native <button> in src/pages/* fails the build naming the file + replacement. 2) An import from src/hardening/* fails lint. 3) Stage runs on every push. 4) Pre-commit blocks locally. | Done | 90% | 1.5
PPIQ-T282 | Auth config-section prefix + bootstrap-collision: lock in & guard | P01 | important | Track 2 — Hardening | App Backend | Auth / Configuration | ALREADY IN PLACE (31-May audit): StartupConfigurationValidator.cs (435L) validates PlantProcess:Auth binding, REJECTS legacy Auth:* keys with a fix hint, checks SigningKey>=32, Issuer/Audience, and bootstrap config. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: WORK: add a startup self-check (no secret leakage) that logs once: the section it bound from, the resolved Users count, whether SigningKey is present and >=32 chars, and whether any Users[].Password equals BootstrapAdminPassword (WARN loudly if so). This converts the two silent failure modes into a loud, one-line startup signal. | Bug Fix | Confirm (do NOT re-implement): Confirm the startup self-check log line and the bootstrap-collision warning fire on a real boot. | Done | 100% | 2
PPIQ-T280 | Frontend auth-failure retry storm: add backoff + attempt cap | P01 | very important | Track 2 — Hardening | App Frontend | Auth / AuthContext | ALREADY IN PLACE (31-May audit): apiClient: AUTH_RETRY_BACKOFF_MS=[0,500,1500], maxAttempts cap, retryable-only; comment '// PPIQ-T280: auth-failure retry storm capped with backoff'. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: AuthContext.tsx auto-logs-in on mount with VITE_SMOKE_* and registers a window 'plantprocess:auth-failure' listener that calls bootstrap() again. apiClient.dispatchAuthFailure fires that event on EVERY non-2xx. When the auto-login itself returns 401/403, the listener re-triggers the failing login, producing an unbounded POST /auth/login storm (observed: thousands of identical requests flooding the API log) and a stuck 'Backend connection failed' screen. Add an attempt cap + exponential backoff, and do NOT let a failure of the bootstrap login itself re-dispatch auth-failure (guard against self-retrigger). | Bug Fix | Confirm (do NOT re-implement): Confirm a failing auto-login produces <=3 attempts then stops (no /auth/login storm) via test. | Done | 90% | 3
PPIQ-T281 | Frontend mislabels all non-2xx + network errors as 'Backend connection failed' | P01 | very important | Track 2 — Hardening | App Frontend | Auth / Error Surfacing | STARTING POINT (31-May audit — already built): apiClient maps 401/403 to a typed auth-failure event distinct from network; status carried through. Full per-status user-facing copy not fully confirmed. WHAT REMAINS — the actual work of this task: Confirm 401 vs 403 vs 500 vs network each render a DISTINCT message in the login/bootstrap UI. FULL REFERENCE SPEC: The login/bootstrap path renders one generic 'Cannot reach the backend API' screen for 401 (wrong creds), 403 (bootstrap blocked), 500 (server/config) and true network failures alike. During the login saga this hid the real cause for hours: backend returned 401/403/500 in sequence and the UI showed the identical red screen each time. Surface the real status: 401 -> invalid credentials, 403 -> bootstrap admin disabled / use a real admin, 500 -> show Problem detail, network/abort (status 0) -> unreachable. This is the founder's Vision §2 'never show a fake failure' rule applied to auth. | Bug Fix | 1) 401 shows an invalid-credentials message distinct from a network-unreachable message. 2) 403 shows the bootstrap-disabled explanation. 3) 500 surfaces the backend Problem detail. 4) Only a true fetch/abort error shows 'cannot reach backend'. 5) Covered by tests mapping status->message. | Partial | 60% | 2.5
PPIQ-T285 | Frontend VITE_SMOKE_PASSWORD must equal backend admin password (env contract) | P01 | important | Track 2 — Hardening | App Frontend | Auth / Env Contract | ALREADY IN PLACE (31-May audit): Auth-matrix + smoke use PPIQ_SMOKE_PASSWORD/PPIQ_ADMIN_PASSWORD env contract; .env docs updated; CI passes creds through. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Because the app auto-logs-in as admin using VITE_SMOKE_PASSWORD (.env.local, highest Vite precedence), a mismatch between that value and the backend Users[0] admin password causes a permanent 401 + the connection-failed screen even when the backend is correct. Add a documented env contract and a dev-time guard: a tiny check (script or startup console.warn) that flags when the configured smoke password is the literal placeholder/empty, and document that .env.local VITE_SMOKE_PASSWORD must match the backend admin password. Longer term (post-demo) replace silent auto-login with an explicit login form fallback when bootstrap fails. | Bug Fix | Confirm (do NOT re-implement): Confirm the dev-time guard warns on empty/placeholder VITE_SMOKE_PASSWORD; optional manual-login fallback on bootstrap 401. | Done | 85% | 1.5
PPIQ-T283 | SQL apply NOTICE-abort bug in dev-bootstrap.ps1 (idempotent re-run fails) | P01 | important | Track 2 — Hardening | Infrastructure | Dev Bootstrap / Migration | ALREADY IN PLACE (31-May audit): tools/phase23/fix-legacy-auth-config-files.cjs migrates stale Auth:* config; StartupConfigurationValidator blocks the legacy keys going forward. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: dev-bootstrap.ps1 Invoke-PsqlFile runs psql with 2>&1 while $ErrorActionPreference='Stop', so a benign psql NOTICE (e.g. 'relation already exists, skipping' from idempotent script 050) is treated as a terminating error and aborts the whole bootstrap on a second run. Fix: set local client_min_messages=warning for the psql invocation and use a local $ErrorActionPreference='Continue' (or -StopOnSqlError opt-in) so NOTICEs don't abort. Also correct the script's user-secrets paths to the PlantProcess:Auth prefix (incl. SigningKey) so a fresh machine truly one-shots login. | Bug Fix | Confirm (do NOT re-implement): Confirm dev-bootstrap.ps1 idempotent re-run (no NOTICE-abort) end-to-end on a clean machine. | Done | 90% | 2
PPIQ-T284 | Kill-by-PORT not by process name in dev/runbook scripts | P01 | important | Track 2 — Hardening | Infrastructure | Dev Tooling / Runbook | ALREADY IN PLACE (31-May audit): tools/dev/Stop-PPIQ-Port.ps1 + Show-PPIQ-PortOwner.ps1 free :5063/:5173 by OwningProcess (Get-NetTCPConnection) and report the new listener. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Stop/relaunch scripts filtered Get-CimInstance for Name='dotnet.exe' matching PlantProcess.Api. But 'dotnet run' builds an apphost and the process actually listening on :5063 is PlantProcess.Api.exe (a child), so the filter never killed the real listener — every config change 'didn't take' because a stale server kept answering on the port. Standardize all dev/runbook scripts to free the port by OwningProcess (Get-NetTCPConnection -LocalPort) and verify the new listener's StartTime, so a restart provably replaces the process. | Bug Fix | Confirm (do NOT re-implement): Confirm both scripts print the fresh PID+StartTime after a restart. | Done | 100% | 1.5
PPIQ-T286 | Verify PostgreSQL public port is closed on the live server (deploy regression) | P01 | very important | Track 2 — Hardening | Infrastructure | Deployment / Network | ALREADY IN PLACE (31-May audit): Infrastructure/deploy/verify-server-exposure.sh + rotate-postgres-password.sh exist; compose keeps Postgres off 0.0.0.0; README documents nmap proof. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: During deployment the server's PostgreSQL port was publicly exposed (the DB container published 5432 to the host/internet). Confirm the live Hetzner stack binds Postgres to the internal Docker network only (no host port publish, or bound to 127.0.0.1), rotate the DB password if it was exposed, and capture an external scan proving 5432 is not reachable from the internet. Distinct from T208 (loopback audit of ALL services) — this is the specific, already-observed Postgres exposure. | Bug Fix | Confirm (do NOT re-implement): Run verify-server-exposure.sh against the live host and attach the scan output. | Done | 90% | 1.5
PPIQ-T287 | Replace bootstrap admin with a real seeded admin before any pilot | P01 | important | Track 2 — Hardening | App Backend | Auth / Bootstrap Lifecycle | ALREADY IN PLACE (31-May audit): StartupConfigurationValidator requires a disabled bootstrap sentinel ('__DISABLED__' / 'DISABLED-*') under Production and fails fast otherwise; validation check asserts it. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: The bootstrap admin is a dev/first-run convenience that is auto-disabled once a real admin exists. Before any pilot/prod cutover, ensure there is a real configured admin (non-bootstrap) with a strong unique password, the bootstrap password is set to a disabled sentinel, and StartupConfigurationValidator rejects dev/default keys+password in Production. Capture this as a one-time prod-readiness step in the runbook. | Bug Fix | Confirm (do NOT re-implement): Confirm a real non-bootstrap admin is seeded in the prod config before cutover. | Done | 90% | 1.5
PPIQ-T208 | Finish loopback-binding audit for all infra services + external scan proof | P01 | important | Track 2 — Hardening | Infrastructure | Docker Compose / Network Exposure | ALREADY IN PLACE (31-May audit): tools/validation/validate-t208-exposure.cjs + Infrastructure/deploy/README.md documents 'nmap -Pn 178.105.152.180' loopback proof; demo compose internal-only. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Closes residual of v4 PPIQ-T105 (only Postgres proven on 127.0.0.1). Audit redis, seq, jaeger, grafana, prometheus, jenkins, workers in docker-compose.demo.yml; bind each published port to 127.0.0.1 unless intentionally public (Caddy 80/443; Jenkins :9090 behind basicauth). Prove with an external nmap and document each decision in Infrastructure/deploy/README.md. | Bug Fix | Confirm (do NOT re-implement): Attach the actual external scan result; confirm only 80/443 reachable. | Done | 85% | 1.5
P02 — Data Lifecycle: Sources, Ingestion, Mapping & Genealogy ¦ 8 tasks ¦ 41 hrs The generic data-in backbone AND the substrate the whole demo runs on. Stand up the eight realistic source systems, split the coherent dataset across them, harden the mapping resolver/joins, build the heat->ladle->tundish->strand->slab->coil genealogy spine via the mapping engine (no hardcoding), then verify every connector against the live sources and make delta-import resumable. EXIT STATE (healthy): from the HMI you can connect to and import from all eight sources, map them into the generic schema, and resolve any coil back to its melt/cast conditions and forward to its defects/QA.
PPIQ-T245 | docker-compose.demo-sources.yml — eight source systems (loopback-bound) | P02 | very important | Track 3 — Demo | Infrastructure | Demo Sources / Compose | ARCHITECTURE · Layer L1 — Ingest & Canonicalize (Intelligence Architecture §2.1). Stands up the heterogeneous source estate the connector layer reads. Honesty boundary: L1 only moves and joins data faithfully — no analysis, scoring or inference happens at this layer. ALREADY IN PLACE (31-May audit): docker-compose.demo-sources.yml (151L): meltshop-postgres, caster-oracle, hsm-oracle, pkl-mssql, downtime-mysql, parsytec-mysql + per-source init SQL under Infrastructure/demo-sources/*. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Author docker-compose.demo-sources.yml standing up the eight source systems from the Vision: Postgres MeltShop (EAF/LF), Oracle Caster, Oracle HSM, MSSQL PKL, Excel Yard, MySQL Downtime, MySQL Parsytec surface-inspection, and Excel QA. Every service is bound to loopback / the internal Docker network only (consistent with the network-hardening in P01) and seeded with realistic schemas matching the Vision's table descriptions so the app must connect to genuinely heterogeneous sources. | New Feature | Confirm (do NOT re-implement): Confirm all services come up healthy and none publish to 0.0.0.0; add the remaining Excel (Yard/QA) sources or document them as file drops. | Done | 90% | 6
PPIQ-T246 | Split the existing coherent dataset across the eight source systems | P02 | very important | Track 3 — Demo | Database | Demo Sources / Seed Distribution | ARCHITECTURE · Layer L1 — Ingest & Canonicalize (Intelligence Architecture §2.1). Splitting the coherent dataset across the eight native sources is what forces the mapping engine to re-join it — the canonical model is faithful copies of genuinely heterogeneous sources, not a pre-joined table. STARTING POINT (31-May audit — already built): Per-source init/001_schema_seed.sql under Infrastructure/demo-sources/* + synthetic_inspection_source_insert.sql (6601L) splitting inspection data into the source shape. WHAT REMAINS — the actual work of this task: Finish splitting ALL of the coherent dataset across the 8 sources so it must be re-joined via the mapping engine; verify row coherence across sources. FULL REFERENCE SPEC: The single-DB seed already produces vision-scale volumes (630 heats, 5,670 slabs/coils, ~40k HSM measurements, ~17k QA results, ~210 downtime events — 100k+ rows). The remaining work is distributing this SAME coherent, genealogy-linked data across the eight separate source containers (per their native structures) so the demo is configured LIVE from the HMI per the Track-3 golden rule. Preserve end-to-end genealogy across systems. | Enhancement | 1) Each source container is seeded with its slice in its native structure. 2) Material ADV_COIL4002 traces end-to-end across every system incl. a downtime and a QA sample. 3) Re-seeding is idempotent. 4) Total volume preserved (100k+ rows). | Partial | 55% | 8
PPIQ-T261 | Seed canonical demo plant layout (flat-steel) | P02 | very important | Track 3 — Demo | Database | Demo Lifecycle / Canonical Layout | ARCHITECTURE · Layer L1 — Ingest & Canonicalize (Intelligence Architecture §2.1). The canonical plant layout is the substrate the genealogy spine and feature store read; it is moved/joined faithfully, never interpreted at L1. STARTING POINT (30-May audit — already built): 112_golden_demo_data (23MB) + 110/111 demo shapes/views encode a flat-steel layout. WHAT REMAINS — the actual work of this task: Seed/confirm the canonical flat-steel demo plant layout (EAF/LF/CC/TF/HSM/...) matches the dataset and is presentable. FULL REFERENCE SPEC: Seed the canonical layout (EAF/LF/CC/TF/HSM/SKP/LCT/HCT/STL/PKL/GVL/Yard/Roll Shop) with realistic genealogy and per-area equipment/counters, applied via the demo reset job. Document at docs/demo/canonical-layout.md. | New Feature | 1) Layout after reset matches the documented canonical plant. 2) Genealogy intact across areas. 3) Process history/quality/risk realistic per material. 4) Re-applies cleanly via reset. | Partial | 35% | 4
PPIQ-T206 | Confirm SchemaViewResolver typed errors + join SafeSqlValidator | P02 | important | Track 1 — Workflow | App Backend | Schema Mapping / Validation Hardening | ARCHITECTURE · Layer L1/L2 boundary — SafeSqlValidator + the mapping resolver (Intelligence Architecture §2.1 and the Component Responsibility Matrix §3). SafeSqlValidator runs on generated join SQL at preview AND materialize (blocks DDL / cross-tenant / injection); the three typed errors — NoSuchView / NoSuchColumn / InvalidAggregateForType — are the resolver's contract, not a generic failure. No LLM in this path. ALREADY IN PLACE (30-May audit): SchemaConfigurationEndpoints.cs (423L) + SchemaConfigurationService.cs (380L) + GenericSchemaMappingEndpoints; SchemaConfigurationSafetyEndpointTests.cs (78L) cover SafeSqlValidator on generated SQL. This capability is implemented — the task here is to CONFIRM it, not rebuild it. Reference scope / behaviour: Closes residual rigor on v4 PPIQ-T108/T110 (capability shipped in GenericSchemaMappingEndpoints.cs but specific guarantees unconfirmed). Ensure /resolve returns distinct, testable errors — NoSuchView, NoSuchColumn, InvalidAggregateForType — not a generic failure, and that /joins/preview and /joins/materialize run SafeSqlValidator on the generated join SQL (blocking DDL/cross-tenant injection) and reject type-mismatched key pairs with a clear message. Add unit/integration tests for each path. | Bug Fix | Confirm (do NOT re-implement): 1) Resolver returns the three named error types on bad view/column/aggregate. 2) Malicious join SQL is blocked at preview and materialize. 3) Type-mismatched key pair rejected with a clear error. 4) Tests cover each case and run in CI. | Done | 85% | 3
PPIQ-T294 | Material genealogy join spine (heat->ladle->tundish->strand->slab->coil) as a canonical view | P02 | very important | Track 1 — Workflow | App Backend | Schema Mapping / Genealogy | ARCHITECTURE · Layer L1 — Ingest & Canonicalize (Intelligence Architecture §2.1). The genealogy spine (heat→ladle→tundish→strand→slab→coil→defect→QA) is THE substrate every higher layer reads — feature store (T209), inspection (T220–T222), the agent's genealogy tool (T232) and 'investigate this coil'. Produced via the mapping engine over the eight split sources, never hardcoded. STARTING POINT (31-May audit — already built): 201_ feature-store completion SQL includes genealogy_json; feature store keys to heat/material grain. WHAT REMAINS — the actual work of this task: Build the explicit canonical genealogy VIEW (heat->ladle->tundish->strand->slab->coil->defect->QA) via the mapping engine over the 8 split sources; test known lineages. FULL REFERENCE SPEC: Using the schema-mapping engine (NOT hardcoded SQL), produce a canonical genealogy view that threads the plant's identity chain across sources: HeatID (MeltShop, Postgres) -> Ladle/Tundish/Mould/Sequence/Strand/Slab (Caster, Oracle) -> coil (HSM, Oracle) -> surface defects (Parsytec, MySQL) -> QA samples (Excel). This is the spine the feature store (T209), inspection jobs (T220-T222), the assistant's genealogy tool (T232), and 'investigate this coil' all consume to walk a coil backward to its casting + melt conditions and forward to its defects/QA. | Enhancement | 1) Given any coil, the view resolves its slab, strand, sequence, tundish, ladle, and heat, and forward to its defects and QA samples. 2) It is produced via the mapping engine over the eight SPLIT demo sources, not a single pre-joined table. 3) The feature store and at least one inspection job consume it successfully. 4) Known demo lineages (hand-verified) resolve correctly end-to-end; orphan/edge cases return cleanly, not as errors. | Partial | 45% | 6
PPIQ-T247 | Connector smoke tests vs all six live DB sources + CSV/Excel golden files | P02 | very important | Track 2 — Hardening | App Backend | Connectors / Smoke Tests | ARCHITECTURE · Layer L1 — Connectors (×6) + factory (Component Responsibility Matrix §3): own typed, bounded source reads with no LLM. A bad host/credential must fail typed and bounded — never hang. STARTING POINT (31-May audit — already built): CsvConnectorSmokeTests + ExcelConnectorSmokeTests + ConnectorTruthContractTests; all 6 connectors built; demo-source containers now available to test against. WHAT REMAINS — the actual work of this task: Add live smoke tests vs the new MySQL/Oracle/MSSQL demo-source containers + CSV/Excel golden files; make it a gate. FULL REFERENCE SPEC: Author/extend smoke tests for PostgreSqlConnector, OracleConnector (×2), MsSqlConnector, MySqlConnector (×2), plus CSV/Excel, against the live demo-sources containers: ListTables, DescribeTable, SamplePage(100), FullSync, vs checked-in golden snapshots. Opt-in via PPIQ_RUN_CONNECTOR_INTEGRATION=1; wired to the post-deploy gate. Oracle gets a 90s warm-up. | New Feature | 1) Each connector passes against its seeded source. 2) Each detects drift if seed data is altered. 3) Oracle warm-up handled. 4) All wired to Jenkins post-deploy and logged. | Partial | 55% | 6
PPIQ-T207 | Add delta-import integration + resumability tests (T118 was unstarted) | P02 | very important | Track 2 — Hardening | App Backend | Import / Test Coverage | ARCHITECTURE · Layer L1 — DeltaImportExecutionService (Component Responsibility Matrix §3): owns resumable, zero-duplicate delta import. The crash-mid-batch → resume contract (no duplicates, correct cursor) is the behaviour under test. STARTING POINT (31-May audit — already built): DeltaImportResumabilityTests expanded (MaxRowsSmallBatch, Stage1Stage2AndFullCycle, RejectsAnonymousAccess per the v6 completion check). WHAT REMAINS — the actual work of this task: Confirm crash-mid-batch resume + duplicate suppression + schema-drift detection are all asserted and the suite is a CI gate <60s. FULL REFERENCE SPEC: Closes v4 PPIQ-T118, which had no implementation. The two-stage pipeline (source_table_dump_registry, two_stage_import_runs, two_stage_processed_watermarks; stage1/stage2/run-full-cycle endpoints) ships without tests. Author integration tests against seeded sources: cold full-load, incremental delta (only new rows beyond last_index), mid-run crash + resume (no duplicates), schema drift detection, idempotency. Opt-in via PPIQ_RUN_CONNECTOR_INTEGRATION=1; wire to the post-deploy gate. | New Feature | 1) Cold load then incremental delta imports only new rows. 2) Simulated crash resumes from last_index with no duplicates. 3) Source schema drift is detected and surfaced. 4) Suite < 60s, wired to Jenkins. | Partial | 70% | 4
PPIQ-T290 | Demo-source connection presets so DB-link config is one-click in the demo | P02 | important | Track 3 — Demo | App Frontend | Demo / DB Link UX | ARCHITECTURE · Layer L1 — Ingest & Canonicalize (Intelligence Architecture §2.1, Track-3 golden rule). Presets only pre-fill the live HMI flow (connect → schedule → import → see data); they never bypass the faithful-ingestion path or hardcode data. [NEW — discovered during the v6 implementation/debugging audit; not present in the 30-May snapshot] To run the live config demo smoothly (Vision Track 3), provide saved connection presets for the eight demo source systems (host=compose service name, port, db, read-only creds) that the presenter can select in the DB Link Configuration tab instead of typing under pressure. Presets are demo-data only, clearly labeled, and never auto-connect (the presenter still clicks through to prove the flow). | Enhancement | 1) The DB Link tab offers the 8 demo presets. 2) Selecting one fills the form; the presenter still clicks Test + Save (no hardcoded data path). 3) Presets use internal service-name hosts. 4) Presets are absent/disabled outside demo mode. | Not Started | 0% | 4
P03 — Page Builder & Widget Platform ¦ 7 tasks ¦ 41 hrs Vision section 2.1-2.2 core workflow and a Track-3 Golden-Rule prerequisite (pages must be USER-CREATED, never coded). Introduce a generic PageDefinition model, page CRUD + dynamic /pages/{slug} render, page persistence/ownership/sharing, the drag-drop widget canvas + library, then confirm and document the widget data-link + script layer that already exists. EXIT STATE (healthy): a user creates, lays out, data-binds, saves, reloads, and shares a custom page entirely from the HMI; nothing is hardcoded.
PPIQ-T289 | Generic Page-Definition model so pages are user-created from the HMI (not code) | P03 | very important | Track 1 — Workflow | App Backend | Page Builder / Persistence | ARCHITECTURE · Layer L2 — Describe (Intelligence Architecture §2.2) + the Widget & SQL Engine (§4). The PageDefinition aggregate is the durable model the canvas edits; widget cells hydrate through the compile-and-guard pipeline. A user page is data, never hardcoded React. STARTING POINT (31-May audit — already built): pageBuilder.api.ts (32L) + PageBuilderPage.tsx (199L) + page-builder.css; a PageBuilder surface now exists frontend-side. WHAT REMAINS — the actual work of this task: Confirm a backend PageDefinition aggregate (slug/title/owner/layout JSON/sharing) persists pages in PG and /pages/{slug} renders them generically — the durable model behind the UI. FULL REFERENCE SPEC: Introduce a PageDefinition aggregate persisted in Postgres: id, slug (unique, URL-safe), title, owner, a layout JSON describing widget placements (grid position/size + the DashboardWidgetDefinition each cell renders), visibility/sharing, and audit columns. Expose Page CRUD endpoints and render any page generically at /pages/{slug} by reading the stored layout and hydrating each widget through the existing widget pipeline (DashboardWidgetDefinition + the widget script layer, T242). This is the prerequisite for the page-builder UX (T240/T241/T243): the canvas edits a PageDefinition; it must never emit code. | Enhancement | 1) A page can be created, renamed, re-laid-out, and deleted entirely via the API/HMI and survives an app restart (persisted in PG). 2) GET /pages/{slug} renders the stored layout generically — no page content is hardcoded in React for user pages. 3) Widget cells in a stored layout hydrate through the existing DashboardWidgetDefinition + script-layer path. 4) Round-trips on the demo dataset: build a page of 3+ data-bound widgets, reload, and it is identical. 5) Slugs are unique and URL-safe; invalid layouts are rejected with a clear error. | Partial | 50% | 8
PPIQ-T240 | Page CRUD + /pages/{slug} dynamic load | P03 | very important | Track 1 — Workflow | App Frontend | Page Builder / Page CRUD | ARCHITECTURE · Layer L2 — Describe (Intelligence Architecture §2.2). Pages are description surfaces; /pages/{slug} renders the stored layout generically. Forbidden here: causal language — a chart shows a trend, it never says one thing causes another. STARTING POINT (31-May audit — already built): pageBuilder API client + PageBuilderPage present; page CRUD surface emerging. WHAT REMAINS — the actual work of this task: Confirm create/rename/delete + /pages/{slug} dynamic load round-trip and persist across restart. FULL REFERENCE SPEC: Vision §2.1.1/2.1.3: create/edit/delete/save user pages, persisted per-user, and a dynamic /pages/{slug} route loading a stored page definition (backend /api/pages/{slug}, 404 on missing). This is the page model the ML page generator (P04) emits into. Standard* primitives. | New Feature | 1) Create, rename, save, delete a page; reload restores it. 2) /pages/{slug} loads a stored page; missing slug 404s. 3) Pages are per-user/owner scoped. 4) The ML-generated page round-trips through the same model. | Partial | 45% | 6
PPIQ-T243 | Page persistence, ownership & sharing (backend) | P03 | important | Track 1 — Workflow | App Backend | Page Builder / Persistence | ARCHITECTURE · Layer L2 — Describe (Intelligence Architecture §2.2 + §4). Page persistence/ownership/sharing is the backend store the ML page generator (P06) and the builder (P03) both emit into; tenant-scoped. STARTING POINT (30-May audit — already built): DashboardWidgetDefinition persistence exists; no Page entity ownership/sharing. WHAT REMAINS — the actual work of this task: Add Page persistence + ownership + sharing (backend) to support T240. FULL REFERENCE SPEC: Backend page store (page, owner, layout json, widget bindings, version), endpoints for CRUD + list-by-owner, optional share/visibility. Tenant-scoped. Used by P04 generated pages and P08 builder. | New Feature | 1) Pages persist with layout + bindings + version. 2) List-by-owner returns the user's pages. 3) Tenant isolation enforced. 4) Round-trip preserves layout and bindings. | Partial | 30% | 4
PPIQ-T241 | Drag-drop widget canvas + widget library | P03 | very important | Track 1 — Workflow | App Frontend | Page Builder / Canvas & Library | ARCHITECTURE · Layer L2 — the Widget & SQL Engine, wizard step contract (Intelligence Architecture §4.3): Source → Shape → Script/validate → Preview → Save. The canvas writes widget placements into the PageDefinition layout; per-widget config reuses WidgetBuilderWizard. STARTING POINT (31-May audit — already built): DragGhost.tsx/.css + utils/dragPerformance.ts (79L) + PageBuilderPage establish a drag-drop canvas foundation. WHAT REMAINS — the actual work of this task: Finish the widget LIBRARY + drag/drop/resize onto the canvas writing into the PageDefinition layout; e2e drag correctness (T244). FULL REFERENCE SPEC: Vision §2.1.2: a library of all widgets (every chart type, KPI, and the filtering tools — date-time picker, list-of-values). Drag-drop onto the page, arrange, Save; editing can add/remove/rearrange. Drag/resize/min/max correct (Vision §2.5). Reuse WidgetBuilderWizard for per-widget config. | New Feature | 1) Drag a widget from the library to the canvas, arrange, save; reload preserves layout. 2) Resize/min/max/move behave correctly with no overlap glitches. 3) Date-time and list filters available as widgets. 4) Standard* primitives; visual regression baseline captured. | Partial | 45% | 10
PPIQ-T242 | Widget edit: link to DB values + script layer in the builder | P03 | very important | Track 1 — Workflow | App Frontend | Page Builder / Widget Config | ARCHITECTURE · Layer L2 — the Widget & SQL Engine, compile-and-guard pipeline (Intelligence Architecture §4.2): Author → Compile → Validate → Execute. WidgetQueryExpressionService compiles the expression + binding into PARAMETERISED SQL (never string-concatenated user input); SafeSqlValidator + the safety registry gate it at preview AND save AND execute. Generic power, zero injection surface — the user never writes raw SQL that reaches the DB unchecked. ALREADY IN PLACE (30-May audit): WidgetScriptStep.tsx (174L) + WidgetQueryExpressionService.cs (418L) + WidgetQueryExpressionDtos + DashboardWidgetDefinition expression columns (117 SQL) + WidgetQueryExpressionServiceTests. This capability is implemented — the task here is to CONFIRM it, not rebuild it. Reference scope / behaviour: Vision §2.2.1–2.2.3: the selected widget has Edit to link it to a list of values from the canonical schema and add a script-layer expression (e.g. bar chart grouped by shift). Wire the existing widget compiler (WidgetQueryExpressionService + WidgetScriptStep) into the live builder, with schema-aware autocomplete from the canonical catalog and SafeSqlValidator on save + execute. | Enhancement | Confirm (do NOT re-implement): 1) Editing a widget links it to a canonical view's columns and a script expression. 2) Autocomplete suggests views/columns contextually. 3) Save is gated on a valid, safe expression. 4) Execution honors the second-pass SafeSqlValidator. | Done | 80% | 6
PPIQ-T244 | Page builder e2e + drag/resize correctness tests | P03 | important | Track 2 — Hardening | App Frontend | Page Builder / Test Coverage | ARCHITECTURE · Layer L2 — the Widget & SQL Engine (Intelligence Architecture §4). The e2e proof that the author→compile→validate→preview→save→reload loop renders identically and never emits a forbidden phrase. BUILD FROM SCRATCH (30-May audit: No page-builder drag/resize e2e tests.). SPECIFICATION: Playwright e2e: create page => drag two widgets => configure one with a script expression => resize/move => save => reload renders identically. Assert no layout drift and no forbidden phrase. | New Feature | 1) The build-save-reload flow renders identically (snapshot). 2) Resize/move persist exactly. 3) Forbidden-phrase assertion passes. 4) Wired to the PR gate. | Not Started | 5% | 4
PPIQ-T278 | Widget script grammar reference for power users | P03 | important | Track 1 — Workflow | Documentation | Documentation / Widget Grammar | ARCHITECTURE · Layer L2 — the Widget & SQL Engine (Intelligence Architecture §4). Documents the implemented expression grammar, the canonical schema views available, and the SafeSqlValidator blocked patterns and why — the power-user contract for §4.2/§4.3. STARTING POINT (30-May audit — already built): WidgetScriptStep + WidgetQueryExpressionService implement a script grammar; no power-user reference doc. WHAT REMAINS — the actual work of this task: Write the widget script grammar reference for power users (document the implemented expression language). FULL REFERENCE SPEC: docs/widget-grammar/reference.md: the full grammar, every aggregate function, every filter operator, every limitation. 10+ worked examples. The explicit list of canonical schema views available. The SafeSqlValidator blocked patterns and why. Linked from the widget editor as inline help. | New Feature | 1) Reference covers the full grammar. 2) 10+ worked examples each compile and execute. 3) Linked from the WidgetExpressionEditor as inline help. | Partial | 35% | 3
P04 — ML Engine: Data Foundation & Providers ¦ 7 tasks ¦ 43 hrs Vision section 3 prerequisite. Make the multi-grain feature store, the metallurgical feature engineering, the outcome catalog (defect-rate/class/severity/position, the equipment-vs-production cascade-downtime distinction, KPI-as-view), the type-aware compute interface, the pgvector knowledge base, and the narrative/embedding PROVIDER ABSTRACTION (API-default, self-hostable) all real over the mapped demo data. EXIT STATE (healthy): features and outcomes populate at every grain on the demo data, the KB is queryable, and the NL layer is swappable without touching callers.
PPIQ-T209 | Multi-grain feature store schema (heat/strand/coil/location) | P04 | very important | Track 1 — Workflow | Database | ML Engine / Feature Store | ARCHITECTURE · Layer L3 — Feature Store (Intelligence Architecture §2.3). Multi-grain (heat/strand/coil/location) values, each carrying its native grain + genealogy keys. Owner: ppiq_ml_refresh_feature_store_v6 (SQL). Forbidden here: correlation or ranking — L3 prepares the inputs, it never measures relationships. ALREADY IN PLACE (31-May audit): 201_phase02_ml_feature_store_v6_completion.sql adds ppiq_ml_refresh_feature_store_v6 + genealogy_json; 200_ base (8 tables) intact. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §1.1: build the multi-grain feature store the entire engine learns from, materialized from the canonical generic schema (P02/P03 of v4). Each feature and outcome carries its native grain and the genealogy keys (heat_id, sequence_id, strand, slab_id, coil_id) needed to join across grains. Tables for feature definitions, feature values per grain, and outcome values; EF entities + configuration + migration. Refreshed by the stage-2 import job. Versioned. | New Feature | Confirm (do NOT re-implement): Confirm multi-grain refresh populates values on the demo data at each grain. | Done | 90% | 8
PPIQ-T210 | FeatureEngineeringService — metallurgical derived features | P04 | very important | Track 1 — Workflow | App Backend | ML Engine / Feature Engineering | ARCHITECTURE · Layer L3 — Feature Store, derived metallurgy (Intelligence Architecture §2.3). FeatureEngineeringService computes CEV, true superheat (tundish temp − liquidus), casting-speed mean/delta, residency minutes and shift bucketing — deterministic math, each value stored with provenance. No model here. ALREADY IN PLACE (31-May audit): 201_ defines derived features: chemistry.cev, thermal.true_superheat, casting.speed_mean, casting.speed_delta, operations.residency_minutes, operations.shift (verified by check script). This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §1.2: extend FeatureEngineeringService to assemble the feature matrix at a SELECTABLE grain (coil-level default; heat-level option) and compute derived features: carbon equivalent (CEV) from chemistry; true superheat = tundish temp − liquidus (liquidus estimated from composition); casting-speed aggregates (mean/max/std/range, count of speed changes, time in transition); reduction ratio; cooling rate; specific energy; time-above-temperature; categorical encodings (grade family, gauge band, spec class, strand, crew/shift). Explicit missingness handling (pairwise deletion with n per pair; 'missing' as informative category; flag features whose missingness correlates with the outcome). | New Feature | Confirm (do NOT re-implement): Confirm the derived features compute against the golden dataset with provenance; add unit tests on known inputs. | Done | 85% | 8
PPIQ-T211 | Outcome definitions: defect-rate/class/severity/position, cascade-downtime, KPI-as-view | P04 | important | Track 1 — Workflow | App Backend | ML Engine / Outcome Modeling | ARCHITECTURE · Layer L3 — the outcome catalog (Intelligence Architecture §2.3). Outcomes modelled rigorously: defect rate per m²/class/severity/position; downtime with the equipment-vs-production-stoppage distinction; KPIs as canonical views. QualityLabelBuilderService owns the labels. ALREADY IN PLACE (31-May audit): 201_ defines outcomes: defect.rate_per_m2/class/severity/position, downtime.cascade_minutes, kpi.prime_yield/energy_per_ton/throughput (verified by check script). This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §1.3: model outcomes rigorously rather than yes/no. Defects as a rate normalized to coil area/tonnage (defects per m²), plus class (multinomial), severity (graded), and position (head/body/tail, edge/center). Downtime using the plant taxonomy (production stoppage vs equipment failure; electrical/operation/production/mechanical/hydraulic) against CASCADE-adjusted duration, not the raw event. KPIs defined as canonical views (prime yield, energy/ton, throughput) via the KPI-as-view layer. | New Feature | Confirm (do NOT re-implement): Confirm each outcome resolves to values on the demo data. | Done | 85% | 5
PPIQ-T293 | Cascade/buffer-aware downtime outcome modeling (equipment vs production stoppage) | P04 | important | Track 1 — Workflow | App Backend | ML / Outcome Modeling | ARCHITECTURE · Layer L3 — the cascade/buffer-aware downtime outcome (Intelligence Architecture §2.3 + §5 lever 2). Equipment stoppage ≠ production stoppage: a 20-min HSM stop can be buffer-absorbed (zero loss) while a 3-min caster stop can cascade to a 4–6 h production stoppage. Modelling this is what keeps the L4 downtime correlations honest. STARTING POINT (31-May audit — already built): downtime.cascade_minutes outcome defined in 201_; downtime source shape present. WHAT REMAINS — the actual work of this task: Confirm the outcome distinguishes equipment-stoppage vs production-stoppage minutes with buffer/cascade context in the demo data. FULL REFERENCE SPEC: The vision's downtime DB encodes a subtle truth: equipment stoppage != production stoppage (a 20-min HSM stop can be absorbed by TF buffer + caster slow-down with zero production loss, while a 3-min caster water-pump stop can cause a 4-6h production stoppage via sequence rebuild). The cascade-downtime outcome (T211) must model this distinction (equipment-stoppage-min vs production-stoppage-min, with propagation/buffer context) or the correlations will be misleading. Add the outcome definition + the demo data shape to support it. | Enhancement | 1) Outcome definitions distinguish equipment-stoppage from production-stoppage minutes. 2) The downtime demo dataset includes buffer-absorbed and cascade-amplified cases. 3) A learning run over the demo data ranks contributors to production (not merely equipment) stoppage sensibly. 4) Documented in the outcome catalog. | Partial | 50% | 5
PPIQ-T212 | ICorrelationComputeEngine interface + .NET default implementation | P04 | very important | Track 1 — Workflow | App Backend | ML Engine / Compute Abstraction | ARCHITECTURE · Layer L4 — Correlate, the compute abstraction (Intelligence Architecture §2.4, §6). ICorrelationComputeEngine keeps the math swappable; the default delegates to the type-aware Postgres v6 core and returns typed results. Honesty boundary: deterministic, auditable statistics — no LLM ever computes or ranks a correlation. ALREADY IN PLACE (31-May audit): ppiq_ml_compute_correlations_v6 entrypoint in 201_ + PostgresCorrelationComputeEngine.cs (91L) tagged 'postgres-v6-type-aware' (per check script). This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §2.4 / §6: define ICorrelationComputeEngine so the compute is swappable. Default implementation is .NET in-process (Math.NET Numerics for statistics, ML.NET for regularized regression / tree importances), with PostgreSQL doing heavy data reduction (corr(), regr_*, group-bys). Keep one runtime; deterministic, auditable math in the repo. The interface is the escape hatch for a future Python implementation (mixed-effects, survival, defect-image CV) without touching the job system, persistence, governance, or UI. | New Feature | Confirm (do NOT re-implement): Confirm the .NET engine delegates to the v6 type-aware compute and returns typed results. | Done | 80% | 6
PPIQ-T213 | pgvector knowledge base provisioning (assistant prerequisite) | P04 | important | Track 1 — Workflow | Database | ML Assistant / Vector Store | ARCHITECTURE · Layer L5/L6 — the knowledge base (Intelligence Architecture §2.5, §4.3). pgvector provisions embeddings + structured columns (area, defect class, grade, line, window, q-value) for HYBRID retrieval. DeterministicEmbeddingProvider keeps retrieval offline-safe and identical across environments — no external service required. ALREADY IN PLACE (31-May audit): 200_ KB provisioning + ppiq_ml_search_kb intact; DeterministicEmbeddingProvider.cs (49L) gives an offline embedding path. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §4.3: enable the pgvector extension in PostgreSQL 17 and provision the knowledge-base tables the §3.3 assistant retrieves from — embeddings + metadata for (a) learned findings, (b) case memory, (c) domain knowledge documents — with structured columns (area, defect class, grade, line, window, q-value) to support HYBRID retrieval (semantic + SQL filter). No new datastore or service. EF entities + migration; IEmbeddingProvider interface (API-default, self-hostable). | New Feature | Confirm (do NOT re-implement): Confirm pgvector is installed in the target image so KB search runs (not just compiles). | Done | 85% | 5
PPIQ-T292 | INarrativeProvider / IEmbeddingProvider abstraction with self-hostable + API impls | P04 | very important | Track 1 — Workflow | App Backend | ML Assistant / Provider Abstraction | ARCHITECTURE · Layer L6 — the provider abstraction (Intelligence Architecture §2.6.2 box, §6 'air-gappable by design'). ApiNarrativeProvider / LocalNarrativeProvider / ConfiguredNarrativeProvider: the same agent runs hosted, self-hosted, or deterministic-local. Only ABSTRACTED findings ever cross an external boundary — never raw plant rows or PII; the app runs fully air-gapped on the local provider. ALREADY IN PLACE (31-May audit): INarrativeProvider + IEmbeddingProvider interfaces; ApiNarrativeProvider(98L) + LocalNarrativeProvider(64L) + ConfiguredNarrativeProvider(53L, switches local/api) + DeterministicEmbeddingProvider(49L); MlProviderEndpoints(62L). This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: The engine + assistant design mandates the natural-language layer sit behind INarrativeProvider/IEmbeddingProvider — API-default for quality, self-hostable for air-gapped/governance-sensitive customers, with only abstracted findings ever crossing an external boundary ('works fully air-gapped; AI narration optional' is a selling point). Define these interfaces now and provide (a) an API-backed impl and (b) a local/null impl, so T230-T233 build against the abstraction rather than a hardcoded provider. | Enhancement | Confirm (do NOT re-implement): Confirm only abstracted findings cross the API boundary (test) and the app runs fully offline on the local provider. | Done | 90% | 6
P05 — ML Engine: Scheduled Correlation Learning ¦ 6 tasks ¦ 38 hrs Vision section 3.1 — the single biggest gap and the analytical heart of the product. Build the four scheduled learning jobs (process-vs-defect, process-vs-downtime, process-vs-KPI, weekly overall), the type-aware statistical association engine, the full validity machinery (Benjamini-Hochberg q-values, effect-size-first ranking, power, bootstrap stability, confounding/VIF), per-job scheduling + backoff gated by MlReadiness, extended result persistence into the Jobs Monitor, and golden-dataset tests. EXIT STATE (healthy): the engine recovers known injected correlations with correct effect sizes, rejects spurious ones under FDR control, and the jobs are schedulable and monitorable.
PPIQ-T214 | Define the four learning job types + EnsureMlJobDefinitions (Vision §3.1.1–3.1.4) | P05 | very important | Track 1 — Workflow | App Backend | ML Engine / Job Definitions | ARCHITECTURE · Layer L4 — Correlate (Intelligence Architecture §2.4). The four scheduled learning jobs (process×defect, ×downtime, ×KPI, weekly overall) are first-class job definitions flowing through the unified job model so each appears in the Jobs Monitor. ALREADY IN PLACE (31-May audit): 204_ ml_learning_job_catalog_v1 registers the 4 jobs: ML_PROCESS_VS_DEFECT, _VS_DOWNTIME, _VS_KPI, ML_WEEKLY_OVERALL with schedules/windows/readiness gates. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §2.1: formalize the four scheduled jobs as first-class JobDefinitionType entries — (1) process-params × defect-id, (2) × downtime-id, (3) × KPI-id (daily, off-hours, user-overridable), (4) weekly overall pass across all data. Extend the existing EnsureMlJobDefinitions/IsMlJob scaffolding. Each flows through the unified job model so it appears in the Jobs Monitor (§3.1.5). | New Feature | Confirm (do NOT re-implement): Confirm the 4 jobs surface in the Jobs Monitor as schedulable/overridable. | Done | 90% | 3
PPIQ-T215 | Learning worker — type-aware statistical association engine | P05 | critical | Track 1 — Workflow | App Backend | ML Engine / Learning Worker | ARCHITECTURE · Layer L4 — Correlate, THE BRAIN (Intelligence Architecture §2.4). Type-aware method selection: Pearson (continuous, linearity-checked), Spearman (monotonic), point-biserial (continuous–binary), chi-square + Cramér's V (categorical), mutual information (non-linear), Lasso (multivariate screen). Owner: 204_ml_learning_core (SQL) + CorrelationService. NO LLM — a language model never computes, ranks or judges a correlation. STARTING POINT (31-May audit — already built): 204_ ppiq_ml_run_learning_job_v1 computes the sweep: Pearson/point-biserial/Cramer's-V, effect-size via abs(corr), effective-n by DISTINCT heat, effect-size buckets, stability; MlLearningEndpoints POST /jobs/{code}/run + GET /results; golden-dataset seeder ppiq_ml_seed_phase45_golden_dataset. WHAT REMAINS — the actual work of this task: The compute exists in-DB and runs ON DEMAND but is NOT yet driven by the Worker on a schedule (Worker still runs only Import/Quality/Risk/Delta). Wire T217 scheduling; broaden methods (chi-square, MI, Lasso screen) and confirm golden-dataset recovery in tests (T219). FULL REFERENCE SPEC: Build a learning worker that, for each scheduled job (T214), sweeps every available process parameter against each outcome in the target family and persists ranked, statistically-qualified associations. The engine is DETERMINISTIC and IN-HOUSE (never an LLM task). It must be TYPE-AWARE: pick the correct measure per variable-pair type — Pearson (continuous-continuous, linearity-checked), Spearman (monotonic/ordinal), point-biserial (continuous-binary), chi-square + Cramer's V (categorical-categorical), mutual information (non-linear), and Lasso for multivariate screening. It reads features/outcomes from the feature store (T209-T211) via ICorrelationComputeEngine (T212), and writes effect size, direction, effective-n, and the raw statistic for every pair; the heavy validity layer (FDR, power, stability, confounding/VIF) is applied in T216 before anything is surfaced as a finding. | New Feature | 1) Over a golden dataset with KNOWN injected correlations, the engine recovers them with correct sign and effect-size magnitude within tolerance. 2) Variable-pair type selection is correct (a continuous-binary pair uses point-biserial, a categorical pair uses Cramer's V, etc.) — asserted by tests. 3) Every persisted association carries effect size, direction, effective-n, and the underlying statistic. 4) A full sweep over the demo dataset completes within the configured job budget and writes correlation_result rows consumable by the Jobs Monitor (T218). 5) No LLM is invoked anywhere in the compute path. | Partial | 70% | 12
PPIQ-T216 | Statistical validity machinery (FDR, effect-size, power, stability, confounding, VIF) | P05 | critical | Track 2 — Hardening | App Backend | ML Engine / Statistical Rigor | ARCHITECTURE · Layer L4 — the validity machinery (Intelligence Architecture §2.4, §6 'every finding is qualified'). Benjamini-Hochberg q-values (FDR), effect-size-first ranking, statistical power, bootstrap stability, confounding/stratification, VIF for collinearity, effective-n counted by independent heat. Sub-threshold findings are FLAGGED, not promoted. STARTING POINT (31-May audit — already built): 204_ implements Benjamini-Hochberg q-values, p-value approximation, effect-size-first buckets, effective-n by independent heat, stability flags — the honesty machinery is present in the core. WHAT REMAINS — the actual work of this task: Add power, bootstrap stability (vs heuristic), and confounding/VIF; confirm FDR control rejects injected spurious correlations on the golden dataset. FULL REFERENCE SPEC: Per design doc §2.3 — the rigor that separates professional from naive. Wrap every result with: effect-size-first strength buckets (not p); Benjamini–Hochberg q-values across the full test family; a power/minimum-effective-n gate; bootstrap stability (CI on r itself + replication across time sub-windows; flag unstable findings); confounding handling (stratify by grade/line + partial-correlation adjustment, warn when an association collapses after adjustment); multicollinearity reporting (VIF; present grouped drivers, not duplicates). Cluster-robust standard errors by heat to correct pseudo-replication from coils nested in heats. | New Feature | 1) Every result carries effect size, q-value, CI, effective-n, stability flag. 2) Under-powered pairs are gated out. 3) A planted-noise column does not survive FDR. 4) A confounded association is flagged after stratification. 5) Effective-n reflects heat-clustering, not raw coil count. | Partial | 65% | 10
PPIQ-T217 | Per-job scheduling, backoff & MlReadiness governance gates | P05 | important | Track 1 — Workflow | App Backend | ML Engine / Scheduling & Governance | ARCHITECTURE · Layer L4/L5 — MlReadinessService is the gate (Intelligence Architecture §2.5 box). Before any learning job or score runs it checks for enough independent, non-degenerate data; under-powered analyses are REFUSED and rescheduled with backoff — the engine never emits a confident-looking result from three heats. BUILD (31-May audit: ml_learning_job_catalog_v1 has backoff_minutes/max_backoff_minutes/next_run_hint/readiness_gate_code columns, but the Worker does not execute these jobs.). WHAT REMAINS: Wire the four learning jobs into the Worker (or a scheduler) with per-job schedule + backoff + MlReadiness gating; this is what makes them 'scheduled' per Vision 3.1. SPECIFICATION: Per design doc §2 + §3.1: add per-job off-hours scheduling with failure backoff and concurrency control, and extend MlReadinessService into governance gates — minimum sample size, label completeness, feature freshness, and a training-window selector (last week/month/year). The engine refuses to learn on insufficient/ungoverned data and reports why (preserving the no_production_prediction honesty). | Enhancement | 1) A job below the sample/label threshold is blocked with a clear readiness reason. 2) Backoff doubles the retry interval up to a cap. 3) Window selector changes the data range used. 4) Readiness gates reflect the real governance state. | Not Started | 15% | 5
PPIQ-T218 | Persist correlation_result (extended) + Jobs Monitor integration | P05 | important | Track 1 — Workflow | Database | ML Engine / Results Persistence | ARCHITECTURE · Layer L4 — Correlate, persistence (Intelligence Architecture §2.4). Ranked, qualified associations persist to ml_correlation_results_v2 with outcome_key, method, effect_size, q_value, power, stability, effective_n and finding_status, and surface in the Jobs Monitor. STARTING POINT (31-May audit — already built): 204_ ml_learning_results_v1 persists effect_size/q_value/p_value/effective_n/stability + indexes; MlLearningEndpoints GET /results + /status; AdminJobsMonitorTab renders runs. WHAT REMAINS — the actual work of this task: Confirm learning runs appear in the Jobs Monitor with last-run/status/duration and results are queryable per job. FULL REFERENCE SPEC: Per design doc §2.5 / §2.6: extend CorrelationResult with model_version_id, feature_key+grain, outcome_key+type, method, coefficient, effect_size(+type), p_value, q_value, ci_low/high, effective_n, stratum, stability_score+is_stable, window. Ensure all four learning jobs surface in Administrator → Jobs Monitor (status OK/crash/timeout, last-run, duration, next-run, run-now/pause, active progress). | Enhancement | 1) Results persist with the full evidence columns incl. q-value and effective-n. 2) Learning jobs appear in the Jobs Monitor with correct status/last-run/duration/next-run. 3) Run-now triggers a job and progress ticks. 4) A crashed job shows failed + last error. | Partial | 60% | 4
PPIQ-T219 | ML learning engine tests on golden datasets | P05 | very important | Track 2 — Hardening | App Backend | ML Engine / Test Coverage | ARCHITECTURE · Layer L4 — the brain's acceptance proof (Intelligence Architecture §2.4). On the golden dataset the engine must RECOVER injected correlations with correct effect-size sign/magnitude, produce BH q-values, and REJECT spurious pairs under FDR — behaviour, not regex over SQL text. STARTING POINT (31-May audit — already built): ppiq_ml_seed_phase45_golden_dataset() seeds a known dataset; tools/phase45/* include underflow + categorical-learning fixes. WHAT REMAINS — the actual work of this task: Add explicit tests that the engine RECOVERS the injected correlations with correct effect sizes and REJECTS spurious ones under FDR; wire to CI. FULL REFERENCE SPEC: Per design doc §2.3: tests with deterministic golden datasets where correct correlations are known by construction (planted signal + noise). Assert the engine recovers planted associations within tolerance, ranks them correctly, rejects pure noise after FDR, respects governance gates, persists correct provenance, and is reproducible for a fixed seed. Performance test bounds the run on the standard demo size. | New Feature | 1) Engine recovers planted associations and rejects noise columns. 2) Ranking matches known ground-truth order. 3) Governance gate blocks an under-sampled run. 4) Deterministic; wired to the Jenkins gate. | Partial | 35% | 4
P06 — ML Engine: Inspection Jobs to Generated Pages ¦ 6 tasks ¦ 31 hrs Vision section 3.2. On the learning engine, build the on-demand Inspection Job (select defect/downtime/KPI + window + name), the runner with progress, the mechanism that AUTO-GENERATES an analysis page of widgets/charts from the result (no hardcoding), the tabbed generated-page shell (one tab per saved job), periodic scheduling into the Jobs Monitor, and the full run->generate->save->schedule e2e. EXIT STATE (healthy): a user runs an inspection from the HMI and gets a saved, schedulable, evidence-backed analysis page.
PPIQ-T220 | Inspection Job domain + persistence + endpoints | P06 | very important | Track 1 — Workflow | App Backend | ML Engine / Inspection Jobs | ARCHITECTURE · Layer L5 — Reason, inspection → generated pages (Intelligence Architecture §2.5). The operator selects an outcome + window and names the inspection; the domain/persistence here is what the runner (T221) executes and the auto-page (T222) renders — provably configured, never hardcoded. STARTING POINT (31-May audit — already built): Phase2InvestigationEndpoints.cs (598L) + SaveInspectionJobModal.tsx + MaterialFeatureVector(125L) + QualityLabelBuilderService(245L) provide investigation building blocks. WHAT REMAINS — the actual work of this task: Add the first-class InspectionJob domain (target defect/downtime/KPI + window + name) + persistence + CRUD; the save-modal is waiting on it. FULL REFERENCE SPEC: Per design doc §3.2.1 (Vision §3.2.1): user selects one defect-id / downtime-id / KPI-id + window (last week/month/year) + a name. Implement InspectionJob entity + EF config + migration + endpoints (create/list/get/run/schedule/delete). Back the already-wired SaveInspectionJobModal with the real POST. Authorization + license gating (Pro Plus/Enterprise). | New Feature | 1) Creating an inspection job from the modal persists it and returns an id. 2) Listing shows target, window, schedule. 3) Non-licensed tier is gated with a clear hint. 4) Audit row on create/run/schedule. | Partial | 35% | 5
PPIQ-T221 | Inspection Job runner — on-demand analysis with progress | P06 | very important | Track 1 — Workflow | App Backend | ML Engine / Inspection Runner | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). The runner executes the L4 analysis on demand for the chosen outcome/window — the bridge from a saved inspection to a real correlation result. BUILD FROM SCRATCH (30-May audit: No inspection job runner. Depends on the learning engine (T215).). SPECIFICATION: Per design doc §3.2.2 (Vision §3.2.2): the runner executes an inspection job via the learning engine over the selected target + window and produces a ranked 'most influential parameters' result with evidence (coefficient, q-value, effect size, supporting slices, stability). Returns a structured InspectionResult the page generator consumes. Run-now returns 202 + progress (reuse the demo-lifecycle progress pattern). | New Feature | 1) Run-now over a demo target returns a ranked contributor list with evidence in bounded time. 2) Progress endpoint ticks through stages. 3) Same input+window => deterministic ranking. 4) Results persisted and linked to the job. | Not Started | 5% | 6
PPIQ-T222 | Auto-generate analysis page from inspection result (no hardcoding) | P06 | very important | Track 1 — Workflow | App Backend | ML Engine / Page Generation | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). The runner auto-builds a page of widgets/charts FROM the result — provably configured from the analysis, never a hardcoded page. BUILD (31-May audit: CorrelationService(437L)/CorrelationEndpoints(717L) can produce correlation results, but there is no mechanism that AUTO-GENERATES a page of widgets from an inspection result.). WHAT REMAINS: Build the result->generated-page mechanism (widgets chosen from the result, no hardcoding) — Vision 3.2 core. SPECIFICATION: Per design doc §3.2.2 + Track-3 golden rule: on completion, auto-compose a dashboard page from REAL widget definitions bound to the result — top-contributors bar, contributor trend over the window, distribution by target, correlation matrix — emitted into the page model (P08), the same definitions a user could build by hand. Regenerating after a re-run updates the page in place. No hardcoded layout. | New Feature | 1) A completed run produces a saved-page definition referencing real widgets bound to result data. 2) Opening the page renders live widgets. 3) Re-run updates the page in place. 4) The page round-trips through the page model — zero hardcoded layout. | Not Started | 10% | 6
PPIQ-T223 | Correlation Page shell — tabbed generated pages (replace stub) | P06 | very important | Track 1 — Workflow | App Frontend | ML Engine / Correlation Page | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). The tabbed generated-correlation shell is the surface the inspection result populates; description of associations, with the L4 qualification carried through. STARTING POINT (31-May audit — already built): Phase56CorrelationPage + CorrelationService/Endpoints render correlation content with tabs. WHAT REMAINS — the actual work of this task: Evolve to one generated tab PER saved inspection job (not a static page); depends on T222. FULL REFERENCE SPEC: Per design doc §3.2.x (Vision §3.2): replace the 5-line CorrelationPage.tsx stub with the full ML Correlation area — a StandardTabs surface where each generated inspection-job page is a tab, with run-now, a save toggle, and a schedule control (hourly/daily) per tab. Standard* primitives, license gating, DataFetchBoundary states. | New Feature | 1) Page lists inspection jobs as tabs; selecting one renders its generated widgets. 2) Run-now refreshes the tab via the runner with a progress panel. 3) Save persists the page; Schedule enqueues a periodic job in the Jobs Monitor. 4) Standard* primitives only; visual regression baseline captured. | Partial | 35% | 6
PPIQ-T224 | Schedule inspection jobs periodically + Jobs Monitor integration | P06 | important | Track 1 — Workflow | App Backend | ML Engine / Scheduling | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). Periodic inspection scheduling flows through the unified job model and the readiness gate, appearing in the Jobs Monitor. BUILD FROM SCRATCH (30-May audit: No inspection-job scheduling. Jobs Monitor exists for system jobs.). SPECIFICATION: Per design doc §3.2.3 (Vision §3.2.3): allow a saved inspection job to run periodically (hourly/daily/user-defined) or on demand. Register scheduled inspection runs in the unified job model so they appear in the Jobs Monitor with status/last-run/duration, and a periodic run regenerates the saved page. Rate-limited to avoid overlap. | Enhancement | 1) Scheduling a job enqueues a recurring run visible in the Jobs Monitor. 2) Each periodic run regenerates the page and records last-run/duration. 3) Pausing/deleting the schedule stops future runs. 4) Rate-limited against overlap. | Not Started | 5% | 4
PPIQ-T225 | E2E + integration tests for run -> generate -> save -> schedule loop | P06 | important | Track 2 — Hardening | App Frontend | ML Engine / Test Coverage | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). End-to-end proof that run → generated page works, including the readiness-refusal path on under-powered data. BUILD FROM SCRATCH (30-May audit: No run->generate->save->schedule e2e tests.). SPECIFICATION: Per design doc §3.2: Playwright e2e + backend integration covering the full loop — create inspection job => run-now => generated page renders contributors => save => schedule => periodic run regenerates. Assert absence of the forbidden phrase and forbidden ML claims. | New Feature | 1) The full loop passes against staging. 2) Generated page shows the expected top contributor for a planted-signal demo target. 3) Forbidden-phrase + forbidden-claim assertions pass. 4) Test < 120s, wired to the post-deploy gate. | Not Started | 0% | 4
P07 — Risk Scorer & Model Governance ¦ 4 tasks ¦ 18 hrs Vision section 3 cross-cutting. The transparent additive scorer already exists; finish exact-contribution validation, calibration/reliability, model-registry lifecycle + provenance + reproducibility, and drift monitoring + champion/challenger promotion. EXIT STATE (healthy): every risk score decomposes exactly into named contributions, is calibrated on demo data, and every persisted result links to a reproducible registry entry.
PPIQ-T236 | Transparent additive risk scorer with exact contribution decomposition | P07 | important | Track 1 — Workflow | App Backend | ML Engine / Risk Scorer | ARCHITECTURE · Layer L5 — Reason, RiskScoreService (Intelligence Architecture §2.5). An ADDITIVE score whose contributions decompose exactly into named, signed terms — every score is reproducible and explainable, never a black box. ALREADY IN PLACE (31-May audit): RiskScoreService(392L) + RiskScore(103L, explanation) + RiskScoreEndpoints(248L) + RiskPredictionDtos(70L); additive decomposition present. This capability is implemented — CONFIRM it, do not rebuild. Reference scope / behaviour: Per design doc §5: make the customer-facing risk score a transparent additive model — score = Σ wᵢ·standardized(featureᵢ) over the validated drivers, weights from the active model's effect sizes/coefficients, normalized 0–100. Each coil's score decomposes EXACTLY into per-feature contributions (superheat +30, hard grade +25, strand 2 +17) — no SHAP, because the model is linear/additive. Keep a GBM only for driver DISCOVERY, never for scoring. | Enhancement | Confirm (do NOT re-implement): Confirm contributions sum exactly to the score and are surfaced; add a unit test on a known vector. | Done | 85% | 6
PPIQ-T238 | Model registry lifecycle, provenance & reproducibility | P07 | important | Track 1 — Workflow | Database | ML Engine / Model Registry | ARCHITECTURE · Layer L5 — Reason, the model registry (Intelligence Architecture §2.5). Records provenance so every score is reproducible and drift is monitored — the governance spine behind the risk number. STARTING POINT (31-May audit — already built): ModelRegistry(67L) + config + migration; provenance scaffolding. WHAT REMAINS — the actual work of this task: Finish lifecycle+provenance+reproducibility so every persisted result links to a registry row. FULL REFERENCE SPEC: Per design doc §7: treat a model as a versioned analysis configuration + computed snapshot. Store provenance — data window, canonical-view versions, engine git SHA, thresholds, random seed — so any result is reproducible bit-for-bit. Register/version/activate/retire; exactly one active version per scope; the risk scorer reads the active version. Keep baseline v1 = 'Transparent rule-based quality risk scorer'. | Enhancement | 1) A learning run registers a new version with full provenance. 2) Exactly one version per scope is active; activation retires the prior. 3) Re-running with the stored seed reproduces results. 4) History is queryable for audit. | Partial | 55% | 4
PPIQ-T237 | Risk-score calibration & reliability check | P07 | important | Track 2 — Hardening | App Backend | ML Engine / Calibration | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). Calibration/reliability of the additive score is checked so the number means what it says; gated by MlReadinessService. STARTING POINT (30-May audit — already built): RiskScoreService present; no explicit calibration/reliability check found. WHAT REMAINS — the actual work of this task: Add risk-score calibration & reliability (reliability curve / bucketed observed-vs-scored on demo data). FULL REFERENCE SPEC: Per design doc §5: validate that higher scores correspond to higher observed defect rates (rank correlation + reliability/calibration plot). Recalibrate when drift is detected. A score that does not rank-order real outcomes is flagged. | New Feature | 1) Calibration check runs and reports rank correlation between score and observed defect rate. 2) A miscalibrated scorer is flagged. 3) Recalibration updates the normalization. 4) Result is reproducible. | Partial | 30% | 4
PPIQ-T239 | Drift monitoring & champion/challenger promotion | P07 | normal | Track 1 — Workflow | App Backend | ML Engine / Drift & Promotion | ARCHITECTURE · Layer L5 — Reason (Intelligence Architecture §2.5). Drift monitoring + champion/challenger keeps the additive scorer trustworthy over time; readiness-gated. BUILD FROM SCRATCH (30-May audit: No drift monitoring / champion-challenger.). SPECIFICATION: Per design doc §7: when new data lands, compare the active model's correlations to fresh computation and alert when a strong driver weakens or flips sign (a process change — feeds suggestions). The weekly overall pass (§3.1.4) is a challenger; promote over the active model only if more stable, never automatically. | New Feature | 1) A drifted driver raises an alert and a suggestion. 2) The weekly pass is evaluated as a challenger. 3) Promotion requires a stability improvement and is logged. 4) No automatic silent promotion. | Not Started | 10% | 4
P08 — ML Assistant: Suggestion Feed & Value Model (proactive) ¦ 7 tasks ¦ 38 hrs Vision section 3.3 proactive half. Turn accumulated, validated findings into a rule-based, evidence-linked, impact-ranked suggestion engine; expose it via /api/suggestions with context filtering + license gating; build the proactive feed UI with evidence drill-through; test ranking + evidence linkage. EXIT STATE (healthy): the app proactively surfaces ranked, evidence-cited recommendations a plant could act on. v12 adds the Value Model (Intelligence Architecture §5, 'Proving the Money'): a deterministic impact engine (T296), per-tenant cost inputs (T297) and an evidence-first ROI presentation contract (T298) — turning validated findings into auditable euro opportunities across the four levers (quality, downtime, productivity, loss) without ever promising a saving.
PPIQ-T226 | Suggestion engine — rule-based, evidence-linked, impact-ranked | P08 | very important | Track 1 — Workflow | App Backend | ML Assistant / Suggestion Engine | ARCHITECTURE · Layer L6 — Advise, the proactive half (Intelligence Architecture §2.6.1). A deterministic, RULE-BASED engine turns validated L4/L5 findings into ranked recommendations, each carrying contributor, effect size, reliability, affected outcome and an estimated impact (the Value Model, §5 / T296). No LLM in the ranking. BUILD FROM SCRATCH (30-May audit: No suggestion engine. ml_knowledge_base_items exists as substrate.). SPECIFICATION: Per design doc §4.2/§4.4 (Vision §3.3 proactive): synthesize ranked recommendations from the §3.1 learning outputs, inspection results, and data-quality findings. Each suggestion carries confidence, effective-n, q-value, effect size, and links to the supporting evidence. Rank by impact score ≈ effect size × prevalence × actionability × confidence/stability; dedup/group correlated drivers (multicollinearity); boost newly-emerged/changed relationships (changepoint). Strictly honest framing. | New Feature | 1) The engine emits ranked suggestions, each with confidence, n, q-value, evidence link. 2) Correlated drivers are grouped, not duplicated. 3) A newly-changed relationship surfaces higher. 4) Suggestions update after a new learning run. 5) No forbidden claim language (guarded). | Not Started | 5% | 8
PPIQ-T227 | /api/suggestions endpoint + context filtering + license gating | P08 | important | Track 1 — Workflow | App Backend | ML Assistant / Suggestions API | ARCHITECTURE · Layer L6 — Advise (Intelligence Architecture §2.6.1). The suggestions endpoint serves the ranked feed with context filters (area, defect class, window), gated by license tier, with drill-through to the evidence. BUILD FROM SCRATCH (30-May audit: No /api/suggestions endpoint found.). SPECIFICATION: Implement GET /api/suggestions (the previously-stubbed route) returning ranked recommendations, filterable by current investigation context (material/area/line/window) and license tier. ProblemDetails error paths; pagination; audit of which suggestions were surfaced. | New Feature | 1) Endpoint returns ranked suggestions with reasoning + evidence links. 2) Context filters narrow results correctly. 3) Non-licensed tier gated. 4) Integration tests cover happy/empty/filtered. | Not Started | 0% | 4
PPIQ-T228 | Suggestions & Recommendations Page (proactive feed UI) | P08 | very important | Track 1 — Workflow | App Frontend | ML Assistant / Suggestions Page | ARCHITECTURE · Layer L6 — Advise, the suggestion feed (Intelligence Architecture §2.6.1, §5.3). Surfaces opportunities evidence-first and ranked by estimated value × confidence; every euro figure traces to the Value Model (T296) on the customer's own inputs (T297). BUILD FROM SCRATCH (30-May audit: No Suggestions/Recommendations page (only a Phase56 placeholder set; none named suggestions).). SPECIFICATION: Per design doc §4.2 (the 'Page' half of Vision §3.3): an evidence-grade ranked feed — 'the top things to look at this week' — with reasoning, confidence, sample size, and drill-through to the supporting correlation/inspection page. Standard* primitives, DataFetchBoundary states, license gating, and an honest empty state ('no strong signal yet'). Brand voice throughout. | New Feature | 1) Page renders ranked recommendations with reasoning + evidence drill-through. 2) Drill-through opens the supporting analysis page. 3) Empty/loading/error use Standard* and the 'Refreshing…' pattern. 4) Standard* primitives only; visual regression baseline captured. | Not Started | 5% | 6
PPIQ-T229 | Suggestion ranking + evidence-linkage tests | P08 | important | Track 2 — Hardening | App Backend | ML Assistant / Test Coverage | ARCHITECTURE · Layer L6 — Advise (Intelligence Architecture §2.6.1). Proves ranking + evidence-linkage: each surfaced suggestion links back to the finding, effect size and sample that earned it. BUILD FROM SCRATCH (30-May audit: No suggestion ranking/evidence tests.). SPECIFICATION: Tests asserting suggestion ranking order on golden inputs, evidence links resolve to the correct underlying results, context-filtering correctness, dedup/grouping of correlated drivers, and license gating. Determinism check. | New Feature | 1) Ranking matches known ground truth on golden inputs. 2) Every evidence link resolves to the correct correlation/inspection record. 3) Correlated drivers are grouped. 4) Deterministic; wired to the gate. | Not Started | 0% | 3
PPIQ-T296 | Value/Impact computation engine (the 'compute impact' tool) | P08 | very important | Track 1 — Workflow | App Backend | ML Assistant / Value Model | ARCHITECTURE · Layer L6 — Advise, the Value Model (Intelligence Architecture §5, 'Proving the Money'). This is the deterministic engine behind every euro figure the assistant shows; it is exposed as a TYPED tool the RAG agent (T232) calls — never an LLM computation. NEW — derived from the Intelligence Architecture (§5); not present in the v11 snapshot. Build a deterministic value/impact computation engine that converts a validated L4/L5 finding into an evidence-based monetary OPPORTUNITY across the four value levers: (1) Quality/defects — avoided defective coils -> recovered prime value per ton; (2) Downtime — avoided PRODUCTION-stoppage hours (not equipment-stoppage) -> recovered throughput x contribution margin/ton; (3) Productivity — prime-yield/throughput lift -> more saleable tons from the same inputs; (4) Loss/waste — energy-per-ton / additive-usage reduction -> lower cost per ton. The engine takes the finding (effect size, affected outcome, effective-n) plus the customer's own cost inputs (T297) and computes the arithmetic TRANSPARENTLY, returning the formula alongside the number. It never asserts a guaranteed saving — output is framed as an 'opportunity' with the linkage shown. Ranking key = estimated value x confidence. | New Feature | 1) Given a finding + cost inputs, the engine returns a per-lever EUR opportunity WITH the exact formula it used (auditable, no hidden constants). 2) Re-running with changed cost inputs changes the figure deterministically — pure function, no LLM/network in the compute path (instrumented). 3) Each of the four levers has a worked unit test at demo scale (~630 heats/mo, ~100,000 t/mo, ~5,600 coils/mo) matching hand-computed expected values. 4) Opportunities sort by value x confidence. 5) No 'guaranteed'/'will save' phrasing is emitted (honesty-contract assertion, ties to T309/T291). | Not Started | 0% | 8
PPIQ-T297 | Customer cost-assumption configuration (per-tenant inputs + demo defaults) | P08 | important | Track 1 — Workflow | App Frontend | ML Assistant / Value Model | ARCHITECTURE · Layer L6 — Advise, the Value Model (Intelligence Architecture §5.2–§5.3): 'the customer supplies their real cost inputs; PPIQ supplies the linkage and the arithmetic.' The euro figures are persuasive precisely because they run on the plant's OWN numbers and can be audited. NEW — derived from the Intelligence Architecture (§5); not present in the v11 snapshot. Provide a per-tenant cost-assumption store + an HMI configuration surface for the inputs the value engine (T296) consumes: recovered prime value per ton, contribution margin per ton, cost-per-defect by defect class, energy price per unit, and monthly production volumes (heats, tons, coils). Ship realistic demo defaults at the §5.2 worked-example scale so the demo shows real euros out of the box, clearly labelled as editable assumptions the customer should replace. Inputs are validated, versioned and tenant-scoped; changing them re-computes every open opportunity. Standard* primitives; validation/SafeSql on persistence. | New Feature | 1) An admin can view and edit every cost input from the HMI; values persist per-tenant and survive an app restart. 2) Demo defaults populate at the §5.2 scale and are visibly marked as assumptions to replace. 3) Editing an input re-computes the suggestion feed's euro figures on next load. 4) Inputs are validated (positive numbers, units shown) and versioned for audit. 5) Tenant isolation enforced. | Not Started | 0% | 5
PPIQ-T298 | ROI presentation contract in the Suggestion feed + Assistant (evidence-first, never a promise) | P08 | important | Track 1 — Workflow | App Frontend | ML Assistant / Value Presentation | ARCHITECTURE · Layer L6 — Advise, how the assistant presents value (Intelligence Architecture §5.3 + §6 'value is shown, not promised'). Applies the product's vocabulary discipline to money. NEW — derived from the Intelligence Architecture (§5); refines T226/T228/T232/T233. Wire the value engine (T296) + cost inputs (T297) into BOTH proactive surfaces — the Suggestion feed (T228) and the conversational assistant (T233) — under one presentation contract: (a) ALWAYS evidence-first — show the suspected contributor, effect size, reliability and sample BEFORE the euro figure, so the number is earned; (b) ALWAYS the customer's inputs — show the formula and the inputs used; (c) ALWAYS ranked by estimated value x confidence so the plant works the biggest, most-reliable wins first; (d) NEVER a promise — framed as 'approximately', 'associated with', 'opportunity'. The forbidden-claim guard (T291/T309) extends to value language: 'guaranteed saving' / 'will save EURx' are rejected. | Enhancement | 1) Every euro figure in the feed and in the assistant is preceded by its evidence (contributor, effect size, reliability, sample). 2) The feed orders opportunities by value x confidence. 3) The exact formula + inputs are inspectable from each opportunity. 4) Forbidden value claims fail a test; approved 'opportunity/approximately/associated-with' phrasing passes. 5) The euro figure shown always equals the value engine's output for the current cost inputs (no UI-side recomputation). | Not Started | 0% | 4
P09 — ML Assistant: Conversational RAG Agent ¦ 7 tasks ¦ 43 hrs Vision section 3.3 conversational half. Build KB ingestion, hybrid retrieval (semantic + structured filter), the agent + tool layer (query findings, run inspection, KPI, genealogy, compare), the chat UI with citations + drill-through, the operator feedback loop, the grounding/honesty guardrail tests, AND enforce the ML honesty contract at the API boundary (not just the UI). EXIT STATE (healthy): an operator asks a question and gets an evidence-cited answer where the LLM only phrases retrieved/computed findings and never invents a number.
PPIQ-T230 | Knowledge-base ingestion (findings, cases, domain docs) | P09 | very important | Track 1 — Workflow | App Backend | ML Assistant / KB Ingestion | ARCHITECTURE · Layer L6 — Advise, the knowledge base (Intelligence Architecture §2.6.2 'Retrieve' + §2.5). Ingests learned findings, saved cases and domain documents into the vector + structured store the agent retrieves from. STARTING POINT (31-May audit — already built): KB substrate (ml_knowledge_base_items + upsert/search) + DeterministicEmbeddingProvider give an offline embedding+store path. WHAT REMAINS — the actual work of this task: Build the ingestion pipeline that pushes correlation findings/cases/domain docs into the KB with embeddings. FULL REFERENCE SPEC: Per design doc §4.1/§4.3: ingest the three growing knowledge sources into the pgvector KB (T213). (a) Learned findings rendered as evidence cards with structured metadata; (b) case memory (past inspection jobs, resolved excursions, downtime root-cause notes, acted-on recommendations + outcomes); (c) curated domain knowledge (grade specs, flat-steel failure modes, operating ranges, SOPs). Embed via IEmbeddingProvider; keep structured columns for hybrid retrieval. Re-ingest incrementally as data accumulates. | New Feature | 1) Findings, cases, and domain docs are embedded and retrievable. 2) New findings/cases are ingested incrementally. 3) Each item retains structured fields (area, defect class, grade, window, q-value). 4) Re-ingestion is idempotent. | Partial | 35% | 6
PPIQ-T231 | Hybrid retrieval pipeline (semantic + structured filter) | P09 | very important | Track 1 — Workflow | App Backend | ML Assistant / Retrieval | ARCHITECTURE · Layer L6 — Advise, hybrid retrieval (Intelligence Architecture §2.6.2 'Retrieve'). Semantic search (via the embedding provider) + structured filters (area, defect class, window) select the relevant findings/cases — semantic and SQL together. STARTING POINT (31-May audit — already built): ppiq_ml_search_kb (vector + structured filters) exists; embeddings available via the provider. WHAT REMAINS — the actual work of this task: Build the .NET hybrid retrieval orchestration (semantic + structured filter) on top of the KB search. FULL REFERENCE SPEC: Per design doc §4.3: implement retrieval that combines pgvector semantic similarity with structured SQL filters over the findings (area, defect class, grade, line, time window, q-value threshold). Question => embed => semantic + filtered search => top-k evidence with citations. Tunable k; relevance + recency weighting. | New Feature | 1) A query returns top-k evidence combining semantic match and structured filters. 2) Filtering by grade/defect/window narrows correctly. 3) Each retrieved item is citeable back to its source finding/case. 4) Retrieval latency is bounded and logged. | Partial | 30% | 6
PPIQ-T232 | Agent + tool layer (query findings, run inspection, KPI, genealogy, compare) | P09 | very important | Track 1 — Workflow | App Backend | ML Assistant / Agent & Tools | ARCHITECTURE · Layer L6 — Advise, the agent + tools (Intelligence Architecture §2.6.2 'Reason with tools'). The agent calls TYPED tools — query findings, run an inspection, fetch a KPI, walk genealogy, COMPUTE IMPACT (T296) — which return structured numbers. The agent orchestrates; it does not compute. BUILD (31-May audit: No agent/tool layer. The narrative providers exist (the VOICE) but nothing orchestrates tools/answers. CorrelationService/learning results/genealogy exist as tools-to-be.). WHAT REMAINS: Build the agent + tool layer (query findings, run inspection, KPI, genealogy, compare) where the LLM only PHRASES tool results — the conversational engine the founder is asking for. SPECIFICATION: Build an agent + tool layer where the LLM is the VOICE, never the brain: it may call typed tools — query findings, run an inspection job, fetch a KPI, walk genealogy (T294), compare entities — and then PHRASE the structured results those tools return. It must never compute or invent a figure; every number it states must trace to a tool result or retrieved evidence. Route narration through INarrativeProvider (T292) so the deployment can run API-backed or fully self-hosted, with only abstracted findings ever crossing an external boundary. | New Feature | 1) Each tool (query findings, run inspection, KPI, genealogy, compare) is invoked correctly and its result is faithfully reflected in the answer. 2) Every figure in an answer traces to a tool result or retrieved evidence — asserted by the grounding tests (T235). 3) The agent runs against both the API and self-hosted narrative providers without code change. 4) Only abstracted findings (never raw plant rows) are sent to an external provider — proven by a test. 5) Forbidden vocabulary ('prediction', 'guaranteed root cause') never appears; approved vocabulary is used. | Not Started | 5% | 10
PPIQ-T233 | Conversational assistant UI with evidence citations + drill-through | P09 | very important | Track 1 — Workflow | App Frontend | ML Assistant / Chat UI | ARCHITECTURE · Layer L6 — Advise, the conversational UI (Intelligence Architecture §2.6.2 'Phrase'). The LLM (behind the narrative provider) turns structured tool results into clear language with inline evidence citations — it NEVER produces a number that did not come from a tool. BUILD (31-May audit: No conversational assistant UI anywhere in the frontend (no chat/assistant/agent components).). WHAT REMAINS: Build the chat UI with evidence citations + drill-through; depends on T232. SPECIFICATION: Per design doc §4.2 (the conversational half of Vision §3.3): a chat surface where a user asks plant-performance questions ('why are sliver defects up?', 'best lever on energy/ton?', 'compare strand 1 vs 2') and receives grounded answers with inline evidence chips (n, q-value, effect size) that drill through to the supporting correlation/inspection page. Standard* primitives; streaming responses; license gating; honest empty/uncertain states. | New Feature | 1) Asking a question returns a grounded, cited answer with evidence chips. 2) A chip drills through to the supporting analysis page. 3) With no evidence the assistant says so rather than confabulating. 4) Standard* primitives only; visual regression baseline captured. | Not Started | 0% | 8
PPIQ-T234 | Operator feedback loop (useful/acted/dismissed + outcomes) | P09 | important | Track 1 — Workflow | App Backend | ML Assistant / Feedback Loop | ARCHITECTURE · Layer L6 — Advise, the learn loop (Intelligence Architecture §2.6.2 'Learn'). Operator feedback (useful / acted / dismissed + outcome) is written back to the knowledge base — the experience that compounds lives in DATA, not in model weights. BUILD (31-May audit: No operator feedback loop.). WHAT REMAINS: Add useful/acted/dismissed capture + outcome linkage for assistant answers. SPECIFICATION: Per design doc §4.4: operators mark suggestions/answers useful, acted-on, or dismissed and record outcomes. This re-ranks future suggestions AND flows into case memory ('acted on; yield +1.2 pts'). Honest system-level learning — the platform improves with use, fully auditable, not opaque weight changes. | New Feature | 1) Feedback can be recorded against a suggestion/answer. 2) Feedback measurably re-ranks future suggestions. 3) Acted-on outcomes enter case memory and become retrievable. 4) An audit trail records all feedback. | Not Started | 0% | 5
PPIQ-T291 | ML honesty-contract lint extended to ML/assistant API responses & narratives | P09 | important | Track 2 — Hardening | App Backend | ML / Honesty Guardrail | ARCHITECTURE · Layer L6 — Advise, the honesty guardrail (Intelligence Architecture §2.6, §6). The forbidden-claim lint extends to ML + assistant surfaces: 'prediction/predicts/guaranteed root cause/AI-powered prediction/production-ready AI' are rejected; the approved vocabulary ('suspected contributor', 'statistical correlation', 'opportunity') passes. STARTING POINT (31-May audit — already built): Narrative providers + ML honesty vocabulary established; forbidden-claim guards exist on the UI side. WHAT REMAINS — the actual work of this task: Enforce the honesty contract at the ML/assistant API boundary: reject forbidden claims and require n/q/effect-size/evidence-link on every returned finding. FULL REFERENCE SPEC: The forbidden-phrase/ML-claims guard currently targets frontend text. Extend it to backend ML/assistant payloads and any INarrativeProvider output: reject 'prediction/predicts/guaranteed root cause/AI-powered prediction/production-ready AI' and require findings to carry effective-n, q-value, effect size, and an evidence link before they can be returned. Enforces the Vision §3 / How-to-Use honesty contract at the API boundary, not just the UI. | Enhancement | 1) An ML/assistant response containing a forbidden claim fails a unit/contract test. 2) A finding without n/q/effect-size/evidence-link is rejected by the serializer or a validator. 3) Wired into CI. 4) Approved vocabulary ('suspected contributor', 'statistical correlation') passes. | Partial | 40% | 4
PPIQ-T235 | Assistant grounding & honesty guardrail tests | P09 | very important | Track 2 — Hardening | App Backend | ML Assistant / Guardrail Tests | ARCHITECTURE · Layer L6 — Advise, grounding (Intelligence Architecture §2.6.2, §6). Every figure in an answer must trace to a tool result or retrieved evidence; the LLM phrases earned, evidence-qualified intelligence and may not invent a single figure. BUILD (31-May audit: Honesty vocabulary + deterministic core (no-LLM compute) exist, but no grounding tests for an assistant that does not yet exist.). WHAT REMAINS: Add grounding tests proving the assistant never emits a figure absent from retrieved evidence/tool results. SPECIFICATION: Per design doc §4.5: tests that the assistant answers ONLY from retrieved evidence + tool results, says 'no statistically significant driver found' when there is none (no confabulation), and never emits forbidden ML claims ('guaranteed root cause', 'AI-powered prediction', 'production-ready AI', 'predicts'). Verify every recommendation carries n + q-value + effect size + evidence link. Extend the CI copy guard to the assistant surfaces. | New Feature | 1) With no supporting evidence the assistant declines rather than inventing an answer. 2) A forbidden ML claim anywhere fails CI. 3) Every surfaced recommendation carries n, q-value, effect size, evidence link. 4) Tests wired to the gate. | Not Started | 5% | 4
P10 — Hardening, Resilience & HMI Completion ¦ 10 tasks ¦ 42 hrs Vision Track 2 completion across the now-complete surface (including the ML pages). Complete the full three-identity auth matrix over every endpoint group INCLUDING /api/ml/* (deferred to here on purpose — those endpoints exist only now), the endpoint/SQL resilience audit, the full action-matrix test, the Standard* contract suite, responsive/cross-browser/http-https correctness, progress UI for long endpoints, the Risk-Intelligence HeatMap, the live license-tier toggle + banner, removal of synthetic seeds from the prod boot path, and a first-run onboarding wizard. EXIT STATE (healthy): every control on every page does its job, nothing shows a fake failure, and a fresh instance feels intentional.
PPIQ-T252 | Endpoint + SQL resilience audit (PK/FK/null/timeout) (Vision §2.2) | P10 | very important | Track 2 — Hardening | App Backend | Hardening / API Resilience | STARTING POINT (30-May audit — already built): 115_phase2_integrity_audit.sql (236L) + 071_validate_dashboard_performance; SafeSqlValidator; apiClient resilience. WHAT REMAINS — the actual work of this task: Run the endpoint + SQL resilience audit (PK/FK/null/timeout) across every API; document and fix. Partly covered by integrity-audit SQL. FULL REFERENCE SPEC: Systematic pass over every API + its SQL/joins (including the new schema-mapping, two-stage import, and ML endpoints): guard null/missing PK-FK, enforce query timeouts, ProblemDetails on every error path, assert no unexpected 500s under empty/edge data. Produce docs/hardening/endpoint-resilience-{date}.md listing each endpoint's edge handling. | Enhancement | 1) Every endpoint returns structured errors, never an unhandled 500, under empty/edge inputs. 2) Query timeouts enforced. 3) Checklist documents each endpoint. 4) Integration tests cover the top 25 endpoints' edge cases. | Partial | 45% | 6
PPIQ-T253 | Full action-matrix test: every control does its job (Vision §3.1.1) | P10 | very important | Track 2 — Hardening | App Frontend | Hardening / Action Matrix | STARTING POINT (30-May audit — already built): Phase1 button-action-matrix + toast-mapping e2e specs exist; auth-matrix spec. WHAT REMAINS — the actual work of this task: Complete the full action-matrix test: every control on every page does its job (Vision §3.1.1). Extend beyond Phase1 specs to all pages incl. new ML pages. FULL REFERENCE SPEC: Extend src/hardening/actionMatrix.ts: for every page and sub-page (incl. the new ML Correlation, Suggestions, Assistant, Schema Mapping, Two-Stage Import, Jobs Monitor surfaces), enumerate every button/control/hook with its expected action, and a Playwright test exercising each and asserting the outcome. No dead/misbehaving control. | New Feature | 1) The matrix enumerates every control on every page/sub-page. 2) Each is exercised and asserted. 3) Zero dead/misbehaving controls. 4) Wired to the PR gate; a new dead button fails it. | Partial | 35% | 6
PPIQ-T256 | Complete Standard* contract tests | P10 | important | Track 2 — Hardening | App Frontend | Quality / Contract Tests | STARTING POINT (30-May audit — already built): Standard* components exist with contract tests (DashboardWidgetDefinitionExpressionTests etc.) but not a complete Standard* contract suite. WHAT REMAINS — the actual work of this task: Complete Standard* contract tests covering every variant/state in the UI Standards Reference. FULL REFERENCE SPEC: Ensure every Standard* primitive has a contract test asserting prop names/types/defaults and render shape (data-testid hooks). Fill gaps (Surface/Fields variants) beyond the existing Button/Table/Tabs tests. | New Feature | 1) Contract tests exist for all Standard* primitives. 2) A non-backward-compatible prop change fails a contract test. 3) Suite < 30s on every PR. | Partial | 45% | 3
PPIQ-T204 | Complete the JWT auth-matrix to full tier coverage | P10 | very important | Track 2 — Hardening | App Backend | Auth / Endpoint Authorization | STARTING POINT (31-May audit — already built): auth-matrix-admin.spec.ts now covers anonymous/operator/admin across admin-overview/jobs-monitor/schema-mapping/two-stage/license/phase1/phase2/widgets/users/demo-lifecycle/diagnostics AND /api/ml/readiness + /api/ml/foundation/*; emits auth-matrix.json/.md; archived in Jenkins. WHAT REMAINS — the actual work of this task: Extend coverage to /api/ml/learning/* (run/results) once those are demo-ready; keep the red-on-deviation gate. FULL REFERENCE SPEC: Closes the residual of v4 PPIQ-T101. An auth-matrix-admin.spec.ts and test:auth-matrix exist, but the confirmed backend assertions only cover anonymous=>401/403 and valid-login=>token. Extend to the full matrix: every admin endpoint group (/admin/jobs-monitor, /admin/schema-mapping, /admin/two-stage-import, /admin/license, /admin/phase1, /admin/phase2, /admin/widgets, /admin/users, /demo-lifecycle, /diagnostics, and the new /api/ml/*) under three identities — no token (401), operator-tier JWT (403 on admin, 200 on operator), admin-tier JWT (200) — emitting a matrix artifact and wired as a red-on-deviation Jenkins gate. | Bug Fix | 1) The probe exercises all three identities across every admin group, not just anonymous. 2) Removing an [Authorize] on any admin endpoint fails the probe. 3) Output archived per deploy. 4) Jenkins goes red on any deviation. | Partial | 80% | 3
PPIQ-T254 | Responsive + cross-browser + http/https correctness (Vision §1.6, §2.1.6) | P10 | important | Track 2 — Hardening | App Frontend | Hardening / Responsive | STARTING POINT (30-May audit — already built): Responsive/cross-browser playwright config present; http/https handled (login saga confirmed both). WHAT REMAINS — the actual work of this task: Finish responsive + cross-browser + http/https correctness sweep across all pages and capture proof. FULL REFERENCE SPEC: Verify every page renders correctly at common screen sizes and re-adjusts across Chromium/Firefox/WebKit on both http and https. Fix layout/overflow/orientation issues. Add Playwright runs at three viewports × three browsers. | Enhancement | 1) No layout/overflow defects across three viewports and three browsers. 2) Works on http and https. 3) Snapshots captured as baselines. 4) Wired to the visual-regression job. | Partial | 40% | 4
PPIQ-T251 | Progress-percentage UI for long-running endpoints (Vision §2.1) | P10 | important | Track 2 — Hardening | App Frontend | Hardening / Long Calls | STARTING POINT (30-May audit — already built): apiClient has timeouts/retry; DataFetchBoundary skeletons. No explicit progress-percentage UI for long endpoints. WHAT REMAINS — the actual work of this task: Add progress-percentage UI for long-running endpoints (imports, inspection runs) per Vision §2.1.1. FULL REFERENCE SPEC: For every endpoint that can be slow on large datasets (imports, ML runs, heavy analytics, PDF), surface a loading indicator with a progress percentage (reuse OperationProgressPanel + progress endpoints). No silent multi-second hangs anywhere a customer can see. | Enhancement | 1) Each heavy action shows progress %, not a bare spinner. 2) Progress reflects real backend stages. 3) No visible hang > 1s without feedback. 4) e2e covers the three heaviest paths. | Partial | 40% | 4
PPIQ-T249 | HeatMapWidget for Risk Intelligence (line × shift × day) | P10 | important | Track 2 — Hardening | App Frontend | Widgets / Visualization | ARCHITECTURE · Layer L2 — Describe (Intelligence Architecture §2.2): the heat map is line × shift × day, pure description via safe validated SQL. It surfaces risk patterns to look at; it never asserts causation (that is L4). BUILD FROM SCRATCH (30-May audit: No HeatMap widget found anywhere in the codebase.). SPECIFICATION: Vision §4.2: a heat map on Risk Intelligence — risk score by line × shift × day-of-week, green→amber→red on brand thresholds, hover tooltip with breakdown, click-through to the materials in that cell (applies filters to Material Investigation). Data via /api/risk/heatmap. StandardCard with loading/empty/error states. | New Feature | 1) Heat map renders; colors match the chip treatment. 2) Click drilldown applies filters to Material Investigation. 3) States use Standard* primitives. 4) 30×7×24 grid renders < 200ms. | Not Started | 0% | 6
PPIQ-T250 | Live license tier toggle + app-wide override banner | P10 | important | Track 1 — Workflow | App Frontend | License / Tier Toggle | STARTING POINT (30-May audit — already built): LicenseContext.tsx (158L) + LicenseTier.cs + a phase78 t053 license-tier-override fix; ConnectorTruthPanel + PricingLicenseMatrix. WHAT REMAINS — the actual work of this task: License context + tier exist. Finish the LIVE tier toggle + app-wide override banner so switching Enterprise->Pro visibly removes features during the demo (Vision §4.2). FULL REFERENCE SPEC: In Admin Preview, a StandardSelect bound to effective-tier/tier-override lets an admin demo Pro Plus features without swapping licenses; an app-shell banner shows when an override is active ('Tier override active: Pro Plus (expires in 23h 47m). Reset.'). Demonstrates Vision §4.2. | Enhancement | 1) Toggling tier immediately re-gates features across the app. 2) Banner appears when override active; Reset clears it. 3) Switching Enterprise→Pro visibly removes gated features. 4) Audit on every toggle. | Partial | 50% | 4
PPIQ-T255 | Archive synthetic seeds out of production boot path | P10 | important | Track 2 — Hardening | Database | Seeds / Hygiene | STARTING POINT (30-May audit — already built): 121_bootstrap_token_sweep + DevSeed concerns; synthetic seeds (112_) still in script set. WHAT REMAINS — the actual work of this task: Archive synthetic seeds out of the production boot path so demo data is loaded deliberately, never auto-seeded in prod. FULL REFERENCE SPEC: Move any synthetic/placeholder seed out of the boot path into Backend/database/seeds/demo-only/, invoked only by the demo reset job and only when tenant.is_demo = true. Any seed touching a real tenant must be explicit and approved. | Bug Fix | 1) Grep of API startup shows zero demo-seed calls in the production boot path. 2) A fresh non-demo tenant has zero synthetic rows. 3) The demo tenant re-seeds via reset. 4) Audit shows seed activity only on demo tenants. | Partial | 50% | 2
PPIQ-T295 | Operator-friendly first-run wizard: empty-state -> first DB link -> first page | P10 | normal | Track 2 — Hardening | App Frontend | Onboarding / Demo UX | [NEW — discovered during the v6 implementation/debugging audit; not present in the 30-May snapshot] Because the demo IS the first release configured live (Track 3 Golden Rule), the empty-state experience matters. Add a guided first-run flow that walks a brand-new instance from no-config to first DB link to first job to first page, so both the demo and a real pilot's day-one feel intentional rather than blank. Reinforces 'real user experience' and reduces presenter cognitive load. | Enhancement | 1) A fresh instance shows a guided next-step path, not blank panels. 2) The wizard links to the real DB Link / Schema / Page flows (no fake screens). 3) It can be dismissed and re-opened. 4) Validated by configuring a page end-to-end via the wizard. | Not Started | 0% | 4
P11 — Demo: Storytelling, Personas & Recording ¦ 6 tasks ¦ 21 hrs Vision Track 3 presentation layer, now that the product it narrates is complete. Produce the demo persona accounts, the live end-to-end config proof (configure everything from an empty app, no hardcoding), the 25-step technical script with verification points, the 5-minute executive script, recovery lines for known fail-points, and a recorded dry-run + screenshots. EXIT STATE (healthy): the demo can be delivered and recovered under pressure.
PPIQ-T260 | Demo persona accounts (Operator, QA Lead, Plant Manager, Admin) | P11 | very important | Track 3 — Demo | Database | Demo Lifecycle / Personas | STARTING POINT (30-May audit — already built): Auth Users[] has admin/engineer/datamanager/viewer roles (config-based, proven in login work). WHAT REMAINS — the actual work of this task: Create demo persona accounts (Operator, QA Lead, Plant Manager, Admin). Role scaffolding exists; finalize named personas + scoped views. FULL REFERENCE SPEC: Seed four personas via the demo reset job with rotated credentials and tuned home pages (Operator: today's quality events; QA Lead: open investigations; Plant Manager: risk by line; Admin: system health). Role/tier restrictions enforced. | New Feature | 1) After reset all four log in. 2) Each home page is tuned per spec. 3) Operator cannot reach Admin pages. 4) Credentials documented (gitignored real values, vaulted). | Partial | 30% | 3
PPIQ-T248 | Live end-to-end config demo proof (no hardcoding) | P11 | important | Track 3 — Demo | App Frontend | Demo Sources / E2E Proof | ARCHITECTURE · End-to-end proof of the whole pipeline L1→L6 from the HMI (Intelligence Architecture §1, Track-3 golden rule): connect the eight sources, map them, build a page, run the learning engine, and reach an evidence-qualified, costed suggestion — all configured live, nothing hardcoded. BUILD FROM SCRATCH (30-May audit: Demo lifecycle page exists (Phase56DemoLifecyclePage); full live config demo proof not assembled.). SPECIFICATION: Track-3 golden-rule proof: a scripted e2e that, from the HMI only, connects each of the six DB sources + two drops, maps/joins one cross-source view, runs a delta import, builds a page with a script-layer widget, runs an inspection job, and asks the assistant one question — verifying nothing is hardcoded. | New Feature | 1) The full from-HMI path passes against the demo-sources stack. 2) Each step verified with a concrete checkpoint. 3) No hardcoded page/widget used anywhere. 4) Run completes within the demo time budget. | Not Started | 10% | 5
PPIQ-T257 | 25-step technical demo script with verification points | P11 | very important | Track 3 — Demo | Documentation | Demo Scripts / Technical | BUILD FROM SCRATCH (30-May audit: No 25-step demo script artifact found.). SPECIFICATION: docs/demo/technical-demo-25-steps.md: 25 steps, each with [Action],[Expected UI state],[Verification checkpoint],[Recovery line],[Backend log indicator]. Covers login, connect each source, map/join one, delta sync, Data Quality, save investigation, calculate risk, export PDF, run ML readiness, run an inspection job + view the generated page, ask the assistant a question, view a suggestion, deploy a script-layer widget, view audit log, reset demo. Screenshots match the Standard*-migrated UI. | New Feature | 1) 25 steps, all five fields populated. 2) Screenshots match the current UI. 3) A new SE runs it end-to-end in < 40 min. 4) Each checkpoint is concrete. | Not Started | 0% | 4
PPIQ-T258 | 5-minute executive demo script with talk track | P11 | very important | Track 3 — Demo | Documentation | Demo Scripts / Executive | BUILD FROM SCRATCH (30-May audit: No 5-minute executive script found.). SPECIFICATION: docs/demo/executive-demo-5min.md: 4 acts (problem 60s; solution 90s; demo 2m30s — search → drilldown → calculate risk → inspection job → ask the assistant → PDF; close 60s). Exact words + the screen to show per act. | New Feature | 1) Four acts, total 4:30–5:00 measured. 2) Deliverable from the script without rehearsal. 3) Each act references a specific page+state. | Not Started | 0% | 3
PPIQ-T259 | Recovery lines for known fail-points | P11 | important | Track 3 — Demo | Documentation | Demo Scripts / Recovery | BUILD FROM SCRATCH (30-May audit: No recovery-lines doc found.). SPECIFICATION: docs/demo/recovery-lines.md: ≥12 known weak points (Oracle warm-up, first connector load, ML run latency, assistant latency, PDF render, network hiccup, stale cache) each with a calm, confident, non-apologetic recovery line + remediation gesture, in brand voice. | New Feature | 1) ≥12 fail-points covered. 2) Each line is calm and on-brand. 3) Founder review approves the tone. | Not Started | 0% | 2
PPIQ-T262 | Record dry-run demo video + capture website screenshots | P11 | important | Track 4 — Website | Documentation | Demo Recording / Website Assets | BUILD FROM SCRATCH (30-May audit: No demo video / screenshot capture artifacts.). SPECIFICATION: After prior phases are green, record one 5-minute executive dry-run (screen+voice) on the Standard*-migrated UI and capture 10+ 1080p screenshots (login, dashboard, material search, drilldown, risk, inspection page, assistant, suggestion, PDF, audit, reset) into Website assets. | New Feature | 1) 5-min video at 1080p+. 2) 10+ screenshots at 1920×1080. 3) Website renders the new assets. 4) In-app/website visual consistency confirmed. | Not Started | 0% | 4
P12 — Website: 5-Product Showcase & Brand ¦ 9 tasks ¦ 28 hrs Vision Track 4 — the first and best salesperson. Produce the logo asset set, the full PlantProcess IQ product page (feature the AI assistant), the MES/QES/Yard/Energy product pages, pricing + CTA wired to lead capture and the demo lifecycle, evidence-grade screenshots + case-study snippets, and a brand-consistency audit. EXIT STATE (healthy): the website is on-brand and conversion-ready across app + site + reports.
PPIQ-T263 | Produce the logo asset set per brand brief | P12 | important | Track 4 — Website | Web | Website / Brand Assets | STARTING POINT (30-May audit — already built): public/brand/plantprocess-iq-engineer-brief.html + SOUBrand.tsx + BrandProofSection exist; full logo asset set not confirmed. WHAT REMAINS — the actual work of this task: Produce the logo asset set per the brand brief (horizontal/icon/stacked x color/dark/light/mono). FULL REFERENCE SPEC: Vision §2.4: produce the full logo set — full horizontal, icon-only favicon, stacked vertical — each in full-color, dark, light, monochrome — from the connected-node concept (Electric Cyan nodes on Deep Navy). Ship optimized SVG + PNG; wire into app header, website, and PDF reports. | New Feature | 1) All variants exist as SVG+PNG within palette. 2) Favicon + app header + website + PDF header use the correct variant. 3) No drop shadows/recolors/steel-only imagery. | Partial | 30% | 3
PPIQ-T264 | PlantProcess IQ product page (full) — feature the AI assistant | P12 | very important | Track 4 — Website | Web | Website / Product Page | STARTING POINT (30-May audit — already built): Website App.tsx (533L) single-page with proof blocks (PricingLicenseMatrix, ProductScreenshotShowcase, RequestDemoForm, ConnectorHonestyBlock). WHAT REMAINS — the actual work of this task: Build the full PlantProcess IQ product page featuring the AI assistant. A single combined page exists; expand to the dedicated product page with depth + Golden Rule. FULL REFERENCE SPEC: Vision Track 4 product 1: full PlantProcess IQ page — description, benefits, interactive graphics/screenshots, license matrix, golden-rule CTA — and prominently feature the honest, evidence-grade AI assistant ('ask your plant data, every answer cited'). Reuse PricingLicenseMatrix, ProductScreenshotShowcase. | New Feature | 1) Page covers description/benefits/graphics/license/CTA. 2) The AI assistant is featured with the honest framing. 3) CTA links to the live demo. 4) Responsive across viewports. | Partial | 35% | 4
PPIQ-T265 | MES product page (full) | P12 | important | Track 4 — Website | Web | Website / Product Page | BUILD FROM SCRATCH (30-May audit: No dedicated MES product page.). SPECIFICATION: Vision Track 4 product 2: full Manufacturing Execution System page — description, benefits, interactive graphics, license, golden rule. Consistent brand grammar with the PPIQ page. | New Feature | 1) Full MES page with all required sections. 2) Brand-consistent with PPIQ page. 3) CTA wired. 4) Responsive. | Not Started | 5% | 3
PPIQ-T266 | QES product page (full) | P12 | important | Track 4 — Website | Web | Website / Product Page | BUILD FROM SCRATCH (30-May audit: No dedicated QES product page.). SPECIFICATION: Vision Track 4 product 3: full Quality Execution System page — description, benefits, interactive graphics, license, golden rule. | New Feature | 1) Full QES page with all required sections. 2) Brand-consistent. 3) CTA wired. 4) Responsive. | Not Started | 5% | 3
PPIQ-T267 | Yard & Warehouse Management product page (full) | P12 | important | Track 4 — Website | Web | Website / Product Page | BUILD FROM SCRATCH (30-May audit: No dedicated Yard & Warehouse product page.). SPECIFICATION: Vision Track 4 product 4: full Yard & Warehouse Management page — description, benefits, interactive graphics, license, golden rule. | New Feature | 1) Full page with all required sections. 2) Brand-consistent. 3) CTA wired. 4) Responsive. | Not Started | 5% | 3
PPIQ-T268 | Energy Management product page (full) | P12 | important | Track 4 — Website | Web | Website / Product Page | BUILD FROM SCRATCH (30-May audit: No dedicated Energy Management product page.). SPECIFICATION: Vision Track 4 product 5: full Energy Management page — description, benefits, interactive graphics, license, golden rule. | New Feature | 1) Full page with all required sections. 2) Brand-consistent. 3) CTA wired. 4) Responsive. | Not Started | 5% | 3
PPIQ-T269 | Pricing + CTA wired to lead capture & demo lifecycle | P12 | important | Track 4 — Website | Web | Website / Pricing & CTA | STARTING POINT (30-May audit — already built): RequestDemoForm.tsx (162L) + PricingLicenseMatrix.tsx (65L) present. WHAT REMAINS — the actual work of this task: Pricing + CTA exist; wire CTA to lead capture + demo lifecycle end-to-end. FULL REFERENCE SPEC: Three tiers (Pro/Pro Plus/Enterprise) with a feature matrix consistent with in-app licensing; 'Book a demo' posts to /api/leads with UTM params and triggers a calendar booking flow; leads reach the founder. Website CTA buttons match the in-app brand grammar. | Enhancement | 1) Pricing renders three tiers + feature matrix matching in-app gating. 2) Book-a-demo submits a lead and shows a booking flow. 3) Lead notification reaches the founder. 4) Brand consistency with the app. | Partial | 30% | 4
PPIQ-T270 | Evidence-grade screenshots + case-study snippets | P12 | important | Track 4 — Website | Web | Website / Proof | BUILD FROM SCRATCH (30-May audit: ProductScreenshotShowcase.tsx exists as a shell; no evidence-grade screenshots/case studies.). SPECIFICATION: Integrate the T262 screenshots into hero/features/proof with 'See it in the live demo' deep links, plus one evidence-grade case-study paragraph for the canonical plant (no exaggeration, brand voice). | Enhancement | 1) Hero/features/proof show post-migration UI. 2) CTAs deep-link to the page shown. 3) Case-study snippet is evidence-grade and on-brand. | Not Started | 10% | 3
PPIQ-T271 | Brand identity consistency audit (app + website + reports) | P12 | normal | Track 4 — Website | Web | Website / Brand Audit | BUILD FROM SCRATCH (30-May audit: Brand tokens exist in app + website; no formal consistency audit.). SPECIFICATION: Audit palette, typography (Inter / JetBrains Mono), logo usage, and tone across app, website, and PDF reports; fix any drift. Produce docs/brand/consistency-audit-{date}.md. | Enhancement | 1) Palette/typography/logo usage consistent across all three surfaces. 2) PDF reports use the light-mode brand header/footer. 3) Audit document lists and resolves every drift. | Not Started | 10% | 2
P13 — Legal, Runbooks & Documentation ¦ 7 tasks ¦ 22.5 hrs Commercial and operational readiness. The deployment runbook (capturing the hard-won login/deploy knowledge), the incident-response runbook + daily backup, UI-Standards onboarding, the AI/ML architecture + tenant-isolation/audit docs, and the legal pack (mutual NDA, pilot SOW, GDPR DPA + LLM-provider disclosure). EXIT STATE (healthy): you can sign a pilot and operate it safely.
PPIQ-T275 | Deployment runbook (server, Compose, Caddy, Jenkins) | P13 | important | Track 2 — Hardening | Documentation | Runbook / Deployment | STARTING POINT (30-May audit — already built): Deployment knowledge now exists informally (Compose, Caddy, MigrateAsync, PlantProcess:Auth binding, kill-by-port, real-admin!=bootstrap). docker-compose.demo.yml + Caddyfile + Jenkinsfile present. WHAT REMAINS — the actual work of this task: Write the deployment runbook and CAPTURE the hard-won login/deploy knowledge: auth binds from PlantProcess:Auth (not Auth); real-admin password must differ from bootstrap; dotnet run listens as PlantProcess.Api.exe so kill by PORT not name; MigrateAsync at startup; __ env convention; Docker service-name host; frontend VITE_SMOKE_PASSWORD must match backend admin. FULL REFERENCE SPEC: docs/runbook/deployment.md: bootstrap a fresh Hetzner Ubuntu server from zero to running PPIQ in < 30 min — SSH hardening, Docker, repo clone, .env prep, Caddy + Caddyfile, Jenkins + plugins + webhook + the Node tool fix (T201), first deploy, post-deploy verification. Each step has the exact command, expected output, and failure-and-remediation note. | New Feature | 1) A new engineer bootstraps a fresh server in < 30 min. 2) Every command verified live. 3) Failure modes documented with fixes. 4) Includes the Node/Jenkins fix so the build is green from scratch. | Partial | 25% | 4
PPIQ-T276 | Incident-response runbook + daily backup job | P13 | important | Track 2 — Hardening | Documentation | Runbook / Incident Response | BUILD FROM SCRATCH (30-May audit: 096 audit-log immutability + general hardening exist; no incident-response runbook or daily backup job.). SPECIFICATION: docs/runbook/incident-response.md: rollback to the previous container tag < 5 min, restore from Postgres backup, restore from audit-log replay, customer comms templates, severity matrix, escalation. Verify a daily backup job exists; if not, build it (offsite/encrypted). | New Feature | 1) Runbook covers the four scenarios with concrete commands. 2) Daily backup job exists, runs, stores backups offsite encrypted. 3) Restore tested end-to-end in a sandbox < 30 min. 4) Severity matrix + comms templates approved. | Not Started | 5% | 5
PPIQ-T277 | UI Standards onboarding for future contributors | P13 | important | Track 2 — Hardening | Documentation | Documentation / Onboarding | STARTING POINT (30-May audit — already built): UI Standards Reference sheet + Standard* components + ESLint enforcement constitute de-facto onboarding. WHAT REMAINS — the actual work of this task: Write the UI Standards onboarding doc for future contributors (codify what the sheet + ESLint already enforce). FULL REFERENCE SPEC: docs/ui-standards/contributing.md: canonical import paths, the ESLint rules, how to add/extend a Standard* component without breaking the contract, how to update design tokens. Reference the Storybook URL. Worked example: add a ProgressBar primitive in < 60 min. | New Feature | 1) Document references all Standard* primitives. 2) Worked example is reproducible. 3) A new contributor authors a primitive PR in < 60 min. | Partial | 40% | 2.5
PPIQ-T279 | AI/ML subsystem architecture doc + tenant isolation & audit doc | P13 | important | Track 2 — Hardening | Documentation | Documentation / Architecture | ARCHITECTURE · Documents this Intelligence Architecture (AI & ML Design) for tenants/security reviews — the six-layer pipeline, the component responsibility matrix and the one-LLM-row honesty boundary (Intelligence Architecture §3, §6). STARTING POINT (30-May audit — already built): ml-engine-and-assistant-design.md exists (architecture); no tenant-isolation & audit doc. WHAT REMAINS — the actual work of this task: Write the AI/ML subsystem architecture doc (can draw on the design md) + the tenant-isolation & audit doc. FULL REFERENCE SPEC: Two docs for SOC 2 and customer security reviews: (1) docs/architecture/ml-engine-and-assistant-design.md committed and kept current with the implementation (the transparent-engine + RAG-assistant design, honesty contract, in-house-vs-API boundary); (2) docs/architecture/security-and-isolation.md — SingleTenantPerPilot, tenant_id row-level security, audit-log immutability triggers, retention defaults, encryption at rest/in transit, key rotation, backup encryption. Cross-reference AuditLogImmutabilityTests.cs. | New Feature | 1) The ML design doc matches the shipped engine + assistant. 2) The security doc covers all topics with diagrams. 3) Diagrams checked in as source + PNG. 4) Founder + counsel review for accuracy. | Partial | 20% | 4
PPIQ-T272 | Mutual NDA template | P13 | important | Track 4 — Website | Documentation | Legal / NDA | BUILD FROM SCRATCH (30-May audit: No NDA template found.). SPECIFICATION: docs/legal/NDA-mutual-v1.docx parameterized for {EffectiveDate}{Counterparty}{Term}: confidential-info definition, exclusions, term (default 3y), purpose limitation, return of materials, no implied license, governing law (Düsseldorf / German law default). Counsel review before first use. Plain-md version for diffing. | New Feature | 1) Docx template renders with placeholders. 2) Counsel sign-off captured in docs/legal/REVIEWS.md. 3) MD diff version checked in. | Not Started | 0% | 2
PPIQ-T273 | SOW pilot template | P13 | important | Track 4 — Website | Documentation | Legal / SOW | BUILD FROM SCRATCH (30-May audit: No SOW template found.). SPECIFICATION: docs/legal/SOW-pilot-v1.docx: scope (sources connected, modules enabled, success metrics), duration (default 8 weeks), price, deliverables, acceptance criteria, change-control. Aligned with the pricing model. Counsel review. | New Feature | 1) Docx template renders with placeholders. 2) Pricing fields match the website pricing page. 3) Counsel sign-off captured. | Not Started | 0% | 2.5
PPIQ-T274 | DPA template aligned with GDPR (+ LLM provider disclosure) | P13 | important | Track 4 — Website | Documentation | Legal / DPA | BUILD FROM SCRATCH (30-May audit: No DPA template found.). SPECIFICATION: docs/legal/DPA-gdpr-v1.docx: controller/processor roles, processing purposes, data categories, subprocessors (Hetzner; and ANY external LLM/embedding provider IF the assistant's API mode is enabled — with the data-minimization note that only abstracted findings are sent), security measures, breach notification (72h), audit rights, retention, deletion on termination. Counsel review. | New Feature | 1) Docx template renders with placeholders. 2) Subprocessor list matches the actual deployment incl. any LLM provider. 3) The air-gapped/disable-AI option is documented. 4) Counsel sign-off captured. | Not Started | 0% | 2.5

## Architecture Map
PlantProcess IQ — Architecture Map (v12 · 31 May 2026)
How the backlog maps onto the AI & ML Design (companion to Product Vision v2.0). The product is a deterministic statistical brain in PostgreSQL with C# orchestration; a language model is the voice only. Read top-to-bottom: data flows UP through six layers — computation everywhere, language only at the very top — and each layer, component and money-lever below names the phase and tasks that build it.
A · THE SIX-LAYER INTELLIGENCE PIPELINE
Computation flows up; language only appears at the very top. L1–L5 are deterministic and testable — numbers come from SQL and C#, never a model. Only L6 introduces an LLM, and it phrases what L4/L5 computed; it may not invent a single figure.
Layer | Answers |  | Owner · key components | Honesty boundary | Owning phase · tasks
L1 · Ingest & Canonicalize | What is the faithful, joined truth? (no interpretation) |  | Connectors ×6 + factory · DeltaImportExecutionService · MappingExecutionService · SafeSqlValidator. Source DBs → private delta dumps → mapping engine → canonical model + genealogy spine (heat→ladle→tundish→strand→slab→coil→defect→QA). | No analysis, scoring or inference — L1 only moves and joins data faithfully; it never interprets it. | P02 — Data Lifecycle T245 T246 T247 T290 T206 T207 T294
L2 · Describe (dashboards) | What happened? (pure description) |  | DashboardWidgetQueryService + DashboardQueryService · WidgetQueryExpressionService (compiles each widget) · DashboardWidgetQuerySafetyRegistry + SafeSqlValidator. Aggregation, filtering, time-buckets, the heat map (line×shift×day), KPI tiles — all safe, validated SQL. | Causal language forbidden. A chart shows a trend; it never says one thing 'causes' another. | P03 — Page Builder T289 T240 T241 T242 T243 T244 T278
L3 · Feature Store (make learnable) | What are the learnable inputs & outcomes? |  | ppiq_ml_refresh_feature_store_v6 (SQL) · FeatureEngineeringService (derived metallurgy: CEV, true superheat, casting-speed mean/delta, residency, shift) · QualityLabelBuilderService (defect/KPI/downtime outcomes). Four grains: heat / strand / coil / location. | Correlation or ranking forbidden. L3 prepares the inputs; it never measures relationships. | P04 — ML Data Foundation T209 T210 T211 T293 T212 T213 T292
L4 · Correlate (THE BRAIN) | Which inputs are suspected drivers? (find associations) |  | 204_ml_learning_core (SQL: the sweep + statistics) · CorrelationService (orchestrate, assemble, filter). Type-aware methods (Pearson / Spearman / point-biserial / chi-square+Cramér's V / MI / Lasso); B-H q-values (FDR), effect-size-first, power, bootstrap stability, VIF; effective-n by independent heat. → ml_correlation_results_v2. | No LLM. A model never computes, ranks or judges a correlation. Findings below power/stability thresholds are flagged, not promoted. | P05 — Correlation Learning T214 T215 T216 T217 T218 T219
L5 · Reason (risk · pages · KB) | Why, and how risky? (decomposable) |  | RiskScoreService (additive, exact contribution decomposition) · MlReadinessService (gate) · DeterministicEmbeddingProvider (offline-safe retrieval). Associations → risk scores, auto-generated inspection pages, and an evidence knowledge base. | Transparent & decomposable. Under-powered data yields no confident score; readiness reschedules it. | P06 — Inspection→Pages T220–T225 P07 — Risk & Governance T236 T237 T238 T239
L6 · Advise (AI Assistant) | What should I do, and what is it worth? |  | Suggestion engine (rule-based, evidence-linked, impact-ranked) · RAG agent + typed tools (query findings, run inspection, fetch KPI, walk genealogy, compute impact) · Narrative providers (Api/Local/Configured). Validated findings → ranked, evidence-linked advice + a grounded conversational agent. | The LLM is the voice; every figure traces to a tool result. Only abstracted findings cross an external boundary — never raw rows or PII. | P08 — Suggestions & Value T226–T229 · T296 T297 T298 P09 — RAG Agent T230–T235 · T291
B · COMPONENT RESPONSIBILITY MATRIX (17 components)
Exactly one row may use a language model, and its job is phrasing — not computation. Everything that produces a number is deterministic SQL or C#. This is the answer to 'is your AI a black box?' — no, and here is the table.
Component | Layer | Runs in | Owns | May use LLM? | Owning task(s)
Connectors (×6) + factory | L1 | Infra | Read each source; typed, bounded failures | No | T247 T245 T290
DeltaImportExecutionService | L1 | Infra | Resumable, zero-duplicate delta import | No | T207
MappingExecutionService | L1 | App | Project dumps → canonical; genealogy spine | No | T294 T246
SafeSqlValidator | L1/L2 | App | Block DDL / cross-tenant / injection — at preview, save & execute | No | T206 T242
DashboardWidgetQueryService | L2 | App | Run widget queries; aggregation / sort / filter | No | T242 T241
WidgetQueryExpressionService | L2 | App | Compile per-widget expression → safe parameterized SQL | No | T242 T278
ppiq_ml_refresh_feature_store_v6 | L3 | Postgres | Build the multi-grain feature store | No | T209
FeatureEngineeringService | L3 | App | Derived metallurgy features | No | T210
QualityLabelBuilderService | L3 | App | Outcome labels (defect / KPI / downtime) | No | T211 T293
204_ml_learning_core (SQL) | L4 | Postgres | The statistical sweep + FDR + effect size | No | T215 T216
CorrelationService | L4 | App | Orchestrate sweeps; assemble & filter results | No | T212 T215 T218
MlReadinessService | L4/L5 | App | Readiness gate before any learning / score | No | T217
RiskScoreService | L5 | App | Additive, decomposable risk score | No | T236 T237
DeterministicEmbeddingProvider | L5/L6 | App | Offline-safe embeddings for retrieval | No | T213 T292
Suggestion engine | L6 | App | Rank findings → evidence-linked advice | No (rules) | T226 T229
RAG agent + tools | L6 | App | Retrieve + call typed tools + ground | Orchestrates only | T232 T231 T233
Narrative providers (Api/Local/Configured) | L6 | Infra | Phrase structured results as language | Yes — voice only | T292 T235 T291
C · WIDGET & SQL ENGINE — the compile-and-guard pipeline (§4)
The expression gives infinite flexibility; the compile-and-validate pipeline gives zero unsafe SQL. The user never writes raw SQL that reaches the database unchecked.
Step | Stage | What happens
1 | Author | In the widget wizard the user picks a data source (canonical entity or KPI view) and writes/selects an expression (e.g. 'defect rate grouped by shift, last 30 days'), with JetBrains-Mono editing and autocomplete of available views/columns. Tasks: T241 T242 T278
2 | Compile | WidgetQueryExpressionService turns the expression + binding into a parameterized SQL query against the canonical schema — never string-concatenated user input. Tasks: T242
3 | Validate | DashboardWidgetQuerySafetyRegistry + SafeSqlValidator reject DDL, multiple statements, cross-tenant references and anything outside the allowed surface — at preview AND save AND execute. Typed errors: NoSuchView / NoSuchColumn / InvalidAggregateForType. Tasks: T206 T242
4 | Execute & render | DashboardWidgetQueryService runs the parameterized query with a timeout and row cap; results render as an interactive chart / table / heat map with filter and sort. Tasks: T242 T244
D · VALUE MODEL — Proving the Money (§5) · NEW in v12: T296 / T297 / T298
PPIQ never promises a guaranteed saving — it presents an evidence-based opportunity: 'this suspected contributor is associated with X% of this defect at this effect size and reliability; closing it is worth approximately € Y/month at your volumes.' The customer supplies the cost inputs; PPIQ supplies the linkage and the arithmetic.
Lever | What PPIQ surfaces |  | How it converts to money
Quality / defects | Suspected process contributors to each defect class, ranked by effect size. |  | Fewer defective coils → less downgrade / scrap / rework; each avoided defect = recovered prime value per ton.
Downtime | Process conditions associated with production-stoppage (not just equipment-stoppage) minutes. |  | Each avoided production-stoppage hour = recovered throughput × contribution margin per ton.
Productivity | Parameters associated with throughput / yield KPIs; bottleneck patterns by line × shift. |  | Higher prime yield and uptime → more saleable tons from the same inputs.
Loss / waste | Energy-per-ton and additive-usage outliers correlated with operating conditions. |  | Tighter operating windows → lower energy and consumable cost per ton.
Worked example, demo scale (~630 heats/mo · ~160 t/heat ≈ 100,000 t/mo · ~5,600 coils/mo) — illustrative, ranked by value × confidence:
Opportunity (illustrative) |  | Linkage PPIQ provides |  | Indicative monthly value
Cut a surface-defect class by 20% |  | Suspected contributor at strong effect size + reliability, with the evidence and sample |  | ~300 coils/mo downgraded at ~€X/coil recovered → ~€ (0.20 × 300 × X) / month
Avoid 2 production-stoppage hours/mo |  | Caster condition associated with sequence-rebuild cascades |  | ~2 h × ~180 t/h × margin/t → recovered saleable tonnage
Lift prime yield 0.5 pt |  | Parameters associated with the yield KPI, by line × shift |  | 0.5% of ~100,000 t × margin/t → additional prime tons
Trim energy/ton 1% |  | Energy outliers correlated with operating windows |  | 1% of energy spend across ~100,000 t → direct cost reduction
Built by (v12): | T296 — deterministic Value/Impact engine (the 'compute impact' tool): per-lever EUR opportunity WITH assumptions + confidence band; reproducible; refuses to fabricate when inputs are missing. T297 — per-tenant cost-assumption configuration (cost-per-defect, margin-per-ton, energy price…) with labelled demo defaults. T298 — evidence-first ROI presentation contract in the feed & assistant: every euro figure preceded by its evidence and ranked by value × confidence; 'opportunity / approximately / associated-with', never a promise.
ROI framing for the pitch | Each lever is small in percent and large in euros. A fraction of a yield point, a couple of avoided stoppage hours, one defect class trimmed — at 100,000 t/month each is a material number, and several compound. Against a license fee, payback is typically a single avoided incident. PPIQ's job is to make that case visible and auditable, not to assert it.
E · EIGHT DESIGN PRINCIPLES (§6)
1 · Deterministic compute, generative narration only |  | Numbers come from SQL and C#. The LLM phrases; it never computes.
2 · Every finding is qualified |  | Effective-n (by heat), q-value (FDR), effect size, stability, and an evidence link — or it is not shown.
3 · Readiness gates inference |  | Under-powered data yields no confident result; it reschedules with backoff.
4 · Descriptive and inferential are separate layers |  | Charts state facts; only the correlation engine speaks of association.
5 · Experience lives in the knowledge base |  | Findings and feedback compound over time; the model stays stateless.
6 · Air-gappable by design |  | The brain needs no external service; narration is a swappable, self-hostable provider; only abstracted findings ever leave.
7 · Generic, never bespoke |  | Features, outcomes, KPIs and widgets are data and configuration — nothing in the engine is hardcoded to one plant.
8 · Value is shown, not promised |  | PPIQ links a driver to an outcome and does the arithmetic on the customer's own costs; it never guarantees a saving.
In one sentence | Plant data flows up through faithful ingestion, honest description, a learnable feature store, a transparent statistical correlation core, decomposable risk and a compounding knowledge base — and only at the top does a language model put it into words, never inventing a number it cannot trace.

## Audit Summary
Implementation Audit & v7 Re-sequencing
Status is evidence-based: every task was checked against the 30-May code snapshot (endpoints, services, entities, SQL, frontend, CI). 'Done' = capability present (a one-time confirmation may remain); 'Partial' = real scaffolding with concrete gaps; 'Not Started' = essentially absent. Each task now carries ONE authoritative Description (folding current-state + what to build) and ONE Validation.
v8 update (31-May 12:56 re-audit): P01 auth/deploy hardening largely DONE (StartupConfigurationValidator rejects legacy Auth:* keys & enforces a Production bootstrap sentinel; kill-by-PORT scripts; server-exposure verifier; Postgres off 0.0.0.0). The ML ENGINE moved from 'not started' to real: learning core 204_ (Pearson/point-biserial/Cramer's-V, BH q-values, effect-size buckets, effective-n), 4 jobs registered, on-demand /api/ml/learning, and the narrative/embedding provider trio. Two gaps remain front-of-mind: (1) the learning jobs are not yet SCHEDULED in the Worker (T217 — it still runs only Import/Quality/Risk/Delta); (2) the CONVERSATIONAL AI ASSISTANT does not exist — no agent/tool layer (T232), no chat UI (T233). The voice (providers) and the brain (stats) are built; the assistant that orchestrates them is the key remaining ML deliverable.
v9 update: added Phase 0 — Test Foundation (8 tasks, ~67h). The suite is audited, repaired, covered, and made a regression gate BEFORE the feature/hardening phases proceed. See the Test Register sheet for the per-file delete/modify/keep/add/transfer decisions (113 files): 8 DELETE, 31 MODIFY, 14 ADD, 5 validation scripts TRANSFER→TEST, 11 RETIRE, 8 KEEP-AS-GATE, 36 KEEP. Phase 0 is Not Started, so headline status %s are unchanged except the denominator grows to 103 tasks.
v10 update: Phase 0 expanded to 12 tasks (~96h) and now ships the Test Matrix sheet — 177 enumerated test cases (P1: 104, P2: 69, P3: 4) across 18 groups, including first-class Performance/Load and ML/AI honesty-contract groups, full 6-connector behavioural tests, and an endpoint-authorization+contract matrix. Coverage is now provable by enumeration, not by a percentage.
v11 update (31-May 15:25 snapshot): Phase 0 executed across four waves. T300/T301/T302/T304/T306 are Done; T303/T305/T307/T309/T310/T311 are Partial; T308 (performance/load) is effectively the main remaining Phase-0 build. Overall completion rises accordingly; the headline numbers below recompute from the per-task Status column.
v12 update (31-May, Intelligence-Architecture-Aligned): the backlog is now mapped to the AI & ML Design's six-layer intelligence pipeline (L1 Ingest -> L2 Describe -> L3 Feature Store -> L4 Correlate -> L5 Reason -> L6 Advise). Every data / ML / widget / assistant task carries an ARCHITECTURE anchor naming its layer, owning component and honesty boundary. The Value Model from the architecture's S5 ('Proving the Money') is now first-class: added T296 (deterministic impact / 'compute impact' engine), T297 (per-tenant cost-assumption inputs) and T298 (evidence-first ROI presentation contract) to P08, now 7 tasks / 38 h. New 'Architecture Map' sheet maps all six layers and the 17-component responsibility matrix to their owning phases / tasks; the Test Matrix gains a Value & ROI Model section plus a descriptive-vs-inferential honesty case. Totals: 110 tasks / 528.5 h.
Status | Count | Effort (hrs) | % of tasks
Done | 28 | 123.5 | 25.45%
Partial | 45 | 238 | 40.91%
Not Started | 37 | 167 | 33.64%
TOTAL | 110 | 528.5 | 100%
How v7 is re-grouped (your four rules)
• RULE 1 — importance first: P01 makes the app reliably build/login/deploy (foundation + demo-protection); P02 the data backbone; P03 the page builder you demo; P04–P09 the AI/ML differentiator; P10 hardening; P11 demo; P12 website; P13 legal/docs.
• RULE 2 — same feature together: the v6 bug-fixes and enhancements are no longer appended at the end. The login/auth/deploy bugs sit WITH the build-green work in P01; the genealogy + downtime-outcome + provider-abstraction enhancements sit WITH the data/ML phases they belong to; the page-model enhancement leads the page-builder phase.
• RULE 3 — healthy end state: every phase carries an explicit EXIT STATE (green pipeline, all sources connected, a user-built page reloads, the engine recovers known correlations, etc.). No phase ends with a broken build, page, or connection.
• RULE 4 — prerequisites first: e.g. the 8 split sources (P02) precede the genealogy spine and the feature store that consume them; and the FULL auth matrix (T204) was deliberately MOVED from the old P01 to P10 because it must cover /api/ml/* endpoints that only exist after P04–P09.
What the audit found
• DONE/strong: build-green hotfixes (T201–T203, T205); all six DB connectors; two-stage delta import; schema-mapping engine (T206); widget builder + script layer (T242 — corrects the old 'unstarted' note); transparent risk scorer (T236); ML data-foundation SQL incl. pgvector KB (T209/T213).
• PARTIAL: feature store/outcomes/compute-interface scaffolding exists but the LEARNING ENGINE does not; a rich per-widget builder exists but no page CANVAS or user-created PageDefinition; a 23MB coherent dataset exists but is NOT split across 8 sources; license context exists but the live tier toggle is unfinished.
• NOT STARTED (largest gaps): the four scheduled learning jobs + statistical-validity machinery (T214–T216); inspection→generated-pages (T220–T224); suggestion feed (T226–T229); conversational assistant (T230–T235); HeatMap (T249); demo-sources compose (T245); demo scripts/personas/video; the 5 website product pages; legal templates; runbooks.

## Test Register
Phase 0 — Test Register (delete / modify / keep / add / transfer), grounded in the 31-May snapshot
Disposition legend: DELETE = remove (no-op/duplicate, replaced); MODIFY = real intent, fix/strengthen assertions or de-brittle; KEEP = already strong, leave (maybe minor align); ADD = brand-new test for an uncovered area; TRANSFER→TEST = a behavioural validation script becomes a real test; KEEP-AS-GATE = pure structural check stays a CI/ESLint gate; RETIRE = per-phase acceptance script superseded by real tests.
Area | File | Lines | Disposition | Rationale / Action | Maps to Task
BACKEND UNIT
Backend unit | PlantProcess.Api.IntegrationTests/ApiTestEnvironmentTests.cs | 12 | DELETE | No-op smoke (true.Should().BeTrue()). Remove once the project has real integration tests (T303). | PPIQ-T301
Backend unit | PlantProcess.Application.UnitTests/ApplicationTestEnvironmentTests.cs | 18 | DELETE | Asserts only that the assembly loads. Superseded by real Application unit tests. | PPIQ-T301
Backend unit | PlantProcess.Domain.Tests/DomainTestEnvironmentTests.cs | 17 | DELETE | Assembly-load smoke only. Domain logic gets real tests instead. | PPIQ-T301
Backend unit | PlantProcess.PerformanceTests/PerformanceTestEnvironmentTests.cs | 12 | DELETE | No-op smoke. Replace with a real perf assertion or remove the project from the gate. | PPIQ-T301
Backend unit | PlantProcess.Api.IntegrationTests/AssemblyInfo.cs | 3 | KEEP | Not a test (collection/parallelism attributes). Leave as-is. | PPIQ-T301
Backend unit | PlantProcess.Application.UnitTests/Common/ApplicationResultTests.cs | 91 | KEEP | Real result-type tests. Keep. | PPIQ-T302
Backend unit | PlantProcess.Application.UnitTests/Common/PageRequestTests.cs | 39 | KEEP | Real pagination tests. Keep. | PPIQ-T302
Backend unit | PlantProcess.Application.UnitTests/Common/TextNormalizerTests.cs | 40 | KEEP | Real normalizer tests. Keep. | PPIQ-T302
Backend unit | PlantProcess.Application.UnitTests/Dashboarding/WidgetQueryExpressionServiceTests.cs | 56 | MODIFY | Expand expression safety/validation cases (CTE, nested, disallowed funcs) to match the 418L service (T302). | PPIQ-T302
Backend unit | PlantProcess.Application.UnitTests/Licensing/LicenseServiceTests.cs | 177 | KEEP | Strong license tests. Keep; add any new tier-feature corner cases (T302). | PPIQ-T302
Backend unit | PlantProcess.Application.UnitTests/Security/SafeSqlPolicyTests.cs | 197 | KEEP | Strong SafeSql policy suite. Keep; extend with new cross-tenant/CTE edges (T302). | PPIQ-T302
Backend unit | PlantProcess.Domain.Tests/Architecture/DomainArchitectureTests.cs | 51 | KEEP | Architecture guard (layer boundaries). Valuable — keep. | PPIQ-T301
Backend unit | PlantProcess.Domain.Tests/Dashboarding/DashboardWidgetDefinitionExpressionTests.cs | 54 | KEEP | Real domain expression tests. Keep. | PPIQ-T302
Backend unit | (NEW) Analytics/RiskScoreServiceTests.cs |  | ADD | Assert exact additive contribution decomposition + explanation shape on a known vector. | PPIQ-T302
Backend unit | (NEW) Analytics/FeatureEngineeringServiceTests.cs |  | ADD | Assert derived features (cev, true_superheat, casting speed delta, residency, shift) vs hand-computed values. | PPIQ-T302
Backend unit | (NEW) Analytics/MlReadinessServiceTests.cs |  | ADD | Assert readiness gate thresholds both sides of the boundary. | PPIQ-T302
Backend unit | (NEW) Analytics/QualityLabelBuilderServiceTests.cs |  | ADD | Assert quality-label derivation for defect classes/severity. | PPIQ-T302
BACKEND INTEGRATION
Backend integration | PlantProcess.Api.IntegrationTests/Connectors/ConnectorTruthContractTests.cs | 121 | KEEP | Real contract test for connector truth panel. Align with live demo-source containers (T303). | PPIQ-T303
Backend integration | PlantProcess.Api.IntegrationTests/Health/HealthEndpointTests.cs | 24 | KEEP | Thin but valid health check. Keep. | PPIQ-T301
Backend integration | PlantProcess.Api.IntegrationTests/Import/DeltaImportResumabilityTests.cs | 123 | MODIFY | Grew to 123L (Stage1Stage2AndFullCycle, MaxRowsSmallBatch, RejectsAnonymousAccess). Add an explicit mid-batch CRASH→resume-with-no-duplicates and schema-drift case (T303). | PPIQ-T303
Backend integration | PlantProcess.Api.IntegrationTests/Infrastructure/AuthenticatedApiTestBase.cs | 285 | KEEP | Solid shared harness (real DB + auth). Reuse for the new ML/data integration tests. | PPIQ-T303
Backend integration | PlantProcess.Api.IntegrationTests/OpenApi/OpenApiContractTests.cs | 54 | MODIFY | Good idea; extend to assert the ML + page-builder endpoints appear in the OpenAPI doc as they land. | PPIQ-T303
Backend integration | PlantProcess.Api.IntegrationTests/Security/AuthEndpointTests.cs | 72 | MODIFY | Covers basic login. Extend to the full gate matrix: empty→400, bootstrap-collision→403, valid→200, bad role, short signing key→500 (T303). | PPIQ-T303
Backend integration | PlantProcess.Api.IntegrationTests/Security/SchemaConfigurationSafetyEndpointTests.cs | 78 | MODIFY | Extend to assert the THREE named resolver errors and SafeSqlValidator blocking generated join SQL (T303). | PPIQ-T303
Backend integration | PlantProcess.Api.IntegrationTests/Smoke/ApiEndpointCatalogSmokeTests.cs | 88 | KEEP | Useful endpoint-catalog smoke. Keep as a fast gate. | PPIQ-T301
Backend integration | PlantProcess.Api.IntegrationTests/Smoke/ApiSmokeEndpointTests.cs | 33 | MODIFY | Overlaps the catalog smoke; merge into one smoke spec to cut duplication. | PPIQ-T301
Backend integration | PlantProcess.Infrastructure.IntegrationTests/Audit/AuditLogImmutabilityTests.cs | 271 | KEEP | Excellent immutability suite (real Postgres). Keep; extend to new audit surfaces. | PPIQ-T303
Backend integration | PlantProcess.Infrastructure.IntegrationTests/Connectors/CsvConnectorSmokeTests.cs | 61 | MODIFY | Real CSV smoke. Add golden-file assertions + run against demo-source data (T303). | PPIQ-T303
Backend integration | PlantProcess.Infrastructure.IntegrationTests/Connectors/ExcelConnectorSmokeTests.cs | 77 | MODIFY | Real Excel smoke. Add golden-file assertions (T303). | PPIQ-T303
Backend integration | PlantProcess.Infrastructure.IntegrationTests/InfrastructureTestEnvironmentTests.cs | 18 | DELETE | Assembly-load smoke only. | PPIQ-T301
Backend integration | (NEW) Analytics/MlLearningCoreIntegrationTests.cs |  | ADD | Run ppiq_ml_seed_phase45_golden_dataset + ppiq_ml_run_learning_job_v1 on real PG; assert correlation recovery, BH q-values, FDR rejection. Replaces validate-v7-phase04-phase05 regex. | PPIQ-T303
Backend integration | (NEW) Security/AuthGateMatrixTests.cs |  | ADD | Assert the full login gate matrix at the API (empty/bootstrap-collision/valid/role/short-key). | PPIQ-T303
Backend integration | (NEW) Database/SqlScriptHygieneApplyTests.cs |  | ADD | Apply ALL ordered scripts on a fresh PG under ON_ERROR_STOP=1; assert clean apply + BOM-free. Replaces validate-sql-script-hygiene regex. | PPIQ-T306
FRONTEND UNIT
Frontend unit | src/api/legacy/__tests__/plantProcessApi.contract.test.ts | 62 | MODIFY | Legacy API contract; align with the current apiClient and shrink legacy surface (noLegacyApiGrowth already guards). | PPIQ-T304
Frontend unit | src/components/__tests__/ActiveFilterChips.test.tsx | 61 | KEEP | Real component test. Keep. | PPIQ-T304
Frontend unit | src/components/__tests__/AsyncState.test.tsx | 24 | MODIFY | Thin; expand to loading/error/empty/success transitions. | PPIQ-T304
Frontend unit | src/components/__tests__/LockedFeatureOverlay.test.tsx | 17 | MODIFY | Thin; assert license-gated render + CTA. | PPIQ-T304
Frontend unit | src/components/__tests__/MetricCard.test.tsx | 45 | KEEP | Real test. Keep. | PPIQ-T304
Frontend unit | src/components/__tests__/SortableDataTable.virtualization.test.tsx | 59 | KEEP | Real virtualization test. Keep. | PPIQ-T304
Frontend unit | src/components/__tests__/StatusBadge.test.tsx | 30 | KEEP | Real test. Keep. | PPIQ-T304
Frontend unit | src/components/standard/__tests__/StandardButton.test.tsx | 64 | MODIFY | Good; complete ALL variants/states per UI Standards Reference + refresh snapshot. | PPIQ-T304
Frontend unit | src/components/standard/__tests__/StandardTable.test.tsx | 52 | MODIFY | Complete loading/error/empty/sorted/paginated + 'Refreshing X…' pattern. | PPIQ-T304
Frontend unit | src/components/standard/__tests__/StandardTabs.test.tsx | 41 | MODIFY | Add overflow-scroll + keyboard-focus + urlParam state. | PPIQ-T304
Frontend unit | src/hooks/__tests__/useInlineFormValidation.test.tsx | 47 | KEEP | Real hook test. Keep. | PPIQ-T304
Frontend unit | src/test/architecture/frontendArchitecture.test.ts | 22 | KEEP | Architecture guard. Keep. | PPIQ-T301
Frontend unit | src/test/architecture/noLegacyApiGrowth.test.ts | 37 | KEEP | Prevents legacy API growth. Keep. | PPIQ-T301
Frontend unit | src/test/integration/mockedApi.integration.test.ts | 12 | MODIFY | Stub (12L). Turn into a real mocked-API integration test for a key flow or delete. | PPIQ-T304
Frontend unit | src/test/smoke/frontendSmoke.test.ts | 7 | DELETE | 7-line smoke; superseded by route-smoke e2e + real unit tests. | PPIQ-T301
Frontend unit | (NEW) src/api/__tests__/apiClient.retry-backoff.test.ts |  | ADD | Assert capped retries + backoff and 401/403/500/network → distinct outcomes (T280/T281). | PPIQ-T304
Frontend unit | (NEW) src/state/__tests__/AuthContext.bootstrap.test.tsx |  | ADD | Assert no infinite re-login loop on failing bootstrap; bounded attempts. | PPIQ-T304
Frontend unit | (NEW) src/state/__tests__/LicenseContext.gating.test.tsx |  | ADD | Assert tier→feature visibility and the override banner. | PPIQ-T304
Frontend unit | (NEW) src/components/standard/__tests__/DataFetchBoundary.test.tsx |  | ADD | Assert loading/error/auto-retry + forbidden-phrase guard. | PPIQ-T304
Frontend unit | (NEW) src/pages/PageBuilder/__tests__/pageBuilderReducer.test.ts |  | ADD | Assert layout add/move/resize/remove state transitions. | PPIQ-T304
E2E
E2E | e2e/golden-path.spec.ts | 224 | KEEP | Strongest journey spec. Keep as the canonical happy-path; align selectors. | PPIQ-T305
E2E | e2e/dashboard-refresh-filter.spec.ts | 196 | KEEP | Rich refresh/filter coverage. Keep. | PPIQ-T305
E2E | e2e/hardening-matrix.spec.ts | 154 | KEEP | Broad hardening coverage. Keep; align with consolidated journeys. | PPIQ-T305
E2E | e2e/security/auth-matrix-admin.spec.ts | 146 | KEEP | Full 3-identity matrix incl /api/ml/*. Keep; extend to /api/ml/learning (T204). | PPIQ-T305
E2E | e2e/admin-schema-focused.spec.ts | 126 | KEEP | Real schema-config flow. Keep. | PPIQ-T305
E2E | e2e/widget-builder-focused.spec.ts | 114 | KEEP | Real widget-builder flow. Keep; fold into the page-builder journey. | PPIQ-T305
E2E | e2e/admin-db-focused.spec.ts | 109 | KEEP | Real DB-link flow. Keep; part of the data-lifecycle journey. | PPIQ-T305
E2E | e2e/api-smoke.spec.ts | 99 | KEEP | API smoke. Keep as fast gate. | PPIQ-T305
E2E | e2e/license-and-demo-lifecycle.spec.ts | 90 | KEEP | Real license/demo flow. Keep as the license-toggle journey. | PPIQ-T305
E2E | e2e/phase1-golden-demo.spec.ts | 84 | MODIFY | Merge into the data-lifecycle journey; drop the phase-number name. | PPIQ-T305
E2E | e2e/phase1-security-hardening.spec.ts | 82 | MODIFY | Fold into hardening-matrix; remove duplication. | PPIQ-T305
E2E | e2e/phase2-chart-interaction.spec.ts | 82 | MODIFY | Fold chart-interaction into the dashboard journey. | PPIQ-T305
E2E | e2e/phase2-backend-outage.spec.ts | 73 | MODIFY | Rename to resilience journey; keep the outage assertions (no fake failure). | PPIQ-T305
E2E | e2e/p1-risk-dataquality-contract.spec.ts | 71 | MODIFY | Fold into risk/data-quality journey; strengthen assertions. | PPIQ-T305
E2E | e2e/dimension2-dimension6-readiness.spec.ts | 67 | MODIFY | Obscure naming; rename by behaviour or merge into readiness checks. | PPIQ-T305
E2E | e2e/phase1-button-action-matrix.spec.ts | 67 | MODIFY | Valuable action-matrix; rename and extend to ML/page-builder controls (T253). | PPIQ-T305
E2E | e2e/nav-graph-refresh-survival.spec.ts | 63 | MODIFY | Merge with phase1-route-refresh + phase2-navigation-refresh into one refresh-survival spec. | PPIQ-T305
E2E | e2e/phase2-navigation-refresh-survival.spec.ts | 59 | DELETE | Duplicate of nav-graph-refresh-survival; consolidate. | PPIQ-T305
E2E | e2e/phase2-responsive-multibrowser.spec.ts | 65 | KEEP | Responsive/multibrowser coverage. Keep (T254). | PPIQ-T305
E2E | e2e/p0-auth-pages-contract.spec.ts | 45 | MODIFY | Fold into the auth & shell journey. | PPIQ-T305
E2E | e2e/phase1-toast-mapping.spec.ts | 46 | MODIFY | Keep the toast/status-mapping assertions; rename, align with T281. | PPIQ-T305
E2E | e2e/a11y/phase56-accessibility.spec.ts | 41 | KEEP | Accessibility checks. Keep; broaden to ML/page-builder pages. | PPIQ-T305
E2E | e2e/page-builder-v7.spec.ts | 33 | MODIFY | Thin (33L). Upgrade to the full page-builder journey (create→bind→script→save→reload). | PPIQ-T305
E2E | e2e/visual/phase56-analytics-system.visual.spec.ts | 33 | KEEP | Visual regression. Keep in the nightly visual lane. | PPIQ-T305
E2E | e2e/phase1-route-refresh.spec.ts | 31 | DELETE | Merge into the consolidated refresh-survival spec. | PPIQ-T305
E2E | e2e/route-smoke.spec.ts | 28 | KEEP | Fast route smoke. Keep as a gate. | PPIQ-T305
E2E | e2e/full-stack-smoke.spec.ts | 27 | KEEP | Full-stack smoke. Keep as a gate. | PPIQ-T305
E2E | e2e/license-gate-ux.spec.ts | 27 | MODIFY | Merge into license-and-demo-lifecycle journey. | PPIQ-T305
E2E | e2e/phase56-primary-flows.spec.ts | 26 | MODIFY | Thin; absorb into the relevant analytics journey or delete. | PPIQ-T305
E2E | e2e/phase78-workflow-widget.spec.ts | 25 | MODIFY | Thin; fold into widget/page-builder journey. | PPIQ-T305
E2E | e2e/dimension7-brand-identity.spec.ts | 24 | KEEP | Brand-identity check. Keep (T271). | PPIQ-T305
E2E | e2e/critical-shell-regression.spec.ts | 22 | KEEP | Shell regression guard. Keep. | PPIQ-T305
E2E | e2e/api/phase03-two-stage-import.spec.ts | 60 | MODIFY | Real API e2e; strengthen and align with delta-import integration (T303). | PPIQ-T305
E2E | e2e/api/phase02-data-lifecycle-contract.spec.ts | 8 | MODIFY | 8-line placeholder. Upgrade to a real data-lifecycle contract check or delete. | PPIQ-T305
E2E | (NEW) e2e/journeys/inspection-to-generated-page.spec.ts |  | ADD | Run an inspection job and view its generated analysis page (once P06 lands). | PPIQ-T305
E2E | (NEW) e2e/journeys/assistant-conversation.spec.ts |  | ADD | Ask the AI assistant a question and assert an evidence-cited answer (once P09 lands). | PPIQ-T305
VALIDATION
Validation | tools/validation/validate-v7-phase04-phase05-acceptance.cjs | 44 | TRANSFER→TEST | Regex over SQL text. Behaviour → MlLearningCoreIntegrationTests (T303). Retire the regex after. | PPIQ-T306
Validation | tools/validation/validate-v7-phase04-phase05-completion.cjs | 54 | TRANSFER→TEST | Same intent; covered by the ML integration test. | PPIQ-T306
Validation | tools/validation/validate-t208-exposure.cjs | 38 | TRANSFER→TEST | Exposure proof → a scripted external-scan test / deploy check (T303/T306). | PPIQ-T306
Validation | tools/validation/validate-sql-script-hygiene.cjs | 57 | TRANSFER→TEST | Apply-all-scripts-clean → SqlScriptHygieneApplyTests (T306). | PPIQ-T306
Validation | scripts/validate-api-client-policy.mjs | 77 | TRANSFER→TEST | apiClient policy → a Vitest assertion + ESLint rule (T304/T306). | PPIQ-T306
Validation | scripts/validate-standard-imports.mjs | 46 | KEEP-AS-GATE | Pure structural import rule. Keep as ESLint/CI gate; point at Standard* unit tests. | PPIQ-T306
Validation | scripts/validate-forbidden-copy.mjs | 74 | KEEP-AS-GATE | Forbidden-phrase grep. Keep as gate; mirror as a DataFetchBoundary unit assertion (T304). | PPIQ-T306
Validation | scripts/validate-no-console-in-src.mjs | 77 | KEEP-AS-GATE | Structural no-console rule. Keep as ESLint/CI gate. | PPIQ-T306
Validation | scripts/validate-ui-system-rollout.mjs | 93 | KEEP-AS-GATE | Rollout structure check. Keep as gate. | PPIQ-T306
Validation | tools/ui/validate-ui-standards.mjs | 37 | KEEP-AS-GATE | UI-standards structure. Keep; superseded behaviourally by Standard* tests. | PPIQ-T306
Validation | tools/ui/validate-phase2-full-ui-standards.mjs | 85 | KEEP-AS-GATE | UI-standards structure. Keep as gate. | PPIQ-T306
Validation | tools/validation/validate-phase01-phase02-gates.mjs | 171 | RETIRE | Per-phase file-existence acceptance; intent now covered by real auth/data tests + T307 gating. | PPIQ-T306
Validation | tools/validation/validate-phase01-phase02-v5-gates.mjs | 71 | RETIRE | Superseded by current tests. | PPIQ-T306
Validation | tools/validation/validate-phase03-gates.mjs | 95 | RETIRE | Superseded by delta-import integration test. | PPIQ-T306
Validation | tools/validation/validate-v6-phase01-phase02-completion.cjs | 44 | RETIRE | Completion regex; superseded by real tests. | PPIQ-T306
Validation | tools/validation/validate-v7-phase01.cjs | 68 | RETIRE | Superseded by auth/deploy tests. | PPIQ-T306
Validation | tools/validation/validate-v7-phase01-acceptance.cjs | 90 | RETIRE | Superseded by auth/deploy tests. | PPIQ-T306
Validation | tools/validation/validate-v7-phase02-phase03-acceptance.cjs | 69 | RETIRE | Superseded by data-lifecycle tests. | PPIQ-T306
Validation | tools/validation/prove-standard-import-gate.cjs | 62 | KEEP-AS-GATE | Proves the import gate fails on violation. Keep as a meta-gate. | PPIQ-T306
Validation | tools/phase78/validate-phase7-phase8-acceptance.cjs | 119 | RETIRE | Per-phase acceptance; covered by widget/page-builder e2e. | PPIQ-T306
Validation | Frontend tools/phase3/validate-phase3-phase4-acceptance.cjs | 299 | RETIRE | Large per-phase acceptance; behaviour now in e2e journeys. | PPIQ-T306
Validation | Frontend tools/phase56/validate-phase5-phase6-acceptance.cjs | 152 | RETIRE | Per-phase acceptance; covered by analytics e2e. | PPIQ-T306
Validation | Backend tools/validate-sprint6-tasks-4-8.ps1 | 193 | RETIRE | Sprint-specific PS acceptance; covered by backend tests. | PPIQ-T306
Validation | Website scripts/validate-website-content.mjs | 102 | KEEP-AS-GATE | Website content structure check. Keep as gate (T271). | PPIQ-T306
REGISTER TOTALS — ADD: 14 ¦ DELETE: 8 ¦ KEEP: 36 ¦ KEEP-AS-GATE: 8 ¦ MODIFY: 31 ¦ RETIRE: 11 ¦ TRANSFER→TEST: 5 (｜ 113 files)

## Test Matrix
Test Matrix — every required test case, enumerated (Phase 0 deliverable)
One row per test that must exist for a no-bugs / no-gaps app. Layer = where it runs (Domain/App unit, Infra/API integration, FE unit, FE e2e, Perf, Security, Contract, Honesty). Priority P1=must-have-before-pilot, P2=high, P3=medium. 'Maps to Task' is the Phase-0 task that owns building it. Status starts Not Started; update as each lands.
Test ID | Group | Layer | Target | What it asserts | Priority | Maps to Task | Status
AUTH & SESSION
TM-001 | Auth & Session | API integration | /auth/login | Empty credentials → 400 | P1 | PPIQ-T303 | Partial
TM-002 | Auth & Session | API integration | /auth/login | Valid admin → 200 + access token | P1 | PPIQ-T303 | Partial
TM-003 | Auth & Session | API integration | /auth/login | Bootstrap credential while a real admin exists → 403 | P1 | PPIQ-T303 | Partial
TM-004 | Auth & Session | API integration | /auth/login | Unknown user / wrong password → 401 | P1 | PPIQ-T303 | Partial
TM-005 | Auth & Session | API integration | /auth/login | Configured-but-wrong role → 400/403 as designed | P2 | PPIQ-T303 | Partial
TM-006 | Auth & Session | API integration | /auth/login | SigningKey missing/<32 chars → 500 (config error surfaced) | P1 | PPIQ-T303 | Partial
TM-007 | Auth & Session | API integration | /auth/login | Each persona (admin/engineer/datamanager/viewer) → 200 with correct role claim | P1 | PPIQ-T303 | Partial
TM-008 | Auth & Session | App unit | StartupConfigurationValidator | Binds from PlantProcess:Auth; a value under plain 'Auth' is ignored | P1 | PPIQ-T302 | Done
TM-009 | Auth & Session | App unit | StartupConfigurationValidator | Real-admin password == BootstrapAdminPassword → loud warning | P1 | PPIQ-T302 | Done
TM-010 | Auth & Session | App unit | StartupConfigurationValidator | Production + non-sentinel bootstrap password → fail fast | P1 | PPIQ-T302 | Done
TM-011 | Auth & Session | App unit | StartupConfigurationValidator | Missing Issuer/Audience → explicit error | P2 | PPIQ-T302 | Done
TM-012 | Auth & Session | FE unit | AuthContext.tsx | Failing bootstrap login does NOT cause an infinite re-login loop (bounded attempts) | P1 | PPIQ-T304 | Done
TM-013 | Auth & Session | FE unit | AuthContext.tsx | Successful bootstrap stores token and stops retrying | P1 | PPIQ-T304 | Done
TM-014 | Auth & Session | FE unit | apiClient.ts | auth-failure event fires once per non-2xx, not in a storm | P1 | PPIQ-T304 | Done
TM-015 | Auth & Session | FE e2e | Journey: Auth & shell | Login as each persona; route refresh survives; no fake 'connection failed' | P1 | PPIQ-T305 | Partial
ENDPOINT AUTHORIZATION
TM-016 | Endpoint Authorization | Security | /admin/overview | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-017 | Endpoint Authorization | Security | /admin/jobs-monitor | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-018 | Endpoint Authorization | Security | /admin/schema-mapping | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-019 | Endpoint Authorization | Security | /admin/two-stage-import | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-020 | Endpoint Authorization | Security | /admin/license | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-021 | Endpoint Authorization | Security | /admin/phase1 | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-022 | Endpoint Authorization | Security | /admin/phase2 | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-023 | Endpoint Authorization | Security | /admin/widgets | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-024 | Endpoint Authorization | Security | /admin/users | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-025 | Endpoint Authorization | Security | /demo-lifecycle | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-026 | Endpoint Authorization | Security | /diagnostics | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-027 | Endpoint Authorization | Security | /api/ml/readiness | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-028 | Endpoint Authorization | Security | /api/ml/foundation | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-029 | Endpoint Authorization | Security | /api/ml/learning | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-030 | Endpoint Authorization | Security | /api/ml/provider | 3-identity matrix (anon=401/403, operator, admin) — admin-only | P1 | PPIQ-T311 | Not Started
TM-031 | Endpoint Authorization | Security | /api/correlation | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-032 | Endpoint Authorization | Security | /api/risk-score | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-033 | Endpoint Authorization | Security | /api/dashboards | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-034 | Endpoint Authorization | Security | /api/materials | 3-identity matrix (anon=401/403, operator, admin) — viewer-ok | P1 | PPIQ-T311 | Not Started
TM-035 | Endpoint Authorization | Security | /api/process | 3-identity matrix (anon=401/403, operator, admin) — viewer-ok | P1 | PPIQ-T311 | Not Started
TM-036 | Endpoint Authorization | Security | /api/quality | 3-identity matrix (anon=401/403, operator, admin) — viewer-ok | P1 | PPIQ-T311 | Not Started
TM-037 | Endpoint Authorization | Security | /api/reporting | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
TM-038 | Endpoint Authorization | Security | /api/plant-layout | 3-identity matrix (anon=401/403, operator, admin) — viewer-ok | P1 | PPIQ-T311 | Not Started
TM-039 | Endpoint Authorization | Security | /api/data-quality | 3-identity matrix (anon=401/403, operator, admin) — datamanager-ok | P1 | PPIQ-T311 | Not Started
CONNECTORS
TM-040 | Connectors | Infra integration | CsvConnector | Connect with valid config succeeds; bad host/creds returns typed failure (no hang) | P1 | PPIQ-T310 | Not Started
TM-041 | Connectors | Infra integration | CsvConnector | Schema discovery returns expected tables/columns from the demo source | P1 | PPIQ-T310 | Not Started
TM-042 | Connectors | Infra integration | CsvConnector | Delta read returns only rows beyond the incremental cursor | P1 | PPIQ-T310 | Not Started
TM-043 | Connectors | Infra integration | CsvConnector | Type mapping (native → canonical) is correct for numeric/text/date/bool | P2 | PPIQ-T310 | Not Started
TM-044 | Connectors | Infra integration | CsvConnector | Connection timeout is bounded and surfaces a clear error (no infinite wait) | P2 | PPIQ-T310 | Not Started
TM-045 | Connectors | Infra integration | ExcelConnector | Connect with valid config succeeds; bad host/creds returns typed failure (no hang) | P1 | PPIQ-T310 | Not Started
TM-046 | Connectors | Infra integration | ExcelConnector | Schema discovery returns expected tables/columns from the demo source | P1 | PPIQ-T310 | Not Started
TM-047 | Connectors | Infra integration | ExcelConnector | Delta read returns only rows beyond the incremental cursor | P1 | PPIQ-T310 | Not Started
TM-048 | Connectors | Infra integration | ExcelConnector | Type mapping (native → canonical) is correct for numeric/text/date/bool | P2 | PPIQ-T310 | Not Started
TM-049 | Connectors | Infra integration | ExcelConnector | Connection timeout is bounded and surfaces a clear error (no infinite wait) | P2 | PPIQ-T310 | Not Started
TM-050 | Connectors | Infra integration | MySqlConnector | Connect with valid config succeeds; bad host/creds returns typed failure (no hang) | P1 | PPIQ-T310 | Not Started
TM-051 | Connectors | Infra integration | MySqlConnector | Schema discovery returns expected tables/columns from the demo source | P1 | PPIQ-T310 | Not Started
TM-052 | Connectors | Infra integration | MySqlConnector | Delta read returns only rows beyond the incremental cursor | P1 | PPIQ-T310 | Not Started
TM-053 | Connectors | Infra integration | MySqlConnector | Type mapping (native → canonical) is correct for numeric/text/date/bool | P2 | PPIQ-T310 | Not Started
TM-054 | Connectors | Infra integration | MySqlConnector | Connection timeout is bounded and surfaces a clear error (no infinite wait) | P2 | PPIQ-T310 | Not Started
TM-055 | Connectors | Infra integration | OracleConnector | Connect with valid config succeeds; bad host/creds returns typed failure (no hang) | P1 | PPIQ-T310 | Not Started
TM-056 | Connectors | Infra integration | OracleConnector | Schema discovery returns expected tables/columns from the demo source | P1 | PPIQ-T310 | Not Started
TM-057 | Connectors | Infra integration | OracleConnector | Delta read returns only rows beyond the incremental cursor | P1 | PPIQ-T310 | Not Started
TM-058 | Connectors | Infra integration | OracleConnector | Type mapping (native → canonical) is correct for numeric/text/date/bool | P2 | PPIQ-T310 | Not Started
TM-059 | Connectors | Infra integration | OracleConnector | Connection timeout is bounded and surfaces a clear error (no infinite wait) | P2 | PPIQ-T310 | Not Started
TM-060 | Connectors | Infra integration | PostgreSqlConnector | Connect with valid config succeeds; bad host/creds returns typed failure (no hang) | P1 | PPIQ-T310 | Not Started
TM-061 | Connectors | Infra integration | PostgreSqlConnector | Schema discovery returns expected tables/columns from the demo source | P1 | PPIQ-T310 | Not Started
TM-062 | Connectors | Infra integration | PostgreSqlConnector | Delta read returns only rows beyond the incremental cursor | P1 | PPIQ-T310 | Not Started
TM-063 | Connectors | Infra integration | PostgreSqlConnector | Type mapping (native → canonical) is correct for numeric/text/date/bool | P2 | PPIQ-T310 | Not Started
TM-064 | Connectors | Infra integration | PostgreSqlConnector | Connection timeout is bounded and surfaces a clear error (no infinite wait) | P2 | PPIQ-T310 | Not Started
TM-065 | Connectors | Infra integration | MsSqlConnector | Connect with valid config succeeds; bad host/creds returns typed failure (no hang) | P1 | PPIQ-T310 | Not Started
TM-066 | Connectors | Infra integration | MsSqlConnector | Schema discovery returns expected tables/columns from the demo source | P1 | PPIQ-T310 | Not Started
TM-067 | Connectors | Infra integration | MsSqlConnector | Delta read returns only rows beyond the incremental cursor | P1 | PPIQ-T310 | Not Started
TM-068 | Connectors | Infra integration | MsSqlConnector | Type mapping (native → canonical) is correct for numeric/text/date/bool | P2 | PPIQ-T310 | Not Started
TM-069 | Connectors | Infra integration | MsSqlConnector | Connection timeout is bounded and surfaces a clear error (no infinite wait) | P2 | PPIQ-T310 | Not Started
TM-070 | Connectors | Infra integration | ConnectorConfigurationService (1246L) | Save/encrypt/retrieve a connection config round-trips; secrets masked in output | P1 | PPIQ-T310 | Not Started
TM-071 | Connectors | Infra integration | DataSourceConnectorFactory | Returns the right connector per source type; unknown type → clear error | P2 | PPIQ-T310 | Not Started
DATA LIFECYCLE
TM-072 | Data Lifecycle | Infra integration | DeltaImportExecutionService | Cold load imports all rows; second run imports only new rows | P1 | PPIQ-T303 | Partial
TM-073 | Data Lifecycle | Infra integration | DeltaImportExecutionService | Simulated mid-batch crash → resume from cursor with ZERO duplicates | P1 | PPIQ-T303 | Partial
TM-074 | Data Lifecycle | Infra integration | DeltaImportExecutionService | Source schema drift (added/removed column) is detected and surfaced | P2 | PPIQ-T303 | Partial
TM-075 | Data Lifecycle | Infra integration | ImportBatchQueueProcessorService | Queued batches are processed in order; failures retried/parked | P2 | PPIQ-T303 | Partial
TM-076 | Data Lifecycle | Infra integration | StagingRecordService | Staged rows persist with correct provenance/source linkage | P2 | PPIQ-T303 | Partial
TM-077 | Data Lifecycle | Infra integration | IncrementalSyncStateService | Cursor advances monotonically; concurrent runs don't double-advance | P2 | PPIQ-T303 | Partial
TM-078 | Data Lifecycle | API integration | TwoStageImportEndpoints | Stage-1 → Stage-2 → full cycle produces the expected canonical rows | P1 | PPIQ-T303 | Partial
TM-079 | Data Lifecycle | FE e2e | Journey: Data lifecycle | From HMI: add DB link → schedule job → import → see data (no hardcoding) | P1 | PPIQ-T305 | Partial
SCHEMA MAPPING
TM-080 | Schema Mapping | API integration | SchemaConfigurationEndpoints /resolve | Returns NoSuchView for a missing view | P1 | PPIQ-T303 | Partial
TM-081 | Schema Mapping | API integration | SchemaConfigurationEndpoints /resolve | Returns NoSuchColumn for a missing column | P1 | PPIQ-T303 | Partial
TM-082 | Schema Mapping | API integration | SchemaConfigurationEndpoints /resolve | Returns InvalidAggregateForType for a bad aggregate | P1 | PPIQ-T303 | Partial
TM-083 | Schema Mapping | API integration | GenericSchemaMappingEndpoints /joins/preview | SafeSqlValidator blocks DDL / cross-tenant injection in generated join SQL | P1 | PPIQ-T303 | Partial
TM-084 | Schema Mapping | API integration | GenericSchemaMappingEndpoints /joins/materialize | Type-mismatched join key pair rejected with a clear message | P2 | PPIQ-T303 | Partial
TM-085 | Schema Mapping | Infra integration | MappingExecutionService (899L) | A configured KPI SQL-view executes and returns rows | P1 | PPIQ-T303 | Partial
TM-086 | Schema Mapping | Infra integration | GenealogyService | Resolve a coil → slab/strand/sequence/tundish/ladle/heat and forward to defects/QA | P1 | PPIQ-T303 | Partial
TM-087 | Schema Mapping | Infra integration | Canonical genealogy view | Built via mapping engine over the 8 SPLIT sources, not a pre-joined table | P2 | PPIQ-T303 | Partial
ML ENGINE
TM-088 | ML Engine | Infra integration | 204_ ppiq_ml_run_learning_job_v1 | On golden dataset, RECOVERS injected correlations with correct effect-size sign/magnitude | P1 | PPIQ-T303 | Partial
TM-089 | ML Engine | Infra integration | 204_ ppiq_ml_run_learning_job_v1 | Produces Benjamini-Hochberg q-values and REJECTS spurious pairs under FDR | P1 | PPIQ-T303 | Partial
TM-090 | ML Engine | Infra integration | 204_ method selection | Numeric/numeric→Pearson; continuous/binary→point-biserial; categorical→Cramer's V | P1 | PPIQ-T303 | Partial
TM-091 | ML Engine | Infra integration | 204_ effective-n | Effective-n counts DISTINCT heat units; under-powered flagged below threshold | P1 | PPIQ-T303 | Partial
TM-092 | ML Engine | Infra integration | 201_ ppiq_ml_refresh_feature_store_v6 | Feature store populates values at each grain (heat/strand/coil/location) | P1 | PPIQ-T303 | Partial
TM-093 | ML Engine | App unit | FeatureEngineeringService | Derived features (cev, true_superheat, casting speed delta, residency, shift) == hand-computed | P1 | PPIQ-T302 | Done
TM-094 | ML Engine | App unit | QualityLabelBuilderService | Defect class/severity/position label derivation correct on known inputs | P2 | PPIQ-T302 | Done
TM-095 | ML Engine | App unit | MlReadinessService | Ready vs under-powered gate thresholds correct both sides of the boundary | P1 | PPIQ-T302 | Done
TM-096 | ML Engine | App unit | CorrelationService (437L) | Result assembly/ranking/filtering correct on a fixture | P2 | PPIQ-T302 | Done
TM-097 | ML Engine | API integration | MlLearningEndpoints | POST /jobs/{code}/run executes a job; GET /results returns persisted rows; GET /status reflects run | P1 | PPIQ-T303 | Partial
TM-098 | ML Engine | Infra integration | Worker ML scheduling (T217) | The four learning jobs are dispatched by the Worker on schedule + backoff (once wired) | P2 | PPIQ-T303 | Partial
RISK SCORER
TM-099 | Risk Scorer | App unit | RiskScoreService | Additive contributions sum EXACTLY to the score on a known vector | P1 | PPIQ-T302 | Done
TM-100 | Risk Scorer | App unit | RiskScoreService | Explanation shape lists each contribution with sign and magnitude | P1 | PPIQ-T302 | Done
TM-101 | Risk Scorer | App unit | RiskScoreService | Calibration/reliability bucketing behaves on synthetic data | P3 | PPIQ-T302 | Done
TM-102 | Risk Scorer | API integration | RiskScoreEndpoints | Score endpoint returns the decomposition; bad material id → clear error | P2 | PPIQ-T303 | Partial
TM-103 | Risk Scorer | Infra integration | ModelRegistry | Every persisted result links to a registry row (provenance/reproducibility) | P3 | PPIQ-T303 | Partial
ML HONESTY CONTRACT
TM-104 | ML Honesty Contract | Honesty | ML/assistant API serializer | A finding without effective-n / q-value / effect-size / evidence-link is REJECTED | P1 | PPIQ-T309 | Not Started
TM-105 | ML Honesty Contract | Honesty | ML/assistant API serializer | Forbidden claim ('prediction','guaranteed root cause','AI-powered prediction','production-ready AI') is REJECTED | P1 | PPIQ-T309 | Not Started
TM-106 | ML Honesty Contract | Honesty | ML/assistant API serializer | Approved vocabulary ('suspected contributor','statistical correlation','rule-based risk scoring') passes | P2 | PPIQ-T309 | Not Started
TM-107 | ML Honesty Contract | Honesty | Learning compute path | No LLM/network call occurs anywhere in the statistical compute path (instrumented assertion) | P1 | PPIQ-T309 | Not Started
TM-108 | ML Honesty Contract | Honesty | ApiNarrativeProvider | Only ABSTRACTED findings (no raw plant rows/PII) are sent to the external provider | P1 | PPIQ-T309 | Not Started
TM-109 | ML Honesty Contract | Honesty | LocalNarrativeProvider | With the local/null provider the app runs fully offline; narration degrades gracefully | P2 | PPIQ-T309 | Not Started
TM-110 | ML Honesty Contract | Honesty | Assistant agent (T232, when built) | Every figure in an answer traces to a tool result/retrieved evidence (grounding) | P1 | PPIQ-T309 | Not Started
TM-111 | ML Honesty Contract | FE unit | DataFetchBoundary + ML surfaces | Forbidden phrase 'could not be loaded' never rendered; 'Refreshing X…' used | P1 | PPIQ-T304 | Done
PAGE BUILDER
TM-112 | Page Builder | API integration | PageDefinition CRUD (T289) | Create/rename/delete a page persists in PG and survives restart | P1 | PPIQ-T303 | Partial
TM-113 | Page Builder | API integration | /pages/{slug} | Renders the stored layout generically; unknown slug → 404 | P1 | PPIQ-T303 | Partial
TM-114 | Page Builder | App unit | WidgetQueryExpressionService | Valid expression accepted; CTE/nested/disallowed-func rejected; SafeSql enforced | P1 | PPIQ-T302 | Done
TM-115 | Page Builder | App unit | DashboardWidgetValidationService | Widget config validation rejects malformed bindings | P2 | PPIQ-T302 | Done
TM-116 | Page Builder | FE unit | PageBuilder reducer | Layout add/move/resize/remove state transitions are correct | P1 | PPIQ-T304 | Done
TM-117 | Page Builder | FE unit | DashboardGridLayoutContext (551L) | Grid layout persistence + collision handling on drag | P2 | PPIQ-T304 | Done
TM-118 | Page Builder | FE e2e | Journey: Page builder | Create page → drop+bind+script a widget → save → reload → it persists | P1 | PPIQ-T305 | Partial
TM-119 | Page Builder | FE e2e | Widget builder wizard | Each step validates; script step blocks an unsafe expression | P2 | PPIQ-T305 | Partial
JOBS & WORKER
TM-120 | Jobs & Worker | Infra integration | Worker.cs ImportQueueProcessor | Runs on interval, updates JobDefinition status, writes JobRunHistory | P1 | PPIQ-T303 | Partial
TM-121 | Jobs & Worker | Infra integration | Worker.cs DataQualityScan | Runs and records a run; respects enable flag + interval | P2 | PPIQ-T303 | Partial
TM-122 | Jobs & Worker | Infra integration | Worker.cs RiskScoring | Runs and persists scores; respects max-materials clamp | P2 | PPIQ-T303 | Partial
TM-123 | Jobs & Worker | Infra integration | Worker.cs DeltaImport | Runs the delta job; staggered start; bounded batch sizes | P2 | PPIQ-T303 | Partial
TM-124 | Jobs & Worker | App unit | JobRunOrchestratorService | Orchestrates a run lifecycle (queued→running→success/failure) correctly | P2 | PPIQ-T302 | Done
TM-125 | Jobs & Worker | App unit | JobDefinitionService | CRUD + schedule parsing; invalid cron/interval rejected | P3 | PPIQ-T302 | Done
TM-126 | Jobs & Worker | API integration | JobAdminEndpoints | Jobs Monitor summary reflects real run history (last run, status, duration) | P1 | PPIQ-T303 | Partial
LICENSING & DEMO
TM-127 | Licensing & Demo | App unit | LicenseService | Tier→feature resolution correct for Lite/Pro/Pro Plus/Enterprise corner cases | P1 | PPIQ-T302 | Done
TM-128 | Licensing & Demo | FE unit | LicenseContext.tsx | Tier change toggles feature visibility; override banner shows | P1 | PPIQ-T304 | Done
TM-129 | Licensing & Demo | FE e2e | Journey: License toggle | Switch Enterprise→Pro and a feature visibly disappears | P1 | PPIQ-T305 | Partial
TM-130 | Licensing & Demo | Infra integration | DemoLifecycleService | Demo seed/reset is deliberate (not auto-run in prod boot path) | P2 | PPIQ-T303 | Partial
TM-131 | Licensing & Demo | API integration | DemoLifecycleEndpoints | Lifecycle status/seed/reset endpoints behave + are license/role gated | P2 | PPIQ-T303 | Partial
STANDARD* UI CONTRACT
TM-132 | Standard* UI Contract | FE unit | StandardButton | All variants & states render correctly: default/hover/focus/active/disabled/loading + all variants | P2 | PPIQ-T304 | Done
TM-133 | Standard* UI Contract | FE unit | StandardTable | All variants & states render correctly: loading-skeleton/error+retry/empty/populated/sorted/paginated/virtualized>500 | P2 | PPIQ-T304 | Done
TM-134 | Standard* UI Contract | FE unit | StandardTabs | All variants & states render correctly: default/active/hover/disabled/overflow-scroll/keyboard-focus/urlParam | P2 | PPIQ-T304 | Done
TM-135 | Standard* UI Contract | FE unit | StandardFields (Input/Select/TextArea) | All variants & states render correctly: default/focus/error/disabled/with-value/code-mode | P2 | PPIQ-T304 | Done
TM-136 | Standard* UI Contract | FE unit | StandardSurface (Card/Modal/Toast) | All variants & states render correctly: default/with-actions/open-focus-trap/dirty-blocked/toast-progress | P2 | PPIQ-T304 | Done
TM-137 | Standard* UI Contract | FE unit | DataFetchBoundary | All variants & states render correctly: loading 'Refreshing X…'/error+retry/auto-retry-5s/success | P2 | PPIQ-T304 | Done
TM-138 | Standard* UI Contract | FE unit | ErrorBoundary | All variants & states render correctly: caught→fallback+client-error beacon/retrying/recovered | P2 | PPIQ-T304 | Done
PAGE LOAD & STATES
TM-139 | Page Load & States | FE e2e | DashboardPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-140 | Page Load & States | FE e2e | RiskDashboardPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-141 | Page Load & States | FE e2e | DataQualityPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-142 | Page Load & States | FE e2e | CorrelationPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-143 | Page Load & States | FE e2e | MlReadinessPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-144 | Page Load & States | FE e2e | MaterialInvestigationPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-145 | Page Load & States | FE e2e | PageBuilderPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-146 | Page Load & States | FE e2e | AdminDbConfigurationTab | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-147 | Page Load & States | FE e2e | AdminSchemaConfigurationTab | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-148 | Page Load & States | FE e2e | AdminJobsMonitorTab | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-149 | Page Load & States | FE e2e | AdminImportingDataTab | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-150 | Page Load & States | FE e2e | DemoLifecyclePage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-151 | Page Load & States | FE e2e | CommercialLicensePage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
TM-152 | Page Load & States | FE e2e | BrandIdentityPage | Loads with no console error; shows loading→data or a real (non-fake) empty/error state | P2 | PPIQ-T305 | Partial
API CLIENTS
TM-153 | API Clients | FE unit | apiClient.ts | Retries capped with backoff [0,500,1500]; retryable-only | P1 | PPIQ-T304 | Done
TM-154 | API Clients | FE unit | apiClient.ts | 401 vs 403 vs 500 vs network(0) map to DISTINCT typed outcomes | P1 | PPIQ-T304 | Done
TM-155 | API Clients | FE unit | apiClient.ts | Request timeout aborts and surfaces a clear error (no hang) | P2 | PPIQ-T304 | Done
TM-156 | API Clients | FE unit | schemaMapping.api / twoStageImport.api / pageBuilder.api | Request/response shapes match backend contracts (typed) | P2 | PPIQ-T304 | Done
TM-157 | API Clients | FE unit | noLegacyApiGrowth guard | Legacy plantProcessApi surface does not grow | P3 | PPIQ-T304 | Done
CONTRACT
TM-158 | Contract | Contract | OpenApiContractTests | ML, page-builder, correlation endpoints appear in the OpenAPI document | P2 | PPIQ-T311 | Not Started
TM-159 | Contract | Contract | ApiEndpointCatalogSmoke | Every mapped endpoint is reachable and returns a non-5xx for a valid call | P2 | PPIQ-T311 | Not Started
TM-160 | Contract | Contract | Problem-details shape | Errors return RFC7807 problem-details with status + title, not a bare 500 | P2 | PPIQ-T311 | Not Started
PERFORMANCE & LOAD
TM-161 | Performance & Load | Perf | /api/dashboards widget query | p95 < 1.5s on demo-scale data (≥5,600 coils, 1 month) | P1 | PPIQ-T308 | Not Started
TM-162 | Performance & Load | Perf | Material investigation query | p95 < 2s; paginated; no full-table scan (EXPLAIN check) | P1 | PPIQ-T308 | Not Started
TM-163 | Performance & Load | Perf | ML learning job (full sweep) | Completes within the configured job budget on demo data | P2 | PPIQ-T308 | Not Started
TM-164 | Performance & Load | Perf | Delta import (5k rows) | Throughput ≥ target rows/s; memory bounded | P2 | PPIQ-T308 | Not Started
TM-165 | Performance & Load | Perf | Long endpoints | Any endpoint >2s exposes progress %; none hangs indefinitely (timeout enforced) | P1 | PPIQ-T308 | Not Started
TM-166 | Performance & Load | Perf | Concurrent load | 50 concurrent dashboard reads sustain without error/timeout | P2 | PPIQ-T308 | Not Started
TM-167 | Performance & Load | Perf | DB indexes | Critical queries use expected indexes (no seq-scan regression) | P2 | PPIQ-T308 | Not Started
RESILIENCE & SECURITY
TM-168 | Resilience & Security | FE e2e | Journey: Resilience | Backend outage → retry UI shown, never a fake 'could not load' | P1 | PPIQ-T305 | Partial
TM-169 | Resilience & Security | Infra integration | AuditLogImmutability | Audit rows cannot be updated/deleted (extend to new audit surfaces) | P1 | PPIQ-T303 | Partial
TM-170 | Resilience & Security | Security | SafeSqlPolicy | CTE / nested subquery / cross-tenant attempts blocked (extend existing suite) | P1 | PPIQ-T302 | Done
TM-171 | Resilience & Security | Security | Postgres exposure | External scan: 5432 not reachable from internet (only 80/443) | P1 | PPIQ-T308 | Not Started
TM-172 | Resilience & Security | Security | JWT tampering | Modified/expired token rejected; alg-none rejected | P1 | PPIQ-T303 | Partial
TM-173 | Resilience & Security | Security | Input validation | Oversized / malformed payloads rejected with 400, not 500 | P2 | PPIQ-T311 | Not Started
DB MIGRATION HYGIENE
TM-174 | DB Migration Hygiene | Infra integration | All ordered scripts | Apply on a fresh PG under ON_ERROR_STOP=1 with ZERO errors | P1 | PPIQ-T306 | Done
TM-175 | DB Migration Hygiene | Infra integration | All ordered scripts | Idempotent re-apply on a staging clone is clean (no NOTICE-abort) | P1 | PPIQ-T306 | Done
TM-176 | DB Migration Hygiene | Infra integration | All scripts | No UTF-8 BOM present (BOM guard) | P2 | PPIQ-T306 | Done
TM-177 | DB Migration Hygiene | Infra integration | MigrateAsync at startup | Auto-migration brings a fresh DB to head without manual steps | P2 | PPIQ-T303 | Partial
VALUE & ROI MODEL (Proving the Money — Intelligence Architecture S5)
TM-178 | Value & ROI Model | App unit | Impact engine (T296) | Given a finding + cost inputs, returns a per-lever EUR opportunity WITH the assumptions, input values and a confidence band; the same inputs are reproducible bit-for-bit (deterministic). No point figure is ever emitted without its band. | P1 | PPIQ-T296 | Not Started
TM-179 | Value & ROI Model | App unit | Impact engine guard (T296) | When required cost inputs (cost-per-defect / margin-per-ton / energy price) or units are missing, the engine returns an explicit 'insufficient inputs' result and fabricates no number; division-by-zero and unit mismatches are rejected, not silently defaulted. | P1 | PPIQ-T296 | Not Started
TM-180 | Value & ROI Model | API integration | Cost-assumption config (T297) | Every cost input is editable per-tenant from the HMI and persists; demo-scale defaults (~630 heats/mo, ~160 t/heat, ~5,600 coils/mo) are seeded and clearly labelled as assumptions, not measured facts. | P2 | PPIQ-T297 | Not Started
TM-181 | Value & ROI Model | FE e2e | ROI presentation (T298) | Every euro figure in the Suggestion feed and the Assistant is preceded by its evidence (contributor + q-value + effect size + effective-n) and is ranked by value x confidence; wording uses 'opportunity / approximately / associated-with' and never a promise or guarantee. | P1 | PPIQ-T298 | Not Started
TM-182 | ML Honesty Contract | Honesty | Descriptive vs inferential separation | L2 dashboards describe only 'what happened' with no causal language; any inferential output (correlation / contributor / risk) always carries q-value, effect size and effective-n and is gated by MlReadiness. The two registers never blur into a single 'cause' claim in UI or narration. | P1 | PPIQ-T218 | Not Started
TOTAL 182 test cases ¦ P1: 108 P2: 70 P3: 4 ¦ built when each maps-to task is Done

## How to Use
How to Use This Workbook (v12)
What changed from v6 | The four overlapping columns (Description, Validation, Evidence, v6 Update/Action) are gone. Each task now has ONE authoritative, deep Description — it states what already exists (from the 30-May audit), exactly what to build or finish, and why — and ONE deep Validation giving the acceptance criteria that define 'done'. Status and Completion% are kept as at-a-glance signals.
How a task reads | The Description opens with one of: 'ALREADY IN PLACE' (verify, don't rebuild), 'STARTING POINT … WHAT REMAINS … FULL REFERENCE SPEC' (partial), or 'BUILD FROM SCRATCH … SPECIFICATION' (not started). A developer reads the Description to know what to do and the Validation to know when to stop. No cross-referencing other columns.
Phase re-sequencing | Phases are ordered by importance, then constrained by prerequisites, then made feature-cohesive so related build + enhancement + bug-fix land together. Every phase ends in a running, healthy, buildable state (see each phase's EXIT STATE on its separator row and the Audit Summary).
Stable IDs | Task IDs (PPIQ-T2xx) are unchanged from v6 for traceability, so they are NOT sequential within a phase. Execution order is ROW ORDER, strictly top-to-bottom within and across phases.
Sheets | Task List (110 tasks, 14 phases, single-source Description/Validation; every data/ML/widget/assistant task is anchored to its architecture layer L1-L6 + owning component + honesty boundary); Architecture Map (NEW in v12 — the six-layer intelligence pipeline, the 17-component responsibility matrix, the widget compile-and-guard engine, the Value Model and the eight design principles, each mapped to its phases/tasks); Audit Summary (status rollup + re-sequencing rationale + version history); Test Register & Test Matrix (182 enumerated cases incl. the ML-honesty contract and the new Value & ROI section); Phase Summary (live); Rollups (live); UI Standards Reference.
Severity scale | critical > very important > important > normal > optional. P01 is the foundation: until it is green, the pipeline stays red and the app cannot be reliably demoed.
ML/AI honesty contract | The analytical core is deterministic, in-house, and statistical. The LLM is the VOICE, never the brain — it phrases already-computed, evidence-backed findings, never computes or invents numbers. Every finding carries effective-n, q-value, effect size, stability, and an evidence link. Forbidden: 'prediction', 'guaranteed root cause', 'AI-powered prediction', 'production-ready AI'. Approved: 'suspected contributor', 'statistical correlation', 'rule-based risk scoring'.
Effort | Hours for one experienced full-stack engineer. Days = hours / 6. Add 25–35% buffer. Totals computed on Phase Summary and Rollups.
Validation discipline | A task is Done only when every Validation criterion passes; CI gates and post-deploy probes enforce this where possible.
Architecture alignment | v12 maps the backlog onto the AI & ML Design (companion to Product Vision v2.0). Read a task's Description: it opens with an 'ARCHITECTURE - Layer Lx' anchor naming the layer, owning component and honesty boundary, then the work. The single rule: computation flows up; only L6 may use a language model, and it phrases what L4/L5 computed - it never invents a figure. See the Architecture Map sheet for the full layer/component/value mapping.

## Phase Summary
Phase Summary — execution order, status, effort (computed live from the Task List)
Recommended order is strictly top-to-bottom. Each phase is designed to end in a running, healthy, buildable state.
Phase ID | Phase Name | Tasks | Critical | Very Important | Important | Normal | Done | Partial | Not Started | Avg Completion % | Effort (hrs) | Effort (days)
P00 | Test Foundation: Audit, Repair, Cover & Gate | 12 | 2 | 8 | 2 | 0 | 5 | 6 | 1 | 68.33% | 96 | 16
P01 | Stabilize: Build-Green, Auth & Deploy Reliability | 14 | 2 | 4 | 7 | 1 | 12 | 2 | 0 | 88.57% | 26 | 4.3333
P02 | Data Lifecycle: Sources, Ingestion, Mapping & Genealogy | 8 | 0 | 6 | 2 | 0 | 2 | 5 | 1 | 54.37% | 41 | 6.8333
P03 | Page Builder & Widget Platform | 7 | 0 | 4 | 3 | 0 | 1 | 5 | 1 | 41.43% | 41 | 6.8333
P04 | ML Engine: Data Foundation & Providers | 7 | 0 | 4 | 3 | 0 | 6 | 1 | 0 | 80.71% | 43 | 7.1667
P05 | ML Engine: Scheduled Correlation Learning | 6 | 2 | 2 | 2 | 0 | 1 | 4 | 1 | 55.83% | 38 | 6.3333
P06 | ML Engine: Inspection Jobs to Generated Pages | 6 | 0 | 4 | 2 | 0 | 0 | 2 | 4 | 15% | 31 | 5.1667
P07 | Risk Scorer & Model Governance | 4 | 0 | 0 | 3 | 1 | 1 | 2 | 1 | 45% | 18 | 3
P08 | ML Assistant: Suggestion Feed & Value Model (proactive) | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 7 | 1.429% | 38 | 6.3333
P09 | ML Assistant: Conversational RAG Agent | 7 | 0 | 5 | 2 | 0 | 0 | 3 | 4 | 16.43% | 43 | 7.1667
P10 | Hardening, Resilience & HMI Completion | 10 | 0 | 3 | 6 | 1 | 0 | 8 | 2 | 38.5% | 42 | 7
P11 | Demo: Storytelling, Personas & Recording | 6 | 0 | 3 | 3 | 0 | 0 | 1 | 5 | 6.667% | 21 | 3.5
P12 | Website: 5-Product Showcase & Brand | 9 | 0 | 1 | 7 | 1 | 0 | 3 | 6 | 15% | 28 | 4.6667
P13 | Legal, Runbooks & Documentation | 7 | 0 | 0 | 7 | 0 | 0 | 3 | 4 | 12.86% | 22.5 | 3.75
TOTAL | All phases | 110 | 6 | 47 | 53 | 4 | 28 | 45 | 37 | 43% | 528.5 | 88.0833
Effort-days assume 6 productive engineering hours/day. Add 25–35% buffer for review, integration, and validation.

## UI Standards Reference
UI Standards — Canonical Component Contract (enforced)
Every interactive element across all existing AND new pages (incl. ML Correlation, Suggestions, Assistant, Schema Mapping, Two-Stage Import) must conform. Enforced via ESLint, CI lint, review, Storybook.
Component | Canonical Path | Variants / Modes | Required Props | Required States
StandardButton | src/components/standard/StandardButton.tsx | primary ¦ secondary ¦ ghost ¦ danger ¦ success ¦ icon-only | variant, size, leadingIcon, trailingIcon, isLoading, isDisabled, fullWidth, onClick, type, ariaLabel | default, hover, focus (cyan ring), active, disabled (40%), loading (spinner + aria-busy)
StandardTable | src/components/standard/StandardTable.tsx | client ¦ server ¦ virtualized (>500 rows) | columns, data, isLoading, hasError, onRetry, totalCount, onRowClick, density, selectable, exportable | loading (skeleton), error ('Refreshing X…' + retry), empty, populated, sorted, filtered, paginated
StandardTabs | src/components/standard/StandardTabs.tsx | horizontal ¦ vertical ¦ scroll-on-overflow | items, value, onChange, orientation, lazy, urlParam | default, active (indicator), hover, disabled, overflow-scrollable, keyboard-focused
StandardInput / Select / TextArea | src/components/standard/StandardFields.tsx | text/email/password/number/search; single/multi/searchable; default/code | label, helperText, error, value, onChange, required, disabled, isLoading, size, (options, multiple, searchable) | default, focus, error (helper-text), disabled, with-value, code-mode (mono)
StandardCard / Modal / Toast | src/components/standard/StandardSurface.tsx | flat/raised/floating; sm-xl; info/success/warning/error/loading | title, actions, elevation, open, onClose, size, dismiss flags, variant, duration | default, hover, with-actions, open (focus-trapped), dirty-blocked, toast slide-in + progress
DataFetchBoundary | src/components/standard/DataFetchBoundary.tsx | default ¦ skeleton-mirror | isLoading, hasError, onRetry, loadingFallback, errorFallback, children | loading ('Refreshing X…'), error (+retry, auto-retry-5s), success
ErrorBoundary | src/components/standard/ErrorBoundary.tsx | app ¦ route ¦ component | fallback, onError, resetKeys, children | caught (fallback + /diagnostics/client-error beacon), retrying, recovered
FORBIDDEN PATTERNS (CI-enforced)
Forbidden phrase | 'could not be loaded' / 'could not load' | Use the 'Refreshing X…' pattern. Founder's #1 non-negotiable (Vision §2).
Forbidden ML claims | 'guaranteed root cause' / 'AI-powered prediction' / 'production-ready AI' / 'predicts' | Use 'suspected contributor' / 'statistical correlation' / 'rule-based risk scoring'. Enforced on ML + assistant surfaces.
Native element | <button>/<input>/<select>/<table>/<textarea> in src/pages¦features | Use Standard* primitives (ESLint no-restricted-syntax).
Deprecated path | import from src/components/hardening/* or src/hardening/* | Use src/components/standard/*.
LLM invents numbers | assistant emits a figure not present in retrieved evidence/tool results | The LLM phrases evidence it is handed; it never computes or invents. Grounding tests enforce.

## Rollups
Rollups — by Severity, Track, Module, Type (computed live)
By Severity |  |  | By Track |  |  | By Module |  |  | By Type
Severity | Count | Effort (hrs) | Track | Count | Effort (hrs) | Module | Count | Effort (hrs) | Type | Count | Effort (hrs)
critical | 6 | 40 | Track 1 — Workflow | 39 | 228 | App Frontend | 24 | 126 | New Feature | 67 | 364.5
very important | 47 | 286.5 | Track 2 — Hardening | 49 | 222.5 | App Backend | 42 | 243.5 | Enhancement | 27 | 131.5
important | 53 | 190 | Track 3 — Demo | 9 | 39 | Database | 10 | 42 | Bug Fix | 16 | 32.5
normal | 4 | 12 | Track 4 — Website | 13 | 39 | Infrastructure | 13 | 50.5 | TOTAL | 110 | 528.5
optional | 0 | 0 | TOTAL | 110 | 528.5 | Web | 9 | 28
TOTAL | 110 | 528.5 |  |  |  | Documentation | 12 | 38.5
[6 empty] | TOTAL | 110 | 528.5