## Read Me
PlantProcess IQ — Task List v13 · 31 May 2026
Net-new backlog. Canonical base: Product Vision & Engineering Doctrine v2.0 (via the Version Improvement Analysis). Every task is 0% done.
What this workbook is | A from-scratch backlog of the work that REMAINS to reach the canonical target. It deliberately contains no Done or Partial items - every task is scoped to its unbuilt slice, so the whole list is 0% complete and can be executed top-to-bottom without parsing statuses.
The base (target state) | Product Vision & Engineering Doctrine v2.0 is the single source of truth, with Architecture v3 as its design companion (per the Version Improvement Analysis recommendation). Each task carries a 'Spec Anchor' back to the exact doctrine section it satisfies.
The current state | Derived from the 31-May implementation snapshot (1,004 files) as captured in the Implementation Validation report and confirmed by direct code search. Capabilities already built are excluded (see the 'Excluded - Already Built' sheet for the audit trail).
How a task qualifies | A task appears here only if its concrete deliverable does NOT yet exist in the code. For capabilities that are partially built, only the missing slice is listed, re-scoped as a clean, self-contained, 0%-done task with a fresh ID.
Relationship to the old list | v13 is not a re-status of the prior list. It is a clean re-derivation of remaining work; prior Done/Partial/Not-Started labels are not carried over. Where a v13 task corresponds to the unfinished part of an older item, the Description + Spec Anchor make the new scope explicit.
ID scheme | PPIQ-N### (N = net-new). 75 tasks across 11 execution phases (N-P1 ... N-P11), sequenced by dependency and commercial priority. Status is uniformly 'Not Started' and Completion % is uniformly 0 by design.
Column legend | Spec Anchor = the Vision/Architecture/Validation reference the task satisfies. Dependencies = task IDs that should land first. Acceptance Criteria = the testable 'done' bar. Effort = engineering hours (indicative).
Sheets | 'v13 Backlog' = the tasks. 'Phase Plan' = execution order with live counts + effort. 'Coverage Map' = every Vision v2.0 area -> the tasks that complete it. 'Excluded - Already Built' = what was left out and why.

## v13 Backlog
v13 Backlog — net-new remaining work (every task 0% done)
Task ID | Task Name | Phase | Track | Module | Submodule | Severity | Description | Acceptance Criteria | Spec Anchor | Dependencies | Task Type | Effort (hrs) | Status | Completion %
N-P1 · Security, Access & Trust Closeout
PPIQ-N001 | Move the access token off localStorage to an httpOnly cookie | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | App Frontend | Auth / Token Storage | very important | Current: the access token is persisted in localStorage, where any XSS can read it (Validation F4). Build: relocate the token to an httpOnly + SameSite cookie (or in-memory store with silent refresh) and remove every localStorage token read/write. | 1) No localStorage token access remains in the bundle. 2) Auth survives a page reload via cookie/refresh. 3) Injected script cannot read the token. 4) Existing auth e2e stays green. | Validation F4 ¦ Vision 10.1 | - | Security | 8 | Not Started | 0
PPIQ-N002 | Define & enforce the RBAC permission matrix | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | App Backend | Access Control / RBAC | critical | Current: role/tenant primitives exist but no explicit permission matrix is enforced per endpoint/feature. Build: a permission catalog (resource x action), a central policy mapping roles to permissions, and authorization attributes on every endpoint group; deny by default. | 1) A matrix test asserts each role's allowed/denied set on every endpoint group. 2) Default is deny. 3) The matrix is data-driven and documented (feeds N005). | Vision (User/Role residual) ¦ v3 3.8 | - | Feature | 16 | Not Started | 0
PPIQ-N003 | Resolve license x role at the corner cases (single entitlement authority) | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | App Backend | Entitlement Resolution | very important | Current: LicenseTier primitives are present but the interaction with roles is not centrally resolved or tested. Build: one Entitlement resolver = f(tier, role) -> capability set, read by both API and UI, with corner-case coverage (Enterprise-admin vs Pro-operator, etc.). | 1) A single resolver authority exists. 2) UI hides/disables exactly what the API forbids. 3) Corner-case unit tests pass. | Vision 4 ¦ v3 3.8 | PPIQ-N002 | Feature | 12 | Not Started | 0
PPIQ-N004 | Tenant-isolation integration tests across data, ML & assistant paths | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | App Backend | Multi-tenancy | critical | Current: TenantId scaffolding exists but isolation is not proven by test. Build: integration tests proving a tenant can never read another tenant's dumps, mappings, findings, suggestions or knowledge-base chunks. | 1) Cross-tenant access returns 403/empty at repo, query, ML-result and KB-retrieval layers. 2) Tests run in CI and gate regressions. | v3 3.8 ¦ Vision 10 | - | Test | 10 | Not Started | 0
PPIQ-N005 | Author the 'User, Role & Access + Audit' doctrine section (the lone residual gap) | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | Documentation | Canonical Spec | very important | Current: Vision v2.0 has no dedicated access-control section - the one heading the original draft left blank. Build: add the section (role catalog, RBAC matrix, license x role interaction, tenant-isolation model, immutable audit-log contract) to the canonical document. | 1) Section added to Vision v2.0 and cross-referenced from v3. 2) It matches the implemented matrix (N002/N003). 3) Reviewed against the Improvement Analysis edit #1. | Improvement Analysis 7 (edit 1) | PPIQ-N002,PPIQ-N003,PPIQ-N004 | Documentation | 6 | Not Started | 0
PPIQ-N006 | Immutable audit-log coverage for every privileged action | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | App Backend | Audit Log | very important | Current: audit-log immutability exists (script 096) but action coverage is incomplete. Build: append-only, tamper-evident entries for auth, config writes, mapping/materialize, job control, license/role changes and data exports, each with actor/tenant/before-after. | 1) Each privileged action writes exactly one immutable entry. 2) An integration test enumerates the covered actions. 3) Entries are provably read-only. | Vision 8/10 ¦ v3 3.8 | PPIQ-N002 | Feature | 8 | Not Started | 0
PPIQ-N007 | Fix the SQL syntax error seen during ordered-script application | N-P1 · Security, Access & Trust Closeout | Track 2 — Hardening | Database | Migration / Scripts | very important | Current: a syntax error surfaces while applying the ordered script set; root cause unconfirmed. Build: reproduce on a fresh DB, isolate the offending statement, fix it, and add the apply to the fail-on-error gate. | 1) The full ordered set applies cleanly under ON_ERROR_STOP=1 on a fresh DB and a staging clone, BOM-free. 2) A CI step proves it. | Validation ¦ Vision 10.3 | - | Bug | 5 | Not Started | 0
N-P2 · The Value Model
PPIQ-N008 | Value/Impact computation engine (finding -> quantified impact) | N-P2 · The Value Model | Track 1 — Workflow | App Backend | Value Model | critical | Current: no code converts a finding into a monetary/operational figure - the architecture's biggest commercial lever (Validation F1). Build: a deterministic engine that, given a validated finding + tenant cost assumptions, computes a bounded impact (EUR/month from defect-rate delta, yield, downtime) with provenance and an explicit abstain path. | 1) Returns a decomposed impact with every input cited. 2) Returns 'insufficient basis' instead of a guess when assumptions are missing. 3) Unit-tested on known vectors. | Validation F1 ¦ v3 5 | - | Feature | 16 | Not Started | 0
PPIQ-N009 | Per-tenant cost-assumption configuration (inputs + demo defaults) | N-P2 · The Value Model | Track 1 — Workflow | App Frontend | Value Model | very important | Current: absent (0 code hits). Build: an admin surface + persisted, versioned model for cost inputs (cost/ton, scrap cost, downtime EUR/min, energy EUR/MWh, grade premiums), with realistic demo defaults, consumed by N008. | 1) Assumptions are tenant-scoped, HMI-editable and versioned. 2) They feed the impact engine. 3) The demo tenant ships with realistic defaults. | v3 5 | PPIQ-N008 | Feature | 10 | Not Started | 0
PPIQ-N010 | ROI presentation contract (evidence-first, never overstated) | N-P2 · The Value Model | Track 1 — Workflow | App Frontend | Value Model | very important | Current: absent. Build: a presentation contract that renders impact as a ranged, evidence-linked figure with its assumption set and honesty caveats, in the suggestion feed and the assistant; forbidden from asserting a guaranteed saving. | 1) Every impact figure shows inputs + range + drill-through. 2) Honesty-lint rejects 'guaranteed'/'will save'. 3) Snapshot tests cover the rendered contract. | v3 5 ¦ Vision 3 (honesty) | PPIQ-N008,PPIQ-N009 | Feature | 8 | Not Started | 0
N-P3 · Intelligence Core Completion
PPIQ-N011 | Add Spearman, mutual information & Lasso to the correlation compute engine | N-P3 · Intelligence Core Completion | Track 1 — Workflow | App Backend | Correlation Methods | very important | Current: Pearson, point-biserial and Cramer's V are implemented; Spearman, mutual information and Lasso are not (Validation F2). Build: implement Spearman (monotonic/ordinal), mutual information (non-linear) and Lasso multivariate screening behind the existing compute-engine interface, auto-selected by variable-pair type. | 1) Each method computes correctly on golden vectors. 2) Method is auto-selected per variable-pair type. 3) Results persist with a method tag. | Vision 3.2.1 ¦ Validation F2 | - | Feature | 16 | Not Started | 0
PPIQ-N012 | Add the missing validity machinery: VIF, bootstrap stability, confounding/stratification | N-P3 · Intelligence Core Completion | Track 1 — Workflow | App Backend | Statistical Validity | very important | Current: BH q-values, effect-size-first ranking, power and effective-n-by-heat exist; VIF, bootstrap stability and confounding/stratification checks do not. Build: variance-inflation screening, bootstrap stability flags and confounder stratification over the association results. | 1) Each association carries a stability flag + VIF. 2) Stratified checks surface confounds. 3) Golden-dataset tests confirm spurious associations are demoted. | Vision 3.2.2 ¦ Validation F2 | PPIQ-N011 | Feature | 14 | Not Started | 0
PPIQ-N013 | Per-job scheduling, backoff & MlReadiness governance gates | N-P3 · Intelligence Core Completion | Track 1 — Workflow | App Backend | ML Scheduling | very important | Current: per-source scheduling exists; ML-job readiness gating and backoff do not. Build: a readiness gate evaluated before each learning run (enough independent heats, freshness) with reschedule-on-not-ready and exponential backoff on failure. | 1) A job refuses to run on insufficient/not-ready data and reschedules. 2) Backoff is observed on repeated failure. 3) Gate decisions are logged and visible in the Jobs Monitor. | Vision 3.2.2 | - | Feature | 10 | Not Started | 0
PPIQ-N014 | Persist the extended correlation result + wire it into the Jobs Monitor | N-P3 · Intelligence Core Completion | Track 1 — Workflow | App Backend | Results / Monitoring | important | Current: a base correlation result exists; extended fields and monitor integration are incomplete. Build: persist effect size, q-value, effective-n, stability, VIF and method per association, and surface each learning run's outcome/duration in the Jobs Monitor. | 1) Extended columns are populated. 2) The Jobs Monitor shows last run/outcome/duration for every learning job. 3) The query is tested. | Vision 2.2.6/3.2 | PPIQ-N012,PPIQ-N013 | Feature | 8 | Not Started | 0
PPIQ-N015 | Golden-dataset test suite for the learning engine | N-P3 · Intelligence Core Completion | Track 1 — Workflow | Backend Tests | ML Tests | very important | Current: engine tests are partial. Build: fixture datasets with known injected associations (and known nulls) that assert recovery of true signals and rejection of spurious ones under FDR. | 1) True associations are recovered with the correct method/effect. 2) Injected spurious signals are rejected. 3) The suite runs in CI and gates regressions. | Vision 8 (results & math) | PPIQ-N011,PPIQ-N012 | Test | 10 | Not Started | 0
N-P4 · Risk Scorer Hardening
PPIQ-N016 | Risk-score calibration & reliability check | N-P4 · Risk Scorer Hardening | Track 1 — Workflow | App Backend | Risk Scorer | important | Current: the additive, decomposable scorer exists; calibration/reliability is absent (0 hits). Build: reliability-curve / Brier calibration on held-out data, surfaced alongside the score. | 1) Calibration is computed and stored. 2) A miscalibrated model is flagged. 3) Tested on a synthetic labelled set. | Vision 3.4 | - | Feature | 10 | Not Started | 0
PPIQ-N017 | Complete the model registry: provenance & reproducibility | N-P4 · Risk Scorer Hardening | Track 1 — Workflow | App Backend | Model Registry | important | Current: registry scaffolding exists; provenance/repro linkage is incomplete. Build: link every persisted score to its inputs, feature snapshot and model version so a run is reproducible from the registry. | 1) The score->inputs->version chain is queryable. 2) Re-running a registered version reproduces the score. 3) Integration-tested. | Vision 3.4 | PPIQ-N016 | Feature | 10 | Not Started | 0
PPIQ-N018 | Drift monitoring & champion/challenger promotion | N-P4 · Risk Scorer Hardening | Track 1 — Workflow | App Backend | Model Lifecycle | important | Current: absent (0 hits). Build: population-stability drift monitoring on features/outcomes and a champion/challenger promotion workflow gated on calibration + drift. | 1) Drift is surfaced with a metric + threshold. 2) A challenger promotes only when it beats champion on calibration/stability. 3) Promotion is audited. | Vision 3.4 | PPIQ-N016,PPIQ-N017 | Feature | 12 | Not Started | 0
N-P5 · Inspection -> Generated Pages
PPIQ-N019 | Inspection Job runner - on-demand analysis with progress | N-P5 · Inspection -> Generated Pages | Track 1 — Workflow | App Backend | Inspection Jobs | very important | Current: the inspection-job domain/endpoints are partial; the on-demand runner with progress is absent. Build: a runner that executes a selected defect/downtime/KPI investigation over a window, emitting a progress percentage. | 1) A run streams progress and cancels cleanly. 2) It never hangs (global timeout). 3) It produces a structured result object. | Vision 3.3 | - | Feature | 12 | Not Started | 0
PPIQ-N020 | Auto-generate the analysis page from an inspection result (no hardcoding) | N-P5 · Inspection -> Generated Pages | Track 1 — Workflow | App Frontend | Generated Pages | very important | Current: absent. Build: from a run result, generate a page of widgets/charts showing the most influential parameters, persisted as a normal Page Definition. | 1) The page is data-driven (no hardcoded layout). 2) It opens in the Correlation area as its own tab. 3) It is editable/savable like any page. | Vision 3.3 | PPIQ-N019 | Feature | 12 | Not Started | 0
PPIQ-N021 | Schedule inspection jobs periodically + Jobs Monitor integration | N-P5 · Inspection -> Generated Pages | Track 1 — Workflow | App Backend | Inspection Jobs | important | Current: absent. Build: let a saved inspection job run on a cadence or on demand, with status/duration reported in the Jobs Monitor. | 1) Scheduled re-runs appear in the monitor. 2) 'Run now' works on demand. 3) Failures are visible and recoverable. | Vision 3.3 | PPIQ-N019 | Feature | 8 | Not Started | 0
PPIQ-N022 | E2E for the run -> generate -> save -> schedule loop | N-P5 · Inspection -> Generated Pages | Track 1 — Workflow | Frontend Tests | Inspection Tests | important | Current: absent. Build: an e2e that drives the full inspection lifecycle through the HMI. | 1) The loop passes headless. 2) The generated page renders all widgets. 3) No 'could not be loaded' appears anywhere in the flow. | Vision 8 | PPIQ-N020,PPIQ-N021 | Test | 6 | Not Started | 0
N-P6 · The AI Assistant
PPIQ-N023 | Suggestion engine - rule-based, evidence-linked, impact-ranked | N-P6 · The AI Assistant | Track 1 — Workflow | App Backend | Suggestions | very important | Current: prerequisites exist but the engine is absent. Build: a deterministic engine that turns validated findings (+ N008 impact) into ranked, evidence-linked recommendations, gated by tier. | 1) Each suggestion links to its evidence + impact. 2) Ranking is by effect/impact, not p-value. 3) Nothing is emitted without a backing finding. | Vision 3.5.1 | PPIQ-N008,PPIQ-N012 | Feature | 12 | Not Started | 0
PPIQ-N024 | /api/suggestions endpoint + context filtering + license gating | N-P6 · The AI Assistant | Track 1 — Workflow | App Backend | Suggestions | important | Current: absent. Build: a read endpoint with area/defect/time filters, tenant-scoped and tier-gated. | 1) Filters work. 2) Tenants are isolated. 3) Tier gating is enforced and contract-tested. | Vision 3.5.1 | PPIQ-N023,PPIQ-N003 | Feature | 6 | Not Started | 0
PPIQ-N025 | Suggestions & Recommendations page - the proactive feed | N-P6 · The AI Assistant | Track 1 — Workflow | App Frontend | Suggestions | important | Current: absent. Build: a feed UI with drill-through to evidence and the ROI presentation contract. | 1) The feed renders ranked items with citations. 2) Drill-through opens the evidence. 3) Loading/empty/error states are real and recoverable. | Vision 3.5.1 | PPIQ-N024,PPIQ-N010 | Feature | 8 | Not Started | 0
PPIQ-N026 | Complete the knowledge-base ingestion pipeline (findings, cases, docs) | N-P6 · The AI Assistant | Track 1 — Workflow | App Backend | Assistant / KB | important | Current: pgvector + embedding provider exist; the ingestion pipeline is incomplete. Build: ingest findings, saved cases and domain docs into the vector + structured store with provenance, tenant-scoped. | 1) Ingestion is idempotent and tenant-scoped. 2) Chunks carry source provenance. 3) Re-ingest updates cleanly. | Vision 3.5.2 | - | Feature | 10 | Not Started | 0
PPIQ-N027 | Complete the hybrid retrieval pipeline (semantic + structured filters) | N-P6 · The AI Assistant | Track 1 — Workflow | App Backend | Assistant / Retrieval | important | Current: partial. Build: combine semantic search with structured filters (area/defect/time) to select evidence for the agent. | 1) Retrieval respects tenant + filters. 2) Relevance is validated on a fixture set. 3) Latency is bounded. | Vision 3.5.2 | PPIQ-N026 | Feature | 8 | Not Started | 0
PPIQ-N028 | Agent + typed-tool layer (findings, inspection, KPI, genealogy, compare) | N-P6 · The AI Assistant | Track 1 — Workflow | App Backend | Assistant / Agent | very important | Current: absent. Build: an agent that calls typed tools and phrases their structured results; it never computes or invents numbers. | 1) Every figure in an answer traces to a tool result. 2) Tool calls are typed and audited. 3) No free-form math is performed by the model. | Vision 3.5.2 | PPIQ-N027 | Feature | 14 | Not Started | 0
PPIQ-N029 | Conversational assistant UI with citations + drill-through | N-P6 · The AI Assistant | Track 1 — Workflow | App Frontend | Assistant / UI | important | Current: absent. Build: a chat UI rendering answers with inline citations and drill-through to evidence. | 1) Citations resolve to sources. 2) Drill-through works. 3) Loading/error states are real; no fabricated figure passes the grounding guard. | Vision 3.5.2 | PPIQ-N028 | Feature | 10 | Not Started | 0
PPIQ-N030 | Operator feedback loop (useful / acted / dismissed + outcomes) | N-P6 · The AI Assistant | Track 1 — Workflow | App Backend | Assistant / Feedback | normal | Current: absent. Build: capture operator feedback on suggestions/answers and feed it back into the knowledge base as 'experience'. | 1) Feedback is persisted with its outcome. 2) The KB experience updates. 3) It is tenant-scoped and tested. | Vision 3.5.2 | PPIQ-N026,PPIQ-N029 | Feature | 6 | Not Started | 0
PPIQ-N031 | Assistant grounding & honesty-guardrail tests | N-P6 · The AI Assistant | Track 1 — Workflow | Backend Tests | Assistant Tests | very important | Current: absent. Build: tests that the agent never emits a number absent from a tool result/evidence and never uses forbidden vocabulary. | 1) Grounding tests fail on any invented figure. 2) Forbidden-phrase assertions pass. 3) The group runs in CI. | Vision 3 (honesty)/8 | PPIQ-N028 | Test | 8 | Not Started | 0
N-P7 · Workflow & HMI Completion
PPIQ-N032 | Schema-drift detection & surfacing on ingestion | N-P7 · Workflow & HMI Completion | Track 1 — Workflow | App Backend | Ingestion | very important | Current: delta import exists; source schema-drift detection is absent. Build: detect when a source table's shape changes and surface it (rather than silently corrupting the dump) via a typed drift event. | 1) A changed source column/type raises a visible drift warning. 2) The import pauses/quarantines rather than corrupting. 3) Tested with a mutated fixture. | Vision 2.2.3/2.2.4 | - | Feature | 8 | Not Started | 0
PPIQ-N033 | Typed resolver errors for the mapping layer | N-P7 · Workflow & HMI Completion | Track 1 — Workflow | App Backend | Schema Mapping | important | Current: SafeSqlValidator + a base resolver exist; the full typed-error set is incomplete. Build: distinct named resolution errors (NoSuchView, NoSuchColumn, InvalidAggregateForType) surfaced to the HMI at preview and materialize. | 1) Each misconfiguration returns its specific typed error, not a generic failure. 2) The UI shows the precise cause. 3) Unit-tested. | Vision 2.2.4 | - | Feature | 6 | Not Started | 0
PPIQ-N034 | Canonical genealogy spine as a mapping-authored view (not hardcoded SQL) | N-P7 · Workflow & HMI Completion | Track 1 — Workflow | App Backend | Genealogy | very important | Current: a join spine exists partially. Build: derive the heat->ladle->tundish->mould->strand->slab->coil->defect->QA spine through the mapping engine so any coil walks back to melt and forward to defects. | 1) The spine is generated from mappings (no hardcoded SQL). 2) A sample coil resolves both directions. 3) It is consumed by the feature store + assistant and tested. | Vision 2.2.5 | PPIQ-N033 | Feature | 10 | Not Started | 0
PPIQ-N035 | Build the Risk-Intelligence HeatMap widget (line x shift x day) | N-P7 · Workflow & HMI Completion | Track 1 — Workflow | App Frontend | Widgets | very important | Current: the widget is not built (references only). Build: an interactive heat map (filter/sort) as a first-class, tested widget - a signature visual and a frequent failure point. | 1) It renders correctly across viewports. 2) Filter/sort work. 3) A dedicated heat-map test passes; it never shows a fake-failure state. | Vision 5.4 | - | Feature | 10 | Not Started | 0
PPIQ-N036 | Widget script-grammar reference for power users | N-P7 · Workflow & HMI Completion | Track 1 — Workflow | Documentation | Widget Script Layer | normal | Current: the script layer exists; a documented grammar is incomplete. Build: a reference for the per-widget expression grammar (e.g., group-by shift) with examples and validation rules. | 1) The grammar is documented with examples. 2) Each example validates under the safe-SQL checker. 3) It is linked from the widget editor. | Vision 2.3.2 | - | Documentation | 4 | Not Started | 0
PPIQ-N037 | Operator-friendly first-run wizard (empty-state -> first link -> first page) | N-P7 · Workflow & HMI Completion | Track 1 — Workflow | App Frontend | Onboarding | important | Current: absent. Build: a guided empty-state flow taking a new tenant from zero to a first DB link, first mapping and first page. | 1) A fresh tenant reaches a working page via the wizard with no manual config. 2) Each step is skippable/resumable. 3) Tested. | Vision 1 | - | Feature | 8 | Not Started | 0
N-P8 · Presentation-Grade Hardening (Quality Bar)
PPIQ-N038 | Endpoint + SQL resilience audit (PK/FK/null/timeout) across every group | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | App Backend | Resilience | very important | Current: partial. Build: review every endpoint's SQL/joins for PK/FK/null/timeout failure and close each path; add a global timeout so nothing hangs. | 1) No endpoint can hang. 2) PK/FK/null paths return typed bounded errors. 3) An enumerated audit checklist passes. | Vision 2.2/5.2 | - | Hardening | 12 | Not Started | 0
PPIQ-N039 | Progress-percentage UI for long-running endpoints | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | App Frontend | Resilience | important | Current: partial. Build: surface a real progress percentage for anything that can exceed ~2s, backed by a global timeout. | 1) Long operations show progress, not a spinner-forever. 2) A global timeout prevents indefinite hangs. 3) Tested on a slow fixture. | Vision 5.2 | - | Hardening | 6 | Not Started | 0
PPIQ-N040 | Action-matrix e2e - every control on every page does its exact job | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Frontend Tests | Action Matrix | very important | Current: partial. Build: enumerate every button/tab/hook on every page and sub-page and assert its action by test, including ML and page-builder surfaces. | 1) The action matrix is enumerated and fully green. 2) Coverage is proven by enumeration, not a percentage. 3) Runs in CI. | Vision 5.3 | - | Test | 12 | Not Started | 0
PPIQ-N041 | Complete the Standard* component contract tests | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Frontend Tests | Standard Components | important | Current: partial. Build: assert every page uses the standard component set and brand styling (no per-page drift) via lint + contract tests. | 1) A non-standard control fails the contract test. 2) Styling drift is caught. 3) Runs in CI. | Vision 5.1 | - | Test | 8 | Not Started | 0
PPIQ-N042 | Responsive + cross-browser + http/https correctness e2e | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Frontend Tests | Cross-browser | important | Current: partial. Build: e2e across viewports and supported browsers, over http and https, asserting correct reflow. | 1) Pages render correctly on each target viewport/browser and both schemes. 2) The matrix is enumerated and green. | Vision 5.1 | PPIQ-N041 | Test | 10 | Not Started | 0
PPIQ-N043 | Live license-tier toggle + app-wide banner + header badge | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | App Frontend | Licensing UX | very important | Current: tier primitives exist; the live demo toggle/banner/badge are incomplete. Build: a real (non-mocked) toggle that visibly adds/removes capability, an app-wide active-tier banner and a header tier badge in brand colours. | 1) Switching Enterprise->Pro removes specific features live. 2) Banner + badge reflect the active tier. 3) Resolution is centralized (N003) and corner-tested. | Vision 4 | PPIQ-N003 | Feature | 8 | Not Started | 0
PPIQ-N044 | Performance & load test layer with explicit thresholds | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Backend Tests | Performance | important | Current: absent. Build: perf tests with thresholds (e.g., p95 < 2s; >2s must show progress) on the heavy endpoints, including the heat map and investigation paths. | 1) Thresholds are defined and asserted. 2) A regression past threshold fails CI. 3) The heat map and investigation endpoints are covered. | Vision 8 (endpoints) | PPIQ-N038 | Test | 8 | Not Started | 0
PPIQ-N045 | Connector behavioural integration tests across all six sources (+ CSV/Excel golden files) | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Backend Tests | Connectors | important | Current: partial. Build: integration tests that each connector reads, tests-before-save and masks credentials, against live PG/MySQL/MSSQL/Oracle plus CSV/Excel golden files. | 1) All six connectors pass behaviourally. 2) Credentials never appear in read-back. 3) Golden files match. | Vision 2.2.1/8 | - | Test | 10 | Not Started | 0
PPIQ-N046 | Endpoint authorization matrix & RFC-7807 contract tests for every group | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Backend Tests | Authz / Contracts | very important | Current: partial. Build: a 3-identity (and tier) authorization matrix plus RFC-7807 contract tests on every endpoint group. | 1) Each group asserts 200/401/403 by identity + tier. 2) Error bodies are RFC-7807. 3) The matrix is complete. | Vision 8 | PPIQ-N002,PPIQ-N003 | Test | 10 | Not Started | 0
PPIQ-N047 | Delta-import resumability tests (crash mid-batch -> resume, zero duplicates) | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Backend Tests | Ingestion Tests | important | Current: partial. Build: integration tests that a crash mid-batch resumes from the last committed cursor with no duplicates, and that drift is surfaced. | 1) A simulated crash resumes cleanly. 2) Zero duplicate rows result. 3) A drift fixture raises a warning. | Vision 2.2.3/8 | PPIQ-N032 | Test | 8 | Not Started | 0
PPIQ-N048 | First-class ML/AI honesty-contract test group | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Backend Tests | Honesty Contract | very important | Current: partial. Build: a dedicated test group asserting forbidden vocabulary is rejected at the API boundary and in narratives, and that findings recover under FDR. | 1) Forbidden phrases fail the group. 2) FDR recovery is asserted. 3) The group is named and gated in CI. | Vision 3/8 | PPIQ-N031 | Test | 8 | Not Started | 0
PPIQ-N049 | Remove the four orphaned components (single canonical implementation) | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | App Frontend | Dead Code | important | Current: AdminDbConfigurationTab, AdminSchemaConfigurationTab, AdminImportingDataTab and WidgetBuilderWizardContent are defined but never imported, diverging from the live Phase78 implementations (Validation F3). Build: delete the dead copies (or wire them in and delete the duplicates) so one canonical implementation remains. | 1) No orphaned/duplicate component remains. 2) Each admin surface has a single dependency path. 3) Build + tests stay green. | Validation F3 | - | Refactor | 5 | Not Started | 0
PPIQ-N050 | Archive synthetic seeds out of the production boot path | N-P8 · Presentation-Grade Hardening (Quality Bar) | Track 2 — Hardening | Infrastructure | Boot Safety | important | Current: partial. Build: ensure no synthetic/demo seed runs on a production boot; seeds live behind an explicit demo profile. | 1) A production boot seeds nothing synthetic. 2) The demo profile still seeds fully. 3) A startup assertion proves it. | Vision 10 | - | Hardening | 4 | Not Started | 0
N-P9 · Demo Build & Doctrine
PPIQ-N051 | Split the coherent dataset across the eight source systems | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Database | Demo Data | very important | Current: partial. Build: distribute the one-month coherent dataset into PG MeltShop, Oracle Caster, Oracle HSM, MSSQL PKL, Excel Yard, MySQL Downtime, MySQL Parsytec and Excel QA with consistent keys. | 1) The same genealogy resolves across all eight sources. 2) Row counts match the scale target. 3) Loads are reproducible. | Vision 6.3 | - | Feature | 12 | Not Started | 0
PPIQ-N052 | Seed the canonical flat-steel plant layout (13 areas) | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Database | Demo Plant | important | Current: partial. Build: seed the 13-area line (EAF/LF/Caster/TF/HSM/SKP/LCT/HCT/STL/PKL/GVL/Yards/Roll Shop) as configured data. | 1) The layout is present as data, not hardcoded. 2) Genealogy derives from it. 3) It matches 6.2. | Vision 6.2 | - | Feature | 8 | Not Started | 0
PPIQ-N053 | Generate the demo dataset at realistic scale (~630 heats / ~5,600 coils / >100k rows) | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Database | Demo Data | very important | Current: dataset incomplete at scale. Build: a deep, realistic month of chemistry/thermal/casting/rolling/inspection/lab data at the stated scale. | 1) Counts hit ~630 heats and ~5,600 coils with >100k detail rows. 2) Distributions look plausible. 3) Regenerable from a script. | Vision 6.1 | PPIQ-N051,PPIQ-N052 | Feature | 12 | Not Started | 0
PPIQ-N054 | Demo-source one-click connection presets | N-P9 · Demo Build & Doctrine | Track 3 — Demo | App Frontend | Demo Config | important | Current: absent. Build: prepared connection presets so each demo DB link is one click during the live demo, while still exercising the real connector path. | 1) Each of the eight links connects in one click. 2) Nothing is hardcoded around the connector. 3) Presets are demo-profile only. | Vision 6 | PPIQ-N051 | Feature | 5 | Not Started | 0
PPIQ-N055 | Live end-to-end configuration demo proof (no hardcoding) | N-P9 · Demo Build & Doctrine | Track 3 — Demo | App Frontend | Demo Doctrine | very important | Current: absent. Build: a scripted proof that every DB link, job, mapping, KPI, page and widget is created live from the HMI on the prepared data. | 1) A dry run builds the full demo from empty via the HMI only. 2) No hardcoded page/widget is used. 3) It is captured as evidence. | Vision 6 (golden rule) | PPIQ-N054 | Feature | 8 | Not Started | 0
PPIQ-N056 | Demo persona accounts (Operator, QA Lead, Plant Manager, Admin) with scoped views | N-P9 · Demo Build & Doctrine | Track 3 — Demo | App Backend | Personas | important | Current: partial; depends on RBAC. Build: seed the four personas with role-scoped access. | 1) Each persona logs in and sees exactly its scoped surface. 2) Scoping is enforced by the RBAC matrix (N002). 3) Tested. | Vision 6.4 | PPIQ-N002 | Feature | 5 | Not Started | 0
PPIQ-N057 | 25-step technical demo script with verification points | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Documentation | Demo Scripts | important | Current: absent. Build: a step-by-step technical walkthrough with a verification checkpoint at each step, covering link->mapping->page->ML->assistant. | 1) 25 steps with expected results. 2) Each is verifiable live. 3) The full intelligence path is covered. | Vision 6.4 | PPIQ-N055 | Documentation | 6 | Not Started | 0
PPIQ-N058 | 5-minute executive demo script with talk track | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Documentation | Demo Scripts | important | Current: absent. Build: a tight executive narrative hitting the three 'sensations'. | 1) A 5-minute path with talk track. 2) It lands the value story. 3) Rehearsed against the dry run. | Vision 1/6.4 | PPIQ-N055 | Documentation | 4 | Not Started | 0
PPIQ-N059 | Recovery lines for known fail-points | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Documentation | Demo Scripts | normal | Current: absent. Build: pre-written, composed recovery lines for each known demo risk, mapped to the script steps. | 1) Every identified fail-point has a recovery line. 2) Lines map to the script steps. | Vision 6.4 | PPIQ-N057 | Documentation | 3 | Not Started | 0
PPIQ-N060 | Record the dry-run video + capture website screenshots | N-P9 · Demo Build & Doctrine | Track 3 — Demo | Documentation | Demo Evidence | normal | Current: absent. Build: a recorded clean dry run and evidence screenshots feeding the website track. | 1) A full dry run is recorded. 2) Screenshots are captured at evidence quality. 3) Assets are handed to the website track. | Vision 6.4 | PPIQ-N055 | Documentation | 5 | Not Started | 0
N-P10 · Website (Pillar V)
PPIQ-N061 | Produce the logo asset set per the brand brief | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Brand Assets | important | Current: partial. Build: the connected-node mark in full/icon/stacked variants and full-colour/dark/light/mono, per the brief. | 1) All variants delivered to spec (Electric Cyan on Deep Navy; no steel-only imagery). 2) A favicon is included. | Vision 7.1 | - | Design | 6 | Not Started | 0
PPIQ-N062 | PlantProcess IQ product page - feature the AI assistant & honest-intelligence story | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Product Pages | very important | Current: partial. Build: the flagship page with interactive graphics, the honesty story and license detail, obeying the golden rule. | 1) On-brand, advanced UX. 2) Honesty language enforced. 3) CTA wired (N066). | Vision 7.2 | PPIQ-N061 | Feature | 10 | Not Started | 0
PPIQ-N063 | MES product page (full) | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Product Pages | normal | Current: absent. Build: the full MES page - description, benefit, graphics, license, CTA. | 1) Complete, on-brand. 2) Golden-rule compliant. | Vision 7.2 | PPIQ-N061 | Feature | 6 | Not Started | 0
PPIQ-N064 | QES product page (full) | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Product Pages | normal | Current: absent. Build: the full QES page - description, benefit, graphics, license, CTA. | 1) Complete, on-brand. 2) Golden-rule compliant. | Vision 7.2 | PPIQ-N061 | Feature | 6 | Not Started | 0
PPIQ-N065 | Yard & Warehouse + Energy Management product pages (full) | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Product Pages | normal | Current: absent. Build: full pages for both remaining products. | 1) Both complete and on-brand. 2) Golden-rule compliant. | Vision 7.2 | PPIQ-N061 | Feature | 8 | Not Started | 0
PPIQ-N066 | Pricing + CTA wired to lead capture & the demo lifecycle | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Conversion | important | Current: partial. Build: pricing/CTA connected to lead capture and the demo/inquiry flow. | 1) A visitor can request an inquiry. 2) Leads are captured. 3) CTA reflects the tiers. | Vision 7.3 | - | Feature | 6 | Not Started | 0
PPIQ-N067 | Evidence-grade screenshots + case-study snippets | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Conversion | normal | Current: absent. Build: polished evidence assets and short case-study snippets from the dry run. | 1) Assets are evidence-grade and on-brand. 2) Embedded across the product pages. | Vision 7.3 | PPIQ-N060 | Design | 5 | Not Started | 0
PPIQ-N068 | Brand-consistency audit across app, website & reports | N-P10 · Website (Pillar V) | Track 4 — Website | Web | Brand | normal | Current: absent. Build: a single audit that palette, type and components match across all three surfaces. | 1) An enumerated checklist passes. 2) Drift items are logged and fixed. 3) One canonical identity is confirmed. | Vision 7.1 | PPIQ-N062 | Documentation | 5 | Not Started | 0
N-P11 · Docs, Legal & Operations
PPIQ-N069 | Deployment runbook (server, Compose, Caddy, Jenkins) | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Documentation | Ops Docs | important | Current: partial. Build: a complete, current runbook covering the Hetzner stack, Compose, Caddy and the CI pipeline, with parity steps. | 1) A clean machine reaches a working login by following the runbook only. 2) Parity steps are included. | Vision 10 | - | Documentation | 6 | Not Started | 0
PPIQ-N070 | Incident-response runbook + daily backup job (verified restore) | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Infrastructure | Ops / Backup | important | Current: absent. Build: an incident playbook and an automated daily backup with a verified restore. | 1) Backups run daily and a restore is tested. 2) The playbook covers the top failure modes. | Vision 10 | - | Feature | 6 | Not Started | 0
PPIQ-N071 | Local<->server parity contract verification | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Infrastructure | Parity | important | Current: absent as an explicit check. Build: a verifier that the API base URL, auth keys, smoke credentials and DB host are defined once and match between local and server. | 1) A parity check fails loudly on any mismatch. 2) It runs in CI/boot. 3) 'Works on my machine' equals 'works on the server'. | Vision 10.3 | - | Hardening | 5 | Not Started | 0
PPIQ-N072 | Kill-by-port tooling that prints the fresh PID/StartTime | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Infrastructure | Ports / Process | normal | Current: kill-by-port exists in dev scripts but the proof-of-fresh-process output is not standardized everywhere. Build: standardize stop/relaunch to free the port by owning process and print the new PID + start time. | 1) A restart provably replaces the listener (new PID/StartTime printed). 2) The stale-listener failure mode cannot recur. | Vision 10.2 | - | Hardening | 3 | Not Started | 0
PPIQ-N073 | AI/ML subsystem architecture + tenant-isolation & audit companion doc | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Documentation | Design Docs | important | Current: partial. Build: the design-companion doc for the intelligence subsystem plus the tenant-isolation/audit reference, cross-linked to Vision v2.0 (the recommended 'design companion'). | 1) The doc is complete and consistent with the implemented matrix. 2) It is referenced from the canonical vision. | Improvement Analysis 6/7 ¦ Vision 3 | PPIQ-N005 | Documentation | 6 | Not Started | 0
PPIQ-N074 | UI Standards onboarding for future contributors | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Documentation | Onboarding | normal | Current: partial. Build: an onboarding guide to the canonical component contract and brand styling. | 1) A new contributor can build a compliant page from the guide. 2) It is linked from the repo. | Vision 5.1 | PPIQ-N041 | Documentation | 4 | Not Started | 0
PPIQ-N075 | Pilot legal pack: mutual NDA, SOW & GDPR-aligned DPA (LLM-provider disclosure) | N-P11 · Docs, Legal & Operations | Track 2 — Hardening | Documentation | Legal | important | Current: absent. Build: the three pilot templates, with the DPA aligned to GDPR and disclosing the LLM provider, consistent with the read-only/air-gapped story. | 1) NDA, SOW and DPA drafts are ready for counsel review. 2) The DPA notes data flows + provider. 3) Consistent with the honesty/air-gapped narrative. | Pilot readiness ¦ Vision 3 (air-gapped) | - | Documentation | 6 | Not Started | 0

## Phase Plan
Phase Plan — execution order (counts & effort computed live)
# | Phase (execution order) | Tasks | Effort (hrs)
1 | N-P1 · Security, Access & Trust Closeout | 7 | 65
2 | N-P2 · The Value Model | 3 | 34
3 | N-P3 · Intelligence Core Completion | 5 | 58
4 | N-P4 · Risk Scorer Hardening | 3 | 32
5 | N-P5 · Inspection -> Generated Pages | 4 | 38
6 | N-P6 · The AI Assistant | 9 | 82
7 | N-P7 · Workflow & HMI Completion | 6 | 46
8 | N-P8 · Presentation-Grade Hardening (Quality Bar) | 13 | 109
9 | N-P9 · Demo Build & Doctrine | 10 | 68
10 | N-P10 · Website (Pillar V) | 8 | 52
11 | N-P11 · Docs, Legal & Operations | 7 | 36
| TOTAL | 75 | 620
By Track
| Track | Tasks | Effort (hrs)
| Track 1 — Workflow | 30 | 290
| Track 2 — Hardening | 27 | 210
| Track 3 — Demo | 10 | 68
| Track 4 — Website | 8 | 52

## Coverage Map
Coverage Map — every Vision v2.0 area -> the v13 tasks that complete it
Confirms nothing in the canonical target is unaddressed. 'Already built?' summarises what exists today (see the Excluded sheet).
Vision v2.0 area | What remains (the v13 work) | v13 tasks | Already built?
2.2.2 DB Link & credentials | Behavioural connector tests + masked-credential proof | N045 | Core built
2.2.3 Two-stage / delta ingestion | Schema-drift detection; resumability tests | N032, N047 | Engine built
2.2.4 Schema mapping engine | Typed resolver errors (full UI design lives in v3 3.3) | N033 | Core + safe-SQL built
2.2.5 Genealogy spine | Mapping-authored canonical spine, both directions | N034 | Partial join built
2.2.6 Jobs Monitor | Extended result + learning-run visibility | N014, N021 | Monitor built
2.3 Page builder & widgets | First-run wizard; heat-map widget; script grammar | N035, N036, N037 | Builder + script layer built
3.1 Feature store & outcomes | (complete - no remaining work) | - | Built incl. cascade-downtime
3.2 Scheduled learning & methods | Spearman/MI/Lasso; VIF/stability/confounding; gates; results; tests | N011-N015 | Pearson/PB/Cramer + FDR/effect/power built
3.3 Inspection -> generated pages | Runner; auto-page generation; scheduling; e2e | N019-N022 | Investigate endpoint built
3.4 Risk scorer | Calibration; registry provenance; drift/champion-challenger | N016-N018 | Additive decomposable scorer built
3.5.1 Proactive suggestions | Engine; endpoint; proactive feed UI | N023-N025 | Prerequisites built
3.5.2 Conversational RAG | KB ingestion; retrieval; agent+tools; UI; feedback; grounding tests | N026-N031 | pgvector + providers built
4 Licensing & tiers | License x role resolution; live toggle / banner / badge | N003, N043 | Tier primitives built
5 / 8 Hardening & Quality Bar | Resilience audit; progress UI; action matrix; contracts; perf; dedup; boot safety | N038-N050 | Error boundary/toasts/apiClient/skeletons; honesty enforced
6 Demo Doctrine | 8-source split; plant layout; scale; presets; live proof; personas; scripts; evidence | N051-N060 | Compose + partial seed built
7 Website (Pillar V) | Logo set; five product pages; conversion; evidence; brand audit | N061-N068 | Partial site built
10 Operational Doctrine | SQL-apply fix; boot safety; runbooks; parity; ports | N007, N050, N069-N072 | Validator/migrations/loopback built
User/Role/Access (residual gap) | RBAC matrix; license x role; tenant tests; audit coverage; doctrine section | N002-N006, N056 | Role/tenant primitives only
Value Model (commercial lever) | Impact engine; cost config; ROI presentation contract | N008-N010 | Nothing built (0 code hits)

## Excluded - Already Built
Excluded from v13 — already built (the audit trail for 'no done tasks')
These capabilities exist in the 31-May snapshot, so they are intentionally NOT in the backlog. Listed for transparency.
Capability (excluded) | Evidence / where it lives | Prior ref
Test foundation, coverage baseline & CI gate | dotnet + vitest coverage; suite is red-on-regression and gated | T300-T306
Auth config-section prefix + bootstrap-collision guard | StartupConfigurationValidator rejects DEV keys / default pw outside Dev | T282
Frontend auth retry backoff + attempt cap | apiClient with bounded retry | T280
PostgreSQL public port closed + loopback audit | 127.0.0.1 binding + external nmap scan guard | T286 / T208
Replace bootstrap admin in production | disabled sentinel + real seeded admin | T287
Eight-source Compose definition (loopback-bound) | docker-compose.demo-sources.yml | T245
SafeSqlValidator + typed resolver base | SafeSqlValidator (CTE fix); SchemaViewResolver base | T206
Widget edit -> DB values + script-layer base | widget builder binding | T242
Multi-grain feature store (heat/strand/coil/location) | feature-store schema | T209
Metallurgical derived features | FeatureEngineeringService | T210
Outcome catalog incl. cascade-downtime + KPI-as-view | outcome definitions | T211 / T293
Correlation compute interface + .NET default impl | ICorrelationComputeEngine | T212
pgvector knowledge-base provisioning | pgvector store | T213
Narrative / Embedding provider abstraction (self-host + API) | INarrativeProvider / IEmbeddingProvider | T292
Four learning-job definitions | EnsureMlJobDefinitions | T214
Additive risk scorer with exact decomposition | risk scorer (base) | T236
Honesty contract enforced | 34 'could not be loaded' occurrences are all lint guards / test negations | Validation
DevSeed endpoints gated behind IsDevelopment() | environment-gated seed endpoints | Validation
Auto-migration at startup | MigrateAsync() on boot | prior session
Frontend resilience base | global ErrorBoundary, Sonner toasts, apiClient timeouts/retry, skeleton loading | prior session