## 00_Read_Me
PLANTPROCESS IQ · DOCTRINE v7 — IMPLEMENTATION AUDIT vs ROADMAP
Re-validated against Doctrine v7.0 (16 gates G1–G16, the 46→84 frame) · Source snapshot 06-Jun-2026 · 1,705 files / 322,856 lines
WHAT CHANGED | This revision re-keys the audit to your canonical reference — Doctrine v7.0 — instead of the auto-generated ground-truth scorecard. v7 defines what 'done' means (16 acceptance gates, §22) and an honest build delta (§21) scoring the build at ~46/100 today against a ~84/100 ceiling, across four waves A/B/C/D.
FOUR NUMBERS, RECONCILED | Doctrine §21 self-assessment (3 Jun): ~46/100 'how much of the full vision is built'. Ground-truth scorecard: 93% 'do the phase artifacts exist' (presence). Prior audit (this file v1): ~78% 'do the claimed phases function'. THIS revision: ~60/100 'how much of the v7 gate bar is met, verified in source'. They differ only by denominator — none is wrong.
HEADLINE 1 — AHEAD OF §21 | The 06-Jun build is materially ahead of the doctrine's 03-Jun delta. Items §21 lists as 'unstarted' are in fact started with real code: the Correlation Engine (Spearman, mutual information, Lasso, Benjamini-Hochberg FDR, bootstrap, readiness gating — verified real, not a shell), the Value Engine (abstain + bounded euro range), the OT-safe Edge Collector (gateway + endpoints + page + SQL + tests), and schema-drift / mapping-health. Security Wave A is largely DONE (see G12).
HEADLINE 2 — BEHIND ON GATE-GREEN | Breadth is ahead; provability is behind. The gates require 95–100% with a passing acceptance fixture (the €28k–€56k value range reproducing, the golden dataset recovering signals under FDR, a coil resolving both genealogy directions, no uncited assistant number). Those fixtures are largely UN-RUN: 31% of tests (incl. the golden-gate + statistical-method + suggestion tests) live in two UNREGISTERED projects, and the §13 'no-85%' rule is itself violated by god-files renamed to .runtime siblings to pass the size gate.
VERIFIED SAFE | Read line-by-line and cleared: SafeSqlValidator, WidgetScriptSqlCompiler, GenealogyService, Argon2id + Ed25519 verify paths, AdvancedCorrelationComputeService (stats helpers consolidated in StatisticalDiscipline.cs — no compile break). 1,705-file hygiene scan: 0 NotImplementedException / swallowed catch / async-void / .Result deadlock / DateTime.Now / string-concat SQL / console.log / @ts-ignore.
DROP-IN PRIORITY (gate order) | Wave A (G12/G9): finish admin-MFA-enforced + prove dev-seed absent in prod build, close DB port on server. Then the single highest-leverage fix overall: register PlantProcess.Analytics.Core.Tests + Analytics.Engine.Tests so the Wave-B/intelligence acceptance fixtures actually run — this alone moves G4/G10 from 'asserted' to 'proven'. Then genuinely decompose the 6 .runtime god-files (don't baseline-pad).
HONEST BOUNDARY | P15+/customer-production items (real IdP metadata, signed pilot acceptance, measured RPO/RTO, certified historian) cannot be produced from source and are correctly NOT claimable — they need a live pilot. Everything here is judged from the committed code only.

## 01_Gate_Scorecard
PLANTPROCESS IQ · DOCTRINE v7 — ACCEPTANCE GATES G1–G16 — independently verified vs doctrine §22
DoD & acceptance fixture from §22 · §21 reality = doctrine's 03-Jun column · 06-Jun reality = this source review · Gate-green requires 95–100% with the fixture passing
Gate | Wave | Definition of done (§22) | Doctrine §21 reality (03-Jun) | Verified 06-Jun reality (source) | % | Status | Blocker to gate-green
G1 | C | Source integration: honest availability, test-before-save, masked secrets, staging, import batch, failure tests | CSV/Excel + MSSQL/MySQL; SafeSqlValidator passing | Connector catalog/DTOs/infra real; SafeSqlValidator verified correct; secrets masked in config; staging present | 70 | MOSTLY DONE | Per-connector behavioural test that credentials never appear on read-back; certify one historian.
G2 | C | Mapping & genealogy: business keys, canonical mapping, safe SQL, versioning, genealogy, rollback | Partial | GenealogyService correct (BFS cycle detect); golden-thread test; MappingHealth + SchemaDriftDetector present; typed-error rollback | 75 | MOSTLY DONE | Prove a coil resolves BOTH directions + a bad mapping returns typed error & rolls back, as an executing fixture.
G3 | C | Workflow (HMI): configure data/page/widgets/jobs/dashboards/reports from HMI, no hardcoding | Reset-job foundation; not complete | Demo scenario (899L), widget builder, page builder present | 55 | PARTIALLY DONE | Recorded dry-run that builds the FULL demo from empty via HMI only, with zero hardcoded page/widget.
G4 | B | Intelligence: simple+advanced analysis, value, suggestions, assistant — evidence-linked, honest, tenant-safe | Partial / unstarted | Correlation engine REAL (Spearman/MI/Lasso/FDR/bootstrap/readiness); value engine (abstain+range); suggestion engine; grounding service real | 60 | PARTIALLY DONE | BLOCKER: golden-gate + statistical + suggestion tests are in an UNREGISTERED project — fixture does not run. Register, then prove FDR signal recovery + no uncited number.
G5 | A/B | Access & value: RBAC, license, tenant isolation, audit on every endpoint; bounded euro range; cross-tenant 403 | Security partial | RBAC + Ed25519 license + audit real; tenant isolation single-tenant-in-practice + silent demo fallback; value engine present | 60 | PARTIALLY DONE | Add a 2-tenant test asserting cross-tenant => 403/empty; reproduce the €28k–€56k range as a fixture.
G6 | D | UI/UX: design system, edge states, no-dead-button; action matrix green; visual + cross-browser | Dark theme | Design tokens + DataFetchBoundary edge states + a11y E2E + visual specs present | 75 | MOSTLY DONE | Enumerate the full action matrix to green; run visual-regression + cross-browser in CI.
G7 | C | Demo: 8-source, 13-area realistic dataset; reset + rebuilt through workflows; one-click readiness | Reset-job foundation | 8 sources present in seed SQL; reset job present | 55 | PARTIALLY DONE | One-click readiness check passing + a recorded clean dry-run; build the dataset THROUGH the HMI (Golden Rule).
G8 | D | Website: ecosystem, pricing, proof, security, CTAs, brand — no unsupported claims; honesty-lint passes | (not in §21) | Website source (37 files), commercial guard, lead-capture marker, ValueHonestyLint present | 70 | MOSTLY DONE | Confirm honesty-lint blocks forbidden claims (Appendix E) + a CTA captures a real lead end-to-end.
G9 | A/D | Operations: deploy, backup, restore, health, readiness, logging, runbooks; clean machine→login; restore verified | Single Docker host; CI/CD live | CI/CD live (Jenkins); Caddy/Docker; health+readiness endpoints | 60 | PARTIALLY DONE | MEASURED restore drill + incident runbooks require a real environment; close the exposed DB port on the server (SSH, not repo).
G10 | ALL | Quality bar: every §13 row has passing proof; NO item at 85% | (not in §21) | §13 referenced — but the 'no-85%' rule is VIOLATED: 6 god-files renamed to .runtime to pass the size gate; 31% of tests unregistered | 50 | PARTIALLY DONE | Reconcile to genuine green: real god-file decomposition + register the 2 test projects. Until then G10 cannot be claimed.
G11 | C | OT-safe acquisition: Edge Collector one-way push, source-impact budget, CDC/replica preference | Unstarted | STARTED (doctrine stale): V5OtSafeEdgeCollectorEndpoints, OtSafeEdgeCollectorGateway, edgeCollector.ts, EdgeCollectorPage, 440_p5 SQL, P5 tests | 55 | PARTIALLY DONE | Verify one-way push is ENFORCED (no inbound OT path) and the source-impact budget is measured, not just modelled.
G12 | A | Identity & security: Argon2id, admin MFA, in-memory token + HttpOnly refresh, SSO/SCIM, per-env keys, dev-seed gated | localStorage token; hardcoded key; dev-seed unconditional | DOCTRINE STALE — VERIFIED DONE: Argon2id+FixedTimeEquals; in-memory token + HttpOnly cookie (localStorage RETIRED); SigningKey>=32 guard; DevSeed gated to Dev; SSO/SCIM real; MFA SQL+endpoints present | 88 | MOSTLY DONE | Final 12%: enforce admin MFA (not just present) + prove dev-seed absent in the prod BUILD artifact.
G13 | B | Data boundary & model gov: gateway 3 serving modes, data-min, redaction, per-tenant no-egress toggle, eval harness | (not in §21) | V5PrivateModelGatewayCertification + AssistantGateway (654L) + grounding present | 60 | PARTIALLY DONE | Prove self-hosted mode leaks nothing + private-endpoint sends only question+scoped evidence; wire the eval harness as a regression gate.
G14 | D | Accessibility & i18n: WCAG 2.1 AA contrast-audited light theme, RTL, locale/units/timezone | Dark theme; EN only | DOCTRINE STALE — STARTED: phase78 i18n runtime + RTL CSS + i18n/RTL E2E + light-theme runtime + locale storage | 60 | PARTIALLY DONE | Pass a full WCAG-AA contrast audit + ship Arabic content + per-user units/timezone switch.
G15 | C/D | Coverage & honesty: population on every analysis, blended provenance, label-quality surfaced | (not in §21) | Coverage/provenance modelled (§5.4-5.5); grounding blocks uncited numbers | 55 | PARTIALLY DONE | Enforce 'every finding states its population + exclusions'; prove a transition coil reports weighted attribution.
G16 | D | Compliance: secure-SDLC evidence, SOC2/ISO27001 track, GDPR, GxP/21CFR11 pack | Roadmap only | SLIGHTLY STALE: ComplianceControls endpoints + control-evidence matrix + SQL + sensitive-data catalog present (scaffold, not just roadmap) | 55 | PARTIALLY DONE | SOC2/ISO/GxP are external cert tracks needing a real audit; deliver GxP audit-trail + e-signature where required.
ROLL-UP | Independent doctrine-aligned roll-up ≈ 60/100 (vs §21 self-assessment 46/100, 03-Jun). 0 gates at green (95–100%). G12 closest (88%). The build is BROADER than §21 records but no gate is green because acceptance fixtures are unproven (test registration + real god-file refactor are the unlocks).

## 02_Doctrine_Delta_§21
PLANTPROCESS IQ · DOCTRINE v7 — DOCTRINE-vs-BUILD DELTA (§21) — refreshed against 06-Jun source
Your §21 was written 03-Jun. Many 'unstarted/localStorage' entries are now STALE — the build advanced. 'Drift' flags where reality is ahead of the doctrine's record.
Capability | Doctrine target (Part I) | §21 reality (03-Jun) | Verified reality (06-Jun source) | Drift | Revised status
Access token | In-memory + HttpOnly refresh cookie (§10.2) | Stored in browser localStorage | RETIRED — in-memory token + HttpOnly cookie; verified in apiClient.ts | AHEAD | DONE
Signing keys / dev-seed | Per-env signed keys; dev-seed gated out of prod | Hardcoded JWT key; dev-seed unconditional | SigningKey>=32-char startup guard; DevSeed gated to IsDevelopment() | AHEAD | DONE
Exposed services | DB bound to 127.0.0.1; no bootstrap admin | PostgreSQL port publicly exposed; bootstrap admin present | Bootstrap-collision detection added; port closure is server-side (not verifiable from repo) | PARTIAL | MOSTLY DONE
Value Engine | Bounded euro ranges, abstain path (§7.5) | Entirely unstarted | STARTED — ValueImpactEngine (abstain + bounded range) + P15 scenario sim; MVP-sized | AHEAD | PARTIALLY DONE
L4 statistics | Spearman, MI, Lasso, VIF, bootstrap + FDR (§7.3) | Unstarted (ML-readiness only) | BUILT — AdvancedCorrelationComputeService: Spearman, MI, Lasso, Benjamini-Hochberg FDR, bootstrap, readiness gating (verified real) | AHEAD | MOSTLY DONE
Suggestion / assistant guard | Deterministic suggestions; no-fabrication guard (§7.6-7.7) | Partial / unstarted | REAL — SuggestionEngine + GroundingService (blocks uncited numbers/causal phrases) verified | AHEAD | MOSTLY DONE
Edge Collector | One-way push + source-impact budget (§4.6) | Unstarted | STARTED — OtSafeEdgeCollectorGateway + endpoints + page + 440_p5 SQL + P5 tests | AHEAD | PARTIALLY DONE
Connectors | Relational + one historian GA, honest status (§4.7) | CSV/Excel + MSSQL/MySQL; SafeSqlValidator passing | Confirmed; connector catalog/infra real; historian still not certified | MATCHES | MOSTLY DONE
Schema drift / mapping health | Snapshot + typed pause + health panel (§4.9) | Unstarted | STARTED — SchemaDriftDetector + Phase34MappingHealthEndpoints + MappingHealthPage + SQL | AHEAD | PARTIALLY DONE
Genealogy / coverage | Recursive spine + coverage + blended provenance (§5) | Partial | Genealogy correct (cycle detect) + golden-thread test; coverage/provenance modelled | MATCHES | MOSTLY DONE
Demo-through-HMI | Full demo built from empty via HMI (§14) | Reset-job foundation; not complete | Demo scenario + reset job present; full from-empty-via-HMI dry-run not proven | MATCHES | PARTIALLY DONE
Accessibility / i18n | WCAG AA light theme + Arabic RTL (§8.6-8.7) | Dark theme; EN only | STARTED — phase78 i18n runtime + RTL CSS + i18n/RTL E2E + light theme; Arabic content + AA audit pending | AHEAD | PARTIALLY DONE
Ops & scale | Time-series store, restore drill, runbooks (§16) | Single Docker host; CI/CD live | Time-series foundation SQL present; CI/CD live; measured restore drill needs real env | MATCHES | PARTIALLY DONE
Compliance | SOC 2 / ISO 27001 + GxP pack (§18) | Roadmap only | SCAFFOLD — ComplianceControls endpoints + control-evidence matrix + sensitive-data catalog; certs need real audit | AHEAD | PARTIALLY DONE
NET | 9 of 14 capabilities are AHEAD of the §21 record — refresh §21 to keep the doctrine honest. The remaining truth: 'started' ≠ 'gate-green'. Update §21's reality column with these findings before the next review so the say-do gap reflects 06-Jun, not 03-Jun.

## 03_Refactor_Rework
PLANTPROCESS IQ · DOCTRINE v7 — REFACTOR / REWORK REGISTER — done-but-badly, mapped to the gate it blocks
Carried forward from v1 and re-keyed to v7 gates. The .runtime renames specifically VIOLATE the §13/G10 'no-85%' rule.
ID | Severity | Blocks gate | Finding | Evidence (source) | Recommended action
RW-01 | HIGH | G10 (quality bar) / G5 / G3 | God-file 'refactors' are 1:1 renames to .runtime siblings, not decompositions | Shims state 'Before lines:1389 / Runtime lines:1389'; .runtime files added to phase56-file-size-baseline.json so the gate passes. 6 files (T-037/T-054/T-055): AdminDbConfigurationTab.runtime.tsx 1127L; MaterialAnalyticsPages.runtime.tsx 1102L; GenericSchemaMappingEndpoints.runtime.cs 1388L; Phase1WorkflowTruthEndpoints.runtime.cs 1368L; WorkflowEndpoints.runtime.cs 1031L; ConnectorConfigurationService.runtime.cs 1246L | Genuinely split by responsibility. This directly blocks G10 — §22 says mark green only at 95-100%, never 85%, and a renamed god-file is an 85% dressed as 100%.
RW-02 | HIGH | G5 / G12 (tenant isolation) | Tenant resolution duplicated 15x with a silent demo-tenant fallback | Each V5 endpoint redefines DefaultTenantId (00..001) + private ResolveTenantId() returning the demo tenant on a missing/invalid claim instead of 401. DB users get a real claim, but the fallback + config-user pinning mean isolation is never exercised | Introduce ITenantContextAccessor (resolve once in middleware); missing/invalid claim => 401. This is also the prerequisite for the G5 acceptance fixture 'cross-tenant returns 403/empty'.
RW-03 | MED-HIGH | G2 / architecture | Raw SQL still embedded in the API layer (Clean-Arch violation) | 27 API .cs files hold ~283 SQL lines (Phase45Closure 31, TwoStageImport 28, GenericSchemaMapping.runtime 17, MlFoundation 14). Pack-4 relocation incomplete | Move SQL into Infrastructure query services behind Application interfaces (NpgsqlDataSource injected); API calls services only.
RW-04 | MED | G10 (quality bar) | Two file-size validators disagree; the narrow one is gamed | check-file-size-complexity.cjs exempts a hardcoded allowlist + an extensible baseline and passes; the broader god-file policy reports unknown=33. 29 non-test files remain >700L | Reconcile to ONE gate that fails on any non-test source >700L with no baseline escape hatch for relocated .runtime files.
RW-05 | LOW | G6 | 4-hop re-export indirection for WidgetBuilder | Wizard.tsx -> .implementation -> Content.tsx -> .implementation -> content/orchestrator. Resolves (no break) but obscures the real module | Collapse to a single wrapper -> orchestrator hop; delete intermediate .implementation shims.
RW-06 | LOW | G2 / G4 (perf) | Genealogy cycle-check is N+1 (one DB round-trip per node) | WouldCreateCycleAsync awaits a query inside the BFS loop; deep graphs => many round-trips. Logic correct, performance not | Replace with a single WITH RECURSIVE ... LIMIT query, or preload the edge set.
RW-07 | INFO | G12 | Vestigial ACCESS_TOKEN_KEY constant in apiClient | ACCESS_TOKEN_KEY='plantprocess.auth.accessToken' defined but token is in-memory; implies a localStorage path that no longer exists | Delete the dead constant to avoid confusion about token persistence.

## 04_Bugs_and_Cleared
PLANTPROCESS IQ · DOCTRINE v7 — BUGS / PROBLEMS + VERIFIED-SAFE — current source
The one concrete defect is test-wiring (now the top blocker to G4/G10 green). PASS rows = read line-by-line and cleared, incl. the newly-confirmed real correlation engine.
ID | Severity | Gate | What | Detail / impact | Status | Fix
BUG-01 | BLOCKER | G4 / G10 / CI | 2 of 8 test projects not registered in PlantProcessIQ.sln | Analytics.Core.Tests (73 tests) + Analytics.Engine.Tests (3) => ~94/301 tests (31%) never run. Hidden: GroundingContractTests (G4/G13), SuggestionEngineTests, P05_KpiEngineTests, ALL P06_* statistical + golden-gate tests. The doctrine's G4 acceptance fixture lives here and does not execute | CONFIRMED | Add <ProjectReference> for both to the .sln; re-run full suite; this single change moves the entire Wave-B intelligence proof from asserted to verified.
BUG-02 | MED | G5 / G12 | Silent demo-tenant fallback on missing/invalid tenant claim | Token without tenant_id maps to demo tenant 00..001 and reads/writes demo data instead of 401 — isolation/defense-in-depth gap blocking the G5 'cross-tenant 403' fixture | CONFIRMED | Reject (401) when the claim is absent/invalid; never default. (See RW-02.)
BUG-03 | LOW | G1 (safe-SQL) | SafeSqlValidator comment-stripping not nesting/string-literal aware | Block-comment regex non-greedy (no nested /*..*/); line-comment strips '--' inside literals. NO security bypass (forbidden-token scan still runs) but can false-reject a valid SELECT | MINOR | Tokenize/skip string literals before stripping comments, or document the constraint.
BUG-04 | INFO | G1 (safe-SQL) | Read-only safety leans on a denylist | Denylists are incomplete; primary controls (SELECT/WITH-only + table allowlist + recursive-LIMIT) are strong but only fully safe if the DB connection also uses a read-only role | BY DESIGN | Run preview/widget queries under a least-privilege read-only PostgreSQL role.
CLEAR-01 | PASS | G4 (NEW) | Correlation engine verified GENUINE, not a shell | AdvancedCorrelationComputeService implements real Spearman, mutual information, Lasso, Benjamini-Hochberg FDR, bootstrap stability, permutation p-values, method selection w/ nonlinearity, readiness BLOCKED gating. Helpers in StatisticalDiscipline.cs/Stats.cs — no compile break. Has a test in the REGISTERED UnitTests project too | PASS | No action — this contradicts §21 'unstarted'; promote in §21.
CLEAR-02 | PASS | G1/G4/G2 | SafeSqlValidator, WidgetScriptSqlCompiler, GenealogyService read line-by-line | Parameterized values; identifier whitelisting; recursive-LIMIT; correct BFS cycle detection; IN-list via = ANY(@p). No logical errors | PASS | No action.
CLEAR-03 | PASS | G12/G5 | Argon2id verify + Ed25519 license verify read line-by-line | CryptographicOperations.FixedTimeEquals (constant-time) on both hash paths; Ed25519 enforces 32-byte key + EdDSA alg + real signature verify with explicit failure | PASS | No action.
CLEAR-04 | PASS | G10 | Build integrity after the rename refactor | All 254 live relative imports/exports resolve; only 5 unresolved, all in tools/archive/retired-*. No build break introduced by .runtime/.implementation renames | PASS | No action.
CLEAR-05 | PASS | ALL | 1,705-file hygiene scan | 0 NotImplementedException / swallowed catch{} / async void / .Result deadlock / DateTime.Now / string-concat SQL / console.log / @ts-ignore / dangerouslySetInnerHTML / shipped TODO | PASS | No action — strong baseline.

## 05_Wave_Plan_A-D
PLANTPROCESS IQ · DOCTRINE v7 — REALIZATION WAVES A–D — independent % complete vs doctrine §20
Doctrine §20 effort estimates beside my source-verified completion. Wave A is largely done; B/C are started but unverified; D is partial.
Wave | Goal | Closes gates | Doctrine est. | My % done | What is genuinely built (06-Jun) | What is left to gate-green
A | Security & identity | G12, G9(start) | ~120-160 h | ~85% | localStorage retired, per-env key guard, dev-seed gated, Argon2id, SSO/SCIM, MFA scaffold all present & verified | Enforce admin MFA; prove dev-seed absent in prod build; close DB port (server-side, SSH).
B | Value engine & L4 stats | G5, G4 | ~160-220 h | ~65% | Correlation engine REAL (Spearman/MI/Lasso/FDR/bootstrap); value engine (abstain+range); suggestions; grounding — all built | REGISTER the test projects so the golden-gate/FDR/value fixtures run; reproduce the €28k-€56k range; expand value engine beyond MVP.
C | Acquisition, connectors & demo-through-HMI | G1,G11,G2,G3,G7 | ~180-240 h | ~55% | Edge Collector + schema-drift + mapping-health STARTED (doctrine had as unstarted); connectors real; demo scenario present | Certify one historian; enforce one-way push + source-impact budget; recorded full demo-from-empty via HMI; one-click readiness.
D | Coverage, i18n, ops & compliance | G6,G14,G15,G16,G9 | ~160-220 h | ~58% | i18n/RTL + light theme + a11y E2E STARTED; compliance scaffold present; CI/CD live | Full WCAG-AA audit + Arabic content; measured restore drill + runbooks (needs env); SOC2/ISO/GxP external tracks.
46→84 | The through-line holds: A makes it safe, B valuable, C provable, D enterprise-ready. The build sits ~60/100 — ahead of §21's 46 on breadth. The fastest credible path to the 84 ceiling is verification first (register tests, real refactor) so the work already done can be MARKED done.