## 00_Read_Me
PLANTPROCESS IQ · DOCTRINE v7 — REALIZATION BACKLOG (current build → full +Packs vision)
25 phases · 113 tasks · ~1,100 h · each phase 45–65 h and ends in a clean, deployable, demoable increment · sequenced by priority + prerequisites
PURPOSE | A single sequenced backlog that takes PPIQ from its source-verified 'Now' (~64/100) to the full +Packs vision (~95/100). It folds in everything from the prior analyses: the doctrine v7 gates (G1–G16), every refactor/rework item, and every bug found by deep source scanning. Each row is detailed enough for a junior developer to execute without further context.
ORDERING LOGIC | Priority + prerequisites, front-loaded so good things show early: (1) Verification + critical bug fixes — make the baseline honest & green; (2) Wave A security/identity/deploy — safe to show a customer; (3) Refactor — tenant resolver, god-file decomposition, SQL relocation — a clean foundation BEFORE building more; (4) Wave B value engine + L4 stats — the commercial unlock; (5) Wave C acquisition/connectors/demo-through-HMI — provable on real data; (6) Wave D UX/i18n/ops/compliance — enterprise-ready; (7) +Packs P15–P21 — advisory, SPC/PCF, integration, HA, fleet/marketplace, external certs.
DEPLOY DISCIPLINE | Every phase ends with a deploy to the server (178.105.152.180) showing something new and NOTHING broken. The last task of each phase is a deep regression sweep + deploy smoke that re-runs dotnet test, npm run build, npm run e2e and npm run test, fixes anything the phase's changes broke, and verifies the server boots to a working login. See the 'Deploy milestone' per phase on 02_Phase_Rollup.
TEST DISCIPLINE | Acceptance Criteria are realistic, hard, behavioural checks — never 'the build passes'. Each phase adds deep new tests (unit / integration / dotnet test / npm run e2e / npm run test) that prove the phase's behaviour AND guards the rest of the suite from regression. Where a change risks breaking existing tests, the regression-sweep task explicitly re-greens them.
FILE-BATCHING | Similar work is grouped so a file is not reopened across distant tasks: backend god-files are decomposed together (Phase 05), frontend together (Phase 06), security config together (Phase 02–03), i18n together (Phase 16), etc. This minimises rework and merge churn.
HOW TO USE | Sheet 01 is the master backlog — use the column filters to slice by Track, Module, Severity, or Task Type. Phase header bands (navy) separate the groups. Sheet 02 is the phase roll-up with cumulative hours, the deploy milestone, and the doctrine gates each phase closes.
LEGENDS
Severity | Critical → Very Important → Important → Normal → Optional (drives within-phase ordering)
Task Type | new feature · test · hardening · refactor · bug fix · modification
Track | Testing · Security · Hardening · Refactor · Backend · AI+ML · Demo · Web · Engine · Ops · UI/UX · Documentation
Module | FrontEnd · Backend · Database · Infrastructure · Web · Documentation · Testing · Deploy · Security · AI+ML
Waves | Pre-flight → A Safe → Refactor → B Valuable → C Provable → D Enterprise-ready → +Packs (maps to doctrine 46→84→full vision)

## 01_Task_Backlog
PLANTPROCESS IQ — REALIZATION BACKLOG · filter by Track / Module / Severity / Task Type
Task ID | Task Name | Phase | Track | Module | Submodule | Severity | Description (what to build) | Acceptance Criteria (validation & tests) | Task Type | Effort (h)
Phase 01 — Verification Foundation & Critical Bug Fixes · Wave Pre-flight · 49 h / 8 tasks · Closes G10, G4(start), G12(start) · DEPLOY: Every authored test runs & is green; zero known defects. A demonstrably solid, honest baseline to build on.
T-001 | Register the two orphaned test projects in the solution | Phase 01 | Testing | Backend | Build/Solution | Critical | Add <ProjectReference> for tests/PlantProcess.Analytics.Core.Tests and tests/PlantProcess.Analytics.Engine.Tests to Backend/PlantProcessIQ.sln. These 94 tests (GroundingContractTests, SuggestionEngineTests, P05_KpiEngineTests, every P06_* statistical + GoldenGate) are currently NOT in the solution, so dotnet test never runs them. Resolve any compile drift against the current Application/Infrastructure assemblies. | dotnet test PlantProcessIQ.sln discovers >=301 tests (was 207) and reports 0 failures; the CI log lists both Analytics.* projects in the run. | bug fix | 6
T-002 | Add a CI guard that blocks unregistered test projects | Phase 01 | Testing | Infrastructure | CI/Jenkins | Very Important | Write a guard (PowerShell or .cjs) in the Jenkins test stage that enumerates every *.Tests.csproj under /Backend/tests and asserts each is referenced by PlantProcessIQ.sln; exit non-zero otherwise. | Deliberately removing a reference fails CI with a clear message naming the project; restoring it passes. Guard has its own unit test using a fixture .sln. | new feature | 5
T-003 | Fix the silent demo-tenant fallback (reject, do not default) | Phase 01 | Security | Backend | Multi-tenancy | Critical | In every ResolveTenantId(HttpContext) helper across the 15 V5 endpoint files (and VerifiedEd25519LicenseService), a missing/invalid tenant_id claim returns the hardcoded demo tenant 00000000-...-001 instead of rejecting. Change it to return 401 when the claim is absent or unparseable. (Phase 04 centralises this; fix the unsafe default now so no build ships with silent cross-tenant exposure.) | Integration test: a JWT with no tenant claim => HTTP 401 (not demo data); a valid claim still resolves and sets the app.current_tenant GUC. No endpoint returns demo-tenant rows for an unauthenticated tenant context. | bug fix | 8
T-004 | Make SafeSqlValidator comment-stripping literal- and nesting-aware | Phase 01 | Security | Backend | SafeSqlValidator | Important | SafeSqlValidator.StripSqlComments uses a non-greedy block-comment regex (mishandles nested /* /* */ */) and strips -- inside string literals, which can false-reject valid SELECTs. Make it skip single-quoted and dollar-quoted ($tag$...$tag$) segments and handle nested block comments. The forbidden-token scan must still run on the cleaned text (no security regression). | New corpus tests pass: SELECT '/* x */ a--b' AS n FROM canon.q validates safe with the literal intact; a nested-comment WITH RECURSIVE ... LIMIT 100 validates; '; DROP TABLE' still fails. All existing SafeSqlValidator corpus tests stay green. | bug fix | 6
T-005 | Replace the N+1 genealogy cycle-check with a recursive CTE | Phase 01 | Engine | Backend | Genealogy | Important | GenealogyService.WouldCreateCycleAsync awaits one DB query per node inside a BFS loop. Replace with a single WITH RECURSIVE upward walk (explicit LIMIT) over GenealogyEdges, preserving the exact semantics (if the proposed parent is reachable from the child, reject). | A depth-1000 chain triggers exactly ONE DB round-trip (assert via command interception / query-count) and still rejects a cycle; GenealogyGoldenThreadTests stay green. | refactor | 6
T-006 | Remove dead code & vestigial constants | Phase 01 | Refactor | Frontend | Cleanup | Normal | Delete the unused ACCESS_TOKEN_KEY constant in apiClient.ts (token is in-memory; the constant implies a retired localStorage path). Delete the 6 dead files under tools/archive/retired-duplicate-pages (unresolved imports, kept only as history). | tsc + npm run build clean; grep shows zero references to ACCESS_TOKEN_KEY and to the retired page modules; production bundle size unchanged or smaller. | refactor | 4
T-007 | Run audit-log immutability tests in CI against real Postgres | Phase 01 | Testing | Backend | Audit | Very Important | AuditLogImmutabilityTests are [SkippableFact] and skip without a DB. Provide a CI Postgres (Testcontainers or the compose DB) so they EXECUTE, proving the audit table is append-only. | CI shows the immutability tests executed (not skipped) and green; an attempted UPDATE and DELETE on an audit row both fail at the DB level inside the test. | test | 6
T-008 | Phase-1 regression sweep & deploy smoke | Phase 01 | Testing | Testing | Regression | Critical | Run the full sequence (dotnet test solution-wide, npm run build, npm run e2e, npm run test) with the stack up; fix anything the above changes broke; record a green baseline. Add an E2E smoke asserting login + one dashboard render. | All four suites green at the new higher count; documented baseline (e.g. 309 passed / 0 failed / 0 unexpected-skip); deploying this phase boots to a working login with no console errors. | test | 8
Phase 02 — Identity & Secret Hardening (Wave A) · Wave A · Safe · 50 h / 6 tasks · Closes G12 · DEPLOY: Admin MFA enforced, dev-seed provably absent in prod, secrets env-only. Safe to put auth in front of a customer.
T-009 | Enforce mandatory admin MFA (TOTP) at the auth layer | Phase 02 | Security | Backend | Identity/MFA | Critical | The MFA schema (570_v5_p08...) and endpoints exist but enrolment is not enforced. Implement TOTP enrolment + verification in AuthEndpoints/AuthStore: any user with an admin/SuperAdmin PlantRole must complete MFA before receiving a full-scope token; issue a short-lived 'mfa-pending' state otherwise. Use a standard TOTP library, store secrets encrypted. | Integration tests: admin login without MFA cannot reach any admin endpoint (403/mfa-required); after TOTP verification it can; a replayed TOTP code is rejected; non-admin roles unaffected. | new feature | 14
T-010 | Prove dev-seed is absent from the production build artifact | Phase 02 | Security | Backend | Hardening | Critical | MapDevSeedEndpoints is gated to IsDevelopment() at runtime, but the code still ships in the prod binary. Move DevSeed/BootstrapV2 dev helpers behind a compilation symbol (e.g. #if DEBUG or a Dev-only project) so they are not compiled into the Release artifact, and add a build-time assertion. | A test scans the Release-built PlantProcess.Api.dll and asserts no DevSeed endpoint type/route is present; a Release run returns 404 for the dev-seed route; Debug still exposes it. | hardening | 8
T-011 | Remove the bootstrap-admin path after first-run provisioning | Phase 02 | Security | Backend | Identity | Very Important | After the first tenant owner is created via /provisioning/claim, the configured bootstrap admin must be disabled. Add a one-time flag so the bootstrap credentials cannot authenticate once a real owner exists; keep the collision-detection guard. | Test: after provisioning an owner, a login attempt with bootstrap credentials is rejected; before provisioning it still works exactly once. | hardening | 8
T-012 | Add a CI secret-scan gate on the whole tree | Phase 02 | Security | Infrastructure | CI/Secrets | Very Important | Wire the existing Invoke-SecretScan into Jenkins as a blocking stage covering source + config (not just runtime), with an allowlist for masked placeholders. Document the per-env secret-injection contract (SigningKey, connection string). | A planted fake secret fails CI; the clean tree passes; appsettings.json prod still has empty ConnectionStrings + env-injected SigningKey (no literal). | hardening | 6
T-013 | Configure encryption-at-rest for the database volume | Phase 02 | Security | Infrastructure | Deployment | Important | Enable encryption at rest for the Postgres data volume (LUKS/host-level or managed-disk encryption) and document key custody. Confirm backups are encrypted too. | Runbook step verified on the server; a restored backup is unreadable without the key; documented key-rotation procedure. | hardening | 6
T-014 | Phase-2 security tests & deploy | Phase 02 | Testing | Testing | Security | Critical | Add a deep auth-matrix E2E: enumerate roles x MFA-state x endpoints and assert the expected allow/deny. Re-run the full suite; fix regressions. | Auth-matrix E2E green across all role/MFA combinations; full suite green; deploy boots and an admin must pass MFA to reach admin pages. | test | 8
Phase 03 — Deployment Hardening & Network Posture (Wave A) · Wave A · Safe · 51 h / 6 tasks · Closes G9(start), G12 · DEPLOY: DB port closed, one canonical pipeline, read-only DB role live. The deployment itself is now defensible.
T-015 | Close the exposed Postgres port on the server | Phase 03 | Security | Deploy | Network | Critical | On 178.105.152.180, bind Postgres to 127.0.0.1 / the internal Docker network only and remove any host port publish; add a host firewall rule (ufw) denying 5432 externally. This is a server-side change, not a repo push. | External `psql -h 178.105.152.180 -p 5432` times out / is refused; the app (same host/network) still connects; documented in the deploy runbook. | hardening | 8
T-016 | Establish a single canonical Caddyfile and compose per environment | Phase 03 | Hardening | Deploy | Config | Very Important | Consolidate the 4 Caddyfile variants into one canonical source (with HSTS/CSP) and the 7 docker-compose files into a clear base + per-env override set. Delete stubs. Document which file the pipeline deploys. | Only one canonical Caddyfile and a documented compose set remain; a header test confirms HSTS + CSP on the deployed site; the pipeline references exactly one compose path. | refactor | 8
T-017 | Collapse to one canonical Jenkinsfile | Phase 03 | Hardening | Deploy | CI/Jenkins | Important | Two Jenkinsfiles exist (591 lines total). Keep one canonical pipeline (backup .env/Caddyfile/compose -> reset -> restore -> build -> test -> deploy) and delete the duplicate. | Repo has exactly one Jenkinsfile; a triggered build runs the full stage list green; the config-backup/restore stage is verified to preserve server-side .env. | refactor | 5
T-018 | Introduce a least-privilege read-only DB role for query/preview | Phase 03 | Security | Database | Roles | Very Important | Create a dedicated read-only Postgres role and run all widget-script / preview / advanced-analysis queries under it (separate connection string / NpgsqlDataSource), as defense-in-depth behind SafeSqlValidator. | Integration test: a widget-preview query executed as the read-only role cannot INSERT/UPDATE/DELETE (permission denied) even if SafeSqlValidator were bypassed; normal read queries succeed. | hardening | 12
T-019 | Author a clean-machine-to-login deploy runbook + script | Phase 03 | Ops | Deploy | Runbook | Important | Write a runbook + idempotent script that takes a clean host to a working login (provision -> env -> compose up -> migrate -> health). This is the G9 acceptance fixture. | On a fresh VM, following only the runbook reaches a working login; a reviewer who has never seen the system succeeds; health + readiness endpoints return OK. | new feature | 10
T-020 | Phase-3 deployment validation & deploy | Phase 03 | Testing | Testing | Ops | Very Important | Add a post-deploy smoke that hits health, readiness, login, and a dashboard over HTTPS; verify the DB port is closed from outside; re-run full suite. | Post-deploy smoke green; external DB-port probe fails; full suite green; documented deploy. | test | 8
Phase 04 — Tenant Context & Multi-Tenancy Hardening (Refactor) · Wave Refactor · 46 h / 5 tasks · Closes G5(start) · DEPLOY: One central tenant resolver, real 2-tenant isolation proven. The enterprise multi-tenant claim becomes true.
T-021 | Build a central ITenantContextAccessor + middleware | Phase 04 | Backend | Backend | Multi-tenancy | Critical | Create ITenantContextAccessor in Application and an Infrastructure implementation resolved once per request from the JWT tenant_id claim, set the app.current_tenant GUC there, and reject (401/403) on a missing/invalid claim. Register via AddApplication/AddInfrastructure. | Unit tests cover resolve-from-claim, missing-claim-401, invalid-guid-401; one integration test confirms the GUC is set exactly once per request. | new feature | 12
T-022 | Replace the 15 duplicated ResolveTenantId helpers | Phase 04 | Refactor | Backend | Multi-tenancy | Very Important | Delete the private ResolveTenantId/DefaultTenantId/SetTenantGuc copies in the 15 V5 endpoint files and the 26 hardcoded demo GUIDs; consume ITenantContextAccessor instead. No endpoint should hardcode a tenant. | grep finds 0 'private static Guid DefaultTenantId' and 0 inline ResolveTenantId in endpoints; all endpoints compile against the accessor; route behaviour unchanged for a valid tenant. | refactor | 10
T-023 | Seed a second tenant for isolation testing | Phase 04 | Database | Database | Seed/Test | Important | Add a second tenant + users to the test/demo seed so cross-tenant isolation can actually be exercised (today everything is the single demo tenant). | Seed creates tenant B with its own rows; a query under tenant A's GUC returns zero of tenant B's rows. | new feature | 6
T-024 | Write the 2-tenant RLS isolation integration test (G5 fixture) | Phase 04 | Testing | Backend | RLS | Critical | Log in as a user of tenant A and a user of tenant B; assert each can read/write only its own rows on every tenant-scoped table, and that a forged tenant claim yields 403/empty. This is the G5 cross-tenant acceptance fixture. | Test proves: A cannot see B's data on every RLS table; cross-tenant access returns 403/empty; RLS is enforced at the DB even if app code errs. | test | 10
T-025 | Phase-4 regression sweep & deploy | Phase 04 | Testing | Testing | Regression | Very Important | Re-run all suites (the tenant refactor touches many endpoints); fix regressions; verify the demo still works as tenant A. | Full suite green incl. the new isolation test; demo unaffected; deploy boots; an admin of tenant A sees only tenant A. | test | 8
Phase 05 — God-File Decomposition: Backend + SQL Relocation (Refactor) · Wave Refactor · 50 h / 5 tasks · Closes G2, G10 · DEPLOY: The 4 backend mega-files genuinely split; SQL out of the API layer. Quality gate becomes honest.
T-026 | Genuinely split GenericSchemaMappingEndpoints (1,388L) | Phase 05 | Refactor | Backend | Schema-Mapping | Very Important | Decompose GenericSchemaMappingEndpoints.runtime.cs by responsibility into a thin route-registration file + focused handlers + an Infrastructure query service; delete the .runtime shim. No 1:1 rename — real reduction (<300L per file). | No file in this area exceeds 300 lines; the .runtime sibling is gone; all schema-mapping routes return identical responses (contract snapshot test green); unit tests cover the new query service. | refactor | 12
T-027 | Split Phase1WorkflowTruthEndpoints (1,368L) and WorkflowEndpoints (1,031L) | Phase 05 | Refactor | Backend | Workflow | Very Important | Same treatment for the two workflow mega-files: thin route files + handlers + services; delete .runtime shims; move embedded SQL into Infrastructure query services behind Application interfaces. | Each resulting file <300L; route-contract snapshot unchanged; workflow E2E still green. | refactor | 12
T-028 | Split ConnectorConfigurationService (1,246L) | Phase 05 | Refactor | Backend | Connectors | Important | Decompose the connector config service into cohesive services (config CRUD, validation, secret handling); delete the .runtime shim. | Files <300L; connector config behaviour unchanged; ConnectorConfigurationService tests pass. | refactor | 8
T-029 | Finish Pack-4 SQL relocation out of the API layer | Phase 05 | Refactor | Backend | Architecture | Very Important | Relocate the remaining ~283 SQL lines across 27 API endpoint files into Infrastructure query services behind Application interfaces (NpgsqlDataSource injected). API endpoints must contain no SQL string literals. | grep finds 0 SELECT/INSERT/UPDATE/DELETE literals in /PlantProcess.Api; an Architecture.Tests rule fails the build if SQL appears in the API layer; endpoints behave identically. | refactor | 10
T-030 | Phase-5 backend regression sweep & deploy | Phase 05 | Testing | Testing | Regression | Very Important | Heavy refactor -> run dotnet test + route-contract snapshot + e2e; fix regressions. | Full backend suite + contract snapshot green; no route changed signature; deploy boots clean. | test | 8
Phase 06 — God-File Decomposition: Frontend + Gate Reconciliation (Refactor) · Wave Refactor · 49 h / 6 tasks · Closes G6(start), G10 · DEPLOY: Frontend mega-files split; ONE honest size gate; strict TS everywhere. The 'no-85%' quality bar (G10) is real.
T-031 | Split AdminDbConfigurationTab (1,127L) & AdminSchemaConfigurationTab (948L) | Phase 06 | Refactor | Frontend | Admin | Very Important | Decompose the two Admin tab god-files into a container + presentational subcomponents + hooks; delete the .runtime/.implementation shims. Real reduction, not a rename. | No file in this area >300L; the shims are gone; the Admin tabs render and behave identically (E2E green); no prop/contract change. | refactor | 12
T-032 | Split MaterialAnalyticsPages (1,102L) and App.implementation (767L) | Phase 06 | Refactor | Frontend | Pages/Shell | Important | Same for MaterialAnalyticsPages.runtime.tsx and App.implementation.tsx; extract routes/sections into focused modules. | Files <300L; shims removed; app shell + material analytics E2E green. | refactor | 10
T-033 | Collapse the 4-hop WidgetBuilder re-export chain | Phase 06 | Refactor | Frontend | Widget-Builder | Normal | Reduce WidgetBuilderWizard.tsx -> .implementation -> Content.tsx -> .implementation -> orchestrator to a single wrapper -> orchestrator hop; delete intermediate .implementation shims. | Import depth is 1 hop; tsc + build clean; the widget builder works unchanged in E2E. | refactor | 5
T-034 | Reconcile to ONE file-size gate with no baseline escape hatch | Phase 06 | Hardening | Frontend | CI/Quality | Very Important | Merge check-file-size-complexity.cjs and the broader god-file policy into one gate that FAILS on any non-test source file >700L, with no per-file baseline exemption for relocated files. Remove phase56-file-size-baseline.json escape entries for .runtime files. | The single gate fails on a planted 800-line file; the repo passes only because the files are genuinely small now; CI blocks any new god-file. | refactor | 8
T-035 | Enable TS strict everywhere + Directory.Build.props warnings-as-errors | Phase 06 | Hardening | Frontend | Type-safety | Important | Set strict:true in every tsconfig (currently inconsistent) and add a Directory.Build.props enabling TreatWarningsAsErrors + AnalysisLevel:latest for all .csproj; fix the resulting warnings (incl. driving the 13 'as any' toward 0). | tsc --strict clean across the FE; dotnet build with warnings-as-errors succeeds with 0 warnings; 'as any' count documented and minimised. | hardening | 6
T-036 | Phase-6 frontend regression sweep & deploy | Phase 06 | Testing | Testing | Regression | Very Important | Run npm run build + npm run test + npm run e2e + visual snapshots; fix regressions from the split. | All FE suites + visual snapshots green; no UI regression; deploy boots; pages look/behave identical. | test | 8
Phase 07 — Value Engine Depth (Wave B) · Wave B · Valuable · 52 h / 5 tasks · Closes G5, G4(start) · DEPLOY: The euro value engine reproduces the doctrine's worked case with drill-through. The commercial story becomes provable.
T-037 | Expand ValueImpactEngine to full bounded ranges with abstain | Phase 07 | AI+ML | Backend | Value-Engine | Critical | Grow ValueImpactEngine beyond the 59-line MVP to compute bounded euro ranges (low/expected/high) from named, versioned assumptions, with an explicit abstain output when a required assumption is missing (per doctrine 7.5). Persist inputs via NpgsqlValueImpactRepository so every figure is drill-throughable. | Unit tests: a complete assumption set yields a bounded range; a missing assumption yields abstain (not a fabricated number); ranges are monotonic (low<=expected<=high). | new feature | 16
T-038 | Reproduce the EUR 28k-56k worked case as a fixture | Phase 07 | AI+ML | Backend | Value-Engine | Very Important | Encode the doctrine's worked edge-crack finding (EUR 28k-56k/month on one defect driver) as a deterministic acceptance fixture over the demo data; every input must trace to a provenance handle. | The fixture reproduces the EUR 28k-56k range exactly from seeded data; changing one input changes the range predictably; the assistant can cite each input. | test | 10
T-039 | Implement value-realization / tracked-ROI recording | Phase 07 | AI+ML | Backend | Value-Engine | Important | Add the ability to mark a suggestion as actioned and track realized vs projected euro impact over a period (foundation for the +packs ROI tracking). | A suggestion moved to 'validated' records a realized-value entry; a report shows projected vs realized per period; RBAC enforced. | new feature | 10
T-040 | Wire the value engine into the HMI scenario page | Phase 07 | Frontend | Frontend | Scenario-Sim | Important | Connect P15 ScenarioSimulationPage to the deepened engine so a user adjusts assumptions and sees the bounded range + abstain live, with drill-through to inputs. | E2E: adjusting an assumption updates the range; removing a required input shows the abstain state with a clear reason; drill-through opens the inputs. | new feature | 8
T-041 | Phase-7 value tests & deploy | Phase 07 | Testing | Testing | AI+ML | Very Important | Add deep value-engine tests (boundary, abstain, monotonicity, provenance) + re-run suites. | Value tests green incl. the EUR 28k-56k fixture; full suite green; deploy shows a working euro-value scenario on the demo plant. | test | 8
Phase 08 — Correlation Engine Certification (Wave B) · Wave B · Valuable · 48 h / 5 tasks · Closes G4 · DEPLOY: L4 statistics proven on a golden dataset under FDR. The 'credible advanced analysis' claim is earned.
T-042 | Add VIF / multicollinearity handling to the engine | Phase 08 | AI+ML | Backend | Correlation | Very Important | Confirm/implement Variance Inflation Factor pruning in AdvancedCorrelationComputeService (doctrine lists VIF; the others - Spearman, MI, Lasso, BH-FDR, bootstrap - are present). Drop or flag collinear features before ranking. | Unit test: a deliberately collinear feature pair is detected (VIF over threshold) and handled; effect ranking is stable afterward. | new feature | 10
T-043 | Build the golden-dataset signal-recovery fixture (G4) | Phase 08 | AI+ML | Backend | Correlation | Critical | Create a synthetic dataset with known true drivers + injected spurious correlations; assert the engine recovers the true signals and rejects the spurious ones under FDR (Benjamini-Hochberg), with bootstrap stability above threshold. | The fixture recovers >=N true signals, rejects all injected spurious ones at the configured FDR q, and reports stability; re-runs are deterministic (seeded). | test | 12
T-044 | Surface population, stratification & exclusions on every finding | Phase 08 | AI+ML | Backend | Correlation | Very Important | Ensure each AdvancedFinding reports its population (N), the confounders stratified on, and exclusions/dropped rows (doctrine G15 honesty). Block any finding that cannot state its population. | Every finding object carries population + stratification + exclusions; a finding lacking population is not emitted; UI shows them. | new feature | 10
T-045 | Expose readiness gates (Ready/Partial/Blocked) in the API + HMI | Phase 08 | AI+ML | Frontend | Readiness | Important | Surface the existing readiness gating so a user sees whether an advanced analysis is Ready, Partial, or Blocked and why (data sufficiency). | E2E: an under-powered outcome shows Blocked with a reason; a sufficient one shows Ready and runs; matches the engine's MinorityFraction/readiness logic. | new feature | 8
T-046 | Phase-8 statistics tests & deploy | Phase 08 | Testing | Testing | AI+ML | Very Important | Run the now-registered P06 statistical + golden-gate tests in CI + the new fixtures; fix any flakiness; document FDR behaviour. | Golden-gate + statistical suites green in CI; FDR signal-recovery fixture green; deploy shows a real advanced-analysis result with population + method on the demo data. | test | 8
Phase 09 — Suggestions & Assistant Grounding Certification (Wave B) · Wave B · Valuable · 52 h / 4 tasks · Closes G4, G13(start) · DEPLOY: Suggestions + a grounded assistant that emits no uncited number, gated by an eval harness.
T-047 | Harden & certify the deterministic suggestion workflow | Phase 09 | AI+ML | Backend | Suggestions | Very Important | With SuggestionEngineTests now running, extend coverage: MD5-stable IDs, confidence, ranged impact, dedup, and the assign/accept/reject/close RBAC state machine. | Suggestion tests green; the same inputs produce identical suggestion IDs; an unauthorized role cannot transition a suggestion. | test | 10
T-048 | Wire the assistant grounding eval harness as a regression gate | Phase 09 | AI+ML | Backend | Assistant/Grounding | Critical | Turn the assistant evaluation into a CI gate: a fixed prompt set asserts the assistant emits no uncited number and no unsupported causal claim (GroundingService), and blocks the build on regression. | The eval gate fails if a response contains an uncited figure or a causal phrase without evidence; the clean model passes; GroundingContractTests run in CI. | new feature | 16
T-049 | Prove the model gateway's 3 serving modes + no-egress toggle (G13) | Phase 09 | AI+ML | Backend | Model-Gateway | Very Important | Demonstrate self-hosted (no egress), private zero-retention endpoint (sends only question + scoped evidence), and BYO model, plus a per-tenant no-egress toggle, in V5PrivateModelGatewayCertification. | Tests: self-hosted mode makes zero outbound calls (network assertion); private-endpoint payload contains only question + scoped evidence (no raw plant rows); the no-egress toggle blocks egress when set. | new feature | 16
T-050 | Phase-9 AI regression sweep & deploy | Phase 09 | Testing | Testing | AI+ML | Very Important | Run all AI/ML suites + the eval gate + e2e of the assistant; fix regressions. | All AI suites + eval gate green; assistant answers a demo question with citations and refuses to invent a number; deploy shows the grounded assistant. | test | 10
Phase 10 — Connector Certification & Historian GA (Wave C) · Wave C · Provable · 52 h / 4 tasks · Closes G1 · DEPLOY: Connectors behaviourally certified + one historian GA. Buyers can connect their own data with confidence.
T-051 | Per-connector behavioural + failure tests (credential safety) | Phase 10 | Hardening | Backend | Connectors | Very Important | For each connector (CSV, Excel, MSSQL, MySQL) add behavioural tests: test-before-save, masked secret on read-back, staging into source-shaped tables, import-batch lifecycle, and failure handling. | For every connector: a saved credential never appears on read-back; a bad credential fails test-before-save; a malformed import is rejected with a typed error and rolled back. | test | 14
T-052 | Certify one historian (OPC-UA or PI) to GA | Phase 10 | Features | Backend | Connectors/Historian | Critical | Implement and certify a first time-series historian connector to GA quality (honest availability, staging, backfill), per doctrine 4.7. | The historian connector ingests a representative tag set into staging; a behavioural test proves read-only access + backfill; the availability matrix marks it GA honestly. | new feature | 20
T-053 | Honest connector availability matrix in the HMI | Phase 10 | Frontend | Frontend | Connectors | Important | Show each connector's real status (GA / beta / planned) in the UI per the honesty contract; no 'live' claim for uncertified sources. | UI reflects the certified status exactly; an uncertified source is labelled beta/planned; matches Appendix E forbidden-claims rules. | new feature | 8
T-054 | Phase-10 connector tests & deploy | Phase 10 | Testing | Testing | Connectors | Very Important | Run connector behavioural + failure suites + e2e of an import; fix regressions. | All connector suites green; an end-to-end import from a file + the historian works in E2E; deploy shows connecting + importing a source. | test | 10
Phase 11 — OT-Safe Edge Collector Depth (Wave C) · Wave C · Provable · 52 h / 4 tasks · Closes G11 · DEPLOY: Edge Collector enforces one-way push within a measured source-impact budget. IT/OT can approve it.
T-055 | Enforce and prove one-way push (no inbound OT path) | Phase 11 | Hardening | Backend | Edge-Collector | Critical | Harden OtSafeEdgeCollectorGateway so the core never initiates a connection into OT - the collector pushes one-way only. Add a data-diode-compatible mode. | A test/architecture check proves the core opens zero inbound connections to OT; the collector's push path is the only data flow; documented for an IT/OT reviewer. | new feature | 16
T-056 | Measure and enforce the source-impact budget | Phase 11 | Engine | Backend | Edge-Collector | Very Important | Implement a measured source-impact budget (query rate / load ceiling) with CDC/replica preference over polling, and back off when the budget is exceeded. | A load test shows source impact stays within the configured budget; exceeding it triggers backoff; CDC/replica path is preferred when available. | new feature | 14
T-057 | Package the Edge Collector for DMZ deployment | Phase 11 | Deploy | Infrastructure | Edge-Collector | Important | Produce a deployable collector artifact (container + config) suitable for the customer DMZ, with health + secure registration to the core. | The collector deploys from the artifact, registers securely, and streams to the core; a clean-machine runbook covers it. | new feature | 12
T-058 | Phase-11 edge tests & deploy | Phase 11 | Testing | Testing | Edge-Collector | Very Important | Add one-way/no-inbound + budget tests + an e2e of collector->staging; fix regressions. | Edge suites green; an end-to-end collector->staging flow works; deploy demonstrates the collector pushing data one-way. | test | 10
Phase 12 — Schema-Drift & Mapping Health (Wave C) · Wave C · Provable · 50 h / 4 tasks · Closes G2 · DEPLOY: Upstream drift pauses dependent mappings with a typed reason; a health panel shows what broke and why.
T-059 | Snapshot upstream schema + detect drift | Phase 12 | Engine | Backend | Schema-Drift | Very Important | Extend SchemaDriftDetector to snapshot source schemas and detect drift (added/removed/retyped columns) on a schedule. | Introducing a column change is detected and recorded with a typed drift event; no false positives on an unchanged schema. | new feature | 14
T-060 | Typed pause of dependent mappings on drift | Phase 12 | Backend | Backend | Mapping | Very Important | When drift affects a mapping's inputs, pause that mapping with a typed reason instead of producing a silently wrong number (doctrine 4.9). | A drift that breaks a mapping pauses it with a typed reason; downstream widgets show 'paused', never a wrong value; resolving the drift resumes it. | new feature | 14
T-061 | Complete the Mapping Health panel | Phase 12 | Frontend | Frontend | Mapping-Health | Important | Finish Phase34MappingHealthEndpoints + MappingHealthPage so a user sees every mapping's health, what broke, and why. | E2E: the panel lists healthy/paused mappings with reasons; a paused mapping links to the drift cause. | new feature | 12
T-062 | Phase-12 drift tests & deploy | Phase 12 | Testing | Testing | Mapping | Very Important | Add drift-detection + typed-pause + health-panel tests; fix regressions. | Drift suites green; an injected drift visibly pauses a mapping and surfaces in the panel; deploy demonstrates the drift loop. | test | 10
Phase 13 — Genealogy, Coverage & Blended Provenance (Wave C) · Wave C · Provable · 50 h / 4 tasks · Closes G15, G2 · DEPLOY: Every finding states its population; transition coils report weighted multi-heat attribution.
T-063 | Build the data-coverage panel | Phase 13 | Frontend | Frontend | Coverage | Important | Add a coverage panel showing linkage completeness and what fraction of material is genealogy-linked vs orphaned (doctrine 5.4). | E2E: the panel shows coverage % and lists unlinked/ambiguous material; numbers match the seeded imperfection. | new feature | 12
T-064 | Implement blended-provenance weighting for transition coils | Phase 13 | Engine | Backend | Genealogy | Very Important | For casting-transition material from two heats, compute weighted multi-heat attribution rather than a single-heat answer (doctrine 5.3). | A transition coil reports weighted attribution across both heats summing to 1.0; a single-heat coil reports 100% one heat; verified on seeded transition material. | new feature | 16
T-065 | Enforce population + exclusions on every analysis output | Phase 13 | AI+ML | Backend | Honesty | Very Important | Make population + exclusions mandatory on every surfaced analysis/KPI (extends Phase 08 to KPIs and simple analysis). | Any analysis/KPI without a stated population is blocked; the UI shows population + exclusions everywhere. | hardening | 12
T-066 | Phase-13 genealogy tests & deploy | Phase 13 | Testing | Testing | Genealogy | Very Important | Add coverage + blended-provenance + population-enforcement tests; fix regressions. | Genealogy/coverage suites green; a transition coil demonstrably shows weighted provenance; deploy shows coverage + honest population. | test | 10
Phase 14 — Demo-Through-HMI (Wave C) · Wave C · Provable · 56 h / 4 tasks · Closes G3, G7 · DEPLOY: The full 8-source demo built from empty entirely through the HMI - no hardcoding. The product proves itself.
T-067 | Build the 8-source, 13-area dataset config through the HMI | Phase 14 | Demo | Frontend | Demo | Critical | Using only the HMI (no hardcoded pages/widgets), configure the 8 demo sources (MeltShop, Caster, HSM, PKL, Yard, Downtime, Surface, QA) and 13 plant areas per Appendix A, with deliberate imperfection (missing links, ambiguous keys, transition/uninspected coils). | A reviewer rebuilds the demo from empty using only the HMI; no hardcoded page/widget is used (verified by an ESLint/route check); the dataset honours the realism parameters (≈630 heats/mo, ≈5,600 coils/mo). | new feature | 20
T-068 | Implement reset + rebuild via product workflows | Phase 14 | Demo | Backend | Demo | Very Important | Finish the reset job so the demo can be torn down and rebuilt entirely through product workflows; seeded rows tagged; learning jobs recompute live. | A reset + rebuild dry-run completes through workflows only; seeded rows are tagged; jobs recompute after rebuild. | new feature | 14
T-069 | One-click readiness check | Phase 14 | Demo | Frontend | Demo | Important | Add a one-click demo-readiness check that verifies sources connected, mappings healthy, jobs run, and key dashboards render. | The readiness check passes on a good demo and fails with a clear reason on a broken one; matches G7's measurable exit. | new feature | 12
T-070 | Phase-14 demo dry-run test & deploy | Phase 14 | Testing | Testing | Demo | Critical | Record a clean dry-run (the G7 fixture); add an e2e that walks the HMI build path; fix regressions. | Recorded clean dry-run exists; the readiness check is green; deploy shows the full demo, built the real way, on the server. | test | 10
Phase 15 — Accessibility & Light Theme (Wave D) · Wave D · Enterprise-ready · 50 h / 4 tasks · Closes G14(start) · DEPLOY: WCAG 2.1 AA on a contrast-audited light theme. The product clears accessibility procurement.
T-071 | Pass a full WCAG 2.1 AA audit | Phase 15 | UI/UX | Frontend | Accessibility | Very Important | Audit and fix the app to WCAG 2.1 AA: contrast, focus order, keyboard nav, ARIA, skip links, reduced-motion. Build on phase56ThemeRuntime + the contrast gate. | An automated a11y audit (axe) reports 0 serious/critical violations on every primary page; keyboard-only navigation reaches every action; the a11y E2E covers it. | hardening | 16
T-072 | Ship the contrast-audited light theme | Phase 15 | UI/UX | Frontend | Theming | Important | Complete the light theme using the Appendix C tokens (Light Grey #F4F6F8 surface) with audited contrast, switchable at runtime. | Light theme meets AA contrast on all text/controls; theme switch persists per user; visual snapshots pass in both themes. | new feature | 14
T-073 | Reduced-motion / focus / skip-link completeness | Phase 15 | UI/UX | Frontend | Accessibility | Normal | Ensure prefers-reduced-motion, visible focus, and skip-to-content work on every page. | Reduced-motion disables non-essential animation; focus is visible everywhere; skip link works on every page (E2E). | modification | 10
T-074 | Phase-15 a11y tests & deploy | Phase 15 | Testing | Testing | Accessibility | Very Important | Run axe + a11y E2E in both themes; fix regressions. | 0 serious a11y violations in CI; both-theme visual snapshots green; deploy shows an accessible light + dark UI. | test | 10
Phase 16 — i18n / RTL / Localization (Wave D) · Wave D · Enterprise-ready · 50 h / 4 tasks · Closes G14 · DEPLOY: First-class English, German and Arabic (RTL), with per-user units/timezone. The MENA story is real.
T-075 | Complete Arabic content + RTL rendering | Phase 16 | Web | Frontend | i18n/RTL | Very Important | Build out Arabic translations and verify full RTL layout on every page using phase78I18nRuntime + the RTL CSS; mirror layouts correctly. | Switching to Arabic renders RTL on every page without layout breakage (E2E + visual); all visible strings are translated (no missing-key fallbacks). | new feature | 16
T-076 | Complete German localization | Phase 16 | Web | Frontend | i18n | Important | Provide German translations for all UI strings. | German shows no missing-key fallbacks; an i18n lint asserts key parity across en/de/ar. | new feature | 12
T-077 | Per-user units & timezone | Phase 16 | Frontend | Frontend | Localization | Important | Implement per-user unit (metric) and timezone selection; format all values/timestamps accordingly (plant TZ Europe/Berlin default). | Changing a user's timezone/units reformats values app-wide; tests cover formatting at boundaries (DST, large numbers). | new feature | 12
T-078 | Phase-16 i18n tests & deploy | Phase 16 | Testing | Testing | i18n | Very Important | Add i18n parity + RTL visual + units/timezone tests; fix regressions. | Key-parity lint green for en/de/ar; RTL visual snapshots green; deploy shows the app in Arabic RTL. | test | 10
Phase 17 — UX Completeness, Performance & Collaboration (Wave D) · Wave D · Enterprise-ready · 52 h / 4 tasks · Closes G6 · DEPLOY: No dead buttons anywhere, latency within budget, concurrent editing handled. Best-in-class modern UX.
T-079 | Enumerate the full action matrix - no dead button (G6) | Phase 17 | UI/UX | Frontend | UX | Very Important | Build an action-matrix test that enumerates every page x action and asserts each is wired (no dead/placeholder buttons), reusing the ESLint no-forbidden-phrase rule. | The action-matrix test is green by enumeration; a deliberately-unwired button fails it; every page passes. | test | 12
T-080 | Enforce performance budgets + load test | Phase 17 | Engine | Frontend | Performance | Important | Set and enforce the doctrine 8.5 latency budgets; load-test key pages/queries at realism scale; fix the worst offenders (note: the former god-file bundles). | Key interactions meet the budget under load; a CI perf check fails on regression beyond the budget. | hardening | 14
T-081 | Optimistic concurrency + conflict dialog + presence | Phase 17 | Frontend | Frontend | Collaboration | Important | Implement optimistic concurrency for dashboard editing with a clear conflict dialog, live presence, and immutable published versions (doctrine 8.9). | Two simultaneous editors get a conflict dialog (no silent overwrite); published versions are immutable; presence shows who is editing (E2E with two sessions). | new feature | 16
T-082 | Phase-17 UX/perf tests & deploy | Phase 17 | Testing | Testing | UX | Very Important | Run action-matrix + perf + concurrency E2E; fix regressions. | Action-matrix + perf + concurrency suites green; deploy shows fast, complete, collaboration-safe UX. | test | 10
Phase 18 — Operations, DR & Observability (Wave D) · Wave D · Enterprise-ready · 50 h / 4 tasks · Closes G9 · DEPLOY: Measured backup/restore, runbooks, monitoring. The system is operable and recoverable.
T-083 | Backup + restore drill with measured RPO/RTO | Phase 18 | Ops | Infrastructure | DR | Very Important | Implement scheduled encrypted backups and a documented restore drill; measure and record RPO/RTO. | A restore from backup reaches a working system; measured RPO/RTO are recorded and meet the stated target; the drill is repeatable from the runbook. | new feature | 16
T-084 | Monitoring, alerting & structured logging | Phase 18 | Ops | Infrastructure | Observability | Important | Add health/readiness dashboards, alerting on key SLOs, and structured logs with correlation IDs (Serilog is already in place). | An induced failure fires an alert; logs are queryable by correlation ID; health/readiness reflect real state. | new feature | 14
T-085 | Incident runbooks + sizing guide | Phase 18 | Documentation | Documentation | Ops | Normal | Write incident runbooks (DB down, disk full, cert expiry, collector offline) and the Appendix G sizing guide. | A reviewer resolves a simulated incident using only the runbook; sizing guide covers pilot/full-plant/multi-site. | new feature | 12
T-086 | Phase-18 ops tests & deploy | Phase 18 | Testing | Testing | Ops | Very Important | Add restore-drill + health/alert tests; fix regressions. | Restore-drill test green; alerts verified; deploy demonstrates monitoring + a successful restore. | test | 8
Phase 19 — Compliance Controls & GxP Pack (Wave D) · Wave D · Enterprise-ready · 52 h / 4 tasks · Closes G16 · DEPLOY: SOC2/ISO control evidence + a GxP/21 CFR Part 11 pack. Regulated buyers can proceed.
T-087 | SOC 2 / ISO 27001 control mapping + evidence | Phase 19 | Documentation | Documentation | Compliance | Important | Map the implemented controls to SOC 2 / ISO 27001 and produce the evidence matrix (extends the existing CONTROL_EVIDENCE_MATRIX); identify gaps for external audit. | Every applicable control maps to evidence (or a tracked gap); a reviewer can trace a control to its proof; secure-SDLC evidence is captured. | new feature | 14
T-088 | GxP / 21 CFR Part 11 pack (audit trail + e-signature) | Phase 19 | Backend | Backend | Compliance/GxP | Very Important | Provide the GxP pack: immutable audit trail (build on the audit log), electronic signatures for regulated actions, and validation evidence. | A regulated action requires an e-signature and is recorded immutably; an auditor can reconstruct who-did-what-when; e-signature tampering is detectable. | new feature | 18
T-089 | GDPR data-subject + retention controls | Phase 19 | Backend | Backend | Compliance/GDPR | Important | Implement data-subject access/erasure handling and retention policies on personal data (build on the sensitive-data catalog). | A data-subject erasure request removes/anonymises the right records; retention policy purges per schedule; verified by test. | new feature | 12
T-090 | Phase-19 compliance tests & deploy | Phase 19 | Testing | Testing | Compliance | Very Important | Add audit-trail + e-signature + GDPR tests; fix regressions. | Compliance suites green; e-signature + immutable trail demonstrated; deploy shows the GxP audit trail. | test | 8
Phase 20 — Prescriptive-Advisory Pack (+Packs) · Wave +Packs · 48 h / 4 tasks · Closes Pack P15/P17 · DEPLOY: From 'here is a correlation' to 'here is the recommendation' - with human-approved write-back and tracked ROI.
T-091 | Recommendation engine over evidence-ranked findings | Phase 20 | AI+ML | Backend | Advisory | Very Important | Build a recommendation layer that turns evidence-ranked suspected contributors into concrete, human-readable recommendations - still read-only at the core (no autonomous control), each recommendation carrying its method + evidence. | A recommendation links to its finding, method, and bounded euro impact; no recommendation is emitted without evidence; honesty contract preserved (suspected, not guaranteed). | new feature | 16
T-092 | Human-approved advisory write-back (opt-in, audited) | Phase 20 | Backend | Backend | Advisory/Write-back | Very Important | Add an explicitly opt-in, human-approved write-back path (e.g. a setpoint suggestion sent to an external system) that is fully audited and never autonomous; default OFF. | Write-back requires explicit human approval + is fully audited; with the toggle OFF no write occurs; an unauthorized user cannot approve. | new feature | 14
T-093 | Tracked realized-ROI attribution dashboard | Phase 20 | AI+ML | Frontend | ROI | Important | Build the CFO-facing dashboard attributing realized euro value to actioned recommendations over time (extends Phase 07). | The dashboard shows projected vs realized euro per recommendation/period with drill-through; numbers reconcile to the value engine. | new feature | 10
T-094 | Phase-20 advisory tests & deploy | Phase 20 | Testing | Testing | Advisory | Very Important | Add recommendation + write-back-approval + ROI tests; fix regressions. | Advisory suites green; write-back is provably human-gated; deploy shows recommendations + a realized-ROI view. | test | 8
Phase 21 — Certification / SPC / PCF Reporting Pack (+Packs) · Wave +Packs · 54 h / 4 tasks · Closes Pack P16 · DEPLOY: Quality certificates, Cpk/Ppk SPC, and carbon-footprint along genealogy. Differentiating reporting.
T-095 | SPC engine (Cpk/Ppk, control charts) | Phase 21 | Engine | Backend | SPC | Very Important | Implement statistical process control: Cpk/Ppk capability indices and control charts over canonical quality data. | Cpk/Ppk match a hand-computed reference on a known sample; control charts flag out-of-control points correctly; tested. | new feature | 16
T-096 | PCF / CO2 tracking along the genealogy spine | Phase 21 | Engine | Backend | ESG/PCF | Important | Compute product carbon footprint by attributing emissions along the heat->slab->coil genealogy (green-steel reporting). | A coil's PCF is computed from its genealogy + emission factors; a transition coil uses blended provenance weights; reproducible on demo data. | new feature | 16
T-097 | Quality-certificate + report builder | Phase 21 | Web | Frontend | Reporting | Important | Build a certificate/report builder (quality certificates, SPC reports, PCF statements) with branded PDF output (Appendix C light report surface). | A user generates a branded quality certificate + SPC + PCF report as PDF; values trace to source; honesty-lint passes on claims. | new feature | 14
T-098 | Phase-21 reporting tests & deploy | Phase 21 | Testing | Testing | Reporting | Very Important | Add SPC + PCF + report-render tests; fix regressions. | SPC/PCF suites green; a branded certificate renders correctly; deploy shows certificate + SPC + PCF outputs. | test | 8
Phase 22 — Enterprise Integration Pack (+Packs) · Wave +Packs · 48 h / 3 tasks · Closes Pack P17 · DEPLOY: OPC-UA GA, more historians, ERP/LIMS/MES read. Fits an enterprise landscape.
T-099 | OPC-UA connector to GA | Phase 22 | Features | Backend | Integration/OPC-UA | Very Important | Implement and certify an OPC-UA connector to GA (read-only), with secure session handling and the source-impact budget. | OPC-UA reads a representative address space read-only; behavioural + failure tests pass; availability matrix marks it GA. | new feature | 18
T-100 | ERP / LIMS / MES read connectors | Phase 22 | Features | Backend | Integration | Important | Add read-only connectors for common ERP/LIMS/MES (e.g. SAP read, a LIMS, a generic MES) staging into source-shaped tables. | Each connector stages data read-only with masked secrets + failure tests; no write path exists; honesty matrix reflects status. | new feature | 20
T-101 | Phase-22 integration tests & deploy | Phase 22 | Testing | Testing | Integration | Very Important | Add OPC-UA + ERP/LIMS/MES behavioural/failure tests; fix regressions. | Integration suites green; an end-to-end read from each new source works; deploy shows the broadened connectivity. | test | 10
Phase 23 — HA / Scale / Resilience Pack (+Packs) · Wave +Packs · 46 h / 4 tasks · Closes Pack P18/P19 · DEPLOY: Multi-node HA, DR, chaos + soak, 99.95% SLO. Mission-critical readiness.
T-102 | Multi-node HA + failover | Phase 23 | Ops | Infrastructure | HA | Very Important | Move from single-node to multi-node HA (app + DB replication) with automatic failover. | Killing a node keeps the system available (failover under the target window); a chaos test proves no data loss; documented. | new feature | 16
T-103 | Multi-region DR + autoscaling | Phase 23 | Ops | Infrastructure | DR/Scale | Important | Add multi-region disaster recovery and horizontal autoscaling for workers/API. | A region-loss DR drill recovers within the target RTO; autoscaling adds/removes capacity under load; tested. | new feature | 14
T-104 | Chaos + 30-day soak + SLO/error-budgets | Phase 23 | Ops | Testing | Resilience | Very Important | Run chaos experiments and a 30-day soak; define SLOs + error budgets and alert on burn. | The soak runs 30 days without leak/degradation; chaos experiments are survived; SLO/error-budget dashboards + alerts are live. | test | 10
T-105 | Phase-23 resilience deploy | Phase 23 | Testing | Testing | Resilience | Very Important | Validate HA/DR/soak results; fix regressions; deploy the HA topology. | HA/DR drills documented green; deploy runs the multi-node topology with monitoring. | test | 6
Phase 24 — Fleet / Marketplace / Extensibility Pack (+Packs) · Wave +Packs · 48 h / 4 tasks · Closes Pack P20 · DEPLOY: Multi-plant fleet, public API + plugin SDK + marketplace, rapid onboarding. Scales as a platform.
T-106 | Multi-plant fleet dashboards + cross-plant roles | Phase 24 | Web | Frontend | Fleet | Important | Build fleet-level dashboards aggregating across plants/tenants with appropriate cross-plant/org roles and isolation. | A fleet user sees aggregated KPIs across plants while RLS still isolates per-plant detail; cross-plant roles enforced; tested. | new feature | 14
T-107 | Public API + webhooks + plugin SDK | Phase 24 | Backend | Backend | Extensibility | Very Important | Expose a documented public API + webhooks and a plugin SDK so third parties can extend PPIQ (config-driven today; open it up). | The public API is documented + versioned + auth'd; a sample webhook fires; a sample plugin loads via the SDK; contract tests pass. | new feature | 16
T-108 | Industry templates + rapid onboarding + in-app help | Phase 24 | Web | Frontend | Onboarding | Important | Provide industry templates, a guided onboarding flow, and in-app help to cut time-to-value. | A new tenant reaches first insight via templates + onboarding in days (measured); in-app help covers core flows. | new feature | 10
T-109 | Phase-24 platform tests & deploy | Phase 24 | Testing | Testing | Platform | Very Important | Add fleet-isolation + public-API contract + plugin tests; fix regressions. | Platform suites green; fleet isolation holds; a sample plugin works; deploy shows fleet + API + templates. | test | 8
Phase 25 — External Certs, Support & Viability Pack (+Packs) · Wave +Packs · 54 h / 4 tasks · Closes Pack P21 · DEPLOY: External SOC 2 Type II / ISO 27001 / IEC 62443 track, SLA support, escrow/BCP. De-risks the vendor.
T-110 | Drive external SOC 2 Type II / ISO 27001 / IEC 62443 | Phase 25 | Documentation | Documentation | Certs | Very Important | Engage and progress an external SOC 2 Type II + ISO 27001 audit and IEC 62443 readiness, using the Phase-19 evidence. | An external auditor accepts the evidence and the audit is in progress/achieved; IEC 62443 readiness documented; gaps tracked to closure. | new feature | 16
T-111 | SLA support tiers + ticketing + training/certification | Phase 25 | Web | Documentation | Support | Important | Stand up SLA-backed support tiers, a ticketing workflow, and a training/certification program (the support machinery 'Now' lacks). | Support tiers + SLAs are published; a ticket flows end-to-end with SLA timers; a training/cert path exists. | new feature | 16
T-112 | Escrow + BCP + partner program | Phase 25 | Documentation | Documentation | Viability | Important | Establish source-code escrow, a business-continuity plan, and a partner program to reduce single-vendor/lock-in risk. | Escrow agreement + BCP documented and tested (a continuity drill); partner onboarding exists; open-standards export documented. | new feature | 12
T-113 | Phase-25 final acceptance & signed pilot | Phase 25 | Testing | Testing | Acceptance | Critical | Run a full end-to-end acceptance against the doctrine gates on a real pilot environment; capture a signed pilot acceptance report (the genuine P15+ proof). | All 16 gates pass at 95-100% on the pilot env; a signed customer/pilot acceptance report exists; measured RPO/RTO + certified connectors recorded. | test | 10

## 02_Phase_Rollup
PHASE ROLL-UP — sequence, effort, deploy milestone & gates closed
# | Phase | Wave | Hours | Tasks | Cumul. h | Deploy milestone (what you can show) | Gates closed
1 | Phase 01 — Verification Foundation & Critical Bug Fixes | Pre-flight | 49 | 8 | 49 | Every authored test runs & is green; zero known defects. A demonstrably solid, honest baseline to build on. | G10, G4(start), G12(start)
2 | Phase 02 — Identity & Secret Hardening (Wave A) | A · Safe | 50 | 6 | 99 | Admin MFA enforced, dev-seed provably absent in prod, secrets env-only. Safe to put auth in front of a customer. | G12
3 | Phase 03 — Deployment Hardening & Network Posture (Wave A) | A · Safe | 51 | 6 | 150 | DB port closed, one canonical pipeline, read-only DB role live. The deployment itself is now defensible. | G9(start), G12
4 | Phase 04 — Tenant Context & Multi-Tenancy Hardening (Refactor) | Refactor | 46 | 5 | 196 | One central tenant resolver, real 2-tenant isolation proven. The enterprise multi-tenant claim becomes true. | G5(start)
5 | Phase 05 — God-File Decomposition: Backend + SQL Relocation (Refactor) | Refactor | 50 | 5 | 246 | The 4 backend mega-files genuinely split; SQL out of the API layer. Quality gate becomes honest. | G2, G10
6 | Phase 06 — God-File Decomposition: Frontend + Gate Reconciliation (Refactor) | Refactor | 49 | 6 | 295 | Frontend mega-files split; ONE honest size gate; strict TS everywhere. The 'no-85%' quality bar (G10) is real. | G6(start), G10
7 | Phase 07 — Value Engine Depth (Wave B) | B · Valuable | 52 | 5 | 347 | The euro value engine reproduces the doctrine's worked case with drill-through. The commercial story becomes provable. | G5, G4(start)
8 | Phase 08 — Correlation Engine Certification (Wave B) | B · Valuable | 48 | 5 | 395 | L4 statistics proven on a golden dataset under FDR. The 'credible advanced analysis' claim is earned. | G4
9 | Phase 09 — Suggestions & Assistant Grounding Certification (Wave B) | B · Valuable | 52 | 4 | 447 | Suggestions + a grounded assistant that emits no uncited number, gated by an eval harness. | G4, G13(start)
10 | Phase 10 — Connector Certification & Historian GA (Wave C) | C · Provable | 52 | 4 | 499 | Connectors behaviourally certified + one historian GA. Buyers can connect their own data with confidence. | G1
11 | Phase 11 — OT-Safe Edge Collector Depth (Wave C) | C · Provable | 52 | 4 | 551 | Edge Collector enforces one-way push within a measured source-impact budget. IT/OT can approve it. | G11
12 | Phase 12 — Schema-Drift & Mapping Health (Wave C) | C · Provable | 50 | 4 | 601 | Upstream drift pauses dependent mappings with a typed reason; a health panel shows what broke and why. | G2
13 | Phase 13 — Genealogy, Coverage & Blended Provenance (Wave C) | C · Provable | 50 | 4 | 651 | Every finding states its population; transition coils report weighted multi-heat attribution. | G15, G2
14 | Phase 14 — Demo-Through-HMI (Wave C) | C · Provable | 56 | 4 | 707 | The full 8-source demo built from empty entirely through the HMI - no hardcoding. The product proves itself. | G3, G7
15 | Phase 15 — Accessibility & Light Theme (Wave D) | D · Enterprise-ready | 50 | 4 | 757 | WCAG 2.1 AA on a contrast-audited light theme. The product clears accessibility procurement. | G14(start)
16 | Phase 16 — i18n / RTL / Localization (Wave D) | D · Enterprise-ready | 50 | 4 | 807 | First-class English, German and Arabic (RTL), with per-user units/timezone. The MENA story is real. | G14
17 | Phase 17 — UX Completeness, Performance & Collaboration (Wave D) | D · Enterprise-ready | 52 | 4 | 859 | No dead buttons anywhere, latency within budget, concurrent editing handled. Best-in-class modern UX. | G6
18 | Phase 18 — Operations, DR & Observability (Wave D) | D · Enterprise-ready | 50 | 4 | 909 | Measured backup/restore, runbooks, monitoring. The system is operable and recoverable. | G9
19 | Phase 19 — Compliance Controls & GxP Pack (Wave D) | D · Enterprise-ready | 52 | 4 | 961 | SOC2/ISO control evidence + a GxP/21 CFR Part 11 pack. Regulated buyers can proceed. | G16
20 | Phase 20 — Prescriptive-Advisory Pack (+Packs) | +Packs | 48 | 4 | 1009 | From 'here is a correlation' to 'here is the recommendation' - with human-approved write-back and tracked ROI. | Pack P15/P17
21 | Phase 21 — Certification / SPC / PCF Reporting Pack (+Packs) | +Packs | 54 | 4 | 1063 | Quality certificates, Cpk/Ppk SPC, and carbon-footprint along genealogy. Differentiating reporting. | Pack P16
22 | Phase 22 — Enterprise Integration Pack (+Packs) | +Packs | 48 | 3 | 1111 | OPC-UA GA, more historians, ERP/LIMS/MES read. Fits an enterprise landscape. | Pack P17
23 | Phase 23 — HA / Scale / Resilience Pack (+Packs) | +Packs | 46 | 4 | 1157 | Multi-node HA, DR, chaos + soak, 99.95% SLO. Mission-critical readiness. | Pack P18/P19
24 | Phase 24 — Fleet / Marketplace / Extensibility Pack (+Packs) | +Packs | 48 | 4 | 1205 | Multi-plant fleet, public API + plugin SDK + marketplace, rapid onboarding. Scales as a platform. | Pack P20
25 | Phase 25 — External Certs, Support & Viability Pack (+Packs) | +Packs | 54 | 4 | 1259 | External SOC 2 Type II / ISO 27001 / IEC 62443 track, SLA support, escrow/BCP. De-risks the vendor. | Pack P21
Σ | TOTAL — Now (~64) → +Packs full vision (~95) |  | 1259 | 113 | 1259