PlantProcess IQ

Independent Validation Report v2 — Status, Gaps, Recovery Plan

29 May 2026 — 17:41 snapshot vs. 4-Track Task List v2 + 4-Track Vision

Delta-on-delta validation against the 25 May Independent Validation Report

Confidential — SOU Industrial Software

# 1. Executive Summary

This report performs a code-level revalidation of the 4-Track v2 plan against the snapshot taken at 17:41 on 29 May 2026 (681 files, ~115,600 lines of code spanning Backend, Frontend, Website, Tests, Tools, Database scripts, Infrastructure). The same 106-task v2 list used in the 25 May audit is the unit of measurement; the same DONE / PARTIAL / MISSING verdict scheme is applied so the two reports diff cleanly.

The key finding is that the four calendar days between 25 May 17:00 and 29 May 17:41 produced only four committed file changes — all of them operational deployment work (Jenkinsfile production pipeline, audit-log immutability integration test, the test csproj, a placeholder README). No code change closed any v2 task that was PARTIAL or MISSING on 25 May. The platform's Track 1 / 2 / 3 / 4 status is therefore essentially identical to what the previous audit reported, with two operational additions on the deployment side.

### Headline numbers (29 May vs. 25 May)

| Metric | 25 May | 29 May | Delta |
| --- | --- | --- | --- |
| Total v2 tasks | 106 | 106 | — |
| Fully DONE | 13 | 13 | 0 |
| PARTIAL (in-flight) | 55 | 55 | 0 |
| MISSING (not started) | 29 | 29 | 0 |
| Total committed file changes in window | — | 4 | +4 |
| Severity-CRITICAL tasks closed | — | 0 | 0 |
| Founder's explicit non-negotiables closed | — | 0 | 0 |

### By track — overall completion against vision

| Track | Vision objective | Done | Partial | Missing | % complete |
| --- | --- | --- | --- | --- | --- |
| Track 1 — Workflow | Generic, end-to-end data lifecycle | 4 | 14 | 7 | 44% |
| Track 2 — Hardening | Demo-safe app, no surprises | 1 | 23 | 9 | 38% |
| Track 3 — Demo | Real customer-flow demo dataset + scripts | 4 | 8 | 9 | 36% |
| Track 4 — Website | Best-of-class first impression / lead-magnet | 4 | 10 | 4 | 50% |

### Vision alignment scoring

Each Track in the 4-Track Vision document was rated on a 0–10 scale against the spec the vision itself states. 0 means the vision has not been started; 10 means the vision is delivered demo-ready with no founder-named exceptions. This scoring is independent of the v2 task completion percentages above — it asks how the customer would experience each track today.

| Track | Vision spec (short) | Today's score | Critical gaps preventing 10/10 |
| --- | --- | --- | --- |
| 1 — Workflow | Generic DB connectors, schema mapping wizard, user-driven page/widget builder with script layer, ML correlation jobs, suggestions assistant, license-tier toggling, RBAC | 4.5 / 10 | Widget Script Layer absent; PageDefinition not built; License toggle hard-codes restart; Suggestions page absent; Demo Reset endpoint absent; Schema Mapping wizard read-only; full ML correlation engine descriptive-only |
| 2 — Hardening | No 'could not load' surprises; every button works; uniform style; standard table/button/tabs; responsive; no white-screens; widget filter/sort/heat-map work; pixel-perfect demo | 3.5 / 10 | 'Could not load' phrase still in 16 places; StandardButton / DataFetchBoundary in two paths; HeatMap widget absent; widget resize handles absent; site-wide audit-replace not done; full button matrix not catalogued |
| 3 — Demo | Real source-shaped DBs (6 containers), 1-month flat-steel dataset, ~630 heats / ~5,600 coils, persona accounts, technical + executive scripts, PDF report, recovery lines | 3 / 10 | No real Oracle / MSSQL / MySQL source containers; demo data lands in 5 named PG schemas only; demo scripts (technical + exec) not authored; persona accounts not seeded; PDF report not customer-branded; recovery lines absent |
| 4 — Website | Public DNS live, real screenshots, polished product pages for PPIQ + MES + QES + Energy + Yard, lead capture, brand-consistent identity, legal pages | 4 / 10 | DNS pending; hero still proof-component; MES / QES / Energy / Yard pages absent; inquiry uses mailto only (no backend); Calendly absent; Lighthouse / SEO baseline absent; no legal pages |

Weighted average against the founder's vision: 3.75 / 10. The headline interpretation is: the platform's backend backbone is real and quite advanced, but customer-facing demo-readiness has only partly caught up.

### The five highest-impact observations for this audit

1. Four-day output gap. Between the 25 May Independent Validation Report (17:00) and this snapshot (29 May 17:41), four files were committed: AuditLogImmutabilityTests.cs (271L), the new PlantProcess.Infrastructure.IntegrationTests.csproj, a 4-line placeholder README.md, and the production Jenkinsfile (173L). These are all deployment-track files. No v2 task in the PARTIAL or MISSING column moved to DONE. The platform is the same code; what changed is the ability to deploy it. Recovery action: the next 5 days need to clear the eight Severity-Critical PARTIAL items in Section 4 below.

2. The founder's #1 non-negotiable is still violated in 16 places. The forbidden phrase 'could not load' / 'could not be loaded' is present in: 12 withPageBoundary(...) fallback titles in App.tsx, 2 DataFetchBoundary.tsx components, and 2 inline error UIs. The 25 May report named exactly this issue; the four-day window did not address it. Recovery action: this is a 30-minute global find-and-replace plus copy redesign. It is the cheapest demo-blocking fix available and the highest-symbolism win for the founder's hardening rules. Done by tomorrow.

3. Two of the founder's largest sprint deliverables remain entirely unwired. The 25 May audit identified three orphan frontend components (Phase1WorkflowTruthPanel, SaveInspectionJobModal, OperationProgressPanel) built but not imported anywhere. A check of App.tsx imports today shows none of these are wired. The backend endpoints they consume are live; the UX exists; only the import statements and route placements are missing. Recovery action: approximately 6 hours of work delivers visible progress on PPIQ-WF-001 (Truth Matrix), PPIQ-WF-016 (Save as Inspection Job), and PPIQ-HARD-026 (Progress Bar).

4. The Widget Script Layer (T1-012 / T1-013 / T1-014) has moved unevenly. Script 113 (113_phase1_widget_script_layer.sql) quietly added seven new columns to dashboard_widget_definitions (query_expression, advanced_expression_json, expression_version, expression_enabled, expression_last_validated_at_utc, etc.) plus an audit table. That is meaningful progress on PPIQ-WF-012 at the database level — and was not credited in the 25 May report. But: the C# entity DashboardWidgetDefinition.cs (168L, last touched 19 May) has not been updated to map these new columns, the EF Configuration has no mapping for them either, and WidgetQueryExpressionService.cs grew from 109L to 341L but is still a token-string facade with a whitelist of keys like widget, dimension, measure — not the compiled WidgetQueryExpression record + SchemaViewResolver + SafeSqlValidator second-pass that the v2 spec requires. The persistence foundation is half-built; the execution engine is not.

5. A production security issue is open in docker-compose. In Infrastructure/deploy/docker-compose.demo.yml line 497, the postgres service binds with "${POSTGRES_PORT:-5432}:5432", which exposes the database on every interface of the Hetzner host by default. The mental note that flagged this — that the fix is to change the binding to "127.0.0.1:5432:5432" rather than rely on UFW — has not been applied; the file's last-write timestamp is 20 May. The Caddyfile basicauth for Jenkins also still has the placeholder hash $2a$14$REPLACE_WITH_REAL_CADDY_BCRYPT_HASH. Recovery action: 20 minutes to fix both. Section 4 enumerates the exact lines.

# 2. What changed since the 25 May audit

The 25 May Independent Validation Report concluded at approximately 17:00. Since then, exactly four files have been touched. Each is summarised below with its task-level meaning.

### 2.1 Production pipeline — Jenkinsfile (173L, 29 May 17:16)

This is the biggest operational improvement in the window. Major points:

- Has githubPush() trigger — directly addresses the recent issue where Jenkins was not auto-deploying on push to main.

- Five stages: Pull → Apply SQL scripts → Build 4 images → Recreate containers → Health + endpoint probes.

- Probes three new endpoints (/admin/phase1/connector-truth, /admin/phase2/pilot/deployment-checklist, /analytics/phase2/ml-lifecycle) expecting 401 = registered + auth required. This is a clean, demo-safe canary for endpoint registration.

- Backs up server-only files (.env, Caddyfile, docker-compose.demo.yml) across git reset — solid operational discipline.

- Uses sslip.io URL (api.178.105.152.180.sslip.io) — DNS not yet flipped to plantprocessiq.com.

- ON_ERROR_STOP=0 used when applying SQL scripts (line psql ... -v ON_ERROR_STOP=0) — this swallows SQL errors per-file. Useful for idempotency but masks regressions; consider a third channel (a separate ON_ERROR_STOP=1 stage on a clean DB) once schemas are stable.

This is real, measurable progress; it unlocks the closing of PPIQ-DEMO-019 (Pre-Demo Environment Checklist) and partially PPIQ-HARD-005 (Production Build + Zero-Console-Error CI Gate).

### 2.2 Audit log immutability proof — AuditLogImmutabilityTests.cs (271L, 29 May 15:56)

A xUnit integration test class with five test cases that prove the append-only contract of the audit log:

- Audit_table_should_allow_insert — happy path.

- Audit_table_should_allow_select — read path.

- Audit_table_should_block_update — UPDATE blocked (expects PostgresException SQLSTATE P0001 or 42501).

- Audit_table_should_block_delete — DELETE blocked.

- Audit_table_should_block_truncate — TRUNCATE blocked.

Opt-in pattern: uses [SkippableFact] with PPIQ_AUDIT_TRIGGER_TEST_CONNECTION env-var sentinel so the suite stays green when no DB is configured. Smart compromise — the file documents that the test uses trigger-based blocking because the local DB user lacks CREATEROLE for a separate runtime role. This delivers part of PPIQ-WF-024 (Audit Log Production Hardening): the immutability proof, but not yet the separate runtime role on Hetzner or the admin query endpoint with filters.

### 2.3 Test project new — PlantProcess.Infrastructure.IntegrationTests.csproj (35L, 29 May 15:57)

New csproj for the integration-test project that hosts the audit-log immutability tests above. Routine scaffolding to support test #2.2.

### 2.4 README.md placeholder (4L, 29 May 17:06)

Contains only the line '# auto-deploy real test'. Triggered by a deployment-pipeline rehearsal. Not material content.

### Net effect on the v2 plan

These four files move two tasks forward without closing either:

- PPIQ-WF-024 (Audit Log Production Hardening + Query Endpoint): advances from PARTIAL to ... still PARTIAL. The trigger-based immutability proof is now testable; the separate plantprocess_app role on Hetzner is not yet applied; the admin GET /admin/audit-log query endpoint with filters is built (Phase 2) but the frontend view is not.

- PPIQ-HARD-005 (Production Build + Zero-Console-Error CI Gate): the Jenkinsfile now exists, but it does not yet wire the npm run validate:phase2:step1-step2 script as a release gate; it builds images and probes endpoints but does not block on Playwright zero-console-error or bundle-size budgets.

- PPIQ-DEMO-019 (Pre-Demo Environment Checklist): the runtime endpoint /admin/phase2/pilot/deployment-checklist existed on 25 May; this snapshot has not added a markdown PRE_DEMO_CHECKLIST.md or a frontend page consuming the endpoint. Still PARTIAL.

All other v2 tasks remain at the verdict they had on 25 May. The breakdown is reproduced exhaustively in Section 5.

# 3. Required Fixes To Get Back On Track

These eleven fixes are itemised in priority order. The list is grouped into three bands: P0 fixes that should be closed before the next sprint commit, P1 fixes that should close inside this 5-day window if a demo is anywhere on the horizon, and P2 fixes that should close before any paid pilot begins. Each item names the exact file, the exact change, and the time estimate.

## P0 — Close today (founder non-negotiables + production security)

### FIX-P0-01: Eliminate the 'could not load' phrase across the entire application (30 min)

Founder stated rule, quoted from Vision §2: 'I will never accept in widget or chart show view could not load or this part of page could not load in front of customer'. Locations to change:

- 12 occurrences in Frontend/PlantProcess.Web/src/App.tsx around lines 5602, 5612, 5621, 5642, 5652, 5668, 5684, 5694, 5704, 5714, 5724, 5734 — all are fallbackTitle=...could not load arguments to withPageBoundary().

- 1 occurrence in Frontend/PlantProcess.Web/src/components/hardening/DataFetchBoundary.tsx line ~38: <h3>{title} could not be loaded</h3>.

- 1 occurrence in Frontend/PlantProcess.Web/src/hardening/DataFetchBoundary.tsx (the duplicate copy) line ~46: <strong>{title} could not be loaded</strong>.

- 1 occurrence in Frontend/PlantProcess.Web/src/components/ErrorBoundary.tsx around line ~141: "This part of the page could not load...".

Recommended replacement copy — neutral, recoverable wording matching brand voice:

// Before:
fallbackTitle="The dashboard could not load"
// After:
fallbackTitle="Refreshing dashboard"
// And the body copy in DataFetchBoundary:
// Before:
<h3>{title} could not be loaded</h3>
<p>Try again or contact support if this persists.</p>
// After:
<h3>Refreshing {title}</h3>
<p>One moment. If this takes more than a few seconds, tap Retry.</p>

After the copy change, add the silent-retry-once-on-network-error with 500 ms back-off behaviour the v2 spec required for DataFetchBoundary (PPIQ-HARD-016). The pattern:

// inside DataFetchBoundary's fetcher orchestration:
// 1. on first error of type 'network' or 'timeout' -> wait 500ms, retry silently
// 2. on second failure -> show recoverable card with Retry button (no 'could not load')
// 3. preserve layout dimensions during retry to prevent reflow
const { data, error, isPending } = useQuery({
  queryKey,
  queryFn: fetcher,
  retry: (failureCount, err) => failureCount < 1 && isNetworkOrTimeout(err),
  retryDelay: 500,
});

### FIX-P0-02: Bind PostgreSQL to localhost only (5 min)

In Infrastructure/deploy/docker-compose.demo.yml, the postgres service exposes 5432 on every interface by default. On the public Hetzner box this is the largest standing attack surface for the audit log and seed data.

# Current (line 496–497):
ports:
  - "${POSTGRES_PORT:-5432}:5432"
# Replace with:
ports:
  - "127.0.0.1:${POSTGRES_PORT:-5432}:5432"
# Or remove entirely if no host-machine pg client needs to reach it (the ppiq-net bridge already routes app traffic).

This change is not satisfiable via UFW alone — Docker sidesteps the UFW chain in the default daemon configuration. The fix has to be at the compose binding layer.

### FIX-P0-03: Replace the Jenkins basicauth bcrypt placeholder (5 min)

In Infrastructure/deploy/Caddyfile line 444:

# Current:
basicauth {
    admin $2a$14$REPLACE_WITH_REAL_CADDY_BCRYPT_HASH
}
# Generate a real hash:
docker run --rm -it caddy:2.8-alpine \
    caddy hash-password --plaintext "<your-jenkins-admin-password>"
# Paste the output value in place of the placeholder.

Until this is done, the Jenkins UI accessed via jenkins.plantprocessiq.com is unauthenticated against Caddy. Defence-in-depth: keep Jenkins's own login enabled in parallel.

### FIX-P0-04: Add HSTS + CSP headers to Caddyfile (10 min)

The marketing-site, app, and API hosts in Infrastructure/deploy/Caddyfile (lines 388–432) currently set five security headers but omit Strict-Transport-Security and Content-Security-Policy. For a production-grade pilot site, both are expected baseline. Add to each host's header block:

header {
    -Server
    Strict-Transport-Security "max-age=31536000; includeSubDomains; preload"
    X-Content-Type-Options nosniff
    X-Frame-Options DENY
    Referrer-Policy strict-origin-when-cross-origin
    Permissions-Policy "geolocation=(), microphone=(), camera=()"
    # Adjust CSP per host — start permissive on the API host, stricter on the website.
    Content-Security-Policy "default-src 'self'; img-src 'self' data: blob:; style-src 'self' 'unsafe-inline' fonts.googleapis.com; font-src 'self' fonts.gstatic.com; script-src 'self'; connect-src 'self' https://api.plantprocessiq.com"
}

Use X-Frame-Options DENY (not SAMEORIGIN) for the API host. SAMEORIGIN remains correct for the marketing and app hosts if iframes inside the app's own domain are expected.

## P1 — Close inside this 5-day window (visible demo wins)

### FIX-P1-01: Wire the three orphan frontend components into the app shell (6 hours)

These were the highest-leverage observation in the 25 May audit and remain so. The components and their backend endpoints are built; only the imports and route placements are missing.

Phase1WorkflowTruthPanel.tsx (285L) — add as a tab inside AdminPage:

// Frontend/PlantProcess.Web/src/pages/AdminPage.tsx — near the top:
import Phase1WorkflowTruthPanel from './Admin/Phase1WorkflowTruthPanel';
// In the tab table (alongside DB Configuration / Schema Configuration / etc):
{ key: 'phase1-truth', label: 'Workflow truth', element: <Phase1WorkflowTruthPanel /> }
// Route /admin/phase1-truth maps to this tab via the admin router.

SaveInspectionJobModal.tsx (185L) — wire into CorrelationPage:

// Frontend/PlantProcess.Web/src/pages/CorrelationPage.tsx — after analysis is complete:
import { SaveInspectionJobModal } from '../components/phase2/SaveInspectionJobModal';
import { StandardButton } from '../components/hardening/StandardButton';
const [saveOpen, setSaveOpen] = useState(false);
// In the render block, after analysis state is 'complete':
{analysisStatus === 'complete' && (
  <StandardButton variant='primary' onClick={() => setSaveOpen(true)}>
    Save as Inspection Job
  </StandardButton>
)}
{saveOpen && (
  <SaveInspectionJobModal
    correlationRunId={runId}
    onSaved={(jobDef) => { toast.success(`Inspection job '${jobDef.code}' saved`); setSaveOpen(false); }}
    onClose={() => setSaveOpen(false)}
  />
)}

OperationProgressPanel.tsx (57L) — wire as a sidebar on AdminPage and on long-running pages:

// Where shown: a thin right-rail panel on AdminPage and inside JobsMonitorTab.
import OperationProgressPanel from '../components/phase2/OperationProgressPanel';
// Hook into useLatestOnlyPolling pulling /admin/phase2/operations/progress/recent every 1s.
// Render only when at least one operation has status 'Running'.

After wiring, backend operations (import jobs, correlation jobs, PDF gen) need to actually write progress to long_operation_progress — see FIX-P1-08 below.

### FIX-P1-02: Consolidate duplicate StandardButton and DataFetchBoundary copies (1 hour)

Two locations for each — risk of drift and lint pollution:

- src/components/hardening/StandardButton.tsx (42L)  — keep this canonical.

- src/hardening/StandardButton.tsx (51L)  — delete. The 'success' variant and busyLabel features should be merged INTO the canonical copy first.

- src/components/hardening/DataFetchBoundary.tsx (56L)  — keep this canonical.

- src/hardening/DataFetchBoundary.tsx (78L)  — delete. The lucide icon usage and loadingMessage prop merge into the canonical copy first.

After deletion, run a project-wide search-and-replace for any lingering imports from the deleted path, plus add an ESLint rule disallowing future imports from src/hardening/* outside the allowlist.

### FIX-P1-03: Build the Demo Lifecycle Reset endpoint + button (4 hours)

Until this exists, repeated demos require manual SQL truncation. DemoLifecycleEndpoints.cs is currently 28 lines (read-only, last touched 21 May). Add:

// Backend/PlantProcess.Api/Endpoints/Demo/DemoLifecycleEndpoints.cs
app.MapPost("/demo-lifecycle/reset", async (
        IDemoLifecycleService service,
        ClaimsPrincipal user,
        CancellationToken ct) =>
    {
        var summary = await service.ResetCustomerStateAsync(user.Identity?.Name ?? "system", ct);
        return Results.Ok(summary);
    })
    .RequireAuthorization("PlantProcessAdmin");
// Backend/PlantProcess.Application/Demo/Services/DemoLifecycleService.cs
// Add ResetCustomerStateAsync that opens a single transaction and TRUNCATEs:
//   - ConnectionProfile / SourceDatasetDefinition / SourceFieldDefinition
//   - MappingDefinition / SchemaViewDefinition / KpiDefinition
//   - Non-system JobDefinition + JobRunHistory
//   - Non-system DashboardDefinition + DashboardWidgetDefinition
//   - CorrelationResult / CorrelationAnalysisDefinition
// Preserves: AspNetUsers, AspNetRoles, IndustryTemplate, AuditLogEntry, license config.
// Returns row-count summary per truncated table.

Frontend: a Hot Red 'Reset Demo State' button in Admin → Demo Lifecycle with a type-DELETE-to-confirm modal. Closes PPIQ-WF-022.

### FIX-P1-04: Author the three SQL connector smoke-test files (3 hours)

These exist in name only — the 25 May audit identified them, and they remain absent. Each follows the CsvConnectorSmokeTests.cs (61L) / ExcelConnectorSmokeTests.cs (77L) pattern.

// Backend/tests/PlantProcess.Infrastructure.IntegrationTests/Connectors/
//   PostgreSqlConnectorSmokeTests.cs
//   MsSqlConnectorSmokeTests.cs
//   MySqlConnectorSmokeTests.cs
// Each:
//   [SkippableFact] — skipped if PPIQ_CERT_{POSTGRES|MSSQL|MYSQL}_CONNECTION not set
//   Full IDataSourceConnector + ISchemaReader + IDataSourceReader cycle
//   Verify identifier quoting: " for PG, [ ] for MSSQL, ` for MySQL
//   Assert at least 1 dataset discovered + 10 rows read
//   Assert masked error on bad credentials (no driver stack trace)

Once these pass against the existing PPIQ_CERT_*_CONNECTION env vars, ConnectorProviderCatalog should flip isCertifiedForDemo=true and isAvailableNow=true — but only

if the env vars actually point at a working source DB. For the demo, this means deploying the docker-compose source DBs (FIX-P1-05). Closes PPIQ-WF-003 once the source DBs exist; partly closes PPIQ-WF-001's truth-matrix correctness.

### FIX-P1-05: Author docker-compose.demo-sources.yml (8 hours, split across days)

This is the single largest demo-blocker after the 'could not load' phrase. Per Vision Track 3, the demo must demonstrate the polyglot-source story end-to-end. Six containers per the v2 spec:

# Backend/Deployment/docker-compose.demo-sources.yml — outline
services:
  meltshop-pg:
    image: postgres:17-alpine
    environment: { POSTGRES_DB: meltshop, POSTGRES_USER: meltshop_owner, ... }
    volumes: [ ./meltshop:/docker-entrypoint-initdb.d:ro, meltshop-data:/var/lib/postgresql/data ]
    healthcheck: { test: ['CMD-SHELL', 'pg_isready -U meltshop_owner -d meltshop'] }
    networks: [ ppiq-demo-sources ]
  caster-oracle:
    image: gvenzl/oracle-xe:21-slim
    environment: { ORACLE_PASSWORD: ${CASTER_ORACLE_PWD}, APP_USER: caster_owner, ... }
    volumes: [ ./caster:/container-entrypoint-initdb.d:ro ]
    healthcheck: { test: ['CMD-SHELL', 'echo SELECT 1 FROM DUAL; | sqlplus -S /...'] }
  hsm-oracle: # separate Oracle instance (or schema if memory-bound)
  pkl-mssql:
    image: mcr.microsoft.com/mssql/server:2022-latest
    environment: { ACCEPT_EULA: 'Y', MSSQL_SA_PASSWORD: ${PKL_MSSQL_PWD} }
  downtime-mysql:
    image: mysql:8
  parsytec-mysql: # separate MySQL instance
  # Excel files mounted as a volume into the app container only
networks:
  ppiq-demo-sources:
    driver: bridge
volumes:
  meltshop-data: {}
  ...
# App service in main compose: depends_on with service_healthy for all six.

This unlocks PPIQ-DEMO-002 through PPIQ-DEMO-007 (the six DDL files) plus puts real teeth behind PPIQ-WF-003 connector certification. On memory-constrained Hetzner boxes, the two Oracle containers may need swap headroom — verify with free -m before bringing up.

### FIX-P1-06: Replace synthetic_*.sql inside-app seed scripts with archive (30 min)

Per PPIQ-DEMO-012, three files violate the Track 3 golden rule of 'no hardcoded UI, configure via HMI':

- Backend/database/seed/synthetic_hsm_source_insert.sql (943KB)

- Backend/database/seed/synthetic_inspection_source_insert.sql

- Backend/database/seed/synthetic_qms_source_insert.sql

Move all three to Backend/database/archived/inside-app-seed-deprecated-2026-05/ with a README.md explaining the rationale and pointing to docker-compose.demo-sources.yml. Then remove their inclusion in any Jenkinsfile or PowerShell deployment scripts.

### FIX-P1-07: Write the two demo scripts and recovery lines (6 hours)

These are documentation but high-leverage: they put words behind the live-demo flow and force the founder to articulate the customer story end-to-end before the customer hears it.

- Documentation/DEMO_TECHNICAL_25STEP_RUNBOOK.md — 25 steps for the process-engineer audience (≈20 min walk-through). Each step: UI clicks, expected result, recovery line, talking point.

- Documentation/DEMO_EXECUTIVE_5MIN_SCRIPT.md — 5 min C-level script: business pain, cost of quality issues, faster investigation, evidence-based language, no-MES-replacement positioning, pilot path.

- Documentation/DEMO_RECOVERY_LINES.md — one memorised recovery line per step of the 25-step runbook for the most likely failure modes.

Closes PPIQ-DEMO-014, PPIQ-DEMO-015, PPIQ-DEMO-022.

### FIX-P1-08: Wire OperationProgressPanel to actual backend operations (4 hours)

The long_operation_progress table and the GET/POST endpoints already exist (migration 116 + Phase2OperationEndpoints.cs). Today, no backend operation writes progress updates to that table. Add progress emission inside:

- DeltaImportExecutionService — emit on each batch of N rows imported.

- MappingExecutionService — emit on each canonical-table batch.

- Correlation orchestrators (ParameterDefectCorrelationLearner etc.) — emit on each phase of the calculation.

- InvestigationReportService — emit on each section rendered to PDF.

Use 1Hz polling from the frontend (the useLatestOnlyPolling hook is built); SignalR is not required for the demo. Closes PPIQ-HARD-026 once the panel is wired (FIX-P1-01).

## P2 — Close before any paid pilot begins

### FIX-P2-01: Build the Widget Script Layer correctly (16+ hours)

PPIQ-WF-013 is unfinished. The current WidgetQueryExpressionService.cs (341L) parses key-value tokens like

widget=chart;chart=bar;measure=avg_speed;dimension=shift

but does not compile to parameter-bound SQL. The v2 spec requires:

// Backend/PlantProcess.Application/Dashboarding/Models/WidgetQueryExpression.cs
public sealed record WidgetQueryExpression(
    string Source,                       // "schema_view:CODE" or "source_dataset:GUID"
    IReadOnlyList<GroupByClause> GroupBy,// with time/shift bucketing
    IReadOnlyList<MeasureClause> Measures, // SUM/AVG/MIN/MAX/COUNT/COUNT_DISTINCT/P50/P95/P99
    IReadOnlyList<FilterClause> Filters, // allow-listed operators
    IReadOnlyList<HavingClause> Having,
    IReadOnlyList<OrderByClause> OrderBy,
    int? Limit,
    IDictionary<string, object> Parameters
);
// Backend/PlantProcess.Application/Dashboarding/Services/Widgets/
//   SchemaViewResolver.cs — Source -> (qualified-table, allowed-column-list)
//   WidgetExpressionCompiler.cs — expression -> parameter-bound SQL
//     enforces identifier whitelist before SQL emission
//     re-validates compiled SQL via SafeSqlValidator second-pass
//     wraps with SET LOCAL statement_timeout = '5s'
// Endpoints:
//   POST /dashboards/widgets/{id}/execute        // uses persisted advanced_expression_json
//   POST /dashboards/widgets/execute-adhoc       // preview
// RBAC: PlantProcessEngineer+

The DB foundation in 113_phase1_widget_script_layer.sql is in place. The remaining work is: (a) update DashboardWidgetDefinition.cs to expose the new columns, (b) update DashboardWidgetDefinitionConfiguration.cs to map them, (c) write the compiler + resolver + execution endpoints.

### FIX-P2-02: Wire live license tier toggle (4 hours)

Per Vision §4.2, this must be demonstrable live in front of a customer. Today: LicenseService is a singleton with options injected at startup, so a tier change requires app restart. Required:

- Refactor LicenseService to use IOptionsMonitor<LicenseOptions> or to re-read on demand.

- Add POST /admin/license/tier-override (PlantProcessAdmin only) that switches the in-memory tier and writes an AuditLogEntry.

- Frontend LicenseGate component subscribes to a TanStack Query cache of /admin/license/status. After a successful tier override, invalidate the query.

- Verify LockedFeatureOverlay re-evaluates within 1–2 seconds, no full-page reload.

Closes PPIQ-WF-021. The 4-Track Vision is explicit about this being a live demo moment.

### FIX-P2-03: Seed the four demo persona accounts (3 hours)

Per PPIQ-DEMO-020: admin@demo, data-manager@demo, engineer@demo, viewer@demo. Each lands on a tailored route after login. Without this, RBAC cannot be demonstrated, and the four roles look identical to the customer.

-- Backend/database/seed/030_demo_persona_accounts.sql (new)
-- Use AspNetUsers + AspNetUserRoles via Identity's password hasher.
-- Or run from a one-off endpoint /admin/demo/seed-personas during setup.
INSERT INTO "AspNetUsers" (...) VALUES
  ('admin@demo',     'PlantProcessAdmin', ...),
  ('data-manager@demo',  'PlantProcessDataManager', ...),
  ('engineer@demo',  'PlantProcessEngineer', ...),
  ('viewer@demo',    'PlantProcessViewer', ...);
-- Document passwords in Documentation/demo/PRE_DEMO_CHECKLIST.md
-- Frontend: after login, redirect each role to its preferred landing page.

Closes PPIQ-DEMO-020.

# 4. Per-Track Exhaustive Status (DONE / PARTIAL / MISSING)

This section is a direct equivalent of Sections 2/3/4 of the 25 May Independent Validation Report, refreshed for the 29 May snapshot. The verdict scheme is the same. The order is by Track. Where a verdict changed between 25 May and 29 May the change is annotated; otherwise the verdict is reproduced unchanged for completeness.

## Track 1 — Workflow (25 tasks · 4 DONE · 14 PARTIAL · 7 MISSING · 44% complete)

| Task ID | Title | Sev | Verdict | Δ vs 25 May | Notes |
| --- | --- | --- | --- | --- | --- |
| PPIQ-WF-001 | Connector Truth Matrix API + FE binding | Critical | PARTIAL | Same | Backend live; frontend panel still orphan; legacy PlannedProviderDto array still at AdminEndpoints.cs:1411 |
| PPIQ-WF-002 | Oracle Connector Implementation | Very Imp | DONE | Same | OracleConnector.cs at 494L; smoke test still absent |
| PPIQ-WF-003 | PG/MSSQL/MySQL Demo Certification | Critical | PARTIAL | Same | Connectors built; smoke-test files PostgreSqlConnectorSmokeTests / MsSqlConnectorSmokeTests / MySqlConnectorSmokeTests still missing |
| PPIQ-WF-004 | DB-Driven Per-Source Scheduling Engine | Critical | PARTIAL | Same | NextRunAtUtc + ScheduleNextRunImmediately work; FOR UPDATE SKIP LOCKED unverified; license-floor enforcement not visible |
| PPIQ-WF-005 | Incremental Cursor / Watermark Import Proof | Critical | PARTIAL | Same | Cursor entity + endpoint live; corrupt-cursor failure path absent |
| PPIQ-WF-006 | Raw / Staging Latest-Copy Viewer | Very Imp | PARTIAL | Same | Endpoint live; UI still orphan; uses raw <table> not StandardTable |
| PPIQ-WF-007 | Schema Mapping Wizard | Critical | PARTIAL | Same | Workbench data endpoint exists; multi-step UI not built; POST endpoint for mapping creation absent |
| PPIQ-WF-008 | Cross-Source Join View Builder polish | Very Imp | PARTIAL | Same | Phase2OperationEndpoints has preview-join + save-join-view; FE join-builder visual UI not built; second-pass SafeSqlValidator not invoked |
| PPIQ-WF-009 | KPI Definition to Parameter Binding | Very Imp | PARTIAL | Same | kpi_parameter_bindings table + GET/POST exist; Widget Builder integration absent; FE KPI page not built |
| PPIQ-WF-010 | Importing Data Job Configuration Page | Critical | PARTIAL | Same | Configuration board endpoint live; FE create-from-mapping button not wired |
| PPIQ-WF-011 | Jobs Monitor Action Surface | Very Imp | PARTIAL | Same | Run-now / retry / enable / disable endpoints exist; full RBAC matrix collapsed to Admin-only; View-Logs absent; FE not wired |
| PPIQ-WF-012 | Widget Script Layer — DB Schema Foundation | Critical | PARTIAL | Upgraded | Script 113 added 7 columns + audit table to dashboard_widget_definitions. C# entity + EF config + DTOs still need updating |
| PPIQ-WF-013 | Widget Script Layer — Safe Expression Engine | Critical | PARTIAL | Same | WidgetQueryExpressionService grew to 341L but is still a token-string parser; WidgetQueryExpression record + SchemaViewResolver + compiler absent |
| PPIQ-WF-014 | Widget Script Layer — FE Builder Script Step | Critical | MISSING | Same | WidgetBuilderWizardContent has no Transform/Script step; Monaco editor absent |
| PPIQ-WF-015 | Save-as-Inspection-Job — Backend | Very Imp | DONE | Same | Endpoint live; EnableNow flag wiring to RunNowAsync incomplete |
| PPIQ-WF-016 | Save-as-Inspection-Job — FE Modal | Very Imp | PARTIAL | Same | SaveInspectionJobModal built but not imported by CorrelationPage |
| PPIQ-WF-017 | Rule-Based Correlation Engines (4 ML jobs) | Very Imp | PARTIAL | Same | NTILE(5) quintile descriptive analysis live; Fisher's exact/Spearman absent; no persistence to CorrelationResult |
| PPIQ-WF-018 | ML Job Lifecycle Honest State Machine | Very Imp | DONE | Same | ml_job_lifecycle_states + GET/POST endpoints + no_production_prediction column live |
| PPIQ-WF-019 | Suggestion & Recommendation Page MVP | Important | MISSING | Same | No /suggestions endpoint; no SuggestionsPage.tsx |
| PPIQ-WF-020 | PageDefinition Generic Abstraction | Important | MISSING | Same | No entity; dashboard CRUD is still the de-facto page model; no /pages/{slug} route |
| PPIQ-WF-021 | Live License Tier Toggle | Very Imp | MISSING | Same | No tier-override endpoint; LicenseService still singleton |
| PPIQ-WF-022 | Demo Lifecycle Reset Endpoint + FE Button | Very Imp | MISSING | Same | DemoLifecycleEndpoints.cs still 28L, last touched 21 May; no POST /demo-lifecycle/reset |
| PPIQ-WF-023 | Tenant Isolation Decision Lock | Critical | DONE | Same | tenant_isolation_decisions table seeded with SingleTenantPerPilot; markdown doc still optional |
| PPIQ-WF-024 | Audit Log Production Hardening + Query Endpoint | Very Imp | PARTIAL | Improved | AuditLogImmutabilityTests.cs now provides trigger-based proof (today's commit). Hetzner-side role separation still pending |
| PPIQ-WF-025 | Bootstrap Admin Lockout after First Real Admin | Important | PARTIAL | Same | AuthEndpoints touched 24 May; lockout logic needs inspection; integration test absent |

## Track 2 — Hardening (33 tasks · 1 DONE · 23 PARTIAL · 9 MISSING · 38% complete)

| Task ID | Title | Sev | Verdict | Notes |
| --- | --- | --- | --- | --- |
| PPIQ-HARD-001 | ErrorBoundary Verification Audit | Critical | PARTIAL | All 14 routes wrapped; per-route artificial-throw audit absent; Playwright assertion absent |
| PPIQ-HARD-002 | Toast Notification System Mapping Audit | Critical | PARTIAL | Sonner wired; per-failure-type matrix not produced; 8-mode coverage spec absent |
| PPIQ-HARD-003 | API Timeout + Idempotent Retry Policy | Very Imp | PARTIAL | Existing apiClient; DEFAULT_TIMEOUTS values need verification (spec: GET 6s, POST/PUT/PATCH 12s, DELETE 8s) |
| PPIQ-HARD-004 | Direct Route + Browser Refresh Contract | Critical | PARTIAL | Some Playwright specs exist; ≥14-route × cold/refresh/back-forward matrix not produced; return-URL test absent |
| PPIQ-HARD-005 | Production Build + Zero-Console-Error CI Gate | Critical | PARTIAL | validate-no-console-in-src.mjs exists; Jenkinsfile updated today does not yet call validate:phase2:step1-step2 as a release gate |
| PPIQ-HARD-006 | Full Button / Action Matrix QA | Critical | PARTIAL | phase1-button-action-matrix.spec.ts referenced; ACTION_MATRIX.md inventory absent |
| PPIQ-HARD-007 | Material Investigation Performance Hardening | Very Imp | PARTIAL | Endpoint exists; Take/Skip params verification + virtualized list confirmation absent |
| PPIQ-HARD-008 | Dashboard Query Performance Budget | Very Imp | MISSING | No PERFORMANCE_BASELINE.md; no Playwright timing assertion; no materialized views |
| PPIQ-HARD-009 | Controlled Backend-Outage States | Very Imp | PARTIAL | phase2-backend-outage.spec.ts exists; the 'could not load' phrasing still present (FIX-P0-01) |
| PPIQ-HARD-010 | Legacy API Client Shrink + No-Growth Guard | Important | PARTIAL | Migration scaffold in src/api/phase1 + phase2WorkflowApi; size diff not measured |
| PPIQ-HARD-011 | Live Demo Stress-Test Protocol | Very Imp | MISSING | STRESS_TEST_PROTOCOL.md absent; three sessions not run |
| PPIQ-HARD-012 | StandardButton + Site-Wide Audit-Replace | Critical | PARTIAL | Two duplicate copies (42L + 51L); site-wide audit-replace not done; brand spec tokens not applied |
| PPIQ-HARD-013 | StandardTable + Site-Wide Rollout | Very Imp | PARTIAL | StandardTable.tsx (93L) exists; many pages still use raw <table> |
| PPIQ-HARD-014 | StandardTabs + Site-Wide Rollout | Important | MISSING | No StandardTabs.tsx component visible |
| PPIQ-HARD-015 | PageGrid Layout + Spacing Tokens | Important | PARTIAL | PageGrid.tsx (55L) + page-grid.css (116L) exist; design-tokens.md absent |
| PPIQ-HARD-016 | DataFetchBoundary + Audit-Replace | Critical | PARTIAL | Two duplicate copies; both contain forbidden 'could not be loaded' phrase; silent retry not implemented |
| PPIQ-HARD-017 | Loading Skeleton Component Set | Very Imp | PARTIAL | LoadingSkeletonSet.tsx + Skeleton.css exist; per-widget skeleton fallbacks unverified |
| PPIQ-HARD-018 | Widget Resize Handles + Min/Max Controls | Very Imp | MISSING | react-grid-layout + react-resizable installed; widgets not refactored |
| PPIQ-HARD-019 | Heat Map Widget Verification | Very Imp | MISSING | No HeatMapWidget.tsx visible |
| PPIQ-HARD-020 | All Chart Widget Types Interactive | Very Imp | PARTIAL | phase2-chart-interaction.spec.ts exists; per-widget compliance checklist absent |
| PPIQ-HARD-021 | Drag-Drop Performance + Memoization Audit | Important | MISSING | No PERFORMANCE_BASELINE.md; React DevTools Profiler measurements absent |
| PPIQ-HARD-022 | Optimistic Save UI on All Forms | Important | MISSING | TanStack Query absent from package.json; pattern not in place |
| PPIQ-HARD-023 | Inline Form Validation Rollout | Important | PARTIAL | useInlineFormValidation hook + InlineFieldError exist; per-admin-form audit absent |
| PPIQ-HARD-024 | Stale-State Polling in Jobs Monitor | Important | PARTIAL | useLatestOnlyPolling.ts exists; JobsMonitorTab integration absent |
| PPIQ-HARD-025 | Six Failure-Modes Consistency Audit | Important | PARTIAL | Phase 2 e2e tests cover some modes; failure-modes.md verification matrix absent |
| PPIQ-HARD-026 | Progress Percentage Indicator | Important | PARTIAL | long_operation_progress table + endpoints + OperationProgressPanel exist; panel orphan; backend operations don't emit progress |
| PPIQ-HARD-027 | Endpoint / SQL / PK / FK Integrity Audit | Important | PARTIAL | 115_phase2_integrity_audit.sql covers ~7 entities; full 27-endpoint sweep absent |
| PPIQ-HARD-028 | Responsive Design + Multi-Browser Testing | Important | PARTIAL | phase2-responsive-multibrowser.spec.ts exists; screenshots not archived; docs absent |
| PPIQ-HARD-029 | Focused QA on 5 Most Complex Pages | Important | MISSING | qa-matrix/WIDGET_BUILDER.md etc. not produced |
| PPIQ-HARD-030 | Component Smoke Tests for High-Risk Files | Important | PARTIAL | Some component tests exist; +5 specific test files pending |
| PPIQ-HARD-031 | Playwright Nav + Refresh-Survival Suite | Important | PARTIAL | Specs exist but short of the required ≥30 test cases × 14 routes |
| PPIQ-HARD-032 | Bundle Size CI Check | Normal | PARTIAL | size-check npm script + check-bundle-size.mjs presence; Jenkinsfile gate absent; thresholds unverified |
| PPIQ-HARD-033 | Visual Regression Baseline | Optional | MISSING | Optional — toHaveScreenshot baseline absent |

## Track 3 — Demo (26 tasks · 4 DONE · 8 PARTIAL · 9 MISSING · 36% complete)

| Task ID | Title | Sev | Verdict | Notes |
| --- | --- | --- | --- | --- |
| PPIQ-DEMO-001 | Golden Demo Dataset — 1 month flat steel | Critical | DONE | tools/phase1/generate_phase1_golden_demo_data.py (324L) — 630 heats × 9 slabs = 5670 coils |
| PPIQ-DEMO-002 | docker-compose.demo-sources.yml — 6 source DBs | Critical | MISSING | Not authored; data lands in 5 named PG schemas (DONE with compromise marker on 25 May) |
| PPIQ-DEMO-003 | MeltShop PostgreSQL Schema DDL | Critical | MISSING | Not authored as a standalone file |
| PPIQ-DEMO-004 | Caster Oracle Schema DDL | Critical | MISSING | Not authored |
| PPIQ-DEMO-005 | HSM Oracle Schema DDL | Critical | MISSING | Not authored |
| PPIQ-DEMO-006 | PKL MSSQL Schema DDL | Critical | MISSING | Not authored |
| PPIQ-DEMO-007 | Downtime + Parsytec MySQL Schema DDL | Critical | MISSING | Not authored |
| PPIQ-DEMO-008 | Yard + QA Excel Templates | Very Imp | MISSING | yard_management.xlsx + qa_samples.xlsx absent |
| PPIQ-DEMO-009 | Python Demo Data Generator | Critical | DONE | 324L generator producing coherent cross-source data; lineage.json output enhancement pending |
| PPIQ-DEMO-010 | Realistic Correlation Injection | Very Imp | PARTIAL | One correlation pattern (FDT/CT/thickness → defect); spec called for three |
| PPIQ-DEMO-011 | Canonical Flat-Steel Plant Layout Seed | Very Imp | PARTIAL | 000_plantprocessiq_unified_advanced_realistic_demo_seed.sql (1628L) likely contains it; standalone 010_plant_layout.sql not carved out |
| PPIQ-DEMO-012 | Retire Inside-App Synthetic Seed Scripts | Important | MISSING | synthetic_*.sql files still in seed dir, not archived |
| PPIQ-DEMO-013 | End-to-End Golden Path E2E Test | Critical | PARTIAL | phase1-golden-demo.spec.ts referenced; 13-step coverage unverified |
| PPIQ-DEMO-014 | 20-Minute Technical Demo Script | Very Imp | MISSING | DEMO_TECHNICAL_25STEP_RUNBOOK.md absent |
| PPIQ-DEMO-015 | 5-Minute Executive Demo Script | Very Imp | MISSING | DEMO_EXECUTIVE_5MIN_SCRIPT.md absent |
| PPIQ-DEMO-016 | Customer-Grade PDF Report Export | Critical | PARTIAL | InvestigationReportService.cs (257L) exists; brand-polish + disclaimer footer absent |
| PPIQ-DEMO-017 | Demo Language Truth Audit | Critical | PARTIAL | demo_language_truth_rules table seeded with 3 rules; codebase-wide audit-language.mjs sweep not inspected; rule set narrow |
| PPIQ-DEMO-018 | Demo Backup Video | Important | MISSING | Not recorded |
| PPIQ-DEMO-019 | Pre-Demo Environment Checklist | Critical | PARTIAL | Endpoint live; markdown checklist + FE page absent |
| PPIQ-DEMO-020 | Demo Persona Modes | Important | MISSING | Persona accounts not seeded; per-role landing not in place |
| PPIQ-DEMO-021 | Demo Data Quality 'Bad Data' Story | Important | PARTIAL | Some randomness in generator; intentional bad-data rows + talking-point script absent |
| PPIQ-DEMO-022 | Live Demo Recovery Lines Rehearsal | Important | MISSING | DEMO_RECOVERY_LINES.md absent |
| PPIQ-DEMO-023 | DNS + Caddy + Let's Encrypt | Very Imp | PARTIAL | Caddyfile production-ready; DNS A records pending; Jenkins bcrypt placeholder still present |
| PPIQ-DEMO-024 | NDA + DPA Templates | Very Imp | MISSING | Templates absent |
| PPIQ-DEMO-025 | Diagnostic SOW Template | Very Imp | MISSING | DIAGNOSTIC_SOW_TEMPLATE.docx absent |
| PPIQ-DEMO-026 | Demo Environment Banner — Global Activation | Important | PARTIAL | DemoEnvironmentBanner.tsx exists; per-route verification pending |

## Track 4 — Website (22 tasks · 4 DONE · 10 PARTIAL · 4 MISSING · 50% complete)

| Task ID | Title | Sev | Verdict | Notes |
| --- | --- | --- | --- | --- |
| PPIQ-WEB-001 | Public DNS + Caddy Production Go-Live | Critical | PARTIAL | Caddyfile production-ready; DNS pending |
| PPIQ-WEB-002 | Replace Hero Placeholder with Real Screenshot | Critical | PARTIAL | ProductScreenshotShowcase references three paths; files presence unverified |
| PPIQ-WEB-003 | Screenshot Gallery / Product Proof | Very Imp | PARTIAL | Component built; real screenshot files not audited |
| PPIQ-WEB-004 | Website Pricing / License Matrix Sync | Critical | PARTIAL | PricingLicenseMatrix.tsx (65L) exists; backend-diff CI check absent |
| PPIQ-WEB-005 | Not MES / Not SCADA / Not L2 / Not BI-only | Critical | DONE | PositioningTruthBlock.tsx renders 3× in App.tsx |
| PPIQ-WEB-006 | Connector Honesty Block | Critical | DONE | ConnectorHonestyBlock.tsx + phase1WebsiteProof.ts content; backend-live-sync absent (acceptable for Phase 1) |
| PPIQ-WEB-007 | Data Diagnostic Offer Page | Very Imp | PARTIAL | RequestDemoForm mentions diagnostic; dedicated page absent |
| PPIQ-WEB-008 | Real Inquiry Form with Email Delivery | Critical | DONE (mailto) | Form works via mailto: (no backend endpoint) |
| PPIQ-WEB-009 | Engineer Brief PDF + Architecture Diagram | Very Imp | PARTIAL | Existing brief HTML from prior sprint; polish pass + PDF export pending |
| PPIQ-WEB-010 | Website Content Validation CI | Important | DONE | validate-website-content.mjs (102L) wired |
| PPIQ-WEB-011 | Brand Consistency App ↔ Website | Important | PARTIAL | Same palette in both; shared brand-tokens npm package not in place |
| PPIQ-WEB-012 | Performance / SEO Basics | Important | MISSING | Lighthouse baseline + OG tags + sitemap.xml + robots.txt absent |
| PPIQ-WEB-013 | Corporate Blue + JetBrains Mono | Important | MISSING | #2F80ED not present; JetBrains Mono not loaded |
| PPIQ-WEB-014 | PlantProcess IQ Product Page Polish | Very Imp | PARTIAL | Main marketing covers product; dedicated page audit pending |
| PPIQ-WEB-015 | MES Product Page | Important | PARTIAL | 13 mentions; no dedicated /products/mes route |
| PPIQ-WEB-016 | QES Product Page | Very Imp | PARTIAL | 0 mentions previously; no dedicated route |
| PPIQ-WEB-017 | Energy Management Product Page | Very Imp | PARTIAL | 0 mentions previously; no dedicated route |
| PPIQ-WEB-018 | Yard & Warehouse Product Page | Important | PARTIAL | 2 mentions; no dedicated route |
| PPIQ-WEB-019 | Calendly Integration | Important | MISSING | No Calendly embed |
| PPIQ-WEB-020 | Logo Design Verification + Brand Variants | Important | PARTIAL | favicon.svg present; full set of variants not enumerated |
| PPIQ-WEB-021 | Privacy Policy + Terms + Cookie Consent | Important | MISSING | /privacy + /terms absent; cookie banner absent |
| PPIQ-WEB-022 | Real Screenshots Across All 5 Product Pages | Very Imp | PARTIAL | ProductScreenshotShowcase references 3 paths; per-page coverage unverified |

# 5. Recommended 5-Day Recovery Sprint Plan

The plan below sequences the eleven fixes from Section 3 into a 5-working-day cadence. The intent: by end of day 5, every founder-named non-negotiable is closed, the orphan components are visibly wired, and the platform is genuinely demoable. Effort estimates are upper-bound. If pairing with one other engineer is feasible, days 3–5 compress.

## Day 1 — P0 closure + orphan wiring (≈8 hours)

- FIX-P0-01: Eliminate 'could not load' phrase across the 16 locations (45 min)

- FIX-P0-02: Bind PostgreSQL to 127.0.0.1 in docker-compose (10 min)

- FIX-P0-03: Replace Jenkins bcrypt placeholder (10 min)

- FIX-P0-04: Add HSTS + CSP headers to Caddyfile (15 min)

- FIX-P1-01a: Wire Phase1WorkflowTruthPanel into AdminPage tab (1.5 hr)

- FIX-P1-01b: Wire SaveInspectionJobModal into CorrelationPage (2 hr)

- FIX-P1-01c: Wire OperationProgressPanel into AdminPage right rail + JobsMonitorTab (1.5 hr)

- FIX-P1-02: Consolidate duplicate StandardButton + DataFetchBoundary (1 hr)

Day-end check: 'could not load' grep returns zero hits in customer-facing copy. The three orphans are visible in the app. No duplicate hardening files remain.

## Day 2 — Reset endpoint + connector smoke tests + visible founder asks (≈8 hours)

- FIX-P1-03: Build POST /demo-lifecycle/reset + ResetCustomerStateAsync + FE button (4 hr)

- FIX-P1-04: Author PostgreSqlConnectorSmokeTests + MsSqlConnectorSmokeTests + MySqlConnectorSmokeTests (3 hr — single sitting once the pattern is set)

- Bootstrap admin lockout verification (PPIQ-WF-025, 0.5 hr)

- Address pending 'syntax error at or near plantadmin' from SQL script application — likely a quoting issue in numbered scripts; surface the offending line via 'docker logs ppiq-postgres | grep plantadmin' (0.5 hr)

Day-end check: Reset button visible in Admin → Demo Lifecycle; clicking with type-DELETE confirmation rebuilds clean demo state. Three smoke-test files pass against a configured PPIQ_CERT_*_CONNECTION.

## Day 3 — Demo source containers + canonical layout seed (≈8 hours)

- FIX-P1-05a: Author docker-compose.demo-sources.yml outline + .env.demo (2 hr)

- FIX-P1-05b: MeltShop PostgreSQL DDL + Caster Oracle DDL (3 hr)

- FIX-P1-05c: HSM Oracle DDL + PKL MSSQL DDL (2 hr)

- FIX-P1-06: Move synthetic_*.sql files to /archived (30 min) — quick win

- Carve out 010_plant_layout.sql from the unified seed file (PPIQ-DEMO-011, 0.5 hr)

Day-end check: docker compose -f docker-compose.demo-sources.yml up -d brings up 4 of 6 source DB containers healthy. Day 4 finishes the remaining two.

## Day 4 — Remaining source DBs + script-writing + progress wiring (≈8 hours)

- Downtime + Parsytec MySQL DDL (2 hr)

- Yard + QA Excel templates (2 hr)

- FIX-P1-07: Write Documentation/DEMO_TECHNICAL_25STEP_RUNBOOK.md + DEMO_EXECUTIVE_5MIN_SCRIPT.md + DEMO_RECOVERY_LINES.md (3 hr — based on actual app screens)

- FIX-P1-08: Emit OperationProgress updates from DeltaImportExecutionService + MappingExecutionService + correlation orchestrators (1 hr — instrumentation only)

Day-end check: All six source DBs healthy. Demo scripts read end-to-end without contradictions. Operation progress fills smoothly during a 5,000-row import.

## Day 5 — Production hardening, persona accounts, dry-run demo (≈8 hours)

- FIX-P2-02: Live license tier toggle (4 hr)

- FIX-P2-03: Seed four demo persona accounts + per-role landing redirect (3 hr)

- Run STRESS_TEST_PROTOCOL session 1: random clicking, refresh during mid-load, resize, rapid filter changes (1 hr — log defects)

Day-end check: A dry-run of the 25-step demo runbook completes without 'could not load', without orphan UX, with one live tier toggle moment, with one persona switch moment, and with a Reset button at the end. Defects from the stress-test go to backlog with severity tags.

# 6. Decision Framework & Closing Position

## 6.1 Where you are on the track

Against the 4-Track Vision, the 29 May snapshot sits at approximately 38–45% completion across all four tracks, with the strongest progress on Track 4 (Website at 50%) and the weakest on Track 3 (Demo at 36%). The backend backbone is substantially ahead of its frontend wiring and ahead of demo readiness. The 25 May report observed this gap and the 4 calendar days since have not closed it; the four files committed in the window addressed operational deployment, not v2 task closure.

Three crisp truths the snapshot tells:

- Backend is real and at advanced quality. Phase 1 + Phase 2 endpoint groups, the connector truth matrix, the audit log immutability proof, the rule-based correlation NTILE quintile analysis, the kpi_parameter_bindings table, the demo_language_truth_rules guard — these are not scaffolding, they are production-quality work. The platform's bones are sound.

- Customer experience is behind the backend. Three high-value frontend components are built and orphan; the founder's #1 hardening rule is violated in 16 places; the live demo cannot reset between runs; there is no script to demo from. None of these is a hard engineering problem; they are unglued promises.

- Demo readiness is the binding constraint to your first paid pilot. Even if a prospect signs an NDA tomorrow, you do not have the real polyglot source containers, the demo scripts, the persona accounts, or the customer-grade PDF report polish. The 5-day plan in Section 5 closes most of this if executed sequentially.

## 6.2 Where the gaps are

Tabular summary of gaps that matter most, ranked by demo impact:

| Rank | Gap | Track | Demo Impact | Effort to close |
| --- | --- | --- | --- | --- |
| 1 | 'Could not load' forbidden phrase × 16 | T2 | Founder will refuse demo if seen | 45 min |
| 2 | Phase1WorkflowTruthPanel orphan (PPIQ-WF-001 FE) | T1 | Showcase moment for connector truth is invisible | 1.5 hr |
| 3 | DataFetchBoundary duplicated + no silent retry | T2 | First flaky widget = first 'could not load' | 1.5 hr |
| 4 | DemoLifecycleEndpoints reset missing (PPIQ-WF-022) | T1 | No clean re-run between back-to-back demos | 4 hr |
| 5 | No docker-compose.demo-sources.yml | T3 | Cannot demonstrate the polyglot source story | 8 hr |
| 6 | Postgres :5432 publicly exposed (sec) | Infra | Pilot blocker on security review | 10 min |
| 7 | Demo scripts absent (T3-014/015/022) | T3 | Founder narrates ad-hoc; weakest commercial moment | 3 hr |
| 8 | Persona accounts not seeded (PPIQ-DEMO-020) | T3 | Cannot demonstrate RBAC + commercial maturity | 3 hr |
| 9 | PDF report not customer-branded (PPIQ-DEMO-016) | T3 | Take-home artefact looks unfinished | 8 hr |
| 10 | Widget Script Layer not done (T1-013/014) | T1 | Strategic feature still unsold; OK for Phase 1 demo | 16+ hr |

## 6.3 Where the strengths are

It is worth naming what is genuinely working — not just because it is fair, but because these are the pieces the demo should be built around:

- Oracle Connector at 494L with bind-parameter discipline, identifier safety, env-var indirection for secrets. Cleanest piece of code in the snapshot.

- Audit log immutability test class (today's work) — disciplined, opt-in via env var, covers insert/select/update/delete/truncate.

- Tenant isolation decision lock pre-seeded as SingleTenantPerPilot — commercially smart, avoids the multi-tenant tar pit until first paid customer.

- ML lifecycle honest state machine with no_production_prediction column — concrete architectural commitment to brand-voice integrity.

- Phase 1 + Phase 2 endpoint design — clean separation of /admin/phase1/* (workflow truth) and /admin/phase2/* (operational + pilot) lets you iterate without breaking previous surfaces.

- Demo language truth rules table with three seeded rules — data-driven enforcement of brand-voice forbidden phrases.

- Production Jenkinsfile (today) with githubPush trigger, server-config backup-and-restore, endpoint-freshness probes.

- Caddyfile with proper reverse proxies for plantprocessiq.com / app / api / jenkins on the same box.

## 6.4 Recommended exit position from this report

In one sentence: spend the next 5 working days running the plan in Section 5. By end of Day 5 you will be genuinely demoable, every founder non-negotiable will be closed, and the orphan wiring problem will be gone. The Widget Script Layer (PPIQ-WF-013) and the MES/QES/Energy product pages are not on the 5-day list — they are Track-1-strategic and Track-4-strategic respectively, and they should be deferred to the post-first-paid-pilot sprint. Track 4 needs a quick win on DNS and Lighthouse SEO basics, but the four missing product pages are a 5-day sprint of their own that should not be conflated with the demo-readiness sprint.

Open this report next to your IDE. Each fix in Section 3 names the exact file, exact line, exact code change. Cross-check Section 5 day-by-day. The 4 calendar days you just had were spent on deployment plumbing — the next 5 should ship product.