## Read Me
PlantProcess IQ - Product Backlog v12
Every task now carries a junior-dev-actionable Description + a hard, QA-testable Acceptance
WHAT v12 FIXES
A column-rename at the v7->v8 step had blanked the Description and Validation/Acceptance for carried-over tasks. v12 recovers the original detailed text for the 84 carried tasks and authors fresh, code-grounded text for the 19 tasks added/reframed after v6 (the 7-step journey, the wire+prove engine tasks, logging, the generic-mapper eradication, multi-tenancy, i18n).
HOW TO READ A TASK
Description = what a junior/mid dev does, where (file:line where known), and how. Validation/Acceptance = the hard, falsifiable checks a QA dev runs to confirm done. Many acceptances demand LIVE HMI behaviour on the demo dataset, per the binding rule (code present + tested is not 'done' until proven live).
STRUCTURE
V1 = the 7-step journey walks end-to-end (Procurement, 1 Jul). V2 = every number justified + logging + the generic-mapper eradication + the Generic-Only CI gate (engineers/CEOs, 14 Jul). V3/V4 = production-real (multi-tenancy, i18n, HA/DR, compliance). Generic-Only red line enforced throughout.

## Backlog
PlantProcess IQ - Product Backlog v12 . full descriptions + acceptance restored/authored
Task ID | Version | Phase | Task Name | Persona(s) | Sub-criterion lifted | Gate | Track | Module | Severity | Status | % done | Description (junior-dev-actionable) | Validation / Acceptance (hard, reproducible) | Task Type | Effort (h) | Remaining (h) | Prereq | Lineage
V1-01 | V1 | V1-P1 Stable environment (nothing breaks) | Local dev reproducibility: EF-first + PGCLIENTENCODING + design-time factory (MERGED) | A1,A4 | A1-2, A1-10 | G9 | Environment | Infra | Critical | MOSTLY-DONE | 80% | MERGES old V1-01+V1-02 and the LOCAL residue of V1-03. The SERVER path is already green (the pipeline runs EF in a sibling before the numbered SQL, handles encoding, and uses ConnectionStrings__PlantProcessDb). Remaining is LOCAL-only and small: (a) fold `dotnet ef database update` into the start of `ppiq.ps1 migrate`/`demo`; (b) export PGCLIENTENCODING=UTF8 before every psql in ppiq.ps1; (c) rewrite PlantProcessDesignTimeDbContextFactory to read ConnectionStrings__PlantProcessDb -> PLANTPROCESS_DESIGNTIME_CONNECTION_STRING -> PLANTPROCESS_DB with an honest error; (d) converge the LOCAL compose remnants (delete duplicate demo-sources fleet + Infrastructure/deploy/docker-compose.demo.yml). Commit so the two session env-vars are no longer needed locally. | From a clean LOCAL DB, `ppiq.ps1 demo` provisions one-shot (EF schema -> SQL decoration -> app on :5063) with ZERO hand-set env vars, twice. grep finds no duplicate demo compose. Evidence: clean-run terminal log + grep. | refactor | 6 | 1.2 | - | V1-01
V1-02 | V1 | V1-P1 Stable environment (nothing breaks) | Delete env/profiles/local.env (leaks plantprocess123) + rotate | A1,A2 | A2-5 | G12 | Environment | Security | Critical | NEW | 10% | Remove env/profiles/local.env (it carries IsBootstrapAdmin=true and the literal plantprocess123) and rotate any key that ever touched it. Keep only deploy/compose/.env.dev (container-local creds) and the git-ignored server /var/lib/ppiq-preserve/.env. Also strip the stale 4-user set from appsettings.Development.json so it stops shadowing the canonical five locally. | grep finds zero `plantprocess123` and zero `IsBootstrapAdmin=true` in the repo; the startup guard still passes; a bare `dotnet run` shows the canonical five users. Evidence: grep output + boot log. | hardening | 3 | 2.7 | - | V1-02
V1-03 | V1 | V1-P1 Stable environment (nothing breaks) | Commit LOCAL test config — fix the clean-machine failures (server suite already green) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 40% | The SERVER pipeline already runs the backend (~567) and frontend (202) suites green. The remaining gap is the LOCAL clean-machine path: author committed appsettings.Test.json (DSN + 64-char signing key + a real admin + PPIQ_FORCE_EXTERNAL_API_TEST_HOST) and wire Do-Test so WebApplicationFactory boots the host and finds the DB without per-run env vars. This was the documented cause of the local 83 reds. | `ppiq.ps1 test` exits 0 TWICE on a fresh LOCAL checkout (no hand-set vars). Evidence: two consecutive green run logs. | hardening | 5 | 3 | V1-01 | V1-03
V1-04 | V1 | V1-P1 Stable environment (nothing breaks) | Persistent infra Caddyfile + correct route targets [NEW 26-Jun] | A2,A4 | A4-9 | G9 | Infra | Infra | Very important | NEW | 0% | NEW from the 26-Jun session. The live infra Caddyfile is an orphaned inode (host bind source deleted) with STALE targets (plantprocess-app-web, plantprocess-website) that don't match the real containers (plantprocess-web, plantprocess-api); app.* still serves 200 but it's fragile and hot-reloads are non-persistent. Re-establish a persistent host-bound Caddyfile in the infra project with CORRECT targets, so routes survive a Caddy recreate. Do NOT recreate ppiq-caddy until this lands. | After recreating ppiq-caddy, app.*/api.*/website.* all route to the correct live containers; the Caddyfile is host-bound and survives a restart. Evidence: docker exec cat + curl matrix. | hardening | 6 | 6 | - | V2-13
V1-05 | V1 | V1-P1 Stable environment (nothing breaks) | Harden .env<->Postgres-volume password coupling + provisioning resilience [NEW 26-Jun] | A4 | A4-9 | G9 | Infra | Infra | Important | NEW | 0% | NEW from the 26-Jun session. Two small hardenings: (1) make ensure-runtime-env.sh PRESERVE POSTGRES_PASSWORD across a stale-key regeneration (today a regen rotates it and diverges from the existing Postgres volume -> 28P01); document the rule that /var/lib/ppiq-preserve/.env must not be deleted, and if it is, the volume must be wiped in the same step. (2) Wrap FirstRunProvisioningHostedService provisioning in try/catch so a provisioning failure logs but never crashes the API at startup. | A simulated stale-key regen keeps the same POSTGRES_PASSWORD and the API still connects; an induced provisioning error is logged and the API still starts. Evidence: regen log + fault-injection test. | hardening | 5 | 5 | - | V2-14
V1-06 | V1 | V1-P1 Stable environment (nothing breaks) | Spamhaus / outbound-mail relay remediation (relay + SPF/DKIM/PTR + block 25) | A4, A6 | A6.10 CTA/lead capture | G9 | hardening | Infra | Very important | NEW | 0% | The Hetzner/Spamhaus abuse notice (23 Jun) requires lead-capture email to stop sending direct on port 25. Route all outbound mail (the website lead-capture, V5OutboundLeadSystemEndpoints) through an authenticated transactional relay on 587/465, publish SPF and DKIM DNS records for plantprocessiq.com, set a valid PTR/reverse-DNS for the sending IP, and block outbound port 25 at the firewall. Relay host/port/credentials live in env/secret config, never hardcoded. Confirm delisting with a PUBLIC Spamhaus checker, not Hetzner's resolvers. | A lead submitted on the live site is delivered to the inbox via the 587/465 relay (headers show the relay, not direct 25); `dig TXT` shows valid SPF + DKIM for plantprocessiq.com; the sending IP has a matching PTR; outbound 25 is closed (egress test); a public Spamhaus lookup shows the IP/domain not listed. | hardening | 5 | 5 |  | (new)
V1-07 | V1 | V1-P1 Stable environment (nothing breaks) | Phase gate: clean checkout boots seeded + green twice + SERVER deploy green | A1,A4 | A1-2, A1-9 | G9 | Environment | Deploy | Critical | NEW | 30% | End-of-phase regression. LOCAL: clean clone -> `ppiq.ps1 reset && ppiq.ps1 demo` boots the seeded stack; `ppiq.ps1 test` green twice; genealogy walk resolves; capture the `seed exit=0` line. SERVER: confirm `git push` -> Jenkins `plantprocessiq-deploy` reaches PIPELINE GREEN (already true at build #96; the gate is to keep it green after the foundation/test work lands). Seals V1-P1 as deployable in both environments. | All LOCAL gates pass on a fresh machine, scripted, with seed exit=0; the SERVER pipeline is green on the same commit. Evidence: one combined run log + the green Jenkins build. | verification | 4 | 2.8 | V1-01, V1-03, V1-04 | V1-07
V1-08 | V1 | V1-P1 Stable environment (nothing breaks) | Wire website CTA to a real inbox (CODE DONE — commit + SMTP + relay) | A6 | A6-10 | G8 | Web | Web | Very important | MOSTLY-DONE | 65% | Per the handover the lead-email CODE is DONE and builds clean (V5OutboundLeadSystemEndpoints.cs TrySendLeadEmailAsync; env PlantProcess__Lead__Smtp__*; form POSTs to /api/v5/outbound/leads). Remaining: COMMIT it; supply live SMTP env; do a real-send test. IMPORTANT: route via an authenticated transactional relay (587/465) with SPF+DKIM+PTR and outbound port 25 blocked - never send from the VPS IP (Hetzner/Spamhaus notice). (Hardened backend + e2e assert is the separate V2 task.) | A test submit lands in your inbox/DB via the relay; Spamhaus web-checker shows the IP not listing. Evidence: the received lead + checker screenshot + commit hash. | feature | 4 | 1.4 | - | V1-18
V1-09 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Rebuild mapping/genealogy/safe-SQL foundation (demo-minimum, model-first) [P0 — biggest real gap] | A3,A4 | A3-5, A4-2, A4-6 | G2 | Workflow | Database | Critical | NEW | 80% | NOT touched by the deploy session or the docs work - still the largest real gap. The foundation is lost (no clean git copy): ppiq_business_key_definitions, canonical_business_keys, canonical_mapping_versions, the canonical genealogy tables, ppiq_walk_genealogy and ppiq_resolve_safe_sql are gone; only genealogy_edges (EF) survives. Rebuild the DEMO-MINIMUM set model-first: entities + IEntityTypeConfiguration for the business-key/canonical-mapping tables; the recursive walk + cycle/orphan validators + the safe-SQL resolver in a thin SQL migration. Scope to what the demo thread needs; defer full mapping-lifecycle hardening to V2. Name everything descriptively (no p03_p04). | On the demo dataset, ppiq_walk_genealogy(C-0044170) returns the full coil->melt chain both directions; a bad mapping returns a typed error and rolls back; the un-quarantined 311/321 validators are green. Evidence: psql output + green migration. | feature | 4 | 0.8 | V1-01 | V1-04
V1-10 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Verify genealogy both directions on C-0044170 live | A3 | A3-5 | G2 | Workflow | FrontEnd | Critical | PARTIAL | 85% | With the foundation rebuilt, walk C-0044170 coil->melt and melt->coils in the running HMI, confirming the Material Investigation evidence panel renders both directions on the customer's own keys. | Recorded walk: both directions resolve on the demo data, no stall. Evidence: clip in the dry-run. | verification | 2 | 0.3 | V1-04 | V1-05
V1-11 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Verify transition-coil weighted attribution (70/30) live | A3 | A3-8 | G15 | Workflow | FrontEnd | Very important | PARTIAL | 80% | Confirm a casting-transition coil reports weighted (e.g. 70/30) attribution across two heats (H-3361/H-3362) with the population/exclusions shown, never a single fabricated heat. The backend test is already green; the live HMI clip is owed. | A transition coil renders weighted provenance + stated population live. Evidence: clip. | verification | 2 | 0.4 | V1-04 | V1-06
V1-12 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | App boots under Playwright (no early webServer exit) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 55% | Fix playwright config so webServer starts the API+web and waits for :5063/:5173 instead of exiting early; run at least one real spec against the booted app. | `ppiq.ps1 e2e` starts the app and runs >=1 spec to green. Evidence: Playwright HTML report. | hardening | 5 | 2.2 | V1-01 | V1-08
V1-13 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | One-click readiness check passes live | A4 | A4-7 | G7 | Workflow | Backend | Critical | PARTIAL | 50% | Make the readiness surface return green (sources healthy, counts match, jobs ready) in one call on the seeded stack. | Readiness endpoint returns all-green on the demo data, shown live. Evidence: screenshot + clip. | feature | 5 | 2.5 | V1-04 | V1-09
V1-14 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Verify every demo-path button live (click-through) + commit the action-matrix | A3 | A3-1, A3-3 | G6 | Workflow | FrontEnd | Critical | MOSTLY-DONE | 75% | Per the handover the action-matrix is DONE 20/20 green (i18n-safe structural guard + truthful data-disabled-reason in phase9ActionMatrix.ts / phase9-action-matrix.spec.ts / MaterialAnalyticsPages.tsx / DemoAnalyticsPages / StandardTable) but the COMMIT is pending and the live click-through on the server demo URL is the remaining proof. Commit the five files; click every control on the 9-step path in the running HMI. (Full StandardButton migration is the V2 task.) | The action-matrix files are committed; every button on the 9-step script performs its action live; 0 unhandled rejections on the path. Evidence: recorded run + commit hash. | verification | 3 | 0.8 | V1-04 | V1-10
V1-15 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Demo-path robustness fault gate - no crash from user/license/docker/DB | A3, A4 | A3.2 e2e no crash · A4.9 operational resilience | G6 | demo | Testing | Critical | NEW | 0% | Guarantee the demo path never crashes from any cause a Procurement viewer could trigger. Enumerate the fault classes - bad login, a role/tier-gated control clicked, a license expiry/grace state, a Jenkins/Docker restart mid-session, a transient DB connection drop (the orphan-stack / conn-key / SigningKey issues) - and make each degrade gracefully (typed error, retry, or read-only banner) instead of a white screen, unhandled 500, or dead UI. Add an error boundary on every demo route and health/retry on the API client. This is enforcement, not a one-off fix. | Inducing each fault (kill the API container, expire the license, drop the DB connection, click a gated control as a low-tier role) produces a graceful message and the app recovers when the fault clears - zero white screens, zero uncaught 500s reaching the user, zero frozen buttons. A checklist enumerates every fault class and its observed graceful behaviour. | test | 6 | 6 |  | (new)
V1-16 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | Record the clean dry-run video (insurance) — Karim-owned | A3,A5 | A3-2 | G7 | Demo | Docs | Critical | NEW | 0% | Per the handover this CANNOT be AI-done. Record an MP4 of the full 9-step walk on the seeded stack against the live server demo URL (app.178.105.152.180.sslip.io) logged in as sysadmin - the pilot acceptance artifact and the backup if live ever fails. Blocks the demo-reel cut. | MP4 exists; no dead click; matches the script. Evidence: the file. | content | 3 | 3 | V1-10 | V1-11
V1-17 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J1 - Auto-login lands on a working home (sysadmin, no login page) | A4, A3 | A2.4 token/session | G12 | workflow | FrontEnd | Important | PARTIAL | 70% | Verify + harden step 1: the app auto-authenticates as the permanent sysadmin (FirstRunProvisioning SOU support account) and lands directly on a populated, navigable home - no login page in V1. No 401, no blank screen, no console error on first load. The auto-login uses the real auth/session machinery (signed token + __Host- cookie), not a bypass. | A cold load of the demo URL reaches a working authenticated home as sysadmin with the nav visible and at least one populated panel; no login prompt appears; the browser console shows no errors; the session is a real signed token (verifiable in the cookie), not a stub. | test | 2 | 0.6 |  | (new)
V1-18 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J2 - Connect + select the demo data source(s) via the DB Configuration tab | A4, A3 | A4.1 source onboarding HMI | G1 | workflow | FrontEnd | Critical | PARTIAL | 60% | Verify + harden step 2: the DB Configuration tab (AdminDbConfigurationTab.tsx, 1126 lines) lets the user register/select one, two, or all 8 demo sources, run a connection test, and choose which tables to import. Confirm the tab invokes the connector/registry backend (ConnectorAdminEndpoints -> ppiq_register_dump_source / ProvisionBaseline) and shows a clear success/failure state. Fix any dead control, any test button that does nothing, any table-picker that does not populate. The 6 connectors (Csv/Excel/MySql/Oracle/Postgres/historian) already exist - this is wiring + UX verification. | From the HMI: select a demo source, run the connection test and see a green result; choose tables and see them registered (verify via SELECT * FROM source_table_dump_registry); repeat for two and for all eight; every control does something (no dead button); a deliberately bad connection shows a typed error, not a crash. | test | 4 | 1.6 |  | (new)
V1-19 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J3 - Run Stage-1 import to staging + see it in Jobs Monitor + job log | A4, A3 | A4.4 Jobs Monitor | G1 | workflow | FrontEnd | Critical | PARTIAL | 50% | Verify + harden step 3: trigger Stage-1 (ppiq_run_stage1_delta_import) from the Importing Data tab; confirm the dump/staging tables fill, the Jobs Monitor tab (AdminJobsMonitorTab 350) + TwoStageImportMonitorPanel (376) show last-run status/duration/rows, and the job log records the run. Confirm incremental behaviour: a second run imports only the new tail (two_stage_processed_watermarks / last-index comparison), not the whole table. | A Stage-1 run populates staging (row count > 0 in the dump tables); the Jobs Monitor shows the run with status, rows, duration; a second immediate run imports 0 or only-new rows (watermark proven); the job log has an Info entry; a forced failure (bad source) shows an Error entry in the monitor and the log. | test | 4 | 2 |  | (new)
V1-20 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J4 - No-code Mapper UI loads the demo staging schema and previews/joins/filters | A4, A3 | A3.4 widget/mapping config | G2 | workflow | FrontEnd | Critical | PARTIAL | 50% | Verify + harden step 4: the Schema Configuration tab (AdminSchemaConfigurationTab.implementation.generated 955) + CanonicalSchemaMappingPanel (514) + V5NoCodeMapperPage must read the real demo STAGING schema (tables + columns from the dump), let the user define a view/join/filter, preview rows, and validate via SafeSqlValidator/SqlAllowlistProvider. This is the verify-needed seam: confirm the UI binds to live staging metadata, not a placeholder. Fix any panel that loads empty. | On the demo staging data the mapper lists the actual source tables and columns; defining a view previews real rows; a join across two dump tables previews correctly; a malformed SQL is rejected by safe-SQL with a typed error (not a 500); no dead control on the tab. | test | 6 | 3 |  | (new)
V1-21 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J5 - Run Stage-2 canonical refresh + monitor + log (TEMP demo shapes - V1 ONLY) | A4, A3 | A4.4 Jobs Monitor | G2 | workflow | FrontEnd | Critical | PARTIAL | 50% | GENERIC-ONLY RED LINE: the hardcoded demo-shape projection used here is a TEMPORARY V1-ONLY measure to hit 1 Jul and MUST be eradicated in V2 (see the V2 generic-projector task). | nan | test | 4 | 2 |  | (new)
V1-22 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J6 - Build/open a dashboard + widget bound to the freshly-imported canonical data | A4, A3 | A3.1 zero dead buttons | G3 | workflow | FrontEnd | Critical | PARTIAL | 40% | Verify + harden step 6: on the now-populated canonical data, create a page (PageBuilderPage.implementation 435), drag a widget (WidgetBuilder wizard - data/filter/preview steps), bind it to a canonical view via the widget script layer (WidgetScriptSqlCompiler 240), and save. CRITICAL seam-6 check: confirm widgets read the canonical_* views that Stage-2 populates - NOT pre-seeded tables - so a live re-import visibly changes the widget. Use DashboardGridLayout (552-state) for drag-drop persistence. | A newly created page+widget renders rows that came through the import; re-running the import and refreshing visibly changes the widget's numbers (proving it reads canonical views, not seed); save+reload persists the page and layout; no dead button in the page/widget builder; the widget's query passes the safe-SQL compiler. | test | 6 | 3.6 |  | (new)
V1-23 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J7 - Run a correlation / inspection + read grounded results on the imported data | A4, A3 | A3.7 correlation honest | G4 | workflow | FrontEnd | Critical | PARTIAL | 50% | Verify + harden step 7: from Advanced Analysis (AdvancedAnalysisPage 214) + Inspection Jobs (InspectionJobsPage 88), configure an inspection (a defect/downtime/KPI + a duration window), run it on the imported canonical data using the already-built engines (CorrelationService 564 + AdvancedCorrelationComputeService 390), and read a grounded suspected-contributor result. The GroundedAssistantPage (129) must explain it with citations and render no uncited number (GroundingService). Wire the engines to the imported demo data live. | An inspection job runs on imported data and returns a suspected contributor with population + method shown (Spearman/MI/etc., q-value, bootstrap stability); the grounded assistant explains it citing evidence handles and renders no uncited number; clicking a number opens its provenance; results match the demo expectation (the defect linked to its superheat driver). | test | 5 | 2.5 |  | (new)
V1-24 | V1 | V1-P2 The 7-step journey walk (end-to-end, no dead end) | J-WALK - End-to-end journey walk under induced faults (the no-dead-end gate) | A4, A3 | A3.2 e2e no crash | G6 | workflow | Testing | Critical | NEW | 0% | The actual V1 test: walk all 7 steps as ONE continuous flow on a clean demo stack (source -> staging -> map -> canonical -> dashboard -> analysis), then induce the fault classes (bad login, role/tier gate, container restart, DB blip) at each step. Enumerate EVERY break, dead button, and crash in ONE pass (preventive-maintenance mandate - do not fix one runtime error at a time) and fix each at source. This gate is the no-dead-end guarantee for the Procurement demo. | The full source-to-analysis walk completes with zero dead buttons, zero white screens, zero uncaught 500s reaching the user; each induced fault degrades gracefully and the stack recovers when it clears; ppiq e2e and the dead-button scanner are both clean; a recorded walk shows no dead click. | test | 6 | 6 |  | (new)
V1-25 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the 9-step demo script (DELIVERED — fill 2 placeholders) | A5 | C5 | G7 | Demo | Docs | Very important | MOSTLY-DONE | 80% | Per the handover the script PlantProcess-IQ-Live-Demo-Script.md is DELIVERED (connect->map->build page->...). Remaining: fill the 2 placeholders (roadmap specifics + your real per-plant price) and rehearse it cold once, including the surprise-question answers (incl. the new 'do you ship a customer-usable admin?' -> no; only the sysadmin support account, customer admin added at commissioning). | You run it cold once end-to-end with the placeholders filled. Evidence: the script doc + a rehearsal note. | content | 2 | 0.4 | V1-11 | V1-12
V1-26 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the ROI model + slide (DELIVERED — fill real price) | A5 | A5-1, A5-7 | G5 | Web | Docs | Very important | MOSTLY-DONE | 80% | Per the handover PlantProcess-IQ-ROI-Model.xlsx + PlantProcess-IQ-ROI-Slide.pptx are DELIVERED (base case EUR 480,000/yr vs a EUR 300k placeholder price; labelled projected-not-proven). Remaining: replace the placeholder price with your real per-plant price and re-verify the figure still exceeds it. Also fits the 07-editions-and-licensing doc (which carries [[PER_PLANT_ACV_RANGE]]). | The model + slide carry a defensible EUR/yr number against your real price, assumptions stated, tied to the demo finding. Evidence: the files. | content | 4 | 0.8 | - | V1-13
V1-27 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the founder credibility pack (DELIVERED as 09-founder doc — fill background) | A5 | A5-10 | - | Web | Docs | Very important | MOSTLY-DONE | 80% | The customer doc 09-founder-and-company.md is DELIVERED and on-brand. Remaining: fill [[YEARS]] and [[BACKGROUND_DETAIL]] (your 14 yrs PSI Metals / SMS / EzzSteel, named plants/processes), [[COMPANY_LOCATION]], [[CONTACT_NAME_AND_EMAIL]], [[WEBSITE_URL]]; optionally produce the one-slide version placed before the offer slide. | The doc (and optional slide) has your named plants + contact filled; on-brand. Evidence: the file. | content | 2 | 0.4 | - | V1-14
V1-28 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Pitch deck (10-12 slides, on-brand) | A5,A6 | A6-1 | G8 | Web | Docs | Very important | NEW | 0% | Problem -> why BI fails -> evidence-grade approach -> LIVE DEMO -> value -> honest boundary -> read-only/OT-safe -> credibility -> pilot offer. <=12 slides, brand palette. The narrative content largely exists across the delivered docs (01-overview, 06-methodology, 04-security, 08-pilot, 09-founder) - assemble into a deck and produce the logo/brand variant set. | Rehearsed once; <=12 slides; on-brand. Evidence: the file. | content | 4 | 4 | - | V1-15
V1-29 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Finalize the pilot offer (DELIVERED as 08-pilot doc — fill price/customer) | A5 | A5-7 | - | Web | Docs | Very important | MOSTLY-DONE | 80% | The customer doc 08-pilot-offer.md is DELIVERED (read-only, time-boxed, fee-credited-on-conversion; scope/success/commercials tables). Remaining: fill [[PILOT_FEE]] (lean EUR30k for the first), [[CONVERSION_TARGET]] (the EUR120k/yr figure), [[CUSTOMER_NAME]], [[PILOT_DURATION]], and the source/target-question specifics per prospect. | One offer with the price + conversion figure + ask filled for a named prospect. Evidence: the file. | content | 2 | 0.4 | - | V1-16
V1-30 | V1 | V1-P3 Presentation pack (deck, ROI, video) | Cut the 2-3 minute demo video (blueprint delivered) | A6 | A6-10 | G8 | Web | Docs | Important | NEW | 0% | Per the handover the cut sheet PlantProcess-IQ-Demo-Reel-CutSheet.md is DELIVERED (2:45 EDL + VO + export + 'no dead click' QC). The MP4 render is yours and depends on the V1-13 recording. | 2-3 min MP4; no dead click. Evidence: the file. | content | 3 | 3 | V1-11 | V1-17
V2-01 | V2 | V2-P3 Value engine & justified numbers | Wire + prove the Value Engine LIVE on demo data (engine already built) | A5, A3 | A5.1 quantified value · A5.7 price-to-value | G5 | AI+ML | Backend | Critical | PARTIAL | 70% | CODE-VALIDATED: ValueImpactEngine.cs is BUILT (bounded Low/Expected/High, ABSTAINS on missing assumptions, attaches a provenance handle + input JSON per term, monotonic guard); ValueRealizationContracts.cs adds the realized-value ledger; ValueHonestyLint blocks forbidden phrases. DO NOT rebuild. LAST MILE: (1) populate ValueImpactInputs + CostAssumptionSet from the DEMO dataset and the real per-plant rates (not BuildDemoRequest); (2) surface the result in a Value dashboard widget with drill-through to each term's input JSON; (3) prove the worked euro range reproduces LIVE through the HMI on a finding for C-0044170; (4) confirm MapValueEndpoints / MapP15ValueRealizationEndpoints return it on demo data. | LIVE on the demo dataset: a defect finding on C-0044170 yields a bounded euro range in the HMI; each term drills through to its input JSON + provenance handle; removing a required assumption flips the widget to the explicit abstain message (never a fabricated number); an e2e spec asserts both the live range and the abstain branch. | new feature | 10 | 3 |  | (new)
V2-02 | V2 | V2-P3 Value engine & justified numbers | Extend the grounding contract to ALL widgets (render-time uncited-number gate) | A5, A3 | A5.4 trustworthy AI · A3.6 population stated | G4 | AI+ML | Backend | Very important | PARTIAL | 55% | CODE-VALIDATED: GroundingService.cs already blocks uncited numbers (every number must trace to a claim handle), blocks causation language, drops synthetic claims, refuses honestly. DO NOT rebuild the contract. Lift the SAME mechanism from the assistant to EVERY surfaced number across dashboards: each KPI/chart-series/tile/cell carries a resolvable provenance handle or is not rendered. Add a render-time guard plus a CI gate enumerating demo-path widgets that fails on any uncited numeric. | A CI gate asserts 0 uncited numerics on the demo path; clicking any number/graph/tile opens its provenance handle resolving to a real source; a deliberately uncited test value is BLOCKED from render (negative test); the implementation reuses GroundingService's proven logic, not a parallel one. | hardening | 8 | 3.6 |  | (new)
V2-03 | V2 | V2-P3 Value engine & justified numbers | Wire + expose L4 statistics LIVE (Spearman/MI/Lasso/VIF/bootstrap/FDR already built) | A3 | A3.7 correlation/ML honest | G4 | AI+ML | Backend | Very important | PARTIAL | 70% | CODE-VALIDATED: AdvancedCorrelationComputeService.cs (390) is BUILT - Spearman, Pearson/point-biserial, normalized MI, Cramer's V, iterative VIF, Lasso, Benjamini-Hochberg FDR, bootstrap stability, stratification. Update Doctrine sec.21 ('unstarted' is wrong). Remaining: run a correlation/inspection job LIVE on demo data through the HMI and surface the suspected contributor (method, q, bootstrap %, strata, excluded records) in 'suspected contributor' language; expose the VIF/Lasso exclusions and FDR q-values in the result UI. | A correlation job recomputes LIVE on demo data and the HMI shows a suspected contributor with the method named, q<0.05 under BH-FDR, bootstrap stability %, stratified, population/exclusions stated; a golden dataset recovers true signals and rejects spurious ones under FDR; the engine test is extended to assert the LIVE surface, not just the compute. | test | 6 | 1.8 |  | (new)
V2-04 | V2 | V2-P3 Value engine & justified numbers | Sharpen AI/ML results: calibration, effect-size ranking, stratified quality | A3 | A3-7 | G4 | AI+ML | AI+ML | Very important | NEW | 0% | Improve the learning output: calibrated scores, effect-size (not just p-value) ranking, stratified quality by visible confounders, under BH-FDR - framed as suspected contributors. The 06-analytics-methodology doc already commits to this posture. | On the golden dataset, true signals are recovered and spurious rejected under FDR; results show effect size + stratification. Evidence: golden-set test + clip. | feature | 12 | 12 | V1-04 | V2-17
V2-05 | V2 | V2-P3 Value engine & justified numbers | Impressive evidence-ranked suggestion engine (deterministic, euro impact) | A3,A5 | A5-1 | G4 | AI+ML | AI+ML | Very important | PARTIAL | 55% | Deterministic, MD5-stable suggestions ranked by evidence + euro impact, workflow-bound with RBAC, surfaced in SuggestionCardsPanel - the 'told me something I didn't know, and proved it' moment. | Suggestions render with population, method, evidence handle and a euro range; reproducible IDs. Evidence: test + clip. | feature | 10 | 4.5 | V1-04 | V2-18
V2-06 | V2 | V2-P3 Value engine & justified numbers | Assistant eval harness + model-version governance gate | A2,A5 | A5-4 | G13 | AI+ML | Testing | Important | NEW | 0% | An eval harness that gates assistant regressions and a model-version governance gate (no uncited number, citations resolve). | The harness fails on an injected uncited-number regression; passes clean. Evidence: the harness + CI. | feature | 6 | 6 | - | V2-19
V2-07 | V2 | V2-P4 Completeness + performance/speed | Full backend+frontend suite green twice on clean machine (local) | A1 | A1-2 | G9 | Testing | Testing | Critical | PARTIAL | 30% | Server suite is green; close the LOCAL clean-machine path so the whole backend+frontend suite runs green twice on a fresh checkout with no hand-set vars. Builds on the local test-config task. | Both suites exit 0 twice on a fresh local machine. Evidence: two green logs. | hardening | 10 | 7 | V1-03 | V2-01
V2-08 | V2 | V2-P4 Completeness + performance/speed | Standardize all native buttons onto StandardButton | A1,A3 | A3-3 | G6 | FrontEnd | FrontEnd | Important | PARTIAL | 10% | ~151 native buttons not on StandardButton. Migrate all to the standard component so styling is uniform current AND future (the Material-Investigation mismatch class is standardized away, not patched once). | A scan shows 0 native buttons outside StandardButton; visual-regression green. Evidence: scan + diff. | refactor | 14 | 12.6 | V2-04 | V2-02
V2-09 | V2 | V2-P4 Completeness + performance/speed | E2E action-matrix enumerating every demo-path control (CI gate) | A1,A3 | A1-5, A3-1 | G6 | Testing | Testing | Very important | PARTIAL | 40% | The action-matrix spec exists and is 20/20 green (handover); promote it to a BLOCKING CI gate that enumerates every control on every demo-path page and runs on push. | The action-matrix spec is green and blocking in CI. Evidence: the spec + CI run. | feature | 8 | 4.8 | V1-10 | V2-03
V2-10 | V2 | V2-P4 Completeness + performance/speed | Visual-regression harness (baseline + diff gate) | A3,A6 | A3-3, A6-8 | G6 | Testing | Testing | Important | NEW | 0% | Capture a baseline of every demo-path page and gate PRs on a pixel/DOM diff so styling never silently drifts. | A deliberate style change fails the diff gate; an intended change updates the baseline. Evidence: CI run. | feature | 6 | 6 | - | V2-04
V2-11 | V2 | V2-P4 Completeness + performance/speed | Performance-at-scale validation (630/5,600, virtualized tables) | A3 | A3-9 | G6 | FrontEnd | Testing | Important | NEW | 0% | Validate no hang/lag at demo scale; virtualize large tables; progress indicators on long loads. | At ~630 heats/~5,600 coils, no hang; tables virtualize; long loads show progress. Evidence: measured run. | feature | 8 | 8 | - | V3-10
V2-12 | V2 | V2-P4 Completeness + performance/speed | Real lead-capture backend (form->DB row+email via relay, e2e asserts) | A6 | A6-10 | G8 | Web | Backend | Important | PARTIAL | 30% | Harden the CTA path into a real backend: validated submit -> stored row + email (via the authenticated relay, never the VPS IP), with an e2e test asserting the row. Builds on the V1 lead-email code. | e2e asserts a lead row + email on submit through the relay. Evidence: the test. | feature | 6 | 4.2 | V1-18 | V2-22
V2-13 | V2 | V2-P5 Role/license/AI-boundary depth | MFA step-up for admin accounts | A2 | A2-4 | G12 | Security | Backend | Very important | NEW | 0% | TOTP/WebAuthn step-up enforced for admin roles per the identity doctrine. (sysadmin is the support account; MFA applies to any admin-capable login.) | An admin action triggers an MFA step-up live; non-admin does not. Evidence: test + clip. | feature | 8 | 8 | - | V2-07
V2-14 | V2 | V2-P5 Role/license/AI-boundary depth | Deepen license tiers: caps enforced + expiry/grace + admin governance | A5 | A5-3 | G12 | Security | Backend | Very important | PARTIAL | 20% | The signed-token activation works (proven on the server with Enterprise). Deepen ENFORCEMENT: seat/source/env caps actually enforced from the token; expiry -> warnings -> configurable read-only grace -> read-only (data never destroyed); soft-vs-hard caps; admin governance to add/manage seats. The 07-editions-and-licensing doc already describes the intended model. | Toggling a tier visibly adds/removes features AND enforces a cap live; an expired token enters grace then read-only. Evidence: tamper test + clips. | feature | 12 | 9.6 | - | V2-08
V2-15 | V2 | V2-P5 Role/license/AI-boundary depth | Real production Ed25519 license signing key (Option-1 -> Option-3) [NEW 26-Jun] | A2,A5 | A2-5, A5-3 | G12 | Security | Security | Very important | NEW | 0% | NEW from the 26-Jun session. The demo activates Enterprise with the DEV Ed25519 key (kid ppiq-dev-ed25519), registered only when PPIQ_PRESENTATION=on. For real customers: generate a REAL production Ed25519 signing keypair (kept in a secret store, never in git), sign per-customer/per-tier tokens with it, register the real public key through the canonical licensing/ops flow (not the dev fixture), and ensure the dev key is NEVER shipped/registered in a real customer Production. ALSO: real customer frontend builds must NOT bake VITE_SMOKE_* (demo credentials) into the bundle - gate the demo auto-login to the demo host only. | A real-key-signed per-customer token activates on a clean 'customer' install with PPIQ_PRESENTATION off and NO dev key registered; grep shows the dev key + VITE_SMOKE_* absent from a customer build. Evidence: activation log + grep. | feature | 10 | 10 | - | V2-09
V2-16 | V2 | V2-P5 Role/license/AI-boundary depth | Full RBAC role-scope live across 6 roles | A5 | A5-2 | G5 | Security | Backend | Very important | PARTIAL | 55% | Owner/Plant-Admin/Data-Engineer/Engineer/Operator/Viewer-Executive: enforce per-role view/edit scope on every page/endpoint and prove it across all six logins. (Server identity is DB-backed app_users; sysadmin is the owner.) | Authorization matrix green by identity; each role sees only its scope live. Evidence: matrix test + clips. | feature | 10 | 4.5 | - | V2-10
V2-17 | V2 | V2-P5 Role/license/AI-boundary depth | Wire DataBoundaryPolicy into assistant dispatch (no-egress live) | A2 | A2-8 | G13 | AI+ML | Backend | Very important | PARTIAL | 50% | Route every assistant call through the gateway so only question + scoped evidence leaves; honour a per-tenant no-egress toggle (self-hosted default). The 04-security doc commits to this. | Self-hosted mode leaks nothing; private-endpoint sends only question+evidence; toggle proven. Evidence: test + capture. | feature | 7 | 3.5 | - | V2-20
V2-18 | V2 | V2-P6 Documentation (screenshots) + web | User guide: embed app screenshots into the delivered 02-capabilities narrative | A3 | A3-2 | - | Docs | Docs | Important | MOSTLY-DONE | 70% | The narrative user guide is DELIVERED (02-platform-capabilities.md + index walk the platform feature by feature, zero placeholders). Remaining: capture real app screenshots from the live demo and embed them inline + a 9-step walkthrough section. | The guide carries screenshots matching the current UI alongside the delivered narrative. Evidence: the doc. | content | 6 | 1.8 | V1-11 | V2-23
V2-19 | V2 | V2-P6 Documentation (screenshots) + web | Install runbook: embed screenshots into the delivered 03-architecture narrative | A4 | A4-9 | G9 | Docs | Docs | Important | MOSTLY-DONE | 70% | The deployment narrative is DELIVERED (03-architecture-and-deployment.md covers SaaS/dedicated/on-prem/air-gapped). Remaining: add the concrete server runbook (infra plantprocessiq + app ppiq-app, the git-push pipeline, .env/secret handling, sysadmin first-login) WITH screenshots, cross-referencing Identity & Topology v4. | A clean machine reaches a working login by following the runbook only. Evidence: the runbook + a clean-follow log. | content | 8 | 2.4 | - | V2-24
V2-20 | V2 | V2-P6 Documentation (screenshots) + web | Admin/Operator guide: screenshots + two-admin model (05-onboarding delivered) | A4 | A4-1 | - | Docs | Docs | Important | MOSTLY-DONE | 70% | The onboarding/integration narrative is DELIVERED (05-data-onboarding-and-integration.md). Remaining: an admin/operator guide with screenshots covering source onboarding, mapping, jobs monitor, schema-drift, and the two-admin model (sysadmin vs the customer admin added at commissioning). | The guide covers each admin task with screenshots. Evidence: the doc. | content | 10 | 3 | - | V2-25
V2-21 | V2 | V2-P6 Documentation (screenshots) + web | Security whitepaper (DELIVERED as 04-security doc — verify + publish) | A2 | A2-1 | G12 | Docs | Docs | Important | MOSTLY-DONE | 85% | The security/procurement brief is DELIVERED (04-security-and-data-protection.md: read-only, identity incl. the two-admin model, secrets, isolation, encryption, audit, AI data boundary - each a design property). Remaining: confirm every stated control matches the shipped code (some are V2 enforcement tasks above) and add the Spamhaus-safe mail posture; then publish. | Each control in the doc maps to shipped behavior or a tracked task; mail posture added. Evidence: the doc + a control-to-code map. | content | 6 | 0.9 | - | V2-26
V2-22 | V2 | V2-P6 Documentation (screenshots) + web | API reference | A1 | A1-7 | - | Docs | Docs | Normal | NEW | 0% | Generate/author an API reference for the public endpoints (auth, licensing ed25519 activate/current with the licenseJws field, readiness, /api/v5/outbound/leads, etc.). | The reference lists each endpoint with request/response shapes (correct field names). Evidence: the doc. | content | 4 | 4 | - | V2-27
V2-23 | V2 | V2-P6 Documentation (screenshots) + web | Pricing & license-tiers PAGE (web) — content delivered in 07-editions doc | A5,A6 | A6-7 | G8 | Web | Web | Important | MOSTLY-DONE | 70% | The CONTENT exists: 07-editions-and-licensing.md states the editions, the signed-entitlement model, renewal, and caps. Remaining: render it as a public web page on the marketing site (honesty-lint green) and fill [[PER_PLANT_ACV_RANGE]]/[[FLEET_ACV_RANGE]] with your real numbers. | The page lists all four tiers with grants/renewal/caps; honesty-lint green; ACV ranges filled. Evidence: the page. | content | 5 | 1.5 | - | V2-16
V2-24 | V2 | V2-P6 Documentation (screenshots) + web | Naming golden-rule pass: rename phase/task-named artifacts | A1 | A1-4 | - | Docs | Database | Important | NEW | 0% | ~193 files carry phase/task tokens (p03_p04, phase8, T042, _v6_, hotfix). This includes the production SQL still named 301_p01_p02_authstore_compatibility_bridge.sql, 302_p02_*, 300_p01_p02_*, 500_v5_p01_*, etc. Rename to descriptive names and update references; preserve only ordered-migration numeric prefixes (strip the embedded phase label). The ppiq-app project rename is already done. | The phase/task-token grep returns 0 (outside ordered-prefix migrations); build + tests green; the server deploy stays green after the renames. Evidence: grep + green build + green deploy. | refactor | 18 | 18 | - | V2-28
V2-25 | V2 | V2-P4 Completeness + performance/speed | System logging to rolling file (systemLog_<day>_<hr>.log, hourly) | A1, A4 | A4.9 operational resilience | G9 | hardening | Backend | Very important | PARTIAL | 30% | Serilog + Sinks.File are already packaged but not configured to a system log file. Configure a structured system-oriented sink: systemLog_<yyyyMMdd>_<HH>.log with RollingInterval.Hour (a new file each hour), levels Info/Warning/Error, enrichers (machine, environment, the correlation id from CorrelationIdMiddleware), exceptions via Serilog.Exceptions. Log path and minimum level are env-configurable, never hardcoded. | Running the API writes systemLog_<day>_<hr>.log; a new file appears at the hour boundary; an induced warning and an induced error both land with timestamp, level, and correlation id (errors include the exception); log path/level are read from config, proven by an override. | hardening | 6 | 4.2 |  | (new)
V2-26 | V2 | V2-P4 Completeness + performance/speed | Job + Data operational logging to rolling files (JobLog/DataLog_<day>_<hr>.log) | A4 | A4.4 Jobs Monitor | G9 | hardening | Backend | Very important | NEW | 0% | Customer-oriented operational logging for EVERY job and data-source operation. Emit a structured event (job type, job name, severity, started/ended, duration, rows, outcome) for: connector reads, incremental/delta imports (DeltaImportExecutionService), mapping publish/rollback, and each correlation/learning job; hook JobRegistrationService + the two-stage functions. Write to JobLog_<day>_<hr>.log and DataLog_<day>_<hr>.log hourly AND persist the same events to a queryable store (table) so the in-app log tab can filter them. | Running an import + a correlation job produces Info events (start/finish, duration, rows) and any failure produces an Error event, in JobLog/DataLog_<day>_<hr>.log AND in the queryable store; a forced job crash is logged as Error with the reason; hourly rotation verified; events carry the job type/name/severity the log tab needs. | new feature | 8 | 8 |  | (new)
V2-27 | V2 | V2-P5 Role/license/AI-boundary depth | In-app Log tab on every page (filter by job type / name / severity / day) | A4, A3 | A4.4 Jobs Monitor | G6 | workflow | FrontEnd | Important | NEW | 0% | A collapsible Log panel docked at the bottom of every page (Dark-Industrial), reading the queryable job/data-log store. Filters: job type, job name, severity (Info/Warning/Error), and day. Live-updates while a job runs; severity colour-coded (ok/warn/crit tokens). Role-scoped (respects FormalRoleAccessMatrix). One generic log-query endpoint + the existing widget/data patterns - no endpoint-per-page. | On any page the Log tab opens and shows recent job/data events; each filter (type, name, severity, day) narrows results correctly; a running job streams new lines into the tab; an Error row renders in the crit colour; a viewer role sees only its permitted scope. | new feature | 10 | 10 |  | (new)
V2-28 | V2 | V2-P3 Value engine & justified numbers | ERADICATE hardcoded Stage-2; generic projector consumes no-code mappings (RED LINE) | A3, A1 | A1.6 generic/any-DB | G2 | workflow | Backend | Critical | NEW | 0% | WIRING-VALIDATED GAP (seam 5, the RED LINE): ppiq_run_stage2_canonical_refresh maps staging->canonical with a HARDCODED IF/ELSIF ladder, one branch per demo source shape (src_meltshop_pg.heats -> heat_no, src_caster_oracle_shape.cast_pieces -> piece_id + a hardcoded genealogy edge, src_hsm_oracle_shape.hsm_coils -> coil_id, plus 'Heat'/'Slab'/'Coil', 'FlatSteel', 'Europe/Berlin'). The no-code mapper UI (CanonicalSchemaMappingPanel + SchemaConfigurationService SchemaViewDefinitions) is DISCONNECTED from it. Replace the ladder with a generic projector that READS the active SchemaViewDefinition / mapping config (source table+column -> canonical field, plus the genealogy-edge rules) and builds the INSERT dynamically. The 8 demo sources become 8 SEED MAPPINGS, not 8 code branches. | ZERO hardcoded dataset-specific branches remain in ppiq_run_stage2_canonical_refresh (no src_*, no heat_no/coil_id/piece_id, no 'Heat'/'Slab'/'Coil', no 'FlatSteel', no 'Europe/Berlin'). A NEW non-demo source shape, mapped only in the no-code UI, projects into canonical with no code change. The 8 demo sources run as SEED MAPPINGS and the demo journey is byte-for-byte unchanged (C-0044170 + 0.70/0.30 regress green). The genericity CI gate passes. A mapping missing a required canonical field fails loudly with a typed error. | new feature | 20 | 20 |  | (new)
V2-29 | V2 | V2-P4 Completeness + performance/speed | Generic-Only CI gate - build FAILS on any dataset/industry-specific identifier in core | A1, A3 | A1.6 generic/any-DB | G10 | hardening | Testing | Critical | NEW | 0% | Make the Generic-Only red line ENFORCEABLE (same spirit as the CI truth-gate). Add an architecture test + CI lint that scans the core/canonical/projection/import path (Domain, Application, the SQL functions under database/scripts, the connectors' canonical mapping) and FAILS the build on any dataset/industry-specific literal: demo schema/table names (src_meltshop_pg, src_hsm_oracle_shape, ...), demo column names (heat_no, coil_id, piece_id, steel_grade, ...), industry type literals ('Heat','Slab','Coil','FlatSteel'), or hardcoded plant constants ('Europe/Berlin', fixed UTC offsets). Allow them ONLY inside seed-data / demo-mapping fixtures (explicit allowlist path). This keeps the product generic forever. | Re-introducing a hardcoded demo identifier into the canonical projection path turns the build RED (negative test). The gate runs in Jenkins and blocks merge. Seed/demo-mapping fixtures are allowlisted and pass. After V2's eradication task, the gate is GREEN on the real code. | hardening | 6 | 6
V3-01 | V3 | V3-P7 Deep security & ops hardening | Enforce RLS on core tables (decide tenant_id; non-superuser app role) | A2 | A2-6 | G12 | Security | Database | Very important | PARTIAL | 40% | Decide deliberately (RLS-scoped core vs single-tenant-per-deploy). If multi-tenant: add tenant_id to the core EF entities model-first, run the app under a non-superuser role so RLS is actually enforced (locally ppiq_dev is bypassrls), and prove cross-tenant 403/empty. NOTE: ppiq_ed25519_license_public_keys already demonstrates forced RLS - use it as the pattern. | Cross-tenant access returns 403/empty live under a non-superuser role. Evidence: RlsTenantIsolation test green + clip. | feature | 10 | 6 | - | V2-11
V3-02 | V3 | V3-P7 Deep security & ops hardening | Encryption at rest: staging/canonical/credential-vault | A2 | A2-9 | G12 | Security | Infra | Important | NEW | 0% | Encryption at rest for the app DB and the source-credential vault; document the key management. The 04-security doc already states this as a design property - implement + verify it. | At-rest encryption is on and verified; credentials are encrypted in the vault. Evidence: config + verification. | hardening | 6 | 6 | - | V2-12
V3-03 | V3 | V3-P7 Deep security & ops hardening | Move Jenkins to a separate Docker network from the app project [NEW 26-Jun] | A2 | A2-10 | G12 | Infra | Infra | Normal | NEW | 0% | NEW from the 26-Jun session. Today ppiq-jenkins and the app project share network reachability via the edge alias. Move Jenkins onto its own network so the CI/CD agent is isolated from the app stack (defense in depth), keeping only the Caddy fronting it. | Jenkins runs on a dedicated network; the app stack cannot reach Jenkins by name; deploys still work. Evidence: network inspect + a green deploy. | hardening | 4 | 4 | V2-13 | V2-15
V3-04 | V3 | V3-P7 Deep security & ops hardening | Wire SourceLoadProtectionPolicy into the live query path | A2 | A2-3 | G11 | Security | Backend | Very important | PARTIAL | 50% | Enforce the per-source impact budget on a real query path so an over-budget query is throttled, not just policy-defined. | An over-budget query is throttled live. Evidence: test + clip. | feature | 7 | 3.5 | - | V2-21
V3-05 | V3 | V3-P7 Deep security & ops hardening | Nightly full-suite CI job (cron) | A1 | A1-5 | G9 | Testing | Deploy | Very important | PARTIAL | 30% | The deploy pipeline runs on push; add a scheduled nightly job that runs the FULL backend+frontend+e2e suite and reports flaky tests, independent of pushes. | A nightly run exists and reports pass-rate + flaky count. Evidence: the cron job + a nightly report. | feature | 6 | 4.2 | V2-01 | V2-05
V3-06 | V3 | V3-P7 Deep security & ops hardening | Health dashboard (suite/e2e pass-rate, flaky count) | A1 | A1-5 | G9 | Testing | Web | Normal | NEW | 0% | A small dashboard surfacing suite pass-rate, e2e pass-rate, and flaky-test count over time. | The dashboard renders current + trend from real runs. Evidence: the page. | feature | 5 | 5 | V2-05 | V2-06
V3-07 | V3 | V3-P7 Deep security & ops hardening | HasDefaultSchema -> ppiq_meta/ppiq_plant for EF entities | A1 | A1-3 | - | Database | Database | Normal | NEW | 0% | Add HasDefaultSchema mapping so EF tables land in ppiq_meta/ppiq_plant instead of public, realising the app-metadata vs customer-data split. | `\dt ppiq_meta.*` and `ppiq_plant.*` list the EF tables after migrate. Evidence: psql output. | refactor | 4 | 4 | - | V2-29
V3-08 | V3 | V3-P8 Multi-industry & generic | Second-industry demo dataset (paper/board line) + mapping templates | A1,A3 | A3-11 | G3 | Demo | Database | Very important | NEW | 0% | A paper/board demo dataset (sources + fixtures) and mapping templates, built entirely through the HMI like the steel demo - proving the generic mandate the docs claim. | The paper demo builds from empty via HMI; a genealogy thread resolves on its keys. Evidence: clip. | feature | 14 | 14 | V1-04 | V3-01
V3-09 | V3 | V3-P8 Multi-industry & generic | Third-industry demo dataset (food & beverage) + tier configs | A1,A3 | A3-11 | G3 | Demo | Database | Very important | NEW | 0% | A food & beverage demo dataset + per-tier configs, same HMI-only build. | The F&B demo builds from empty via HMI. Evidence: clip. | feature | 12 | 12 | V3-01 | V3-02
V3-10 | V3 | V3-P8 Multi-industry & generic | Generic canonical-mapping template library + no-code visual-mapper polish | A1,A4 | A4-2 | G2 | Workflow | FrontEnd | Very important | NEW | 0% | A reusable template library + polish on the no-code visual mapper so the common case needs zero SQL across industries. | A non-developer maps a new source via templates + drag-drop, no SQL. Evidence: clip. | feature | 12 | 12 | V1-04 | V3-03
V3-11 | V3 | V3-P8 Multi-industry & generic | Demo dataset polish + per-industry scripted reset | A3 | A3-11 | G7 | Demo | Deploy | Important | PARTIAL | 60% | Polish each demo dataset and add a one-command scripted reset per industry so any prospect sees the same clean story. | One command resets+reseeds an industry to a known state. Evidence: run log. | feature | 6 | 2.4 | V3-01 | V3-04
V3-12 | V3 | V3-P8 Multi-industry & generic | Historian connector to GA (behavioural-tested) | A1,A2 | A2-2 | G1 | Workflow | Backend | Very important | NEW | 0% | Take one historian connector (e.g. OPC-UA) to GA with behavioural certification tests. | The historian connector passes behavioural certification + links live. Evidence: test + clip. | feature | 12 | 12 | - | V3-05
V3-13 | V3 | V3-P8 Multi-industry & generic | One-command customer-install package (per-industry overlay) | A4 | A4-9 | G9 | Infra | Deploy | Very important | NEW | 0% | Package a one-command customer install with a per-industry overlay, building on the green server pipeline + PPIQ_SITE_HOST host-derivation. | A fresh host installs + reaches login with one command + an overlay. Evidence: clean-install log. | feature | 8 | 8 | V2-13 | V3-06
V3-14 | V3 | V3-P9 Accessibility, i18n & scale | WCAG 2.1 AA light theme + contrast audit | A6 | A6-9 | G14 | FrontEnd | FrontEnd | Important | NEW | 0% | A WCAG 2.1 AA light theme + contrast audit across the app. | An automated WCAG audit passes AA; the light theme renders. Evidence: audit report. | feature | 10 | 10 | - | V3-07
V3-15 | V3 | V3-P9 Accessibility, i18n & scale | Arabic RTL + locale/units/timezone switching per user | A6 | A6-9 | G14 | FrontEnd | FrontEnd | Important | NEW | 0% | Arabic RTL layout + per-user locale/units/timezone switching. | Switching to Arabic re-flows RTL correctly; units/timezone follow the user. Evidence: clip. | feature | 8 | 8 | V3-09 | V3-08
V3-16 | V3 | V3-P9 Accessibility, i18n & scale | i18n as resource files (.resx/JSON) + fix mojibake | A1 | A1-1 | G14 | FrontEnd | Backend | Important | NEW | 0% | Move i18n out of SQL inserts (420/425/610) into resource files; fix the encoding-damaged strings. | Strings load from resource files; no mojibake; the SQL i18n inserts are retired. Evidence: diff + render. | refactor | 8 | 8 | - | V3-09
V3-17 | V3 | V3-P9 Accessibility, i18n & scale | Soak job (24-72h synthetic load on demo path) | A4 | A4-9 | G9 | Testing | Testing | Important | NEW | 0% | A 24-72h synthetic-load soak against the demo path to catch leaks/instability. | A 24h+ soak completes with no leak/regression. Evidence: soak report. | feature | 8 | 8 | - | V3-11
V3-18 | V3 | V3-P9 Accessibility, i18n & scale | Real-domain TLS cutover (off sslip.io) [NEW 26-Jun] | A2,A6 | A6-6 | G9 | Infra | Deploy | Important | NEW | 0% | NEW from the 26-Jun session. The demo runs on 178.105.152.180.sslip.io with host-derived URLs (PPIQ_SITE_HOST). To move to a real domain: set PPIQ_SITE_HOST=<domain>, CADDY_AUTO_HTTPS=on, ACME_EMAIL=<addr>, point real DNS, and let Caddy issue real certs - all URLs + CORS follow automatically. | The app/api/website serve on the real domain over valid public TLS; CORS allows the real origins. Evidence: cert + curl. | hardening | 6 | 6 | V2-13 | V3-12
V3-19 | V3 | V3-P9 Accessibility, i18n & scale | QES product page to depth | A6 | A6-7 | G8 | Web | Web | Optional | NEW | 0% | Take the QES product page to full depth (was 'coming soon'). | The QES page is complete; honesty-lint green. Evidence: the page. | content | 7 | 7 | - | V3-13
V3-20 | V3 | V3-P9 Accessibility, i18n & scale | Energy Management product page to depth | A6 | A6-7 | G8 | Web | Web | Optional | NEW | 0% | Take the Energy Management product page to full depth. | The Energy page is complete; honesty-lint green. Evidence: the page. | content | 7 | 7 | - | V3-14
V3-21 | V3 | V3-P7 Deep security & ops hardening | Multi-tenancy: tenant column on material_units + tenant-parameterized canonical layer + RLS | A2, A1 | A2.6 tenant isolation | G12 | hardening | Database | Very important | NEW | 0% | CODE-VALIDATED GAP: the canonical layer is single-tenant-baked. canonical_material_units / canonical_genealogy_edges (310_mapping_genealogy_foundation.sql) are VIEWS with a HARDCODED tenant_id constant; material_units has NO tenant column; two tests only agree because a migration forces the constant to be the earliest ppiq_tenants row. Add a real tenant_id to material_units (+ backfill migration), parameterize the canonical views by the session tenant, and put RLS on the base tables so a customer can never read another tenant's rows. Model-first: EF entity + IEntityTypeConfiguration + ModelSnapshot in sync; DB constructs in a numbered SQL migration. | A cross-tenant query returns 0 rows / 403 (RLS proven by test); the canonical views resolve the SESSION tenant, not a constant; the genealogy tests pass without relying on 'earliest row == constant'; a second seeded tenant's data is fully isolated end-to-end. | hardening | 16 | 16 |  | (new)
V3-22 | V3 | V3-P7 Deep security & ops hardening | i18n-harden the honesty + grounding gates (structural, not English keywords) | A5, A2 | A5.4 trustworthy AI | G4 | hardening | Backend | Important | NEW | 0% | CODE-VALIDATED GAP (violates the EN/DE/AR i18n doctrine): ValueHonestyLint forbids English literals ('guaranteed','will save') and GroundingService's forbidden-phrase list is English-only ('root cause','is caused by'...). The number-block is structural (good) but the phrase-block breaks in German/Arabic. Replace English-keyword phrase detection with structural/typed signals: a causation-assertion type flag on claims, claim-type metadata, and locale-aware resource-backed term sets - so the honesty/causation gate holds in EN/DE/AR. | The honesty/causation gate blocks the same intent in German and Arabic test fixtures (not just English); no raw English-keyword regex remains in the value/grounding path; the existing English tests still pass. | hardening | 8 | 8 |  | (new)
V3-23 | V3 | V3-P7 Deep security & ops hardening | Log retention, size caps & optional forwarding (ops policy) | A4, A2 | A4.9 operational resilience | G9 | hardening | Infra | Normal | NEW | 0% | Production logging policy: a retention window (delete/compress logs older than N days), per-file and total size caps, and an optional forward target (a file share or syslog/OTLP) - all env-configurable. Ensure logs never fill the VPS disk; ensure no secrets are written (scrub connection strings/tokens from log output). | Logs older than the configured window are pruned/compressed; total log size stays under the cap under a soak; a secret deliberately passed through is NOT present in any log (scrub test); the forwarding target receives events when enabled. | hardening | 4 | 4 |  | (new)
V4-01 | V4 | V4-P10 Ops / HA + OT | Backup/restore drill (verified restore, recorded) | A4 | A4-9 | G9 | Infra | Deploy | Very important | NEW | 0% | Drill a full backup + verified restore of the app DB; record it. Closes the restore half of A4-9/G9 the deploy session did not. | A restore from backup reaches a working login; recorded. Evidence: the recording. | feature | 8 | 8 | - | V4-01
V4-02 | V4 | V4-P10 Ops / HA + OT | Verify deploy rollback to :previous | A4 | A4-9 | G9 | Infra | Deploy | Important | NEW | 30% | The pipeline already tags :previous and rolls back on a failed health gate. Verify it end-to-end by inducing a health-gate failure and confirming the rollback restores service. | An induced bad deploy rolls back to :previous and service stays up. Evidence: pipeline log. | verification | 5 | 3.5 | - | V4-02
V4-03 | V4 | V4-P10 Ops / HA + OT | Time-series store (hypertables, compression, retention) | A4 | A4-8 | G9 | Infra | Database | Very important | NEW | 0% | Introduce a time-series store (hypertables/columnar, compression, downsampling, retention) for high-frequency parameters. | Parameter data lands in the time-series store with compression + retention. Evidence: schema + query. | feature | 12 | 12 | - | V4-03
V4-04 | V4 | V4-P10 Ops / HA + OT | Deployable OT-safe edge agent (one-way push) | A2 | A2-2 | G11 | Infra | Backend | Very important | NEW | 0% | Build a deployable Edge Collector that pushes one-way from the DMZ; the core never connects into OT. The docs already describe this model. | The agent pushes one-way; no inbound path to OT; load within budget. Evidence: deploy + capture. | feature | 12 | 12 | - | V4-04
V4-05 | V4 | V4-P10 Ops / HA + OT | Human-approved advisory write-back (business workflow, never OT) | A5 | A5-9 | G5 | Backend | Backend | Very important | NEW | 0% | Advisory write-back into business workflow (case/action tracking) with human approval - never a setpoint/command to control. | An approved advisory creates a tracked action; no OT write path exists. Evidence: workflow + code-search. | feature | 10 | 10 | - | V4-05
V4-06 | V4 | V4-P10 Ops / HA + OT | Enforce performance budgets in CI | A1 | A1-2 | G6 | Testing | Testing | Important | NEW | 0% | Add performance budgets as CI gates so regressions fail the build. | A deliberate perf regression fails CI. Evidence: CI run. | feature | 6 | 6 | - | V4-06
V4-07 | V4 | V4-P10 Ops / HA + OT | Load-test at reference-plant scale | A4 | A4-9 | G9 | Testing | Testing | Very important | NEW | 0% | Load-test at realistic reference-plant scale (well beyond demo scale). | The system holds at reference scale within budget. Evidence: load report. | feature | 8 | 8 | - | V4-07
V4-08 | V4 | V4-P11 Compliance + ops | Start SOC 2 Type II observation window | A2 | A2-9 | G16 | Docs | Security | Very important | NEW | 0% | Begin the SOC 2 Type II observation window (controls evidenced over time). | The observation window is open with controls evidenced. Evidence: the tracker. | content | 10 | 10 | - | V4-08
V4-09 | V4 | V4-P11 Compliance + ops | ISO 27001 mapping + sensitive-data catalog | A2 | A2-9 | G16 | Docs | Security | Important | NEW | 0% | Map controls to ISO 27001 and catalog sensitive data. | The mapping + catalog exist. Evidence: the docs. | content | 8 | 8 | - | V4-09
V4-10 | V4 | V4-P11 Compliance + ops | GxP / 21 CFR Part 11 pack (audit trail, e-signature) | A2 | A2-9 | G16 | Docs | Security | Optional | NEW | 0% | A GxP / 21 CFR Part 11 pack where required (audit trail + e-signature). | The pack evidences audit trail + e-signature. Evidence: the docs. | content | 12 | 12 | - | V4-10
V4-11 | V4 | V4-P11 Compliance + ops | Public status page | A4 | A4-9 | - | Web | Web | Normal | NEW | 0% | A public status page for the hosted service. | The status page reflects real health. Evidence: the page. | content | 4 | 4 | - | V4-11
V4-12 | V4 | V4-P11 Compliance + ops | AI triage loop (agent drafts fix PRs, human-approved) | A1 | A1-5 | - | AI+ML | Testing | Important | NEW | 0% | An AI triage loop where an agent drafts fix PRs from failing tests, human-approved. | The loop drafts a PR for an injected failure; human merges. Evidence: the PR. | feature | 10 | 10 | - | V4-12
V4-13 | V4 | V4-P11 Compliance + ops | Recorded certified dry-run (one-click readiness on video) | A4 | A4-7 | G7 | Demo | Docs | Very important | NEW | 0% | A recorded certified dry-run showing one-click readiness green - the reference acceptance artifact. | The recording shows readiness green end-to-end. Evidence: the file. | content | 4 | 4 | V1-09 | V4-13
V4-14 | V4 | V4-P11 Compliance + ops | Consolidate full operator/admin/security docs | A4 | A4-9 | - | Docs | Docs | Important | NEW | 30% | Consolidate the delivered doc suite (01-09) + the screenshot-embedded guides into one coherent, cross-linked, versioned doc set. | One consolidated doc set, cross-linked. Evidence: the docs. | content | 8 | 5.6 | V2-24 | V4-14
V4-15 | V4 | V4-P12 Business / reference | Incorporate (UG/GmbH) + imprint | A5 | - | - | Web | Docs | Very important | NEW | 0% | Incorporate the company (UG/GmbH) and add the legal imprint. | The entity exists + imprint published. Evidence: the registration. | content | 8 | 8 | - | V4-15
V4-16 | V4 | V4-P12 Business / reference | Pilot contract + MNDA + DPA templates | A5 | - | - | Docs | Docs | Very important | NEW | 0% | Pilot contract, mutual NDA, and DPA templates ready to sign (the 08-pilot doc is the commercial offer; these are the legal instruments). | The three templates exist + reviewed. Evidence: the files. | content | 8 | 8 | - | V4-16
V4-17 | V4 | V4-P12 Business / reference | Target list + outreach sequence (PSI network) | A5 | - | - | Web | Docs | Very important | NEW | 0% | A target list + outreach sequence leveraging your PSI/SMS network. | The list + sequence exist + first touches sent. Evidence: the tracker. | content | 10 | 10 | - | V4-17
V4-18 | V4 | V4-P12 Business / reference | Convert presentation customer into a signed paid pilot | A5 | - | - | Web | Docs | Critical | NEW | 0% | Convert the presentation prospect into a signed paid pilot (using the delivered 08-pilot offer with your price filled). | A signed pilot agreement exists. Evidence: the signature. | content | 12 | 12 | V1-16 | V4-18
V4-19 | V4 | V4-P12 Business / reference | Prove ROI on the customer's real data (pilot deliverable) | A5 | A5-1 | G5 | AI+ML | AI+ML | Critical | NEW | 0% | On the customer's real data, prove a bounded ROI - the pilot deliverable. | A proven (not projected) euro figure on the customer's data. Evidence: the report. | feature | 8 | 8 | V4-18 | V4-19
V4-20 | V4 | V4-P12 Business / reference | Run the paid pilot | A4,A5 | - | - | Workflow | Backend | Critical | NEW | 0% | Run the paid pilot end-to-end on the customer's environment. | The pilot completes its scope. Evidence: the pilot log. | feature | 20 | 20 | V4-18 | V4-20
V4-21 | V4 | V4-P12 Business / reference | Convert pilot to a signed contract | A5 | - | - | Web | Docs | Critical | NEW | 0% | Convert the completed pilot into a signed annual contract. | A signed contract exists. Evidence: the signature. | content | 12 | 12 | V4-20 | V4-21
V4-22 | V4 | V4-P12 Business / reference | Produce the case study / reference | A5 | - | - | Web | Docs | Very important | NEW | 0% | Produce a case study / reference from the pilot customer. | A published case study + a reference contact. Evidence: the file. | content | 6 | 6 | V4-21 | V4-22
V4-23 | V4 | V4-P12 Business / reference | Viability arrangement (hire / escrow+BCP / partner) | A5 | - | - | Web | Docs | Very important | NEW | 0% | Close the bus-factor objection: a hire, source escrow + BCP, or a partner. | A viability arrangement is in place. Evidence: the agreement. | content | 12 | 12 | - | V4-23
V4-24 | V4 | V4-P12 Business / reference | Support SLA offering | A4 | - | - | Docs | Docs | Important | NEW | 0% | A support SLA offering (tiers, response times). | The SLA offering exists. Evidence: the doc. | content | 5 | 5 | - | V4-24
V4-25 | V4 | V4-P12 Business / reference | Funding / partnership decision | A5 | - | - | Web | Docs | Normal | NEW | 0% | Decide funding/partnership direction. | A decision recorded. Evidence: the note. | content | 4 | 4 | - | V4-25

## Version Summary
Version Summary v12
Version | Tasks | Scope (h) | Remaining (h)
V1 | 30 | 122 | 73.4
V2 | 29 | 258 | 188.9
V3 | 23 | 188 | 175.1
V4 | 25 | 222 | 218.1
TOTAL | 107 | 790 | 655.5