## Sheet1
No. | Task Name | Task Level | Backend / Frontend / Both | Task Group | Task Brief Description | Task Detailed Description
1 | Run backend build and confirm zero errors | Critical | Backend | Validation | Confirm full backend solution compiles. | Run dotnet build on the full solution and confirm Domain, Application, Infrastructure, Api, and Workers compile cleanly. This is the first gate before any new feature work.
2 | Run frontend build and confirm zero errors | Critical | Frontend | Validation | Confirm React/Vite app compiles. | Run npm run build in the frontend project and fix all TypeScript, import, and component errors. This is especially important after adding WidgetBuilderWizard.
3 | Apply migrations and verify schema alignment | Critical | Backend | Validation | Confirm DB matches EF model. | Apply all migrations including the latest dashboard definitions migration. Start the API and verify no EF schema mismatch appears.
4 | Smoke test critical API endpoints | Critical | Backend | Validation | Prove runtime API behavior. | Test health, dashboard workspace, dashboard metadata, widget query, correlation, material investigation, PDF report, and data quality scan endpoints.
5 | Smoke test dashboard UI in browser | Critical | Frontend | Validation | Prove dashboard runs visually. | Open the React app with backend running and verify dashboard pages, cards, filter UI, wizard opening, and routing.
6 | Validate drag, resize, and reflow | Critical | Frontend | Dashboard UX | Confirm dashboard layout behavior. | Test widget drag, resize, responsive breakpoints, full-row expansion, fullscreen, collapse, and hidden states.
7 | Validate filter interaction | Critical | Frontend | Dashboard UX | Confirm global filter behavior. | Apply dashboard filters and selection breadcrumbs, then validate affected charts/tables refresh correctly.
8 | Validate theme consistency | Important | Frontend | UI Theme | Confirm dark/light theme stability. | Test dark default theme, light theme toggle, localStorage theme memory, and visual consistency across all pages.
9 | Validate worker startup and scheduled jobs | Critical | Backend | Validation | Confirm Workers project runs. | Start Workers and verify import queue processor, data-quality scan, and risk scoring jobs start without configuration errors.
10 | Verify backend API port configuration | Critical | Backend | Configuration | Confirm API does not rely on fixed port. | Validate API can run through ASPNETCORE_URLS or environment configuration without editing source files.
11 | Verify frontend port configuration | Important | Frontend | Configuration | Confirm Vite port can be changed. | Validate frontend can run on a configured port and still communicate with backend through environment variables.
12 | Verify database port configuration | Critical | Backend | Configuration | Remove hardcoded DB assumptions. | Ensure DB host, port, database, username, and password are environment-driven, not hardcoded in development JSON.
13 | Confirm CORS origins are configurable | Critical | Backend | Configuration | Validate deployment-safe CORS. | Keep allowed origins configurable by appsettings and environment variable. Production must reject empty or localhost-only unsafe origins.
14 | Verify no hidden frontend localhost fallback | Critical | Frontend | Configuration | Prevent accidental wrong API target. | Confirm VITE_API_BASE_URL is required and the frontend fails clearly if it is missing. No silent localhost fallback should exist.
15 | Create full-stack .env.example | Critical | Both | Configuration | Make setup repeatable. | Add all required variables for API URL, ports, DB, CORS, logging, secrets, and feature flags. This is required for Docker/team/demo setup.
16 | Validate Docker Compose variables | Important | Both | Configuration | Make Docker portable. | Update Docker Compose to consume env variables for API, frontend, PostgreSQL, and allowed origins.
17 | Add Swagger/OpenAPI examples | Important | Backend | Developer Experience | Improve API usability. | Add useful examples for dashboard query, source registration, mapping preview, import batch, readiness, and report endpoints.
18 | Complete widget dimension and measure step | Critical | Frontend | Dashboard Builder | Add wizard step 3. | Extend the wizard to select dimension, measure, and parameter where required using backend metadata compatibility rules.
19 | Complete widget filter step | Critical | Frontend | Dashboard Builder | Add filter configuration. | Add site, area, equipment, material type, defect, risk class, source system, date range, and parameter filters.
20 | Complete widget preview step | Critical | Both | Dashboard Builder | Preview widget before saving. | Call backend widget query endpoint and render chart/table preview inside the wizard. Show validation errors clearly.
21 | Add dashboard/widget save API | Critical | Backend | Dashboard Persistence | Persist widgets in DB. | Add endpoints and services to create, update, delete, and retrieve dashboards and widgets using DashboardDefinition and DashboardWidgetDefinition.
22 | Save widget from frontend wizard | Critical | Frontend | Dashboard Persistence | Finish add-widget flow. | After preview, save the widget to backend and refresh the dashboard workspace automatically.
23 | Persist dashboard layout to backend | Critical | Both | Dashboard Persistence | Replace localStorage layout. | Save grid layout to backend instead of relying on localStorage. Keep localStorage only as fallback or temporary draft cache.
24 | Add widget edit, remove, and clone | Important | Both | Dashboard Builder | Manage saved widgets. | Add widget action menu for rename, edit, remove, duplicate, hide, collapse, and fullscreen.
25 | Add system dashboard templates | Important | Both | Dashboard Templates | Provide ready dashboards. | Seed templates for Quality Overview, Risk Dashboard, Data Quality, Correlation, and Material Investigation.
26 | Add dashboard performance indexes | Critical | Backend | Performance | Prevent slow dashboard queries. | Add indexes on material, timestamps, equipment, quality event date, defect, risk class, source system, and process step references.
27 | Create ConnectionProfile entity | Critical | Backend | Connector Foundation | Store source connection metadata. | Add provider, connection mode, host, port, database/schema, file path, API URL, active flag, and read-only flag.
28 | Add provider type classification enum | Critical | Backend | Connector Foundation | Normalize provider types. | Define providers such as CSV, Excel, PostgreSQL, SQL Server, Oracle, MySQL, and REST API.
29 | Add SecretReference strategy | Critical | Backend | Connector Security | Avoid storing passwords. | Store secret references instead of plain credentials, resolving from environment variables, Docker secrets, or future vault integration.
30 | Add connection validation rules | Critical | Backend | Connector Foundation | Validate profile fields. | Enforce required profile fields based on provider type and connection mode.
31 | Create SourceDatasetDefinition entity | Critical | Backend | Source Schema | Represent source tables/files/sheets. | Store dataset name, type, schema, table/view/file/sheet name, profile ID, and discovery metadata.
32 | Create SourceFieldDefinition entity | Critical | Backend | Source Schema | Represent source columns. | Store field name, source data type, nullable flag, ordinal, sample value, and profiling metadata.
33 | Link StagingRecord to source dataset | Critical | Backend | Staging | Improve lineage. | Add SourceDatasetDefinitionId so each staged row knows its exact source dataset, not only source system.
34 | Define connector abstraction interfaces | Critical | Backend | Connector Framework | Create generic connector contract. | Add IDataSourceConnector, ISchemaReader, and IDataSourceReader interfaces in Application.
35 | Add connector factory | Critical | Backend | Connector Framework | Resolve connector by provider. | Implement factory in Infrastructure to return the correct connector implementation based on provider type.
36 | Add connection test endpoint | Critical | Backend | Connector Framework | Test source connectivity. | Add endpoint to validate connection profile, resolve secret reference, and return success/failure with response time.
37 | Add CSV connector MVP | Critical | Backend | Connector Framework | First safe connector. | Implement CSV schema discovery, sample preview, and import-to-staging. CSV is the best first customer-safe connector.
38 | Add Excel connector MVP | Important | Backend | Connector Framework | Support spreadsheet exports. | Implement sheet discovery, header detection, field extraction, sample preview, and staging import.
39 | Add PostgreSQL connector MVP | Important | Backend | Connector Framework | Read external PostgreSQL sources. | Implement read-only discovery and sample reading from external PostgreSQL databases.
40 | Add SQL Server connector MVP | Important | Backend | Connector Framework | Read MES/L2 MSSQL sources. | Implement read-only table/view/field discovery and sample preview using SQL Server connector.
41 | Add Oracle connector MVP | Important | Backend | Connector Framework | Read Oracle plant databases. | Implement Oracle connector skeleton and read-only schema discovery for Oracle-heavy industrial environments.
42 | Add schema discovery API | Critical | Backend | Source Schema | Discover and store source schema. | Add endpoint to discover datasets and fields from a selected connection profile and save them.
43 | Add sample rows preview API | Critical | Backend | Source Schema | Preview source rows. | Return a limited preview of rows before staging/importing data. This is essential for mapping confidence.
44 | Add source dataset and field discovery UI | Important | Frontend | Source UI | Browse discovered source schema. | Add UI to trigger schema discovery and browse datasets, fields, data types, and sample values.
45 | Add source management UI | Important | Frontend | Source UI | Manage source connections. | Add pages to create, edit, test, activate, and deactivate connection profiles.
46 | Upgrade staging lifecycle states | Critical | Backend | Staging | Track import lifecycle. | Add/confirm states such as Created, Queued, Running, Completed, Failed, PartiallyMapped, Replayed, and Skipped.
47 | Add row checksum/hash | Important | Backend | Staging | Detect duplicate raw rows. | Compute deterministic hash per staged row to detect duplicates and changed rows.
48 | Add bulk staging insert optimization | Important | Backend | Staging | Support large imports. | Use efficient bulk insert for staging records, ideally PostgreSQL COPY for large CSV/source loads.
49 | Add import monitoring UI | Important | Frontend | Operations UI | Monitor import batches. | Show import batch status, row counts, failures, timestamps, and rerun options.
50 | Upgrade MappingDefinition for field-level mapping | Critical | Backend | Mapping | Store source-to-canonical rules. | Add structured mapping rules linking source fields to canonical fields with transform and unit rules.
51 | Add mapping validation service | Critical | Backend | Mapping | Validate before execution. | Check missing required fields, invalid target fields, incompatible types, duplicate mappings, and unsupported transformations.
52 | Add mapping preview endpoint | Critical | Both | Mapping | Preview canonical output. | Preview mapped rows before committing canonical records and show transformation errors clearly.
53 | Add transformation rules engine | Important | Backend | Mapping | Transform source values. | Support trim, parse date, parse decimal, enum mapping, default value, lookup, and null handling.
54 | Add unit normalization service | Important | Backend | Mapping | Normalize measurement units. | Convert common manufacturing units for temperature, length, mass, time, speed, pressure, and force.
55 | Add mapping workbench API endpoints | Important | Backend | Mapping | Support full mapping UI. | Add endpoints for source fields, canonical targets, mapping creation, validation, preview, activation, and execution.
56 | Add mapping workbench UI | Important | Frontend | Mapping UI | Visually map source fields. | Build UI with source fields, canonical target fields, transform rules, preview, validation errors, and save/activate actions.
57 | Add failed-row viewer and rerun | Important | Both | Mapping / Operations | Fix failed imports/mappings. | Let users inspect failed rows, see error reasons, and rerun after fixing mapping or source data.
58 | Add mapping versioning | Normal | Backend | Mapping Governance | Track mapping changes. | Store mapping version, effective date, author, and change reason.
59 | Add source lineage consistently to canonical records | Important | Backend | Data Lineage | Ensure all mapped records trace back. | Audit canonical entities so mapped records keep source system, import batch, dataset, and source record reference.
60 | Perform canonical model neutrality audit | Critical | Backend | Domain Governance | Confirm product is not steel-only. | Review entities, services, DTOs, metadata, and seed data to ensure steel terms remain configuration/demo metadata only.
61 | Add QualityDecision entity | Important | Backend | Domain Model | Store formal quality outcomes. | Model Accept, Reject, Hold, Rework, Downgrade, Claim, or Release decisions separately from quality events.
62 | Add InspectionResult entity | Important | Backend | Domain Model | Store inspection-specific results. | Model Visual, NDT, Dimensional, Camera, Manual, and Lab inspection results separately from broad quality events.
63 | Add Sample and SampleResult entities | Normal | Backend | Domain Model | Store lab/sample data. | Model chemistry, mechanical, dimensional, environmental, or quality sample results.
64 | Add ParameterWindow entity | Important | Backend | Process Intelligence | Store expected process ranges. | Configure min/max/target process windows by parameter, operation, equipment, route, material type, or industry template.
65 | Add AggregatedFeature entity and persistence | Important | Backend | Analytics Performance | Persist feature-engineering outputs. | Store calculated feature vectors per material to avoid repeated heavy recalculation.
66 | Add scheduled feature refresh job | Important | Backend | Analytics Performance | Keep features updated. | Add worker job to refresh aggregated features after imports/mapping executions.
67 | Add materialized/read-model refresh strategy | Normal | Backend | Performance | Optimize heavy dashboard metrics. | Add read-model/materialized aggregation refresh for expensive dashboard queries once datasets grow.
68 | Add quality label builder | Important | Backend | ML Foundation | Generate ML labels. | Build labels from quality events, decisions, defect catalogs, and time windows for defect/no-defect or reject/no-reject training.
69 | Add Python baseline training script | Important | Backend / ML | ML Foundation | Start real ML path. | Add script using scikit-learn to train baseline models from exported feature/label dataset.
70 | Add prediction explanation storage | Important | Backend | ML Explainability | Store risk contributors. | Extend risk score/explanation storage with top contributing features, values, direction, and explanation text.
71 | Add model comparison in registry | Normal | Backend | ML Governance | Compare model versions. | Store AUC, precision, recall, F1, training window, validation window, and sample counts.
72 | Upgrade readiness scoring dimensions | Important | Backend | Readiness Product | Make readiness more detailed. | Score source availability, schema, mapping, genealogy, data quality, correlation, and prediction readiness separately.
73 | Add commercial readiness report endpoint | Important | Backend | Readiness Product | Package readiness for customers. | Create structured readiness report with findings, blockers, scores, pilot feasibility, and next actions.
74 | Add readiness PDF export | Important | Backend | Reporting | Make readiness sales-ready. | Export readiness assessment into a formatted PDF for workshops and customer follow-up.
75 | Upgrade material investigation report | Important | Both | Reporting | Add full context. | Include genealogy, process timeline, parameters, risk contributors, quality decisions, inspection results, and data-quality issues.
76 | Upgrade PDF export formatting | Important | Backend | Reporting | Make report customer-grade. | Replace simple PDF output with branded sections, tables, charts, footer, timestamp, and disclaimer.
77 | Upgrade correlation UI with genealogy context | Important | Frontend | Analytics UI | Show upstream/downstream context. | Display genealogy link mode, parent material, child material, process step, and depth for correlation results.
78 | Add authentication foundation | Critical | Both | Security | Protect all APIs. | Implement JWT or Identity-based login and require authentication for API access.
79 | Add RBAC roles and permission policies | Critical | Both | Security | Restrict sensitive actions. | Add Admin, DataManager, Engineer, and Viewer roles with policies for source, mapping, dashboard, reports, and security.
80 | Add tenant/customer/site isolation | Critical | Both | Security / Productization | Prepare for multi-customer future. | Add tenant/customer boundary or at least design it now so future data isolation is not painful.
81 | Add audit log entity and service | Critical | Backend | Audit | Track critical changes. | Audit source profiles, mappings, imports, dashboards, widgets, reports, security actions, and risk calculations.
82 | Add data retention rules | Important | Backend | Compliance | Control retention. | Configure retention for staging data, failed rows, audit logs, reports, and risk scores.
83 | Add secure secret resolution | Critical | Backend | Security | Resolve credentials safely. | Resolve secrets from environment/Docker/future vault and mask them in logs/API.
84 | Add backend unit tests | Important | Backend | Testing | Protect core services. | Test widget validation, mapping validation, data quality, risk scoring, feature engineering, and readiness scoring.
85 | Add integration tests with PostgreSQL | Important | Backend | Testing | Validate workflows. | Test import → staging → mapping → canonical → dashboard/correlation/report flow against real test DB.
86 | Add frontend component tests | Normal | Frontend | Testing | Protect dashboard UI. | Test wizard navigation, filters, dashboard layout actions, and preview error handling.
87 | Add CI/CD build pipeline | Important | Both | DevOps | Automate validation. | Pipeline should run backend build, frontend build, tests, and optionally migration validation.
88 | Create customer-safe synthetic dataset pack | Important | Both | Demo Data | Create repeatable demo data. | Prepare synthetic manufacturing data with known hidden patterns across genealogy, parameters, quality events, and risk.
89 | Prepare 10-minute end-to-end demo script | Important | Both | Sales Readiness | Tell one clear product story. | Script should cover source, mapping, readiness, dashboard, correlation, risk, investigation, and report.
90 | Prepare pilot scope template | Important | Both | Sales Readiness | Control first customer pilot. | Define route, defect family, data sources, required fields, deliverables, timeline, assumptions, and go/no-go criteria.
91 | Create customer data discovery checklist | Normal | Both | Sales Readiness | Guide readiness workshops. | Checklist should cover MES/L2/historian/lab/inspection/ERP sources, access method, keys, timestamps, genealogy, quality labels, and IT constraints.
92 | Create honest product capability summary | Normal | Both | Sales Governance | Prevent over-promising. | Summarize what works today, what is partial, what is missing, and what must not be promised yet.
93 | Add AI-assisted chart suggestion | Optional | Both | AI Assistant | Suggest widget config from natural language. | Only implement after widget builder and metadata validation are stable. AI output must pass backend validation before use.
94 | Add embedded BI integration option | Optional | Both | BI Integration | Support Qlik/Power BI embedding. | Add optional embedded BI panel controlled by feature flag while keeping PlantProcess IQ as the intelligence backend.
95 | Add audit log | Critical | Backend | Track critical changes. | Audit changes to source systems, connection profiles, mappings, dashboards, widgets, imports, and security settings. This is essential for industrial customer trust. | Audit records created for changes.
96 | Add backend unit tests | Important | Backend | Protect domain/service logic. | Add tests for services such as mapping, data quality, dashboard metadata, widget validation, and risk scoring. This reduces regression as the product grows. | Unit tests run successfully.
97 | Add integration tests | Important | Backend | Test API + database behavior. | Add integration tests using a test PostgreSQL database. Cover dashboard metadata, widget query, import workflow, mapping preview, and data-quality scan. | Integration tests pass reliably.
98 | Add frontend component tests | Normal | Frontend | Protect dashboard UI behavior. | Add tests for dashboard filters, widget builder, chart preview, and layout behavior. This is useful after the builder UI stabilizes. | Key UI tests pass.
99 | Add CI build pipeline | Normal | Both | Automate build and test checks. | Add a pipeline that runs backend build, frontend build, and tests. This prevents broken changes from silently entering the project. | Pipeline passes on commit.
100 | Prepare demo script | Important | Both | Create a clean 10-minute demo. | Prepare a demo flow showing source registration, staging, mapping, dashboard, dynamic widget creation, correlation, risk, and investigation report. This turns the product into something explainable to customers. | Demo can be presented end-to-end.
101 | Prepare pilot scope template | Important | Both | Define first customer pilot structure. | Create a template for one route, one defect family, selected source systems, required fields, expected outputs, and timeline. This keeps pilot discussions controlled and avoids scope explosion. | Pilot template is ready to reuse.
102 | Add AI-assisted chart suggestions | Optional | Both | Suggest widgets from natural language. | Later, allow users to type prompts like “show defect rate by casting speed.” This should only come after metadata, widget query, and saved dashboards are stable. | AI suggestion creates valid widget draft.
103 | Add embedded BI option | Optional | Both | Support Qlik/Power BI hybrid mode. | Later, allow optional embedded Qlik/Power BI dashboards while keeping PlantProcess IQ as the intelligence backend. This is useful for enterprise customers already using BI tools. | BI embed works without replacing core product.