## Active Board
PPIQ PRODUCT BACKLOG v25 - 21-Jul-2026. M1 reframed to the 7 presentation targets (Parts A+B >=75% FRONTEND-demonstrable, engine >=75%, chatbot >=75%, journey on faked data, 3 premade pages + 1 built live). Frozen-ID law upheld; canvas/associative/catalogue = M2 (M2-31/37/38). New M1 target-tracker rows M1-34..M1-40.
ID | Milestone | Phase | Group | Task Name | Severity | Type | Module | Status | Est (h) | Origin | Description (junior-complete) | Validation / Acceptance
M1-18 | M1 | M1-P1 Golden Chain | G0 Runtime | Finish the trunk: second merge of the 10 stranded 17-Jul commits, branch deletion, fresh bundle off-machine | Critical | governance | Repo | PARTIAL | 0.25 | v23 + 18-Jul session | STATUS: 90% done. Evidence so far: merge ab9771f9 on main; matrix fix rescued into commit 4f57b7e5 (PlantAccessControl.cs line 212 maps /api/ml/foundation - without this commit the engine 403s); root tools committed 0e2da1b7/913a8ba7; .gitignore evidence rules added. 18-Jul discovery: TEN commits sit on branch 'presentation' and NOT on main (578015f4 provider fix, 84dd6abd rebuild script, 36a317f2 test deletion, workspace page, website v2, Backlog v23 docs) - main's history is a day behind although the shared working tree hides it. The second merge conflicts on exactly ONE file (.gitignore, both sides appended different ignore blocks; correct resolution = line union). REMAINING: download Finish-PresentationMerge.ps1 from the 18-Jul chat outputs to repo root and run: powershell -NoProfile -ExecutionPolicy Bypass -File .\Finish-PresentationMerge.ps1 (it re-merges, resolves .gitignore by union from index stages :2/:3, refuses to auto-resolve any other file, commits, builds, deletes the branch with --delete, cuts a fresh --all bundle, copies to OneDrive\PPIQ-Archive with SHA256 verify). | git log --oneline main..presentation prints ZERO lines; branch 'presentation' gone (git branch shows only main); dotnet build Backend\PlantProcessIQ.sln green after merge; a PPIQ_main_*.bundle newer than the merge exists in OneDrive\PPIQ-Archive and 'git bundle verify' passed on it; the M1-18_FinishMerge_*.txt log is kept as evidence.
M1-19 | M1 | M1-P1 Golden Chain | G1 Import | Oracle discovery in the HMI: PPIQ_SRC schema on CP-04/CP-06 + dated screenshot | Critical | defect fix | Connectors | PARTIAL | 0.25 | v23 | STATUS: earned x2 via API on 17-Jul (HSM_COILS..., CC_HEATS... discovered through /api). The v23 acceptance explicitly requires the UI walk, so the task is NOT closed by the API proof. REMAINING (5 minutes, in the browser): open Connections; edit profile CP-04 (caster Oracle) -> field 'Schema Name' -> type PPIQ_SRC -> Save -> Test connection (expect green) -> Discover (expect table list CC_HEATS, CC_SEQUENCES, CC_SLABS, V_PARAMETER_DEFINITIONS). Repeat on CP-06 (HSM Oracle; expect HSM_COILS, HSM_PASSES, V_PARAMETER_DEFINITIONS). Take ONE screenshot per profile showing the discovery list with today's date visible (taskbar clock suffices). If a red banner appears, STOP and file it - do not improvise credentials. | Two dated screenshots committed under docs/evidence/ (or kept in the demo evidence folder) showing PPIQ_SRC table discovery for CP-04 and CP-06 in the HMI; zero red banners during the walk; the phrase 'live Oracle connector' is now permitted in customer-facing language.
M1-21 | M1 | M1-P1 Golden Chain | G3 Engine | Governed engine run COMPLETES: wall-7 named and fixed, first fresh findings in results_v2 | Critical | defect fix | Engine | PARTIAL | 2 | v23 rewritten 20-Jul (six walls fixed this session) | STATUS: six successive blockers were found and FIXED on 20-Jul, each with evidence: (1) harness grain default 'material' (a grain that exists nowhere; use -Grain coil); (2) heat_id absent at coil grain -> migration 740 added genealogy lineage view ppiq_ml_unit_heat_lineage + heat_id resolution (proof: 2,441 distinct heats at coil, log FeatureStoreFix_103157); (3) defect.class/defect.severity outcome VALUES never emitted -> 740 emits them (51,691 rows); (4) window anchored to now() excluded the historical fleet -> pass -WindowDays 3650; (5) THE API WAS CONNECTED TO ppiq_app NOT ppiq_presentation (fingerprint: refresh returned exactly 40 features/1 outcome = the post-purge ppiq_app state) -> restart via scripts\run\start-api.ps1 -Profile presentation; (6) features and outcomes never met at the same grain (loader joins on effective_sample_key WHERE grain=@g on BOTH sides; superheat lived at heat grain, CRACK at coil) -> migration 741 projects heat-grain parameter features onto descendant coils via the lineage (proof: coil-grain features 5 -> 97,183, superheat-at-coil 12,147, and the API refresh now returns 111,611 = the projection survives refresh, log Apply741_161504 + GoldenAnalysis_163106 section [3]). REMAINING - wall 7: with a COMPLETE store the 16:31 run still returned 8x Blocked. The gate's reasons are computed but discarded (DTO gap, see M2-25), so name the blocker from outside: (a) run the message query: psql -c "SELECT target_outcome_key,status,left(message,200) FROM ml_correlation_compute_runs WHERE completed_at_utc > now()-interval '2 hours' ORDER BY completed_at_utc DESC LIMIT 8;" - the message may embed the dimension; (b) run the PATCHED Diagnose-ReadinessBlock.ps1 (re-download - the disk copy crashes at [3]) with -OutcomeKey defect.rate_per_m2 -WindowDays 3650, which reconstructs all five dimensions in SQL. Then apply the named surgical fix. Most likely completer: defect.rate_per_m2 (continuous -> minority auto-passes). defect.class may honestly block on minority-class (20 categories); if so the cure is M2-27 per-code binary outcomes, NOT a threshold change - the gate is NEVER weakened. | ml_correlation_compute_runs contains at least one run with status Completed/Ok created today; results_v2 row count rises above 320 with a NEW distinct compute_run_id; at least one finding pairs a param.* feature with a defect.* outcome with a non-trivial effect size and a q_value; the wall-7 root cause is written in one paragraph in the run log; NO readiness threshold in ReadinessGate.cs was modified (git diff proves it).
M1-27 | M1 | M1-P2 Verify & Rehearse | G12 UX | Dashboard widgets verified rendering after the 20-template self-repair | Critical | defect fix | Frontend | NEW | 1 | 20-Jul session (widget toast + repair endpoint discovery) | CONTEXT: /dashboard rendered eight empty widget stubs with toast 'Dashboard widget query is invalid' (POST /analytics/dashboard/widgets/query 400). The validator can only complain about: unsupported widget/chart type, unsupported/missing measure code, unsupported/missing dimension code, measure-requires-parameter, chart-vs-measure incompatibility, bad time range (DashboardWidgetValidationService.cs). At 15:57 the product's OWN repair was invoked and reported ensure created=20, repair repaired=20 system dashboards (log WidgetQueries_155747). WHAT TO DO: (1) hard-reload localhost:5173/dashboard - if all eight widgets render data and clicking a chart slice filters the workspace, mark PASS and screenshot; ALSO open 3-4 other codes via /workspace/<CODE> (list codes: psql -c "SELECT dashboard_code FROM dashboard_definitions WHERE is_deleted=false ORDER BY 1;"). (2) If ANY widget still shows the toast: run the PATCHED Diagnose-WidgetQueries.ps1 (list-extraction fixed 20-Jul evening) which replays every widget query and prints the server's validation errors verbatim per widget; send the log - the fix will be one registry/definition alignment. (3) Root-cause note for the file: templates drifted from the safety registry with no gate; the guard test is M2-33. | Browser screenshot of PRODUCTION_OVERVIEW with all eight widgets showing real data; one screenshot proving click-to-filter (select a slice, another widget visibly changes); zero 'query is invalid' toasts across the demo-path workspaces; if the replay script was needed, its log shows 8 OK.
M1-28 | M1 | M1-P1 Golden Chain | G1 Import | The in-room live-registration moment + prepared-instance disclosure line | Critical | execution | Pipeline | NEW | 1 | 20-Jul ruling: demo runs on the prepared instance (disclosed), imports become one live act | RULING (20-Jul): the demo uses the prepared ppiq_presentation instance, DISCLOSED, per Rule 3. The full Runsheet A-E is deferred to M1-33 (post-demo, for the citable chain). What remains for the room is ONE live act that proves the front door: register a single small dataset live and watch rows arrive. SCRIPT: after showing Connections, say the disclosure sentence VERBATIM: 'I prepared and trained this instance on our emulated multi-source plant so we spend our time on the product - on your install this starts empty and fills through the DB-link, which I will show you right now.' Then: Prepare Import -> pick meltshop v_parameter_definitions (26 rows, fast, visible) -> map to ParameterDefinition (mapping already authored or author live if rehearsed) -> execute -> open the batch -> show staging rows -> show the canonical table gaining rows WITH source_system = the connector and the batch id. Rehearse this exact path twice tonight; it must take under 5 minutes and produce zero red banners. | Rehearsal log: the act performed twice end-to-end under 5 minutes each; a written fallback line for source-down ('the connector reports the source unreachable - this is the same honesty you get in production'); the disclosure sentence is printed in the deck speaker notes on the architecture slide.
M1-29 | M1 | M1-P2 Verify & Rehearse | G12 UX | Workspace switcher: the 12 dashboards reachable from the nav, not by typed URL | Critical | enhancement | Frontend | NEW | 1.5 | 20-Jul finding: workspaces exist but only /workspace/:code routes reach them | CONTEXT: App.tsx:475 routes /workspace/:dashboardCode to RoutedInteractiveWorkspacePage and /dashboard hardcodes PRODUCTION_OVERVIEW - but NO nav entry lists the codes, so the 12 workspaces are invisible unless the URL is typed (this is why they were believed 'vanished'). TASK: add a 'Workspaces' section to the left nav (AppLayout.tsx / the nav component beside Command Dashboard): on mount, GET /analytics/dashboard/definitions (note: NO /api prefix - the group mounts at /analytics/dashboard), read the array (response may wrap it in a property - handle items/definitions/dashboards), render one NavLink per definition to /workspace/{dashboardCode} with the definition name, sorted by name, system templates first. Keep styling identical to existing nav entries (dark-industrial tokens, no new colors). Do NOT build a new page - this is nav only. If time is short before the demo, the fallback is a static list of the codes returned by the psql query in M1-27, hardcoded for the demo and replaced by the fetch in M2. | All dashboard definitions appear as clickable nav entries; clicking each renders its workspace with widgets (spot-check 4 of them); browser refresh on a /workspace/<CODE> URL still renders (route param path works); vitest suite still green; screenshot of the expanded nav committed as evidence.
M1-31 | M1 | M1-P1 Golden Chain | G0 Runtime | Commit migrations 740+741 into the repo + fold into Rebuild-PresentationDb | Critical | governance | Repo | NEW | 1 | 20-Jul session - the engine fixes exist ONLY as loose files at repo root right now | DANGER: 740_feature_store_heat_lineage... and 741_feature_store_coil_grain_projection.sql live at C:\Workspace\PlantProcess-IQ\ root, UNCOMMITTED, applied by hand to ppiq_presentation. If anyone runs Rebuild-PresentationDb.ps1 (M2-18) tomorrow morning, the rebuilt DB will NOT contain the lineage view, the projection, or the defect outcomes - the engine goes blind again silently. DO: move 741 (which supersedes and contains 740) into Backend\database\scripts\741_feature_store_coil_grain_projection.sql; keep 740 beside it or archive it with a header note '741 supersedes'; add the script to whatever list Rebuild-PresentationDb executes (open scripts\demo\Rebuild-PresentationDb.ps1, find the migration loop, confirm it globs the scripts folder or add the file explicitly); commit with message 'engine: heat lineage + coil-grain projection + defect outcomes (migrations 740/741)'; re-cut the bundle (M1-18 step already does this if run after). | git ls-files shows the migration(s) under Backend/database/scripts/; Rebuild-PresentationDb.ps1 demonstrably includes them (paste the relevant lines); after the next rebuild, psql 'SELECT count(*) FROM ppiq_ml_unit_heat_lineage' returns > 0 and coil-grain features survive; committed SHA recorded here.
M1-32 | M1 | M1-P2 Verify & Rehearse | G4 Quality | Golden script hygiene: GROUP BY bug + the lying [PARTIAL] template | Nice to have | cleanup | Tooling | NEW | 0.5 | 20-Jul: the closing text claimed signal recovery on a run with zero results | Two defects in Run-GoldenAnalysis.ps1: (1) the [BEFORE] method-distribution query errors 'aggregate functions are not allowed in GROUP BY' (GROUP BY 1 references the concatenated aggregate expression; fix: GROUP BY effect_size_type, method and build the string in SELECT only); (2) the closing 'WHAT YOU HAVE EARNED [PARTIAL]... engine recovered a planted validation signal' prints even when results_v2 gained ZERO rows - gate that block on (resAfter - resBefore) > 0, else print the honest 'no findings this run' line. The evidence file must never claim more than the run earned. | Script runs with zero SQL errors; a run with no new results prints no recovery claim (test by re-running while blocked); diff committed.
M1-01 | M1 | M1-P1 Golden Chain | G2 Assistant | Assistant grounded: reindex + one cited answer + one honest refusal | Critical | validation | Assistant | OPEN | 1.5 | v23 (build done; proof remains) | Infrastructure exists (canon.assistant_chunk, reindex endpoint). Today kb_items=0 and the corpus is unindexed. DO: POST /api/assistant/reindex with the bearer token (login e2eadmin as in the scripts; the working login path on this build is /auth/login) -> expect 200 with chunkCount >= 20. Then in the UI ask: 'which source tables are registered?' -> expect isRefusal=false with at least one citation that resolves when clicked. Then ask a predictive question ('which coils will fail tomorrow?') -> expect an explicit refusal - THE REFUSAL IS A FEATURE, show it deliberately in the room. If a completed engine run exists by then (M1-21), also ask about the newest finding and check the answer cites the run. | POST /api/assistant/reindex returns 200 with chunkCount >= 20 (paste the response); screenshot of a cited answer whose citation opens; screenshot of the refusal on the predictive question; both moments written into the demo script.
M1-11 | M1 | M1-P2 Verify & Rehearse | G16 Demo | Browser certification NARROWED: the demo path graded with screenshots | Critical | validation | All | OPEN | 2 | v23 (narrowed per 17-Jul cut: demo path only, full 12-workspace pass moves post-demo) | SCOPE (narrowed): only what the room will see. Walk in the browser, as a naive user, grading each surface [P] pass / [B] built-but-issue / [X] broken: (1) login; (2) Connections incl. the two Oracle profiles post M1-19; (3) Prepare Import + the M1-28 live-registration path; (4) Importing/Jobs Monitor; (5) genealogy search: pick one coil, walk coil->slab->heat, click into provenance; (6) Command Dashboard + PRODUCTION_OVERVIEW + 2 more workspaces: drag a widget, resize it, click a slice, watch cross-filter, save layout, reload, layout persists; (7) findings page (step 10); (8) Supervisor page (step 14); (9) assistant (step 15). EVERY [X] on this list either gets fixed tonight or its surface is REMOVED from the demo path - no red banners in the room, ever. Screenshots per step, one line per grade. | A graded checklist (P/B/X per surface) with a dated screenshot per step, saved under docs/evidence/ or the demo folder; zero [X] remaining on the path (fixed or removed); each [B] has its one spoken sentence written down; the rehearsal (M1-14) uses exactly this certified path.
M1-14 | M1 | M1-P2 Verify & Rehearse | G16 Demo | Dress rehearsal x2: timed full walk on the certified path with contingency sheet | Critical | execution | All | OPEN | 3 | v23 | The exact meeting script, twice, end-to-end, timed, on ppiq_presentation: opening frame -> disclosure sentence -> connections -> LIVE registration act (M1-28) -> genealogy walk -> workspaces (drag/resize/cross-filter live) -> findings + honest-gate sentence -> supervisor sentence -> assistant cited answer + deliberate refusal -> close. Contingency sheet: one line per step for source-down / API-down / widget-dead ('this is the same honesty you get in production' family). Run 1 tonight after M1-11 certification; run 2 tomorrow morning. NO code changes after run 2 - the constitution's no-code-after-noon rule applies in spirit. | Two timed runs logged (target under 40 minutes each); contingency sheet exists with a line per step; zero red banners in run 2; the deck order matches the walk order exactly.
M1-15 | M1 | M1-P2 Verify & Rehearse | G6 Docs | Deck + website to the PROVEN story: evidence-linked claims + 3 vision mockups + disclosure slide | Critical | content | Website | OPEN | 3 | v23 expanded 20-Jul (prepared-data disclosure + canvas vision as labeled design) | Every commercial claim names its evidence (batch id, run id, screenshot, cert log) or is future-tense. CHANGES: (1) the money slide uses whatever M1-21 actually produced - a completed finding with its run id, OR the honesty framing ('the gate refuses to fabricate; that refusal is the moat') - never the 9.3x number without a run id behind it; (2) add the prepared-instance disclosure line to the architecture slide speaker notes (verbatim from M1-28); (3) add THREE vision slides badged 'Pilot Milestone - Design': ETL block canvas, AI/ML toolbox composer, statistics function palette (dark-industrial mockups - being produced; place as full-bleed images with the badge visible); (4) workspace screenshots come from the M1-11 certified pass only; (5) honesty-lint stays green. | Deck walk matches rehearsal exactly; each claim has a named evidence artifact in the notes; the three vision slides carry the Design badge visibly; honesty-lint green; no slide contains the 9.3x number unless a completed run id is printed beside it.
M1-22 | M1 | M1-P2 Verify & Rehearse | G12 UX | Step-13 Suggestion 401: map the route in the access matrix or fence the page | Critical | defect fix | Frontend | OPEN | 0.5 | v23; class confirmed by the 17-Jul /api/ml/foundation fix | CONTEXT: red banner 'SUGGESTION RUNTIME NOT REACHABLE: 401 UNAUTHORIZED' on the step-13 page. This is almost certainly the SAME class as the fixed engine 403: the deny-by-default endpoint matrix in Backend/PlantProcess.Api/Security/PlantAccessControl.cs simply lacks the suggestion route. FIX (30 min, the pattern is proven): find the exact failing route in the browser Network tab (likely /api/suggestions or /analytics/suggestion...); add one tuple to the matrix next to line ~212 following the existing pattern: ("<route-prefix>", All(), "analysis.execute", false) - choose the permission that matches the page's role gating; rebuild; retest the page. COMMIT the change immediately (the 17-Jul fix lived uncommitted for a day and nearly died). FALLBACK if not green in 30 min: hide the page from the nav for the demo (no red banners in the room) and file the route for M2. | The step-13 page loads with zero error banners AND a real recommendation path renders; OR the page is absent from the nav and the walk shows no reference to it; the matrix change is in a commit whose message names the route; the full 15-step walk shows zero 401/403 banners.
M1-05 | M1 | M1-P2 Verify & Rehearse | G3 Engine | Supervisor step-14: verify the existing page renders, decide render-or-script | Very important | validation | Engine | OPEN | 0.5 | v23 (build exists since 14-Jul; only the verification remains) | SupervisorReportPage + SupervisorEndpoints exist with certification tests; ml_knowledge_base_items has 0 rows (kb_items=0 in today's readiness). VERIFY: open the page; if it renders an honest empty/framing state cleanly, grade [B] and use the scripted sentence: 'step-14 v0 frames the weekly supervisor - the closed tuning loop is the pilot keystone'. If one honest step produces a real report row (e.g. the kb upsert endpoint against an existing finding), take it and grade [P]. NO fabricated report content under any circumstance. | Decision recorded in the walk notes: [P] with a real row visible, or [B] with the exact scripted sentence written; screenshot either way; zero errors on the page.
M1-23 | M1 | M1-P2 Verify & Rehearse | G12 UX | Command Dashboard KPIs: Quality events + Risk show real values | Very important | defect fix | Frontend | OPEN | 1 | v23; RETEST FIRST - the 15:57 template repair may have fixed it | CONTEXT: Materials KPI read 40,148 but Quality events and Risk showed '-' against 51,691 events - a read-model/key mismatch. NEW INFORMATION (20-Jul): the system-template repair rebuilt 20 dashboards at 15:57; this KPI wiring may already be fixed. STEP 1: reload the Command Dashboard and check the two KPIs BEFORE touching code. STEP 2 (only if still '-'): open browser Network tab, find the KPI fetch, compare the measure/dimension codes it sends against the widget validation registry codes (same investigation as M1-27 - they are probably the same root cause); align the definition, not the registry. STEP 3: verify each KPI against direct SQL: psql -c "SELECT count(*) FROM quality_events;" and the risk_scores count - the UI numbers must match the SQL numbers exactly. | Both KPIs display numbers; each number equals the direct psql count on ppiq_presentation (paste both in the log); screenshot committed; if the repair fixed it, one line in the log says so with the timestamp.
M1-06 | M1 | M1-P2 Verify & Rehearse | G12 UX | Alerting: two live rules + evaluation writes the log (demo-optional) | Very important | validation | Frontend | OPTIONAL | 1 | v23; include only if step 12 stays on the demo path | AlertingPage is built and test-covered. If alerting stays in the walk: create two threshold rules in the UI (e.g. thermal superheat > 36), run evaluation, confirm plant_data_log gains rows and the alert list renders them. If cut from the path, skip entirely - do not half-show it. | Rules visible in UI; evaluation writes plant_data_log rows > 0; alert list renders them; screenshot; OR the step is removed from the demo path in the M1-11 checklist.
M1-09 | M1 | M1-P2 Verify & Rehearse | G3 Engine | Finding read hygiene: latest-run dedup view for step 10 | Nice to have | enhancement | Engine | OPTIONAL | 1 | v23 narrowed; do only if step-10 duplicates would be visible in the room | results_v2 shows visible duplicates (e.g. product.gauge_band -> defect_hold_binary twice, identical effect/n - see today's golden log [BEFORE]). If step 10 is on the demo path with the historical findings, an engineer will notice. NARROW FIX: create a read view public.ppiq_findings_latest AS SELECT DISTINCT ON (feature_key, outcome_key) * FROM ml_correlation_results_v2 ORDER BY feature_key, outcome_key, created_at_utc DESC; point the findings page query at the view (one-line change in the endpoint SQL). If not done, the spoken sentence is: 'historical runs accumulate; the read layer dedups in the pilot build'. | Findings page shows one row per feature/outcome pair; OR the sentence is in the script; view committed if built.
M1-33 | M1 | M1-P1 Golden Chain | G1 Import | Full Runsheet A-E post-demo: the citable chain on watched data (absorbs old M1-20 + M1-03 scope) | Critical | execution | Pipeline | DEFERRED | 6 | v23 M1-20/M1-03, deferred by the 20-Jul prepared-data ruling; run within 3 days after the meeting | The original golden-chain execution: Phases A (4 taxonomy registrations: meltshop v_parameter_definitions 26, caster V_PARAMETER_DEFINITIONS 4, HSM 7, parsytec v_defect_definitions 20 -> DefectCatalog), B (units + genealogy ~37,322 each), C (observations: C1 1,802 + C2 18,661; C3 overnight breadth), D (quality events ~34,312), E (governed run over the imported window). Instrumented end-to-end: run Verify-ImportPhases.ps1 -Baseline first (NOTE: re-capture - the baseline file was overwritten with plantprocessiq numbers on 20-Jul), then -Phase A/B/C/D after each phase (checks deltas AND connector-only provenance - the current taxonomy carries ADVANCED_DEMO_SEED 12+7, PPIQ_CONFIG 8+2, PHASE_F_SEED 1, all Rule-2 residue the import + sweep retires). After D: re-run the refresh + Run-GoldenAnalysis -Execute -Grain coil -WindowDays 3650; the finding then carries the fresh batch ids and the sentence 'computed on data you watched arrive' becomes true. | Batch ids recorded per phase; Verify-ImportPhases green on A-D including provenance (no non-connector source_system growth); genealogy walk resolves from THIS batch's rows; a Completed run whose window covers the imported data; the M1-33 evidence file names every id.
M2-25 | M2 | M2-P0 Keystone | G3 Engine | Readiness transparency: blocked runs explain themselves (apply the held pack) | Critical | defect fix | Engine | NEW | 3 | 17-Jul session finding; the 20-Jul wall-7 hunt paid its full price | THE DEFECT: AdvancedCorrelationComputeService builds the five gate reasons with exact numbers, then DotNetAdvancedCorrelationEngine drops them (CorrelationComputeResult has no ReadinessReasons member) and NpgsqlAdvancedResultWriter persists message+request_json only - so a blocked run is forensically mute; on 20-Jul this cost hours because eight Blocked runs could not name their dimension. THE FIX exists as a reviewed apply pack from 17-Jul (Apply-CorrelationReadinessTransparency.ps1): adds optional ReadinessReasons to the DTO (defaulted null so all four construction sites keep compiling), both engines populate it, writer serialises a readiness_json column (migration 735, additive, idempotent), plus view ppiq_correlation_run_readiness WITH (security_invoker=true) because the table carries FORCE RLS. ALSO fold migration 735 into Rebuild-PresentationDb (same trap as M1-31). Falsify once: run one deliberately blocked compute and SELECT the reasons from the view. | A deliberately blocked run's readiness_json names its dimensions with numbers; the view returns one row per reason; build green; migration in scripts/ and in the rebuild command; the pack's log archived.
M2-26 | M2 | M2-P0 Keystone | G3 Engine | Window anchoring: dataset-max instead of wall clock | Critical | defect fix | Engine | NEW | 2 | 20-Jul finding: now()-anchored windows blind any historical/backfilled dataset | The refresh and loader anchor windows to now(); a plant that pauses (or a demo on historical data) goes blind - on 20-Jul windowDays=120 rebuilt a 1-row store from a 40k dataset. FIX: anchor to max(observed_at_utc) of the relevant table/outcome (the loader already half-does this - lines 47-48 COALESCE to the max; the REFRESH function does not). Change ppiq_ml_refresh_feature_store's two window predicates to observed_at_utc >= (SELECT max(...) same-table) - make_interval(days => p_window_days); add a config flag if wall-clock mode is ever wanted. Update the harness default -WindowDays back to a sane 120 once anchoring is fixed. | Refresh with windowDays=120 on the historical fleet returns the full row counts; a unit/SQL test proves the anchor; committed + in rebuild.
M2-28 | M2 | M2-P1 Hardening | G3 Engine | results_v2 tenant integrity: stamp the tenant, backfill the NULLs | Critical | defect fix | Engine | NEW | 1.5 | 20-Jul diagnostic: FORCE RLS + tenant_id NULL on all 320 rows = findings invisible to the app through that table | ml_correlation_results_v2 has FORCE row security with policy tenant_id = ppiq_current_tenant(), and every existing row carries tenant_id NULL - the application literally cannot read its own findings via this table (only owner-psql can). FIX: (1) writer stamps tenant_id (the writer already receives @tid - verify it is bound and non-null through the API path; the NULLs suggest the session GUC is empty when the engine writes); (2) audited backfill: UPDATE ... SET tenant_id = '00000000-0000-0000-0000-000000000001' WHERE tenant_id IS NULL - with a count logged before/after; (3) a probe test: as the app role with the GUC set, SELECT count(*) must equal the owner count. Coordinate with M2-32 (tenant rename). | App-role query returns all findings; new runs insert non-null tenant_id; backfill count recorded; probe test committed.
M2-29 | M2 | M2-P1 Hardening | G0 Runtime | Amendment 6 execution: schema topology (ppiq_meta/ppiq_plant/ppiq_staging), empty public, eradicate Arch-B residue | Critical | governance | Database | NEW | 16 | 20-Jul ratified draft (concept_Amendment_6_Schema_Topology_DRAFT.md); extends M2-20 | Execute the drafted Amendment 6: (1) DbContext explicit schema per aggregate (meta/plant/staging - classification test: exists-because-of-this-customer => plant/staging, ships-identical => meta); (2) ALTER TABLE ... SET SCHEMA migration moving all application tables out of public, updating every schema-qualified function/view (incl. 740/741 objects) and the rebuild command; (3) dissolve canon + acquisition namespaces into ppiq_plant/ppiq_staging; (4) eradicate: every src_*_shape table and schema, dump_store, the legacy plantprocessiq DATABASE (after verifying against the M1-12 OneDrive archive), plus review MapDemoLifecycleEndpoints/MapDemoReadinessEndpoints which the current eradication list walks past; (5) generated inventory (information_schema) ruling every ppiq_* script table: enter-the-Domain-model / justified-infrastructure / delete; (6) gates falsified once: G1 schemaPlacementContract architecture test, G2 sqlSchemaLint over scripts/, G3 publicSchemaEmpty runtime probe. Full journey re-certification afterwards. | G1/G2/G3 all green after a recorded red each; fresh install shows zero app tables in public and SELECT across ppiq_plant.* = 0 day one (the A2 one-liner); plantprocessiq gone; inventory committed as the amendment's appendix; concept.md bumped v1.2.
M2-31 | M2 | M2-P2 Product | G12 UX | Node-wiring canvas foundation (reactflow) powering UI-1 join canvas + UI-3 toolbox | Critical | enhancement | Frontend | NEW | 20 | 20-Jul finding: react-grid-layout is the ONLY DnD lib in the tree; the wiring paradigm has no foundation | The low-code vision's missing half: adopt @xyflow/react (reactflow) as the shared canvas kit (nodes, edges, ports, minimap, dark-industrial theme from the token set); build two consumers: (1) UI-1 Visual Join Canvas over the EXISTING backend (ppiq_visual_mapper_joins/_columns/_business_keys/_dry_runs/_templates - the tables and dry-run endpoints already work; the canvas is a new front over them): drag staged datasets as nodes, draw join edges on keys, preview via dry-run; (2) UI-3 Analysis Toolbox: method/function blocks (from the statistics registry incl. M2-04 additions) wired to parameter/outcome pickers, compiling to the same AnalysisJobConfig payload the form produces today. M3-02/M3-03 are RESCOPED to consume this foundation (do not build canvases twice). The three M1-15 vision mockups are the design contract. [v25: implements Prep-builder spec SS3/4/5/7/8/16 (canvas) AND is the authoring upgrade for Part A/B; M1 demos the same capability via forms (M1-35). Prereq for M2-37/38 UX parity.] | Both canvases demoed on the emulated plant: a cross-source join (oracle piece_id x mysql material_id) authored by drag+wire and executed via dry-run; an analysis job authored by blocks producing an identical payload to the form; interactiveWorkspaceContract-style gate extended to the canvas pages; mockup-to-product diff reviewed against the design badge slides.
M2-27 | M2 | M2-P0 Keystone | G3 Engine | Per-defect-code binary outcomes (defect.<code>_binary) for the money framing | Very important | enhancement | Engine | NEW | 2 | 20-Jul: defect.class (20 categories) may honestly block on minority-class; the planted R1 is binary by design | IF M1-21's wall-7 (or the class-balance dimension) shows defect.class refusing on minority share: emit per-code binary outcomes exactly like the historical quality.defect_hold_binary pattern - migration 742: seed ml_outcome_definitions rows defect.<lower(defect_code)>_binary (binary) from defect_catalogs; refresh emits per coil: 1.0 if the coil has >=1 quality_event of that code in-window else 0.0 (dense zeros REQUIRED - the engine needs both classes); heat_id via the lineage as in 741. Then superheat -> defect.crack_long_binary is the clean odds-ratio the money slide was designed around, with SCRATCH's binary as the null control at ~1.0. | A completed run on defect.crack_long_binary with an odds-ratio effect and q-value; scratch binary ~1.0; definitions visible in the catalog endpoint; migration committed + in rebuild.
M2-30 | M2 | M2-P1 Hardening | G6 Docs | Constitution + docs execution: v1.1 applied, folder reorganized, Doctrine v8.1 adopted, personas filed | Very important | governance | Docs | NEW | 1.5 | 18-20 Jul deliverables held during the demo crunch | Run the three held scripts in order AFTER Finish-PresentationMerge: Apply-ConceptV11.ps1 (five amendments, anchored, backs up v1.0, commits - Model A ratified 19-Jul), Reorganize-ProductDocs.ps1 (canonical folders 0_founding/1_constitution/2_doctrine/3_planning/4_instruments/5_commercial/9_archive + INDEX.md; nothing deleted, snapshots immutable; splits rules.txt at PART A), then drop PlantProcessIQ_Doctrine_v8.1.md (the executed 8-directive merge) into 2_doctrine and point INDEX at it (v8.0.docx archives unmodified); file Aspects_of_Review_Personas_A11-A13.md with the audit lineage. Also add Amendment 6 DRAFT into 1_constitution pending its M2-29 execution. | concept.md header reads v1.1 with changelog; INDEX.md exists and every species has exactly one living document; v8.1 in 2_doctrine; personas filed; all commits pushed into the bundle.
M2-32 | M2 | M2-P1 Hardening | G0 Runtime | Tenant hygiene: rename default-demo, align ppiq_tenants vs tenants, session GUC audit | Very important | defect fix | Database | NEW | 1 | Roadmap v9 P2 item, now load-bearing after the 20-Jul tenant findings | Two tenant registries exist (ppiq_tenants key 'default', tenants key 'default-demo' - same GUID) and the name violates Rule 1 wording. Rename to a neutral key (e.g. 'default'), reconcile the two tables (or retire one with a view), audit every place the session tenant GUC (ppiq_current_tenant()) is set - API middleware, engine writer, jobs - so M2-28's stamping has one source of truth. | One registry (or documented pair) with no 'demo' in customer-visible keys; a written list of every GUC set-point; app + engine both resolve the same tenant id; probe committed.
M2-34 | M2 | M2-P3 Audit | G4 Quality | First A11 (UI/UX) + A12 (AI/Engine) + A13 (Infrastructure) audits | Very important | review | All | NEW | 6 | 20-Jul personas mandate (renumbered from A7-A9 per frozen-ID law) | Run the three new personas against the post-demo build using Aspects_of_Review_Personas_A11-A13.md - each arrives pre-loaded with this session's findings (A11: forms-vs-canvas truth, unmounted builder entry, S5 gaps; A12: window anchor, mute blocked runs, tenant-NULL findings, 375 blind runs; A13: Arch-B residue, pgvector absent, sizing table unverified). Findings enter the backlog as NEW ids, Origin = the audit report; the report itself is immutable. | Three dated audit reports committed; every finding has a backlog id or a written won't-fix; no report edited after filing.
M2-33 | M2 | M2-P1 Hardening | G4 Quality | Dashboard template/registry drift guard + definitions endpoint contract | Nice to have | tooling | Frontend | NEW | 1 | 20-Jul: templates drifted from the widget safety registry silently; the list endpoint shape broke tooling twice | Two small guards: (1) a test that replays every SYSTEM dashboard widget query against the validation service at build time - drift between templates and the safety registry turns red before it turns into eight dead widgets; (2) document + contract-test the /analytics/dashboard/definitions response shape (it defeated two diagnostic clients on 20-Jul). | CI red when a system template's query fails validation (falsified once by breaking one on purpose); a contract test pins the definitions response shape.
M2-35 | M2 | M2-P1 Hardening | G4 Quality | Tooling: per-database baseline files for Verify-ImportPhases | Nice to have | cleanup | Tooling | NEW | 0.25 | 20-Jul: -Baseline against plantprocessiq silently overwrote the presentation baseline | Verify-ImportPhases.ps1 writes .import-baseline.json regardless of -Database; running it against a second DB destroys the first baseline (happened 20-Jul 10:36). Fix: filename .import-baseline.<database>.json; loader matches on the same key; note in the header. | Two baselines for two databases coexist; -Phase A against presentation uses the presentation baseline (proven by a deliberate cross-run).
M2-01 | M2 | M2-P1 | G3 Engine | Supervisor engine (step-14 keystone): jobs improve each other + weekly deep revision | Critical | new feature | Engine | OPEN | 16 | CARRIED v22 M2-01 | Full implementation with guardrails: may tune job configs/feature windows/thresholds; must NEVER weaken readiness gates, refusal logic or evidence; every change logged with justification. Builds on the M1-05 verified v0 state. | After two supervised cycles, at least one job config adjusted with logged justification and measurably improved metric; gates untouched.
M2-02 | M2 | M2-P1 | G2 Assistant | Real LLM binding behind IAssistantModel (on-prem Ollama + optional hosted) | Critical | new feature | Assistant | OPEN | 10 | CARRIED v22 M2-02 | Swap-in implementations beside ExtractiveAssistantModel; config-selected per install; answers remain retrieval-grounded + cited; refusal-first preserved. | Same eval set answered by both models; citations still resolve; predictive questions still refuse; latency budget documented.
M2-03 | M2 | M2-P1 | G0 Runtime | Bounded-parallelism job executor (100+ jobs) | Critical | new feature | Backend | OPEN | 12 | CARRIED v22 M2-03 | Channel<JobRequest> + N consumers; per-class pools (import/analysis/ML); statement timeouts + per-class work_mem; NOTIFY wakeups; job telemetry. | 100 defined jobs across classes complete a full cycle with bounded drift; no pool exhaustion; telemetry populated.
M2-04 | M2 | M2-P1 | G3 Engine | Statistics method registry: Spearman, chi-square, ANOVA/Mann-Whitney + Surface-3 picker | Critical | new feature | Engine | OPEN | 10 | CARRIED v22 M2-04 | Registry of methods with applicability rules; Surface-3 lets the user pick; all results keep the evidence contract. | Each method produces a verified result on the rigged set (chi-square finds a planted categorical driver; Spearman survives monotone).
M2-05 | M2 | M2-P1 | G10 Surface-1 | Step-4 full no-code data preparation (per-view Loading jobs + prep/load unification) | Critical | new feature | Frontend | OPEN | 12 | CARRIED v22 M2-05 | Productize the demo path: visual field-map editor, filters/linking/grouping, SchemaView->MappingDefinition relationship decided, per-view jobs. [v24 note: the canvas UX for this surface is delivered by M2-31; this task owns the job/loading semantics, not the wiring UI.] | A non-developer maps a NEW source to canonical entirely in the HMI incl. schedule; steps 4-6 clickable start to finish.
M2-06 | M2 | M2-P1 | G12 UX | 4th UI complete: routing-deviation + chemistry-range rules, email/webhook delivery | Critical | new feature | Frontend | OPEN | 12 | CARRIED v22 M2-06 | Extend v0: rule types (threshold / routing deviation vs genealogy / chemistry range vs expected_min_max), delivery channels, ack workflow. | Each rule type fires on a crafted case; email+webhook delivered; ack recorded.
M2-08 | M2 | M2-P2 | G0 Runtime | Scale foundations: partitions (monthly+BRIN), incremental feature refresh, PgBouncer, restore drill | Critical | infrastructure | Backend | OPEN | 10 | CARRIED v22 M2-08 | Pre-pilot infra musts from sizing model v1. | Medium-profile synthetic load (7.5M obs) refreshes incrementally in bounded time; restore drill signed off.
M2-09 | M2 | M2-P2 | G14 Security | Roles/users vs journey: role catalog, named policies, MFA verify, SCIM finish-or-fence | Critical | security | Backend | OPEN | 8 | CARRIED v22 M2-09 | Replace '?? viewer' fallback + literals with a role catalog; verify MFA enrolment; finish or fence SSO/SCIM; user flows match journey. | Role matrix documented+tested per surface; MFA walk recorded; SCIM passing or disabled behind a flag.
M2-10 | M2 | M2-P2 | G14 Security | Licensing production-grade: tier->feature matrix, production Ed25519 keypair, gated-endpoint tests | Critical | security | Backend | OPEN | 5 | CARRIED v22 M2-10 | Document tier -> LicenseFeature codes; rotate off the dev keypair (Option 3); test one gated endpoint per tier incl. ML/assistant gates. | Matrix published; dev token rejected in prod mode; per-tier tests green.
M2-16 | M2 | M2-P1 | G12 UX | Interactive Workspace Doctrine epic P1: S5 components + S6 builder entry + S4/S7 gap fixes | Critical | new feature | Frontend | OPEN | 24 | NEW 16-Jul (doctrine gap matrix ~70h, P1 slice) | Amendment-7 conformance slice: conditional-format tables, list component, date-time-range filter (S5); re-mount Add-widget builder on workspace pages (S6); close every S4 min/max and S7 drag/persistence gap the M1-11 grading found; real heatmap widget row (config proven by Widget Drift). | All 12 workspaces graded [P] on every doctrine standard; a user adds a widget through the builder on a workspace page.
M2-17 | M2 | M2-P1 | G4 Quality | Amendment 7 committed + interactiveWorkspaceContract architecture gate installed | Critical | governance | Tests | OPEN | 6 | NEW 16-Jul (Amendment 7) | The doctrine document into docs/doctrine/ on main; the gate per its section 5: frozen legacy allowlist, ratchet semantics, widget-query-contract enforcement. A doctrine without a gate is a wish. | Gate red on an injected non-conforming page, green on main; allowlist snapshot committed; doctrine in git log.
M2-20 | M2 | M2-P3 | G16 Demo | Eradication epic: every Rule-1-violating installer/endpoint/page out of the product | Critical | cleanup | All | OPEN | 10 | REWRITE v22 M1-07 residue + eradication list | Consolidates old M1-07 residue + the standing list: TwoStageImportEndpoints.cs, CustomerDemoReportEndpoints.cs, /demo* routes, installer scripts 110/111/140/142/665 + seed/ violations on fresh install, 4 unrouted pages, drifted duplicate scanners, MaskSecrets default. [v24 note: schema-object eradication (dump_store, src_* schemas, plantprocessiq DB, DemoLifecycle/DemoReadiness endpoints) now owned by M2-29 Amendment-6 epic - this task keeps the installer-script/page/endpoint deletions; +2h for the endpoint review.] | Fresh install on ppiq_acceptance_empty is 100% generic; grep gates clean; endpoints absent from Swagger.
M2-07 | M2 | M2-P2 | G1 Import | Range validation on ingest (expected_min/max) + time-series observation support | Very important | enhancement | Pipeline | OPEN | 5 | CARRIED v22 M2-07 | Validate observations against parameter_definitions ranges (typed warning, not silent); prove multi-reading-per-unit series through the pipeline. | Out-of-range reading produces a visible data-quality issue; 10-readings/heat series imports+projects+correlates.
M2-11 | M2 | M2-P2 | G15 Governance | Close out-of-band paths: staging-reset endpoint, purge audit, source_system allow-list, retention, deletion UX | Very important | governance | Backend | OPEN | 5 | CARRIED v22 M2-11 | Everything an auditor flagged: admin endpoint replaces psql resets; projector accepts only registered connector source_systems; retention job visible. | No documented workflow requires psql; allow-list test rejects a foreign source_system; retention job in monitor.
M2-13 | M2 | M2-P3 | G4 Quality | CI truth gates + test debt: same-table CREATE gate, seed NOT-NULL gate, register/const/binding tests | Very important | tests | Tests | OPEN | 6 | CARRIED v22 M2-13 | The two deferred gates plus uncovered seams (register upsert, const: branch, execute query-binding, AddAssistant guard + factory tests). | All gates red on injected violations, green on main; new tests in CI.
M2-14 | M2 | M2-P3 | G12 UX | Journey UX hardening: mapping surfaces renamed by outcome, i18n/RTL verified, widget lite-SQL click-tools | Very important | enhancement | Frontend | OPEN | 5 | REWRITE v22 M2-14 (6h; M1-17 clause done) | 'Prepare views' vs 'Load to plant data' naming; real Arabic RTL pass; group-by/filter click-builders in the widget wizard. (Progress guide DONE as M1-17 - clause removed.) | New-user walk without verbal guidance reaches step 10; RTL screenshots approved.
M2-19 | M2 | M2-P2 | G15 Governance | ppiq_acceptance_empty: third database + profile + Rule-2 acceptance run | Very important | governance | Infra | OPEN | 1 | NEW 16-Jul (senior rec 3) | Senior rec 3: 'starts empty' is untestable without a permanently-empty instance. Create DB + profile; the Rule-2 acceptance (fresh install shows zero content everywhere) runs against it in CI cadence. | Profile works; acceptance walk on the empty DB shows zero demo content on every surface; documented in Identity & Topology.
M2-21 | M2 | M2-P3 | G4 Quality | Journey certification suite completion: backend contracts hardened, MSW fixture layer, Playwright specs green, skippables mandatory | Very important | tests | Tests | OPEN | 12 | NEW 15-Jul (certification framework P1) | The adopted framework's test expansion, P1 slice: the 3 backend contract suites to green against real contracts, a real MSW fixture layer, the 2 journey Playwright specs passing in CI, SkippableFacts converted (live-Postgres path in CI), test isolation via PPIQ_TEST_PG_CONNSTRING. | test:journey:* all green in CI; skipped count = 0 for critical suites; Phase3GoldenThread isolated from dev DB.
M2-22 | M2 | M2-P3 | G12 UX | UI debt burn-down wave 1: ratchet 161/112 -> demo-path zero | Very important | cleanup | Frontend | OPEN | 10 | NEW 15-Jul (conformance scan) | Frozen debt under the monotonic ratchet: AdminDbConfigurationTab (18), AnalysisJobConfigPage (18+25), widget-builder (20), Alerting (10), ImportPrep (9+13) converted to Standard* primitives; baseline lowered accordingly. | Ratchet baseline reduced by >=100 D1; demo-path pages at 0 raw controls; suite green.
M2-15 | M2 | M2-P3 | G14 Security | Ops/security residue: secrets story, mail/Spamhaus remediation, backend mojibake, phase-dir renames | Nice to have | cleanup | Ops | OPEN | 3 | REWRITE v22 M2-15 (4h; src mojibake done) | Src-tree mojibake DONE 16-Jul (gate green); remaining: 6 backend .cs files, Phase8/9 dir renames, SPF/DKIM/PTR + relay 587, secrets manager pattern. | Deliverability test passes; noMojibake backend list empty; grep clean on phase tokens; no plaintext secrets.
M2-23 | M2 | M2-P3 | G15 Governance | Purge the 5 provenance-NULL units in ppiq_app + root-cause note | Nice to have | cleanup | Data | OPEN | 0.5 | NEW 16-Jul (defect #5) | The dev DB's only Rule-2 breach (certifier catch): five units with NULL source_system/source_record_id, created outside the import path. Identify origin, delete, note the seam. | Certifier S06 nullProv=0 on ppiq_app; origin documented.
M2-24 | M2 | M2-P3 | G10 Surface-1 | Register page final step: explicit job binding (from-mapping + schedule-now) | Nice to have | enhancement | Frontend | OPEN | 1 | MOVED from v22 M1-16 (senior rec 17: not demo-critical) | Small remainder: wire the page's final step to import-jobs/from-mapping + schedule-now (register already schedules implicitly). | Clicking finish shows the scheduled job and next-run time.
M3-01 | M3 | M3-P1 | G5 Feedback | Customer-comment intake from the meeting: log, triage, re-prioritize M3 | Critical | governance | Docs | OPEN | 2 | CARRIED v22 M3-01 | Every comment becomes a numbered row with severity and owner; M3 scope finalized within 48h of the meeting. | Comment log committed; M3 plan v1 published.
M3-02 | M3 | M3-P1 | G10 Surface-1 | Visual mapper polish + mapping templates library | Very important | new feature | Frontend | OPEN | 6 | CARRIED v22 M3-02 | Drag-drop field mapping, per-industry starter templates shipped as emulation fixtures (never code branches). [v24 RESCOPED: consumes the M2-31 canvas foundation - templates library + polish only; est cut 8->6h.] | A new industry source mapped from a template in <10 min by a non-developer.
M3-03 | M3 | M3-P1 | G3 Engine | 3rd UI drag-and-drop analysis toolbox | Very important | new feature | Frontend | OPEN | 6 | REWRITE v22 M3-03 (doctrine ref added) | Draggable method/parameter components over the M2 method registry; saved analyses shareable; conforms to Amendment 7 workspace primitives. [v24 RESCOPED: consumes the M2-31 canvas foundation - toolbox content + payload compilation only; est cut 10->6h.] | User composes a two-method analysis by drag-drop; result matches scripted equivalent; doctrine gate green.
M3-04 | M3 | M3-P1 | G0 Runtime | Large-profile scale: analytics read replica, partition automation, load test at 60M obs/yr | Very important | infrastructure | Backend | OPEN | 10 | CARRIED v22 M3-04 | Per sizing model v1 Large row; automated partition creation; correlation on replica. | Synthetic Large load meets documented latency budgets.
M3-05 | M3 | M3-P1 | G1 Import | Connector expansion per customer landscape (files/API/historians as required) | Very important | new feature | Connectors | OPEN | 8 | CARRIED v22 M3-05 | Scoped from customer comments: CSV/file drop, REST, OPC-UA historian - each as a new IDataSourceReader family, zero core changes. | New connector imports through the unchanged pipeline.
M3-06 | M3 | M3-P1 | G13 Deploy | HA + multi-plant deployment hardening | Nice to have | infrastructure | Deploy | OPEN | 8 | CARRIED v22 M3-06 | Failover story, per-plant isolation review, installer runbook (sysadmin auto-provision, Customer Admin manual per Golden Rule). | Documented install executes on a clean VM end-to-end.
M1-34 | M1 | M1-P2 Verify & Rehearse | G16 Demo | TARGET: Part B (Qlik workspace) >=75% frontend-demonstrable | Critical | target | Frontend | TARGET | 3 | 21-Jul targets + Rules662 matrix | GOAL: the 3 premade page-types render + interact at >=75% of the SS0-12 spec's DEMONSTRABLE surface (not full spec - that is M2). Matrix baseline: layout/style/evidence ~90%, interaction ~70% post the 08:41 fix. To cross 75% demonstrable, VERIFY (M1-11 pass) + land these small sure wins ONLY: (a) confirm switcher morph + global-filter requery + one bar-click cross-filter work (this morning's fix); (b) DEF-006 hide Clone/Remove menu items if not wired (hiding a dead button > showing it); (c) DEF-007 either mount DrilldownDrawer or suppress the drilldown affordance; (d) ensure honest empty-states not error toasts on the demo path. NOT in M1: associative engine SS0 (M2-37), chart catalogue breadth SS2 (M2-38), bookmarks/sheets SS4. Those get the one-sentence roadmap. | M1-11 pass shows: switcher OK, table view OK, global filter requeries all widgets, one chart-click cross-filters, drag/resize/save persists, CSV export works, fullscreen OK - >=9 of 12 pass steps green with screenshots; every dead control on the demo path is hidden or fixed; the >=75% figure is defended by the completed pass sheet, not asserted.
M1-35 | M1 | M1-P2 Verify & Rehearse | G16 Demo | TARGET: Part A (Prep builder) >=75% frontend-demonstrable via the LIVE type-1 build | Critical | target | Frontend | TARGET | 3 | 21-Jul target #7 + Rules662 matrix | GOAL: demonstrate Part A at >=75% by BUILDING ONE type-1 page live (#7) through the EXISTING forms UI - not the canvas (canvas=M2-31). The matrix proved the spec's hard invariants are already built: versioned Transformation Definition (draft/validated/published/rolled_back, 540:35-147), dry-run preview (540:117), safe-sql read-only gate (rejected_by_safe_sql). So the live act = author a mapping/prep definition in UI-1, run its dry-run/preview, see the sample result, save it as a named versioned artifact, link it to the load job. That exercises SS2/SS5/SS6/SS10/SS15 LIVE. VERIFY the forms path end-to-end tonight; script the exact clicks; rehearse twice. The room sentence for the missing canvas: 'the builder's versioning, preview and read-only safety are live and you just watched them - the visual wiring canvas renders on top of this same engine in the pilot (M2-31).' | A rehearsed <5-min live walk: author -> dry-run preview shows sample rows -> save as named definition (visible new version row) -> linked to a job. Screenshots of each step; the safe-sql rejection shown once as a feature (bad SQL -> honest error). >=75% defended by which SS sections are demonstrated live (list them in the pass).
M1-36 | M1 | M1-P1 Golden Chain | G3 Engine | TARGET: Engine >=75% - a Completed run OR the honest-abstain moat, either qualifies | Critical | target | Engine | TARGET | 2 | 21-Jul target #3 (absorbs M1-21 wall-7) | GOAL: engine demonstrable at >=75%. TWO acceptable forms, both real: (A) a COMPLETED governed run on defect.class after wall-7 is named+fixed (store already proven: 2441 heats, 100% completeness, projection survives refresh) - needs the inside-engine log read (restart API in a visible console, run Invoke-EngineDirect, read the AdvancedCorrelationComputeService verdict line) then the surgical fix; OR (B) if wall-7 is structural, demo the HONEST-ABSTAIN as the moat: a live governed run returning Blocked 'analysis refused (honest abstain)' with a real run id - your own marketing names this the differentiator none of Primetals/PSI/SST can screenshot. 75% = the engine visibly runs, is governed, and either completes or honestly refuses - NOT a fabricated number. The citable 9.3x stays M1-33 (post-demo, watched data). | Either: ml_correlation_compute_runs has a Completed run today with a finding pairing param.* to defect.* (effect+q); OR a live Blocked run with a real run id is rehearsed with the moat sentence. Wall-7 root cause written in one paragraph. No 9.3x quoted without a run id.
M1-37 | M1 | M1-P1 Golden Chain | G2 Assistant | TARGET: Chatbot/LLM >=75% - a few Q&A with SOME value + learning-curve framing | Critical | target | Assistant | TARGET | 1.5 | 21-Jul target #4 (absorbs M1-01) | GOAL (your words): ask a couple of random questions, get a couple of answers WITH SOME VALUE - accuracy not mandatory; the honest frame is 'still on its learning curve, needs a bigger accurate dataset'. DO: POST /api/assistant/reindex (login e2eadmin, path /auth/login) -> chunkCount>=20; then in the chat ask 2-3 grounded questions ('which source tables are registered?', 'what defects are tracked?', 'summarise data quality') -> answers should cite or at least draw on the corpus; ask ONE predictive question -> the refusal is a FEATURE, show it. If answers are thin, that's acceptable at 75% WITH the learning-curve sentence - but they must not error or hallucinate wildly. Rehearse the exact 3 questions so the room demo is smooth. | reindex returns chunkCount>=20 (paste); 2-3 scripted questions return non-empty answers with some grounding; 1 predictive refusal shown; the learning-curve sentence is in the script; no server error in the chat during the rehearsed set.
M1-38 | M1 | M1-P1 Golden Chain | G1 Import | TARGET: whole 15-step journey green on the FAKED/prepared dataset | Critical | target | Pipeline | TARGET | 2 | 21-Jul target #5 | GOAL: every one of the 15 journey steps shows healthy/green on the prepared ppiq_presentation instance (the faked dataset is disclosed per M1-28). This is the journey RAIL a customer sees. VERIFY each step's page loads without red banners and shows plausible data: 1 Connect, 2 Register, 3 Import, 4 Prepare, 5 Map, 6 Loaded, 7 Dashboards, 8 Analysis, 9 Run, 10 Findings, 11 ML ready, 12 ML jobs, 13 ML results/Suggestions (M1-22 401 fix), 14 Supervisor (M1-05), 15 Assistant (M1-37). Any step that cannot go green gets HIDDEN from the rail for the demo, not shown broken. Screenshot the full green rail. | Screenshot of the 15-step rail with every demo-path step green; each red/broken step either fixed or removed from the walk; the disclosure sentence (M1-28) covers the prepared data; zero red banners in the rehearsed walk.
M1-39 | M1 | M1-P2 Verify & Rehearse | G16 Demo | TARGET: 3 premade pages (one per type) demo-ready | Critical | target | Frontend | TARGET | 1.5 | 21-Jul target #6 | GOAL: exactly 3 premade pages, ONE PER TYPE, polished and demo-ready: TYPE-1 a linked-raw-data dashboard (a Qlik workspace, e.g. PRODUCTION_OVERVIEW - already rendering post fixes + layout SQL); TYPE-2 a statistics/correlation results page (Correlations / findings); TYPE-3 an AI+ML results page (Model Insights / assistant-backed). Pick the single best-rendering workspace for each type, run the M1-11 pass on those 3 specifically, fix or hide any defect on THOSE pages only (don't chase all 12). These 3 are the spine of the room demo. | 3 named pages, one per type, each passing its M1-11 sub-pass with screenshots; each reachable via nav or a typed /workspace URL noted in the script; any defect on these 3 fixed or hidden.
M1-40 | M1 | M1-P2 Verify & Rehearse | G0 Runtime | TARGET: protect the work - commit everything before any further edits | Critical | governance | Repo | TARGET | 0.25 | 21-Jul - 24h of fixes still uncommitted | CRITICAL and FIRST: every fix from 20-21 Jul is uncommitted working tree - migrations 740/741/742, the observationCount C# fix (2 files), the layout SQL effects, the Qlik-interactions tsx fix, all session scripts. ONE bad edit or rebuild erases them. DO NOW: $env:Path += ';C:\Program Files\Git\cmd'; git add -A; git commit -m 'demo-eve: engine 740-742, observationCount measure, qlik interactions, layout, tools'. This is M1-31 widened to everything. Do it BEFORE the M1-11 pass, before any further script. | git status clean (or only intended new files); git log shows the demo-eve commit; migrations + both C# files + the tsx fix are in git ls-files; bundle re-cut after (M1-18).
M2-37 | M2 | M2-P2 Product | G12 UX | Associative selection engine (Qlik spec SS0): possible/excluded states + coloring | Very important | enhancement | Frontend | NEW | 16 | 21-Jul Rules662 matrix | The deepest distance from 'Qlik standard': today filters requery (M1 fix); the spec SS0 wants an ASSOCIATIVE model - selecting a value computes possible vs excluded values across ALL fields and renders green/white/grey. Build: selection state store, possible-set computation per field from the current selection, tri-state rendering in filter dropdowns and charts, alternate-states support. Prereq for a true Qlik claim. | Selecting a value greys out impossible values elsewhere; possible set computed server- or client-side; green/white/grey rendering; alternate states; a spec-SS0 checklist passes.
M2-38 | M2 | M2-P2 Product | G12 UX | Chart & widget catalogue completion (spec SS2/SS3/SS4) | Very important | enhancement | Frontend | NEW | 20 | 21-Jul Rules662 matrix | Today ~7 chart types; spec SS2 wants the full catalogue: scatter, heatmap, pareto, box-plot, gauge, waterfall, combo; SS3 non-chart widgets (text, container, tabs, KPI variants); SS4 dashboard constructs (bookmarks, sheets). Add incrementally, each honoring the safety registry + interaction contract. | Each new chart type renders from a widget definition, passes validation, supports selection; bookmarks save/restore a filter+layout state; catalogue checklist vs SS2-4 tracked.
M2-39 | M2 | M2-P2 Product | G3 Engine | Transformation-definition field alignment to spec SS2/SS11 | Nice to have | enhancement | Backend | NEW | 8 | 21-Jul matrix | The versioned artifact exists (540) but the spec's SS2/SS11 want: definition_hash (reproducibility), output_schema (inferred cols/types/nullability), source_bindings by stable internal id (rename-safe), per-output-column lineage. Add these to ppiq_visual_mapper_versions + the save path. | Saved definition carries hash, output_schema, id-based bindings, per-column lineage; a source rename does not break a saved definition; SS2/SS11 checklist green.

## Closed & Archived
CLOSED & ARCHIVED - immutable; superseded scope always names its destination. Nothing here is deleted from history.
ID | Disposition | Task | Evidence / destination
M1-25 | DONE | Gate hygiene: stale JourneyRail.test.tsx deleted | 17-Jul: commit 36a317f2 (on presentation; lands on main via M1-18 finish); suite 253/253 green.
M2-18 | DONE | One-command demo environment: Rebuild-PresentationDb.ps1 | 17-Jul: committed (84dd6abd on presentation), proven 3x. WARNING: does not yet include migrations 735/740/741 - see M1-31/M2-25.
M1-12 | DONE | Continuity: FLEET_RELATIONS + fixtures + fleet archived off-machine | 18-Jul: FLEET_RELATIONS committed 2b8a9a44; fixtures zip + fleet3months zip + verified bundle hash-copied to OneDrive\PPIQ-Archive (logs M1-12_Complete_v4_140352).
M1-24 | SUPERSEDED | Parallel-session code review | Cut 17-Jul (post-demo); absorbed into M2-34 A11/A12 audits.
M1-26 | SUPERSEDED | Certifier v0.2 self-defects | Cut 17-Jul; folded into M2-21 certification completion.
M1-20 | SUPERSEDED | Runsheet A-E as a DEMO prerequisite | 20-Jul prepared-data ruling: demo runs on the disclosed prepared instance; the in-room act is M1-28; the full citable chain is M1-33 (post-demo). Original scope preserved verbatim inside M1-33.
M1-03 | SUPERSEDED | Taxonomy-first proof as a demo prerequisite | Merged into M1-33 Phase A acceptance (counts 26/4/7/20 + connector-only provenance).
(unplanned) | DONE | Access-matrix engine fix committed | 4f57b7e5 (18-Jul): /api/ml/foundation mapping rescued from the working tree into history.
(unplanned) | DONE | Doctrine v8.1 produced | 20-Jul: eight-directive merge executed against the real v8 text; adoption tracked in M2-30.
(unplanned) | DONE | System dashboard templates ensure+repair 20/20 | 20-Jul 15:57 via /analytics/dashboard/definitions/system-templates; browser verification = M1-27.

## Lineage v22-v23
REMOVED FROM v22 - traceability (nothing silently deleted)
v22 ID | Disposition | Task | Evidence / destination
M1-04 | DONE | Step-4 mapping UI authors MappingDefinition through the HMI | Proven in walk + certification tests (failedRows contract fixed 16-Jul). Evidence: walk doc [V] rows; suite green.
M1-10 | DONE | Production error shape (no stack traces to clients) | Walk P6/P10 verify the {title,errorCode,traceId} shape live [V].
M1-13 | DONE | ppiq.ps1 API readiness poll | Walk P2 cites the M1-13 line as live [V].
M1-17 | DONE | Journey progress rail (step X of 15) | Rail live in 16-Jul screenshots; certification test green; stale old test removal = new M1-25.
M1-07 | DONE (frontend) | Arch-B frontend removal | Two-Stage ghost card excised 15-Jul (SHA-confirmed). Backend residue folded into M2-20 eradication epic.
M1-02 | MERGED | Jobs Monitor four job types honest | Merged into M1-11 evidence-graded certification (one browser pass, one checklist).
M1-08 | SUPERSEDED | Purge + re-import into ppiq_app | Purge done 14-Jul. Re-import superseded by M1-20 golden chain into ppiq_presentation (strategy: senior recs 2,3).
M1-16 | MOVED | Register page explicit job binding | Not customer-critical (senior rec 17). Now M2-24.

## Phase Summary
PHASE SUMMARY - live formulas over the Active Board
Milestone | Status | Tasks | Hours | Critical
M1 | PARTIAL | 3 | 2.5 | 3
M1 | NEW | 5 | 5 | 4
M1 | OPEN | 7 | 11.5 | 5
M1 | OPTIONAL | 2 | 2 | 0
M1 | DEFERRED | 1 | 6 | 1
M2 | NEW | 11 | 54.25 | 5
M2 | OPEN | 22 | 183.5 | 12
M3 | OPEN | 6 | 40 | 1
TONIGHT (M1 not deferred/optional) |  |  | 19