## Read Me
PlantProcess IQ — Product Backlog v4
Versioned release plan. Operationalizes PPIQ_Product_Roadmap_v3, the Identity & Topology v3 reference, and the 20-Jun realization scoreboard.
WHAT CHANGED FROM v3.1
1. Reorganized from milestones (M1/M2/M3) into VERSIONS (V1-V4). Version 1 is the first release for the customer presentation and totals < 100 h.
2. Tasks >85% done are REMOVED to the 'Completed (Removed)' sheet (5 tasks: the .env.dev, schemas, demo-sources, role-users and Ed25519-token closures).
3. Tasks 65-85% done are marked MOSTLY-DONE and ordered FIRST in their phase (e.g. ppiq.ps1 entrypoint).
4. Added the gap-closing tasks needed so every persona AND every sub-criterion reaches >=75 — proven on the 'Coverage to 75' sheet.
5. Surfaced the new realities the optimistic file-count hid: the lost genealogy/safe-SQL foundation (now V1-07, P0), the 151 non-standard buttons (V2-02, not 41), and the live config defects (V1-04/05).
THE FOUR VERSIONS
V1 · First Release — Presentation-Ready (<100 h). A crash-free, live, reproducible demo + healthy server deploy + ROI story + collateral + a sharp website. Lifts the demo-gating personas.
V2 · Product Depth. License + user-role depth, sharper AI/ML results + an impressive suggestion engine, the full test harness, and docs WITH app screenshots (how-to-use / how-to-install).
V3 · Generic & Multi-Industry. Paper and food/beverage demo datasets + tiers, a generic no-code mapping template library, a historian connector, accessibility (WCAG light + Arabic RTL) and scale.
V4 · Enterprise & Reference. HA/restore, OT-safe edge agent, human-approved advisory write-back, SOC 2 / ISO / GxP, and the pilot -> proven-ROI -> signed-contract -> case-study business arc.
HOW TO READ A ROW
Each task carries the Persona(s) and the exact Sub-criterion it lifts, the Doctrine v7 Gate it serves, a junior-dev-actionable Description, and a hard reproducible Acceptance check (never 'build passes'). Status/% done is assessed against the 20-Jun code export.
THE TARGET (requirement 3)
Every one of the 63 sub-criteria has at least one lifting task and a projected score >=75; the six personas clear 75 once their sub-criteria do. See the 'Coverage to 75' sheet for the full map (current -> task -> version -> projected).
NAMING LAW (permanent)
No task creates an artifact named with phase/task/version-phase codes. V2-24 renames the 193 existing offenders. Task IDs here (V1-07 etc.) are backlog handles, never artifact names.
SCORE BANDS
Critical <55 · Needs work 55-69 · Solid 70-84 · Strong 85+ ¦ Status: REMOVED >=85% · MOSTLY-DONE 65-84% · PARTIAL <65% · NEW 0%

## Backlog
PlantProcess IQ — Product Backlog v4 · versioned (V1<100h) · floor-to-75 · generated from Roadmap v3 + Identity v3 + the 20-Jun scoreboard
Task ID | Version | Phase | Task Name | Persona(s) | Sub-criterion lifted | Gate | Track | Module | Severity | Status | % done | Description (junior-dev-actionable) | Validation / Acceptance (hard, reproducible) | Task Type | Effort (h) | Prereq
V1-01 | V1 | V1-P1 Reproducible env | Harden ppiq.ps1 single entrypoint (bake env, EF-first migrate) | A1,A4 | A1-2, A1-10 | G9 | Environment | Infra | Critical | MOSTLY-DONE | 72% | ppiq.ps1 verbs exist and work, but `migrate`/`demo` do not run `dotnet ef database update` before the numbered SQL, and PGCLIENTENCODING is not baked in. Fold EF-update into the start of migrate/demo; export PGCLIENTENCODING=UTF8 before every psql; remove the redundant inline EF call from the Jenkins stage. | From a clean DB, `ppiq.ps1 demo` provisions one-shot (EF schema then SQL decoration then app on :5063) with no manually-set env vars. Evidence: terminal log of a clean run. | refactor | 3 | —
V1-02 | V1 | V1-P1 Reproducible env | Commit reproducibility config: design-time factory + PGCLIENTENCODING + EF-first | A1 | A1-2 | G9 | Environment | Infra | Critical | NEW | 10% | Rewrite PlantProcessDesignTimeDbContextFactory to read ConnectionStrings__PlantProcessDb -> PLANTPROCESS_DESIGNTIME_CONNECTION_STRING -> PLANTPROCESS_DB with an honest error. Commit so the two session env-vars (PLANTPROCESS_DB, PGCLIENTENCODING) are no longer needed to boot. | A fresh clone runs `dotnet ef database update` and `ppiq.ps1 migrate` with zero hand-set env vars. Evidence: clean-clone run log; grep shows no transient env-var requirement in docs. | hardening | 5 | V1-01
V1-03 | V1 | V1-P1 Reproducible env | Converge to ONE canonical compose + delete orphaned + duplicate fleets | A1,A2 | A1-3, A2-10 | G9 | Environment | Infra | Critical | NEW | 20% | Keep the live `plantprocessiq` project + `docker-compose.sources.yml`. Delete the orphaned `plantprocess-*` stack, the duplicate `docker-compose.demo-sources*.yml` fleet and `.ports.yml`, and `Infrastructure/deploy/docker-compose.demo.yml`. Align Caddy service/port to the API :5063. | `grep -rl docker-compose.demo` and the duplicate-fleet grep both return nothing; `docker compose ... up -d` brings up exactly one healthy app stack Caddy routes to. Evidence: dir listing + docker ps. | refactor | 6 | —
V1-04 | V1 | V1-P1 Reproducible env | Fix connection-string key __DefaultConnection -> __PlantProcessDb (incl. the generator) | A2 | A2-5, A2-10 | G12 | Environment | Infra | Critical | NEW | 10% | Replace ConnectionStrings__DefaultConnection with ConnectionStrings__PlantProcessDb in deploy/compose/.env.dev, docker-compose.yml, and env/profiles/local.env, AND in the generator tools/realization/continue-phase03-phase04-from-t016.cjs that re-emits the wrong key. The generator is the root cause - fix it or it re-introduces the defect. | grep finds zero `__DefaultConnection`; a generated compose contains `__PlantProcessDb`; the container API boots and connects. Evidence: grep output + boot log. | bug fix | 3 | —
V1-05 | V1 | V1-P1 Reproducible env | Delete env/profiles/local.env (leaks plantprocess123) + rotate | A2 | A2-5 | G12 | Environment | Security | Critical | NEW | 10% | Remove env/profiles/local.env (it carries IsBootstrapAdmin=true and the literal plantprocess123) and rotate any key that ever touched it. Keep only deploy/compose/.env.dev (container-local creds) and a git-ignored server .env. | grep finds zero `plantprocess123` and zero `IsBootstrapAdmin=true` in the repo; the startup guard still passes. Evidence: grep output. | bug fix | 2 | —
V1-06 | V1 | V1-P1 Reproducible env | Commit test config — permanently fix the 83 clean-machine failures | A1 | A1-2 | G10 | Environment | Testing | Critical | PARTIAL | 25% | Author committed appsettings.Test.json (DSN + 64-char signing key + a real admin + PPIQ_FORCE_EXTERNAL_API_TEST_HOST) and wire Do-Test so WebApplicationFactory boots the host and finds the DB without per-run env vars. This is the documented cause of the 83 reds. | `ppiq.ps1 test` exits 0 TWICE on a fresh checkout (no hand-set vars). Evidence: two consecutive green run logs. | hardening | 6 | V1-02
V1-07 | V1 | V1-P1 Reproducible env | Rebuild mapping/genealogy/safe-SQL foundation (demo-minimum, model-first) | A3,A4 | A3-5, A3-8, A4-2 | G2 | Foundation | Database | Critical | NEW | 5% | The foundation is lost (no clean git copy): ppiq_business_key_definitions, canonical_business_keys, canonical_mapping_versions, the canonical genealogy tables, ppiq_walk_genealogy and ppiq_resolve_safe_sql are gone; only genealogy_edges (EF) survives. Rebuild the DEMO-MINIMUM set model-first: entities + IEntityTypeConfiguration for the business-key/canonical-mapping tables; the recursive walk + cycle/orphan validators + the safe-SQL resolver in a thin SQL migration. Scope to what the demo thread needs; defer full mapping-lifecycle hardening to V2. | On the demo dataset, ppiq_walk_genealogy(C-0044170) returns the full coil->melt chain both directions; a bad mapping returns a typed error and rolls back; the 311/321 validators are green (un-quarantined). Evidence: psql output + green migration. | new feature | 18 | V1-02
V1-08 | V1 | V1-P1 Reproducible env | Verify genealogy both directions on C-0044170 live | A3 | A3-5 | G2 | Demo | Backend | Critical | PARTIAL | 20% | With the foundation rebuilt, walk C-0044170 coil->melt and melt->coils in the running HMI, confirming the Material Investigation evidence panel renders both directions. | Recorded walk: both directions resolve on the demo data, no stall. Evidence: clip in the dry-run. | test | 4 | V1-07
V1-09 | V1 | V1-P1 Reproducible env | Verify transition-coil weighted attribution (70/30) live | A3 | A3-8 | G15 | Demo | AI+ML | Very important | PARTIAL | 30% | Confirm a casting-transition coil reports weighted (e.g. 70/30) attribution across two heats with the population/exclusions shown. | A transition coil renders weighted provenance + stated population live. Evidence: clip. | test | 3 | V1-07
V1-PT1 | V1 | V1-P1 Reproducible env | V1-P1 acceptance gate: clean checkout boots seeded + green twice | A1 | A1-2, A1-5 | G10 | Environment | Testing | Critical | NEW | 0% | End-of-phase regression: clean clone -> `ppiq.ps1 reset && ppiq.ps1 demo` boots the seeded stack; `ppiq.ps1 test` green twice; genealogy walk resolves. Seals V1-P1 as deployable. | All three gates pass on a fresh machine, scripted. Evidence: one combined run log. | test | 4 | V1-06,V1-07
V1-10 | V1 | V1-P2 Live demo + collateral | App boots under Playwright (no early webServer exit) | A3,A5 | A3-2, A5-8 | G7 | Demo | FrontEnd | Critical | PARTIAL | 55% | Fix playwright config so webServer starts the API+web and waits for :5063/:5173 instead of exiting early; run at least one real spec against the booted app. | `ppiq.ps1 e2e` starts the app and runs >=1 spec to green. Evidence: Playwright HTML report. | bug fix | 5 | V1-PT1
V1-11 | V1 | V1-P2 Live demo + collateral | One-click readiness check passes live | A4 | A4-7 | G7 | Demo | Backend | Critical | PARTIAL | 50% | Make the readiness surface return green (sources healthy, counts match, jobs ready) in one call on the seeded stack. | Readiness endpoint returns all-green on the demo data, shown live. Evidence: screenshot + clip. | modification | 4 | V1-10
V1-12 | V1 | V1-P2 Live demo + collateral | Fix every demo-path button (live click-through) | A3 | A3-1, A3-3 | G6 | Demo | FrontEnd | Critical | PARTIAL | 58% | The dead-button scan is green (0 stub handlers) but live-path proof is missing. Click every control on the 9-step path in the running HMI; wire/disable-with-reason any that misbehaves. (Full StandardButton migration is V2-02.) | Every button on the 9-step script performs its action live; 0 unhandled rejections on the path. Evidence: recorded run. | bug fix | 5 | V1-10
V1-13 | V1 | V1-P2 Live demo + collateral | Record the clean dry-run video (insurance) | A3 | A3-2 | G7 | Demo | Testing | Critical | NEW | 0% | Record an MP4 of the full 9-step walk on the seeded stack - the pilot acceptance artifact and the backup if live ever fails. | MP4 exists; no dead click; matches the script. Evidence: the file. | test | 3 | V1-12
V1-14 | V1 | V1-P2 Live demo + collateral | Rehearse the 9-step demo script cold | A3 | A3-2 | G7 | Demo | Docs | Very important | NEW | 0% | Write the 9-step script (connect->map->build page->run job->dashboard->genealogy->value->assistant->export) and rehearse it until reflexive, including the surprise-question answers from Roadmap 1.3. | You run it cold once end-to-end. Evidence: the script doc + a rehearsal note. | modification | 2 | V1-13
V1-15 | V1 | V1-P2 Live demo + collateral | Illustrative ROI model for the presentation (projected-not-proven) | A5 | A5-1, A5-7 | G5 | Collateral | AI+ML | Very important | NEW | 10% | Tie a live demo finding (e.g. edge-crack/superheat) to a conservative EUR/yr figure with stated assumptions, labelled projected-not-proven, that exceeds the stated price. | A slide + handout with a defensible EUR/yr number, assumptions, and the demo finding it derives from. Evidence: the file. | new feature | 4 | V1-11
V1-16 | V1 | V1-P2 Live demo + collateral | Founder domain-credibility pack (14 yrs PSI/SMS, named plants) | A5 | A5-10 | G8 | Collateral | Docs | Very important | NEW | 0% | One-pager + a slide naming specific plants/processes from your PSI Metals / SMS / EzzSteel years, placed before the offer slide. The biggest non-code lever a solo founder has. | One-pager + slide exist, on-brand, with named plants. Evidence: the file. | new feature | 2 | —
V1-17 | V1 | V1-P2 Live demo + collateral | Pitch deck (10-12 slides, on-brand) | A5,A6 | A5-9 | G8 | Collateral | Docs | Very important | NEW | 0% | Problem -> why BI fails -> evidence-grade approach -> LIVE DEMO -> value -> honest boundary -> read-only/OT-safe -> credibility -> pilot offer. <=12 slides, brand palette, also produces logo/brand assets for the variant set. | Rehearsed once; <=12 slides; on-brand. Evidence: the file. | new feature | 4 | V1-16
V1-18 | V1 | V1-P2 Live demo + collateral | One-page product brief (light-surface PDF) | A6 | A6-9 | G8 | Collateral | Docs | Important | NEW | 0% | What it is, the read-only/evidence-grade differentiator, pilot scope, the data-ask - rendered as a light-surface PDF with brand header/footer. | Renders with brand header/footer. Evidence: the PDF. | new feature | 2 | V1-17
V1-19 | V1 | V1-P2 Live demo + collateral | Pilot offer document (EUR30-40k -> EUR120k license) | A5 | A5-7 | G5 | Collateral | Docs | Very important | NEW | 0% | One page: the pilot price (lean EUR30k for the first), the credited EUR120k/yr license figure, the 8-week proven-ROI deliverable, and the data-ask. | One page with a number + the ask. Evidence: the file. | new feature | 2 | V1-15
V1-20 | V1 | V1-P2 Live demo + collateral | Cut the 2-3 minute demo video | A6 | A6-9 | G8 | Collateral | Web | Important | NEW | 0% | Edit the dry-run into a 2-3 min highlight reel for follow-up and LinkedIn. | 2-3 min MP4; no dead click. Evidence: the file. | new feature | 3 | V1-13
V1-21 | V1 | V1-P2 Live demo + collateral | Sharpen the IQ product page; others 'coming soon' | A6 | A6-7 | G8 | Collateral | Web | Critical | PARTIAL | 40% | Complete the PlantProcess IQ page (description + benefit + graphics + honest claims); stub QES/Energy/Yard as 'coming soon'. Closes the A6-7 Critical for the presentation (full pack depth is V3). | IQ page complete; honesty-lint green; others stubbed. Evidence: the page + lint pass. | modification | 3 | —
V1-22 | V1 | V1-P2 Live demo + collateral | Wire website CTA to a real inbox (lead delivery) | A6 | A6-10 | G8 | Collateral | Web | Very important | PARTIAL | 30% | Point RequestDemoForm at a real delivery (email + a stored row) so a submission actually reaches you. (Hardened backend + e2e assert is V2-18.) | A test submit lands in your inbox/DB. Evidence: the received lead. | modification | 3 | V1-21
V2-01 | V2 | V2-P3 Stability + UI | Full backend+frontend suite green twice on clean machine | A1 | A1-2 | G10 | Codebase | Testing | Critical | PARTIAL | 20% | Beyond the 83-failure fix, run the whole suite (dotnet test + npm test + e2e) twice on a clean machine, quarantine and flag any flaky test deterministically. | test && e2e exit 0 twice on a fresh checkout. Evidence: two green logs + flaky ledger. | test | 10 | V1-06
V2-02 | V2 | V2-P3 Stability + UI | Standardize all 151 native buttons onto StandardButton | A1,A3 | A1-1, A3-3 | G6 | Codebase | FrontEnd | Important | PARTIAL | 10% | button-inventory.csv shows 151/164 wired native <button> off the design system (~8% adoption). Migrate them to StandardButton, batching by file; keep the inventory as the burn-down ledger. | standardStatus non-standard count -> 0; StandardButton snapshot/contract tests green. Evidence: regenerated inventory. | refactor | 14 | V1-12
V2-03 | V2 | V2-P3 Stability + UI | E2E action-matrix enumerating every demo-path control | A3 | A3-1 | G6 | Codebase | Testing | Very important | NEW | 0% | Author an e2e matrix that enumerates every interactive control on the demo path and asserts each does something real - the structural no-dead-button proof. | Matrix enumerates every demo control and passes. Evidence: the spec + report. | test | 8 | V2-02
V2-04 | V2 | V2-P3 Stability + UI | Visual-regression harness (baseline + diff gate) | A3 | A3-3 | G6 | Codebase | Testing | Important | NEW | 0% | Capture baseline screenshots of the demo pages and gate PRs on pixel diffs above a threshold. | Visual-regression green on the demo path; an intentional change is caught. Evidence: the report. | test | 6 | V2-02
V2-05 | V2 | V2-P3 Stability + UI | Nightly full-suite CI job (cron) | A1 | A1-2 | G10 | Non-code-tech | Testing | Very important | PARTIAL | 30% | Add a Jenkins cron that runs up->migrate->seed->test->e2e on an ephemeral stack nightly with a pass/fail trend (the blocking stages already exist in the Jenkinsfile). | Nightly job runs the full suite + e2e and records a trend. Evidence: two nightly runs. | new feature | 6 | V2-01
V2-06 | V2 | V2-P3 Stability + UI | Health dashboard (suite/e2e pass-rate, flaky count) | A4 | A4-4 | G9 | Non-code-tech | Testing | Normal | NEW | 0% | A small dashboard showing suite + e2e pass-rate, soak result, and open-flaky count. | Dashboard renders the trend. Evidence: screenshot. | new feature | 5 | V2-05
V2-07 | V2 | V2-P4 License + Role + Security | MFA step-up for admin accounts | A2 | A2-4 | G12 | Codebase | Security | Very important | NEW | 0% | Add an MFA step-up for admin-role actions (doctrine requires admin MFA). TOTP enrolment + challenge on privileged endpoints. | Admin login requires the second factor live; a non-MFA admin call is rejected. Evidence: test + clip. | new feature | 8 | V1-06
V2-08 | V2 | V2-P4 License + Role + Security | Deepen license tiers: caps enforced + expiry/grace + admin governance | A5 | A5-3 | G5 | Codebase | Backend | Very important | NEW | 0% | Enforce the signed seat/source/job/dashboard caps; surface issue/expiry from the token; on expiry -> warnings -> configurable read-only grace (data never destroyed); add admin governance to view entitlement + caps. | A live Enterprise->Pro toggle changes caps; exceeding a seat cap is blocked; expiry triggers grace. Evidence: tests + clip. | new feature | 12 | V2-07
V2-09 | V2 | V2-P4 License + Role + Security | Full RBAC role-scope live across 6 roles | A5 | A5-2 | G5 | Codebase | Backend | Very important | PARTIAL | 55% | Owner/Plant-Admin/Data-Engineer/Engineer/Operator/Viewer-Executive: enforce per-role view/edit scope on every page/endpoint and prove it across all six logins. | Authorization matrix green by identity; each role sees only its scope live. Evidence: matrix test + clips. | hardening | 10 | V2-08
V2-10 | V2 | V2-P4 License + Role + Security | Enforce RLS on core tables (decide tenant_id; non-superuser app role) | A2 | A2-6 | G5 | Codebase | Database | Very important | PARTIAL | 40% | Decide deliberately (RLS-scoped core vs single-tenant-per-deploy). If multi-tenant: add tenant_id to the core EF entities model-first, run the app under a non-superuser role so RLS is actually enforced (locally ppiq_dev is bypassrls), and prove cross-tenant 403/empty. | Cross-tenant access returns 403/empty live under a non-superuser role. Evidence: RlsTenantIsolation test green + clip. | hardening | 10 | V2-07
V2-11 | V2 | V2-P4 License + Role + Security | Encryption at rest: staging/canonical/credential-vault | A2 | A2-9 | G12 | Codebase | Security | Important | NEW | 0% | Enable encryption at rest for the staging/canonical stores and the credential vault; confirm secrets never reach the browser. | At-rest encryption on; audit-immutability green in CI. Evidence: config + CI run. | hardening | 6 | —
V2-12 | V2 | V2-P4 License + Role + Security | Pricing & license-tiers page (grants/renewal/caps) | A6 | A6-7 | G8 | Codebase | Web | Important | NEW | 0% | Publish the tier grants, renewal terms and caps so a buyer's licensing questions are answered before the call. | Tiers page live; honesty-lint green. Evidence: the page. | new feature | 5 | V2-08
V2-13 | V2 | V2-P5 AI/ML quality | Sharpen AI/ML results: calibration, effect-size ranking, stratified quality | A3 | A3-7, A3-11 | G4 | Codebase | AI+ML | Very important | NEW | 0% | Build on the 1,172-line compute engine: add confidence calibration, rank by effect size (not just p), and improve stratified-finding quality so results are more exact and more impressive - while keeping every number cited. | On the golden dataset, true signals recovered + spurious rejected under FDR; calibrated confidences; a live recompute. Evidence: golden-set test + clip. | new feature | 12 | V1-09
V2-14 | V2 | V2-P5 AI/ML quality | Impressive evidence-ranked suggestion engine (deterministic, euro impact) | A5 | A5-9 | G4 | Codebase | AI+ML | Very important | PARTIAL | 55% | Deterministic, MD5-stable suggestions ranked by evidence + euro impact, workflow-bound with RBAC, surfaced in SuggestionCardsPanel - the 'told me something I didn't know, and proved it' moment. | Suggestions render with population, method, evidence handle and a euro range; reproducible IDs. Evidence: test + clip. | new feature | 10 | V2-13
V2-15 | V2 | V2-P5 AI/ML quality | Assistant eval harness + model-version governance gate | A2 | A2-8 | G13 | Codebase | AI+ML | Important | NEW | 0% | A regression harness for the assistant (no-uncited-number, abstain, grounding) that gates a model-version change. | Harness blocks a regression on a model swap. Evidence: the gate firing in CI. | test | 6 | V2-13
V2-16 | V2 | V2-P5 AI/ML quality | Wire DataBoundaryPolicy into assistant dispatch (no-egress live) | A2 | A2-8 | G13 | Codebase | AI+ML | Very important | PARTIAL | 50% | Route every assistant call through the gateway so only question + scoped evidence leaves; honour a per-tenant no-egress toggle (self-hosted default). | Self-hosted mode leaks nothing; private-endpoint sends only question+evidence; toggle proven. Evidence: test + capture. | hardening | 7 | V2-15
V2-17 | V2 | V2-P5 AI/ML quality | Wire SourceLoadProtectionPolicy into the live query path | A2 | A2-3 | G11 | Codebase | Backend | Very important | PARTIAL | 50% | Enforce the per-source impact budget on a real query path so an over-budget query is throttled, not just policy-defined. | An over-budget query is throttled live. Evidence: test + clip. | hardening | 7 | —
V2-18 | V2 | V2-P5 AI/ML quality | Real lead-capture backend (form->DB row+email, e2e asserts) | A6 | A6-10 | G8 | Codebase | Backend | Important | PARTIAL | 30% | Harden the CTA path into a real backend: validated submit -> stored row + email, with an e2e test asserting the row. | e2e asserts a lead row + email on submit. Evidence: the test. | new feature | 6 | V1-22
V2-19 | V2 | V2-P6 Docs + hygiene | 'How to use' user guide WITH app screenshots + 9-step walkthrough | A6 | A6-6 | G8 | Non-code-tech | Docs | Important | NEW | 0% | A user guide with real app screenshots walking the 9-step flow (connect -> map -> build -> run -> dashboard -> genealogy -> value -> assistant -> export). | Guide exists with current screenshots + the walkthrough. Evidence: the file. | new feature | 8 | V1-13
V2-20 | V2 | V2-P6 Docs + hygiene | 'How to install' deployment runbook WITH screenshots | A4 | A4-9 | G9 | Non-code-tech | Docs | Important | NEW | 0% | A step-by-step install runbook (local + server) with screenshots, env layout, and the one-command path - so a clean machine reaches a working login by runbook alone. | A reviewer follows it to a working login. Evidence: the file + a dry-run note. | new feature | 8 | V1-02
V2-21 | V2 | V2-P6 Docs + hygiene | Admin/Operator guide WITH screenshots | A4 | A4-1 | G9 | Non-code-tech | Docs | Important | NEW | 0% | Admin + operator workflows (users, roles, sources, mapping, jobs) with screenshots. | Guide exists + reviewed once. Evidence: the file. | new feature | 10 | V2-20
V2-22 | V2 | V2-P6 Docs + hygiene | Security whitepaper (posture, data boundary, OT-safety) | A2 | A2-1 | G16 | Non-code-tech | Docs | Important | NEW | 0% | The procurement-facing security posture: Argon2id, signed licensing, read-only/OT-safe, tenant isolation, audit, data boundary. | Whitepaper exists + reviewed once. Evidence: the file. | new feature | 6 | —
V2-23 | V2 | V2-P6 Docs + hygiene | API reference | A1 | A1-7 | G16 | Non-code-tech | Docs | Normal | NEW | 0% | Generate/curate an API reference for the public endpoints (auth, licensing, connectors, analytics, value). | API reference published. Evidence: the file/site. | new feature | 4 | —
V2-24 | V2 | V2-P6 Docs + hygiene | Naming golden-rule pass: rename 193 phase/task-named artifacts | A1 | A1-4 | G10 | Codebase | Refactor | Important | NEW | 0% | 193 files carry phase/task tokens (p03_p04, phase8, T042, _v6_, hotfix). Rename to descriptive names and update references; preserve only ordered-migration numeric prefixes (strip the embedded phase label). | The phase/task-token grep returns 0 (outside ordered-prefix migrations); build + tests green. Evidence: grep + green build. | refactor | 18 | V2-01
V2-25 | V2 | V2-P6 Docs + hygiene | HasDefaultSchema -> ppiq_meta/ppiq_plant for EF entities | A1 | A1-3 | G2 | Codebase | Database | Normal | NEW | 0% | Add HasDefaultSchema mapping so EF tables land in ppiq_meta/ppiq_plant instead of public, realising the app-metadata vs customer-data split. (Residual of the old 000_schemas task.) | `\dt ppiq_meta.*` and `ppiq_plant.*` list the EF tables after migrate. Evidence: psql output. | refactor | 4 | V1-07
V3-01 | V3 | V3-P7 Multi-industry data | Second-industry demo dataset (paper/board line) + mapping templates | A1,A3 | A1-6 | G1 | Codebase | Database | Very important | NEW | 0% | Author a realistic paper/board demo plant (sources + imperfections) and the canonical-mapping templates that map it - proving the platform is generic beyond flat steel. | ppiq.ps1 up-sources brings up the paper fleet healthy; the canonical model maps it; a genealogy thread resolves. Evidence: counts + clip. | new feature | 14 | V2-25
V3-02 | V3 | V3-P7 Multi-industry data | Third-industry demo dataset (food & beverage) + tier configs | A1,A3 | A1-6 | G1 | Codebase | Database | Very important | NEW | 0% | A food & beverage demo plant + tier-specific configs, demonstrating per-industry/per-tier datasets. | F&B fleet healthy + mapped; tier configs switch. Evidence: counts + clip. | new feature | 12 | V3-01
V3-03 | V3 | V3-P7 Multi-industry data | Generic canonical-mapping template library + no-code visual-mapper polish | A4 | A4-2 | G2 | Codebase | FrontEnd | Very important | NEW | 0% | A reusable template library + a polished no-code visual mapper so the common case needs no SQL (safe-SQL only for the long tail). | A new source is mapped live with no code via a template; a KPI-as-view is built. Evidence: clip. | new feature | 12 | V1-07
V3-04 | V3 | V3-P7 Multi-industry data | Demo dataset polish + per-industry scripted reset | A4 | A4-3 | G7 | Codebase | Database | Important | PARTIAL | 60% | Polish each demo dataset and add a one-command scripted reset per industry so any prospect sees the same clean story. | One command resets+reseeds an industry to a known state. Evidence: run log. | modification | 6 | V3-02
V3-05 | V3 | V3-P7 Multi-industry data | Historian connector to GA (behavioural-tested) | A1 | A1-6 | G1 | Codebase | Backend | Very important | NEW | 0% | Bring one historian/OPC connector to GA with honest availability + behavioural tests, broadening reach toward incumbents. | The connector passes behavioural tests live; credentials never on read-back. Evidence: tests + clip. | new feature | 12 | —
V3-06 | V3 | V3-P7 Multi-industry data | One-command customer-install package (per-industry overlay) | A4 | A4-9 | G9 | Non-code-tech | Deploy | Very important | NEW | 0% | A one-command install that takes the server overlay + a customer .env (+ an industry overlay) to a working install. | A clean machine reaches a working login via one command. Evidence: run log. | new feature | 8 | V2-20
V3-07 | V3 | V3-P8 Accessibility + scale | WCAG 2.1 AA light theme + contrast audit | A6 | A6-4 | G14 | Codebase | FrontEnd | Important | NEW | 0% | Add a contrast-audited WCAG 2.1 AA light theme alongside the dark one. | AA contrast audit passes on the light theme. Evidence: audit report. | new feature | 10 | —
V3-08 | V3 | V3-P8 Accessibility + scale | Arabic RTL + locale/units/timezone switching per user | A6 | A6-8 | G14 | Codebase | FrontEnd | Important | NEW | 0% | RTL layout for Arabic + per-user locale, units and timezone switching. | Arabic RTL renders; units/timezone switch per user. Evidence: clips. | new feature | 8 | V3-07
V3-09 | V3 | V3-P8 Accessibility + scale | i18n as resource files (.resx/JSON) + fix mojibake | A6 | A6-2 | G14 | Codebase | FrontEnd | Important | NEW | 0% | Move German/Arabic strings out of SQL seeds into resource files and repair the encoding-damaged (mojibake) translations. | Strings load from resources; no mojibake; honesty-lint green. Evidence: rendered locales. | refactor | 8 | V3-08
V3-10 | V3 | V3-P8 Accessibility + scale | Performance-at-scale validation (630/5,600, virtualized tables) | A3 | A3-9 | G6 | Codebase | Testing | Important | NEW | 0% | Measure interaction latency at >=630 heats / >=5,600 coils with virtualized tables; assert performance budgets. | No lag at demo scale; budgets met (measured). Evidence: perf report. | test | 8 | —
V3-11 | V3 | V3-P8 Accessibility + scale | Soak job (24-72h synthetic load on demo path) | A4 | A4-4 | G9 | Non-code-tech | Testing | Important | NEW | 0% | Hold the stack up under a synthetic load driver on the demo path; assert no memory growth, no unhandled rejections, no crashed jobs - the 'tested for days' evidence. | A 24-72h soak passes clean. Evidence: soak report. | test | 8 | V2-05
V3-12 | V3 | V3-P8 Accessibility + scale | QES product page to depth | A6 | A6-7 | G8 | Codebase | Web | Optional | NEW | 0% | Build the Quality/Surface pack page to IQ depth (description+benefit+graphics+licensing); honesty-lint green. | QES page complete; lint green. Evidence: the page. | new feature | 7 | V1-21
V3-13 | V3 | V3-P8 Accessibility + scale | Energy Management product page to depth | A6 | A6-7 | G8 | Codebase | Web | Optional | NEW | 0% | Build the Energy pack page to IQ depth; honesty-lint green. | Energy page complete; lint green. Evidence: the page. | new feature | 7 | V1-21
V4-01 | V4 | V4-P9 Ops/HA + OT | Backup/restore drill (verified restore, recorded) | A4 | A4-9 | G9 | Codebase | Deploy | Very important | NEW | 0% | Document and perform a backup + verified restore drill; record it. | A restore is performed + verified, recorded. Evidence: the recording. | new feature | 8 | —
V4-02 | V4 | V4-P9 Ops/HA + OT | Verify deploy rollback to :previous | A4 | A4-9 | G9 | Codebase | Deploy | Important | NEW | 0% | Tag and test rollback to the previous image on a bad deploy. | A bad deploy rolls back to :previous. Evidence: run log. | test | 5 | V4-01
V4-03 | V4 | V4-P9 Ops/HA + OT | Time-series store (hypertables, compression, retention) | A4 | A4-3 | G9 | Codebase | Database | Very important | NEW | 0% | Add the time-series-optimized store for high-frequency process parameters (hypertables/columnar, compression, downsampling, retention). | Process-parameter ingest scales on the TS store; retention applies. Evidence: load test + config. | new feature | 12 | —
V4-04 | V4 | V4-P9 Ops/HA + OT | Deployable OT-safe edge agent (one-way push) | A2 | A2-2 | G11 | Codebase | Infra | Very important | NEW | 0% | Turn the OtSafeEdgeCollectorGateway contract into a deployable agent in the DMZ that pushes one-way (CDC/replica preferred); no inbound path to OT. | The agent pushes one-way; no inbound OT path; source-load within budget. Evidence: deploy + capture. | new feature | 12 | V2-17
V4-05 | V4 | V4-P9 Ops/HA + OT | Human-approved advisory write-back (business workflow, never OT) | A5 | A5-1 | G5 | Codebase | Backend | Very important | NEW | 0% | The read-only ceiling-raiser: an advisory write-back to a BUSINESS workflow (never a control system) that requires human approval + audit. | A write-back requires approval + is audited; no OT path. Evidence: test + clip. | new feature | 10 | —
V4-06 | V4 | V4-P9 Ops/HA + OT | Enforce performance budgets in CI | A1 | A1-9 | G10 | Codebase | Testing | Important | NEW | 0% | Gate CI on the demo-path performance budgets so a regression fails the build. | A budget regression fails CI. Evidence: the gate firing. | test | 6 | V3-10
V4-07 | V4 | V4-P9 Ops/HA + OT | Load-test at reference-plant scale | A3 | A3-9 | G9 | Codebase | Testing | Very important | NEW | 0% | Run a load test at the reference customer's real scale. | Load test passes at reference scale. Evidence: report. | test | 8 | V4-03
V4-08 | V4 | V4-P10 Compliance + ops | Start SOC 2 Type II observation window | A2 | A2-1 | G16 | Non-code-tech | Security | Very important | NEW | 0% | Open the SOC 2 Type II observation window with an auditor/tool now (6-12 month window; starting late gates a year). | Observation window opened. Evidence: auditor/tool confirmation. | new feature | 10 | V2-22
V4-09 | V4 | V4-P10 Compliance + ops | ISO 27001 mapping + sensitive-data catalog | A2 | A2-1 | G16 | Non-code-tech | Security | Important | NEW | 0% | Map controls to ISO 27001 and build a sensitive-data catalog. | Mapping + catalog exist. Evidence: the docs. | new feature | 8 | V4-08
V4-10 | V4 | V4-P10 Compliance + ops | GxP / 21 CFR Part 11 pack (audit trail, e-signature) | A2 | A2-9 | G16 | Codebase | Security | Optional | NEW | 0% | A regulated-industries pack (audit trails, e-signature, validation evidence) for pharma/regulated process plants. | GxP audit-trail + e-signature available where required. Evidence: the pack + test. | new feature | 12 | V2-11
V4-11 | V4 | V4-P10 Compliance + ops | Public status page | A4 | A4-9 | G9 | Non-code-tech | Infra | Normal | NEW | 0% | A public status/health page. | Status page live. Evidence: the URL. | new feature | 4 | —
V4-12 | V4 | V4-P10 Compliance + ops | AI triage loop (agent drafts fix PRs, human-approved) | A1 | A1-2 | G10 | Non-code-tech | Testing | Important | NEW | 0% | An agent reads the latest CI failure + failing test + surrounding code and drafts a fix as a PR with diff + explanation for your review (never auto-merged); flags/quarantines flakies. | The agent opens a reviewable fix PR for a real failure. Evidence: a sample PR. | new feature | 10 | V2-05
V4-13 | V4 | V4-P10 Compliance + ops | Recorded certified dry-run (one-click readiness on video) | A3 | A3-2 | G7 | Non-code-tech | Testing | Very important | NEW | 0% | Record the one-click readiness check green end-to-end - the certified pilot acceptance artifact. | One-click readiness green on video. Evidence: the recording. | test | 4 | V1-13
V4-14 | V4 | V4-P10 Compliance + ops | Consolidate full operator/admin/security docs | A4 | A4-1 | G16 | Non-code-tech | Docs | Important | NEW | 0% | Consolidate the V2 docs into a published operator/admin/security suite for a customer to run + you to support. | Docs published. Evidence: the site/files. | new feature | 8 | V2-21
V4-15 | V4 | V4-P11 Business/Reference | Incorporate (UG/GmbH) + imprint | A5 | A5-10 | G8 | Admin-business | Docs | Very important | NEW | 0% | Register the entity (lets you invoice) + publish the imprint. | Entity registered; imprint live. Evidence: registration. | new feature | 8 | —
V4-16 | V4 | V4-P11 Business/Reference | Pilot contract + MNDA + DPA templates | A2 | A2-1 | G16 | Admin-business | Docs | Very important | NEW | 0% | Lawyer-reviewed pilot contract, MNDA and DPA templates so you can sign when M1 lands. | Templates reviewed + ready. Evidence: the files. | new feature | 8 | V4-15
V4-17 | V4 | V4-P11 Business/Reference | Target list + outreach sequence (PSI network) | A5 | A5-10 | — | Admin-business | Docs | Very important | NEW | 0% | A named list of 8-12 plants via your PSI network + a sent outreach sequence. | Named list + sent sequence; >=3 conversations opened. Evidence: the list + sent log. | new feature | 10 | —
V4-18 | V4 | V4-P11 Business/Reference | Convert presentation customer into a signed paid pilot | A5 | A5-7 | — | Admin-business | Docs | Critical | NEW | 0% | The M2 spine: convert the presentation customer to a signed paid pilot. | A signed pilot exists. Evidence: the signature. | new feature | 12 | V4-16
V4-19 | V4 | V4-P11 Business/Reference | Prove ROI on the customer's real data (pilot deliverable) | A5 | A5-1 | G5 | Admin-business | AI+ML | Critical | NEW | 0% | Run the value engine on the customer's real pilot data and produce a measured before/after - what converts the pilot to the license. | A proven ROI figure on their data. Evidence: the report. | new feature | 8 | V4-18
V4-20 | V4 | V4-P11 Business/Reference | Run the paid pilot | A5 | A5-9 | — | Admin-business | Docs | Critical | NEW | 0% | Execute the 6-8 week pilot on the customer's sources. | Pilot delivered to acceptance. Evidence: acceptance sign-off. | new feature | 20 | V4-19
V4-21 | V4 | V4-P11 Business/Reference | Convert pilot to a signed contract | A5 | A5-7 | — | Admin-business | Docs | Critical | NEW | 0% | Convert the proven pilot into a signed EUR120k/yr license. | A signed contract exists. Evidence: the signature. | new feature | 12 | V4-20
V4-22 | V4 | V4-P11 Business/Reference | Produce the case study / reference | A5 | A5-9 | — | Admin-business | Docs | Very important | NEW | 0% | A quotable, numbers-backed case study from the pilot - the next buyer needs to see it. | A case study with before/after exists. Evidence: the file. | new feature | 6 | V4-21
V4-23 | V4 | V4-P11 Business/Reference | Viability arrangement (hire / escrow+BCP / partner) | A5 | A5-10 | — | Admin-business | Docs | Very important | NEW | 0% | Lower the bus-factor objection: a hire/co-founder OR source-escrow+BCP OR an OEM/partner - one, documented. | One viability arrangement in place + documented. Evidence: the doc. | new feature | 12 | —
V4-24 | V4 | V4-P11 Business/Reference | Support SLA offering | A4 | A4-9 | — | Admin-business | Docs | Important | NEW | 0% | Publish small SLA tiers so you can charge a contract price. | Published SLA tiers. Evidence: the page. | new feature | 5 | —
V4-25 | V4 | V4-P11 Business/Reference | Funding / partnership decision | A5 | A5-10 | — | Admin-business | Docs | Normal | NEW | 0% | A written decision on the funding/partnership path + next step. | A written decision + next step. Evidence: the doc. | new feature | 4 | —
[14 empty] | TOTAL (all versions) | 644

## Version Summary
Version Summary · effort + the floor each version lifts
Version | Theme | Tasks | Effort (h) | < 100 h? | Defining outcome (deployable) | Personas it lifts | Floor after
V1 | First Release — Presentation-Ready | 23 | 96 | YES — 96 h | Live recorded demo + healthy deploy + ROI + collateral + sharp website | A3,A5,A6 (the demo-gating lenses) | ~70-76
V2 | Product Depth — license/role · AI-ML · tests · docs | 25 | 206 | — | Suite green twice, MFA + tier/role depth, sharper AI + suggestions, docs w/ screenshots | A1,A2,A5 to Solid | ~75-80
V3 | Generic & Multi-Industry | 13 | 120 | — | Paper + food datasets, generic mapper, historian GA, WCAG + RTL, scale | A1,A3,A4,A6 generic depth | ~76-82
V4 | Enterprise & Reference | 25 | 222 | — | HA + OT agent + advisory write-back + SOC2/ISO + signed pilot + case study | A2,A4,A5 enterprise + reference | ~80+
| TOTAL | 86 | 644

## Phase Summary
Phase Summary · each phase deployable; V2-V4 phases held to ~45-65 h
Phase | Version | Tasks | Effort (h) | 45-65 h band?
V1-P1 Reproducible env | V1 | 10 | 54 | in band
V1-P2 Live demo + collateral | V1 | 13 | 42 | lean 42
V2-P3 Stability + UI | V2 | 6 | 49 | in band
V2-P4 License + Role + Security | V2 | 6 | 51 | in band
V2-P5 AI/ML quality | V2 | 6 | 48 | in band
V2-P6 Docs + hygiene | V2 | 7 | 58 | in band
V3-P7 Multi-industry data | V3 | 6 | 64 | in band
V3-P8 Accessibility + scale | V3 | 7 | 56 | in band
V4-P9 Ops/HA + OT | V4 | 7 | 61 | in band
V4-P10 Compliance + ops | V4 | 7 | 56 | in band
V4-P11 Business/Reference | V4 | 11 | 105 | heavy 105
V1's two phases run ~54 h and ~42 h (kept tight so the whole release stays under 100 h). V2-V4 phases are sized to the 45-65 h working band; each phase ends deployable.

## Coverage to 75
Coverage to 75 · every sub-criterion has a lifting task and projects >=75
Current floors (20-Jun): A1 63 · A2 72 · A3 61 (headline) · A4 64 · A5 67 · A6 63. Target: all six personas AND all 63 sub-criteria >=75.
Sub-criterion | Name | Current | Lifting task(s) | Version | Projected
A1-1 | Hygiene & clean code | 58 | V2-02 | V2 | 78
A1-2 | Stability under change | 58 | V1-06 / V2-01 | V1->V2 | 80
A1-3 | Repo structure | 59 | V1-03 / V2-25 | V1 | 80
A1-4 | Naming & structure | 60 | V2-24 | V2 | 82
A1-5 | Tests execute, not enumerate | 80 | holds (CI truth-gate) | - | 82
A1-6 | Generic any-DB | 68 | V3-01 / V3-05 | V3 | 80
A1-7 | Extensibility | 72 | V3-05 / V2-23 | V2/V3 | 80
A1-8 | Structural consistency | 66 | V2-02 | V2 | 76
A1-9 | Pipeline & deploy | 72 | V1-03 / V4-06 | V1/V4 | 82
A1-10 | Switchable profiles | 62 | V1-01 / V2-09 | V1/V2 | 78
A1-11 | No silent failure | 68 | V1-12 / V2-03 | V1/V2 | 80
A1-12 | Endpoint resilience | 63 | V2-03 | V2 | 76
A2-1 | Read-only absolute | 76 | holds; V2-22 reinforces | - | 82
A2-2 | OT-safe topology | 60 | V4-04 | V4 | 80
A2-3 | Source-load protection | 68 | V2-17 | V2 | 80
A2-4 | Token & session | 80 | holds; V2-07 MFA | V2 | 84
A2-5 | Secrets handling | 66 | V1-04 / V1-05 | V1 | 80
A2-6 | Tenant isolation | 66 | V2-10 | V2 | 82
A2-7 | Per-endpoint authz | 76 | holds | - | 80
A2-8 | AI data boundary | 62 | V2-15 / V2-16 | V2 | 80
A2-9 | Audit & encryption | 68 | V2-11 | V2 | 80
A2-10 | Deploy hardening | 66 | V1-03 / V4-01 | V1/V4 | 80
A3-1 | Zero dead buttons | 66 | V1-12 / V2-03 | V1/V2 | 80
A3-2 | E2E no crash | 60 | V1-10 / V1-13 | V1 | 80
A3-3 | Uniform styling | 57 | V2-02 / V2-04 | V2 | 78
A3-4 | Widget customization | 64 | V1-10 / V2-14 | V1/V2 | 78
A3-5 | Genealogy golden thread | 54 | V1-07 / V1-08 | V1 | 80
A3-6 | Population stated | 68 | V1-09 / V2-13 | V1/V2 | 82
A3-7 | Correlation/ML honest | 69 | V2-13 | V2 | 82
A3-8 | Blended provenance | 62 | V1-07 / V1-09 | V1 | 80
A3-9 | Performance at scale | 60 | V3-10 / V4-07 | V3/V4 | 80
A3-10 | Interactivity + heatmap | 64 | V1-10 / V2-04 | V1/V2 | 78
A3-11 | Correct results | 62 | V1-13 / V2-13 | V1/V2 | 80
A4-1 | Source onboarding (HMI) | 64 | V2-21 / V3-03 | V2/V3 | 80
A4-2 | Mapping & schema config | 54 | V1-07 / V3-03 | V1/V3 | 80
A4-3 | Import jobs & delta | 68 | V3-04 / V4-03 | V3/V4 | 80
A4-4 | Jobs Monitor | 62 | V2-06 / V3-11 | V2/V3 | 78
A4-5 | Schema-drift | 68 | V3-03 | V3 | 78
A4-6 | Fail loudly | 69 | V1-07 / V2-13 | V1/V2 | 80
A4-7 | Readiness meter | 64 | V1-11 | V1 | 80
A4-8 | Backfill & protection | 64 | V2-17 / V4-03 | V2/V4 | 78
A4-9 | Operational resilience | 58 | V2-20 / V4-01 | V2/V4 | 82
A4-10 | Concurrency | 68 | V1-10 / V2-03 | V1/V2 | 80
A5-1 | Quantified value (EUR) | 66 | V1-15 / V4-19 | V1/V4 | 82
A5-2 | Role-scoped view/edit | 64 | V2-09 | V2 | 80
A5-3 | License tiers live | 69 | V2-08 | V2 | 82
A5-4 | Trustworthy AI | 69 | V2-13 / V2-15 | V2 | 80
A5-5 | Honest boundary | 69 | V1-09 / V2-13 | V1/V2 | 80
A5-6 | Speed of insight | 64 | V1-11 / V2-13 | V1/V2 | 78
A5-7 | Price-to-value | 62 | V1-15 / V1-19 | V1 | 80
A5-8 | Cross-device/browser | 62 | V3-07 / V3-10 | V3 | 78
A5-9 | Distinctiveness | 70 | V1-17 / V2-14 | V1/V2 | 82
A5-10 | Founder credibility | 52 | V1-16 | V1 | 80
A6-1 | Tagline & voice | 74 | V1-21 | V1 | 78
A6-2 | Honesty-lint | 74 | V2-22 / V3-09 | V2/V3 | 80
A6-3 | Palette fidelity | 80 | holds | - | 82
A6-4 | Typography | 72 | V3-07 | V3 | 78
A6-5 | Logo system | 64 | V1-17 | V1 | 78
A6-6 | Website UX | 64 | V3-07 / V3-08 | V3 | 80
A6-7 | All products to depth | 52 | V1-21 / V3-12 / V3-13 | V1/V3 | 80
A6-8 | In-app brand | 68 | V2-02 | V2 | 78
A6-9 | Reports/PDF brand | 68 | V1-18 / V1-20 | V1 | 78
A6-10 | CTA & lead capture | 58 | V1-22 / V2-18 | V1/V2 | 80

## Completed (Removed)
Completed (Removed) · tasks >85% done — taken off the active plan
Old ID | Task | % done | Evidence (20-Jun / Identity v3) | Residual work moved to
M1-T02 | Author committed .env.dev (local-only, non-secret) | 95% | Identity v3 sec.0/3/4: .env.dev carries the 5 role users, the token-free 68-char signing key and ConnectionStrings__PlantProcessDb. Canonical identity values locked. | A new V1 task (V1-04/V1-05) fixes the wrong key + the local.env leak that live alongside it.
M1-T03 | Two-schema migration 000_schemas.sql | 85% | Schemas ppiq_meta + ppiq_plant are created. Identity v3 sec.2.2 confirms (gate `\dn` met). | Residual: EF tables still land in public -> moved to V2-25 (HasDefaultSchema).
M1-T04 | Demo-sources compose + committed fixtures (8 sources) | 90% | Identity v3 sec.5: docker-compose.sources.yml (project ppiq-sources) + 630 heats/5,670 coils/39,690 passes/1,987 defects/17,010 QA/210 downtime seeded. T04 closed. | Residual: delete the DUPLICATE demo-sources fleet -> moved into V1-03 (compose convergence).
M1-T05 | Seed one user per role via config | 95% | Identity v3 sec.4: 5 role users (admin/exec/engineer/operator/viewer) in .env.dev; login uses config users; Argon2id on load; bootstrap disabled. | Residual: delete the stale 4-user set in appsettings.Development.json -> folded into V1-05 cleanup.
M1-T06 | Dev Ed25519 license keypair + per-tier tokens | 95% | Identity v3 sec.6: light/pro/proplus/enterprise tokens minted (kid ppiq-dev-ed25519); all 5 Ed25519 checks green this session. | None for the demo; tier-cap ENFORCEMENT depth moved to V2-08.