## Backlog
PPIQ PRODUCT BACKLOG v23 - golden-chain M1 / hardening M2 - 16-Jul-2026 (meeting ~20-Jul). Derives from: concept v1.1, Amendment 7, senior recs 1-17, State Assessment 16-Jul. IDs frozen; removed/done items on the Removed sheet.
ID | Milestone | Phase | Group | Task Name | Severity | Type | Module | Description | Validation | Est (h) | Origin
M1-18 | M1 | M1-P1 Golden Chain | G0 Runtime | Protect the work: logical commits on presentation, safety tag, senior-diff review, merge to main | Critical | governance | Repo | Senior recs 1+5: the 15-16 Jul tree is entirely uncommitted and shared by both branches. Commit in logical units (mojibake fix / presentation profile / workspace wiring / docs), tag pre-merge, read the full presentation->main diff (incl. the parallel-session InteractiveWorkspacePage), run backend+frontend gates, merge, delete branch. One long-lived branch from here. | git log shows logical commits; tag exists; gates green on merged main; presentation branch deleted; working tree clean. | 1 | NEW 16-Jul (senior recs 1,5)
M1-19 | M1 | M1-P1 Golden Chain | G1 Import | Oracle live FOR REAL: PPIQ_SRC on CP-04/CP-06 + proven test-connect and discovery | Critical | defect fix | Connectors | Open since 15-Jul; red banner captured in 16-Jul screenshot. Enter Schema Name PPIQ_SRC on both Oracle profiles, prove test-connect and live table discovery in the HMI. Until green, the phrase 'live Oracle connector' is banned from customer-facing language (senior rec 12). | Discovery lists PPIQ_SRC tables for both profiles in the UI; dated screenshot; zero red banners on the connections walk. | 0.5 | NEW 16-Jul (defect #1)
M1-20 | M1 | M1-P1 Golden Chain | G1 Import | GOLDEN EVIDENCE CHAIN part 1: execute Import Registration Runsheet A-E into ppiq_presentation | Critical | execution | Pipeline | The chain the demo IS (senior rec 6): fresh import batch -> staging -> mapping -> canonical rows -> genealogy, executed live against the fleet sources INTO the presentation DB on top of the restored base. Record every batch ID. Taxonomy-first: definitions views import before facts (absorbs old M1-08 re-import). | Batch IDs recorded per phase; staging/canonical counts pasted; genealogy walk heat->slab->coil resolves from THIS batch's rows; certifier S02/S03/S06 flip green. | 6 | REWRITE v22 M1-08 (4h) + runsheet
M1-21 | M1 | M1-P1 Golden Chain | G3 Engine | GOLDEN EVIDENCE CHAIN part 2: fresh governed run -> 9.3x signal + 1.0x null, linked end-to-end | Critical | execution | Engine | Senior recs 7+16: historical findings prove nothing about this import. Run the governed learning job over the imported window; the money finding must carry current batch ID, run ID, window, population, effect, q-value, and reject the SCRATCH null control at ~1.0x. Customer wording fixed: 'engine recovered a planted validation signal and rejected a null control - validates the method; ROI is what the pilot measures.' | results_v2 rows reference the NEW run id; SUPERHEAT->CRACK_LONG ~9.3x with q<0.01; SCRATCH ~1.0x; evidence record renders in HMI; wording in deck matches. | 3 | NEW 16-Jul (senior recs 6,7,16)
M1-01 | M1 | M1-P1 Golden Chain | G2 Assistant | GOLDEN EVIDENCE CHAIN part 3: assistant cites the imported corpus | Critical | validation | Assistant | Infrastructure exists (canon.assistant_chunk, reindex endpoint); what remains is PROOF on the imported plant: reindex, then the grounded-answer walk. Chain terminus: a cited answer about data the customer watched arrive. | POST /api/assistant/reindex -> 200, chunkCount>=20; 'which source tables are registered?' -> isRefusal=false with >=1 citation resolving in UI; predictive question still refuses. | 3 | REWRITE v22 M1-01 (10h; build done, proof remains)
M1-03 | M1 | M1-P1 Golden Chain | G1 Import | Taxonomy-first proven through the chain (definitions arrive by DB-link with provenance) | Very important | validation | Pipeline | Clarified Rule 2 stands: defect/parameter taxonomy imported from the source taxonomy views (v_parameter_definitions 26 rows, v_defect_definitions 20, CASTER 4, HSM 7), never hand-inserted. Verified as part of M1-20 Phase A with explicit counts. | defect_catalogs/parameter_definitions gain rows with connector source_system; counts match the four source views exactly. | 2 | REWRITE v22 M1-03 (3h)
M1-09 | M1 | M1-P1 Golden Chain | G3 Engine | Finding read hygiene: latest-run dedup view + odds ratio + population surfaced | Very important | enhancement | Engine | results_v2 shows duplicate rows across runs; the engineer will notice. Latest-run-per-job read view (dedup) + OR + population in the finding payload so the fresh 9.3x displays cleanly. | Finding list shows one row per feature/outcome (latest run); the fresh finding displays OR with q-value and population. | 2 | CARRIED v22 M1-09
M1-22 | M1 | M1-P1 Golden Chain | G12 UX | Step-13 Suggestion 401: map the route or fence the page for the demo | Critical | defect fix | Frontend | Red 'SUGGESTION RUNTIME NOT REACHABLE: 401 UNAUTHORIZED' banner captured in screenshot - almost certainly an unmapped route in the deny-by-default access matrix (same class as the M1-05-era POST 403). Fix properly; if not green by Day 3 end, hide from nav - no red banners in the room. | Page loads clean with a real recommendation path OR page absent from nav; full walk shows zero error banners. | 2 | NEW 16-Jul (defect #2)
M1-23 | M1 | M1-P2 Verify & Rehearse | G12 UX | Command Dashboard KPI wiring: Quality events + Risk read real values | Very important | defect fix | Frontend | Materials KPI reads 40,148 but Quality events and Risk show '-' against 51,691 events - a read-model/key mismatch, screenshot-evidenced. Cosmetic but on the step-7 centerpiece. | Both KPIs display numbers matching direct SQL counts on ppiq_presentation. | 2 | NEW 16-Jul (defect #3)
M1-11 | M1 | M1-P2 Verify & Rehearse | G16 Demo | Evidence-graded browser certification: 15-step walk + 12 workspaces to [P] grade | Critical | validation | All | Senior recs 8+9: workspaces are [D]+[B] until a browser proves them. One consolidated pass (absorbs old M1-02 jobs-monitor check): all 15 steps + all 12 workspaces graded [P]/[B]/[T]/[D]/[X] - rendering, drag, resize, min/max, filtering, click-to-filter, layout save, reload persistence. Every FAIL becomes a numbered bug BEFORE rehearsal. | Graded checklist committed under docs/ with dated screenshots; no [X] on the demo path; each [D] has a spoken sentence. | 4 | REWRITE v22 M1-11+M1-02 (6h)
M1-24 | M1 | M1-P2 Verify & Rehearse | G4 Quality | Review the parallel-session code: InteractiveWorkspacePage + 20:15 pack + journey-professional.css | Very important | review | Frontend | Unreviewed code sits on the demo path: the workspace page (origin unknown to this session), five rewritten surfaces, and a 496-line global stylesheet imported first. Read the diff, browser-verify the restyle on every demo screen, fix Sev-1s only. | Review notes committed; global CSS verified on all demo screens; Sev-1 findings fixed or reverted. | 1 | NEW 16-Jul (defect #8)
M1-25 | M1 | M1-P2 Verify & Rehearse | G4 Quality | Gate hygiene: delete stale JourneyRail.test.tsx after rail browser check | Nice to have | cleanup | Tests | Old M1-17 test superseded by the certification suite; red for structural reasons (labels wrapped in nested spans). Verify the rail visually, then delete the stale test - never loosen a matcher to force green. | Rail visually correct; stale test deleted; full vitest suite green. | 0.5 | NEW 16-Jul (defect #4)
M1-26 | M1 | M1-P2 Verify & Rehearse | G4 Quality | Certifier v0.2: S06 offender detail via information_schema; S08 pattern fixed | Nice to have | tooling | Tooling | The go/no-go instrument has two self-defects: S06 detail query guesses a nonexistent column; S08 pattern misses the analysis-job storage (likely job_definitions discriminator). Fix both so every red row names real evidence. | Certifier report contains zero SQL errors; S08 row cites real storage; re-run archived. | 1 | NEW 16-Jul (defect #7)
M1-12 | M1 | M1-P2 Verify & Rehearse | G0 Runtime | Continuity: fleet assets committed durably (FLEET_RELATIONS + source SQLs + registry proofs) | Critical | governance | Docs | The repo cleanup deleted ppiq-fleet-3months/ and FLEET_RELATIONS.md from the tree - the planted-relations ground truth existed only in session dumps until rescued. Commit FLEET_RELATIONS.md into docs/emulation/, archive the six source SQLs off-laptop, paste registry truth queries. | git ls-files shows docs/emulation/FLEET_RELATIONS.md; archive location recorded; registry query outputs pasted. | 1 | REWRITE v22 M1-12 (0.5h; scope grew after deletion)
M1-06 | M1 | M1-P2 Verify & Rehearse | G12 UX | Alerting proven live: two rules via UI-4 + evaluation writes the plant data log | Very important | validation | Frontend | AlertingPage is built and test-covered ([B]); alert_rules=0. Create two rules in the UI (e.g. thermal superheat > 36), run evaluation, watch rigged high-superheat rows log. | Rules visible in UI; evaluation writes plant_data_log rows>0; alert list renders them; graded [P]. | 1.5 | REWRITE v22 M1-06 (6h; UI done, proof remains)
M1-05 | M1 | M1-P2 Verify & Rehearse | G3 Engine | Supervisor step-14 honest state: verify the EXISTING page/endpoints, then render-or-script decision | Very important | validation | Engine | Senior rec 11 correction adopted: SupervisorReportPage exists in-tree with certification tests; ml_knowledge_base_items table exists (0 rows). Verify what renders against live data. If a real report row is one honest step away, take it; otherwise the scripted sentence stands. NO fabricated report content. | Either: page renders one real report row in the walk; or: documented scripted sentence + page graded [B] honestly. Decision recorded. | 3 | REWRITE v22 M1-05 (4h; senior rec 11)
M1-14 | M1 | M1-P2 Verify & Rehearse | G16 Demo | Dress rehearsal x2: full 15-step journey on ppiq_presentation (:5063), timed, with contingency sheet | Critical | execution | All | The exact meeting script twice end-to-end on the presentation profile: golden chain narration, one live dashboard build, the framing sentence, the 9.3x wording, fallback notes per step (source-down / API-down). | Two clean timed runs; contingency sheet exists; certifier run archived same day (~12-13/16 honest greens expected); no code changes after. | 3 | REWRITE v22 M1-14 (3h)
M1-15 | M1 | M1-P2 Verify & Rehearse | G6 Docs | Website + deck updated to the PROVEN story with evidence-linked claims | Critical | content | Website | Senior recs 15+16: every commercial claim names its evidence (batch ID, run ID, screenshot, cert report). Money slide uses the fresh chain finding with the validated-method wording. Workspace screenshots from the [P]-graded pass. Honesty-lint stays green. | Deck walk matches rehearsal exactly; each claim has a named evidence artifact; honesty-lint green; website carries rules + discovery. | 4 | REWRITE v22 M1-15 (4h)
M2-01 | M2 | M2-P1 | G3 Engine | Supervisor engine (step-14 keystone): jobs improve each other + weekly deep revision | Critical | new feature | Engine | Full implementation with guardrails: may tune job configs/feature windows/thresholds; must NEVER weaken readiness gates, refusal logic or evidence; every change logged with justification. Builds on the M1-05 verified v0 state. | After two supervised cycles, at least one job config adjusted with logged justification and measurably improved metric; gates untouched. | 16 | CARRIED v22 M2-01
M2-02 | M2 | M2-P1 | G2 Assistant | Real LLM binding behind IAssistantModel (on-prem Ollama + optional hosted) | Critical | new feature | Assistant | Swap-in implementations beside ExtractiveAssistantModel; config-selected per install; answers remain retrieval-grounded + cited; refusal-first preserved. | Same eval set answered by both models; citations still resolve; predictive questions still refuse; latency budget documented. | 10 | CARRIED v22 M2-02
M2-03 | M2 | M2-P1 | G0 Runtime | Bounded-parallelism job executor (100+ jobs) | Critical | new feature | Backend | Channel<JobRequest> + N consumers; per-class pools (import/analysis/ML); statement timeouts + per-class work_mem; NOTIFY wakeups; job telemetry. | 100 defined jobs across classes complete a full cycle with bounded drift; no pool exhaustion; telemetry populated. | 12 | CARRIED v22 M2-03
M2-04 | M2 | M2-P1 | G3 Engine | Statistics method registry: Spearman, chi-square, ANOVA/Mann-Whitney + Surface-3 picker | Critical | new feature | Engine | Registry of methods with applicability rules; Surface-3 lets the user pick; all results keep the evidence contract. | Each method produces a verified result on the rigged set (chi-square finds a planted categorical driver; Spearman survives monotone). | 10 | CARRIED v22 M2-04
M2-05 | M2 | M2-P1 | G10 Surface-1 | Step-4 full no-code data preparation (per-view Loading jobs + prep/load unification) | Critical | new feature | Frontend | Productize the demo path: visual field-map editor, filters/linking/grouping, SchemaView->MappingDefinition relationship decided, per-view jobs. | A non-developer maps a NEW source to canonical entirely in the HMI incl. schedule; steps 4-6 clickable start to finish. | 12 | CARRIED v22 M2-05
M2-06 | M2 | M2-P1 | G12 UX | 4th UI complete: routing-deviation + chemistry-range rules, email/webhook delivery | Critical | new feature | Frontend | Extend v0: rule types (threshold / routing deviation vs genealogy / chemistry range vs expected_min_max), delivery channels, ack workflow. | Each rule type fires on a crafted case; email+webhook delivered; ack recorded. | 12 | CARRIED v22 M2-06
M2-16 | M2 | M2-P1 | G12 UX | Interactive Workspace Doctrine epic P1: S5 components + S6 builder entry + S4/S7 gap fixes | Critical | new feature | Frontend | Amendment-7 conformance slice: conditional-format tables, list component, date-time-range filter (S5); re-mount Add-widget builder on workspace pages (S6); close every S4 min/max and S7 drag/persistence gap the M1-11 grading found; real heatmap widget row (config proven by Widget Drift). | All 12 workspaces graded [P] on every doctrine standard; a user adds a widget through the builder on a workspace page. | 24 | NEW 16-Jul (doctrine gap matrix ~70h, P1 slice)
M2-17 | M2 | M2-P1 | G4 Quality | Amendment 7 committed + interactiveWorkspaceContract architecture gate installed | Critical | governance | Tests | The doctrine document into docs/doctrine/ on main; the gate per its section 5: frozen legacy allowlist, ratchet semantics, widget-query-contract enforcement. A doctrine without a gate is a wish. | Gate red on an injected non-conforming page, green on main; allowlist snapshot committed; doctrine in git log. | 6 | NEW 16-Jul (Amendment 7)
M2-07 | M2 | M2-P2 | G1 Import | Range validation on ingest (expected_min/max) + time-series observation support | Very important | enhancement | Pipeline | Validate observations against parameter_definitions ranges (typed warning, not silent); prove multi-reading-per-unit series through the pipeline. | Out-of-range reading produces a visible data-quality issue; 10-readings/heat series imports+projects+correlates. | 5 | CARRIED v22 M2-07
M2-08 | M2 | M2-P2 | G0 Runtime | Scale foundations: partitions (monthly+BRIN), incremental feature refresh, PgBouncer, restore drill | Critical | infrastructure | Backend | Pre-pilot infra musts from sizing model v1. | Medium-profile synthetic load (7.5M obs) refreshes incrementally in bounded time; restore drill signed off. | 10 | CARRIED v22 M2-08
M2-09 | M2 | M2-P2 | G14 Security | Roles/users vs journey: role catalog, named policies, MFA verify, SCIM finish-or-fence | Critical | security | Backend | Replace '?? viewer' fallback + literals with a role catalog; verify MFA enrolment; finish or fence SSO/SCIM; user flows match journey. | Role matrix documented+tested per surface; MFA walk recorded; SCIM passing or disabled behind a flag. | 8 | CARRIED v22 M2-09
M2-10 | M2 | M2-P2 | G14 Security | Licensing production-grade: tier->feature matrix, production Ed25519 keypair, gated-endpoint tests | Critical | security | Backend | Document tier -> LicenseFeature codes; rotate off the dev keypair (Option 3); test one gated endpoint per tier incl. ML/assistant gates. | Matrix published; dev token rejected in prod mode; per-tier tests green. | 5 | CARRIED v22 M2-10
M2-11 | M2 | M2-P2 | G15 Governance | Close out-of-band paths: staging-reset endpoint, purge audit, source_system allow-list, retention, deletion UX | Very important | governance | Backend | Everything an auditor flagged: admin endpoint replaces psql resets; projector accepts only registered connector source_systems; retention job visible. | No documented workflow requires psql; allow-list test rejects a foreign source_system; retention job in monitor. | 5 | CARRIED v22 M2-11
M2-18 | M2 | M2-P2 | G16 Demo | One-command demo environment: Rebuild-PresentationDb.ps1 committed under scripts/demo/ | Very important | tooling | Tooling | Senior rec 4: the presentation DB is a reproducible artifact, never truth. Consolidate this week's proven scripts (clone -> restore -> Rule-1 reapply -> provenance neutralize -> dashboards+widgets) into one committed, idempotent rebuild command with the snapshot as input fixture. | From zero: one command rebuilds ppiq_presentation byte-equivalent in counts; README in scripts/demo/; snapshot location recorded. | 4 | NEW 16-Jul (senior rec 4)
M2-19 | M2 | M2-P2 | G15 Governance | ppiq_acceptance_empty: third database + profile + Rule-2 acceptance run | Very important | governance | Infra | Senior rec 3: 'starts empty' is untestable without a permanently-empty instance. Create DB + profile; the Rule-2 acceptance (fresh install shows zero content everywhere) runs against it in CI cadence. | Profile works; acceptance walk on the empty DB shows zero demo content on every surface; documented in Identity & Topology. | 1 | NEW 16-Jul (senior rec 3)
M2-20 | M2 | M2-P3 | G16 Demo | Eradication epic: every Rule-1-violating installer/endpoint/page out of the product | Critical | cleanup | All | Consolidates old M1-07 residue + the standing list: TwoStageImportEndpoints.cs, CustomerDemoReportEndpoints.cs, /demo* routes, installer scripts 110/111/140/142/665 + seed/ violations on fresh install, 4 unrouted pages, drifted duplicate scanners, MaskSecrets default. | Fresh install on ppiq_acceptance_empty is 100% generic; grep gates clean; endpoints absent from Swagger. | 8 | REWRITE v22 M1-07 residue + eradication list
M2-21 | M2 | M2-P3 | G4 Quality | Journey certification suite completion: backend contracts hardened, MSW fixture layer, Playwright specs green, skippables mandatory | Very important | tests | Tests | The adopted framework's test expansion, P1 slice: the 3 backend contract suites to green against real contracts, a real MSW fixture layer, the 2 journey Playwright specs passing in CI, SkippableFacts converted (live-Postgres path in CI), test isolation via PPIQ_TEST_PG_CONNSTRING. | test:journey:* all green in CI; skipped count = 0 for critical suites; Phase3GoldenThread isolated from dev DB. | 12 | NEW 15-Jul (certification framework P1)
M2-13 | M2 | M2-P3 | G4 Quality | CI truth gates + test debt: same-table CREATE gate, seed NOT-NULL gate, register/const/binding tests | Very important | tests | Tests | The two deferred gates plus uncovered seams (register upsert, const: branch, execute query-binding, AddAssistant guard + factory tests). | All gates red on injected violations, green on main; new tests in CI. | 6 | CARRIED v22 M2-13
M2-14 | M2 | M2-P3 | G12 UX | Journey UX hardening: mapping surfaces renamed by outcome, i18n/RTL verified, widget lite-SQL click-tools | Very important | enhancement | Frontend | 'Prepare views' vs 'Load to plant data' naming; real Arabic RTL pass; group-by/filter click-builders in the widget wizard. (Progress guide DONE as M1-17 - clause removed.) | New-user walk without verbal guidance reaches step 10; RTL screenshots approved. | 5 | REWRITE v22 M2-14 (6h; M1-17 clause done)
M2-15 | M2 | M2-P3 | G14 Security | Ops/security residue: secrets story, mail/Spamhaus remediation, backend mojibake, phase-dir renames | Nice to have | cleanup | Ops | Src-tree mojibake DONE 16-Jul (gate green); remaining: 6 backend .cs files, Phase8/9 dir renames, SPF/DKIM/PTR + relay 587, secrets manager pattern. | Deliverability test passes; noMojibake backend list empty; grep clean on phase tokens; no plaintext secrets. | 3 | REWRITE v22 M2-15 (4h; src mojibake done)
M2-22 | M2 | M2-P3 | G12 UX | UI debt burn-down wave 1: ratchet 161/112 -> demo-path zero | Very important | cleanup | Frontend | Frozen debt under the monotonic ratchet: AdminDbConfigurationTab (18), AnalysisJobConfigPage (18+25), widget-builder (20), Alerting (10), ImportPrep (9+13) converted to Standard* primitives; baseline lowered accordingly. | Ratchet baseline reduced by >=100 D1; demo-path pages at 0 raw controls; suite green. | 10 | NEW 15-Jul (conformance scan)
M2-23 | M2 | M2-P3 | G15 Governance | Purge the 5 provenance-NULL units in ppiq_app + root-cause note | Nice to have | cleanup | Data | The dev DB's only Rule-2 breach (certifier catch): five units with NULL source_system/source_record_id, created outside the import path. Identify origin, delete, note the seam. | Certifier S06 nullProv=0 on ppiq_app; origin documented. | 0.5 | NEW 16-Jul (defect #5)
M2-24 | M2 | M2-P3 | G10 Surface-1 | Register page final step: explicit job binding (from-mapping + schedule-now) | Nice to have | enhancement | Frontend | Small remainder: wire the page's final step to import-jobs/from-mapping + schedule-now (register already schedules implicitly). | Clicking finish shows the scheduled job and next-run time. | 1 | MOVED from v22 M1-16 (senior rec 17: not demo-critical)
M3-01 | M3 | M3-P1 | G5 Feedback | Customer-comment intake from the meeting: log, triage, re-prioritize M3 | Critical | governance | Docs | Every comment becomes a numbered row with severity and owner; M3 scope finalized within 48h of the meeting. | Comment log committed; M3 plan v1 published. | 2 | CARRIED v22 M3-01
M3-02 | M3 | M3-P1 | G10 Surface-1 | Visual mapper polish + mapping templates library | Very important | new feature | Frontend | Drag-drop field mapping, per-industry starter templates shipped as emulation fixtures (never code branches). | A new industry source mapped from a template in <10 min by a non-developer. | 8 | CARRIED v22 M3-02
M3-03 | M3 | M3-P1 | G3 Engine | 3rd UI drag-and-drop analysis toolbox | Very important | new feature | Frontend | Draggable method/parameter components over the M2 method registry; saved analyses shareable; conforms to Amendment 7 workspace primitives. | User composes a two-method analysis by drag-drop; result matches scripted equivalent; doctrine gate green. | 10 | REWRITE v22 M3-03 (doctrine ref added)
M3-04 | M3 | M3-P1 | G0 Runtime | Large-profile scale: analytics read replica, partition automation, load test at 60M obs/yr | Very important | infrastructure | Backend | Per sizing model v1 Large row; automated partition creation; correlation on replica. | Synthetic Large load meets documented latency budgets. | 10 | CARRIED v22 M3-04
M3-05 | M3 | M3-P1 | G1 Import | Connector expansion per customer landscape (files/API/historians as required) | Very important | new feature | Connectors | Scoped from customer comments: CSV/file drop, REST, OPC-UA historian - each as a new IDataSourceReader family, zero core changes. | New connector imports through the unchanged pipeline. | 8 | CARRIED v22 M3-05
M3-06 | M3 | M3-P1 | G13 Deploy | HA + multi-plant deployment hardening | Nice to have | infrastructure | Deploy | Failover story, per-plant isolation review, installer runbook (sysadmin auto-provision, Customer Admin manual per Golden Rule). | Documented install executes on a clean VM end-to-end. | 8 | CARRIED v22 M3-06

## Phase Summary
PHASE SUMMARY - PPIQ Backlog v23 (formulas over the Backlog sheet)
Milestone | Phase | Tasks | Hours | Critical
M1 | M1-P1 Golden Chain | 8 | 19.5 | 6
M1 | M1-P2 Verify & Rehearse | 10 | 21 | 4
M2 | M2-P1 | 8 | 102 | 8
M2 | M2-P2 | 7 | 38 | 3
M2 | M2-P3 | 8 | 45.5 | 1
M3 | M3-P1 | 6 | 46 | 1
M1 TOTAL |  | 18 | 40.5 | 10
M2 TOTAL |  | 23 | 185.5 | 12
M3 TOTAL |  | 6 | 46 | 1
GRAND TOTAL |  | 47 | 272 | 23

## Removed (Done-Invalid)
REMOVED FROM v22 - traceability (nothing silently deleted)
v22 ID | Disposition | Task | Evidence / destination
M1-04 | DONE | Step-4 mapping UI authors MappingDefinition through the HMI | Proven in walk + certification tests (failedRows contract fixed 16-Jul). Evidence: walk doc [V] rows; suite green.
M1-10 | DONE | Production error shape (no stack traces to clients) | Walk P6/P10 verify the {title,errorCode,traceId} shape live [V].
M1-13 | DONE | ppiq.ps1 API readiness poll | Walk P2 cites the M1-13 line as live [V].
M1-17 | DONE | Journey progress rail (step X of 15) | Rail live in 16-Jul screenshots; certification test green; stale old test removal = new M1-25.
M1-07 | DONE (frontend) | Arch-B frontend removal | Two-Stage ghost card excised 15-Jul (SHA-confirmed). Backend residue folded into M2-20 eradication epic.
M1-02 | MERGED | Jobs Monitor four job types honest | Merged into M1-11 evidence-graded certification (one browser pass, one checklist).
M1-08 | SUPERSEDED | Purge + re-import into ppiq_app | Purge done 14-Jul. Re-import superseded by M1-20 golden chain into ppiq_presentation (strategy: senior recs 2,3).
M1-16 | MOVED | Register page explicit job binding | Not customer-critical (senior rec 17). Now M2-24.