## Cover
PlantProcess IQ - 2-Week Launch Backlog (Iteration 2)
Tightened to guarantee the 6 launch goals: presentable scorecard, a more-than-acceptable app, working mainstream workflow, a no-surprise demo, a shiny UI, and a server deploy that actually updates on push.
WHAT CHANGED IN THIS ITERATION
- +5 NEW tasks (purple flag): P1-T01 stabilize live deploy + rollback (day 1); P2-T12 app flagship 'wow' visual pass; P3-T18 demo performance / no-hang; P5-T29 guided golden-path demo + presenter script; P6-T36 presentation-day go/no-go + offline fallback.
- Existing tasks enriched: version/build stamps, zero-console-errors, keyboard/focus, prefers-reduced-motion, push->live verification, harder acceptance everywhere.
- Sequencing gap fixed: the live stack is stabilized on DAY 1 (P1-T01) so the team lead sees it on the server in Week 1 and every phase can deploy; the permanent convergence + Jenkins rebuild stay in Week 2 (P4-T20/T21).
- 36 tasks / 6 phases; each phase 56-65h (within 45-65).
SCORE TRAJECTORY
Milestone | Overall /84 | Band
Doctrine published (stale s21) | 46 | CRITICAL
Verified now (Scorecard v2) | 66 | NEEDS WORK
After Phase 1-3 (team lead) | ~72 | SOLID
After Phase 4-6 (customer) | ~77 | SOLID
Doctrine ceiling | 84 | SOLID
HOW THE 6 PHASES HIT THE 6 GOALS
Phase | Focus | When | Deploy milestone (something new, nothing broken) | Primary score lift
Phase 1 | Stabilize live + structural honesty + test reality | Week 1 - team-lead | Server shows latest build (stamped) + rollback ready; repo no longer shamming; tests run & gate locally | Developer 62->~71; unblocks deploy-each-phase (NEW P1-T01)
Phase 2 | UI standardization + flagship visual uplift | Week 1 - team-lead | Every page same standard look, no dead buttons, no failed loads, 3 flagship screens look impressive | Eng Customer UI/UX 64->~78; app starts looking shiny (NEW P2-T12)
Phase 3 | Intelligence, value & demo performance | Week 1 - team-lead | Bounded EUR value, honest correlations + citations, snappy no-hang endpoints | CEO value 56->~70 + trust 80->85; AI/ML ->~80 (NEW P3-T18)
Phase 4 | Deploy convergence & pipeline rebuild | Week 2 - customer | A git push genuinely updates the live demo (stamp match); tests gate the deploy | Gate G9/G10; root cause of FE/BE-not-updating SOLVED [MANDATED]
Phase 5 | Demo-through-HMI & guided narrative | Week 2 - customer | Demo built from empty through the product; nothing hardcoded; on-rails guided tour | Gate G3/G7; Wave C 55->~85; no-surprise demo (NEW P5-T29)
Phase 6 | Website, evaluation surface, a11y & presentation readiness | Week 2 - customer | Shiny site + honest customer evaluation; AA light/RTL; rehearsed go/no-go + rollback | Brand 72->~80; CEO cross-device 56->~70; Gate G8/G14 (NEW P6-T36)

## Task List
Task ID | Task Name | Phase | Track | Module | Submodule | Severity | Description (what to build) | Acceptance Criteria (hard tests) | Task Type | Effort (h) | Score Impact / Boosts
PHASE 1 - Stabilize live + structural honesty + test reality ¦ Week 1 - team-lead ¦ ends deployable: Server shows latest build (stamped) + rollback ready; repo no longer shamming; tests run & gate locally
P1-T01 | [NEW] Stabilize the live server deploy NOW + rollback safety net | Phase 1 | Deploy | Infrastructure | Live-stack stabilization | Critical | Before any score work, make the SERVER show the latest build and make every deploy reversible - WITHOUT yet rebuilding the pipeline. Manually rebuild the four app images from freshly pulled code and recreate the LIVE ppiq-app-* containers IN PLACE (compose project plantprocessiq, Infrastructure/deploy/docker-compose.demo.yml, `--no-deps` so ppiq-postgres + its volume are untouched), reusing the working config baked into the running containers (valid 64-char SigningKey, ConnectionStrings__PlantProcessDb, Caddy wiring). Tag the current known-good images (plantprocess-api:known-good-YYYYMMDD etc.) and write ONE rollback script deploy/rollback.sh that re-points the live containers to the last known-good tag in <2 min. Delete the crash-looping orphan plantprocess-* containers. Add a visible build/version stamp (commit short-sha) to the app footer + an /version endpoint. THIS is the deliberate minimal deploy task pulled into Week 1 to cover the sequencing gap and to make 'deploy at the end of every phase' actually possible; the FULL compose convergence (P4-T20) and Jenkins rebuild (P4-T21) stay in Week 2. | Live app/api/website hosts serve the latest commit, verified by a build/version stamp == `git rev-parse --short HEAD`; RestartCount on every ppiq-app-* is 0 and stays 0 for 10 min; ZERO orphan plantprocess-* containers remain; deploy/rollback.sh restores the previous known-good build in <2 min (rehearsed once and timed); ppiq-postgres volume id + row counts unchanged. | Bug fix | 8 | Goal 4 & 6; unblocks deploy-each-phase; Gate G9
P1-T02 | Inline re-export shims & rename runtime-suffix modules | Phase 1 | Hardening | FrontEnd | App shell / module structure | Critical | The frontend closes refactors by renaming, not decomposing: App.tsx is a 2-line `export * from './App.implementation'` re-exporting AppRoutes.generated; StandardTable.tsx re-exports StandardTable.implementation; 48 of 280 src .ts/.tsx files are <=6-line shims and 30 carry .implementation/.runtime/.generated/.view/.model suffixes (~15k lines). For EACH shim: delete it, rename the target to the honest name, update all imports. Where a >1000-line file bundles many concerns (AdminDbConfigurationTab.runtime.generated.tsx 1132, MaterialAnalyticsPages.runtime.generated.tsx 1107), split it into real feature sub-modules by responsibility. Additionally: remove dead/duplicate exports flagged by the TS compiler and ensure each module has a single clear responsibility. No production module name may end in .implementation/.runtime/.generated and no file may be a pure passthrough. | grep for `export * from .*(implementation¦runtime¦generated)` in src returns ZERO; no src file <=6 lines except explicit index barrels; `npm run build` + `tsc -b --noEmit` clean with ZERO warnings; `npm run test` (vitest) green; a NEW guard scripts/validate-no-passthrough-shims.mjs fails CI if any <=6-line re-export reappears; `npx ts-prune` reports no new unused exports. | Refactor | 13 | Developer (structure 50->~70); Gate G10
P1-T03 | Prune dead weight & relocate one-off tooling out of the product tree | Phase 1 | Hardening | Documentation | Repo hygiene | very important | 16,088 lines across tools/_archive (31 files), deploy/_legacy_consolidated_20260604_115150 (8 files) and .archived files ship in the repo; 612 files / 156,827 lines (~30% of the tree) are one-off validators/closure docs under tools/+docs/+scripts/ dwarfing the product. Delete _archive/_legacy/.archived (recoverable from git history); consolidate genuinely-reused validators into one ci/validators/ folder; delete per-pack/per-phase one-shot scripts. Add the archive paths to .gitignore and document the clone-size before/after. | _archive/_legacy*/.archived absent from the working tree; repo file+line count drops measurably (recorded in docs/cleanup-report.md with before/after); `git clean -nffdx` shows nothing unexpected; `git status` clean; build + ALL tests still green (nothing referenced the deletions). | Refactor | 6 | Developer (structure); Gate G10
P1-T04 | Self-provisioning test database so `dotnet test` runs green | Phase 1 | Hardening | Testing | Integration test harness | Critical | The 117 backend test projects include integration suites (Infrastructure.IntegrationTests, Api.IntegrationTests) needing live Postgres via PPIQ_TEST_CONNECTION_STRING; today they error when unset (the 62-failure symptom). Make the run self-provisioning: a fixture/collection that (a) reads PPIQ_TEST_CONNECTION_STRING or falls back to a throwaway plantprocess_test_db, (b) creates the DB if absent, (c) applies Backend/database/scripts/*.sql in order, (d) applies Backend/tests/_fixtures/seed_test_auth.sql + test-seeds/900_clean_test_auth_seed.sql, (e) tears down/resets between runs. Connect as a NON-superuser role so FORCE-RLS tests are valid. Make the run reproducible (a single `dotnet test` command + a documented one-time createdb). | `dotnet test PlantProcessIQ.sln --nologo` on a clean machine with only Postgres up passes ALL projects (0 failed, 0 errored, 0 skipped beyond the documented 1); RlsTenantIsolationTests refuses to run under superuser and passes under the app role; a second consecutive run is also green (idempotent reset); documented in Backend/tests/README.md. | Test | 11 | Developer (test 52->~72); Gate G10, G4
P1-T05 | Promote the golden-dataset FDR validation to an executable gated test | Phase 1 | AI+ML | Testing | Statistical discipline | very important | The Benjamini-Hochberg FDR golden-dataset evidence lives only as SQL rows (phase5_golden_dataset_evidence, GOLD-003) - asserted, not EXECUTED. Add a real test that builds a synthetic dataset with k planted true signals + m planted noise pairs, runs the ACTUAL Spearman + normalized MI + Lasso + VIF pipeline (ManagedStatisticalComputeEngine / AdvancedCorrelationComputeService) under Benjamini-Hochberg q<=0.10, and asserts: 100% of planted signals recovered (power), 100% of noise rejected (no false positives), and determinism (same seed -> identical ranking + identical q-values). | The test recovers all planted signals and rejects all planted noise at q<=0.10, is byte-identical-deterministic across two runs, and runs inside `dotnet test`; a mutation that removes the FDR correction makes the test FAIL (proving the gate bites). | Test | 8 | Eng Customer (AI/ML); CEO (trust); Gate G4
P1-T06 | Fix stale tenant-GUC reset (multi-tenant isolation hardening) | Phase 1 | Hardening | Security | RLS / tenancy | Critical | TenantGucConnectionInterceptor.ApplyTenantGuc[Async] EARLY-RETURNS when TryGetTenantId is false, so a pooled connection that served tenant X keeps app.current_tenant=X when reused by a no-tenant context (e.g. a worker), risking cross-tenant reads under RLS. Change it to ALWAYS set the GUC on connection open: to the resolved tenant when present, and to an explicit empty value (`SELECT set_config('app.current_tenant','',false)`) when absent, so a missing tenant FAILS CLOSED (zero rows) on every connection and never inherits a prior tenant. Audit all worker/job/hosted-service paths that open pooled connections for the same assumption. | A new integration test opens a connection as tenant A, returns it to the pool, then runs a no-tenant op on a reused connection and asserts current_setting('app.current_tenant',true) is empty AND a tenant-scoped query returns 0 rows; an audit note lists every pooled-connection entry point and confirms each is safe; all existing RLS tests stay green. | Bug fix | 8 | CEO (access/trust); Developer (stability); Gate G5
P1-T07 | Phase 1 acceptance: local full-validation gate + regression sweep | Phase 1 | Hardening | Testing | Phase gate | very important | Author ONE repo-local validation entrypoint (consolidate tools/ci/run-local-full-validation) that runs FAIL-FAST in order: `npm run lint`, `npm run test` (vitest), `dotnet test PlantProcessIQ.sln`, the no-passthrough-shim guard, and a build of both FE apps. Wire it as a git pre-push hook (husky or core.hooksPath). This is the LOCAL stand-in for the blocking CI rebuilt in Phase 4, and it is what makes the Phase-1 server deploy (via P1-T01) safe. | The single command exits non-zero if ANY of lint/vitest/dotnet test/shim-guard/build fail and zero when all pass, on a clean checkout; a deliberately broken test forces non-zero; documented in CONTRIBUTING.md; after this phase a deploy via P1-T01 shows the new build with the version stamp and nothing broken. | Test | 9 | Developer (test/G10); whole-repo
PHASE 2 - UI standardization + flagship visual uplift ¦ Week 1 - team-lead ¦ ends deployable: Every page same standard look, no dead buttons, no failed loads, 3 flagship screens look impressive
P2-T08 | Complete the Standard-component rollout (eliminate native controls) | Phase 2 | Hardening | FrontEnd | Design system | Critical | The Standard component system (StandardTable/StandardFields/StandardButton/StandardSelect) is only partially adopted; the CI gate validate:standard-imports is ADVISORY and several admin pages still use native <input>/<select>/<button> (PPIQ-T012 inventory: AdminDbConfigurationTab, AdminImportingDataTab, InteractiveCharts, etc.). Convert EVERY remaining native control across all pages/tabs to the Standard equivalents (brand spec: disabled=0.35 opacity, 8px radius, Inter 14px semibold, focus ring visible). Remove ALL inline `style=` in favour of design tokens. Make validate:standard-imports BLOCKING (remove `¦¦ echo WARN`). | `npm run validate:standard-imports` passes with ZERO exceptions and is a hard gate; tools/ui/audit-ui-instances reports 0 native form controls and 0 inline styles in src/pages and src/components outside Standard wrappers; every interactive control is reachable and operable by keyboard with a visible focus ring; visual-regression updated and green; zero console warnings. | Refactor | 16 | Eng Customer (UI/UX 64->~78); Gate G6; Track 2
P2-T09 | Standardize all action buttons; fix Material Investigation styling | Phase 2 | Hardening | FrontEnd | Material Investigation / buttons | very important | On Material Investigation the search field, Search, Load Investigation, Calculate Risk and PDF Report buttons have mismatched styling (called out explicitly in the brief). Replace with StandardButton variants (primary/secondary/ghost), align spacing+orientation, standard loading/disabled state on submit, and sweep every page so button hierarchy, size, icon placement and wording are consistent. Ensure StandardButton uses isDisabled (not disabled) consistently and shows a spinner while its action is in flight. | A visual-regression spec covering Material Investigation + 6 representative pages passes; a lint rule rejects raw <button> inside src/pages; every primary action shows an in-flight spinner and is disabled while running; review confirms identical primary/secondary treatment across all pages; zero console errors. | Bug fix | 10 | Eng Customer (UI/UX); Gate G6; Track 2
P2-T10 | No-dead-button action matrix (every control does its job) | Phase 2 | Hardening | Testing | Action matrix | Critical | Hardening rule: never press a button that does not do its proper function. Enumerate EVERY interactive control on every page/sub-page/nav (generate the matrix from the route table so new pages are auto-required) and for each assert the REAL effect (min/max, calculation, data load, navigation, save, export) - not just that it renders. Fix any control that no-ops, errors, or silently fails. Cover the nav, tabs, table row actions, and modal actions. | `npm run test:auth-matrix` + a new e2e/action-matrix-full.spec.ts enumerate 100% of page actions and pass by ENUMERATION (every control triggers a verifiable effect); the matrix is route-table-driven; ZERO dead buttons; a deliberately broken handler makes the matrix fail. | Test | 12 | Eng Customer (UI/UX, workflow); Gate G6; Track 2
P2-T11 | Edge states & progress on slow calls (loading / empty / error) | Phase 2 | Hardening | FrontEnd | Edge states | very important | The brief forbids 'view could not load' surprises and requires a loading icon with progress on long calls. Enumerate loading/empty/error/partial states for every data-bound widget and page; each must show a Standard skeleton/spinner (with progress for calls >300ms), a crafted empty state (not blank), and a TYPED, actionable error with retry (never a raw stack or silent fail). Confirm aria-busy + interaction-disable during load and that a failed widget never breaks the whole page (error boundary per widget). | An e2e injects latency + a backend outage and asserts EVERY page shows a proper loading-then-error state with working retry and never a broken/blank panel; one widget failing does not blank the page (error boundary); a11y check passes aria-busy; zero unhandled promise rejections in console. | Hardening | 12 | Eng Customer (UI/UX); CEO (perf); Goal 4; Track 2
P2-T12 | [NEW] App flagship visual 'wow' pass (command-center hero + data-viz) | Phase 2 | Hardening | FrontEnd | Visual design / flagship screens | very important | Standardization (P2-T08) makes the app consistent; THIS makes it impressive. Take the 2-3 screens the team-lead/customer will actually see - the main operations dashboard, the Material Investigation/genealogy view, and the Value/ROI dashboard (P3-T14) - and lift them to a true dark-industrial command-center standard: deliberate hierarchy + spacing, polished data-viz (one chart theme: axes, units, gridlines, tooltips, legends), KPI hero tiles with sparklines + trend deltas, crafted empty/zero states (illustration, not blank), and subtle purposeful motion (skeleton->content fade, value count-up, chart enter). Stay in the brand palette; no animation that slows interaction; respect prefers-reduced-motion. | Before/after of the 3 flagship screens reviewed against the brand spec; all charts share one theme verified by a visual-regression spec; every panel has a crafted loading + empty state; motion <=200ms and disabled under prefers-reduced-motion; dashboard interaction stays ~60fps with no jank; zero console errors. | Hardening | 7 | Goal 5 (app shiny); Eng Customer (UI/UX); Brand
P2-T13 | Phase 2 acceptance: visual-regression + responsive multi-breakpoint baseline | Phase 2 | Hardening | Testing | Phase gate | very important | Refresh + expand the visual-regression baseline across the standardized + polished UI, and add a responsive spec at 3 breakpoints (mobile/tablet/desktop). Re-run the full vitest + e2e suite to catch regressions from the standardization and visual sweep. | Visual snapshots stable across the flagship + standardized screens; responsive spec passes at 3 widths with no overflow/overlap; full vitest + chromium e2e green; no regression vs Phase 1; deploy via P1-T01 shows the polished UI on the server with the version stamp. | Test | 8 | Eng Customer (UI/UX); Gate G6
PHASE 3 - Intelligence, value & demo performance ¦ Week 1 - team-lead ¦ ends deployable: Bounded EUR value, honest correlations + citations, snappy no-hang endpoints
P3-T14 | Value/ROI executive surface (reproduce the bounded EUR range in-product) | Phase 3 | AI+ML | FrontEnd | Value engine UX | Critical | ValueImpactEngine computes Low/Mid/High with an abstain path (Doctrine 7.5) but it is not surfaced as an exec deliverable. Build a Value/ROI dashboard + a monthly value report (PDF, light theme) that: takes an approved finding, calls the value engine, shows the bounded euro range with drill-through on every input (defect/scrap, ATTRIBUTABLE production-stop minutes, yield loss) and the honest ABSTAIN message when assumptions are missing, plus a payback view vs license cost. Reproduce the 7.5 worked case so the EUR 28k-56k range renders from REAL computation, not a fixture. Surface the provenance handle for every number. | The dashboard renders a bounded range with full input drill-through for a seeded finding; with a missing assumption it shows the ABSTAIN text and NO fabricated number; the PDF matches the brand light theme and prints cleanly; an e2e asserts the rendered Low/Mid/High EXACTLY equals the engine output; every displayed number has a provenance handle (no orphan numbers). | New feature | 14 | CEO (value=price 56->~70, exec UX); Gate G5; North Star
P3-T15 | Widget/dashboard schema-drift root-cause fix; heatmap + interactive filter/sort | Phase 3 | Workflow | FrontEnd | Widgets / dashboards | very important | Two schema-drift hotfixes (scripts 206/207) indicate the dashboard-widget definition schema churned. Reconcile the widget-definition schema ONCE (single source of truth across DB, API DTO and FE types in dashboard-widget-types.ts) and remove the drift. Then verify every chart type is dynamic + interactive with working filter/sort/drill, and that the HEATMAP renders and interacts correctly (explicit brief requirement), including the phase11 heatmap interactions. Ensure filters compose (multiple filters AND correctly) and persist on refresh. | Widget-definition schema validated end-to-end (a contract test fails on any FE/DTO/DB drift, so no future hotfix is needed); an e2e exercises filter + multi-filter + sort + drill on bar/line/heatmap and asserts the data changes correctly; heatmap interaction spec passes; filters survive a page refresh; zero console errors. | Bug fix | 12 | Eng Customer (widgets 68->~78); Gate G3; Track 1
P3-T16 | Strengthen the grounding guard + surface evidence/citations in the assistant UI | Phase 3 | AI+ML | Backend | Grounding / assistant | very important | GroundingService blocks uncited numbers and a 5-phrase forbidden list via NAIVE substring matching - a determined phrasing evades it ('the underlying driver'). Replace substring checks with a tokenized + lemma/regex matcher covering causal/value claim FAMILIES, expand the forbidden set, and add unit cases for evasion phrasings. In AssistantChat render the resolved evidence handles/citations next to every claim so the 'cites every number' North Star is visible and clickable. Keep the provider/model-version drift gate. Ensure a refusal is graceful (explains why) not a crash. | New grounding unit tests block paraphrased causal/value claims and pass the full evasion set; AssistantGroundingEvalGate still passes; the UI shows a clickable citation chip per claim resolving to a finding/job/source; an uncited number NEVER reaches the DOM (e2e); a blocked answer renders a graceful honest message, no console error. | Hardening | 12 | CEO (trust 80->85); Gate G4, G13
P3-T17 | Correlation -> generated-page workflow with honest statistics surfaced | Phase 3 | AI+ML | FrontEnd | Correlation / suggestions | important | Per Track 1 3.2, an inspection job (defect/downtime/KPI over a window) should produce a page of widgets ranking suspected contributors. Wire the correlation UI so a run surfaces, PER contributor: method (Spearman/MI), q-value, confidence interval, effect size, sample size, and population/exclusions (5.4 coverage transparency) - labelled 'suspected contributor', never 'root cause'. Deterministic suggestion cards (MD5-stable) link to their evidence. Add a clear 'how to read this' affordance so a non-statistician trusts it. | Running an inspection job renders a ranked contributor page with q-value/CI/effect-size/population shown; identical inputs produce identical card IDs + order; the forbidden-language lint passes on ALL surfaced copy; an e2e runs a job and asserts the ranked page renders with stats and no overclaiming words. | New feature | 10 | Eng Customer (AI/ML); CEO (trust); Gate G4, G15; Track 1
P3-T18 | [NEW] Demo performance / no-hang latency pass | Phase 3 | Hardening | Backend | Performance / latency budget | very important | The 4-track rule: endpoints don't hang. Profile the hot paths the demo actually uses (dashboard load, widget queries, genealogy walk, correlation job, value computation, investigation search) and enforce a latency budget: per-endpoint SLOs (p95 < 1.5s for reads; anything longer is async + progress), server-side timeouts + cancellation so nothing hangs indefinitely, verify EXPLAIN/index coverage on the demo dataset (scripts 050/511), and confirm materialized views refresh on a sane cadence. Add a load smoke over the demo paths at presentation-like concurrency. | A latency report shows p95 < 1.5s for demo read paths on the seeded dataset; any longer op returns within its timeout with a progress UI (never an indefinite spinner); a load smoke at 10 concurrent users shows no 5xx and no request >5s; the slow-query log is clean for the demo paths. | Hardening | 7 | Goal 4 & 5; Eng Customer; CEO (performance)
P3-T19 | Phase 3 acceptance: golden signals + value abstain + grounding regression | Phase 3 | AI+ML | Testing | Phase gate | very important | Phase-acceptance suite running the golden-dataset recovery (P1-T05), the value-engine abstain/monotonic cases, the grounding evasion set, and the perf budget smoke (P3-T18) together, plus a full regression of vitest + dotnet test. | Golden signals recovered + noise rejected under FDR; value engine abstains on missing inputs and never emits a non-monotonic range; grounding blocks all evasion phrasings; perf smoke passes; full vitest + dotnet test green; deploy via P1-T01 shows the intelligence/value surfaces working on the server. END OF WEEK-1 BLOCK: reds eliminated, internal scorecard ~72. | Test | 10 | Eng Customer (AI/ML); CEO (trust); Gate G4
PHASE 4 - Deploy convergence & pipeline rebuild ¦ Week 2 - customer ¦ ends deployable: A git push genuinely updates the live demo (stamp match); tests gate the deploy
P4-T20 | Fix the deploy root cause: converge to ONE canonical compose Caddy serves | Phase 4 | Deploy | Infrastructure | Compose / Caddy | Critical | (Permanent fix of what P1-T01 stabilized manually.) Git pushes build a parallel plantprocess-* stack (project ppiq-demo, deploy/compose/docker-compose.demo.yml) Caddy never routes to, while the live demo is the ppiq-app-* stack (project plantprocessiq, Infrastructure/deploy/docker-compose.demo.yml). Converge to ONE canonical compose = the live plantprocessiq project: fix the connection key from ConnectionStrings__DefaultConnection to the app's ConnectionStrings__PlantProcessDb; add a 64-char SigningKey + the server-only deploy .env; align the Caddy upstream service+port (image listens :5063 not :8080; service plantprocess-app-web not plantprocess-web); restore the caddy service the on-disk file lost; delete the duplicate deploy/compose/docker-compose.demo.yml; keep ppiq-postgres + its volume untouched (--no-deps). [MANDATED #1] | A single `docker compose -f <canonical> up -d --no-deps` rebuilds + recreates the four app services IN PLACE; Caddy serves the new build at app/api/website hosts (200/401); ZERO orphan plantprocess-* containers; backend RestartCount stable; only ONE docker-compose.demo.yml remains in the repo; Postgres volume id + row counts unchanged. | Bug fix | 14 | CEO (perf); Brand (deploy); Gate G9; Goal 6 [MANDATED]
P4-T21 | Rebuild the Jenkins pipeline (pull->migrate->seed->lint->npm test->dotnet test->build->recreate live) | Phase 4 | Deploy | Infrastructure | CI/CD | Critical | Replace the gate-rich but test-poor Jenkinsfile with the EIGHT-step pipeline: (1) pull origin/main preserving server-only .env/Caddyfile; (2) migrate the app DB + demo-source DBs idempotently with ON_ERROR_STOP=1 (FAIL on SQL error - remove the 'continuing' swallow); (3) run all seeds; (4) lint; (5) `npm run test` (vitest) BLOCKING; (6) `dotnet test PlantProcessIQ.sln` against plantprocess_test_db BLOCKING; (7) build prerequisites; (8) build + recreate the LIVE plantprocessiq stack in place + stamp the build sha. Remove catchError->SUCCESS so e2e can fail the build. Enforces gate G10 'no 85% on a gate'. [MANDATED #2] | A push that breaks a unit test FAILS the pipeline (proven by a deliberate break); a push with a broken migration FAILS at stage 2; a clean push updates the live demo within the pipeline run and the app version stamp == the pushed sha; the pipeline runs the FULL dotnet + vitest suites (not --list); no orphan stack created; pipeline log shows all 8 stages executed and gating. | New feature | 16 | Developer (test/G10); CEO (trust); Gate G10, G9; Goal 6 [MANDATED]
P4-T22 | Fix migration latent + make seed deterministic | Phase 4 | Hardening | Database | Migrations / seed | very important | Backend/database/scripts/700_*_role.sql (and siblings) targets a database named plantprocessiq that does not exist - the real DB is plantprocess_app_db; under ON_ERROR_STOP=1 this fails the build, so fix the target. Audit ALL numbered scripts for hardcoded DB names, ensure idempotency (re-run twice with no error), and make the seed deterministic + re-runnable (upserts, not blind inserts) so a redeploy never duplicates demo rows. | Applying scripts/*.sql then seed/*.sql TWICE against a fresh DB yields identical row counts and zero errors under ON_ERROR_STOP=1; the 700 role script runs clean against plantprocess_app_db; a grep finds no hardcoded wrong DB names. | Bug fix | 8 | Developer (stability); CEO (trust); Gate G2, G9
P4-T23 | Health, readiness & restore-drill runbook (clean-machine bring-up) | Phase 4 | Hardening | Infrastructure | Ops | important | Per gate G9, prove a clean machine reaches a working login by runbook only and that a backup restores. Document the bring-up (compose + .env + migrate + seed) in deploy/RUNBOOK.md, ensure /health + a NEW /ready endpoint reflect DB + migration state, and verify ppiq-backup-runner produces a restorable dump (restore into a scratch DB and validate row counts). | Following RUNBOOK.md on a fresh VM reaches a working login; /ready returns 200 ONLY when migrations are applied (returns 503 otherwise); a backup is taken and restored into a scratch DB with matching row counts (documented with the commands + output). | Hardening | 10 | CEO (trust posture); Gate G9; Wave D
P4-T24 | Phase 4 acceptance: green pipeline + clean-machine deploy proof | Phase 4 | Deploy | Testing | Phase gate | very important | Execute the rebuilt pipeline end-to-end on the server and capture evidence: a successful push updates the live stack (version stamp matches); a broken unit test and a broken migration each fail the pipeline at the right stage; the clean-machine runbook reaches login. Confirm no app regression after recreate-in-place. | Pipeline artifacts show migrate+seed+lint+npm test+dotnet test all executed AND gating; live demo reflects the new commit (stamp match); orphan check passes (0 plantprocess-*); smoke gate green; rollback (deploy/rollback.sh from P1-T01) still works against the converged stack. | Test | 8 | Developer (G10); CEO (trust); Gate G9, G10
PHASE 5 - Demo-through-HMI & guided narrative ¦ Week 2 - customer ¦ ends deployable: Demo built from empty through the product; nothing hardcoded; on-rails guided tour
P5-T25 | Remove hardcoded demo/analytics pages; serve demo via DynamicPage only | Phase 5 | Demo | FrontEnd | Golden Rule | Critical | A no-hardcoded-demo guard exists (T-041, verify-no-hardcoded-demo-pages.mjs, DENY pages/DemoAnalytics + pages/DemoLifecycle), yet hardcoded modules still live in src/ (DemoAnalyticsPages.implementation.tsx 461, plantProcessDemoScenario.implementation.ts 899, MaterialAnalyticsPages.runtime.generated.tsx 1107). Migrate any demo content they provide into PageDefinitions authored THROUGH the page-builder and rendered by DynamicPage at /pages/:slug; delete the hardcoded modules + their routes; make the T-041 guard BLOCKING. | `node scripts/verify-no-hardcoded-demo-pages.mjs` passes and is a hard gate; the demo analytics/lifecycle pages render from PageDefinition via the dynamic slug route; deleting the modules leaves the demo intact; build + tests green; zero console errors on the migrated pages. | Refactor | 10 | Eng Customer (workflow); Developer (structure); Gate G3, G7; Track 3
P5-T26 | Build the full demo from empty ENTIRELY through the HMI (recorded dry run) | Phase 5 | Demo | Web | Demo-through-HMI | Critical | Per the Golden Rule the demo must be created from empty through the product: connect the 8 sources (DB-link config), define import jobs + rates, write the mapping/join SQL views into the canonical model, build pages in the page-builder, configure widgets/charts (incl. the widget script layer), schedule the ML/correlation jobs, and view dashboards - with NOTHING hardcoded. Produce a scripted, recorded dry-run plus a checklist others can follow. | A recorded clean dry-run exists showing the full demo built through the HMI only; a fresh DB + the dry-run reproduces the demo; the T-041 guard is green during the run; ZERO console errors across the full build; every page that results is a PageDefinition (no code page). | New feature | 16 | Eng Customer (feature depth); Gate G3, G7; Track 1/3; North Star
P5-T27 | Scale & realism of the eight-source demo dataset | Phase 5 | Demo | Database | Demo data | very important | Per Track 3 the dataset should be ~1 month of realistic flat-steel production: ~630 heats, ~5,600 slabs/coils, with deliberate imperfection (gaps, late samples, mixed-heat/transition coils, downtime-vs-production-stop distinction). Extend the Infrastructure/demo-sources init data (MeltShop PG, Caster/HSM Oracle, PKL MSSQL, Downtime/Parsytec MySQL, Yard/QA Excel) to that scale with genealogy that resolves both directions, and verify cross-source joins on the customer's keys. | The seeded demo contains >=630 heats and >=5,600 coils across the 8 sources; a coil resolves full genealogy BOTH directions; a known transition coil reports weighted/blended attribution (5.3); the data-coverage panel shows realistic gaps; a planted true driver is recoverable by the correlation job (ties P1-T05 to real data). | Modification | 12 | Eng Customer (feature depth); Gate G7, G15; Track 3
P5-T28 | One-click demo reset/rebuild + readiness check | Phase 5 | Demo | Backend | Reset job | important | Provide a governed reset job that returns the demo to a known clean state and a one-click readiness check verifying: sources connected, mappings valid, jobs scheduled, dashboards populated, no dead widgets, no console errors, version stamp current - so the demo can be re-armed before a customer session. | The reset job restores the clean demo state idempotently; the readiness check passes GREEN on a correctly built demo and fails with a SPECIFIC reason (which step) when anything is missing; running it twice is stable. | New feature | 8 | Eng Customer (workflow); Gate G7; Goal 4; Track 3
P5-T29 | [NEW] Guided golden-path demo mode + presenter script | Phase 5 | Demo | FrontEnd | Guided tour / demo narrative | important | De-risk the live presentation with a known-good rail. Build a lightweight guided demo mode: a scripted golden-path tour (source connected -> mapping -> page built -> widget -> correlation finding -> genealogy -> bounded value -> report) with optional step highlights/tooltips, plus a one-page presenter script (talking points + the exact clicks) that follows ONLY verified-working paths and avoids any half-finished corner. Keeps the demo impressive and on-rails so you never improvise into a broken view. | The guided tour runs the full golden path end-to-end on the seeded demo with NO dead step; a presenter completes the scripted flow in <10 min with zero console errors and no failed load; the script is checked in (docs/demo-script.md) and matches the live build; the tour is feature-flagged so it can be hidden in production. | New feature | 6 | Goal 4 (no surprises) & 5 (impressive); Eng Customer
P5-T30 | Phase 5 acceptance: Golden-Rule dry-run + genealogy + coverage proof | Phase 5 | Demo | Testing | Phase gate | very important | Acceptance suite proving the demo is HMI-built and honest: T-041 guard green, readiness check green, guided golden-path passes, a genealogy walk both directions on a real coil, blended attribution on a transition coil, coverage/exclusions surfaced. Full regression of e2e. | All of the above pass; recorded dry-run archived; no hardcoded demo page; guided tour completes clean; e2e green; deploy via the rebuilt pipeline shows the demo working on the server. | Test | 8 | Eng Customer (feature depth); Gate G3, G7, G15
PHASE 6 - Website, evaluation surface, a11y & presentation readiness ¦ Week 2 - customer ¦ ends deployable: Shiny site + honest customer evaluation; AA light/RTL; rehearsed go/no-go + rollback
P6-T31 | Website polish to brand-true, honesty-linted sales surface | Phase 6 | Web | Web | Marketing site | very important | Bring the website (PlantProcess.Website) to a shiny, brand-true state per Track 4: complete the 5-product ecosystem cards (PPIQ + MES/QES/Yard/Energy as 'core + packs' per Doctrine 15.1), the pricing/license matrix (Light/Pro/Pro Plus/Enterprise), proof sections (ProductScreenshotShowcase, ConnectorHonesty, PositioningTruth), the dark-industrial visual system and interactive graphics, responsive down to mobile. Keep the honesty-lint (forbidden-copy) BLOCKING - no 'guaranteed root cause / AI prediction / live Oracle today'. | Honesty-lint passes and is a hard gate; all 5 products render with description/benefit/license/proof; the brand audit matches the palette+typography spec; Lighthouse >=90 performance + SEO + a11y on the landing page; renders cleanly on a phone; zero console errors. | Modification | 12 | Brand (website 68->~80); Gate G8; Track 4
P6-T32 | Customer-facing capability & evaluation surface (honest self-assessment) | Phase 6 | Web | Web | Proof / evaluation | very important | The customer asked to see 'our evaluation of the software'. Build an honest, presentable capability-and-evidence surface (web page or in-app 'About this build' panel) showing doctrine-gate conformance as a CAPABILITY MATRIX (GA vs in-pilot), the honesty contract, connector availability per source, and proof artifacts (a genealogy walk, an FDR-controlled finding, the bounded value range) - framed in APPROVED language, NOT the brutal internal scorecard. This is the customer-safe analogue of the internal scorecard; it must never show red/critical wording. | The surface renders a capability matrix with honest statuses, links to LIVE proof (genealogy, finding, value range), and passes the forbidden-copy lint; a review confirms no overclaim and no internal red/yellow language leaked; works on mobile; zero console errors. | New feature | 12 | Brand (website); CEO (trust, value=price); Gate G8; Goal 1/5; Track 4
P6-T33 | Lead capture -> delivery integration + CTA proof | Phase 6 | Web | Web | Lead capture | important | Make the RequestDemoForm actually deliver: wire submission to email/webhook (the doctrine's outbound message path - never a setpoint), validate + store the lead, send a confirmation, and prove the CTA captures end-to-end. Per gate G8 'CTA captures a lead'. | An e2e submits the form and asserts a lead is stored + a notification/webhook fires; validation rejects bad input with clear inline errors; no PII leaks client-side; a confirmation is sent. | New feature | 8 | Brand (website); Gate G8; Track 4
P6-T34 | WCAG-AA light theme + Arabic RTL (close the G14 gate) | Phase 6 | Hardening | FrontEnd | Accessibility / i18n | very important | G14 is a RED gate. Deliver a contrast-audited WCAG-2.1-AA light theme (the doctrine's light-mode report/print surface extended to the app shell) and complete the Arabic RTL pass (the 610 i18n/RTL scaffolding + src/i18n) with locale/units/timezone switching per user. Both dark and light themes must pass contrast; no clipped/mirrored-wrong layout in RTL. | axe/a11y audit passes AA on BOTH themes (0 serious/critical violations); Arabic renders RTL with correctly mirrored layout; units/timezone switch per user; a visual spec covers light + RTL; keyboard navigation works in both directions. | Hardening | 14 | CEO (cross-device/perf 56->~70); Gate G14; Wave D
P6-T35 | Cross-browser + a11y wired blocking in the pipeline | Phase 6 | Testing | Testing | Cross-browser gate | very important | Widen Playwright beyond chromium to Firefox + WebKit and wire a11y + cross-browser + visual + auth-matrix as BLOCKING stages in the rebuilt pipeline (Phase 4 made it gating). Fix any browser-specific breakage found. | e2e + a11y pass on chromium/firefox/webkit AND gate the pipeline (a deliberate break fails it); no browser-specific layout/console errors; visual snapshots stable across engines. | Test | 12 | CEO (cross-device); Brand; Gate G6, G8, G14
P6-T36 | [NEW] Presentation-day go/no-go + rollback rehearsal + offline fallback | Phase 6 | Hardening | Deploy | Presentation readiness | Critical | The final insurance before the customer session. Run a go/no-go checklist on the EXACT deployed stack (not localhost): readiness check green (P5-T28), guided golden-path passes (P5-T29), zero console errors across the demo, version stamp == intended commit, rollback rehearsed (P1-T01 script), known-good image pinned. Prepare an offline fallback: a recorded screen-capture of the full golden path + a short screenshot deck, so a network/server hiccup never becomes a dead demo. FREEZE the demo dataset snapshot so nothing changes between rehearsal and the live session. | The go/no-go checklist passes on the deployed stack within 24h of the session; the recorded fallback walkthrough exists and is current; the dataset is snapshotted/frozen and the readiness check is green against it; a deliberate 'kill the API' drill recovers via rollback in <2 min; sign-off recorded in docs/go-no-go.md. | Test | 6 | Goal 4 (no surprises, hard); CEO (trust); Gate G9
| TOTAL EFFORT (h) | [8 empty] | 373 | 36 tasks (5 NEW) - solo-founder 2-week sprint envelope

## Phase Summary
Phase | Focus | Tasks | Effort (h) | 45-65h? | Deploy milestone | Primary score lift | Window
Phase 1 | Stabilize live + structural honesty + test reality | 7 | 63 | OK | Server shows latest build (stamped) + rollback ready; repo no longer shamming; tests run & gate locally | Developer 62->~71; unblocks deploy-each-phase (NEW P1-T01) | Week 1 - team-lead
Phase 2 | UI standardization + flagship visual uplift | 6 | 65 | OK | Every page same standard look, no dead buttons, no failed loads, 3 flagship screens look impressive | Eng Customer UI/UX 64->~78; app starts looking shiny (NEW P2-T12) | Week 1 - team-lead
Phase 3 | Intelligence, value & demo performance | 6 | 65 | OK | Bounded EUR value, honest correlations + citations, snappy no-hang endpoints | CEO value 56->~70 + trust 80->85; AI/ML ->~80 (NEW P3-T18) | Week 1 - team-lead
Phase 4 | Deploy convergence & pipeline rebuild | 5 | 56 | OK | A git push genuinely updates the live demo (stamp match); tests gate the deploy | Gate G9/G10; root cause of FE/BE-not-updating SOLVED [MANDATED] | Week 2 - customer
Phase 5 | Demo-through-HMI & guided narrative | 6 | 60 | OK | Demo built from empty through the product; nothing hardcoded; on-rails guided tour | Gate G3/G7; Wave C 55->~85; no-surprise demo (NEW P5-T29) | Week 2 - customer
Phase 6 | Website, evaluation surface, a11y & presentation readiness | 6 | 64 | OK | Shiny site + honest customer evaluation; AA light/RTL; rehearsed go/no-go + rollback | Brand 72->~80; CEO cross-device 56->~70; Gate G8/G14 (NEW P6-T36) | Week 2 - customer
| TOTAL | 36 | 373
Each phase ends independently deployable (P1-T01 makes Week-1 server deploys possible). Effort is a prioritized budget - flex within a phase as long as it still ends green.